## Report Data
|  | Sl. No | Site Id | Site Name | Candidate Id | Candidate Name | Territorial Authority | Team | Tier Identifier | Candidate Status | Property Type | Site Type | Structure Type | Cabinet Colour | Cabinet Layout | Co Status | Antenna Height (Top of panel) | Structure Height (Top of lightning spike) | RF Rank | Latitude | Longitude | Target Date RF Issue Search Brief | Date RF Issue Search Brief | Target Date TX Plan Issued | Date TX Plan Issued | Link Types | Links To | Site Search Instruction Pack Issued | Initial Council Presentation Complete | Target Date Site Search Complete | Date Site Search Complete | Acquisition arranged access to candidates | TX Confirmed LOS | Target Date Of Caravan | Date Of Caravan | Target Date Work Order 1 Issued | Date Work Order 1 Issued | Target Date Planning Drawing Rev1 Issued | Date Planning Drawing Rev1 Issued | PD Version | Target Date Planning Drawing Complete | Date Planning Drawing Complete | Target Date Lease Terms Agreed | Date Lease Terms Agreed | Target Date Lease Executed | Date Lease Executed | PD Version Used for Lease | Target Date All Site Acquisition Complete | Date All Site Acquisition Complete | RMA Activity Status | Target Date RMA Lodged | Date RMA Lodged | Target Date RMA Approved | Date RMA Approved | PD Version Used for TP | Target Date All Town Planning Complete | Date All Town Planning Complete | Target Date Construction Drawing Instruction Issued | Date Construction Drawing Instruction Issued | Target Date Construction Drawing Rev1 Issued | Date Construction Drawing Rev1 Issued | CD Version | PD Version used for CD | Target Date Construction Drawing Complete | Date Construction Drawing Complete | Date Pole Available | Target Date PM Approve CDs | Date PM Approve CDs | Date TCF Letter Sent | Date All Build Approvals Obtained | Target Civil Works Start Date | Civil Works Start Date | Target Date Civil Construction Complete | Date Civil Construction Complete | Date Equipment Delivered to Site | Target Date TI Complete | Date TI Complete | Target Date Transmission - Backhaul RFS | Date Transmission - Backhaul RFS | Target Date All TX Licenses Obtained | Date All TX Licenses Obtained | Target Date All RF Licenses Obtained | Date All RF Licenses Obtained | Target Date Final TX&RF Spec | Date Final TX&RF Spec | Date Integration Complete | Target Date Site On Air Complete | Date Site On Air Complete | Target Date PAC Signed | Date PAC Signed | Target Date FAC Signed | Date FAC Signed | Project Management Comments | Co-operator | Target Date Integration Complete | Target [MS12] BOQ - Ordered | [MS12] BOQ - Ordered | Target [MS16] BOQ - At RDP and Complete | [MS16] BOQ - At RDP and Complete | Target [MS17] Date Steelwork - At RDP and Complete | [MS17] Date Steelwork - At RDP and Complete | Target [MS23] AC - Power ON | [MS23] AC - Power ON | Target Date Integrated with Volume 4 | Date Integrated with Volume 4 | Date SSLU Analysis Completed | SSLU Risk | Cluster | Target Date Fiber Delivered to Site | Date Fiber Delivered to Site | Build Status | Target Date Equipment Delivered to Site | TCF Letter Required | Target Date TCF Letter Sent | Easting | Northing | Physical Address | Acquisition comments | Town planning comments | Network type | Financial status | Date L700 On Air | Date L1800 On Air | Programme | Decommission date | Date Pole Ordered | Date Equipment Ordered | Target Date Tender Instruction | Date Tender Instruction | Target Date Fibre Feasibility Requested | Date Fibre Feasibility Requested | Target Date New Connect Order Placed | Date New Connect Order Placed | Target Date PO6 Issued | Date PO6 Issued | Target [MS30] PAC/PAD - Submitted TO 2 DEG | [MS30] PAC/PAD - Submitted TO 2 DEG | Date Planning Drawing Instruction Issued
0 | AKL | 1 | AKL-004-001 | Woodhill |  |  | Rodney District |  | TIER_1_ALL
0 | AKL | 2 | AKL-004-002 | Kumeu | AKL-004-002-A | Kumeu | Rodney District |  | TIER_1_ALL | ACTIVE | COLO | A | COLO | grey |  |  |  | 40 |  | -36.7765 | 174.5589 |  |  |  |  | Fibre Optic | AKL-007-185-A | [11 empty] | 2007-12-07 | 6 |  |  |  |  | 2009-04-14 | 2009-04-14 | 4 | 2009-04-14 | 2009-04-14 |  |  |  | 2008-05-01 |  |  | 2008-05-01 | 2008-05-01 |  | 2008-03-06 |  | 2008-07-02 | 4 | 5 | 2008-10-10 | 2008-10-10 | [5 empty] | 2009-03-09 | 2009-03-09 | 2009-03-27 | 2009-03-27 |  | 2009-04-21 | 2009-04-21 | [8 empty] | 2009-04-30 | 2009-04-30 | 2009-04-30 |  |  |  |  | Site rental negotiation updated. Co-lo application form needs to be submitted by AP. MB to submit project plan then will get licence. Awating confirmation from Telecom if LL is delivered. (JL 27/4) |  | 2009-04-30 | [17 empty] | FALSE |  | 2649566 | 6490524 | SH2 Kumeu Auckland |  |  | CELLSITE | [8 empty] | 2009-02-24 | [8 empty] | 2007-12-13
0 | AKL | 3 | AKL-004-003 |  | AKL-004-003-E | Riverhead | Rodney District | 3 | TIER_1_ALL | ACTIVE | GF | A | P7 | grey |  |  | 25 | 25 |  | -36.7427 | 174.6136 |  |  |  |  | Leased Line | AKL-007-106-A | FALSE | FALSE |  |  | FALSE |  |  | 2008-10-01 |  |  |  | 2008-10-23 | 4 | 2009-01-16 | 2009-01-16 |  |  |  | 2008-11-14 | 1 |  | 2008-11-14 |  | 2009-01-21 |  | 2009-03-31 |  |  | 2009-03-31 | 2009-02-12 | 2008-11-05 | 2008-12-03 |  | 2008-12-05 | 1 | 3 | 2008-12-05 | 2008-12-05 | 2009-04-17 |  |  |  |  | 2009-04-06 | 2009-04-06 | 2009-05-22 | 2009-05-22 |  | 2009-06-12 | 2009-06-11 | [8 empty] | 2009-06-11 | 2009-06-17 | 2009-06-11 |  |  |  |  | On Air Riverhead Township link. REQUIRE 300mmØ |  | 2009-06-17 |  |  |  |  | 2009-04-17 | 2009-04-17 | [11 empty] | FALSE |  | 2654516 | 6494179 | 43 Mill Flat Rd, Riverhead |  |  | CELLSITE | [7 empty] | 2009-04-03 | 2009-04-03 | [8 empty] | 2008-09-30
0 | AKL | 4 | AKL-004-005 |  | AKL-004-005-D | Redvale | Rodney District |  | TIER_1_ALL | ACTIVE | GF | A | P3 | grey |  |  | 20 | 20 |  | -36.6851 | 174.7014 |  |  |  |  | Leased Line | AKL-007-106-A | [11 empty] | 2008-09-12 | 4 | 2009-02-27 | 2009-02-25 |  |  |  | 2008-10-14 | 4 | 2009-02-18 | 2009-02-18 |  |  |  | 2009-03-27 |  |  | 2009-03-27 | 2009-03-31 |  | 2008-11-03 |  | 2008-11-28 | 2 | 3 | 2009-03-03 | 2009-03-03 | 2009-01-30 |  |  |  |  | 2009-04-06 | 2009-04-07 | 2009-04-28 | 2009-04-28 |  | 2009-05-08 | 2009-04-28 | [8 empty] | 2009-06-23 | 2009-06-19 | 2009-06-23 |  |  |  |  | On Air |  | 2009-06-19 | [5 empty] | 2009-01-30 | [11 empty] | FALSE |  | 2662484 | 6500418 | 1370 East Coast Bay Rd, Redvale, Auckland |  |  | CELLSITE | [7 empty] | 2009-04-06 | 2009-04-06 | [8 empty] | 2008-08-19
0 | AKL | 5 | AKL-004-006 |  | AKL-004-006-C | Muriwai | Rodney District |  | TIER_1_ALL | ACTIVE | GF | Ab | P3 | grey |  |  | 16.5 | 16.5 |  | -36.8154 | 174.431 |  |  |  |  | Leased Line | AKL-007-106-A | [11 empty] | 2008-09-10 | 4 | 2009-04-14 | 2009-04-14 |  |  | 2009-09-02 | 2009-09-04 | 3 | 2009-11-30 |  |  |  |  | 2008-12-19 |  |  | 2008-12-03 | 2008-12-03 | 2009-04-02 | 2009-04-01 |  | 2009-04-22 | 2 | 4 | 2009-04-30 | 2009-04-27 | 2009-05-25 |  |  |  |  | 2009-09-07 | 2009-09-07 | 2009-09-30 | 2009-09-30 |  | 2009-10-09 | 2009-10-02 | [8 empty] | 2009-11-09 | 2009-11-06 | 2009-11-09 |  |  |  |  | CO-SITES APPROVED. New access track installed. Pole modified for larger headframe. Iwi wants to approve agreement. Early Access granted. Iwi meeting Tuesday 8/9 & Mana confirmed they're ok with our site. Delays with power as SFA required from VF & TNZ for power supply sharing. LL once power on. VF approval for SFA received, and TNZ now too. SFA to be completed for power share/connection. |  | 2009-11-06 |  |  |  |  | 2009-05-22 | 2009-05-25 | [11 empty] | FALSE |  | 2638075 | 6486408 | Grass Track Rd Muriwai |  |  | CELLSITE | [7 empty] | 2009-09-07 | 2009-09-07 | [8 empty] | 2008-08-15
0 | AKL | 6 | AKL-004-007 | Waimauku | AKL-004-007-B | Waimauku Greenfield | Rodney District | 23 | TIER_4 | ACTIVE | GF | DF | T2 20 RH | Grey | STACK_A | COSITE |  |  |  | -36.7776 | 174.496 |  |  |  |  | Microwave | AKL-004-006-C | FALSE | FALSE |  |  | FALSE |  | 2015-03-13 | 2015-03-03 | 2015-03-17 | 2015-03-11 | 2015-04-24 | 2015-05-04 | 1 | 2015-05-01 | 2015-05-04 | 2015-05-29 | 2015-05-27 | 2015-06-26 | 2015-06-25 |  | 2015-07-03 | 2015-06-30 | PERMITTED | 2015-06-01 | 2015-05-26 | 2015-06-30 | 2015-06-24 | 1 | 2015-06-30 | 2015-06-24 | 2015-06-17 | 2015-06-16 | 2015-07-24 | 2015-08-10 | 1 |  | 2015-07-31 | 2015-08-10 | [5 empty] | 2015-09-14 | 2015-09-15 | 2015-10-30 | 2015-11-04 | 2015-11-04 | 2015-10-23 | [10 empty] | 2015-11-17 | 2015-11-17 |  | 2015-11-27 |  | 2015-11-27 | 25/05/15 - Co site application lodged with Spark 11/06/15 - Co-site approval from Spark 22/09/15 - GHD wanted additional excavations. Steve to advise when CR required for Muriwai for link install 17 -30 Oct 19/10/15 - CR47637 for Muriwai access 16-06 Nov. CR 47633 integration to 6/11 10/11/15 - 24hr BER test deliver 12/11 and go to air that night hopefully 12/11/15 - BER started late and will not finish in time to go to air | [10 empty] | 2015-11-09 | 2015-11-05 | [5 empty] | BUILD | 2015-10-02 | TRUE |  | 2643946 | 6490497 | Waimauku Greenfield Pollard Lane Waimauku Auckland | Pollard Lane Waimauku - 07/05/2015 | Now permitted activity as mast was kept under height - 27/05/2015 | CELLSITE |  |  |  | ROAMING |  | 2015-08-03 | 2015-07-01 | 2015-07-31 | 2015-08-02 |  |  |  |  | 2015-09-04 | 2015-09-03 |  |  | 2015-03-11
0 | AKL | 7 | AKL-004-009 | Red Beach | AKL-004-009-D | Red Beach | Rodney District | 3 | TIER_3 | ACTIVE | RT | DF | RT |  | INLINE | COSITE | 8 | 5.5 |  | -36.6033 | 174.6926 |  | 2011-12-19 |  |  | Microwave | AKL-004-041-B | FALSE | FALSE |  |  | FALSE |  | 2012-05-17 | 2012-05-17 | 2012-05-23 | 2012-05-23 | 2012-07-10 | 2012-07-16 | 2 | 2012-07-16 | 2012-12-17 |  | 2012-06-19 | 2012-10-05 | 2012-09-28 |  | 2012-10-05 | 2012-10-04 | DISCRETIONARY_FULL | 2012-08-08 | 2013-01-24 | 2013-04-09 | 2013-04-08 | 2 | 2012-09-05 | 2012-09-05 | 2012-09-03 | 2012-09-03 | 2012-10-25 | 2012-11-01 | 1 |  | 2012-10-25 | 2012-11-01 | 2012-11-12 |  |  | 2012-10-01 |  | 2012-11-05 | 2012-11-05 | 2012-12-07 | 2012-12-07 | 2012-11-27 | 2013-01-29 | 2013-01-29 | [8 empty] | 2013-01-29 | 2013-02-12 | 2013-02-14 | 2013-02-15 | 2013-02-15 | 2013-08-30 | 2013-10-11 |  |  | 2013-01-29 | 2012-11-05 | 2012-11-05 | 2012-11-05 | 2012-11-12 | 2012-11-12 | 2012-11-12 | 2012-11-30 | 2012-11-30 | 2013-01-31 | 2013-01-31 |  |  | OREWA |  |  | BUILD | 2012-11-28 | TRUE | 2012-10-08 | 2661876 | 6509518 | Thai'ed Up Building 178 Hibiscus Coast Highway Red Beach |  | Approved by council on 5.9.12 with rev 1 plans. - 05/09/2012 Retrospective application Council Ref: LAN-59712 - 05/02/2013 | CELLSITE | [15 empty] | 2013-01-31 | 2013-02-07
0 | AKL | 8 | AKL-004-010 | Whangaparaoa | AKL-004-010-B | Whangaparaoa LPR | Rodney District | 3 | TIER_3 | ACTIVE | RSR | DU | P4C |  | INLINE | STANDALONE | 11 | 11.5 |  | -36.6252 | 174.7446 |  | 2012-06-01 |  |  | Microwave | AKL-004-043-D | FALSE | FALSE |  |  | FALSE |  | 2012-08-22 | 2012-08-22 | 2012-08-23 | 2012-08-29 | 2012-10-15 | 2012-10-05 | 5 | 2012-10-15 | 2013-04-24 | 2012-10-30 | 2012-10-31 | 2012-11-15 | 2012-11-14 |  | 2012-11-22 | 2012-11-14 | NES | 2012-11-12 | 2013-04-15 | 2013-05-06 | 2013-05-07 | 5 | 2012-12-10 | 2012-12-10 |  |  | 2013-01-24 | 2013-01-24 | 2 |  | 2013-01-24 | 2013-07-09 |  |  |  | 2013-02-13 |  | 2013-04-02 | 2013-04-02 | 2013-05-24 | 2013-05-27 | 2013-05-27 | 2013-06-24 | 2013-06-24 | [8 empty] | 2013-06-24 | 2013-07-05 | 2013-06-27 | 2013-07-04 | 2013-06-28 | 2013-09-27 | 2013-09-27 |  |  | 2013-06-18 | [6 empty] | 2013-06-21 | 2013-06-12 | 2013-06-27 | 2013-06-24 |  |  | TIER_1_INFILL |  |  | BUILD | 2013-05-27 | TRUE | 2013-03-01 | 2666478 | 6506987 | 142 Stanmore Bay Road Whangaparaoa |  |  | CELLSITE | [15 empty] | 2013-06-25
0 | AKL | 9 | AKL-004-011 |  |  |  | Rodney District |  | TIER_9
0 | AKL | 10 | AKL-004-013 | Gulf Harbour | AKL-004-013-A | Gulf Harbour | Rodney District | 3 | TIER_3 | ACTIVE | RT | DF | RT |  | STACK_A | COSITE |  |  |  | -36.6171 | 174.797 |  | 2012-05-29 |  |  | Fibre Optic | AKL-005-078-A | FALSE | FALSE |  |  | FALSE |  | 2012-07-10 | 2012-07-10 | 2012-07-17 | 2012-07-19 | 2012-09-11 | 2012-09-04 | 2 | 2012-09-11 | 2012-10-11 | 2012-11-08 | 2012-11-09 | 2012-11-30 | 2012-11-13 |  | 2013-04-19 |  | CONTROLLED | 2012-11-12 | 2012-11-12 | 2012-12-24 | 2012-12-10 | 2 | 2012-12-27 | 2012-12-10 | 2013-02-08 |  | 2013-03-27 | 2013-03-27 | 1 |  | 2013-03-27 | 2013-03-27 | [5 empty] | 2013-05-27 | 2013-05-27 | 2013-06-24 | 2013-06-25 | 2013-06-27 | 2013-07-22 | 2013-07-30 | 2013-07-16 | 2013-07-22 | [6 empty] | 2013-07-30 | 2013-07-31 | 2013-08-30 | 2013-08-19 | 2013-08-15 | 2013-11-17 | 2013-11-15 | No letters required. TNZ has leased whole clock tower. co locataion application is in. 9 Nov 2012 TNZ prelim approval received. 27/11/2012 Golf Club board meeting is on 04/12/12. Colocation is on agenda. Require their approval. 14.01.2013 Chairman says agreed, now await their documentation. 24.01.2013 Club have come back sayiong they will give approval on condition we pay annual rental - this is being dsicussed with TNZ and Site Aqu dept. 26/02/13 - CD's urgently required - due 01 March |  | 2013-07-22 | [6 empty] | 2013-07-01 | 2013-07-01 | 2013-07-25 | 2013-07-25 |  |  | TIER_1_INFILL | 2013-07-01 | 2013-07-08 | BUILD | 2013-06-27 | FALSE |  | 2671185 | 6507795 | Gulf Harbour Country Club Gulf Harbour Road Gulf Harbour Whangaparaoa |  |  | CELLSITE | [15 empty] | 2013-07-31
0 | AKL | 11 | AKL-004-014 | Omaha | AKL-004-014-B | Omaha - Hubbard Farm GF | Rodney District | 23 | TIER_4 | ACTIVE | GF | DF | T2 20 RH |  | INLINE | COSITE |  |  |  | -36.3596 | 174.7988 |  | 2015-02-17 |  |  | Fibre Optic | AKL-005-088-A | FALSE | FALSE |  |  | FALSE |  | 2015-04-13 | 2015-03-03 | 2015-04-16 | 2015-03-26 | 2015-05-07 | 2015-05-08 | 1 | 2015-05-11 | 2015-05-08 | 2015-07-17 | 2015-07-10 | 2015-07-30 | 2015-07-27 |  | 2015-07-31 | 2015-07-27 | NON_COMPLYING_FULL | 2015-07-24 | 2015-07-21 | 2015-10-06 | 2015-09-16 | 1 | 2015-10-09 | 2015-09-16 | 2015-07-03 | 2015-06-16 | 2015-09-18 | 2015-09-15 | 1 |  | 2015-09-18 | 2015-09-15 | [5 empty] | 2015-10-19 | 2015-10-19 | 2015-11-27 | 2015-11-30 |  |  |  | 2015-12-10 | 2015-11-24 | [7 empty] | 2015-12-14 | 2015-12-13 |  |  |  |  | 04/11/15 - Fibre date advised as 10 Dec - trying to improve on. Power transformer being data logged. Easement issues should be resolved with docs exchanged with Vector 7/12/15 - Vol4 received and in circulation | TNZ | [9 empty] | 2015-12-04 | 2015-12-07 | 2015-02-24 | MEDIUM |  | 2015-12-10 | 2015-11-24 | BUILD |  | TRUE |  | 2671939 | 6536353 | Hubbard Farm Takatu Road Omaha |  |  | CELLSITE |  |  |  | ROAMING |  | 2015-08-03 | 2015-10-12 | 2015-09-11 | 2015-09-14 | 2015-04-23 | 2015-04-23 | 2015-06-01 |  | 2015-10-13 | 2015-10-16 |  |  | 2015-03-26
0 | AKL | 12 | AKL-004-015 | Leigh | AKL-004-015-E | Leigh - 242 Rodney Road GF | Rodney District | 23 | TIER_4 | ACTIVE | GF | DF | T2 20 RH |  | STACK_A |  |  |  |  | -36.2901 | 174.7614 |  | 2011-12-19 |  |  | Microwave | AKL-004-014-B | FALSE | FALSE |  |  | FALSE |  | 2015-07-03 | 2015-07-01 | 2015-07-06 | 2015-07-01 | 2015-08-28 | 2015-07-30 | 2 | 2015-09-04 | 2015-09-22 | 2015-08-21 | 2015-08-25 | 2015-09-18 | 2015-09-17 |  | 2015-09-21 | 2015-09-21 | PERMITTED | 2015-08-28 | 2015-09-01 | 2015-10-09 | 2015-10-08 | 1 | 2015-10-12 | 2015-10-08 | 2015-08-24 | 2015-08-24 | 2015-10-09 | 2015-10-13 | 1 |  | 2015-10-09 | 2015-10-13 | [5 empty] | 2015-11-02 | 2015-11-02 | 2015-12-17 | 2015-12-17 | [12 empty] | 2015-12-23 | 2015-12-21 |  |  |  |  | 19/10/15 - CD's issued, pricing expected 20/10 04/11/15 - Construction started. - on air date dependent on Omaha Fibre (trying to improve on 10 Dec delivery) 30/11/15 - Pole up 1 Dec, Link in 3 Dec, BER and comp by 9 Dec 2/12/15 - Power co unable to install HV transformer until new year!!! 20 day notice required to residents, which they did not do in time 7/12/15 - Vector agreed to allow TX to be put in 17 Dec (21 backup). Connection form lodged. Integrate on Generator. | [10 empty] | 2015-12-18 | 2015-12-15 |  |  | AUCKLAND_WHANGAREI |  |  | BUILD |  | TRUE |  | 2668742 | 6544138 | 242 Rodney Road Leigh |  | May prove to be non-complying depending on final interpretation of Council - 01/09/2015 | CELLSITE |  |  |  | ROAMING |  | 2015-09-24 | 2015-10-12 | 2015-10-09 | 2015-09-21 |  |  |  |  | 2015-10-30 | 2015-10-29 |  |  | 2015-07-01
0 | AKL | 13 | AKL-004-016 | Kraacks Hill | AKL-004-016-B | Kraaks Hill Greenfield Matariki | Rodney District | 23 | TIER_4 | ACTIVE | GF | DU | T2 20 RF | Grey | INLINE | COSITE | 20 | 20 |  | -36.3732 | 174.6106 |  |  |  |  | Microwave, Microwave | AKL-004-017-D, AKL-004-014-B | FALSE | FALSE |  |  | FALSE |  | 2012-07-26 | 2012-07-26 | 2012-08-07 | 2012-08-07 | 2012-10-10 | 2012-10-09 | 2 | 2012-10-10 | 2015-05-05 | 2015-05-29 | 2015-04-28 | 2015-07-07 | 2015-06-30 |  | 2015-07-14 | 2015-06-30 | DISCRETIONARY_FULL | 2012-11-29 | 2012-11-27 | 2013-02-07 | 2013-01-16 | 1 | 2013-02-05 | 2013-01-17 | 2015-05-08 | 2015-04-29 | 2015-06-26 | 2015-07-01 | 1 |  | 2015-06-26 | 2015-07-01 | [5 empty] | 2015-09-04 | 2015-09-04 | 2015-12-09 | 2015-12-09 | 2015-10-02 | 2015-10-23 | 2015-10-23 | [9 empty] | 2015-12-15 | 2015-12-15 |  |  |  |  | 20/10/15 - Link in this week. Still need power 04/11/15 - Desperately trying to get easement issues resolved Vector/ Matariki 10/11/15 - signed docs with Vector. Pressing for power 30/11/15 - Transformer upgraded, Vector to connect power (trying for 4 Dec) 07/11/15 - Power likely 08 Dec, 24hr BER wed, Vol4 final Thurs/Frid. Try for rapid sign-off for SOA Monday |  | 2015-10-09 | [8 empty] | 2015-11-30 | 2015-11-03 |  |  | AUCKLAND_WHANGAREI |  |  | BUILD | 2015-10-02 | FALSE |  | 2655025 | 6535187 | Grimmer Road SH1, Kraaks Hill Dome Forest |  | lodged with council on the 27.11.12 - 27/11/2012 | CELLSITE |  |  |  | ROAMING |  | 2015-08-03 | 2015-07-01 | 2015-06-30 | 2015-07-03 |  |  |  |  | 2015-08-14 | 2015-08-12 |  |  | 2012-08-07
0 | AKL | 14 | AKL-004-017 | Warkworth | AKL-004-017-D | Warkworth GF Cosite | Rodney District | 23 | TIER_4 | ACTIVE | GF | DU | T2 15 RFH |  | INLINE | COSITE | 14.5 | 15 |  | -36.4011 | 174.6532 |  | 2011-12-19 |  |  | Fibre Optic | AKL-005-088-A | FALSE | FALSE |  |  | FALSE |  | 2012-11-06 | 2012-11-06 | 2012-11-08 | 2012-11-08 | 2012-12-06 | 2013-01-17 | 3 |  | 2014-12-18 | 2015-01-30 | 2015-02-05 | 2015-05-15 | 2015-05-06 |  | 2015-05-15 | 2015-07-02 | DISCRETIONARY_FULL | 2015-03-02 | 2015-03-10 | 2015-04-24 | 2015-04-10 | 3 | 2015-05-01 | 2015-04-10 | 2015-03-16 | 2015-03-11 | 2015-06-26 | 2015-06-25 | 1 |  | 2015-06-26 | 2015-06-25 | [5 empty] | 2015-08-17 | 2015-08-17 | 2015-09-23 | 2015-10-01 |  | 2015-10-23 |  | 2015-08-14 | 2015-09-09 | [7 empty] | 2015-10-23 | 2015-10-22 |  | 2015-11-23 |  | 2015-11-23 | 25/08/15 - Pile Cap poured. Cabinet base next week. Power Transformer upgrade required. Integrate week 7 Sept (CR Lodged) 08/09/15 - Tower delivery Friday morning - some concerns on getting it onto site. Power transformer to be upgraded still. Shift Integration to 21-25 Sept. MUST get to air SEPT 16/09/15 - Look to integrate on generator. Power not being provided until 15 Oct. Liven site week 19 Oct 02/10/15 - Vol4 completed. Need power for Vol4 approval 22/10/15 - Power on , SR signed off, Site to air | [8 empty] | 2015-09-25 |  | 2015-10-21 | 2015-10-22 |  |  | AUCKLAND_WHANGAREI | 2015-09-08 | 2015-09-09 | BUILD |  | FALSE |  | 2658785 | 6532016 | 20 View Roadf Watercare Property Warkworth |  |  | CELLSITE |  |  |  | ROAMING |  | 2015-05-15 | 2015-04-24 | 2015-05-11 | 2015-04-29 | 2015-04-23 | 2015-04-23 | 2015-04-23 | 2015-04-23 | 2015-07-24 | 2015-07-27 |  |  | 2012-11-08
0 | AKL | 15 | AKL-004-018 | Snells Beach | AKL-004-018-A | Snells Beach VF Colo | Rodney District | 23 | TIER_4 | ACTIVE | COLO | DU | COLO |  | STACK_A | COLO | 20 | 20 |  | -36.404 | 174.7171 |  | 2011-12-19 |  |  | Fibre Optic | AKL-005-088-A | FALSE | FALSE |  |  | FALSE |  | 2012-03-26 | 2012-03-26 | 2012-04-03 | 2012-03-29 | 2012-06-08 | 2012-06-21 | 3 | 2012-06-15 | 2012-10-23 | 2015-06-05 | 2015-04-28 | 2015-08-14 | 2015-07-23 |  | 2015-10-02 | 2015-07-27 | DISCRETIONARY_FULL | 2015-05-25 | 2015-05-22 | 2015-07-06 | 2015-06-24 | 1 | 2015-07-13 | 2015-06-24 | 2015-07-06 | 2015-05-01 | 2015-06-12 | 2015-06-23 | 2 |  | 2015-06-19 | 2015-09-21 | [5 empty] | 2015-09-21 | 2015-09-30 | 2015-10-30 | 2015-11-04 |  |  |  | 2015-11-30 | 2015-12-01 | [7 empty] | 2015-12-11 | 2015-12-10 |  |  |  |  | 04/08/15 - Lodged for Final and Build Approval with VF 06/08/15 - Final approval received. Build approval in process. PO issued and Skcomms have steelwork underway 07/09/15 - VF require updated CD's to reflect better ladder design for pole and also painting requirements 30/09/15 - VF Approval to build issued 20/10/15 - Cabs in next Wed, waiting power connection. Ringframe this week. 4/11/15 - Build completed - awaiting Fibre. Chorus requested to deliver 24/11/14 - Chorus Fibre now scheduled for 27 Nov 7/12/15 - Vol 4 rec 4/12 | VNZ | [9 empty] | 2015-12-04 | 2015-12-04 |  |  | AUCKLAND_WHANGAREI | 2015-11-30 | 2015-12-01 | BUILD |  | TRUE |  | 2664510 | 6531583 | James Street Snells Beach |  | Status for CO-lo: Discretionary activity, anything in zone is. -AT. Zoned residential L (low intensity) - 04/09/2012 | CELLSITE |  |  |  | ROAMING |  |  | 2015-03-19 | 2015-06-22 | 2015-06-16 | 2015-04-23 | 2015-04-23 | 2015-06-01 |  | 2015-08-28 | 2015-08-07 |  |  | 2012-04-03
0 | AKL | 16 | AKL-004-019 |  |  |  | Rodney District |  | TIER_9
0 | AKL | 17 | AKL-004-020 |  |  |  | Rodney District |  | TIER_9
0 | AKL | 18 | AKL-004-021 |  |  |  | Rodney District |  | TIER_9
0 | AKL | 19 | AKL-004-022 | Wellsford | AKL-004-022-B | Wellsford GF | Rodney District | 23 | TIER_4 | ACTIVE | GF | DU | T2 20 RH |  | INLINE | COSITE | 20 | 20 |  | -36.2923 | 174.5346 |  | 2011-12-19 |  |  | Fibre Optic | AKL-005-088-A | FALSE | FALSE |  |  | FALSE |  | 2012-03-12 | 2012-03-12 | 2012-04-03 | 2012-03-29 | 2012-04-24 | 2012-05-22 | 1 |  | 2012-05-22 | 2012-06-18 | 2012-06-19 | 2012-07-16 | 2012-07-19 | 1 | 2012-08-24 | 2012-08-16 | PERMITTED | 2012-06-18 | 2012-06-19 | 2012-07-30 | 2012-07-23 | 1 | 2012-07-30 | 2012-07-23 | 2015-01-27 | 2015-01-27 | 2015-03-27 | 2015-03-27 | 1 |  | 2015-03-27 | 2015-03-27 | [5 empty] | 2015-05-11 | 2015-05-13 | 2015-07-29 | 2015-07-29 | 2015-07-22 | 2015-07-17 | 2015-07-29 | 2015-07-28 | 2015-07-28 | [6 empty] | 2015-07-27 | 2015-08-21 | 2015-08-06 |  | 2015-08-31 |  | 2015-08-31 | Huawei Build PO 35468 13/05/15 - Access track to be re-positioned due to access steepness. Ralph on site and agreed new position. Works started on site 04/06/15 - Power trench and cable in. Fibre onto site. Pile in. 15/6 restart on site with Pile Cap / cabinet foundations, pole 29/6, Integrate 6 July 29/06/15 - Duco advise pole delayed till 10 July - all dates delayed 07/07/17 - Duco pole delayed to 17 July !!! 24/07/15 - pole up, integration planned for 30/31 July 03/08/15 - Site Integrated with Vol 4 |  | 2015-07-06 | [8 empty] | 2015-08-04 | 2015-07-31 |  |  | AUCKLAND_WHANGAREI | 2015-07-28 | 2015-07-28 | BUILD | 2015-06-29 | TRUE |  | 2648373 | 6544289 | Cnr of Worthington and Matheson Rd Adjacent to Watercare tanks Wellsford |  |  | CELLSITE |  |  |  | ROAMING |  | 2015-03-13 | 2015-04-02 | 2015-04-07 | 2015-04-07 | 2015-04-23 | 2015-04-23 | 2015-04-23 | 2015-04-23 | 2015-05-05 | 2015-05-05 |  |  | 2012-04-03
0 | AKL | 20 | AKL-004-024 | Waiwera | AKL-004-024-A | Waiwera | Rodney District | 3 | TIER_3 | ACTIVE | GF | DU | T2 15 RFH |  | INLINE | COSITE | 15 | 15 |  | -36.5478 | 174.6995 |  | 2011-12-19 |  |  | Microwave | AKL-004-046-C | FALSE | FALSE |  |  | FALSE |  | 2012-02-29 | 2012-02-29 | 2012-03-12 | 2012-03-09 | 2012-05-25 | 2012-06-06 | 1 | 2012-06-08 | 2012-06-06 | 2012-09-14 | 2012-09-10 | 2012-11-29 |  | 1 | 2012-11-29 |  | DISCRETIONARY_FULL | 2012-11-05 | 2012-11-06 | 2012-12-21 | 2012-12-17 | 1 | 2012-12-31 | 2012-12-19 |  |  | 2013-02-13 | 2013-02-28 | 1 |  | 2013-02-13 | 2013-02-28 | 2013-02-08 | [26 empty] | Brad to contact LL. LL is aware of the value of his site. May request high rental. If this site fails we may have to do 2 other sites wiawera town / Puhoi and Hatfield. 29 Feb. Site visit. VNZ co lo out of the question - low and loaded. Team Talk have approached LL for a site between VNZ and Kordia. We would also want to be between the two. Site changed to HARD MATCH ONLY 5 Oct 2012 12 OCT - Back into build program Letters not required 17.10.2012 Back on build program. WO2 due 15 Nov 2012 24.01.2013 Downers to build. Landlord has requested that work be correlated with Team Talk BUILD PROGRAMM, ALL WORK TO BE COMPLETE END FEB. 05.02.2013 Await Team Talk commencement. Downer to update SB. 15/04/13 Team Talk commenced. Mr Heaton wants tar seal fixed and resealed even if we dont damage. TT have alleady had trucks up there and damaged concrete. TT will give 10k towards road repair. Mr Heatons contractor gave quote to fix tar = 50K. We cant bear all costs. TT threatening to take Mr Heaton to court re lack of access. 2degrees to step back and wait for all this road issues to clear. |  | 2013-05-24 | 2013-01-08 | 2013-01-08 | 2013-02-04 | 2013-02-04 | 2013-02-08 | 2013-02-08 | 2013-05-16 | [5 empty] | OREWA |  |  | HARDMATCH |  | FALSE |  | 2662615 | 6515657 | Jervis Road | LEASE TERMINATED - 27/05/2014 | Lodged at council with Andrew Gusberts on the 6.11.2012 - 08/11/2012 | CELLSITE | WIPHOLDING | [14 empty] | 2013-05-30
0 | AKL | 21 | AKL-004-025 | Orewa Bypass | AKL-004-025-A | Orewa Bypass | Rodney District | 3 | TIER_3 | ACTIVE | GF | DU | P1 |  | STACK_A |  | 14.5 | 15 |  | -36.5816 | 174.6744 |  | 2011-12-19 |  |  | Microwave | AKL-004-041-B | FALSE | FALSE |  |  | FALSE |  | 2012-02-29 | 2012-02-29 | 2012-04-26 | 2012-04-26 | 2012-06-11 | 2012-06-06 | 8 | 2012-08-28 | 2013-03-15 | 2012-12-07 | 2013-01-15 | 2013-04-30 |  |  | 2013-04-30 |  | DISCRETIONARY_RESTRICT | 2013-05-01 |  | 2013-05-31 |  |  | 2013-06-03 | [36 empty] | 2 possible locations at the Watertank. Measured up both at caravan. Mikhail and Erwin to Cherry Pick asap. Watercare have advised that our chosen position is not suitable for them. We need to move within the site or find a new location completely. Looking at rental of $10K. Have had drawings upreved to V2 - Moved site position. Watercare not happy with this position have asked we move to bottom corner. We have looked at it - need to Cherry pick from here. 5 October 2012 - Site changed to HARD MATCH ONLY. 24.01.2013 Watercare happy with position and lease docs underway. They have asked for Gobi blocks to be used on access to site - busy investigating. 26.03.2013 Lease with Mike D for concideration. | [14 empty] | OREWA |  |  | HARDMATCH |  | TRUE |  | 2660298 | 6511948 | West Hoe Heights Road Watercare Watertank
0 | AKL | 22 | AKL-004-026 |  |  |  | Rodney District |  | TIER_9
0 | AKL | 23 | AKL-004-027 |  |  |  | Rodney District |  | TIER_9
0 | AKL | 24 | AKL-004-028 | Waitoki | AKL-004-028-A | Waitoki VF Colocation | Rodney District | 23 | TIER_4 | ACTIVE | COLO | DU | COLO |  | STACK_A | COLO |  |  |  | -36.6332 | 174.5772 |  |  |  |  | Microwave, Microwave | AKL-004-059-A | FALSE | FALSE |  |  | FALSE |  | 2015-04-13 | 2015-03-03 | 2015-04-16 | 2015-03-11 | 2015-04-15 | 2015-05-18 | 2 | 2015-04-17 | 2016-02-10 | 2015-06-26 | 2015-06-11 | 2015-09-07 | 2015-08-25 |  | 2015-09-30 | 2015-08-25 | NON_COMPLYING_FULL | 2015-07-06 | 2015-06-30 | 2015-08-07 | 2015-08-05 | 1 | 2015-08-07 | 2015-08-05 | 2015-08-31 | 2015-08-24 | 2015-10-02 | 2015-09-24 | 1 |  | 2015-10-02 | 2015-09-24 | [5 empty] | 2015-11-16 | 2015-11-17 | 2015-12-09 | 2015-12-11 | [12 empty] | 2016-03-23 | [5 empty] | 11/06/15 - Colo Preliminary Approval received. VF to supply Lease and DOV docs 25/8/15 - Lodged for Final approval - Received same day (Record) 23/10/14 - Lodged for Build Approval 17/11/15 - Build approval received 30/11/15 - Power 3 Dec, link in today, BER by 9/12 7/12 - Vol 4 by 14 Dec 8/1/16 - Issue with trees in MW path too substantial. Need another pole away from site for MW link 4/2/16 - pole location for MW link identified, plans in action. Allow for 2 links to cater for VF as well. 9/2/16 - Plans supplied to Brad. Will take a month to get signed off and build. Draft license with John W | VNZ | [9 empty] | 2015-12-14 | 2015-12-15 | [5 empty] | BUILD |  | TRUE |  | 2651493 | 6506397 | VF Colocation 684 Kahikatea Flat Road Waitoki |  | Non complying likely for earthworks - 28/04/2015 | CELLSITE | WIPACTIVE |  |  | ROAMING |  |  | 2015-10-12 | 2015-10-02 | 2015-10-09 |  |  |  |  | 2015-11-06 | 2015-11-02 |  |  | 2015-03-11
0 | AKL | 25 | AKL-004-029 | Silverdale Off Ramp | AKL-004-029-A | Silverdale Offramp | Rodney District | 3 | TIER_3 | ACTIVE | GF | DU | T2 15 RFH |  | INLINE | STANDALONE | 14.5 | 15 |  | -36.6259 | 174.6616 |  | 2012-06-01 |  |  | Microwave | AKL-004-042-B | FALSE | FALSE |  |  | FALSE |  | 2012-07-26 | 2012-07-26 | 2012-07-31 | 2012-07-30 | 2012-09-05 | 2012-09-10 | 1 | 2012-09-05 | 2012-09-10 | 2012-10-24 | 2012-10-24 | 2012-11-16 | 2012-11-16 | 1 | 2012-11-16 | 2012-11-16 | PERMITTED | 2012-11-05 | 2012-11-06 | 2012-12-03 | 2012-12-04 | 1 | 2012-12-03 | 2012-12-04 |  |  | 2013-01-24 | 2013-01-29 | 1 |  | 2013-01-24 | 2013-01-29 | 2013-02-04 |  |  | 2013-01-17 |  | 2013-02-18 | 2013-02-15 | 2013-03-08 | 2013-03-04 | 2013-02-22 | 2013-03-15 | 2013-03-14 | [8 empty] | 2013-03-14 | 2013-04-12 | 2013-04-09 | 2013-04-25 | 2013-04-24 | 2013-08-15 | 2013-08-23 |  |  | 2013-03-15 | 2013-01-08 | 2013-01-08 | 2013-02-06 | 2013-02-06 | 2013-02-04 | 2013-02-04 | 2013-04-02 | 2013-03-27 | 2013-04-05 | 2013-04-04 |  |  | TIER_1_INFILL |  |  | BUILD | 2013-02-22 | TRUE |  | 2659057 | 6507055 | Off RAMP Silverdale |  | Lodged with Andrew Gysberts on 6.11.2012 - 08/11/2012 | CELLSITE | [15 empty] | 2013-04-05 | 2013-04-05
0 | AKL | 26 | AKL-004-036 | North Shore Aerodrome | AKL-004-036-C | North Shore Aerodrome | Rodney District | 3 | TIER_3 | ACTIVE | GF | DU | T2 20 RF |  | INLINE | COSITE |  | 20 |  | -36.6566 | 174.6648 |  | 2012-06-01 |  | 2010-04-06 | Fibre Optic | AKL-005-078-A | TRUE | TRUE | 2010-03-15 |  | FALSE |  | 2012-07-18 | 2012-07-18 | 2012-08-19 | 2012-08-16 | 2012-09-24 | 2012-09-24 | 1 | 2012-09-24 | 2012-09-24 | 2012-10-19 | 2012-10-22 | 2012-11-23 | 2012-11-26 | 1 | 2012-11-30 | 2012-11-26 | DISCRETIONARY_RESTRICT | 2012-10-31 | 2012-11-01 | 2012-11-30 | 2012-12-03 | 1 | 2012-12-26 | 2012-12-03 |  |  | 2013-02-07 | 2013-02-08 | 1 |  | 2013-02-07 | 2013-02-08 | 2013-01-15 |  |  |  |  | 2013-02-04 | 2013-02-04 | 2013-02-19 | 2013-02-19 | 2013-02-18 | 2013-04-10 | 2013-04-11 | 2013-04-08 | 2013-04-05 | [6 empty] | 2013-04-10 | 2013-04-19 | 2013-04-17 | 2013-04-25 | 2013-04-24 | 2013-08-31 | 2013-10-10 |  |  | 2013-04-10 | 2013-01-07 | 2013-01-07 | 2013-01-08 | 2013-01-08 | 2013-01-15 | 2013-01-15 | 2013-03-28 | 2013-03-27 | 2013-04-12 | 2013-04-11 |  |  | TIER_1_INFILL | 2013-04-02 | 2013-04-04 | BUILD | 2013-02-18 | FALSE |  | 2659275 | 6503649 | Adjacent to Vodafone Aileron Rise Off Wilks Rd Dairy Flat |  |  | CELLSITE | [15 empty] | 2013-04-12 | 2013-04-12
0 | AKL | 27 | AKL-004-037 | Gulf Harbour |  |  | Rodney District |  | TIER_9 | [22 empty] | FALSE | [60 empty] | Coverage to Gulf Harbour area. TNZ clock tower recommended for coverage. Antennas to be located on top of the tower.
0 | AKL | 28 | AKL-004-038 | Tindalls Beach |  |  | Rodney District |  | TIER_9 | [22 empty] | FALSE | [60 empty] | Coverage to the SW , NE & NW directions. New site. Consider 15-20m pole and the recommended location.
0 | AKL | 29 | AKL-004-039 | Whangaparaoa |  |  | Rodney District |  | TIER_9 | [22 empty] | FALSE | [60 empty] | Coverage to the NW, East and West of the site. Consider co-location with 30m Telecom pole. However consider Telecom site is limited by trees and coverage is restricted to the West of the site.
0 | AKL | 30 | AKL-004-040 | Red Beach |  |  | Rodney District |  | TIER_9 | [22 empty] | FALSE
0 | AKL | 31 | AKL-004-041 | Orewa | AKL-004-041-B | Orewa Central | Rodney District | 3 | TIER_3 | ACTIVE | GF | DU | T2 20 UF |  | STACK_A |  | 18 | 18 | 1 | -36.5863 | 174.6933 |  | 2011-12-19 |  | 2010-04-06 | Fibre Optic | AKL-005-078-A | TRUE | TRUE | 2010-03-15 |  | FALSE |  | 2012-03-26 | 2012-03-26 | 2012-04-03 | 2012-03-30 | 2012-06-01 | 2012-06-07 | 1 | 2012-06-08 | 2012-06-07 | 2012-07-06 | 2012-07-04 | 2012-09-07 | 2012-09-10 | 1 | 2012-09-14 | 2012-09-10 | DISCRETIONARY_FULL | 2012-07-17 | 2012-07-16 | 2012-08-28 | 2012-08-22 | 1 | 2012-09-04 | 2012-08-29 | 2012-09-03 | 2012-09-03 | 2012-10-18 | 2012-10-25 | 1 |  | 2012-10-18 | 2012-10-25 | 2012-11-20 |  |  | 2012-09-28 |  | 2012-12-10 | 2012-12-10 | 2013-01-11 | 2013-01-11 | 2012-12-13 | 2013-01-22 | 2013-01-22 | 2013-01-22 | 2013-01-22 | [6 empty] | 2013-01-24 | 2013-02-07 | 2013-02-07 | 2013-02-15 | 2013-02-15 | 2013-06-14 | 2013-05-24 |  |  | 2013-01-23 | 2012-10-02 | 2012-10-02 | 2012-11-05 | 2012-11-05 | 2012-11-20 | 2012-11-20 | 2013-01-21 | 2013-01-22 | 2013-01-31 | 2012-12-10 |  |  | OREWA | 2012-12-14 | 2012-12-14 | BUILD | 2012-12-13 | TRUE | 2012-10-01 | 2661978 | 6511398 | 8-10 George Lowe Place Orewa |  | RMA status TBC as of 5.4.12 - Discretionary = worst case scenario - 05/04/2012 | CELLSITE | [15 empty] | 2013-01-29 | 2013-01-30
0 | AKL | 32 | AKL-004-042 | Silverdale | AKL-004-042-B | Silverdale LPR (NZTA) | Rodney District | 3 | TIER_3 | ACTIVE | RSR | DU | P4F |  | INLINE |  | 12.3 | 13.8 | 1 | -36.6162 | 174.681 |  | 2011-12-19 |  | 2010-04-06 | Fibre Optic | AKL-007-106-A | TRUE | TRUE | 2010-03-15 |  | FALSE |  | 2012-02-13 | 2012-02-13 | 2012-02-15 | 2012-02-15 | 2012-03-30 | 2012-04-04 | 1 | 2012-03-30 | 2012-04-04 | 2012-06-11 | 2012-06-19 | 2012-09-28 | 2012-09-25 | 1 | 2012-10-05 | 2012-09-25 | NES | 2012-06-19 | 2012-06-18 | 2012-07-30 | 2012-07-20 | 1 | 2012-08-06 | 2012-07-20 | 2012-08-15 |  | 2012-09-13 | 2012-10-02 | 1 |  | 2012-09-20 | 2012-10-02 | 2012-10-14 |  |  | 2012-09-10 |  | 2012-10-10 | 2012-10-10 | 2012-10-15 | 2012-10-15 | 2012-10-15 | 2012-11-28 | 2012-11-22 | 2012-11-29 | 2012-12-06 | [6 empty] | 2012-12-10 | 2013-01-25 | 2013-01-24 | 2013-02-08 | 2013-02-08 | 2013-07-31 | 2013-07-17 |  |  | 2013-01-10 | 2012-10-06 | 2012-10-06 | 2012-10-11 | 2012-10-12 | 2012-10-10 | 2012-10-14 | 2013-01-21 | 2013-01-22 | 2012-12-10 | 2012-12-10 |  |  | OREWA | 2012-11-27 | 2012-12-06 | BUILD | 2012-10-16 | TRUE |  | 2660811 | 6508102 | 27 Hibiscus Coast Highway (NZTA) Silverdale |  |  | CELLSITE | [15 empty] | 2013-01-30 | 2013-01-25 | 2012-02-15
0 | AKL | 33 | AKL-004-043 | Stanmore Bay | AKL-004-043-D | Stanmore Bay | Rodney District | 3 | TIER_3 | ACTIVE | GF | DU | T2 15 RFH |  | STACK_A | COSITE | 14.5 | 15 |  | -36.626 | 174.7204 |  | 2012-06-01 |  | 2010-04-06 | Fibre Optic | AKL-005-078-A | TRUE | TRUE | 2010-03-15 |  | FALSE |  | 2012-08-14 | 2012-08-14 | 2012-08-21 | 2012-08-16 | 2012-09-26 | 2012-09-28 | 3 | 2012-10-02 | 2012-11-13 | 2012-11-08 | 2012-11-09 | 2012-11-30 | 2012-11-13 |  | 2013-04-12 |  | DISCRETIONARY_RESTRICT | 2012-10-31 | 2012-11-01 | 2013-01-25 | 2013-01-25 | 2 | 2013-01-31 | 2013-01-25 |  |  | 2013-01-24 | 2013-02-04 | 2 |  | 2013-01-24 | 2013-03-13 | 2013-03-04 |  |  | 2013-01-29 |  | 2013-03-18 | 2013-03-18 | 2013-04-08 | 2013-04-05 | 2013-04-04 | 2013-04-16 | 2013-04-17 | 2013-04-09 | 2013-04-16 | [6 empty] | 2013-04-17 | 2013-04-22 | 2013-04-24 | 2013-05-08 | 2013-05-07 | 2013-08-31 | 2013-09-06 | 16/07/13 PSVP Exp 07/08/13 |  | 2013-04-16 | 2013-02-04 | 2013-02-04 | 2013-03-04 | 2013-03-04 | 2013-03-04 | 2013-03-04 | 2013-04-19 | 2013-04-19 | 2013-04-15 | 2013-04-11 |  |  | TIER_1_INFILL | 2013-04-05 | 2013-04-12 | BUILD | 2013-04-05 | TRUE | 2013-02-01 | 2664318 | 6506940 | 463A Whangaparaoa Road Whangaparaoa Rodney District |  |  | CELLSITE | [15 empty] | 2013-04-29 | 2013-04-23
0 | AKL | 34 | AKL-004-044 | Manly | AKL-004-044-E | Manly | Rodney District | 3 | TIER_3 | ACTIVE | GF | DU | P4F |  | STACK_A | STANDALONE | 10 | 10.5 |  | -36.6364 | 174.7478 |  | 2012-06-01 |  | 2010-04-06 | Microwave | AKL-004-055-A | TRUE | TRUE | 2010-03-15 |  | FALSE |  | 2012-08-01 | 2012-08-01 | 2012-08-08 | 2012-08-07 | 2012-09-24 | 2012-09-24 | 1 | 2012-09-24 | 2012-09-24 | 2012-11-09 | 2012-11-13 | 2013-02-22 | 2013-03-22 | 1 | 2013-02-28 | 2013-03-26 | DISCRETIONARY_FULL | 2012-11-21 | 2012-11-21 | 2012-12-21 | 2012-12-19 | 1 | 2013-01-25 | 2012-12-20 |  |  | 2013-01-24 | 2013-01-23 | 1 |  | 2013-01-24 | 2013-01-23 | 2013-02-08 |  |  | 2013-02-26 |  | 2013-04-22 | 2013-04-27 | 2013-05-15 | 2013-05-13 | 2013-05-20 | 2013-05-28 | 2013-05-27 | [8 empty] | 2013-05-27 | 2013-06-14 | 2013-05-31 | 2013-06-19 | 2013-06-14 | 2013-09-13 | 2013-09-19 |  |  | 2013-05-28 | 2013-01-14 | 2013-01-14 | 2013-02-04 | 2013-02-04 | 2013-02-08 | 2013-02-08 | 2013-05-28 | 2013-05-27 | 2013-05-28 | 2013-05-27 |  |  | TIER_1_INFILL |  |  | BUILD | 2013-05-20 | TRUE | 2013-02-26 | 2666743 | 6505740 | 100% Shop Whangaparaoa Road |  | Lodged at Auckland Council on the 21.11.12. - 21/11/2012 | CELLSITE | [15 empty] | 2013-06-03 | 2013-06-04
0 | AKL | 35 | AKL-004-045 | Hillcrest |  |  | Rodney District |  | TIER_9 | [22 empty] | FALSE | [60 empty] | Coverage to the North, South and East of the site. Nominal location is a hilltop water tank site for a new 15-20m structure. Site visit 15/3/10 Option A:Pukeko bridge location good for Northern Mwy and Hatfields Beach.
0 | AKL | 36 | AKL-004-046 | Army Bay | AKL-004-046-C | Army Bay Roof Top | Rodney District | 3 | TIER_3 | ACTIVE | RT | DF | RT |  | INLINE | COSITE |  |  |  | -36.6056 | 174.7958 |  | 2012-06-01 |  | 2010-04-06 | Fibre Optic | AKL-005-078-A | TRUE | TRUE | 2010-03-15 |  | FALSE |  | 2012-07-10 | 2012-07-10 | 2012-07-17 | 2012-07-17 | 2012-08-24 | 2012-08-29 | 1 | 2012-08-24 | 2012-08-29 | 2012-09-28 | 2012-10-02 | 2012-10-19 | 2012-10-30 | 1 | 2012-10-19 | 2012-10-30 | PERMITTED | 2012-09-28 | 2012-10-01 | 2012-11-02 | 2012-10-30 | 1 | 2012-11-05 | 2012-10-31 |  |  | 2013-02-11 | 2013-02-14 | 1 |  | 2013-02-11 | 2013-02-14 | 2013-01-15 |  |  | 2012-11-09 |  | 2013-02-11 | 2013-02-11 | 2013-03-08 | 2013-03-09 | 2013-02-21 | 2013-03-27 | 2013-03-27 | 2013-02-27 | 2013-02-27 | [6 empty] | 2013-03-27 | 2013-04-12 | 2013-04-12 | 2013-04-11 | 2013-04-11 | 2013-08-31 | 2013-10-22 |  |  | 2013-03-27 | 2012-12-04 | 2012-12-04 | 2013-01-15 | 2013-01-15 | 2013-01-15 | 2013-01-15 | 2013-03-15 | 2013-03-14 | 2013-03-27 | 2013-03-27 |  |  | TIER_1_INFILL | 2013-02-25 | 2013-02-25 | BUILD | 2013-02-26 | TRUE | 2012-11-07 | 2671101 | 6509066 | 1337 Whangaparaoa Road Whangaparaoa Rodney District |  |  | CELLSITE | [15 empty] | 2013-04-03 | 2013-04-04
0 | AKL | 37 | AKL-004-048 | Tindalls Beach | AKL-004-048-C | Tindalls Beach LPR | Rodney District | 3 | TIER_3 | ACTIVE | RSR | DU | P4F |  | INLINE | STANDALONE | 14.5 | 15 |  | -36.6315 | 174.7639 |  | 2012-06-01 |  | 2010-04-06 | Fibre Optic | AKL-005-078-A | TRUE | TRUE | 2010-03-15 |  | FALSE |  | 2012-08-01 | 2012-08-01 | 2012-08-08 | 2012-08-06 | 2012-09-10 | 2012-09-11 | 2 | 2012-09-10 | 2012-11-09 | 2012-10-30 | 2012-10-31 | 2012-11-30 | 2012-11-14 |  | 2012-11-30 | 2012-11-14 | NES | 2012-11-12 | 2012-11-12 | 2012-12-10 | 2012-12-10 | 2 | 2012-12-10 | 2012-12-10 |  |  | 2012-11-29 | 2012-12-04 | 2 |  |  | 2013-02-07 | 2013-01-15 |  |  | 2012-12-11 |  | 2013-01-23 | 2013-01-23 | 2013-02-15 | 2013-02-15 | 2013-01-31 | 2013-02-20 | 2013-02-20 | 2013-02-07 | 2013-02-05 | [6 empty] | 2013-02-21 | 2013-04-12 | 2013-04-12 | 2013-03-13 | 2013-03-13 | 2013-06-21 | 2013-06-21 |  |  | 2013-02-21 | 2012-12-10 | 2012-12-10 | 2013-01-14 | 2013-01-14 | 2013-01-15 | 2013-01-15 | 2013-02-13 | 2013-02-12 | 2013-02-27 | 2013-02-27 |  |  | TIER_1_INFILL | 2013-02-04 | 2013-02-04 | BUILD | 2013-02-13 | TRUE | 2012-12-11 | 2668194 | 6506256 | 925 Whangaparaoa Road Manly |  |  | CELLSITE | [15 empty] | 2013-02-26 | 2013-02-27
0 | AKL | 38 | AKL-004-050 | Riverhead Township | AKL-004-050-A | Riverhead Township Truck Yard | Rodney District | 3 | TIER_1_INFILL | ACTIVE | GF | Ab | P2 | Grey |  | STANDALONE | 19.5 | 20 | 1 | -36.7588 | 174.6059 |  |  |  |  | Microwave | AKL-004-003-E | FALSE | FALSE |  |  | FALSE |  | 2011-03-28 | 2011-03-28 | 2011-05-03 | 2011-04-26 | 2011-06-09 | 2011-06-09 | 1 | 2011-06-09 | 2011-06-09 | 2011-06-16 | 2011-04-27 | 2011-06-01 | 2011-06-03 | 1 | 2011-06-08 | 2011-06-03 | DISCRETIONARY_RESTRICT | 2011-06-30 | 2011-06-30 | 2011-08-10 | 2011-07-27 | 1 | 2011-08-17 | 2011-07-27 |  |  |  | 2011-11-03 | 1 |  |  | 2011-11-03 | 2012-02-13 |  |  |  |  | 2011-12-08 | 2011-12-08 | 2012-01-20 | 2012-01-24 | 2012-01-13 | 2012-01-24 | 2012-01-27 | [8 empty] | 2012-02-10 | 2012-02-15 | 2012-02-15 | 2012-02-15 | 2012-02-20 | 2012-05-21 | 2012-10-19 | 10.03 Initial Nominal visits. Kelly to contact Landlord - see if he is willing. He is willing. Site vist / caravan done. Need LOS before WO1 issue. LOS Done. WO1 issued. Lease signed. Await the RC. RC received. SITE HARD MATCHED. |  | 2012-01-27 | 2011-12-08 | 2011-12-21 | 2011-12-08 | 2012-02-13 | 2012-01-09 | 2012-02-13 | 2011-12-19 | 2012-01-20 | [7 empty] | BUILD | 2012-01-17 | FALSE |  | 2653800 | 6492413 | 62 Barrit Road Riverhead |  |  | CELLSITE | [15 empty] | 2012-02-10 | 2012-02-13
0 | AKL | 39 | AKL-004-051 | Kumeu East | AKL-004-051-C | Bus stop LPR HARD MATCH | Rodney District | 3 | TIER_1_INFILL | ACTIVE | RSR | D | P4F | Green | INLINE | COSITE |  | 15.5 |  | -36.788 | 174.5831 |  |  |  |  | Microwave | AKL-005-022-H | FALSE | FALSE |  |  | FALSE | 2011-04-14 | 2011-03-28 | 2011-04-28 |  | 2011-04-26 | 2011-06-16 | 2011-06-16 | 3 | 2011-09-02 | 2011-09-06 | 2011-09-21 | 2011-09-22 | 2011-11-09 | 2011-11-15 |  | 2011-12-02 | 2011-12-08 | NES | 2011-09-26 | 2011-09-22 | 2011-10-31 | 2011-10-14 | 3 | 2011-10-31 | 2011-10-19 | [29 empty] | 2013-01-14 |  | 2013-01-14 |  |  |  | 10.03 Initial nominal visit. LPR at bus stop - Ab cabinets thus not NES ! WO1 Issued. HARD MATCH SITE - Must use D cabinets. Now NES. Drawings to be changed. Drawings issued. Await NZTA letter so that we can submit the RMA | [17 empty] | HARDMATCH |  | FALSE |  | 2651702 | 6489207 | State Highway 16 Next to Bus stop at the Coatsville Riverhead Highway and HW16 T junction |  | Lodged on 22.9.11 with rev 3 plans - 22/09/2011 Approved on the 14.10.11 with rev 3 plans, council reference - COC-57939 - 14/10/2011 | CELLSITE | WIPHOLDING
0 | AKL | 40 | AKL-004-052 | RBI - Kumeu Township |  |  | Rodney District |  | TIER_9 | [22 empty] | FALSE
0 | AKL | 41 | AKL-004-053 | Helensville | AKL-004-053-B | Vodafone Co Location | Rodney District | 3 | TIER_3 | ACTIVE | COLO | DU | COLO |  | INLINE | COLO | 20 | 20 |  | -36.6572 | 174.4534 |  | 2011-12-19 |  |  | Fibre Optic | AKL-007-106-A | FALSE | FALSE |  |  | FALSE |  | 2012-03-08 | 2012-03-08 | 2012-03-09 | 2012-03-09 | 2012-06-08 | 2012-05-29 | 2 | 2012-06-08 | 2012-07-03 | 2012-07-17 | 2012-07-27 | 2012-09-28 | 2012-09-25 |  | 2012-09-28 | 2012-10-16 | DISCRETIONARY_FULL | 2012-07-04 | 2012-07-04 | 2012-08-15 | 2012-08-02 | 2 | 2012-08-22 | 2012-08-08 | 2012-09-03 |  | 2012-10-11 | 2012-10-11 | 1 |  | 2012-10-11 | 2012-10-11 | 2012-11-12 |  |  |  |  | 2012-11-05 | 2012-11-05 | 2012-11-16 | 2012-11-12 | 2012-11-12 | 2012-12-04 | 2012-12-03 | 2012-11-22 | 2012-11-27 | [6 empty] | 2012-12-04 | 2012-12-14 | 2012-12-12 | 2013-01-15 | 2012-12-19 | 2013-05-10 | 2013-05-06 |  | VNZ | 2012-12-04 |  |  | 2012-10-29 | 2012-11-12 | 2012-11-12 | 2012-11-12 | 2012-11-30 | 2012-11-30 | 2012-12-11 | 2012-12-06 |  |  | OREWA | 2012-11-16 | 2012-11-27 | BUILD | 2012-11-14 | FALSE |  | 2640375 | 6503924 | 96-110 State Highway 16 Helensville |  | Permitted if within 20m - as of 5.4.12 - 05/04/2012 | CELLSITE | [15 empty] | 2012-12-12 | 2012-12-12
0 | AKL | 42 | AKL-004-054 | Upper Orewa | AKL-004-054-B | Upper Orewa | Rodney District | 3 | TIER_3 | ACTIVE | COLO | DU | COLO |  | STACK_A | COLO | 20 | 20 |  | -36.5971 | 174.6618 |  | 2012-06-01 |  |  | Microwave | AKL-004-009-D | FALSE | FALSE |  |  | FALSE |  | 2012-07-26 | 2012-07-26 | 2012-07-31 | 2012-07-30 | 2012-08-27 | 2012-09-04 | 1 | 2012-08-27 | 2012-09-04 | 2012-10-15 | 2012-10-15 | 2013-02-15 | 2013-02-18 |  | 2013-02-21 | 2013-03-15 | DISCRETIONARY_FULL | 2012-10-16 | 2012-10-15 | 2012-11-23 | 2012-11-15 | 1 | 2012-12-19 | 2012-11-15 |  |  | 2013-02-08 | 2013-01-24 | 1 |  | 2013-02-08 | 2013-01-24 | 2013-03-18 |  |  |  |  | 2013-03-19 | 2013-03-12 | 2013-05-08 | 2013-05-08 | 2013-03-12 | 2013-05-13 | 2013-05-14 | [8 empty] | 2013-05-14 | 2013-05-27 | 2013-05-24 | 2013-05-28 | 2013-05-28 | 2013-08-30 | 2013-09-06 | PSVP Exp 28/08/13. | VNZ | 2013-05-13 | 2013-03-04 | 2013-03-04 | 2013-03-05 | 2013-03-05 | 2013-03-18 | 2013-03-18 | 2013-03-28 | 2013-03-27 | 2013-05-13 | 2013-05-13 |  |  | TIER_1_INFILL |  |  | BUILD | 2013-03-19 | FALSE |  | 2659137 | 6510257 | 27 Kowhai Road Orewa |  |  | CELLSITE | [15 empty] | 2013-05-16 | 2013-05-16
0 | AKL | 43 | AKL-004-055 | Wade Head | AKL-004-055-A | Wade Head | Rodney District | 3 | TIER_3 | ACTIVE | GF | DU | T2 20 RF |  | INLINE | COSITE | 19.5 | 20 |  | -36.6312 | 174.735 |  | 2012-06-06 |  |  | Fibre Optic | AKL-005-078-A | FALSE | FALSE |  |  | FALSE |  | 2012-07-10 | 2012-07-10 | 2012-07-17 | 2012-07-17 | 2012-08-27 | 2012-08-27 | 2 | 2012-08-27 | 2012-11-13 | 2012-10-05 | 2012-10-02 | 2012-11-23 | 2012-11-30 | 2 | 2012-11-28 | 2012-11-30 | DISCRETIONARY_RESTRICT | 2012-10-11 | 2013-10-22 | 2013-02-15 |  | 2 | 2013-02-22 | 2012-11-20 |  |  | 2013-01-24 | 2013-02-05 | 1 |  | 2013-01-24 | 2013-02-05 | 2013-02-12 |  |  | 2013-01-17 |  | 2013-02-18 | 2013-02-15 | 2013-03-08 | 2013-03-01 | 2013-03-04 | 2013-03-13 | 2013-03-13 | 2013-03-11 | 2013-03-11 | [6 empty] | 2013-03-14 | 2013-04-12 | 2013-04-12 | 2013-04-02 | 2013-03-28 | 2013-08-31 | 2013-12-20 | 16/07/2013 nO fan ISSUED, Boundary S not done at WO stage. Site in incorrect location. |  | 2013-03-13 | 2013-02-04 | 2013-02-04 | 2013-02-12 | 2013-02-12 | 2013-02-12 | 2013-02-12 | 2013-03-20 | 2013-03-15 | 2013-03-18 | 2013-03-18 |  |  | TIER_1_INFILL | 2013-03-08 | 2013-03-08 | BUILD | 2013-03-05 | TRUE |  | 2665605 | 6506344 | Arklow ln |  |  | CELLSITE | [15 empty] | 2013-03-22 | 2013-03-18
0 | AKL | 44 | AKL-004-056 | Dairy Flat | AKL-004-056-A | Dairy Flat | Rodney District | 3 | TIER_3 | ACTIVE | GF | DU | T2 20 RH |  | INLINE | COSITE | 19.5 | 20 |  | -36.6412 | 174.6308 |  |  |  |  | Microwave | AKL-004-043-D | FALSE | FALSE |  |  | FALSE |  | 2012-07-18 | 2012-07-18 | 2012-07-27 | 2012-07-23 | 2012-08-20 | 2012-08-22 | 2 | 2012-08-20 | 2012-09-14 | 2012-09-10 | 2012-09-10 | 2012-09-14 | 2012-09-14 |  | 2012-09-14 | 2012-10-24 | DISCRETIONARY_RESTRICT | 2012-09-24 | 2012-09-10 | 2012-10-22 | 2012-10-11 | 2 | 2012-10-29 | 2012-10-11 | [35 empty] | VNZ Site not co locatable. Do own site further down slope. 20m. Landlord is willing. | [14 empty] | TIER_1_INFILL |  |  | HARDMATCH |  | TRUE |  | 2656273 | 6505414 | 120 Kahikatea Flat Rd Pine Valley Dairy Flat |  |  | CELLSITE | WIPHOLDING
0 | AKL | 45 | AKL-004-057 | Cellutronics 005 |  |  | Rodney District |  | TIER_6
0 | AKL | 46 | AKL-004-058 | Kumeu East |  |  | Rodney District |  | TIER_9
0 | AKL | 47 | AKL-004-059 | Kaukapakapa | AKL-004-059-A | Kaupapakapa COLO | Rodney District | 23 | TIER_4 | ACTIVE | COLO | DU | COLO |  | STACK_A | COLO | 35 | 35 |  | -36.6151 | 174.4763 |  |  |  |  | Microwave | AKL-004-060-A | FALSE | FALSE |  |  | FALSE |  | 2014-12-04 | 2014-12-04 | 2015-02-16 | 2015-02-18 | 2015-03-13 | 2015-03-24 | 1 | 2015-03-20 | 2015-03-24 | 2015-06-05 | 2015-05-13 | 2015-08-21 | 2015-09-21 |  | 2015-09-18 | 2015-09-21 | DISCRETIONARY_FULL | 2015-05-18 | 2015-04-20 | 2015-06-26 | 2015-05-19 | 1 | 2015-07-03 | 2015-05-19 | 2015-05-15 | 2015-05-15 | 2015-06-19 | 2015-06-09 | 2 |  | 2015-06-19 | 2015-09-09 | [5 empty] | 2015-10-14 | 2015-10-14 | 2015-11-06 | 2015-11-17 |  | 2015-11-06 | 2015-11-17 | [9 empty] | 2015-11-30 | 2015-11-30 |  |  |  |  | 27/07/15 - Site awarded to Downers - Huawei to provide formal docs 04/08/15 - Downers to provide Project Plan. Huawei to issue quote 07/08/15 - Quote received and POR raised 13/08/15 - PO 36683 Issued. Doing Acceptance of preliminary approval. 25/08/15 - Metalwork started. Lodged for Final Approval - VF not accepting yet until Clearspan lease issue signed 01/09/15 - Lease with VF. Documents for Final Approval with Liz to lodge 07/09/15 - Lodged for Build approval 09/09/15 - VF have come back with questions on their antenna azimuths - may now clash with ringframe - need urgent review 16/9/15 - Have build approval. Downers to start 24/11/15 - Integrated, Vol 4 (less sweeps) supplied. Feeder connectors to be changed | VNZ | [9 empty] | 2015-11-27 | 2015-11-24 | [5 empty] | BUILD |  | FALSE |  | 2642505 | 6508569 | VF Colocation Stoney Property Alpine Road Kaukapakapa Auckland |  |  | CELLSITE |  |  |  | ROAMING |  |  | 2015-04-24 | 2015-06-19 | 2015-06-16 |  |  |  |  | 2015-08-14 | 2015-08-14 |  |  | 2015-02-18
0 | AKL | 48 | AKL-004-060 | Kaukapakapa TX Only | AKL-004-060-A | Kaukapakapa Exchange | Rodney District | 23 | TIER_4 | ACTIVE | COLO | TX | BO |  |  | COLO | 4.5 | 5.2 | [7 empty] | Fibre Optic | AKL-006-058-A | FALSE | FALSE |  |  | FALSE |  | 2014-12-04 | 2014-12-04 | 2015-02-16 | 2015-02-13 | 2015-03-02 | 2015-03-10 | 1 | 2015-03-31 | 2015-03-10 | 2015-05-22 | 2015-05-08 | 2015-06-12 | 2015-05-22 |  | 2015-06-19 | 2015-05-22 | NON_COMPLYING_FULL | 2015-04-01 | 2015-03-31 | 2015-06-08 | 2015-05-06 | 1 | 2015-06-15 | 2015-05-06 | 2015-05-13 | 2015-04-29 | 2015-06-03 | 2015-06-02 | 1 |  | 2015-06-10 | 2015-06-02 | [5 empty] | 2015-09-14 | 2015-08-25 | [5 empty] | 2015-09-23 | 2015-09-21 | [7 empty] | 2015-11-27 | 2015-11-30 |  |  |  |  | 08/05/15 - Colocation preliminary Approval received 20/05/15 - Final approval received. Need CD's and Project plan to proceed when ready 26/05/15 - Rev 0.2 ready to issue. Visionstream calling for coax. Ron to confirm Chorus build price and issue order. Rack to be ordered/supplied. 28/05/15 - 2D has approved Chorus build and requested for 1/8 start. Fibre 15/8 RFS 27/07/15 - Site awarded to Downers - Huawei to provide formal docs 04/08/15 - Downers to do Project Plan. Huawei to issue quote 09/09/15 - still waiting for Huawei to issue coax - URGENT Graham 16/09/15 - Racks in. Cable install when pole goes in 21/9/15 - Fibre live | TNZ | [9 empty] | 2015-11-20 | 2015-11-30 |  |  |  | 2015-09-23 | 2015-09-21 | BUILD |  | FALSE |  |  |  | 1065 Kaipara Coast Highway, Kaukapakap. |  |  | TXSITE |  |  |  | ROAMING |  |  | 2015-03-13 | 2015-07-03 | 2015-06-16 | 2015-04-23 | 2015-04-23 | 2015-04-23 | 2015-04-23 | 2015-08-14 | 2015-08-12 |  |  | 2015-02-13
0 | AKL | 49 | AKL-004-061 | Te Hana |  |  | Rodney District |  | TIER_9 | [22 empty] | FALSE
0 | AKL | 50 | AKL-004-062 | Matakana | AKL-004-062-A | Matakana | Rodney District | 25 | TIER_5 | ACTIVE | GF | DF | T2 20 RF |  | STACK_A | COSITE | 18 | 19.45 |  | -36.3632 | 174.7151 |  |  |  |  | Fibre Optic | AKL-005-088-A | FALSE | FALSE |  |  | FALSE |  | 2015-09-23 | 2015-09-28 | 2015-10-09 | 2015-09-28 | 2015-10-30 | 2015-10-20 | 2 | 2015-11-25 | 2015-11-24 | 2015-11-24 | 2015-11-18 | 2015-12-17 | 2016-01-27 |  | 2015-12-18 | 2016-02-10 | NON_COMPLYING_FULL | 2015-11-23 | 2015-11-24 | 2016-01-13 | 2015-12-16 | 2 | 2016-01-18 | 2015-12-16 | 2015-12-22 | 2015-12-18 | 2016-02-12 |  |  |  | 2016-02-16 | [6 empty] | 2016-03-14 |  | 2016-03-21 |  |  | 2016-03-31 |  | 2016-03-31 |  | 2016-03-14 |  | 2016-02-24 |  | 2016-01-29 | 2016-01-27 |  | 2016-04-15 | [5 empty] | 21 Oct: Fibre feasibility requested 21 Oct: RF letter requested for Planning application 3 Nov: Site Acq negotiating lease. Expect to conclude 20 Nov 17 Nov: RF & TX spec requested 18 Nov: Lease signed. Waiting on execution 2 Dec: Fibre order placed. ATN BoQ requested. Pole ordered 4 Dec: Fibre ordered 14 Dec: Antennas & pole ordered. 20 Jan: Antennas ordered. Need ETA. CD ordered. 25 Jan: Geotech survey completed. 27 Jan: Tender visit. 2 Feb: Geotech complete. CD's underway. Co-site lodged. Power capacity confirmed. Additional fuse ordered. | [10 empty] | 2016-04-08 |  |  |  |  | 2016-03-29 |  | BUILD | 2016-03-21 | FALSE |  | 2664421 | 6536116 | 948 Matakana Road |  |  | CELLSITE |  |  |  | ROAMING |  | 2016-01-14 |  | 2016-02-15 |  | 2015-10-21 | 2015-10-22 | 2015-12-11 | 2015-12-04 | 2016-02-24 |  |  |  | 2015-09-28
0 | AKL | 51 | AKL-004-063 | Kawau Island | AKL-004-063-A | Kawau Island | Rodney District | 25 | TIER_5 | ACTIVE | COLO | DU | T2 15 UF |  | STACK_A | COLO | 16.89 | 19 |  | -36.4173 | 174.834 | [6 empty] | FALSE | FALSE |  |  | FALSE |  | 2015-10-08 | 2015-08-10 | 2015-11-10 | 2015-11-13 | 2015-11-18 | 2015-11-23 | 2 | 2015-11-20 | 2015-11-25 | 2016-02-19 |  | 2016-03-15 |  |  | 2016-03-15 |  |  | 2016-03-15 |  | 2016-04-14 |  |  | 2016-04-15 |  | 2016-03-04 |  | 2016-03-11 | [10 empty] | 2016-04-25 |  | 2016-05-10 |  |  | 2016-05-13 |  | 2016-04-08 |  | 2016-05-04 |  | 2016-04-06 |  | 2016-02-24 |  |  | 2016-05-31 | [5 empty] | 19 Oct: VF confirmed U15 type monopole 27 Oct: Structural assessment complete. 0.6m dish capacity at Snells Beach as linking site. 4 Nov: Order PD's 11 Nov: PDRev0 issued for comment 29 Nov: PD Rev 1.1 issued 30 Nov: Co-lo sent to VF 2 Dec: Iwi & Planner visits organised for 9th Dec. 9 Dec: Iwi visit completed. 15 Dec: Co-lo application submitted. Power status queried with Steve. | VNZ | [9 empty] | 2016-05-20 | [6 empty] | BUILD | 2016-04-19 | FALSE |  | 2674963 | 6529887 | Smelting Works Bay |  |  | CELLSITE |  |  |  | ROAMING |  |  |  | 2016-02-26 | [5 empty] | 2016-03-16 |  |  |  | 2015-11-04
0 | AKL | 52 | AKL-004-064 | Wellsford South |  |  | Rodney District | 25 | TIER_9 | [22 empty] | FALSE | [60 empty] | New site having a basic configuration of U9/G9. The objective of this site is to provide coverage to a section of Motorway SH1 which is frequently visited by people during holidays. Another purpose is to provide continuous coverage between the two sites of Wellsford(004-022) and Kraacks Hill(004-016) Candidate options are: 1. VFNZ co-location 2. 20m greenfield pole within search ring Proposed design is to have 2 sectors with U9/G9 , but this may change after the caravan We may not need this site as Kraacks Hill may be able to provide the coverage at SH1. The Kraacks Hill site will be On-Air 16th Dec. Will confirm after drive test.
0 | AKL | 53 | AKL-004-065 | Puhoi Bridge | AKL-004-065-A | Puhoi Bridge GF | Rodney District | 22 | TIER_5 | ACTIVE | GF | DF | T2 20 RH |  | STACK_A | STANDALONE | 19.5 | 20 |  | -36.5333 | 174.6883 |  |  |  |  | Microwave | AKL-004-066-A | FALSE | FALSE |  |  | FALSE |  | 2015-12-21 | 2015-12-21 | 2015-12-21 | 2015-12-21 | 2016-02-01 | 2016-01-27 | 1 | 2016-02-08 | 2016-01-27 | 2016-03-18 |  | 2016-04-29 |  |  | 2016-04-29 |  | DISCRETIONARY_FULL | 2016-03-18 |  | 2016-06-30 |  |  | 2016-06-30 |  | 2016-03-21 |  | 2016-05-02 |  |  |  | 2016-05-09 | [6 empty] | 2016-08-08 |  | 2016-09-05 |  |  | 2016-09-19 | [10 empty] | 2016-10-17 | [5 empty] | 21/10/15 - VF data pack received - property is being sold, lease not being renewed This GF site is very risky - will required an Archaeological investigation and Heritage authority for RC which can take 3-4 months. Have requested Spark data pack for a back up site | [10 empty] | 2016-10-03 | [6 empty] | BUILD |  | FALSE |  | 2661645 | 6517287 | off Hibiscus Coast Highway |  |  | CELLSITE | WIPACTIVE |  |  | ROAMING |  |  |  | 2016-06-30 | [5 empty] | 2016-07-18 |  |  |  | 2015-12-21
0 | AKL | 54 | AKL-004-066 | Puhoi Straights | AKL-004-066-A | GF - smart pole | Rodney District | 22 | TIER_5 | ACTIVE | GF | DU | SP |  | STACK_A | COSITE | 12 | 12 |  | -36.4828 | 174.658 |  |  |  |  | Fibre Optic | AKL-005-088-A | FALSE | FALSE |  |  | FALSE |  | 2016-01-25 | 2016-01-25 | 2016-01-28 | 2016-01-26 | 2016-02-29 |  |  | 2016-03-07 |  | 2016-03-28 |  | 2016-05-09 |  |  | 2016-05-09 |  | DISCRETIONARY_FULL | 2016-04-04 |  | 2016-05-16 |  |  | 2016-05-16 |  | 2016-04-04 |  | 2016-05-09 |  |  |  | 2016-05-16 | [6 empty] | 2016-07-04 |  | 2016-08-08 |  |  | 2016-08-22 | [10 empty] | 2016-09-26 | [5 empty] | 21/10/15 - VF data pack recieved | [10 empty] | 2016-09-12 | [6 empty] | BUILD |  | FALSE |  | 2659038 | 6522945 | 16 Schollum Access Rd, Off SH1, Pohuehue, Auckland |  |  | CELLSITE | WIPACTIVE |  |  | ROAMING |  |  |  | 2016-05-16 |  | 2016-01-25 |  | 2016-04-11 |  | 2016-06-13 |  |  |  | 2016-01-26
0 | AKL | 55 | AKL-004-067 | Warkworth South | AKL-004-067-A | Warkworth South | Rodney District | 25 | TIER_5 | ACTIVE | COLO | DU | COLO |  | STACK_A | COLO | 15 | 15 |  | -36.4612 | 174.6534 |  |  |  |  | Fibre Optic | AKL-005-088-A | FALSE | FALSE |  |  | FALSE |  | 2015-11-30 | 2015-11-30 | 2015-12-14 | 2015-12-16 | 2016-01-20 | 2016-01-26 | 2 | 2016-01-22 | 2016-01-26 | 2016-03-15 |  | 2016-04-01 |  |  | 2016-04-01 |  |  | 2016-03-22 |  | 2016-04-19 |  |  | 2016-04-20 |  | 2016-04-19 |  | 2016-04-26 |  |  |  | 2016-04-29 | [6 empty] | 2016-05-09 |  | 2016-05-17 |  |  | 2016-05-19 |  | 2016-03-30 |  | 2016-03-25 |  | 2016-04-27 |  | 2016-04-06 |  |  | 2016-05-31 | [5 empty] | 22 Oct: RF search ring requested 5 Nov: Likely co-lo with VF but also need diversity. SDP requested 13 Nov: SDP received 17 Nov: Site to be caravanned in case Puhoi Straights not secured. 22 Dec: PD requested. 25 Jan: PD issued for final comments. Prepare co-lo application. 27 Jan: Co-lo lodged. PD issued. | VNZ | [9 empty] | 2016-05-26 |  |  |  |  | 2016-03-29 |  | BUILD | 2016-05-09 | FALSE |  | 2658672 | 6525348 | Cowan Bay Road Warkworth |  |  | CELLSITE |  |  |  | ROAMING |  |  |  | 2016-03-28 |  | 2015-12-02 | 2015-12-02 | 2016-01-22 | 2016-01-20 | 2016-04-11 |  |  |  | 2015-12-14
0 | AKL | 56 | AKL-005-001 |  | AKL-005-001-A | Devonport North | North Shore City |  | TIER_1_ALL | ACTIVE | RSR | A6 | P4A | green |  |  | 10 | 10 |  | -36.8246 | 174.7987 |  |  |  |  | Microwave | AKL-005-008-D | [5 empty] | 2009-05-13 | [5 empty] | 2007-10-10 | 5 |  | 2008-08-26 |  |  | 2008-02-28 | 2008-02-28 | 5 | 2008-02-28 | 2008-02-28 |  |  |  | 2008-09-30 |  |  | 2008-09-11 | 2008-09-11 |  | 2008-02-26 |  | 2008-03-25 | 4 | 5 | 2008-10-01 | 2008-10-01 | [6 empty] | 2008-09-24 | 2008-10-31 | 2008-10-31 |  | 2008-10-31 | 2008-10-20 | [8 empty] | 2009-03-13 | 2009-03-16 | 2009-03-13 |  |  |  |  | On Air |  | 2009-03-16 | [17 empty] | FALSE |  | 2670854 | 6484762 | Corner of Albert and Lake road Devonport North Shore |  |  | CELLSITE |  |  | 2014-09-05 | [5 empty] | 2008-09-16 | [8 empty] | 2007-09-19
0 | AKL | 57 | AKL-005-002 |  | AKL-005-002-D | Stanley Bay | North Shore City |  | TIER_1_ALL | ACTIVE | RSR | A6 | P4A | green |  |  | 9.6 | 9.6 |  | -36.8232 | 174.7893 |  |  |  |  | Microwave | AKL-005-008-D | [5 empty] | 2009-05-12 | [5 empty] | 2007-10-09 | 7 | 2008-12-16 | 2008-12-16 |  |  | 2008-02-28 | 2008-02-28 | 3 | 2009-02-19 | 2009-03-12 |  |  |  | 2009-01-20 |  |  | 2008-12-16 | 2008-12-16 |  | 2008-01-21 |  | 2008-03-25 | 4 | 7 | 2009-01-12 | 2009-01-12 | 2009-01-19 | [5 empty] | 2009-02-03 | 2009-02-16 | 2009-02-16 |  | 2009-02-16 | 2009-02-16 | [8 empty] | 2009-04-02 | 2009-04-15 | 2009-04-02 |  |  |  |  | (Mar27 DJ) DMR link to 5-008 Birkenhead Central cmplt. Dep on 2nd LL at 5-008. Fcst SOA Apr15 |  | 2009-04-15 | [5 empty] | 2009-01-19 | [11 empty] | FALSE |  | 2670020 | 6484940 | Streetlight on Jim Titchener Parade Stanley Bay North Shore (light pole approx 20 to the East of the Navy Gate House) |  |  | CELLSITE |  |  | 2014-09-05 | [5 empty] | 2009-01-16 | [8 empty] | 2007-09-18
0 | AKL | 58 | AKL-005-003 |  | AKL-005-003-A | Devonport South | North Shore City |  | TIER_1_ALL | ACTIVE | RT | A6 | NOPOLE | grey |  |  | 13.8 | 13.8 |  | -36.8321 | 174.7967 |  |  |  |  | Microwave | AKL-007-112-A | [5 empty] | 2009-05-08 | [5 empty] | 2007-08-01 | 5 |  | 2009-05-12 |  |  | 2007-12-19 | 2007-12-19 | 1 | 2007-12-19 | 2007-12-19 |  |  |  | 2008-08-31 |  |  | 2008-08-27 | 2008-08-27 |  | 2007-09-21 |  | 2008-02-08 | 1 | 1 | 2008-02-08 | 2008-02-08 | [6 empty] | 2008-09-15 | 2008-10-03 | 2008-09-25 |  | 2008-10-20 | 2008-10-10 | [8 empty] | 2008-11-25 | 2008-12-03 | 2008-11-25 |  |  |  |  | On Air |  | 2008-11-19 | [17 empty] | FALSE |  | 2670663 | 6483939 | Esplanade Hotel Devonport Central 1 Victoria Rd Devonport North Shore City |  |  | CELLSITE |  |  | 2014-09-05 | [5 empty] | 2008-09-11 | [8 empty] | 2007-06-11
0 | AKL | 59 | AKL-005-004 |  | AKL-005-004-H | Belmont | North Shore City |  | TIER_1_ALL | ACTIVE | GF | Ab6 | P4F | grey |  | COSITE |  |  |  | -36.8078 | 174.7903 |  |  |  |  | Leased Line | AKL-007-106-A | [6 empty] | 2009-09-18 | 2009-09-18 |  |  |  | 2009-10-21 | 4 | 2009-11-25 | 2010-05-06 |  |  | 2009-12-18 | 2009-10-30 | 2 | 2010-02-17 | 2010-02-16 | NON_COMPLYING_LIMITED | 2009-12-01 | 2010-03-22 | 2010-04-19 | 2010-04-20 | 3 | 2010-05-31 | 2010-05-27 | 2009-11-30 | 2009-12-02 |  | 2009-11-11 | 3 | 3 | 2009-12-11 | 2010-01-27 | 2009-12-15 |  |  |  |  | 2010-05-03 | 2010-05-04 | 2010-06-04 | 2010-06-04 |  | 2010-06-08 | 2010-06-04 | [8 empty] | 2010-06-11 | 2010-06-11 | 2010-06-11 |  |  |  |  | CO-SITE approved. Council recommend tree removal for tenants, they preparing report as RC will be required, no time frames given. New pole location required due to VF LOS. Lease variation required for new pole location. Will swap plans at Council for RC. Site meeting with VF 8/12, they will do calcs to determine the size of their Fresnel zone and whether we'll interfere or not. No response from VF yet, Barbara chasing. No BC required. Bevan getting Parks approval, also include trimming if possible. Drawings revised for trees and pathway diversion. LOS pole test completed and LOS clear, cosite approved. Tree consent notified by council commissioners, we'll therefore continue with our consent asking for parks permission to trim tree. Beavn chasing parks for landowner and arborist approvals. Council now require combined approval, report due out this week (by 26.03). 14/4 - do not need consent to trim trees. Commenced 3 May. Foundation excavation showed pipes. Need to move pole closer to fence. Requ neighbour consent - await 12/5 - variation on lease required. No longer need to move the mast. Problem with underground pipes resolved.Recommenced with work, estimate completion first week in June 2010. 02/02/2010 Mast was erected today. |  | 2010-06-11 |  |  |  |  | 2009-12-24 | 2009-12-15 | [11 empty] | FALSE |  | 2670146 | 6486651 | 150 Lake Road Belmont North Shore |  |  | CELLSITE |  |  | 2014-09-05 |  |  |  |  | 2010-05-03 | 2010-05-04 | [8 empty] | 2009-09-21
0 | AKL | 60 | AKL-005-005 |  | AKL-005-005-B | Hauraki Cnr | North Shore City |  | TIER_1_ALL | ACTIVE | RSR | A6 | P4A | green |  |  | 15 | 15 |  | -36.7977 | 174.7806 |  |  |  |  | Microwave | AKL-005-015-B | [5 empty] | 2009-05-12 | [5 empty] | 2007-10-04 | 2 |  | 2008-07-07 |  |  | 2008-02-28 | 2008-02-28 | 2 | 2008-02-28 | 2008-02-28 |  |  |  | 2008-08-31 |  |  | 2008-08-27 | 2008-08-27 |  | 2008-02-26 |  | 2008-03-28 | 2 | 2 | 2008-07-17 | 2008-07-17 | [6 empty] | 2008-09-10 | 2008-09-21 | 2008-09-21 |  | 2008-09-26 | 2008-09-23 | [8 empty] | 2008-11-25 | 2008-12-31 | 2008-11-25 |  |  |  |  | On Air | [19 empty] | FALSE |  | 2669306 | 6487786 | Pole outside 319 Lake Road Hauraki Corner North Shore |  |  | CELLSITE |  |  | 2014-09-05 | [5 empty] | 2008-09-10 | [8 empty] | 2007-09-19
0 | AKL | 61 | AKL-005-006 |  | AKL-005-006-B | Harbour Bridge North | North Shore City |  | TIER_1_ALL | ACTIVE | COLO | A6 | COLO | grey |  | COSITE | 12 | 12 |  | -36.8227 | 174.7507 |  |  |  |  | Leased Line | AKL-007-106-A | [11 empty] | 2007-11-16 | 5 | 2008-10-22 | 2008-10-22 |  |  | 2009-04-01 | 2009-03-30 | 4 | 2009-04-06 | 2009-03-30 |  |  |  | 2008-05-02 |  |  | 2009-03-06 | 2009-02-27 |  | 2008-05-23 |  | 2008-07-29 | 4 | 5 | 2009-02-03 | 2009-02-03 | [5 empty] | 2009-04-02 | 2009-04-02 | 2009-04-24 | 2009-04-24 |  | 2009-05-15 | 2009-05-13 | [8 empty] | 2009-05-30 | 2009-06-05 | 2009-05-30 |  |  |  |  | Build proceeding Antenna swap outs completed 09/07/13. |  | 2009-06-05 | [17 empty] | FALSE |  | 2666580 | 6485070 | TNZ Co-location, Sulphur Beach Rd, Northcote Point, North Shore, Auckland |  |  | CELLSITE |  |  | 2014-09-05 |  |  |  |  | 2009-04-02 | 2009-04-02 | [8 empty] | 2007-11-09
0 | AKL | 62 | AKL-005-007 | Birkenhead South | AKL-005-007-A | Birkenhead South | North Shore City | 3 | TIER_1_INFILL | ACTIVE | RT | B6 | NOPOLE | grey | INLINE | COSITE | 13 | 13.5 |  | -36.8174 | 174.7323 |  |  |  |  | Microwave | AKL-007-129-B | FALSE | FALSE |  |  | FALSE |  |  | 2011-02-17 |  | 2011-02-17 |  | 2008-10-20 | 3 | 2009-09-02 | 2009-08-31 |  | 2009-12-17 | 2009-12-18 | 2009-12-17 | 3 | 2009-12-18 | 2009-12-18 | DISCRETIONARY_RESTRICT | 2009-12-02 | 2008-08-21 | 2009-12-23 | 2009-12-22 | 3 | 2010-01-29 | 2009-12-22 |  |  |  | 2009-12-23 | 2 | 3 |  | 2011-04-14 | 2011-09-14 |  |  |  |  | 2011-08-01 | 2011-08-01 | 2011-09-11 | 2011-09-11 | 2011-09-03 | 2011-09-18 | 2011-09-14 | [8 empty] | 2011-09-19 | 2011-09-19 | 2011-09-19 | 2011-09-30 | 2011-09-30 | 2011-12-29 | 2012-03-22 | CO-SITE's Approved. No BC required. 01.07 Contractor re visited site yesterday & is to forward a quote to build. Quotes have been received. They have been given to Dawie and Mike. Await approval. ON HOLD UNTIL FURTHER NOTICE. Barbara 07.02.2011 - WO2 issued. Construction drawings issued by Huawei, circulated and back for minor amendments. PAC dates moved to 01 Sept to accomodate Kingsland Build in time for RWC 2011 |  | 2011-09-15 | 2011-08-22 | 2011-08-22 | 2011-08-22 | 2011-08-22 | 2011-09-14 | 2011-09-14 | 2011-08-24 | 2011-09-01 | [8 empty] | 2011-09-03 | FALSE |  | 2664952 | 6485686 | 88 Hinemoa Street Birkenhead South Auckland |  |  | CELLSITE |  |  | 2014-09-05 | [12 empty] | 2011-09-21 | 2011-09-20 | 2008-09-19
0 | AKL | 63 | AKL-005-008 |  | AKL-005-008-D | Birkenhead Central | North Shore City |  | TIER_1_ALL | ACTIVE | RT | B6 | NOPOLE | grey |  |  | 13 | 13 |  | -36.811 | 174.7245 |  |  |  |  | Microwave, Leased Line | AKL-007-065-D, AKL-007-106-A | [5 empty] | 2009-05-13 | [5 empty] | 2007-10-05 | 5 |  | 2009-06-19 |  |  | 2008-04-30 | 2008-06-13 | 3 | 2008-04-30 | 2008-06-13 |  |  |  | 2008-02-05 |  |  | 2008-07-04 | 2008-07-04 |  | 2007-11-06 |  | 2008-02-20 | 2 | 3 | 2008-10-01 | 2008-10-01 | [6 empty] | 2008-08-29 | 2008-10-03 | 2008-10-03 |  | 2009-02-11 | 2009-02-11 | [8 empty] | 2009-03-13 | 2009-03-16 | 2009-03-13 |  |  |  |  | On Air |  | 2009-03-16 | [17 empty] | FALSE |  | 2664268 | 6486409 | Highbury Mall 1-16 Hammond Pl Birkenhead North Shore City |  |  | CELLSITE |  |  | 2014-09-05 | [5 empty] | 2008-06-25 | [8 empty] | 2007-08-30
0 | AKL | 64 | AKL-005-009 |  | AKL-005-009-C | Birkenhead West | North Shore City |  | TIER_1_ALL | ACTIVE | RT | B6 | NOPOLE | grey |  |  | 8.8 | 8.8 |  | -36.8114 | 174.713 |  |  |  |  | Microwave, Microwave | AKL-007-087-A, AKL-007-087-A | [5 empty] | 2009-05-12, 2009-05-11 | [5 empty] | 2007-12-20 | 6 | 2009-02-24 | 2009-02-24 |  |  | 2008-02-13 | 2008-02-13 | 1 | 2008-03-16 | 2008-02-13 |  |  |  | 2008-09-30 |  |  | 2009-02-27 | 2009-01-28 |  | 2008-01-22 |  | 2008-02-28 | 2 | 4 | 2008-12-23 | 2008-12-23 | [6 empty] | 2009-01-20 | 2009-02-23 | 2009-02-20 |  | 2009-03-20 | 2009-03-20 | [8 empty] | 2009-03-23 | 2009-03-27 | 2009-03-23 |  |  |  |  | On Air |  | 2009-03-27 | [17 empty] | FALSE |  | 2663245 | 6486384 | 174 Mokia Rd Birkenhead North Shore City Post Code |  |  | CELLSITE |  |  | 2014-09-05 |  |  |  |  | 2008-12-24 | 2009-01-14 | [8 empty] | 2008-02-01
0 | AKL | 65 | AKL-005-010 |  | AKL-005-010-A | Kauri Park | North Shore City |  | TIER_1_ALL | ACTIVE | RSR | A6 | P4A | green |  |  | 12 | 12 |  | -36.8062 | 174.7064 |  |  |  |  | Microwave | AKL-005-015-B | [5 empty] | 2009-05-12 | [5 empty] | 2007-10-12 | 4 |  | 2008-08-13 |  |  | 2008-02-29 | 2008-02-25 | 4 | 2008-02-29 | 2008-02-25 |  |  |  | 2008-08-31 |  |  | 2008-08-27 | 2008-08-27 |  | 2008-06-03 |  | 2008-06-24 | 2 | 4 | 2008-09-11 | 2008-09-11 | [6 empty] | 2008-10-13 | 2008-10-29 | 2008-10-31 |  | 2008-11-12 | 2008-11-12 | [8 empty] | 2008-11-26 | 2008-12-03 | 2008-11-26 |  |  |  |  | On Air |  | 2008-11-19 | [17 empty] | FALSE |  | 2662668 | 6486974 | Corner of Verran and Verbena roads outside Mobil Garage Birkenhead Auckland |  |  | CELLSITE |  |  | 2014-09-05 | [5 empty] | 2008-09-16 | [8 empty] | 2007-09-04
0 | AKL | 66 | AKL-005-011 |  | AKL-005-011-H | Northcote Onewa | North Shore City |  | TIER_1_ALL | ACTIVE | GF | A6 | SP | grey |  |  | 18.8 | 18.8 |  | -36.8077 | 174.7412 |  |  |  |  | Leased Line | AKL-007-106-A | [11 empty] | 2009-04-01 | 2 | 2009-03-30 | 2009-05-06 |  |  | 2009-04-14 | 2009-04-07 |  | 2009-05-29 | 2009-06-03 |  | 2009-04-03 |  | 2009-05-15 |  |  | 2009-05-15 | 2009-04-27 | 2009-04-14 | 2009-04-01 |  | 2009-06-05 | 1 | 1 | 2009-06-12 | 2009-06-05 | 2009-06-30 |  |  |  |  | 2009-06-22 | 2009-06-22 | 2009-07-24 | 2009-07-24 |  | 2009-07-27 | 2009-07-27 | [8 empty] | 2009-08-03 | 2009-08-10 | 2009-08-03 |  |  |  |  | On Air |  | 2009-08-10 |  |  |  |  | 2009-06-26 | 2009-06-30 | [11 empty] | FALSE |  | 2665764 | 6486744 | 31 Woodside Ave Northcote |  |  | CELLSITE |  |  | 2014-09-05 |  |  |  |  | 2009-06-22 | 2009-06-22 | [8 empty] | 2009-03-16
0 | AKL | 67 | AKL-005-012 |  | AKL-005-012-A | Glenfield Central | North Shore City |  | TIER_1_ALL | ACTIVE | RSR | A6 | P4A | green |  |  | 12.3 | 12.3 |  | -36.7777 | 174.723 |  |  |  |  | Microwave, Leased Line | AKL-005-049-A, AKL-007-106-A | [5 empty] | 2009-05-11 | [5 empty] | 2007-10-19 | 6 | 2008-10-16 | 2009-10-16 |  |  | 2008-02-28 | 2008-02-28 | 1 | 2008-02-28 | 2008-02-28 |  |  |  | 2008-12-03 |  |  | 2008-12-03 | 2008-12-03 |  | 2008-02-26 |  | 2009-01-08 | 1 | 3 | 2009-01-08 | 2009-01-08 | 2008-11-11 | [5 empty] | 2009-02-12 | 2009-02-27 | 2009-02-27 |  | 2009-02-28 | 2009-02-27 | [8 empty] | 2009-05-07 | 2009-05-25 | 2009-05-07 |  |  |  |  | On Air |  | 2009-05-25 | [5 empty] | 2008-11-11 | [11 empty] | FALSE |  | 2664209 | 6490114 | Streetlight pole outside TNZ Switch opposite 477 Glenfield Rd Glenfield North Shore |  |  | CELLSITE |  |  | 2014-09-05 | [5 empty] | 2009-02-03 | [8 empty] | 2007-09-19
0 | AKL | 68 | AKL-005-013 |  | AKL-005-013-A | Beach Haven North | North Shore City |  | TIER_1_ALL | ACTIVE | RSR | A6 | P4A | green |  |  | 12 | 12 |  | -36.7881 | 174.6994 |  |  |  |  | Leased Line | AKL-007-106-A | [11 empty] | 2007-10-12 | 1 | 2007-10-12 | 2007-10-12 |  |  | 2008-02-28 | 2008-02-28 | 1 | 2008-02-28 | 2008-02-28 |  |  |  | 2008-07-15 |  |  | 2008-06-12 | 2008-06-12 |  | 2008-02-26 |  | 2008-03-25 | 1 | 1 | 2008-03-25 | 2008-03-25 | [6 empty] | 2008-07-22 | 2008-08-19 | 2008-08-19 |  | 2008-09-08 | 2008-08-29 | [8 empty] | 2009-03-13 | 2009-03-17 | 2009-03-13 |  |  |  |  | (Mar13 DJ) Site On Air |  | 2009-03-17 | [17 empty] | FALSE |  | 2662084 | 6488999 | Streetlight on corner of Birkdale and Beach Haven roads Outside Gardian at Beach Haven Beach Haven North Shore |  |  | CELLSITE |  |  | 2014-09-05 | [5 empty] | 2008-06-13 | [8 empty] | 2007-09-19
0 | AKL | 69 | AKL-005-014 | Northcote | AKL-005-014-C | Northcote, LPR TNZ Transmission Yard | North Shore City |  | TIER_1_ALL | ACTIVE | RSR | A6 | P4F | green | [5 empty] | -36.7924 | 174.7484 |  |  |  |  | Microwave | AKL-007-112-A | [5 empty] | 2011-04-28 | [5 empty] | 2008-09-05 | 7 | 2009-09-30 | 2009-09-30 |  |  | 2009-04-17 | 2009-04-24 |  | 2009-11-13 | 2009-11-23 |  | 2009-06-05 |  | 2009-08-14 |  |  | 2009-11-06 | 2009-11-04 | 2009-03-18 | 2009-03-26 |  | 2009-03-26 | 4 |  | 2009-10-08 | 2009-10-05 | 2009-08-14 |  |  |  |  | 2009-11-16 | 2009-11-16 | 2009-12-04 | 2009-12-03 |  | 2009-12-04 | 2009-12-03 | [8 empty] | 2009-12-03 | 2009-12-09 | 2009-12-03 |  |  |  |  | On Air |  | 2009-12-09 |  |  |  |  | 2009-08-21 | 2009-08-14 | [11 empty] | FALSE |  | 2666443 | 6488434 | Telecom NZ Transmission Yard, Cnr Akoranga Dr & Northcote Rd, Northcote, North Shore, Auckland |  |  | CELLSITE |  |  | 2014-09-05 | [5 empty] | 2009-11-16 | [8 empty] | 2008-08-12
0 | AKL | 70 | AKL-005-015 |  | AKL-005-015-B | Takapuna | North Shore City |  | TIER_1_ALL | ACTIVE | RT | A6 | NOPOLE | grey |  |  | 43 | 43 |  | -36.7904 | 174.7718 |  |  |  |  | Microwave | AKL-007-112-A | [5 empty] | 2009-05-13 | [5 empty] | 2007-09-25 | 6 |  | 2015-09-08 |  |  | 2008-04-30 | 2008-05-21 | 4 | 2008-04-30 | 2008-05-21 |  |  |  | 2008-07-15 |  |  | 2008-06-19 | 2008-06-19 |  | 2007-11-06 |  | 2008-01-18 | 2 | 5 | 2008-01-18 | 2009-01-01 | [6 empty] | 2008-07-10 | 2008-08-29 | 2008-08-29 |  | 2008-10-20 | 2008-10-20 | [8 empty] | 2008-11-17 | 2008-12-03 | 2008-11-17 |  |  |  |  | None |  | 2008-11-19 | [17 empty] | FALSE |  | 2668533 | 6488612 | AIA Building 5-7 Byron Ave Takapuna North Shore City Post Code |  |  | CELLSITE |  |  | 2014-09-05 | [5 empty] | 2008-06-20 | [8 empty] | 2007-08-22
0 | AKL | 71 | AKL-005-016 |  | AKL-005-016-D | Lake Pupuke | North Shore City |  | TIER_1_ALL | ACTIVE | RT | B6 | NOPOLE | grey |  |  | 19.5 | 19.5 |  | -36.7876 | 174.7583 |  |  |  |  | Microwave | AKL-005-015-B | [5 empty] | 2009-05-15 | [5 empty] | 2008-11-19 | 5 | 2009-04-17 | 2011-11-14 |  |  | 2009-06-05 | 2009-06-17 | 2 | 2009-08-21 | 2009-08-24 |  | 2008-12-12 |  | 2009-02-28 |  |  | 2009-02-28 | 2009-01-30 | 2009-06-19 | 2009-05-26 | 2009-05-08 | 2009-06-29 | 2 | 4 | 2009-07-03 | 2009-07-27 | [5 empty] | 2009-07-30 | 2009-07-30 | 2009-09-09 | 2009-09-09 |  | 2009-09-16 | 2009-09-16 | [8 empty] | 2009-09-21 | 2009-09-21 | 2009-09-21 |  |  |  |  | On Air |  | 2009-09-21 | [17 empty] | FALSE |  | 2667340 | 6488950 | Waimarie Building, 44 Taharoto Rd, Smales Farm, North Shore, Auckland |  |  | CELLSITE |  |  | 2014-09-05 |  |  |  |  | 2009-07-30 | 2009-07-30 | [8 empty] | 2008-09-19
0 | AKL | 72 | AKL-005-017 |  | AKL-005-017-F | Milford | North Shore City |  | TIER_1_ALL | ACTIVE | RSR | A6 | P4A | green |  |  | 12.6 | 12.6 |  | -36.7738 | 174.7697 |  |  |  |  | Leased Line | AKL-007-106-A | [11 empty] | 2008-06-27 | 4 | 2009-03-23 | 2009-03-19 |  |  | 2009-04-30 | 2009-04-24 |  | 2009-05-08 | 2009-09-15 |  |  |  | 2009-03-20 |  |  | 2009-04-15 | 2009-04-24 |  | 2008-09-26 |  | 2008-10-09 | 3 | 4 | 2009-04-03 | 2009-04-01 | 2009-02-17 |  |  |  |  | 2009-05-07 | 2009-05-04 | 2009-05-20 | 2009-05-15 |  | 2009-05-18 | 2009-05-15 | [8 empty] | 2009-05-29 | 2009-05-29 | 2009-05-29 |  |  |  |  | Build has commenced at this site. On Track. (May20 DJ) waiting leased line delivery May29 > SOA!! |  | 2009-05-29 | [5 empty] | 2009-02-17 | [11 empty] | FALSE |  | 2668389 | 6490455 | Cnr Kitchener & Saltburn Rds, Milford, North Shore, Auckland |  |  | CELLSITE |  |  | 2014-09-05 |  |  |  |  | 2009-05-07 | 2009-05-04 | [8 empty] | 2008-06-13
0 | AKL | 73 | AKL-005-018 |  | AKL-005-018-A | Greenhithe Central | North Shore City |  | TIER_1_ALL | ACTIVE | RSR | A | P4A | green |  |  | 12 | 12 |  | -36.7767 | 174.6695 |  |  |  |  | Microwave | AKL-005-023-G | [5 empty] | 2009-05-12 | [5 empty] | 2007-10-12 | 1 |  | 2007-10-12 |  |  | 2008-02-28 | 2008-02-28 | 1 | 2008-02-28 | 2008-02-28 |  |  |  | 2008-11-30 |  |  | 2008-11-14 | 2008-11-14 |  | 2008-02-26 |  | 2008-03-25 | 1 | 1 | 2008-03-25 | 2008-03-25 | [6 empty] | 2008-12-04 | 2008-12-19 | 2008-12-18 |  | 2008-12-19 | 2008-12-23 | [8 empty] | 2009-02-13 | 2009-02-18 | 2009-02-13 |  |  |  |  | On Air |  | 2009-02-18 | [17 empty] | FALSE |  | 2659440 | 6490317 | Corner of Greenhithe & Rame Rds, Greenhithe, North Shore, Auckland |  |  | CELLSITE |  |  | 2015-12-10 | [5 empty] | 2008-12-02 | [8 empty] | 2007-09-19
0 | AKL | 74 | AKL-005-019 |  | AKL-005-019-C | Greenhithe South | North Shore City |  | TIER_1_ALL | ACTIVE | RSR | A | P4A | green |  |  | 14.2 | 14.2 |  | -36.7809 | 174.6783 |  |  |  |  | Microwave, Leased Line | AKL-006-028-D, AKL-007-106-A | [5 empty] | 2011-04-28 | [5 empty] | 2008-11-27 | 1 | 2008-11-27 | 2008-11-27 |  |  | 2009-03-13 | 2009-02-20 |  | 2009-03-30 | 2009-03-27 |  | 2008-12-24 |  | 2009-05-15 |  |  | 2009-05-15 | 2009-05-14 | 2008-12-22 | 2009-01-08 |  | 2009-03-03 | 2 | 1 | 2009-04-16 | 2009-04-17 | 2009-04-21 |  |  |  |  | 2009-05-18 | 2009-05-18 | 2009-06-12 | 2009-06-12 |  | 2009-06-16 | 2009-06-16 | [8 empty] | 2009-06-28 | 2009-06-28 | 2009-06-28 |  |  |  |  | (Jun03 DJ) On track SOA Jun26. (Jun10 DJ) TI and LL delayed but holding SOA Jun26. (Jun18 DJ) still holding SOA Jun26. (Jun24 DJ) on track SOA Jun26. |  | 2009-06-28 |  |  |  |  | 2009-04-22 | 2009-04-21 | [11 empty] | FALSE |  | 2660210 | 6489830 | Adjacent to 2 William Pitcher Place, Greenhithe, North Shore, Auckland |  |  | CELLSITE |  |  | 2015-12-10 |  |  |  |  | 2009-05-18 | 2009-05-18 | [8 empty] | 2008-10-10
0 | AKL | 75 | AKL-005-020 |  | AKL-005-020-C | Northcote West | North Shore City |  | TIER_1_ALL | ACTIVE | RSR | A6 | P4A | grey |  |  | 12.7 | 12.7 |  | -36.799 | 174.7235 |  |  |  |  | Microwave | AKL-005-015-B | [5 empty] | 2009-05-11 | [5 empty] | 2008-09-11 | 4 | 2009-06-10 | 2009-06-10 |  |  | 2009-04-30 | 2009-04-24 |  | 2009-05-08 | 2009-06-23 |  |  |  | 2009-01-30 |  |  | 2009-01-19 | 2009-01-19 | 2009-01-30 | 2009-01-21 |  | 2009-02-12 | 3 | 4 | 2009-06-10 | 2009-06-10 | 2009-05-04 |  |  |  |  | 2009-06-15 | 2009-06-15 | 2009-07-03 | 2009-07-02 |  | 2009-07-10 | 2009-07-10 | [8 empty] | 2009-07-20 | 2009-07-22 | 2009-07-20 |  |  |  |  | On Air |  | 2009-07-22 |  |  |  |  | 2009-05-01 | 2009-05-04 | [11 empty] | FALSE |  | 2664210 | 6487750 | Lightpole Cnr Eskdale & Glenfield Rd First pole heading north on cemetry side Glenfield Auckland |  |  | CELLSITE |  |  | 2014-09-05 |  |  |  |  | 2009-06-15 | 2009-06-15 | [8 empty] | 2008-08-12
0 | AKL | 76 | AKL-005-021 |  | AKL-005-021-D | Wairau South | North Shore City |  | TIER_1_ALL | ACTIVE | GF | A6 | P1 | grey |  |  | 15 | 15 |  | -36.7819 | 174.7401 |  |  |  |  | Microwave | AKL-005-015-B | [5 empty] | 2009-05-12 | [5 empty] | 2008-04-04 | 2 |  | 2008-04-11 |  |  | 2008-04-29 | 2008-04-29 | 2 | 2008-04-29 | 2008-04-29 | [6 empty] | 2008-05-26 | 2008-05-26 |  | 2008-04-21 |  | 2008-05-28 | 1 | 2 | 2008-05-28 | 2008-05-28 | [6 empty] | 2008-06-25 | 2008-06-30 | 2008-07-14 |  | 2008-08-08 | 2008-08-08 | [8 empty] | 2008-11-14 |  | 2008-11-14 |  |  |  |  | On Air | [19 empty] | FALSE |  | 2665725 | 6489611 | 49 Porana Road Sunnybrae Auckland |  |  | CELLSITE |  |  | 2014-09-05 | [5 empty] | 2008-05-29 | [8 empty] | 2008-02-27
0 | AKL | 77 | AKL-005-022 | Paremoremo | AKL-005-022-J | Paremoremo GF | North Shore City | 3 | TIER_3 | ACTIVE | GF | DU | P1 |  | INLINE | STANDALONE |  | 15 |  | -36.7598 | 174.6495 |  | 2012-06-01 |  |  | Microwave | AKL-006-028-D | FALSE | FALSE |  |  | FALSE |  | 2012-07-10 | 2012-07-10 | 2012-07-17 | 2012-07-17 | 2012-08-23 | 2012-08-22 | 3 | 2012-08-23 | 2015-05-12 | 2012-09-13 | 2012-09-10 | 2012-11-16 | 2012-11-19 | 2 | 2012-11-23 | 2012-11-19 | DISCRETIONARY_RESTRICT | 2012-11-19 | 2012-11-15 | 2013-01-25 | 2013-01-18 | 2 | 2013-01-28 | 2013-01-18 |  |  | 2013-01-24 | 2013-01-29 | 1 |  | 2013-01-24 | 2013-01-29 | 2013-02-11 |  |  | 2013-01-21 |  | 2013-02-21 | 2013-02-20 | 2013-03-19 | 2013-03-19 | 2013-03-15 | 2013-03-26 | 2013-03-26 | [8 empty] | 2013-03-28 | 2013-04-09 | 2013-04-11 | 2013-04-15 | 2013-04-15 | 2013-08-31 | 2013-09-20 |  |  | 2013-03-28 | 2013-02-05 | 2013-02-05 | 2013-02-04 | 2013-02-04 | 2013-02-11 | 2013-02-11 | 2013-03-22 | 2013-03-22 | 2013-03-26 | 2013-04-02 |  |  | TIER_1_INFILL |  |  | BUILD | 2013-03-15 | TRUE | 2013-01-22 | 2657690 | 6492222 | 130 Merewhira Road Opposite VNZ site |  |  | CELLSITE | [15 empty] | 2013-04-02 | 2013-04-02
0 | AKL | 78 | AKL-005-023 |  | AKL-005-023-G | North Harbour | North Shore City |  | TIER_1_ALL | ACTIVE | RSR | A6 | P4A | green |  |  | 12 | 12 |  | -36.7567 | 174.7029 |  |  |  |  | Microwave, Leased Line | AKL-005-027-F, AKL-007-106-A | [5 empty] | 2009-05-15 | [5 empty] | 2007-10-19 | 4 | 2008-08-11 | 2009-10-16 |  |  | 2008-02-28 | 2008-02-28 | 3 | 2008-02-28 | 2008-02-28 |  |  |  | 2008-07-12 |  |  | 2008-08-15 | 2008-08-15 |  | 2008-03-11 |  | 2008-04-30 | 3 | 3 | 2008-08-12 | 2008-08-12 | [6 empty] | 2008-07-18 | 2008-08-25 | 2008-08-15 |  | 2008-09-12 | 2008-09-04 | [8 empty] | 2009-02-13 | 2009-02-18 | 2009-02-13 |  |  |  |  | Site On Air |  | 2009-02-18 | [17 empty] | FALSE |  | 2662462 | 6492474 | Pole ouside 173 Albany Highway Albany North Shore Auckland |  |  | CELLSITE |  |  | 2014-09-05 | [5 empty] | 2008-06-11 | [8 empty] | 2007-09-20
0 | AKL | 79 | AKL-005-024 |  | AKL-005-024-E | Wairau Park | North Shore City |  | TIER_1_ALL | ACTIVE | RT | B6 | NOPOLE | grey |  |  | 14 | 14 |  | -36.7693 | 174.7357 |  |  |  |  | Microwave | AKL-005-025-A | [5 empty] | 2009-05-12 | [5 empty] | 2007-08-10 | 3 | 2009-04-02 | 2009-04-01 |  |  | 2008-03-04 | 2008-03-04 | 2 | 2008-03-04 | 2008-03-04 |  |  |  | 2008-01-18 |  |  | 2008-01-18 | 2008-01-18 |  | 2007-11-08 |  | 2008-02-21 | 2 | 2 | 2008-04-29 | 2008-04-29 | [6 empty] | 2008-05-19 | 2008-05-29 | 2008-05-29 |  | 2008-06-28 | 2008-07-08 | [8 empty] | 2009-02-10 | 2009-02-27 | 2009-02-11 |  |  |  |  | Site On Air |  | 2009-02-27 | [17 empty] | FALSE |  | 2665361 | 6491014 | 205 Wairau Road Glenfield North Shore City |  |  | CELLSITE |  |  | 2014-09-05 | [5 empty] | 2008-04-30 | [8 empty] | 2007-07-09
0 | AKL | 80 | AKL-005-025 |  | AKL-005-025-A | Wairau North | North Shore City |  | TIER_1_ALL | ACTIVE | GF | A6 | P2 | grey |  |  | 15 | 15 |  | -36.7762 | 174.7386 |  |  |  |  | Microwave | AKL-005-015-B | [5 empty] | 2009-05-12 | [5 empty] | 2007-12-13 | 2 |  | 2008-05-21 |  |  | 2007-12-18 | 2007-12-18 | 1 | 2007-12-18 | 2007-12-18 |  |  |  | 2008-06-30 |  |  | 2008-06-19 | 2008-06-19 |  | 2007-11-06 |  | 2008-03-31 | 1 | 2 | 2008-03-31 | 2008-03-31 | [6 empty] | 2008-07-07 | 2008-08-15 | 2008-08-11 |  | 2008-08-22 | 2008-08-22 | [8 empty] | 2008-11-26 | 2008-12-04 | 2008-11-26 |  |  |  |  | On Air |  | 2008-11-20 | [17 empty] | FALSE |  | 2665602 | 6490244 | 30 Poland Rd North Shore Auckland |  |  | CELLSITE |  |  | 2014-09-05 | [5 empty] | 2008-06-24 | [8 empty] | 2007-10-31
0 | AKL | 81 | AKL-005-026 |  | AKL-005-026-C | Castor Bay | North Shore City |  | TIER_1_ALL | ACTIVE | RSR | D | P4C | green |  |  | 12.3 | 12.3 |  | -36.7552 | 174.7642 |  |  |  |  | Leased Line | AKL-007-106-A | [11 empty] | 2008-07-09 | 3 | 2008-12-09 | 2008-12-09 |  |  | 2009-04-30 | 2009-04-24 |  | 2009-05-08 | 2009-09-15 |  | 2009-01-26 |  | 2009-03-30 |  |  | 2009-03-30 | 2009-03-23 | 2008-12-12 | 2008-12-23 |  | 2009-02-19 | 2 | 3 | 2009-04-01 | 2009-04-01 | 2009-04-30 |  |  |  |  | 2009-05-18 | 2009-05-18 | 2009-05-29 | 2009-05-29 |  | 2009-06-05 | 2009-06-05 | [8 empty] | 2009-06-12 | 2009-06-16 | 2009-06-12 |  |  |  |  | (May28 DJ) delayed LL bumped SOA 4 days (Jun03 DJ) On track SOA Jun16. (Jun10 DJ) Leased del Jun9. On track SOA Jun16. Jun12 > SOA!! |  | 2009-06-16 |  |  |  |  | 2009-04-27 | 2009-04-30 | [11 empty] | FALSE |  | 2667934 | 6492532 | 110 Beach Road Castor Bay Auckland |  |  | CELLSITE | [7 empty] | 2009-05-18 | 2009-05-18 | [8 empty] | 2008-10-09
0 | AKL | 82 | AKL-005-027 |  | AKL-005-027-F | Albany South | North Shore City |  | TIER_1_ALL | ACTIVE | GF | A6 | P2 | grey |  |  | 20 | 20 |  | -36.7422 | 174.7208 |  |  |  |  | Microwave | AKL-005-049-A | [5 empty] | 2009-05-11 | [5 empty] | 2008-04-11 | 2 |  | 2014-05-26 |  |  | 2008-04-18 | 2008-04-18 | 1 | 2008-04-18 | 2008-04-18 |  |  |  | 2008-12-12 |  |  | 2008-12-04 | 2008-12-04 |  | 2008-04-21 |  | 2008-05-22 | 1 | 1 | 2008-05-22 | 2008-05-22 | 2008-12-19 | [5 empty] | 2008-12-12 | 2009-01-23 | 2009-01-20 |  | 2009-01-23 | 2009-01-20 | [8 empty] | 2009-03-24 | 2009-03-27 | 2009-03-24 |  |  |  |  | On Air |  | 2009-03-27 | [5 empty] | 2008-12-19 | [11 empty] | FALSE |  | 2664094 | 6494048 | Albany Heights Limited C/o- Datastar (NZ) Limited 21 Arrenway Drive Albany Auckland |  |  | CELLSITE |  |  | 2014-09-05 | [5 empty] | 2008-12-05 | [8 empty] | 2008-03-19
0 | AKL | 83 | AKL-005-028 |  | AKL-005-028-F | Sunset North | North Shore City |  | TIER_1_ALL | ACTIVE | RT | B6 | NOPOLE | grey |  |  | 13.4 | 13.4 |  | -36.7424 | 174.7332 |  |  |  |  | Microwave | AKL-005-049-A | [5 empty] | 2009-05-11 | [5 empty] | 2008-10-06 | 4 |  | 2008-11-19 |  |  | 2008-09-30 | 2008-10-20 | 2 | 2008-09-30 | 2008-10-20 |  | 2008-12-05 |  | 2009-01-22 |  |  | 2009-02-27 | 2009-01-23 |  | 2008-11-03 |  | 2008-12-02 | 1 | 4 | 2008-12-02 | 2008-12-02 | [6 empty] | 2009-01-05 | 2009-01-23 | 2009-01-23 |  | 2009-02-09 | 2009-02-04 | [8 empty] | 2009-04-06 | 2009-04-03 | 2009-04-06 |  |  |  |  | On Air |  | 2009-04-03 | [17 empty] | FALSE |  | 2665196 | 6494002 | 17 Antares Plc, Mairangi Bay, Auckland |  |  | CELLSITE |  |  | 2014-09-05 | [5 empty] | 2008-12-16 | [8 empty] | 2008-06-04
0 | AKL | 84 | AKL-005-029 |  | AKL-005-029-A | Mairangi Bay | North Shore City |  | TIER_1_ALL | ACTIVE | RT | B | NOPOLE | grey |  |  | 10 | 10 |  | -36.738 | 174.7534 |  |  |  |  | Microwave, Leased Line | AKL-005-045-A, AKL-007-106-A | [5 empty] | 2011-04-28 | [5 empty] | 2007-11-09 | 2 | 2007-11-09 | 2009-03-26 |  |  | 2008-02-11 | 2008-02-11 | 1 | 2008-02-11 | 2008-02-11 |  |  |  | 2008-02-08 |  |  | 2008-02-08 | 2008-02-08 |  | 2008-02-11 |  | 2008-03-18 | 1 | 1 | 2008-03-18 | 2008-03-18 | [6 empty] | 2008-05-12 | 2008-05-23 | 2008-05-27 |  | 2008-06-06 | 2008-05-30 | [8 empty] | 2009-02-11 | 2009-03-07 | 2009-02-11 |  |  |  |  | Site On Air |  | 2009-03-07 | [17 empty] | FALSE |  | 2667009 | 6494454 | 439 Beach Rd, Cnr Montrose Trc, Mairangi Bay, North Shore City |  |  | CELLSITE | [8 empty] | 2008-03-19 | [8 empty] | 2007-08-27
0 | AKL | 85 | AKL-005-030 |  | AKL-005-030-C | Rothesay Bay | North Shore City |  | TIER_1_ALL | ACTIVE | RSR | A | P4A | green |  |  | 11.2 | 11.2 |  | -36.7265 | 174.7486 |  |  |  |  | Leased Line, Microwave | AKL-007-106-A, AKL-005-059-A | [5 empty] | 2011-04-28 | [5 empty] | 2007-11-16 | 4 | 2009-02-10 | 2009-02-10 |  |  | 2008-02-28 | 2008-02-28 | 2 | 2008-02-27 | 2009-02-17 |  |  |  | 2008-12-05 |  |  | 2009-03-11 | 2009-02-12 |  | 2008-02-26 |  | 2008-10-09 | 2 | 4 | 2009-02-19 | 2009-02-19 | 2009-01-19 | [5 empty] | 2009-02-18 | 2009-02-28 | 2009-03-04 |  | 2009-02-28 | 2009-03-04 | [8 empty] | 2009-05-07 | 2009-05-08 | 2009-05-07 |  |  |  |  | LL due 30/4 - TNZ requested to bring forward (JL 27/4) (May6 DJ) LL delivered May4 - on track for SOA |  | 2009-05-08 | [5 empty] | 2009-01-19 | [11 empty] | FALSE |  | 2666611 | 6495742 | Cnr Montgomery Ave & Beach Rd, Rothesay Bay, North Shore |  |  | CELLSITE | [7 empty] | 2009-03-12 | 2009-02-16 | [8 empty] | 2007-09-20
0 | AKL | 86 | AKL-005-031 |  | AKL-005-031-A | North Harbour Stadium | North Shore City |  | TIER_1_ALL | ACTIVE | GF | A6 | NOPOLE | green |  |  | 20 | 20 |  | -36.7279 | 174.7013 |  |  |  |  | Leased Line, Microwave | AKL-007-106-A, AKL-005-052-A | [5 empty] | 2009-05-15 | [5 empty] | 2007-11-30 | 4 |  | 2009-09-11 |  |  | 2008-03-04 | 2008-03-04 | 2 | 2008-03-04 | 2008-03-04 |  |  |  | 2008-04-30 |  |  | 2008-04-30 | 2008-04-30 |  | 2008-02-27 |  | 2008-06-18 | 2 | 3 | 2008-07-02 | 2008-07-02 | [6 empty] | 2008-07-21 | 2008-08-19 | 2008-08-19 |  | 2008-08-29 | 2008-08-27 | [8 empty] | 2008-12-03 | 2009-02-27 | 2008-12-03 |  |  |  |  | On Air |  | 2009-02-27 | [17 empty] | FALSE |  | 2662386 | 6495677 | North Shore Stadium Oteha Valley Road Auckland |  |  | CELLSITE |  |  | 2014-09-05 | [5 empty] | 2008-07-03 | [8 empty] | 2007-10-16
0 | AKL | 87 | AKL-005-032 |  | AKL-005-032-A | Glenvar | North Shore City |  | TIER_1_ALL | ACTIVE | RSR | A | P4A | green |  |  | 10.5 | 10.5 |  | -36.7003 | 174.7254 |  |  |  |  | Leased Line, Microwave | AKL-007-106-A, AKL-005-059-A | [5 empty] | 2011-04-28 | [5 empty] | 2007-10-09 | 2 | 2008-12-19 | 2008-12-19 |  |  | 2009-02-27 | 2008-02-28 | 1 | 2009-02-27 | 2009-02-17 |  |  |  | 2009-01-30 |  |  | 2009-04-10 | 2009-04-15 |  | 2008-02-26 |  | 2008-03-28 | 2 | 2 | 2008-12-22 | 2008-12-22 | 2009-03-24 |  |  |  |  | 2009-04-24 | 2009-04-27 | 2009-05-12 | 2009-05-12 |  | 2009-05-12 | 2009-05-12 | [8 empty] | 2009-05-27 | 2009-05-27 | 2009-05-27 |  |  |  |  | (May14 DJ) underway - on track |  | 2009-05-27 |  |  |  |  | 2009-05-08 | 2009-03-24 | [11 empty] | FALSE |  | 2664595 | 6498688 | Streetlight outside 78 Fitzwilliam Drive Torbay North Shore |  |  | CELLSITE | [7 empty] | 2009-04-24 | 2009-04-27 | [8 empty] | 2007-09-20
0 | AKL | 88 | AKL-005-033 |  | AKL-005-033-H | Browns Bay North | North Shore City |  | TIER_1_ALL | ACTIVE | RSR | D | P4F | green | [5 empty] | -36.7075 | 174.7379 |  |  |  |  | Leased Line | AKL-007-106-A | [11 empty] | 2009-04-02 | 1 | 2009-04-01 | 2009-04-02 |  |  | 2009-10-30 | 2009-10-28 |  | 2009-10-30 | 2009-10-30 |  | 2009-04-09 |  | 2009-05-08 |  |  | 2009-05-08 | 2009-05-07 | 2009-04-06 | 2009-03-18 |  | 2009-04-14 | 2 |  | 2009-04-24 | 2009-09-25 | 2009-06-11 |  |  |  |  | 2009-11-16 | 2009-11-11 | 2009-11-23 | 2009-11-20 |  | 2009-11-23 | 2009-11-20 | [8 empty] | 2009-11-26 | 2009-11-26 | 2009-11-26 |  |  |  |  | Site in build |  | 2009-11-26 |  |  |  |  | 2009-06-10 | 2009-06-11 | [11 empty] | FALSE |  | 2665698 | 6497868 | RSR outside 10 Finchley Rd Waiake Auckland |  |  | CELLSITE | [8 empty] | 2009-11-11 | [8 empty] | 2009-03-06
0 | AKL | 89 | AKL-005-034 |  | AKL-005-034-C | Campbells Bay | North Shore City |  | TIER_1_ALL | ACTIVE | RT | A | NOPOLE | grey |  |  | 8.4 | 8.4 |  | -36.7449 | 174.7578 |  |  |  |  | Leased Line | AKL-007-106-A | [11 empty] | 2007-07-10 | 3 | 2008-09-11 | 2008-09-11 |  |  | 2008-03-17 | 2008-03-17 | 3 | 2008-03-17 | 2008-03-17 |  |  |  | 2008-04-30 |  |  | 2008-09-18 | 2008-09-18 |  | 2008-02-26 |  | 2008-06-24 | 4 | 3 | 2008-11-12 | 2008-11-12 | [6 empty] | 2008-07-28 | 2008-10-31 | 2008-10-31 |  | 2008-12-23 | 2009-01-09 | [8 empty] | 2009-03-02 | 2009-03-06 | 2009-03-02 |  |  |  |  | (Mar2 DJ) Site On Air |  | 2009-03-06 | [17 empty] | FALSE |  | 2667393 | 6493684 | Harcourts, 278 Beach Rd, Campbells Bay, North Shore, Auckland |  |  | CELLSITE | [8 empty] | 2008-06-25 | [8 empty] | 2007-06-18
0 | AKL | 90 | AKL-005-035 |  | AKL-005-035-D | Sunnynook | North Shore City |  | TIER_1_ALL | ACTIVE | RSR | D6 | P4F | green |  |  | 13.2 | 13.2 |  | -36.7615 | 174.7386 |  |  |  |  | Microwave | AKL-005-024-E | [5 empty] | 2009-05-11 | [5 empty] | 2008-09-11 | 4 | 2009-01-07 | 2009-03-11 |  |  | 2009-04-30 | 2009-04-24 |  | 2009-05-08 | 2009-09-15 |  | 2009-01-19 |  | 2009-03-20 |  |  | 2009-03-20 | 2009-03-12 | 2009-01-16 | 2008-12-23 |  | 2009-02-20 | 1 | 2 | 2009-03-13 | 2009-02-20 | 2009-05-18 |  |  |  |  | 2009-05-18 | 2009-05-18 | 2009-05-26 | 2009-05-26 |  | 2009-06-09 | 2009-06-05 | [8 empty] | 2009-06-12 | 2009-06-12 | 2009-06-12 |  |  |  |  | (May28 DJ) Build commenced May18. On track. (Jun03 DJ) On track SOA Jun12. (Jun10 DJ) On track SOA Jun12. > SOA!! |  | 2009-06-12 |  |  |  |  | 2009-05-15 | 2009-05-18 | [11 empty] | FALSE |  | 2665640 | 6491875 | 166 Sunnynook Rd, Sunnynook, Auckland |  |  | CELLSITE |  |  | 2014-09-05 |  |  |  |  | 2009-05-18 | 2009-05-18 | [8 empty] | 2008-09-01
0 | AKL | 91 | AKL-005-036 |  | AKL-005-036-C | Pinehill | North Shore City |  | TIER_1_ALL | ACTIVE | RSR | A6 | P4A | green |  |  | 10 | 10 |  | -36.7307 | 174.724 |  |  |  |  | Leased Line, Microwave | AKL-007-106-A, AKL-005-052-A | [5 empty] | 2009-05-11 | [5 empty] | 2007-10-04 | 1 |  | 2007-10-04 |  |  | 2008-02-25 | 2008-02-25 | 1 | 2008-02-25 | 2008-02-25 |  |  |  | 2008-09-30 |  |  | 2008-08-18 | 2008-08-18 |  | 2008-02-26 |  | 2008-04-29 | 2 | 1 | 2008-05-12 | 2008-05-12 | [6 empty] | 2008-08-25 | 2008-09-05 | 2008-09-05 |  | 2008-09-12 | 2008-09-05 | [8 empty] | 2009-03-23 | 2009-03-30 | 2009-03-23 |  |  |  |  | On Air |  | 2009-03-30 | [17 empty] | FALSE |  | 2664401 | 6495322 | Roadside along Greville Road Opposite the Mad Butcher North Shore |  |  | CELLSITE |  |  | 2014-09-05 | [5 empty] | 2008-08-21 | [8 empty] | 2007-09-21
0 | AKL | 92 | AKL-005-037 | Esmonde Road | AKL-005-037-E | Barrys Point | North Shore City | 3 | TIER_1_ALL | ACTIVE | RT | B6 | NOPOLE | grey |  |  | 6 | 6 |  | -36.795 | 174.7647 |  |  |  |  | Leased Line, Microwave | AKL-007-106-A, AKL-005-065-A | FALSE | FALSE |  |  | FALSE | 2009-05-11 | [5 empty] | 2007-11-02 | 1 | 2007-11-02 | 2007-11-02 |  |  | 2007-11-30 | 2007-11-30 | 1 | 2007-11-30 | 2007-11-30 |  |  |  | 2008-01-21 |  |  | 2008-01-21 | 2008-01-21 |  | 2007-11-12 |  | 2008-01-20 | 1 | 1 | 2008-01-20 | 2008-01-20 | [6 empty] | 2008-04-04 | 2008-04-18 | 2008-04-18 |  | 2008-05-09 | 2008-05-19 | [8 empty] | 2009-04-28 | 2009-04-28 | 2009-04-28 |  |  |  |  | waiting LL, f'cst SOA Apr24 900mHZ required to Infratel (JL 21/4) (Apr23 DJ) On track - Downers will do in-boundary ducting Waiting for 900MHz kit for integration. 900MHz kit being installed 27/4 |  | 2009-04-28 | [17 empty] | FALSE |  | 2667891 | 6488113 | 79 Barrys Point Road Takapuna |  |  | CELLSITE |  |  | 2014-09-05 | [5 empty] | 2008-01-22 | [8 empty] | 2007-08-27
0 | AKL | 93 | AKL-005-038 |  | AKL-005-038-A | Unsworth Heights | North Shore City |  | TIER_1_ALL | ACTIVE | RSR | A6 | P4A | green |  |  | 10.5 | 10.5 |  | -36.759 | 174.72 |  |  |  |  | Leased Line | AKL-007-106-A | [11 empty] | 2007-10-30 | 2 | 2007-10-30 | 2009-03-31 |  |  | 2008-02-28 | 2008-02-28 | 1 | 2008-02-28 | 2008-02-28 |  |  |  | 2008-08-31 |  |  | 2008-07-07 | 2008-07-07 |  | 2008-02-26 |  | 2008-03-28 | 2 | 1 | 2008-08-11 | 2008-08-11 | [6 empty] | 2008-08-18 | 2008-09-19 | 2008-09-12 |  | 2008-10-03 | 2008-09-15 | [8 empty] | 2009-03-24 | 2009-03-27 | 2009-03-24 |  |  |  |  | (Mar24 DJ) Site On Air |  | 2009-03-27 | [17 empty] | FALSE |  | 2663980 | 6492191 | Streetlight pole opposite 60 Caribbean Rd Unsworth Heights North Shore |  |  | CELLSITE |  |  | 2014-09-05 | [5 empty] | 2008-08-05 | [8 empty] | 2007-09-21
0 | AKL | 94 | AKL-005-039 |  | AKL-005-039-D | Browns Bay South | North Shore City |  | TIER_1_ALL | ACTIVE | RSR | A | P4A | green |  |  | 15 | 15 |  | -36.7261 | 174.74 |  |  |  |  | Leased Line, Leased Line | AKL-007-106-A, AKL-007-106-A | [11 empty] | 2007-10-10 | 1 |  | 2007-10-10 |  |  | 2008-02-28 | 2008-02-28 | 1 | 2008-02-28 | 2008-02-28 |  |  |  | 2008-11-30 |  |  | 2008-11-14 | 2008-11-14 |  | 2008-02-26 |  | 2008-03-28 | 1 | 1 | 2008-03-28 | 2008-03-28 | [6 empty] | 2008-12-15 | 2008-12-22 | 2008-12-22 |  | 2008-12-22 | 2008-12-22 | [8 empty] | 2009-05-14 | 2009-05-13 | 2009-05-14 |  |  |  |  | On Air |  | 2009-05-13 | [17 empty] | FALSE |  | 2665839 | 6495807 | Streetlight swap on pole, O/s 101 Browns Bay Rd, Browns Bay, North Shore |  |  | CELLSITE | [8 empty] | 2008-12-02 | [8 empty] | 2007-09-21
0 | AKL | 95 | AKL-005-041 |  | AKL-005-041-A | Murrays Bay | North Shore City |  | TIER_1_ALL | ACTIVE | RSR | A6 | P4A | green |  |  | 12.5 | 12.5 |  | -36.7327 | 174.7335 |  |  |  |  | Microwave | AKL-005-027-F | [5 empty] | 2009-05-12 | [5 empty] | 2007-10-19 | 3 |  | 2008-08-11 |  |  | 2008-02-28 | 2008-02-28 | 3 | 2008-02-28 | 2008-02-28 |  |  |  | 2008-07-31 |  |  | 2008-07-31 | 2008-07-31 |  | 2008-02-26 |  | 2008-05-26 | 1 | 3 | 2008-05-26 | 2008-05-26 | 2009-03-02 | [5 empty] | 2008-08-06 | 2008-09-12 | 2008-08-26 |  | 2008-09-26 | 2008-08-26 | [8 empty] | 2009-03-24 | 2009-03-27 | 2009-03-24 |  |  |  |  | On Air |  | 2009-03-27 |  |  |  |  | 2009-02-28 | 2009-03-02 | [11 empty] | FALSE |  | 2665251 | 6495085 | 602 East Coast Rd Pinehill North Shore |  |  | CELLSITE |  |  | 2014-09-05 | [5 empty] | 2008-08-04 | [8 empty] | 2007-09-21
0 | AKL | 96 | AKL-005-042 |  | AKL-005-042-G | Glenfield South | North Shore City |  | TIER_1_ALL | ACTIVE | RSR | D6 | P4C | green |  |  | 14 | 14 |  | -36.7824 | 174.7207 |  |  |  |  | Microwave, Microwave, Leased Line | AKL-005-016-D, AKL-005-016-D, AKL-007-106-A | [5 empty] | 2009-04-22, 2009-04-22 | [5 empty] | 2008-12-23 | 2 | 2009-01-12 | 2009-01-12 |  |  | 2009-04-30 | 2009-04-24 |  | 2009-04-30 | 2009-09-15 |  | 2009-01-30 |  | 2009-03-06 |  |  | 2009-03-13 | 2009-03-01 | 2009-01-12 | 2009-01-08 |  | 2009-03-09 | 1 | 1 | 2009-03-13 | 2009-03-09 | 2009-05-18 |  |  |  |  | 2009-06-02 | 2009-06-02 | 2009-06-12 | 2009-06-05 |  | 2009-06-18 | 2009-06-05 | [8 empty] | 2009-07-14 | 2009-07-15 | 2009-07-14 |  |  |  |  | On Air |  | 2009-07-15 |  |  |  |  | 2009-05-15 | 2009-05-18 | [11 empty] | FALSE |  | 2663996 | 6489590 | 426 Glenfield Road Glenfield Auckland |  |  | CELLSITE |  |  | 2014-09-05 |  |  |  |  | 2009-06-02 | 2009-06-02 | [8 empty] | 2008-12-03
0 | AKL | 97 | AKL-005-044 |  | AKL-005-044-A | Bayview | North Shore City |  | TIER_1_ALL | ACTIVE | RSR | D6 | P4A | green |  |  | 9.6 | 9.6 |  | -36.7726 | 174.7073 |  |  |  |  | Leased Line | AKL-007-106-A | [11 empty] | 2007-10-19 | 5 | 2008-12-17 | 2008-12-17 |  |  | 2009-04-17 | 2009-04-01 | 2 | 2009-04-17 | 2009-03-31 |  |  |  | 2009-02-28 |  |  | 2009-02-28 | 2008-12-08 |  | 2008-02-26 |  | 2008-05-08 | 4 | 4 | 2009-01-12 | 2009-01-12 | 2008-09-26 |  |  |  |  | 2009-05-14 | 2009-05-14 | 2009-05-20 | 2009-05-20 |  | 2009-05-22 | 2009-05-22 | [8 empty] | 2009-06-25 | 2009-06-25 | 2009-06-25 |  |  |  |  | (May20 DJ) Civils complete - on track (Jun03 DJ) ref'cast SOA Jun20. (Jun10 DJ) Leased delivered Jun4. Pwr due Jun18. On track SOA Jun20. (Jun18 DJ) Pwr issues bumps SOA 1mth Jul17. (Jun24 DJ) Resolution of power issues brings fwd f'cst SOA Jun25. |  | 2009-07-17 | [5 empty] | 2008-09-26 | [11 empty] | FALSE |  | 2662815 | 6490705 | Streetlight pole, O/s 56 Bayview Rd, Glenfield West, North Shore |  |  | CELLSITE |  |  | 2014-09-05 |  |  |  |  | 2009-05-14 | 2009-05-14 | [8 empty] | 2007-09-21
0 | AKL | 98 | AKL-005-045 |  | AKL-005-045-A | Mairangi Bay North | North Shore City |  | TIER_1_ALL | ACTIVE | RSR | A6 | P4A | green |  |  | 12.5 | 12.5 |  | -36.7469 | 174.7428 |  |  |  |  | Leased Line, Microwave | AKL-007-106-A, AKL-005-028-F | [5 empty] | 2009-05-12 | [5 empty] | 2007-10-04 | 2 | 2007-10-04 | 2009-10-16 |  |  | 2008-02-28 | 2008-02-28 | 1 | 2008-02-28 | 2008-02-28 |  |  |  | 2008-08-31 |  |  | 2008-08-31 | 2008-07-07 |  | 2008-02-26 |  | 2008-05-15 | 1 | 1 | 2008-05-15 | 2008-05-15 | 2008-08-05 | [5 empty] | 2008-09-09 | 2008-09-30 | 2008-09-30 |  | 2008-10-03 | 2008-09-30 | [8 empty] | 2009-04-03 | 2009-04-03 | 2009-04-03 |  |  |  |  | (Mar27 DJ)F'SOA Mar13>20>31 |  | 2009-04-03 | [5 empty] | 2008-08-05 | [11 empty] | FALSE |  | 2666043 | 6493486 | Cnr of East Coast Rd & Galaxy Dr, Mairangi Bay, North Shore |  |  | CELLSITE |  |  | 2014-09-05 | [5 empty] | 2008-08-05 | [8 empty] | 2007-09-21
0 | AKL | 99 | AKL-005-047 |  | AKL-005-047-E | Beach Haven | North Shore City |  | TIER_1_ALL | ACTIVE | RSR | A | P4A | green |  |  | 8 | 8 |  | -36.7909 | 174.6899 |  |  |  |  | Microwave, Leased Line | AKL-005-012-A, AKL-007-106-A | [11 empty] | 2007-10-12 | 1 |  | 2007-10-12 |  |  | 2008-02-28 | 2008-02-28 | 1 | 2008-02-28 | 2008-02-28 |  |  |  | 2008-12-12 |  |  | 2008-12-12 | 2008-12-10 |  | 2008-02-26 |  | 2008-05-22 | 1 | 1 | 2008-05-22 | 2008-05-22 | 2008-12-17 | [5 empty] | 2009-01-12 | 2009-01-30 | 2009-01-30 |  | 2009-02-05 | 2009-02-02 | [8 empty] | 2009-03-30 | 2009-04-10 | 2009-03-30 |  |  |  |  | On Air |  | 2009-03-30 | [5 empty] | 2008-12-17 | [11 empty] | FALSE |  | 2661226 | 6488703 | Cnr Tramway & Beach Haven Rds, Beach Haven, North Shore, Auckland |  |  | CELLSITE |  |  | 2015-12-10 | [5 empty] | 2008-12-11 | [8 empty] | 2007-09-21
0 | AKL | 100 | AKL-005-048 |  | AKL-005-048-D | Browns Bay Central | North Shore City |  | TIER_1_ALL | ACTIVE | GF | A | P1 | grey |  |  | 13.8 | 13.8 |  | -36.716 | 174.7414 |  |  |  |  | Leased Line | AKL-007-106-A | [11 empty] | 2008-07-31 | 4 | 2009-02-16 | 2009-03-26 |  |  |  | 2008-10-07 | 2 | 2009-04-30 | 2009-05-14 |  |  |  | 2009-03-27 |  |  | 2009-03-27 | 2009-03-19 |  | 2008-09-08 |  | 2008-10-01 | 1 | 2 | 2009-04-09 | 2008-10-01 | 2008-12-19 |  |  |  |  | 2009-04-14 | 2009-04-14 | 2009-05-15 | 2009-05-08 |  | 2009-05-15 | 2009-05-08 | [8 empty] | 2009-06-13 | 2009-06-23 | 2009-06-13 |  |  |  |  | On Air |  | 2009-06-23 |  |  |  |  | 2009-02-06 | 2008-12-19 | [11 empty] | FALSE |  | 2665990 | 6496920 | Browns Bay Bowling Club, 4 Woodlands Cres, Browns Bay, Auckland |  |  | CELLSITE | [7 empty] | 2009-04-14 | 2009-04-14 | [8 empty] | 2008-07-22
0 | AKL | 101 | AKL-005-049 |  | AKL-005-049-A | Sunset Rd Hub | North Shore City |  | TIER_1_ALL | ACTIVE | GF | A6 | P3 | green |  |  | 15 | 15 | 1 | -36.7543 | 174.7285 |  |  |  |  | Microwave | AKL-005-015-B | [5 empty] | 2009-05-11 | [5 empty] | 2008-02-21 | 5 |  | 2013-08-29 |  |  | 2008-07-31 | 2008-10-01 | 3 | 2008-07-31 | 2008-10-01 |  |  |  | 2009-05-22 |  |  | 2009-05-22 | 2009-05-15 |  | 2008-05-22 |  | 2008-08-25 | 2 | 3 | 2008-08-25 | 2009-08-19 | 2009-03-13 |  |  |  |  | 2009-05-25 | 2009-05-25 | 2009-06-26 | 2009-06-26 |  | 2009-06-29 | 2009-06-29 | [8 empty] | 2009-06-30 | 2009-06-30 | 2009-06-30 |  |  |  |  | Awaiting pole availability ready to construct. 26/05 |  | 2009-06-30 |  |  |  |  | 2009-03-27 | 2009-03-13 | [11 empty] | FALSE |  | 2664749 | 6492699 | Land behind Highgrove Lane Wairau Park North Shore Auckland |  |  | CELLSITE |  |  | 2014-09-05 |  |  |  |  | 2009-05-25 | 2009-05-25 | [8 empty] | 2008-01-29
0 | AKL | 102 | AKL-005-050 |  | AKL-005-050-F | Torbay | North Shore City |  | TIER_1_ALL | ACTIVE | GF | Ab | P1 | grey |  |  | 13.5 | 13.5 |  | -36.6959 | 174.752 |  |  |  |  | Microwave | AKL-005-059-A | [11 empty] | 2009-08-31 | 1 | 2009-08-28 | 2009-08-31 |  |  | 2009-09-04 | 2009-09-04 |  | 2009-09-10 | 2009-09-14 |  | 2009-09-03 |  | 2009-09-24 |  |  | 2009-09-24 | 2009-09-23 | 2009-09-02 | 2009-09-02 |  | 2009-09-23 | 1 | 1 | 2009-09-23 | 2009-09-23 | 2009-03-27 |  |  |  |  | 2009-09-30 | 2009-09-30 | 2009-10-23 | 2009-10-23 |  | 2009-10-28 | 2009-10-27 | [8 empty] | 2009-10-27 | 2009-10-30 | 2009-10-27 |  |  |  |  | On Air |  | 2009-10-30 |  |  |  |  | 2009-03-27 | 2009-03-27 | [11 empty] | FALSE |  | 2666979 | 6499131 | 1030 Beach Road Torbay |  |  | CELLSITE | [7 empty] | 2009-09-30 | 2009-09-30 | [8 empty] | 2009-08-10
0 | AKL | 103 | AKL-005-051 |  | AKL-005-051-F | Northcross | North Shore City |  | TIER_1_ALL | ACTIVE | RSR | D | P4F | green |  |  | 14.2 | 14.2 |  | -36.7085 | 174.727 |  |  |  |  | Microwave | AKL-005-052-A | [5 empty] | 2009-04-15 | [5 empty] | 2008-12-23 | 1 | 2008-12-19 | 2008-12-23 |  |  | 2009-04-30 | 2009-04-24 |  | 2009-05-08 | 2009-09-15 |  | 2009-02-06 |  | 2009-03-13 |  |  | 2009-03-13 | 2009-03-12 | 2009-01-12 | 2009-01-08 |  | 2009-03-04 | 1 | 1 | 2009-02-27 | 2009-03-04 | 2009-05-18 |  |  |  |  | 2009-05-18 | 2009-05-18 | 2009-05-29 | 2009-05-28 |  | 2009-06-19 | 2009-06-19 | [8 empty] | 2009-07-01 | 2009-07-03 | 2009-07-01 |  |  |  |  | (Jun03 DJ) On track SOA Jun15. (Jun10 DJ) TX change at Albany East bumps TI to Jun19, SOA to Jun23 (Jun18 DJ) still holding SOA Jun23. (Jun24 DJ) TX linking issue bumps SOA Jun30. (Jul01 DJ) Linking issue delays SOA f'cst Jul03. |  | 2009-07-03 |  |  |  |  | 2009-05-15 | 2009-05-18 | [11 empty] | FALSE |  | 2664717 | 6497777 | 954 East Coast Rd Northcross Auckland |  |  | CELLSITE | [7 empty] | 2009-05-18 | 2009-05-18 | [8 empty] | 2008-12-03
0 | AKL | 104 | AKL-005-052 |  | AKL-005-052-A | Albany East | North Shore City | 3 | TIER_1_ALL | ACTIVE | GF | A6 | P3 | grey |  |  | 18.8 | 18.8 |  | -36.7288 | 174.7142 |  |  |  |  | Microwave | AKL-005-049-A | FALSE | FALSE |  |  | FALSE | 2009-05-11 | [5 empty] | 2008-06-27 | 5 | 2008-09-29 | 2014-05-26 |  |  | 2009-02-27 | 2009-01-19 | 4 | 2009-01-20 | 2009-01-19 |  |  |  | 2009-03-06 |  |  | 2009-03-06 | 2009-09-25 |  | 2008-09-08 |  | 2008-09-29 | 3 | 4 | 2008-10-13 | 2009-09-01 | 2009-02-02 |  |  |  |  | 2009-03-20 | 2009-03-20 | 2009-04-17 | 2009-04-15 |  | 2009-04-24 | 2009-04-15 | [8 empty] | 2009-04-22 | 2009-04-30 | 2009-04-22 |  |  |  |  | On Air Link to Schnapper Rock. REQUIRE : 300mmØ |  | 2009-04-30 |  |  |  |  | 2009-01-28 | 2009-02-02 | [11 empty] | FALSE |  | 2663532 | 6495550 | 69 Corinthian Drv, Albany, North Shore, Auckland |  |  | CELLSITE |  |  | 2014-09-05 |  |  |  |  | 2009-03-09 | 2009-02-23 | [8 empty] | 2008-04-28
0 | AKL | 105 | AKL-005-053 |  | AKL-005-053-C | Albany West | North Shore City |  | TIER_1_ALL | ACTIVE | GF | A6 | P2 | grey |  |  | 18.8 | 18.8 |  | -36.7486 | 174.6991 |  |  |  |  | Microwave | AKL-005-052-A | [10 empty] | 2009-03-20 | 2009-03-19 | 3 | 2009-05-08 | 2009-05-08 |  |  | 2009-06-30 | 2009-06-30 | 3 | 2009-06-30 | 2009-06-30 |  | 2009-03-27 |  | 2009-05-29 |  |  | 2009-05-29 | 2009-05-14 | 2009-04-22 | 2009-04-08 | 2009-04-22 | 2009-05-20 | 1 | 1 | 2009-06-05 | 2009-05-20 | 2009-04-17 |  |  |  |  | 2009-08-03 | 2009-07-22 | 2009-08-12 | 2009-08-12 |  | 2009-08-14 | 2009-08-14 | [8 empty] | 2009-08-21 | 2009-08-21 | 2009-08-21 |  |  |  |  | On Air |  | 2009-08-21 |  |  |  |  | 2009-04-17 | 2009-04-17 | [11 empty] | FALSE |  | 2662136 | 6493384 | 297 Albany Highway Albany Auckland |  |  | CELLSITE |  |  | 2014-09-05 |  |  |  |  | 2009-08-03 | 2009-07-22 | [8 empty] | 2009-03-04
0 | AKL | 106 | AKL-005-054 |  | AKL-005-054-A | Wainoni | North Shore City |  | TIER_1_ALL | ACTIVE | RSR | D | P4F | green |  |  | 14 | 14 |  | -36.7705 | 174.6854 |  |  |  |  | Leased Line | AKL-007-106-A | [11 empty] | 2008-12-03 | 2 | 2009-01-23 | 2008-12-22 |  |  | 2009-04-30 | 2009-04-27 | 2 | 2009-05-15 | 2009-05-22 |  | 2009-01-26 |  | 2009-05-08 |  |  | 2009-05-08 | 2009-04-29 | 2009-01-23 | 2008-12-24 |  | 2009-02-19 | 1 | 2 | 2009-02-19 | 2009-02-19 | 2009-05-07 |  |  |  |  | 2009-05-11 | 2009-05-11 | 2009-05-25 | 2009-05-26 |  | 2009-05-29 | 2009-05-26 | [8 empty] | 2009-06-18 | 2009-06-18 | 2009-06-18 |  |  |  |  | (May20 DJ) Early start approval - under const (May28 DJ) On schedule. (Jun03 DJ) ref'cast SOA Jun18. (Jun10 DJ) Leased due Jun12. On track SOA Jun18. (Jun18 DJ) leased line bumped 3 days, still holding SOA Jun18. |  | 2009-06-18 |  |  |  |  | 2009-05-06 | 2009-05-07 | [11 empty] | FALSE |  | 2660865 | 6490974 | Transit NZ Ltd Albany Highway (Access off Lemon Grove Lane) Greenhithe Wainoni Auckland |  |  | CELLSITE |  |  | 2015-12-10 |  |  |  |  | 2009-05-11 | 2009-05-11 | [8 empty] | 2008-10-10
0 | AKL | 107 | AKL-005-055 |  | AKL-005-055-B | Forrest Hill | North Shore City |  | TIER_1_ALL | ACTIVE | RSR | A6 | P4A | green |  |  | 12 | 12 | 1 | -36.7702 | 174.7492 |  |  |  |  | Microwave | AKL-005-025-A | [5 empty] | 2009-05-11 | [5 empty] | 2008-07-03 | 2 | 2008-08-28 | 2008-08-28 |  |  | 2009-04-30 | 2009-04-24 |  | 2009-05-08 | 2009-09-15 | [7 empty] | 2008-11-14 | 2008-09-17 | 2008-10-07 |  | 2008-10-17 | 1 | 2 | 2008-10-17 | 2008-10-17 | 2009-04-30 |  |  |  |  | 2009-05-08 | 2009-05-08 | 2009-05-20 | 2009-05-20 |  | 2009-05-28 | 2009-05-27 | [8 empty] | 2009-05-28 | 2009-05-28 | 2009-05-28 |  |  |  |  | (May28 DJ) On track for SOA. |  | 2009-05-28 |  |  |  |  | 2009-05-01 | 2009-04-30 | [11 empty] | FALSE |  | 2666562 | 6490889 | Opp 96 Forrest Hill Rd, Forrest Hill, Auckland |  |  | CELLSITE |  |  | 2014-09-05 |  |  |  |  | 2009-05-08 | 2009-05-08 | [8 empty] | 2008-06-13
0 | AKL | 108 | AKL-005-058 |  |  |  | North Shore City |  | TIER_1_ALL
0 | AKL | 109 | AKL-005-059 |  | AKL-005-059-A | Torbay Hub | North Shore City |  | TIER_1_ALL | ACTIVE | GF | A | P6 | green |  |  | 18.8 | 18.8 |  | -36.7024 | 174.7204 |  |  |  |  | Microwave, Microwave | AKL-005-052-A, AKL-005-052-A | [5 empty] | 2009-05-22, 2009-04-15 | [5 empty] | 2009-03-02 | 9 | 2009-04-22 | 2012-10-26 |  |  | 2009-05-27 | 2009-05-29 | 6 | 2009-05-27 | 2009-06-30 |  | 2009-03-10 |  | 2009-06-30 |  |  | 2009-06-30 | 2009-06-26 | 2009-05-01 | 2009-04-14 |  | 2009-05-27 | 3 | 7 | 2009-07-10 | 2009-07-09 | 2009-05-25 |  |  |  |  | 2009-07-13 | 2009-07-13 | 2009-08-14 | 2009-08-14 |  | 2009-08-18 | 2009-08-18 | [8 empty] | 2009-08-19 | 2009-08-20 | 2009-08-19 |  |  |  |  | Access track being constructed. MB 02/07 |  | 2009-08-20 |  |  |  |  | 2009-05-29 | 2009-05-25 | [11 empty] | FALSE |  | 2664141 | 6498468 | Watercare, 2 Lonely Track Rd, Cnr Lonely Track Rd & East Coast Rd, Torbay, North Shore, Auckland |  |  | CELLSITE | [7 empty] | 2009-07-13 | 2009-07-13 | [8 empty] | 2009-01-23
0 | AKL | 110 | AKL-005-061 |  | AKL-005-061-B | Browns Bay West | North Shore City |  | TIER_1_ALL | ACTIVE | RSR | D | P4C | green |  |  | 9.2 | 9.2 |  | -36.7156 | 174.7336 |  |  |  |  | Leased Line | AKL-007-106-A | [11 empty] | 2008-10-29 | 4 | 2009-02-24 | 2009-02-24 |  |  | 2009-04-30 | 2009-04-24 |  | 2009-05-08 | 2009-09-15 |  | 2009-02-20 |  | 2009-03-20 |  |  | 2009-03-20 | 2009-03-19 | 2008-12-01 | 2008-12-24 |  | 2009-03-11 | 1 | 2 | 2009-03-13 | 2009-03-11 | 2009-05-18 |  |  |  |  | 2009-05-18 | 2009-05-18 | 2009-05-28 | 2009-05-27 |  | 2009-06-05 | 2009-06-02 | [8 empty] | 2009-06-23 | 2009-06-22 | 2009-06-23 |  |  |  |  | (May28 DJ) - Telecom LL RFS bumped May29> Jun6. SOA>Jun19. (Jun03 DJ) SOA re-f'cast Jun15. (Jun10 DJ) Leased del Jun9. On track SOA Jun15. (Jun18 DJ) Pwr delay bumps SOA to Jun22. (Jun24 DJ) SOA!! |  | 2009-06-22 |  |  |  |  | 2009-05-15 | 2009-05-18 | [11 empty] | FALSE |  | 2665294 | 6496975 | Corner Sartors & Robin Lane Browns Bay North Shore Auckland |  |  | CELLSITE |  |  | 2015-12-10 |  |  |  |  | 2009-05-18 | 2009-05-18 | [8 empty] | 2008-10-08
0 | AKL | 111 | AKL-005-064 |  | AKL-005-064-K | Hillcrest South | North Shore City |  | TIER_1_ALL | ACTIVE | RSR | D6 | P4F | green |  |  | 9.3 | 9.3 |  | -36.7931 | 174.7372 |  |  |  |  | Leased Line | AKL-007-106-A | [11 empty] | 2008-12-17 | 1 | 2008-12-19 | 2008-12-17 |  |  | 2009-04-30 | 2009-04-24 |  | 2009-05-08 | 2009-09-15 |  | 2009-02-13 |  | 2009-03-20 |  |  | 2009-03-20 | 2009-03-19 | 2008-12-19 | 2008-12-24 |  | 2009-03-09 | 1 | 1 | 2009-03-06 | 2009-03-09 | 2009-05-20 |  |  |  |  | 2009-05-11 | 2009-05-11 | 2009-05-27 | 2009-05-26 |  | 2009-06-05 | 2009-06-05 | [8 empty] | 2009-06-16 | 2009-06-19 | 2009-06-16 |  |  |  |  | (May28 DJ) On track -SOA. (Jun03 DJ) On track SOA Jun19. (Jun10 DJ) Leased delivered Jun5 On track SOA Jun19. (Jun16 DJ) still holding SOA Jun19. Jun16 > SOA!! |  | 2009-06-19 |  |  |  |  | 2009-05-20 | 2009-05-20 | [11 empty] | FALSE |  | 2665440 | 6488370 | Cnr Munstead Plc & Stanaway St, (O/S 48 Stanaway Rd) Northcote, North Shore, Auckland |  |  | CELLSITE |  |  | 2014-09-05 |  |  |  |  | 2009-05-11 | 2009-05-11 | [8 empty] | 2008-10-08
0 | AKL | 112 | AKL-005-065 |  | AKL-005-065-A | Hillcrest West | North Shore City |  | TIER_1_ALL | ACTIVE | RSR | D6 | P4C | green |  |  | 12.6 | 12.6 |  | -36.7913 | 174.726 |  |  |  |  | Microwave | AKL-005-016-D | [10 empty] | 2009-02-05 | 2008-12-05 | 5 | 2009-02-19 | 2009-10-16 |  |  | 2009-04-30 | 2009-04-24 |  | 2009-05-08 | 2009-06-23 |  | 2009-02-27 |  | 2009-03-20 |  |  | 2009-03-20 | 2009-03-13 | 2008-12-19 | 2008-12-23 |  | 2009-03-04 | 1 | 1 | 2009-03-06 | 2009-03-04 | 2009-05-04 |  |  |  |  | 2009-05-25 | 2009-05-20 | 2009-05-29 | 2009-05-28 |  | 2009-06-16 | 2009-06-25 | [8 empty] | 2009-06-26 | 2009-06-25 | 2009-06-26 |  |  |  |  | (Jun03 DJ) SOA re-f'cast Jun12>21. (Jun10 DJ) Power delayed but shouldn't impact for SOA Jun22. (Jun18 DJ) latest update now has power delaying SOA from Jun22> Jul17. (Jun24 DJ) power situation improved - brings SOA fwd to Jun25 |  | 2009-07-17 |  |  |  |  | 2009-05-01 | 2009-05-04 | [11 empty] | FALSE |  | 2664445 | 6488589 | Junction of Coronation & Archers Rd, Glenfield South, North Shore, Auckland |  |  | CELLSITE |  |  | 2014-09-05 |  |  |  |  | 2009-05-25 | 2009-05-20 | [8 empty] | 2008-10-10
0 | AKL | 113 | AKL-005-067 | Stratos Abis Sat Link |  |  | North Shore City |  | TIER_6
0 | AKL | 114 | AKL-005-068 | Albany Test Bed | AKL-005-068-A | Albany Testbed | North Shore City |  | TIER_6 | ACTIVE | RT | TX | [7 empty] | -36.7485 | 174.7031 | [17 empty] | 2010-07-28 | 1 | 2010-07-19 | 2010-07-28 |  |  | 2010-08-30 | 2010-08-17 |  | 2010-08-30 | 2010-08-18 | PERMITTED | 2010-07-29 | 2010-07-30 | 2010-08-30 |  | 1 | 2010-08-30 |  | 2010-08-02 | [5 empty] | 2010-08-03 | [6 empty] | 2010-07-16 |  | 2010-07-16 | 2010-07-16 |  | 2010-07-21 | 2010-07-21 | [8 empty] | 2010-07-21 | 2010-07-21 | 2010-07-21 |  |  |  |  | Await a photo montage from Sean. 15/07 Sean F to lodge tomorrow. Letter still with legal, to tie in with existing lease agreement.16/07 MW installed with Landlords approval. Legal letter expected 23/07 - to be forwarded to Peter for signature.29/07 Letter sent to Peter. RMA submitted. Await CHQ. CHQ SUBMITTED. AWAIT LANDLORD APPROVAL AND RMA APPROVAL. 12/08 Council advised dont need RMA only COC. Still await Landlord approval. 18/08 Rec landlord approval. |  | 2010-07-21 | [17 empty] | FALSE |  | 2662497 | 6493380 | Albany Warehouse, 8G Piermark Dr, Auckland |  |  | CELLSITE |  |  | 2014-06-02 |  |  |  |  | 2010-07-16 | 2010-07-16
0 | AKL | 115 | AKL-005-069 | Campbells Bay South |  |  | North Shore City |  | TIER_9 | [22 empty] | FALSE | [60 empty] | Aim to provide GSM900 and UMTS2100 services to indoor level. Tier 1 Infill Project.
0 | AKL | 116 | AKL-005-070 | Crown Hill | AKL-005-070-A | Crown Hill shops | North Shore City | 3 | TIER_1_INFILL | ACTIVE | RT | B6 | RT | Grey | INLINE | COSITE | 10.6 | 7.6 | 1 | -36.7689 | 174.7589 |  |  |  |  | Microwave | AKL-005-016-D | FALSE | FALSE |  |  | FALSE | 2011-07-19 | 2011-07-19 | 2011-07-19 | 2011-08-01 | 2011-07-28 | 2011-09-16 | 2011-09-20 | 1 | 2011-09-16 | 2011-09-20 | 2011-09-23 | 2011-09-22 | 2011-11-30 | 2011-12-15 | 1 | 2011-11-30 | 2011-12-15 | DISCRETIONARY_FULL | 2011-10-05 | 2011-10-06 | 2012-02-06 | 2012-02-03 | 1 | 2012-02-06 | 2012-02-03 |  |  |  | 2012-03-23 | 2 |  | 2012-03-22 | 2012-10-05 | 2012-04-18 |  |  |  |  | 2012-04-10 | 2012-04-11 | 2012-04-20 | 2012-04-30 | 2012-05-07 | 2012-05-15 | 2012-05-21 | [8 empty] | 2012-06-15 | 2012-06-07 | 2012-06-15 | 2012-07-03 | 2012-06-29 | 2012-09-27 | 2012-10-29 | 10.03 Initial nominal visit. Roof top - Vodafone are situated on the roof. 3 Business below and 1 ontop along with 1 residential flat. Kelly to contact owner to see how willing. Trevor has made this a back up if the Campbells Bay co lo with TNZ falls over. Campbels Bay not looking good structuraly, need to caravan this site. Caravaned - Kelly has meeting with Hamish Chandra on 28.7.11 AT 10 to discuss the proposal. If all good. WO1 will be issued. |  | 2012-06-19 | 2012-04-02 | 2012-04-02 | 2012-04-10 | 2012-04-10 | 2012-04-17 | 2012-04-18 | 2012-05-11 | 2012-05-17 | [5 empty] | 2012-06-06 | 2012-06-11 |  | 2012-04-20 | FALSE |  | 2667431 | 6491023 | Cnr of East Coast Road and Stanley road |  | Lodged 6 October 2011 with Mark Ross AC - 06/10/2011 | CELLSITE |  |  | 2014-09-05 | [12 empty] | 2012-06-22 | 2012-06-20
0 | AKL | 117 | AKL-005-071 | Vauxhall |  |  | North Shore City |  | TIER_9 | [22 empty] | FALSE | [60 empty] | Aim to provide GSM900 and UMTS2100 to indoor level. Tier 1 Infill Project.
0 | AKL | 118 | AKL-005-072 | Campbells Bay South |  |  | North Shore City |  | TIER_9 | [22 empty] | FALSE
0 | AKL | 119 | AKL-005-073 | Crown Hill Water Tank |  |  | North Shore City |  | TIER_9 | [22 empty] | FALSE | [60 empty] | TNZ Pole at Water tank for Co-location
0 | AKL | 120 | AKL-005-074 | Schnapper Rock | AKL-005-074-A | LPR at Development | North Shore City |  | TIER_6 | ACTIVE | RSR | DU | P4F | grey | INLINE | STANDALONE | 14.5 | 15 | 1 | -36.7561 | 174.6921 | [6 empty] | FALSE | FALSE |  |  | FALSE |  | 2011-06-21 | 2011-05-31 | 2011-06-07 | 2011-06-02 | 2011-07-28 | 2011-07-29 | 1 | 2011-07-28 | 2011-07-29 | 2012-03-15 | 2012-01-12 | 2012-03-22 | 2012-01-12 |  | 2012-03-30 | 2012-02-14 | NES | 2011-08-01 | 2011-08-01 | 2011-09-12 | 2011-08-16 | 1 | 2011-09-19 | 2011-08-16 | [35 empty] | cp 7-8 June. wo1 ISSUED 02.06.2011. Boundary survey required. Harcourts have a fence up, but I think its over the boundary.. Hard Match so can use D cabinets thus now NES. Cabinets must be at GL not on a platform. Await amended Rev 0 dwngs. Rec Dwngs. Site RC received. Await licence from AKL city.....Have all approvals. 07.01.2013 - To issue WO2 - Its now a build site. Need to change cabinets from D to DU.Done 24.02.2013 WO2 not signed back on HOLD | [17 empty] | HARDMATCH |  | TRUE | 2013-02-28 | 2661500 | 6492560 | opp 101 Schnapper Rock Road, Auckland |  | NES Application s139 request for certificate of compliance lodged on the 1.8.11, processing with Aimee Buckingham - 03/08/2011 Council Reference Number: QA-2134068 - 17/08/2011 | CELLSITE | WIPHOLDING
0 | AKL | 121 | AKL-005-075 | Glenfield | AKL-005-075-D | LPR Cnr Glenfield St | North Shore City |  | TIER_6 | ACTIVE | RSR | DU | P4F | Green | INLINE | COSITE |  | 15 | 1 | -36.7701 | 174.722 | [6 empty] | FALSE | FALSE |  |  | FALSE |  | 2011-08-18 | 2011-08-18 | 2011-09-19 | 2011-09-23 | 2011-10-12 | 2011-10-12 | 2 | 2011-10-14 | 2012-03-29 | 2012-03-15 | 2012-03-23 | 2012-03-23 | 2012-06-11 |  | 2012-03-30 | 2012-06-11 | DISCRETIONARY_FULL | 2012-03-19 | 2012-05-03 | 2012-04-30 | 2012-05-29 | 2 | 2012-04-30 | 2012-06-13 | [35 empty] | Proposed road widening to commence Nov 2011, with construction time of 18 Months. Curent LPR position will be relocated. All over head Power and Telephone lines will be undergrounded (Kelly / Kelly contact 09.06.2011 EMAIL). Council would be happy for us to build this in the new spot before construction complete. Mikhail to CP new proposed position as per road widening plan. Await Trevors return so that the correct pole can be chosen. Pole B47 has been Cherry picked and is the prefered site. Kelly to get more detailed drwings from council. Then issue WO1. Council dwgs taking long. Issued WO1 now. Can uprev later. Need to get going. Rev 1 plans issued. Issue Telco Notice. Council advises will only do road widening in 2013. This is a hard match site and has been moved to the lowest build priority. We will retain the position on which the Telco Notice was served. 07.01.2013 wo2 TO BE ISSUED, NOW A BUILD SITE. Will need to change D cabinets to DU. Done. 24.02.2013 WO2 not signed. Back on hold | [17 empty] | HARDMATCH |  | TRUE |  | 2664140 | 6490953 | Corner of Glenfield and Wairoa Glenfield |  |  | CELLSITE | WIPHOLDING
0 | AKL | 122 | AKL-005-076 | Paremoremo Prison COW |  |  | North Shore City |  | TIER_1_INFILL
0 | AKL | 123 | AKL-005-077 | Long Bay | AKL-005-077-C | New Development | North Shore City |  | TIER_6 | ACTIVE | RSR | DU | P4F |  | INLINE | COSITE | 12.5 | 13 |  | -36.6881 | 174.7416 | [6 empty] | FALSE | FALSE |  |  | FALSE |  | 2012-10-15 | 2012-10-05 | 2012-10-15 | 2012-10-05 | 2012-11-14 | 2012-11-13 | 2 | 2012-11-14 | 2013-05-30 |  | 2012-10-05 | 2013-05-31 |  |  | 2013-05-31 |  | PERMITTED | 2013-05-01 |  | 2013-05-31 |  |  | 2013-05-31 | [36 empty] | Development belongs to Todd Corp. Aug 2012 we were invited to site and shown plans of Development. RF to decide wich option they would like - Position. Most likely a customised LPR to match existing in the central median of main rd throuh dev. Road will eventually be vested back to AT . Todd Dev would like us to install in March 2013. This site is HARD MATCH ONLY. 27/11/2012 co site application submitted to TNZ. They will also submit to us. We will only submit for NES CoC in March 2013 once Todd Dev have placed poles and we are ready to install. TNZ are doing the same. 26.03.2013 TNZ have submitted to AT. Nicola asked about ours. Gave her prelim plans. She advises cabinets in the road median cant happen, we need to redesign with developers. | [14 empty] | TIER_1_INFILL |  |  | HARDMATCH |  | TRUE |  | 2666071 | 6500014 | New Development Longbay Central Median Beach Road
0 | AKL | 124 | AKL-005-078 | Glenfield Exchange | AKL-005-078-A | Chorus Exchange | North Shore City |  | TIER_6 | ACTIVE | COLO | TX |  |  |  | COLO |  |  |  | -36.7777 | 174.7228 | [66 empty] | 2012-03-01 |  | 2012-03-01 |  |  | SOA and PAC dates entered to reflect in use status for finance | TNZ | [18 empty] | FALSE |  | 2664191 | 6490112 | 9 Mayfield Road, Glenfield, Auckland |  |  | TXSITE
0 | AKL | 125 | AKL-005-079 | Birkdale | AKL-005-079-A | Birkdale | North Shore City | 23 | 2015P | ACTIVE | RSR | DU5 | P4F |  | INLINE |  | 14.5 | 14.5 |  | -36.7934 | 174.7073 |  |  |  |  | Fibre Optic | AKL-005-078-A | FALSE | FALSE |  |  | FALSE |  | 2014-02-28 | 2014-02-28 | 2014-02-28 | 2014-02-28 | 2014-05-19 | 2014-05-16 | 6 | 2014-05-20 | 2014-11-13 | 2014-11-14 | 2014-10-23 | 2014-11-28 | 2014-11-17 |  | 2014-11-28 | 2014-11-17 | DISCRETIONARY_FULL | 2014-10-15 | 2014-10-08 | 2014-12-05 | 2014-12-16 | 6 | 2014-12-05 | 2014-12-16 | 2014-09-30 | 2014-09-30 | 2014-10-31 | 2014-10-31 | 1 |  | 2014-10-31 | 2014-10-31 |  |  |  | 2015-02-04 |  | 2015-03-16 | 2015-03-16 | 2015-04-17 | 2015-03-27 |  | 2015-04-08 |  | 2015-04-17 | [8 empty] | 2015-05-29 | 2015-05-29 |  |  |  |  | 30.09 Still waiting on AT letter so that we can submit the RMA AND TN 18.12.14 HARDMATCHED AT LAST ! Have CD's. Ready to Tender. 18/2/15 - Tenders being received 30/3/15 - Civils completed, now moving to TI works 04/05/15 - Site integrated, some issues with licensing. Should have Vol4 this week 19/05/15 - Still issues with Sector 2 imbalance. Kevin working on 26/05/15 - Weather delayed swap out of S2 antenna | [10 empty] | 2015-05-07 | 2015-05-12 | 2014-02-19 | HIGH |  | 2015-04-03 | 2015-04-06 | BUILD | 2015-04-01 | TRUE | 2014-12-15 | 2662775 | 6488395 | Cnr of Eskdale & Lauderdale Birkdale | AT Condition: Boundary to be surveyed before construction takes place Has this already been done? - 25/11/2014 | Lightpole capable of upgrades/LTE etc will exceed NES and take on underlying North Shore City Plan activity status. - 01/04/2014 | CELLSITE |  |  | 2015-05-29 | CAPACITY |  |  |  | 2015-03-09 | 2015-03-09 | [8 empty] | 2014-02-28
0 | AKL | 126 | AKL-005-080 | Albany West |  |  | North Shore City |  | TIER_9
0 | AKL | 127 | AKL-005-081 | Bayswater | AKL-005-081-A | Customer experience | North Shore City |  | TIER_6 | ACTIVE | [100 empty] | HARDMATCH
0 | AKL | 128 | AKL-005-082 | Esmonde Road |  |  | North Shore City |  | TIER_9 | [22 empty] | FALSE
0 | AKL | 129 | AKL-005-083 | Northcote Microcell |  |  | North Shore City |  | TIER_9 | [22 empty] | FALSE | [75 empty] | AUCKLAND
0 | AKL | 130 | AKL-005-084 | Northcross South | AKL-005-084-A | Customer experience | North Shore City |  | TIER_6 | ACTIVE | [100 empty] | HARDMATCH
0 | AKL | 131 | AKL-005-085 | Esmonde Road | AKL-005-085-B | Samsung | North Shore City | 3 | 2014 | ACTIVE | RT | DU5 | RT | Grey | INLINE | COSITE |  |  |  | -36.8016 | 174.7601 |  |  |  |  | Fibre Optic | AKL-005-078-A | FALSE | FALSE |  |  | FALSE |  | 2014-02-18 | 2014-02-18 | 2014-03-19 | 2014-03-12 | 2014-04-08 | 2014-04-11 | 3 | 2014-04-09 | 2014-06-04 | 2014-05-30 | 2014-05-26 | 2014-06-19 | 2014-06-17 |  | 2014-06-20 | 2014-06-20 | PERMITTED | 2014-05-27 | 2014-05-27 | 2014-06-30 | 2014-06-27 | 2 | 2014-06-27 | 2014-06-27 | 2014-05-23 | 2014-05-23 | 2014-06-30 | 2014-06-27 | 1 |  | 2014-07-11 | 2014-06-27 | [5 empty] | 2014-08-11 | 2014-08-11 | 2014-09-12 | 2014-09-15 | 2014-09-06 | 2014-09-12 | 2014-09-15 | 2014-09-05 | 2014-09-12 | [7 empty] | 2014-09-30 | 2014-09-30 |  |  |  |  | 10.02.14 Rec VNZ Cosite Data - have circulated. 12.02.14 John W to set up survey meet with Samsung to assess viablity 13.02.14 Meeting Tue 18.02 at 3.30pm 18.02.14 Surveyed roof, looks promising. BR to do photo montage presentation. 24.02.14 Done photomontage. John submitted to Ashley 10.03.14 Owners happy, but want to speak to VNZ and Samsung (Tenant) first. 24.03 VNZ ok for us to proceed. Cosite will be required. 06.5.14 Been busy negotiating with LL rebuild. We have to lift everything onto the roof and fix down the large platform over the weekend. Other work can be done in the week. Samsung have requested we move the antenna. Plans are being amended. John W busy discussing commercials. 20.05.14 Access writen into SC of lease. Plans reviewed and reviewed. BR not happy with design with steel beams. Considered various options. Need to accept the current plans. Plans to be issued and Rob to submit RMA. Plans issued. 04.06.14 Lease about to be signed. Paul Noticed generator socket. Had to change plans. 05.06.14 Plans changed and issued, back with Paul. Ben from Cable net doing Fibre design on site today. 09.06.14 Have signed lease - await Mike to return from overseas to execute. 17.06.14 Await Mike to sign the lease. CD's Rev 0 on design review - to come to me later today. | [10 empty] | 2014-09-16 | 2014-09-22 | 2014-05-28 | LOW |  | 2014-07-19 | 2014-08-12 | BUILD | 2014-09-06 | FALSE |  | 2667466 | 6487395 | Samsung Building The Warehouse Way |  |  | CELLSITE |  |  | 2014-09-30 |  |  |  |  | 2014-08-09 | [9 empty] | 2014-03-12
0 | AKL | 132 | AKL-005-086 | Northcote Point |  |  | North Shore City |  | TIER_6
0 | AKL | 133 | AKL-005-087 | Northcross South |  |  | North Shore City |  | TIER_6
0 | AKL | 134 | AKL-005-088 | Torbay exchange co-lo | AKL-005-088-A | Torbay TX only site | North Shore City |  | TIER_6 | ACTIVE | COLO | TX | COLO |  |  | COLO | [71 empty] | 2014-10-30 | [31 empty] | TXSITE
0 | AKL | 135 | AKL-005-089 | Northcote Microcell | AKL-005-089-B | RSR - Kilham Ave | North Shore City | 22 | 2014 | ACTIVE | RSR | MC | NOPOLE |  |  | STANDALONE | 5.3 |  |  | -36.802 | 174.7454 |  |  |  |  | Fibre Optic | AKL-005-078-A | FALSE | FALSE |  |  | FALSE |  |  | 2014-08-26 | 2014-09-01 | 2014-09-01 | 2014-09-15 | 2014-09-09 | 2 | 2014-09-15 | 2014-10-17 | 2014-10-31 | 2014-10-29 | 2014-11-07 | 2014-11-18 | 2 | 2014-11-14 | 2014-11-18 | DISCRETIONARY_FULL | 2014-09-16 | 2014-09-17 | 2014-11-07 | 2014-10-29 | 2 | 2014-11-14 | 2014-10-29 | 2014-10-20 | 2014-09-30 | 2014-10-24 | 2014-10-24 | 1 |  | 2014-10-31 | 2014-10-24 | [5 empty] | 2014-11-24 | 2014-11-14 | 2014-12-18 | 2014-12-19 | 2014-12-02 | 2014-12-18 | 2014-12-03 | 2014-12-15 | 2014-12-03 | [7 empty] | 2015-01-23 | 2015-01-16 |  |  |  |  | MC's installed, fibre delivered - just awaiting power | [10 empty] | 2015-01-16 | 2015-01-15 | 2014-09-17 | LOW |  | 2014-12-15 | 2014-12-03 | BUILD | 2014-12-02 | FALSE |  | 2666153 | 6487371 | RSR pole, Opposite Food City, Kilham Ave, Northcote | Date Lease Issued is the date the Telco notice was sent. - 18/09/2014 |  | CELLSITE | [17 empty] | 2014-09-01
0 | AKL | 136 | AKL-005-090 | Birkenhead Exchange co-lo | AKL-005-090-A | Exchange Co-Lo | North Shore City |  | TIER_6 | ACTIVE | COLO | TX | [104 empty] | 22A Mokoia Rd, Birkenhead |  |  | TXSITE | WIPACTIVE
0 | AKL | 137 | AKL-006-001 |  | AKL-006-001-F | Kelston | Waitakere City |  | TIER_1_ALL | ACTIVE | GF | A6 | P2 | grey |  |  | 15 | 15 |  | -36.9039 | 174.6592 |  |  |  |  | Microwave | AKL-006-021-E | [5 empty] | 2009-05-12 | [5 empty] | 2008-02-22 | 2 | 2008-04-16 | 2008-04-16 |  |  | 2008-02-29 | 2008-02-29 | 1 | 2008-02-29 | 2008-02-29 |  |  |  | 2008-05-31 |  |  | 2008-05-31 | 2008-05-26 |  | 2008-02-27 |  | 2008-05-21 | 1 | 2 | 2008-05-21 | 2008-05-21 | [6 empty] | 2008-06-25 | 2008-07-11 | 2008-07-11 |  | 2008-08-11 | 2008-08-08 | [8 empty] | 2009-02-18 | 2009-02-27 | 2009-02-18 |  |  |  |  | Site On Air |  | 2009-02-27 | [17 empty] | FALSE |  | 2658247 | 6476224 | 4083-4085 Great North Road Kelston Auckland |  |  | CELLSITE |  |  | 2014-09-05 | [5 empty] | 2008-05-27 | [8 empty] | 2008-01-18
0 | AKL | 138 | AKL-006-002 |  | AKL-006-002-D | Henderson South | Waitakere City |  | TIER_1_ALL | ACTIVE | GF | A6 | P2 | grey |  |  | 18 | 18 |  | -36.8904 | 174.626 |  |  |  |  | Microwave | AKL-006-040-A | [5 empty] | 2009-05-11 | [5 empty] | 2008-01-17 | 6 | 2008-11-06 | 2008-11-06 |  |  | 2008-02-20 | 2008-02-20 | 3 | 2008-02-20 | 2008-02-20 |  |  |  | 2008-12-10 |  |  | 2009-01-27 | 2009-01-27 |  | 2008-03-28 |  | 2008-10-21 | 2 | 6 | 2008-12-15 | 2008-12-15 | 2009-02-02 | [5 empty] | 2009-02-10 | 2009-03-20 | 2009-03-18 |  | 2009-03-25 | 2009-03-25 | [8 empty] | 2009-04-27 | 2009-04-30 | 2009-04-27 |  |  |  |  | On Air |  | 2009-04-30 |  |  |  |  | 2009-01-28 | 2009-02-02 | [11 empty] | FALSE |  | 2655317 | 6477775 | 104-106 Henderson Valley Road Henderson Auckland |  |  | CELLSITE |  |  | 2014-09-05 |  |  |  |  | 2009-02-05 | 2009-02-02 | [8 empty] | 2007-12-06
0 | AKL | 139 | AKL-006-003 |  | AKL-006-003-D | Henderson East | Waitakere City | 3 | TIER_1_ALL | ACTIVE | RT | D6 | NOPOLE | grey |  |  | 25.2 | 25.2 |  | -36.8787 | 174.6328 |  |  |  |  | Microwave | AKL-006-007-B | FALSE | FALSE |  |  | FALSE | 2009-05-08 | [5 empty] | 2009-03-09 | 5 | 2009-03-20 | 2012-01-26 |  |  | 2009-06-26 | 2009-06-25 | 3 | 2009-06-26 | 2009-06-25 |  | 2009-03-11 |  | 2009-05-01 |  |  | 2009-05-01 | 2009-05-04 | 2009-03-31 | 2009-03-25 |  | 2009-05-20 | 1 | 2 | 2009-05-29 | 2009-05-20 | [5 empty] | 2009-07-27 | 2009-07-22 | 2009-08-27 | 2009-08-27 |  | 2009-09-11 | 2009-09-04 | [8 empty] | 2009-09-11 | 2009-09-18 | 2009-09-11 |  |  |  |  | On Air Link to McLaren Park. REQUIRE : 300mmØ |  | 2009-09-18 | [17 empty] | FALSE |  | 2655948 | 6479065 | 7 Ratanui St Henderson |  |  | CELLSITE |  |  | 2014-09-05 |  |  |  |  | 2009-07-27 | 2009-07-22 | [8 empty] | 2009-02-11
0 | AKL | 140 | AKL-006-004 |  | AKL-006-004-C | Ranui | Waitakere City |  | TIER_1_ALL | ACTIVE | GF | A6 | P3 | grey |  |  | 25 | 25 |  | -36.8686 | 174.6155 |  |  |  |  | Leased Line | AKL-007-106-A | [11 empty] | 2008-04-09 | 1 |  | 2008-04-09 |  |  | 2008-05-31 | 2008-06-23 | 1 | 2008-05-31 | 2008-06-23 |  |  |  | 2008-11-30 |  |  | 2008-11-30 | 2008-09-16 |  | 2008-08-27 |  | 2008-09-19 | 2 | 1 | 2008-09-30 | 2008-09-30 | 2008-12-23 | [5 empty] | 2008-10-13 | 2009-01-27 | 2009-01-27 |  | 2009-01-26 | 2009-01-27 | [8 empty] | 2009-03-27 | 2009-04-10 | 2009-03-27 |  |  |  |  | On Air |  | 2009-04-10 |  |  |  |  | 2008-12-22 | 2008-12-23 | [11 empty] | FALSE |  | 2654419 | 6480209 | 182 Swanson Road Henderson Auckland |  |  | CELLSITE |  |  | 2014-09-05 | [5 empty] | 2008-09-25 | [8 empty] | 2008-02-27
0 | AKL | 141 | AKL-006-005 |  | AKL-006-005-E | Lincoln North | Waitakere City |  | TIER_1_ALL | ACTIVE | RSR | D6 | P4F | green |  |  | 14.4 | 14.4 |  | -36.8596 | 174.6296 |  |  |  |  | Leased Line | AKL-007-106-A | [11 empty] | 2009-03-05 | 1 | 2009-03-16 | 2009-03-05 |  |  | 2009-04-15 | 2009-03-27 |  | 2009-04-15 | 2009-03-31 |  | 2009-03-23 |  | 2009-03-23 |  |  | 2009-03-23 | 2009-03-24 | 2009-03-23 | 2009-03-18 |  | 2009-04-06 | 1 | 1 | 2009-04-06 | 2009-04-06 | 2009-05-13 |  |  |  |  | 2009-05-14 | 2009-05-14 | 2009-05-22 | 2009-05-22 |  | 2009-05-30 | 2009-06-02 | [8 empty] | 2009-06-26 | 2009-06-26 | 2009-06-26 |  |  |  |  | On Air |  | 2009-06-26 |  |  |  |  | 2009-05-11 | 2009-05-13 | [11 empty] | FALSE |  | 2655697 | 6481187 | LPR o/s 186-198 Lincoln Rd Henderson |  |  | CELLSITE |  |  | 2014-09-05 |  |  |  |  | 2009-05-14 | 2009-05-14 | [8 empty] | 2009-02-17
0 | AKL | 142 | AKL-006-006 |  | AKL-006-006-D | Te Atatu Junction | Waitakere City |  | TIER_1_ALL | ACTIVE | RSR | A6 | P4B | green | [5 empty] | -36.8582 | 174.6523 |  |  |  |  | Microwave | AKL-006-007-B | [5 empty] | 2009-05-08 | [5 empty] | 2008-04-11 | 2 | 2008-10-14 | 2008-10-14 |  |  | 2009-02-27 | 2009-02-11 | 2 | 2009-03-20 | 2009-03-20 |  |  |  | 2009-04-30 |  |  | 2009-04-30 | 2009-05-01 | 2008-09-29 | 2008-08-27 |  | 2008-10-29 | 1 | 1 | 2008-10-29 | 2008-10-29 | 2009-05-04 |  |  |  |  | 2009-05-11 | 2009-05-11 | 2009-06-19 | 2009-06-19 |  | 2009-06-24 | 2009-06-24 | [8 empty] | 2009-06-24 | 2009-06-24 | 2009-06-24 |  |  |  |  | (Jun03 DJ) Transit Traffic Mgmt being approved. On track SOA Jun26. (Jun10 DJ) CI TI bumped due to TMP restrictions Holding SOA for Jun26. (Jun18 DJ) still holding SOA Jun26. (Jun24 DJ)actual SOA advanced to Jun24 > SOA!! |  | 2009-06-26 |  |  |  |  | 2009-05-08 | 2009-05-04 | [11 empty] | FALSE |  | 2657723 | 6481300 | End of Western Off Ramp, Te Atatu Junction, Along SH16, Te Atatu, Auckland |  |  | CELLSITE |  |  | 2014-09-05 |  |  |  |  | 2009-05-11 | 2009-05-11 | [8 empty] | 2008-02-04
0 | AKL | 143 | AKL-006-007 |  | AKL-006-007-B | Central Park Hub | Waitakere City |  | TIER_1_ALL | ACTIVE | GF | A6 | P3 | grey |  |  | 35 | 35 |  | -36.8515 | 174.636 |  |  |  |  | Microwave | AKL-007-112-A | [5 empty] | 2009-05-08 | [5 empty] | 2007-09-28 | 12 |  | 2012-01-26 |  |  | 2008-04-08 | 2008-04-08 | 2 | 2008-04-08 | 2008-04-08 | DISCRETIONARY_FULL |  | 2011-09-23 | 2008-09-30 | 2011-10-07 | 10 | 2008-10-31 | 2008-09-30 |  | 2008-02-26 |  | 2008-11-21 | 5 |  | 2008-11-21 | 2011-10-18 | 2009-03-06 | [5 empty] | 2009-01-26 | 2009-03-20 | 2009-03-13 |  | 2009-04-17 | 2009-04-17 | [8 empty] | 2009-04-17 | 2009-04-17 | 2009-04-17 |  |  |  |  | CW Complete. T.I ongoing. |  | 2009-04-17 |  |  |  |  | 2009-03-02 | 2009-03-06 | [11 empty] | FALSE |  | 2656286 | 6482078 | 6 Tony St (Douglas Sheldon) Auckland |  | Approved by council on the 7.10.11, council reference: LUC-2011-858 - 10/10/2011 | CELLSITE |  |  | 2014-09-05 | [5 empty] | 2008-12-05 | [8 empty] | 2007-10-01
0 | AKL | 144 | AKL-006-008 |  | AKL-006-008-C | Te Atatu North | Waitakere City |  | TIER_1_ALL | ACTIVE | GF | A6 | OTHERS | grey |  |  | 20 | 20 |  | -36.831 | 174.6475 |  |  |  |  | Microwave | AKL-007-008-A | [11 empty] | 2008-10-31 | 2 | 2008-11-19 | 2008-11-19 |  |  | 2009-04-15 | 2009-04-16 | 2 | 2009-04-15 | 2009-04-16 |  |  |  | 2008-12-17 |  |  | 2009-01-29 | 2008-12-17 | 2009-04-24 | 2009-05-11 |  | 2009-06-10 | 1 | 2 | 2009-06-10 | 2009-06-10 | 2009-01-30 |  |  |  |  | 2009-06-11 | 2009-06-11 | 2009-07-20 | 2009-07-14 |  | 2009-07-20 | 2009-07-14 | [8 empty] | 2009-07-22 | 2009-07-24 | 2009-07-22 |  |  |  |  | On Air |  | 2009-07-24 |  |  |  |  | 2009-03-13 | 2009-01-30 | [11 empty] | FALSE |  | 2657355 | 6484327 | 745 Te Atatu Rd, Te Atatu Peninsula, Auckland |  |  | CELLSITE |  |  | 2014-09-05 |  |  |  |  | 2009-06-11 | 2009-06-11 | [8 empty] | 2008-10-08
0 | AKL | 145 | AKL-006-009 |  | AKL-006-009-B | Massey West | Waitakere City |  | TIER_1_ALL | ACTIVE | GF | A6 | P2 | grey |  |  |  | 17 |  | -36.8412 | 174.6198 |  |  |  |  | Microwave | AKL-007-041-B | [11 empty] | 2007-10-12 | 4 |  | 2014-06-04 |  |  | 2007-12-12 | 2007-12-12 | 1 | 2009-12-09 | 2009-10-30 |  |  |  | 2008-04-30 |  |  | 2008-04-30 | 2008-04-30 |  | 2007-10-18 |  | 2008-04-10 | 1 | 3 | 2008-04-10 | 2008-04-10 | 2008-05-22 | [5 empty] | 2008-05-30 | 2008-06-30 | 2008-06-24 |  | 2008-07-31 | 2008-07-21 | [8 empty] | 2009-10-13 | 2009-10-14 | 2009-10-13 |  |  |  |  | Easement agreed in principle just requires plans amended by Vector to be attached to the easement and to be sent off by Rod. As-builts to be used for easement finalisation. Power on & easement to be completed. |  | 2009-10-14 | [5 empty] | 2008-05-22 | [11 empty] | FALSE |  | 2654860 | 6483245 | Massey West 203 Triangle Rd Waitakere City Post Code |  |  | CELLSITE |  |  | 2014-09-05 | [5 empty] | 2008-05-22 | [8 empty] | 2007-10-02
0 | AKL | 146 | AKL-006-010 |  | AKL-006-010-A | Massey North | Waitakere City |  | TIER_1_ALL | ACTIVE | GF | A6 | P2 | grey |  |  | 15 | 15 |  | -36.8211 | 174.6119 |  |  |  |  | Microwave | AKL-007-008-A | [11 empty] | 2007-10-09 | 1 |  | 2007-10-09 |  |  | 2008-12-30 | 2008-06-13 | 1 | 2008-12-30 | 2008-06-13 |  |  |  | 2008-07-31 |  |  | 2008-07-31 | 2008-05-14 |  | 2007-11-06 |  | 2008-07-30 | 1 | 1 | 2008-07-30 | 2008-07-30 | [6 empty] | 2008-08-04 | 2008-09-03 | 2008-09-02 |  | 2008-09-11 | 2008-09-11 | [8 empty] | 2009-06-28 | 2009-06-27 | 2009-06-28 |  |  |  |  | On Air |  | 2009-06-27 | [17 empty] | FALSE |  | 2654199 | 6485490 | Westgate Shopping Centre Carpark Tower Auckland |  |  | CELLSITE |  |  | 2014-09-05 | [5 empty] | 2008-08-01 | [8 empty] | 2007-09-12
0 | AKL | 147 | AKL-006-011 |  | AKL-006-011-A | Swanson | Waitakere City |  | TIER_1_ALL | ACTIVE | GF | A | P3 | grey |  |  | 22 | 22 |  | -36.8661 | 174.5882 |  |  |  |  | Microwave | AKL-006-007-B | [5 empty] | 2009-05-08 | [5 empty] | 2007-10-12 | 3 | 2008-02-05 | 2008-02-05 |  |  | 2008-04-14 | 2008-04-14 | 2 | 2008-04-14 | 2008-04-14 |  |  |  | 2008-03-17 |  |  | 2008-03-17 | 2008-03-17 |  | 2007-12-20 |  | 2008-03-27 | 1 | 3 | 2008-03-27 | 2008-03-27 | [6 empty] | 2008-05-19 | 2008-05-30 | 2008-05-30 |  | 2008-06-13 | 2008-06-13 | [8 empty] | 2009-03-30 | 2009-03-30 | 2009-03-30 |  |  |  |  | (Mar24 DJ) waiting Telecom LL, RFS slipped Mar20 > Mar27. F'SOA Mar30. (Mar30 DJ) confmd delivery of Leased Line. |  | 2009-03-30 | [17 empty] | FALSE |  | 2651996 | 6480536 | 5-7 North Candia Auckland |  |  | CELLSITE | [8 empty] | 2008-05-22 | [8 empty] | 2007-10-10
0 | AKL | 148 | AKL-006-012 |  | AKL-006-012-D | Green Bay | Waitakere City |  | TIER_1_ALL | ACTIVE | GF | A | P1 | green |  |  | 12 | 12 |  | -36.9307 | 174.6799 |  |  |  |  | Leased Line | AKL-007-106-A | [11 empty] | 2007-11-23 | 3 |  | 2008-05-20 |  |  | 2007-12-12 | 2007-12-12 | 1 | 2007-12-12 | 2007-12-12 |  |  |  | 2008-06-30 |  |  | 2008-06-30 | 2008-06-20 |  | 2007-11-08 |  | 2008-05-23 | 2 | 3 | 2008-06-19 | 2008-06-19 | [6 empty] | 2008-06-18 | 2008-09-05 | 2008-08-26 |  | 2008-08-27 | 2008-08-27 | [8 empty] | 2009-03-20 | 2009-03-24 | 2009-03-20 |  |  |  |  | On Air |  | 2009-03-24 | [17 empty] | FALSE |  | 2660033 | 6473207 | 56 Godley Road Green Bay Auckland |  |  | CELLSITE | [8 empty] | 2008-06-23 | [8 empty] | 2007-11-02
0 | AKL | 149 | AKL-006-013 |  | AKL-006-013-B | Lynnmall | Waitakere City |  | TIER_1_ALL | ACTIVE | RT | B6 | OTHERS | grey |  |  | 12 | 12 |  | -36.9076 | 174.6829 |  |  |  |  | Microwave | AKL-007-112-A | [5 empty] | 2009-05-13 | [5 empty] | 2007-07-20 | 4 | 2009-04-02 | 2010-05-11 |  |  | 2008-02-28 | 2008-02-28 | 2 | 2008-02-28 | 2008-02-28 |  |  |  | 2007-09-12 |  |  | 2007-09-12 | 2007-09-12 |  | 2007-09-21 |  | 2007-11-30 | 1 | 2 | 2007-11-30 | 2007-11-30 | [6 empty] | 2008-05-13 | 2008-05-23 | 2008-05-23 |  | 2008-05-30 | 2008-05-30 | [8 empty] | 2008-12-11 | 2008-12-31 | 2008-12-11 |  |  |  |  | None |  | 2008-12-31 | [17 empty] | FALSE |  | 2660350 | 6475769 | 3053 Great North Rd (Curves Bldg) Auckland |  |  | CELLSITE |  |  | 2014-06-16 | [5 empty] | 2008-03-03 | [8 empty] | 2007-06-20
0 | AKL | 150 | AKL-006-014 |  | AKL-006-014-A | Lincoln West | Waitakere City |  | TIER_1_ALL | ACTIVE | RSR | A6 | P4A | green |  |  | 14 | 14 |  | -36.8562 | 174.6209 |  |  |  |  | Microwave | AKL-006-007-B | [5 empty] | 2009-05-08 | [5 empty] | 2007-07-31 | 3 |  | 2007-11-01 |  |  | 2008-01-16 | 2008-01-16 | 3 | 2008-01-16 | 2008-01-16 |  |  |  | 2008-01-24 |  |  | 2008-01-24 | 2008-01-24 |  | 2008-02-05 |  | 2008-03-11 | 1 | 3 | 2008-03-11 | 2008-03-11 | [6 empty] | 2008-04-07 | 2008-05-23 | 2008-05-29 |  | 2008-06-06 | 2008-05-31 | [8 empty] | 2009-04-17 | 2009-04-20 | 2009-04-17 |  |  |  |  | On Air |  | 2009-04-20 | [17 empty] | FALSE |  | 2654934 | 6481579 | 124 Universal Drive Pole number 80034 Henderson Waitakere City Auckland |  |  | CELLSITE |  |  | 2014-09-05 | [5 empty] | 2008-03-12 | [8 empty] | 2007-06-13
0 | AKL | 151 | AKL-006-015 |  | AKL-006-015-A | Clearwater Cove | Waitakere City |  | TIER_1_ALL | ACTIVE | GF | A | P1 | grey |  |  | 12 | 12 |  | -36.8103 | 174.6435 |  |  |  |  | Microwave, Leased Line, Microwave | AKL-007-129-B, AKL-007-106-A, AKL-007-129-B | [5 empty] | 2009-04-07, 2009-04-07 | [5 empty] | 2007-05-30 | 2 | 2008-07-29 | 2008-07-29 |  |  | 2008-04-08 | 2008-04-08 | 1 | 2008-04-08 | 2008-04-08 |  |  |  | 2008-08-31 |  |  | 2008-08-31 | 2008-09-23 |  | 2008-02-27 |  | 2008-05-15 | 1 | 1 | 2008-05-15 | 2008-05-15 | 2008-12-15 | [5 empty] | 2008-12-10 | 2009-01-16 | 2009-01-09 |  | 2009-01-30 | 2009-01-09 | [8 empty] | 2009-03-20 | 2009-03-18 | 2009-03-20 |  |  |  |  | (Mar20 DJ) Site On Air |  | 2009-03-18 | [5 empty] | 2008-12-15 | [11 empty] | FALSE |  | 2657044 | 6486635 | 12 Clearwater Cove (the Brokerage) Auckland |  |  | CELLSITE |  |  | 2015-12-10 | [5 empty] | 2008-12-05 | [8 empty] | 2007-05-11
0 | AKL | 152 | AKL-006-016 |  | AKL-006-016-A | Glendene West | Waitakere City |  | TIER_1_ALL | ACTIVE | RT | B6 | NOPOLE | grey |  |  | 8 | 8 |  | -36.8872 | 174.6443 |  |  |  |  | Leased Line, Microwave | AKL-007-106-A, AKL-006-001-F | [5 empty] | 2009-05-12 | [5 empty] | 2007-10-11 | 3 | 2007-10-11 | 2009-09-22 |  |  | 2008-02-22 | 2008-02-22 | 1 | 2008-02-22 | 2008-02-22 |  |  |  | 2007-11-22 |  |  | 2007-11-22 | 2007-11-22 |  | 2007-11-06 |  | 2008-03-11 | 1 | 1 | 2008-03-11 | 2008-03-11 | [6 empty] | 2008-06-09 | 2008-06-17 | 2008-06-17 |  | 2008-06-20 | 2008-06-20 | [8 empty] | 2009-01-23 | 2009-01-30 | 2009-01-23 |  |  |  |  | Site On Air |  | 2009-01-30 | [17 empty] | FALSE |  | 2656951 | 6478096 | 59 James Laurie St Glendene West Waitakere City Post Code |  |  | CELLSITE |  |  | 2014-09-05 | [5 empty] | 2008-03-12 | [8 empty] | 2007-07-10
0 | AKL | 153 | AKL-006-017 |  | AKL-006-017-A | Glen Eden North | Waitakere City |  | TIER_1_ALL | ACTIVE | GF | A6 | P3 | grey |  |  | 20 | 20 |  | -36.9093 | 174.6507 |  |  |  |  | Microwave | AKL-006-027-E | [5 empty] | 2009-05-11 | [5 empty] | 2007-07-04 | 4 |  | 2008-06-06 |  |  | 2007-12-03 | 2007-12-03 | 1 | 2007-12-03 | 2007-12-03 |  |  |  | 2008-07-12 |  |  | 2008-07-12 | 2008-06-19 |  | 2007-09-21 |  | 2008-06-11 | 2 | 4 | 2008-06-20 | 2008-06-20 | [6 empty] | 2008-07-08 | 2008-08-22 | 2008-08-22 |  | 2008-09-03 | 2008-08-28 | [8 empty] | 2009-04-01 | 2009-03-30 | 2009-04-01 |  |  |  |  | On Air |  | 2009-03-30 | [17 empty] | FALSE |  | 2657478 | 6475637 | Glen Eden North 12-14 Waikumete Rd Waitakere City Post Code |  |  | CELLSITE |  |  | 2014-09-05 | [5 empty] | 2008-06-23 | [8 empty] | 2007-05-11
0 | AKL | 154 | AKL-006-018 |  | AKL-006-018-H | Titirangi Village | Waitakere City |  | TIER_1_ALL | ACTIVE | RT | B | NOPOLE | grey |  |  | 9.8 | 9.8 |  | -36.9377 | 174.6572 |  |  |  |  | Microwave | AKL-007-133-A | [5 empty] | 2009-05-12 | [5 empty] | 2009-02-26 | 3 | 2009-07-22 | 2009-07-22 |  |  | 2009-08-24 | 2009-08-20 | 3 | 2009-11-30 | 2012-11-08 |  | 2009-03-06 |  | 2009-05-08 |  |  | 2009-08-07 | 2009-08-13 | 2009-03-23 | 2009-03-23 |  | 2009-04-28 | 2 | 3 | 2009-08-19 | 2009-08-19 | [5 empty] | 2009-08-24 | 2009-08-24 | 2009-09-14 | 2009-09-14 |  | 2009-09-25 | 2009-09-23 | [8 empty] | 2009-09-24 | 2009-09-25 | 2009-09-24 |  |  |  |  | On Air but still require lease. Letter received from LL permitting us to start building the site. Lease still in signoff, second copy taken to LL. |  | 2009-09-25 | [17 empty] | FALSE |  | 2657995 | 6472475 | 423 Titirangi Road Titirangi Auckland |  |  | CELLSITE | [7 empty] | 2009-08-24 | 2009-08-24 | [8 empty] | 2009-01-21
0 | AKL | 155 | AKL-006-019 |  | AKL-006-019-A | Whenuapai | Waitakere City |  | TIER_1_ALL | ACTIVE | GF | A | P3 | grey |  |  | 20 | 20 |  | -36.7934 | 174.6151 | [17 empty] | 2007-08-08 | 1 |  | 2007-08-08 |  |  | 2008-02-13 | 2008-02-13 | 1 | 2008-02-13 | 2008-02-13 |  |  |  | 2008-08-31 |  |  | 2008-08-31 | 2010-03-24 |  | 2007-09-21 |  | 2008-02-01 | 4 | 1 | 2009-01-27 | 2009-01-27 | [6 empty] | 2008-07-28 | 2008-09-19 | 2008-09-17 |  | 2008-09-26 | 2008-09-17 | [8 empty] | 2009-04-29 | 2009-05-08 | 2009-04-29 |  |  |  |  | On Air |  | 2009-05-08 | [17 empty] | FALSE |  | 2654549 | 6488550 | 79-89 Brigham Creek Rd (About Storage) Auckland |  |  | CELLSITE | [8 empty] | 2008-07-25 | [8 empty] | 2007-07-07
0 | AKL | 156 | AKL-006-020 |  | AKL-006-020-A | Hobsonville | Waitakere City |  | TIER_1_ALL | ACTIVE | RSR | A | P4A | green |  |  | 14 | 14 |  | -36.8012 | 174.6406 |  |  |  |  | Leased Line | AKL-007-106-A | [11 empty] | 2007-07-30 | 3 |  | 2008-05-01 |  |  | 2008-09-30 | 2008-10-01 | 3 | 2008-09-30 | 2008-10-01 |  |  |  | 2008-07-31 |  |  | 2008-07-31 | 2008-08-28 |  | 2008-04-10 |  | 2008-04-30 | 2 | 3 | 2008-05-12 | 2008-05-12 | [6 empty] | 2008-09-29 | 2008-10-09 | 2008-10-09 |  |  | 2008-10-09 | [8 empty] | 2009-04-28 | 2009-05-08 | 2009-04-28 |  |  |  |  | On Air |  | 2009-05-08 | [17 empty] | FALSE |  | 2656805 | 6487642 | LPR o/s 116 Hobsonville Rd, Hobsonville, Waitakere City, Auckland |  |  | CELLSITE |  |  | 2015-12-10 | [5 empty] | 2008-09-29 | [8 empty] | 2007-07-09
0 | AKL | 157 | AKL-006-021 |  | AKL-006-021-E | Glendene East | Waitakere City |  | TIER_1_ALL | ACTIVE | GF | A6 | P3 | green |  |  | 20 | 20 |  | -36.8881 | 174.6622 |  |  |  |  | Microwave | AKL-007-129-B | [11 empty] | 2008-02-27 | 2 | 2008-03-27 | 2008-03-27 |  |  | 2008-04-04 | 2008-04-04 | 1 | 2008-04-04 | 2008-04-04 |  |  |  | 2008-06-30 |  |  | 2008-06-30 | 2008-05-28 |  | 2008-04-01 |  | 2008-06-27 | 2 | 2 | 2008-07-15 | 2008-07-15 | [6 empty] | 2008-07-14 | 2008-08-19 | 2008-08-15 |  | 2008-08-22 | 2008-08-22 | [8 empty] | 2009-02-17 | 2009-02-09 | 2009-02-17 |  |  |  |  | Site On Air |  | 2009-02-09 | [17 empty] | FALSE |  | 2658544 | 6477963 | 33 Bancroft Crescent Glendene Auckland |  |  | CELLSITE |  |  | 2014-09-05 | [5 empty] | 2008-06-30 | [8 empty] | 2008-01-18
0 | AKL | 158 | AKL-006-023 |  | AKL-006-023-A | Waikaukau | Waitakere City |  | TIER_1_ALL | ACTIVE | GF | A6 | P3 | grey |  |  | 25 | 25 |  | -36.9075 | 174.6364 |  |  |  |  | Microwave, Microwave | AKL-006-017-A, AKL-006-017-A | [5 empty] | 2009-03-31, 2009-03-31 | [5 empty] | 2007-07-01 | 1 | 2007-07-01 | 2007-07-01 |  |  | 2007-07-27 | 2007-07-27 | 1 | 2007-07-27 | 2007-07-27 |  |  |  | 2007-10-31 |  |  | 2007-10-31 | 2007-10-31 |  | 2008-01-21 |  | 2007-12-11 | 1 | 1 | 2007-12-11 | 2007-12-11 | [6 empty] | 2008-04-14 | 2008-05-07 | 2008-05-07 |  | 2008-05-23 | 2008-05-23 | [8 empty] | 2009-04-01 | 2009-04-02 | 2009-04-01 |  |  |  |  | (Mar27 DJ) Fcst SOA Mar 31st. Landowner to be contacted today and asked about Interferance issue. DJ |  | 2009-03-31 | [17 empty] | FALSE |  | 2656204 | 6475860 | 8 Waikaukau Rd Glen Eden (Blow Molders) Waitakere City Post Code |  |  | CELLSITE |  |  | 2014-09-05 | [5 empty] | 2007-12-12 | [8 empty] | 2007-05-14
0 | AKL | 159 | AKL-006-024 |  | AKL-006-024-D | McLeod Park | Waitakere City |  | TIER_1_ALL | ACTIVE | GF | A6 | P2 | grey |  |  | 20 | 20 |  | -36.8778 | 174.6517 |  |  |  |  | Leased Line | AKL-007-106-A | [11 empty] | 2008-04-21 | 1 |  | 2008-04-21 |  |  | 2008-04-29 | 2008-04-29 | 1 | 2008-04-29 | 2008-04-29 | [7 empty] | 2008-06-23 |  | 2008-04-29 |  | 2008-06-26 | 1 | 1 | 2008-06-26 | 2008-06-26 | [6 empty] | 2008-07-28 | 2008-08-25 | 2008-08-25 |  | 2008-08-30 | 2008-08-27 | [8 empty] | 2009-04-08 | 2009-04-17 | 2009-04-08 |  |  |  |  | On Air |  | 2009-04-17 | [17 empty] | FALSE |  | 2657634 | 6479130 | 151 McLeod Road McLeod Park Auckland |  |  | CELLSITE |  |  | 2014-09-05 | [5 empty] | 2008-07-01 | [8 empty] | 2008-04-07
0 | AKL | 160 | AKL-006-025 |  | AKL-006-025-E | Sunnyvale | Waitakere City |  | TIER_1_ALL | ACTIVE | GF | A6 | P1 | green |  |  | 15 | 15 |  | -36.8957 | 174.6315 |  |  |  |  | Microwave | AKL-006-040-A | [5 empty] | 2009-05-11 | [5 empty] | 2007-09-28 | 4 |  | 2008-03-14 |  |  | 2007-11-29 | 2007-11-29 | 1 | 2007-11-29 | 2007-11-29 |  |  |  | 2008-04-30 |  |  | 2008-04-30 | 2008-04-30 |  | 2008-01-11 |  | 2008-04-22 | 1 | 4 | 2008-04-22 | 2008-04-22 | [6 empty] | 2008-05-14 | 2008-06-20 | 2008-06-20 |  | 2008-06-27 | 2008-06-27 | [8 empty] | 2009-03-12 | 2009-03-17 | 2009-03-12 |  |  |  |  | On Air |  | 2009-03-17 | [17 empty] | FALSE |  | 2655790 | 6477174 | 38-44 Bruce McLaren Road Sunnyvale |  |  | CELLSITE |  |  | 2014-09-05 | [5 empty] | 2008-05-22 | [8 empty] | 2007-09-10
0 | AKL | 161 | AKL-006-026 |  | AKL-006-026-F | Titirangi North | Waitakere City |  | TIER_1_ALL | ACTIVE | RSR | A | P4A | green | [5 empty] | -36.9209 | 174.6592 |  |  |  |  | Microwave, Microwave, Leased Line | AKL-006-029-C, AKL-006-029-C, AKL-007-106-A | [5 empty] | 2009-03-31, 2009-03-31 | [5 empty] | 2008-03-17 | 2 |  | 2008-05-01 |  |  | 2008-08-01 | 2008-06-13 | 2 | 2008-08-01 | 2008-06-13 |  |  |  | 2008-08-23 |  |  | 2008-08-23 | 2008-06-06 |  | 2008-05-15 |  | 2008-06-05 | 2 | 2 | 2008-07-11 | 2008-07-11 | [6 empty] | 2008-07-07 | 2008-08-08 | 2008-08-08 |  | 2008-08-28 | 2008-08-09 | [8 empty] | 2009-02-23 | 2009-02-24 | 2009-02-23 |  |  |  |  | On Air |  | 2009-02-24 | [17 empty] | FALSE |  | 2658210 | 6474329 | Outside 83A Pleasant Road Titirangi Auckland |  |  | CELLSITE | [8 empty] | 2008-06-16 | [8 empty] | 2008-02-04
0 | AKL | 162 | AKL-006-027 |  | AKL-006-027-E | Kelston Gully | Waitakere City |  | TIER_1_ALL | ACTIVE | RT | B6 | NOPOLE | grey |  |  | 13.7 | 13.7 |  | -36.9096 | 174.6634 | [17 empty] | 2008-07-29 | 5 | 2009-01-27 | 2009-01-27 |  |  | 2008-12-19 | 2008-12-09 | 5 | 2009-02-13 | 2009-02-13 |  |  |  | 2008-09-13 |  |  | 2009-03-30 | 2009-03-19 | 2009-01-19 | 2008-09-26 |  | 2008-11-03 | 2 | 5 | 2009-02-09 | 2009-02-09 | [6 empty] | 2009-03-03 | 2009-03-27 | 2009-03-27 |  | 2009-05-29 | 2009-05-29 | [8 empty] | 2009-06-18 | 2009-06-25 | 2009-06-18 |  |  |  |  | On Air |  | 2009-06-25 | [17 empty] | FALSE |  | 2658605 | 6475579 | 2 West Coast Rd, Kelston, Auckland |  |  | CELLSITE |  |  | 2014-09-05 |  |  |  |  | 2009-03-02 | 2009-03-02 | [8 empty] | 2008-06-20
0 | AKL | 163 | AKL-006-028 |  | AKL-006-028-D | West Harbour | Waitakere City | 3 | TIER_1_ALL | ACTIVE | GF | Ab6 | P3 | grey |  |  | 17.2 | 17.2 |  | -36.8148 | 174.6257 |  |  |  |  | Microwave, Microwave | AKL-006-007-B, AKL-006-007-B | FALSE | FALSE |  |  | FALSE | 2009-04-29, 2009-04-29 | [5 empty] | 2008-11-28 | 11 | 2009-06-12 | 2014-05-26 |  |  | 2009-08-31 | 2009-08-26 | 4 | 2009-10-01 | 2009-10-09 |  | 2009-05-29 |  | 2009-09-16 |  |  | 2009-09-16 | 2009-09-16 | 2009-05-29 | 2009-06-03 |  | 2009-06-19 | 5 | 10 | 2009-08-11 | 2009-12-23 | 2009-02-02 |  |  |  |  | 2009-09-15 | 2009-09-16 | 2009-10-30 | 2009-10-30 |  | 2009-10-30 | 2009-10-30 | [8 empty] | 2009-11-06 | 2009-11-06 | 2009-11-06 |  |  |  |  | On Air Link to Paremoremo Prison Co Lo REQUIRE : 600mmØ |  | 2009-11-06 |  |  |  |  | 2009-01-28 | 2009-02-02 | [11 empty] | FALSE |  | 2655442 | 6486163 | Watercare Yard, Adj to 76 Hobsonville Rd, West Harbour, Auckland |  |  | CELLSITE |  |  | 2014-09-05 |  |  |  |  | 2009-09-15 | 2009-09-15 | [8 empty] | 2008-10-28
0 | AKL | 164 | AKL-006-029 |  | AKL-006-029-C | Glen Eden West | Waitakere City |  | TIER_1_ALL | ACTIVE | RT | A | NOPOLE | grey | [5 empty] | -36.922 | 174.6387 |  |  |  |  | Microwave, Microwave | AKL-006-023-A, AKL-006-023-A | [5 empty] | 2009-03-31, 2009-03-31 | [5 empty] | 2008-02-27 | 6 | 2008-12-15 | 2010-04-21 |  |  | 2008-04-14 | 2008-04-14 | 4 | 2008-04-14 | 2008-04-14 |  |  |  | 2009-05-15 |  |  | 2009-05-15 | 2009-05-01 | 2008-11-17 | 2008-04-18 |  | 2008-05-26 | 3 | 5 | 2008-12-16 | 2009-11-24 | [5 empty] | 2009-05-18 | 2009-05-18 | 2009-06-08 | 2009-06-10 |  | 2009-06-27 | 2009-06-26 | [8 empty] | 2009-06-26 | 2009-06-29 | 2009-06-26 |  |  |  |  | On Air |  | 2009-06-29 | [17 empty] | FALSE |  | 2656380 | 6474250 | 108 Glengarry Road Glen Eden Auckland |  |  | CELLSITE | [7 empty] | 2009-05-18 | 2009-05-18 | [8 empty] | 2008-02-21
0 | AKL | 165 | AKL-006-031 |  | AKL-006-031-A | Western Heights | Waitakere City |  | TIER_1_ALL | ACTIVE | RSR | A6 | P4A | green |  |  | 14 | 14 |  | -36.883 | 174.6147 |  |  |  |  | Microwave | AKL-006-040-A | [5 empty] | 2009-05-11 | [5 empty] | 2007-07-30 | 5 |  | 2009-05-08 |  |  | 2008-01-16 | 2008-01-16 | 2 | 2008-01-16 | 2008-01-16 |  |  |  | 2007-11-12 |  |  | 2007-11-12 | 2007-11-12 |  | 2008-01-22 |  | 2008-03-19 | 1 | 3 | 2008-03-19 | 2008-03-19 | [6 empty] | 2008-04-14 | 2008-05-30 | 2008-05-30 |  | 2008-06-20 | 2008-06-12 | [8 empty] | 2009-03-12 | 2009-03-26 | 2009-03-12 |  |  |  |  | On Air |  | 2009-03-26 | [17 empty] | FALSE |  | 2654325 | 6478612 | Lightpole replacement at cnr Sturges Road & Palamino Drive Western Heights Waitakere City Auckland |  |  | CELLSITE |  |  | 2014-09-05 | [5 empty] | 2008-03-20 | [8 empty] | 2007-07-16
0 | AKL | 166 | AKL-006-032 |  | AKL-006-032-A | Glendene South | Waitakere City |  | TIER_1_ALL | ACTIVE | RSR | A6 | P4A | green |  |  | 0 | 0 |  | -36.897 | 174.6478 |  |  |  |  | Microwave | AKL-006-001-F | [5 empty] | 2009-05-12 | [5 empty] | 2007-07-31 | 3 |  | 2008-02-25 |  |  | 2008-01-16 | 2008-01-16 | 2 | 2008-01-16 | 2008-01-16 |  |  |  | 2007-11-22 |  |  | 2007-11-22 | 2007-11-22 |  | 2008-01-22 |  | 2008-03-07 | 1 | 3 | 2008-03-07 | 2008-03-07 | [6 empty] | 2008-04-07 | 2008-05-23 | 2008-05-29 |  | 2008-06-06 | 2008-06-06 | [8 empty] | 2009-02-17 | 2009-02-09 | 2009-02-17 |  |  |  |  | On Air |  | 2009-02-09 | [17 empty] | FALSE |  | 2657240 | 6477000 | Streetlight pole opposite 4219 Great North Rd Glendene South Waitakere City Auckland |  |  | CELLSITE |  |  | 2014-09-05 | [5 empty] | 2008-03-10 | [8 empty] | 2007-07-01
0 | AKL | 167 | AKL-006-033 |  | AKL-006-033-C | Piha | Waitakere City |  | TIER_1_ALL | ACTIVE | GF | A | P2 | Forest Green |  | COSITE | 8 | 8 |  | -36.9628 | 174.4717 |  |  |  |  | Leased Line | AKL-007-106-A | [11 empty] | 2008-07-22 | 2 | 2009-04-14 | 2009-04-14 |  |  |  | 2008-08-18 | 1 | 2009-04-30 | 2009-04-20 |  |  |  | 2009-05-01 |  |  | 2009-05-01 | 2009-04-30 | 2008-09-03 | 2008-09-08 |  | 2008-10-03 | 1 | 1 | 2008-10-03 | 2008-10-03 | 2009-04-20 |  |  |  |  | 2009-05-04 | 2009-05-04 | 2009-06-12 | 2009-06-05 |  | 2009-06-12 | 2009-06-12 | [8 empty] | 2009-06-13 | 2009-06-15 | 2009-06-13 |  |  |  |  | On Air |  | 2009-06-15 |  |  |  |  | 2009-04-17 | 2009-04-20 | [11 empty] | FALSE |  | 2641421 | 6469991 | Track leading off 89 Piha Road Piha, Auckland |  |  | CELLSITE | [7 empty] | 2009-05-04 | 2009-05-04 | [8 empty] | 2008-07-11
0 | AKL | 168 | AKL-006-034 |  | AKL-006-034-A | Waitakere Village | Waitakere City |  | TIER_1_ALL | ACTIVE | COLO | A | COLO | grey |  | COSITE |  |  |  | -36.8534 | 174.5452 |  |  |  |  | Leased Line | AKL-007-106-A | [11 empty] | 2007-12-07 | 2 |  | 2008-10-22 |  |  | 2009-03-15 | 2009-03-31 | 1 | 2009-03-15 | 2009-03-31 |  |  |  | 2008-05-31 |  |  | 2008-05-31 | 2008-05-23 |  | 2008-03-06 |  | 2008-05-20 | 2 | 2 | 2008-12-01 | 2008-12-01 | [6 empty] | 2009-03-24 | 2009-04-03 | 2009-04-03 |  | 2009-05-01 | 2009-05-05 | [8 empty] | 2009-05-27 | 2009-05-22 | 2009-05-27 |  |  |  |  | Build proceeding, awaiting LL connection 26/05 |  | 2009-05-22 | [17 empty] | FALSE |  | 2648184 | 6482017 | McEntee Road Waitakere Village Auckland |  |  | CELLSITE | [8 empty] | 2009-03-24 | [8 empty] | 2007-12-13
0 | AKL | 169 | AKL-006-036 |  | AKL-006-036-G | Harbour View | Waitakere City |  | TIER_1_ALL | ACTIVE | GF | A6 | P1 | grey |  |  | 13.8 | 13.8 |  | -36.8419 | 174.6512 |  |  |  |  | Microwave | AKL-006-008-C | [5 empty] | 2009-05-11 | [5 empty] | 2008-11-20 | 4 | 2009-03-27 | 2009-03-27 |  |  | 2009-03-31 | 2009-04-07 | 4 | 2009-06-15 | 2009-06-24 |  | 2008-11-27 |  | 2009-01-31 |  |  | 2009-05-15 | 2009-05-15 | 2009-03-31 | 2009-04-01 | 2009-04-06 | 2009-04-30 | 2 | 4 | 2009-04-30 | 2009-05-05 | 2009-02-03 |  |  |  |  | 2009-05-18 | 2009-05-18 | 2009-06-30 | 2009-06-30 |  | 2009-07-22 | 2009-07-22 | [8 empty] | 2009-08-12 | 2009-08-13 | 2009-08-12 |  |  |  |  | On Air |  | 2009-08-13 |  |  |  |  | 2009-02-06 | 2009-02-03 | [11 empty] | FALSE |  | 2657666 | 6483108 | 556 Te Atatu Rd, Te Atatu Peninsula, Auckland |  |  | CELLSITE |  |  | 2014-09-05 |  |  |  |  | 2009-05-18 | 2009-05-18 | [8 empty] | 2008-11-04
0 | AKL | 170 | AKL-006-037 |  | AKL-006-037-G | Lincoln Rd South | Waitakere City |  | TIER_1_ALL | ACTIVE | RSR | D6 | P4F | green |  |  | 14.8 | 14.8 |  | -36.8711 | 174.6283 |  |  |  |  | Microwave | AKL-006-007-B | [5 empty] | 2009-05-08 | [5 empty] | 2009-03-05 | 1 | 2009-03-16 | 2009-03-05 |  |  | 2009-04-15 | 2009-03-27 |  | 2009-04-15 | 2009-03-31 |  | 2009-03-23 |  | 2009-03-23 |  |  | 2009-03-23 | 2009-03-24 | 2009-03-23 | 2009-03-18 |  | 2009-04-06 | 1 | 1 | 2009-04-06 | 2009-04-06 | 2009-05-13 |  |  |  |  | 2009-05-04 | 2009-05-04 | 2009-05-25 | 2009-05-22 |  | 2009-06-05 | 2009-06-04 | [8 empty] | 2009-06-04 | 2009-06-11 | 2009-06-04 |  |  |  |  | On Air |  | 2009-06-11 |  |  |  |  | 2009-05-08 | 2009-05-13 | [11 empty] | FALSE |  | 2655555 | 6479916 | Outside 45 Lincoln Rd Henderson |  |  | CELLSITE |  |  | 2014-09-05 |  |  |  |  | 2009-05-04 | 2009-05-04 | [8 empty] | 2009-02-17
0 | AKL | 171 | AKL-006-038 |  | AKL-006-038-C | Cnr Hutchinson & Willerton | Waitakere City |  | TIER_1_ALL | ACTIVE | RSR | D | P4F | green |  |  | 12 | 12 |  | -36.9192 | 174.676 |  |  |  |  | Leased Line | AKL-007-106-A | [11 empty] | 2009-04-08 | 1 | 2009-04-03 | 2009-04-08 |  |  | 2009-06-09 | 2009-06-24 |  | 2009-06-09 | 2009-06-24 |  | 2009-04-30 |  | 2009-06-05 |  |  | 2009-06-05 | 2009-06-02 | 2009-04-22 | 2009-04-15 |  | 2009-05-15 | 1 | 1 | 2009-05-13 | 2009-05-15 | 2009-06-18 |  |  |  |  | 2009-06-15 | 2009-06-15 | 2009-08-20 | 2009-08-19 |  | 2009-08-24 | 2009-08-24 | [8 empty] | 2009-08-31 | 2009-08-30 | 2009-08-31 |  |  |  |  | On Air |  | 2009-08-30 |  |  |  |  | 2009-06-19 | 2009-06-18 | [11 empty] | FALSE |  | 2659705 | 6474494 | Vector pole outside on roading reserve adjacent and serving 75 Hutcinson. |  |  | CELLSITE | [7 empty] | 2009-06-15 | 2009-06-15 | [8 empty] | 2009-03-23
0 | AKL | 172 | AKL-006-040 |  | AKL-006-040-A | Henderson Central | Waitakere City |  | TIER_1_ALL | ACTIVE | RT | B6 | NOPOLE | grey |  |  | 22 | 22 |  | -36.8823 | 174.6321 |  |  |  |  | Microwave, Leased Line | AKL-006-003-D, AKL-007-106-A | [5 empty] | 2009-05-11 | [5 empty] | 2008-07-31 | 3 |  | 2010-05-04 |  |  | 2008-08-31 | 2008-09-15 | 1 | 2008-08-31 | 2008-09-15 |  | 2010-05-26 |  | 2010-06-25 |  |  |  | 2010-06-25 |  | 2008-09-08 |  | 2008-09-24 | 1 | 1 | 2008-09-24 | 2008-09-24 | [6 empty] | 2008-10-28 | 2008-11-24 | 2008-11-25 |  | 2009-02-20 | 2009-02-20 | [8 empty] | 2009-02-24 | 2009-02-26 | 2009-02-24 |  |  |  |  | On Air 14/4 - NEED TO RELOCATE CABINETS. Drawings to be issued asap. Possibly require new RMA and lease amendment/variation. Drawings submitted to John Henry PM 28.04.2010 for approval. Site vist with Woosh 28.04.2010 to determine temp antenna mounts during construction. 12 May. Sean to submit RMA today. Plans have been forwarded to John Henry PM. 19 May. RMA lodged, await chq for payment. Temp mounts dont need consent. 26 May. Chq for RMA submission ready today. Temp mounts erected today. |  | 2009-02-26 | [17 empty] | FALSE |  | 2655870 | 6478659 | John Henry Centre, 4-6 Edsel Rd, Henderson, Waitakere City, Auckland |  |  | CELLSITE |  |  | 2014-09-05 | [5 empty] | 2008-10-13 | [8 empty] | 2008-05-27
0 | AKL | 173 | AKL-006-043 |  | AKL-006-043-C | Titirangi East | Waitakere City |  | TIER_1_ALL | ACTIVE | GF | A | P3 | green |  |  | 22 | 22 |  | -36.9232 | 174.6886 |  |  |  |  | Leased Line, Microwave | AKL-007-106-A, AKL-007-110-F | [11 empty] | 2008-10-15 | 4 | 2009-04-15 | 2009-04-15 |  |  |  | 2008-11-26 | 2 | 2009-04-30 | 2009-04-28 |  | 2008-12-10 |  | 2009-03-27 |  |  | 2009-03-27 | 2009-03-25 |  | 2008-10-20 |  | 2008-11-21 | 2 | 2 | 2008-12-15 | 2008-12-15 | 2009-03-27 |  |  |  |  | 2009-03-31 | 2009-03-31 | 2009-04-30 | 2009-04-29 |  | 2009-04-30 | 2009-04-29 | [8 empty] | 2009-06-08 | 2009-06-10 | 2009-06-08 |  |  |  |  | On Air |  | 2009-06-10 |  |  |  |  | 2009-03-20 | 2009-03-27 | [11 empty] | FALSE |  | 2660820 | 6474030 | Titirangi Golf Course, Cnr Golf & Portage Rds, Titirangi, Waitakere City |  |  | CELLSITE | [7 empty] | 2009-03-31 | 2009-03-31 | [8 empty] | 2008-09-16
0 | AKL | 174 | AKL-006-045 | Riversdale Rd | AKL-006-045-H | Tony Segedin HARD MATCH | Waitakere City |  | TIER_6 | ACTIVE | RSR | DU | P4F |  | INLINE | STANDALONE |  |  |  | -36.8965 | 174.678 | [6 empty] | FALSE | FALSE |  |  | FALSE |  | 2011-10-06 | 2011-10-06 | 2011-10-13 | 2011-10-19 | 2011-11-18 | 2011-11-21 | 1 | 2011-11-18 | 2011-11-21 | 2012-02-15 | 2012-02-09 | 2012-03-19 | 2012-03-01 |  | 2012-03-30 | 2012-03-01 | DISCRETIONARY_FULL | 2011-12-12 | 2011-12-13 | 2012-02-22 | 2012-01-20 | 1 | 2012-02-29 | 2012-01-25 | [35 empty] | hardmatched | [17 empty] | HARDMATCH |  | FALSE |  | 2659930 | 6477012 | 11 Tony Segedin Road |  | Lodged at council with planner Mark Ross on the 13.12.2011. - 14/12/2011 Approved on the 20.1.2012, council reference number: R/LUC/2011/4573 with Rev 1 Plans - 25/01/2012 | CELLSITE | WIPHOLDING
0 | AKL | 175 | AKL-006-046 | Woodlands Park | AKL-006-046-A | Woodlands Park | Waitakere City | 3 | TIER_3 | ACTIVE | GF | D | P2 | Grey | INLINE | COSITE | 14.5 | 15 |  | -36.9528 | 174.6226 |  |  |  |  | Microwave | AKL-007-075-A | FALSE | FALSE |  |  | FALSE |  | 2011-06-07 | 2011-05-31 | 2011-06-07 | 2011-06-02 | 2011-07-28 | 2011-07-29 | 3 | 2011-07-28 | 2012-12-03 | 2012-02-22 | 2012-02-29 | 2012-09-25 | 2012-09-11 |  | 2012-10-02 | 2012-09-11 | DISCRETIONARY_FULL | 2011-08-08 | 2011-08-08 | 2012-06-22 | 2012-06-18 | 1 | 2012-06-29 | 2012-06-19 | 2012-07-20 |  | 2012-10-12 | 2012-10-05 | 2 | 3 | 2012-10-12 | 2013-08-30 | 2012-10-14 |  |  | 2012-09-12 |  | 2012-10-09 | 2012-10-09 | 2012-10-23 | 2012-10-23 | 2012-10-18 | 2012-10-29 | 2012-10-29 | [8 empty] | 2012-11-08 | 2012-11-30 | 2012-11-21 | 2013-01-10 | 2012-11-23 | 2013-08-30 | 2013-09-03 | This is a D site |  | 2012-11-07 | 2012-10-06 | 2012-10-06 | 2012-10-10 | 2012-10-10 | 2012-10-10 | 2012-10-14 | 2012-11-02 | 2012-10-31 | 2012-11-09 | 2012-11-06 |  |  | TIER_1_INFILL |  |  | BUILD | 2012-10-18 | TRUE |  | 2654881 | 6470856 | Watercare Woodlands Park Water Reservoir Off Exhibition Dr, Waitakere, Auckland |  | Discretionary application Lodged on the 8.8.2011 - 10/08/2011 | CELLSITE | [15 empty] | 2012-11-09 | 2012-11-12
0 | AKL | 176 | AKL-006-047 | McLaren Park | AKL-006-047-A | Forest Hill LPR | Waitakere City | 3 | TIER_1_INFILL | ACTIVE | RSR | DU | P4F | Green | INLINE |  | 13 | 13.5 |  | -36.8969 | 174.6191 |  |  |  |  | Microwave | AKL-006-003-D | FALSE | FALSE |  |  | FALSE |  | 2011-06-07 | 2011-06-07 | 2011-06-14 | 2011-06-07 | 2011-07-28 | 2011-07-29 | 1 | 2011-07-28 | 2011-07-29 | 2012-01-24 | 2012-01-24 | 2012-03-22 | 2012-01-24 |  | 2012-03-30 | 2012-02-14 | NES | 2011-08-08 | 2011-08-08 | 2011-09-19 | 2011-09-06 | 1 | 2011-09-26 | 2011-09-07 |  |  |  | 2012-07-13 | 1 |  |  | 2012-07-13 | 2012-07-21 |  |  |  |  | 2012-07-23 | 2012-07-25 | 2012-07-30 | 2012-07-27 | 2012-07-31 | 2012-08-21 | 2012-08-21 |  | 2012-08-21 | [6 empty] | 2012-08-21 | 2012-09-14 | 2012-08-28 | 2012-10-06 | 2012-08-31 | 2013-04-30 | 2013-04-22 | 12.06.2014 : "D" configuration build. (APM, Battery, & 2 x RFC) using version "B" cabinets. Thus making it a "DU" Site. (As per Ron Bush/blr) |  | 2012-08-20 | 2012-07-21 | 2012-07-21 | 2012-07-20 | 2012-07-21 | 2012-07-16 | 2012-07-21 | 2012-07-31 | 2012-08-16 | 2012-08-27 | 2012-08-27 | [5 empty] | BUILD | 2012-07-31 | FALSE |  | 2654687 | 6477067 | 34 A McLaren Park Forest Hill Road, Henderson, Auckland |  | NES S139 Application lodged on the 8/82011 - 10/08/2011 | CELLSITE | [15 empty] | 2012-08-27 | 2012-08-22
0 | AKL | 177 | AKL-006-048 | Triangle Road | AKL-006-048-A | Triangle Road - LPR | Waitakere City | 3 | TIER_1_INFILL | ACTIVE | RSR | Ab6 | P4B | green | INLINE |  | 14.7 | 15.2 |  | -36.8341 | 174.6038 |  |  |  |  | Microwave | AKL-007-015-C | FALSE | FALSE |  |  | FALSE | 2011-06-01 | 2011-06-07 | 2011-06-07 | 2011-06-14 | 2011-06-07 | 2011-07-28 | 2011-07-29 | 2 | 2011-07-28 | 2011-09-20 | 2012-02-29 | 2012-01-24 | 2012-03-15 | 2012-01-24 |  | 2012-03-22 | 2012-02-14 | DISCRETIONARY_FULL | 2011-08-08 | 2011-08-08 | 2011-10-31 | 2011-10-27 | 1 | 2011-11-07 | 2011-10-27 |  |  | 2012-03-01 | 2012-03-02 | 1 |  |  | 2012-03-02 | 2012-04-02 |  |  |  |  | 2012-03-26 | 2012-03-26 | 2012-04-05 | 2012-04-10 | 2012-04-02 | 2012-04-13 | 2012-04-12 | [8 empty] | 2012-04-13 | 2012-04-13 | 2012-04-13 | 2012-05-23 | 2012-05-04 | 2012-08-02 | 2012-09-03 | CP complete. WO1 issued. BUILD SITE. Have RC, Await AKL city council license. To issue WO2 in Nov |  | 2012-04-13 | 2012-04-02 | 2012-04-02 | 2012-04-02 | 2012-04-02 | 2012-04-02 | 2012-04-02 | 2012-04-04 | 2012-04-10 | [8 empty] | 2012-04-02 | FALSE |  | 2653448 | 6484056 | intersection of Triangle Road and Don Buck Road, Auckland |  | Discretionary consent lodged on the 8/8/2011 - 10/08/2011 | CELLSITE |  |  | 2014-09-05 | [12 empty] | 2012-04-20 | 2012-04-20
0 | AKL | 178 | AKL-006-049 | RBI - Waitakere Village |  |  | Waitakere City |  | RBI | [22 empty] | FALSE
0 | AKL | 179 | AKL-006-050 | RBI - Huia |  |  | Waitakere City |  | RBI | [22 empty] | FALSE
0 | AKL | 180 | AKL-006-051 | 107 Waima Cres Mini-Repeater | AKL-006-051-A | Waima Cres | Waitakere City |  | TIER_6 | ACTIVE | [106 empty] | 107 Waima Cres Titirangi
0 | AKL | 181 | AKL-006-052 | RCL Construction Mini Repeater |  |  | Waitakere City |  | TIER_6
0 | AKL | 182 | AKL-006-053 | Albany North | AKL-006-053-F | Dairy Flat Highway | Waitakere City | 22 | TIER_5 | ACTIVE | GF | DF | T2 25 RF |  | STACK_A | STANDALONE | 24.5 | 25 | [7 empty] | Fibre Optic | AKL-005-088-A | FALSE | FALSE |  |  | FALSE |  | 2015-11-19 | 2015-11-19 | 2015-11-20 | 2015-11-19 | 2016-01-18 | 2016-01-15 | 1 | 2016-01-22 | 2016-01-15 | 2016-02-19 |  | 2016-03-30 |  |  | 2016-03-31 |  | NON_COMPLYING_FULL | 2016-02-22 |  | 2016-04-25 |  |  | 2016-04-25 |  | 2016-02-22 |  | 2016-03-31 |  |  |  | 2016-03-31 | [6 empty] | 2016-06-20 |  | 2016-07-18 |  |  | 2016-08-01 | [10 empty] | 2016-09-05 | [16 empty] | 2016-08-22 |  |  |  | TIER_1_INFILL |  |  | BUILD |  | FALSE |  |  |  | 960 Dairy Flat Highway |  |  | CELLSITE | WIPACTIVE |  |  | ROAMING |  |  |  | 2016-04-28 |  |  | 2015-11-19 |  |  | 2016-05-23 |  |  |  | 2015-11-19
0 | AKL | 183 | AKL-006-054 | Coatesville | AKL-006-054-B | Coatsville GF | Waitakere City | 22 | TIER_5 | ACTIVE | GF | DF | T2 20 RF |  | STACK_A | COSITE | 18.5 | 20 |  | -36.7096 | 174.6374 |  |  |  |  | Microwave | AKL-007-112-A | FALSE | FALSE |  |  | FALSE |  | 2015-09-14 | 2015-09-14 | 2015-09-21 | 2015-09-28 | 2015-10-16 | 2012-08-22 | 3 |  | 2015-11-12 | 2012-09-21 | 2012-09-18 | 2012-12-07 | 2012-12-14 |  | 2012-12-14 | 2012-12-14 | NON_COMPLYING_FULL | 2015-10-23 | 2015-10-20 | 2015-11-23 | 2015-12-04 | 1 | 2015-11-30 | 2015-12-04 | 2015-11-09 | 2015-11-10 | 2015-12-14 | 2015-12-14 | 1 |  | 2015-12-14 | 2015-12-14 | [5 empty] | 2016-02-29 |  | 2016-03-28 |  |  | 2016-04-11 | [10 empty] | 2016-05-09 | [5 empty] | GF Cosite with VNZ, 20M permitted. TX and RF happy. Landlord was on site at Caravan - he is happy. TP are happy. Just need to construct 200m of road and ask VNZ for power share. Site is Hard Match. Thus we cant build the road now. Landlord not happy. Brad will try and make arrangement re lease commencement date and pay road on build. 27/11/2012 RMA Withdrawn. Will resubmit after Landlord has built road. RMA will be withdrawn - as is we have to show we have a road / access to site. We cant. Council want detail about the road construction - we dont have it. Thus withdraw, let Landlord build road. Resubmit without road detail - as it will now be shown as existing. 24.01.2013 Landlord has engaged a contractor, Brad to advise if RC has commenced for his road (AS have offered to assist) 25/08 AS RF has validated old site location and it has passed. Need to Caravan as everything as it is what we wanted before RMA submission. 12/1/16 - VF co-site application submitted | [10 empty] | 2016-04-25 |  |  |  | TIER_1_INFILL |  |  | BUILD |  | FALSE |  | 2656710 | 6497817 | off 326 Sunnyside Road |  |  | CELLSITE | WIPHOLDING |  |  | ROAMING |  | 2015-12-01 | 2016-01-14 | 2016-01-18 | 2016-01-12 |  |  |  |  | 2016-02-15 |  |  |  | 2015-09-28
0 | AKL | 184 | AKL-006-055 | Minnehaha mini repeater | AKL-006-055-A | Minnehaha repeater | Waitakere City | 12 | TIER_6 | ACTIVE | BO | 900_MINI_RPTR | OTHERS |  |  | STANDALONE |  |  |  | -36.9524 | 174.6326 | [6 empty] | FALSE | FALSE |  |  | FALSE |  | 2012-06-06 | [52 empty] | 2012-06-29 | 2012-06-29 | [24 empty] | FALSE |  | 2655771 | 6470885 | RCL Construction & Civil Limited 55 Minnehaha Ave Titirangi Auckland 0604 |  |  | REPEATER
0 | AKL | 185 | AKL-006-056 | Riversdale |  |  | Waitakere City |  | TIER_9
0 | AKL | 186 | AKL-006-057 | Hobsonville |  |  | Waitakere City |  | TIER_9
0 | AKL | 187 | AKL-006-058 | Henderson exchange | AKL-006-058-A | Chorus TX only site | Waitakere City |  | TIER_6 | ACTIVE | COLO | TX | COLO |  |  | COLO | [71 empty] | 2014-10-30 | [31 empty] | TXSITE
0 | AKL | 188 | AKL-007-001 |  | AKL-007-001-B | Onehunga South | Auckland City |  | TIER_1_ALL | ACTIVE | COLO | A6 | COLO | grey |  | COSITE |  |  |  | -36.9277 | 174.7839 |  |  |  |  | Microwave | AKL-007-114-D | [11 empty] | 2007-10-09 | 1 | 2007-10-09 | 2007-10-09 |  |  | 2007-12-03 | 2007-12-03 | 1 | 2007-12-03 | 2007-12-03 |  |  |  | 2007-12-07 |  |  | 2007-12-07 | 2007-12-07 |  | 2007-10-18 |  | 2008-02-22 | 2 | 1 | 2008-03-10 | 2008-03-10 | [6 empty] | 2008-04-01 | 2008-04-10 | 2008-04-10 |  | 2008-04-24 | 2008-04-24 | [8 empty] | 2009-03-10 | 2009-03-09 | 2009-03-10 |  |  |  |  | (Mar10 DJ) Site On Air - linking back via Queenstown Rd LL |  | 2009-03-09 | [17 empty] | FALSE |  | 2669298 | 6473361 | 5 Selwyn St Onehunga Auckland |  |  | CELLSITE |  |  | 2014-08-12 | [5 empty] | 2008-03-11 | [8 empty] | 2007-09-26
0 | AKL | 189 | AKL-007-002 |  | AKL-007-002-A | Southdown North | Auckland City |  | TIER_1_ALL | ACTIVE | GF | A6 | P3 | grey |  |  | 20 | 20 |  | -36.916 | 174.8243 |  |  |  |  | Microwave, Leased Line | AKL-007-114-D, AKL-007-106-A | [11 empty] | 2008-02-22 | 1 |  | 2008-02-22 |  |  | 2007-12-20 | 2008-02-26 | 1 | 2007-12-20 | 2008-02-26 |  |  |  | 2008-04-30 |  |  | 2008-04-30 | 2008-04-30 |  | 2008-02-27 |  | 2008-05-19 | 1 | 1 | 2008-05-19 | 2008-05-19 | [6 empty] | 2008-06-09 | 2008-06-27 | 2008-07-21 |  | 2008-07-06 | 2008-07-22 | [8 empty] | 2009-04-02 | 2009-04-02 | 2009-04-02 |  |  |  |  | On Air |  | 2009-04-02 | [17 empty] | FALSE |  | 2672928 | 6474581 | 3-5 Sims Rd Penrose Auckland |  |  | CELLSITE |  |  | 2014-08-12 | [5 empty] | 2008-05-20 | [8 empty] | 2008-01-24
0 | AKL | 190 | AKL-007-003 |  | AKL-007-003-A | Ellerslie Racecourse | Auckland City |  | TIER_1_ALL | ACTIVE | RT | B6 | NOPOLE | grey |  |  | 26.7 | 26.7 |  | -36.8905 | 174.8026 |  |  |  |  | Microwave | AKL-007-113-A | [5 empty] | 2009-05-11 | [5 empty] | 2007-06-20 | 2 | 2007-12-19 | 2007-12-19 |  |  | 2008-02-11 | 2008-02-11 | 1 | 2008-02-11 | 2008-02-11 |  |  |  | 2007-12-06 |  |  | 2007-12-06 | 2007-12-06 |  | 2008-01-21 |  | 2007-11-30 | 1 | 2 | 2007-11-30 | 2007-11-30 | [6 empty] | 2008-03-17 | 2008-04-18 | 2008-04-18 |  | 2008-04-29 | 2008-04-29 | [8 empty] | 2009-03-16 | 2009-03-17 | 2009-03-16 |  |  |  |  | (Mar16 DJ) Site On Air. NOTE - BBU 3806 SWAPPED OUT FOR NEW 3900 UNIT ON 17/10/2012. |  | 2009-03-17 | [17 empty] | FALSE |  | 2671051 | 6477447 | Ellerslie Racecourse 80-100 Ascott Ave Ellerslie Auckland |  |  | CELLSITE |  |  | 2014-06-16 | [5 empty] | 2008-02-15 | [8 empty] | 2007-05-21
0 | AKL | 191 | AKL-007-004 |  | AKL-007-004-A | Newmarket Viaduct | Auckland City |  | TIER_1_ALL | ACTIVE | RT | B6 | NOPOLE | grey |  |  | 18.6 | 18.6 |  | -36.877 | 174.7788 |  |  |  |  | Microwave | AKL-007-094-B | [5 empty] | 2009-05-11 | [5 empty] | 2007-08-30 | 8 | 2009-01-08 | 2009-01-08 |  |  | 2007-08-28 | 2007-08-28 | 1 | 2007-08-28 | 2007-08-28 |  | 2007-10-12 | [5 empty] | 2008-12-01 |  | 2008-01-21 |  | 2007-10-12 | 3 | 8 | 2009-01-08 | 2009-01-08 | [6 empty] | 2009-01-05 | 2009-01-30 | 2009-01-30 |  | 2009-02-16 | 2009-02-11 | [8 empty] | 2009-04-24 | 2009-04-24 | 2009-04-24 |  |  |  |  | On track for SOA. Awaiting far end linking only2/04 |  | 2009-04-24 | [17 empty] | FALSE |  | 2668960 | 6478987 | 19 Great South Rd Newmarket Auckland City Post Code |  |  | CELLSITE |  |  | 2014-06-16 | [5 empty] | 2009-01-05 | [8 empty] | 2007-08-13
0 | AKL | 192 | AKL-007-005 |  | AKL-007-005-A | Mt Roskill South | Auckland City |  | TIER_1_ALL | ACTIVE | RT | B6 | NOPOLE | grey |  |  | 14 | 14 |  | -36.9147 | 174.7531 |  |  |  |  | Leased Line | AKL-007-106-A | [11 empty] | 2007-08-13 | 2 |  | 2007-12-10 |  |  | 2007-11-29 | 2007-11-29 | 2 | 2007-11-29 | 2007-11-29 |  |  |  | 2007-10-15 |  |  | 2007-10-15 | 2007-10-15 |  | 2007-10-04 |  | 2007-10-25 | 2 | 2 | 2007-12-12 | 2007-12-12 | [6 empty] | 2008-02-07 | 2008-02-18 | 2008-02-18 |  | 2008-03-15 | 2008-03-15 | [8 empty] | 2008-04-21 |  | 2008-04-21 |  |  |  |  | On Air |  | 2008-04-21 | [17 empty] | FALSE |  | 2666584 | 6474849 | Mt Roskill Kitchens 8-10 Carr Rd Mt Roskill Auckland City Post Code |  |  | CELLSITE |  |  | 2014-08-12 | [5 empty] | 2007-11-30 | [8 empty] | 2007-05-18
0 | AKL | 193 | AKL-007-006 |  | AKL-007-006-E | Rosebank | Auckland City |  | TIER_1_ALL | ACTIVE | GF | A6 | P2 | grey | [5 empty] | -36.8817 | 174.6807 |  |  |  |  | Microwave | AKL-007-008-A | [11 empty] | 2008-07-08 | 2 |  | 2015-09-03 |  |  | 2008-07-31 | 2008-06-23 | 1 | 2008-07-31 | 2008-06-23 |  |  |  | 2008-10-31 |  |  | 2008-10-31 | 2008-10-20 |  | 2008-09-26 |  | 2008-11-05 | 2 | 1 | 2008-11-12 | 2008-11-12 | 2008-12-15 | [5 empty] | 2008-12-02 | 2008-12-19 | 2008-12-19 |  | 2008-12-19 | 2008-12-22 | [8 empty] | 2009-03-10 | 2009-03-10 | 2009-03-10 |  |  |  |  | On Air |  | 2009-03-10 | [5 empty] | 2008-12-15 | [11 empty] | FALSE |  | 2660209 | 6478641 | 379 Rosebank Rd, Avondale, Auckland |  |  | CELLSITE |  |  | 2014-09-05 | [5 empty] | 2008-11-24 | [8 empty] | 2008-04-07
0 | AKL | 194 | AKL-007-007 |  | AKL-007-007-D | Wesley | Auckland City |  | TIER_1_ALL | ACTIVE | COLO | A6 | COLO | grey |  | COSITE | 16.7 | 16.7 |  | -36.9048 | 174.7272 |  |  |  |  | Microwave | AKL-007-041-B | [5 empty] | 2009-05-11 | [5 empty] | 2007-11-16 | 5 | 2008-11-13 | 2008-11-13 |  |  | 2009-02-27 | 2009-03-04 | 2 | 2009-02-27 | 2009-03-04 |  |  |  | 2009-04-17 |  |  | 2009-04-17 | 2009-04-14 |  | 2008-05-23 |  | 2008-07-24 | 3 |  | 2009-01-29 | 2009-01-29 | [5 empty] | 2009-04-20 | 2009-04-20 | 2009-05-08 | 2009-05-08 |  | 2009-05-15 | 2009-05-15 | [8 empty] | 2009-07-15 | 2009-07-15 | 2009-07-15 |  |  |  |  | CCCH fault on sector 2 and 3. TS ongoing MB 09/07 |  | 2009-07-15 | [17 empty] | FALSE |  | 2664299 | 6476000 | 122 Stoddard Road Mt Albert Auckland |  |  | CELLSITE |  |  | 2014-06-16 |  |  |  |  | 2009-04-20 | 2009-04-20 | [8 empty] | 2007-11-09
0 | AKL | 195 | AKL-007-008 |  | AKL-007-008-A | Carrington Hub | Auckland City |  | TIER_1_ALL | ACTIVE | BO | A6 | NOPOLE | green |  |  | 28.3 | 28.3 |  | -36.8755 | 174.709 | [16 empty] | 2009-01-30 | 2007-10-30 | 10 | 2009-03-10 | 2011-07-26 |  |  | 2009-04-24 | 2009-04-28 | 5 | 2009-04-24 | 2009-04-28 |  | 2009-03-06 |  | 2009-05-01 |  |  | 2009-05-01 | 2009-05-05 | 2009-03-13 | 2008-01-21 |  | 2007-11-26 | 10 |  | 2009-03-27 | 2011-10-18 | [5 empty] | 2009-05-04 | 2009-05-04 | 2009-06-05 | 2009-06-05 |  | 2009-06-26 | 2009-06-26 | [8 empty] | 2009-06-27 | 2009-06-30 | 2009-06-27 |  |  |  |  | Build proceeding 26/05 |  | 2009-06-30 | [17 empty] | FALSE |  | 2662743 | 6479281 | Gate 2 Carrington Road Auckland |  |  | CELLSITE |  |  | 2014-06-16 |  |  |  |  | 2009-05-04 | 2009-05-04 | [8 empty] | 2007-10-11
0 | AKL | 196 | AKL-007-009 |  | AKL-007-009-L | Balmoral | Auckland City |  | TIER_1_ALL | ACTIVE | RSR | D6 | P4C | green |  | STANDALONE |  |  |  | -36.887 | 174.7472 | [17 empty] | 2009-12-11 | 4 | 2010-02-05 | 2010-11-18 |  |  | 2010-02-26 | 2010-02-25 |  | 2010-02-26 | 2010-02-25 |  | 2009-12-18 |  | 2010-03-05 |  |  | 2010-03-05 | 2010-03-05 | 2010-01-04 | 2010-01-13 |  | 2010-01-25 | 2 | 1 | 2010-02-09 | 2010-02-09 | [5 empty] | 2010-03-29 | 2010-03-29 | 2010-04-19 | 2010-04-23 |  | 2010-04-11 | 2010-04-13 | [8 empty] | 2010-04-13 | 2010-04-14 | 2010-04-13 |  |  |  |  | Site must be built by end March as this is a cabinet replacement on private property. PDI issued, boundary survey complete, there's just about 2.4m clearance for parking, to be shown on PD's. Council requested cabinets move slightly to the east to avoid requiring traffic assesment. RC delays with Oleg, councils contract processing planner. Council delays issuing RON, once SOA cabinets will be removed from Mc'Donalds by 16/4. 14/4 - L is now running as active candidate (previously candidate H - McDonalds site). Ensure all parties concerned know the active candidate is now changed and files and folders are marked with this change. |  | 2010-04-14 | [17 empty] | FALSE |  | 2666120 | 6477940 | 533 Dominion Road Balmoral |  |  | CELLSITE |  |  | 2014-06-16 |  |  |  |  | 2010-03-29 | 2010-03-29 | [8 empty] | 2009-11-30
0 | AKL | 197 | AKL-007-010 |  | AKL-007-010-A | Mt Albert East | Auckland City |  | TIER_1_ALL | ACTIVE | RSR | A6 | P4A | green |  |  | 12 | 12 |  | -36.877 | 174.7263 |  |  |  |  | Microwave | AKL-007-015-C | [5 empty] | 2009-05-12 | [5 empty] | 2007-11-14 | 2 |  | 2007-11-14 |  |  | 2008-03-11 | 2008-03-11 | 1 | 2008-03-11 | 2008-03-11 |  |  |  | 2008-07-31 |  |  | 2008-07-31 | 2008-07-11 |  | 2008-03-11 |  | 2008-03-28 | 2 | 2 | 2008-09-09 | 2008-09-09 | [6 empty] | 2008-08-11 | 2008-09-25 | 2008-09-25 |  | 2008-09-25 | 2008-09-25 | [8 empty] | 2008-12-12 | 2008-12-31 | 2008-12-12 |  |  |  |  | On Air |  | 2008-12-31 | [17 empty] | FALSE |  | 2664282 | 6479087 | Selkirk road Behind 15A Jesmond Terrace Mount Albert Auckland |  |  | CELLSITE |  |  | 2014-06-16 | [5 empty] | 2008-08-05 | [8 empty] | 2007-10-19
0 | AKL | 198 | AKL-007-011 |  | AKL-007-011-F | Epsom | Auckland City |  | TIER_1_ALL | ACTIVE | RT | B6 | NOPOLE | grey |  |  | 23.8 | 23.8 |  | -36.8897 | 174.7755 | [16 empty] | 2008-12-22 | 2008-12-22 | 3 | 2008-12-12 | 2009-03-24 |  |  | 2009-02-16 | 2009-02-20 | 2 | 2009-04-17 | 2009-04-15 |  | 2008-12-19 |  | 2009-05-01 |  |  | 2009-05-01 | 2009-06-30 | 2008-12-15 | 2008-12-16 |  | 2008-12-24 | 2 | 3 | 2008-12-24 | 2009-03-24 | [5 empty] | 2009-05-01 | 2009-05-01 | 2009-06-05 | 2009-06-05 |  | 2009-06-19 | 2009-06-19 | [8 empty] | 2009-06-22 | 2009-06-24 | 2009-06-22 |  |  |  |  | TP retrospective Section 127 may need to be processed, Janelle to confirm 04/06MB. nOTE BBU 3806 SWAPPED OUT FOR NEW 3900 UNIT ON 17/10/2012. |  | 2009-06-24 | [17 empty] | FALSE |  | 2668637 | 6477591 | Auckland Trotting Club Greenlane Road West Auckland |  |  | CELLSITE |  |  | 2014-06-16 |  |  |  |  | 2009-05-01 | 2009-05-01 | [8 empty] | 2008-12-04
0 | AKL | 199 | AKL-007-012 |  | AKL-007-012-B | Kepa Bush Reserve | Auckland City |  | TIER_1_ALL | ACTIVE | RSR | A6 | P4A | green |  |  | 10 | 10 |  | -36.8617 | 174.8254 |  |  |  |  | Microwave | AKL-007-113-A | [5 empty] | 2009-05-13 | [5 empty] | 2007-08-16 | 3 |  | 2008-03-26 |  |  | 2008-06-30 | 2008-06-23 | 3 | 2008-06-30 | 2008-06-23 |  |  |  | 2007-11-21 |  |  | 2007-11-21 | 2007-11-21 |  | 2007-11-05 |  | 2008-03-26 | 2 | 3 | 2008-08-29 | 2008-08-29 | [6 empty] | 2008-07-18 | 2008-09-19 | 2008-09-16 |  | 2008-09-24 | 2008-09-22 | [8 empty] | 2008-11-28 | 2008-12-10 | 2008-11-28 |  |  |  |  | None |  | 2008-11-26 | [17 empty] | FALSE |  | 2673154 | 6480604 | Opposite 180 Kepa Rd Orakei Auckland |  |  | CELLSITE |  |  | 2014-08-12 | [5 empty] | 2008-06-24 | [8 empty] | 2007-07-24
0 | AKL | 200 | AKL-007-013 |  | AKL-007-013-A | Lake Park West | Auckland City |  | TIER_1_ALL | ACTIVE | RT | A6 | NOPOLE | grey | [5 empty] | -36.8911 | 174.8357 | [17 empty] | 2007-11-23 | 5 | 2009-04-24 | 2009-04-28 |  |  | 2007-12-19 | 2007-12-19 | 1 | 2009-09-18 | 2009-09-15 |  |  |  | 2009-06-12 |  |  | 2009-06-12 | 2009-06-12 | 2009-03-23 | 2007-11-05 |  | 2008-08-08 | 4 |  | 2009-08-21 | 2009-08-13 | 2009-06-17 |  |  |  |  | 2009-09-30 | 2009-09-30 | 2009-11-09 | 2009-11-10 |  | 2009-11-17 | 2009-11-17 | [8 empty] | 2009-11-20 | 2009-11-20 | 2009-11-20 |  |  |  |  | On Air |  | 2009-11-20 |  |  |  |  | 2009-06-12 | 2009-06-17 | [11 empty] | FALSE |  | 2674004 | 6477314 | 83-89 Lunn Ave Auckland |  |  | CELLSITE |  |  | 2014-08-12 | [5 empty] | 2009-09-30 | [8 empty] | 2007-07-31
0 | AKL | 201 | AKL-007-014 |  | AKL-007-014-A | Royal Oak | Auckland City |  | TIER_1_ALL | ACTIVE | RT | B6 | NOPOLE | grey |  |  | 13.3 | 13.3 |  | -36.9113 | 174.7757 |  |  |  |  | Leased Line, Microwave | AKL-007-106-A, AKL-007-114-D | [11 empty] | 2007-07-15 | 1 |  | 2007-07-15 |  |  | 2007-08-29 | 2007-08-29 | 1 | 2007-08-29 | 2007-08-29 |  |  |  | 2007-09-21 |  |  | 2007-09-21 | 2007-09-21 |  | 2008-01-21 |  | 2007-10-25 | 1 | 1 | 2007-10-25 | 2007-10-25 | [6 empty] | 2007-11-12 | 2008-01-31 | 2008-01-31 |  | 2008-02-25 | 2008-02-25 | [8 empty] | 2008-05-16 |  | 2008-05-16 |  |  |  |  | None |  | 2008-05-16 | [17 empty] | FALSE |  | 2668607 | 6475189 | 703 Manukau Rd Royal Oak Auckland City |  |  | CELLSITE |  |  | 2014-08-12 | [5 empty] | 2007-11-13 | [8 empty] | 2007-05-16
0 | AKL | 202 | AKL-007-015 |  | AKL-007-015-C | Dominion Rd North (L Triangle Rd) | Auckland City | 3 | TIER_1_ALL | ACTIVE | RT | B6 | NOPOLE | grey |  |  | 17 | 17 |  | -36.8714 | 174.7528 |  |  |  |  | Microwave | AKL-007-112-A | FALSE | FALSE |  |  | FALSE | 2009-05-11 | [5 empty] | 2007-08-23 | 10 | 2009-04-02 | 2014-04-23 |  |  | 2007-12-20 | 2007-11-09 | 3 | 2007-12-20 | 2009-09-15 |  |  |  | 2007-10-03 |  |  | 2007-10-03 | 2009-03-31 |  | 2008-01-21 |  | 2007-09-25 | 8 |  | 2008-09-17 | 2011-10-18 | [6 empty] | 2007-11-19 | 2007-12-12 | 2007-12-12 |  | 2008-01-15 | 2008-01-15 | [8 empty] | 2008-02-04 |  | 2008-02-04 |  |  |  |  | On Air Link to Triangle Road. REQUIRE : 600mmØ |  | 2008-02-04 | [17 empty] | FALSE |  | 2666653 | 6479655 | Target Building 93 Dominion Rd Mt Eden Auckland City Post Code |  |  | CELLSITE |  |  | 2014-06-16 | [5 empty] | 2007-11-19 | [8 empty] | 2007-07-02
0 | AKL | 203 | AKL-007-016 |  | AKL-007-016-B | Mt Roskill | Auckland City |  | TIER_1_ALL | ACTIVE | GF | A6 | P1 | grey |  |  | 15 | 15 |  | -36.9039 | 174.7415 |  |  |  |  | Microwave | AKL-007-112-A | [5 empty] | 2009-05-08 | [5 empty] | 2008-02-12 | 3 | 2009-02-25 | 2009-02-25 |  |  | 2008-07-11 | 2008-11-25 | 1 | 2009-03-27 | 2009-03-20 |  |  |  | 2009-04-10 |  |  | 2009-04-10 | 2009-04-07 | 2008-12-15 | 2008-12-18 |  | 2009-01-30 | 3 | 3 | 2009-03-06 | 2009-05-05 | 2009-01-09 |  |  |  |  | 2009-04-15 | 2009-04-15 | 2009-05-29 | 2009-05-26 |  | 2009-06-05 | 2009-06-05 | [8 empty] | 2009-06-18 | 2009-06-19 | 2009-06-18 |  |  |  |  | Build Proceeding 26/05 |  | 2009-06-19 | [5 empty] | 2009-01-09 | [11 empty] | FALSE |  | 2665572 | 6476076 | 368 Mt Albert Road Mt Albert Auckland |  |  | CELLSITE |  |  | 2014-06-16 |  |  |  |  | 2009-04-14 | 2009-04-14 | [8 empty] | 2008-01-18
0 | AKL | 204 | AKL-007-018 |  | AKL-007-018-F | Remuera | Auckland City |  | TIER_1_ALL | ACTIVE | RSR | D6 | P4C | green |  |  | 14.4 | 14.4 |  | -36.8804 | 174.7959 |  |  |  |  | Leased Line | AKL-007-106-A | [11 empty] | 2008-12-04 | 3 | 2009-01-09 | 2009-01-09 |  |  | 2009-03-27 | 2009-03-27 | 2 | 2009-03-27 | 2009-03-27 |  |  |  | 2009-03-31 |  |  | 2009-04-03 | 2009-04-07 | 2009-01-29 | 2009-01-22 |  | 2009-02-09 | 1 | 3 | 2009-02-09 | 2009-02-09 | 2009-05-13 |  |  |  |  | 2009-05-04 | 2009-05-04 | 2009-05-22 | 2009-05-22 |  | 2009-05-29 | 2009-05-29 | [8 empty] | 2009-06-12 | 2009-06-12 | 2009-06-12 |  |  |  |  | (May28 DJ) On track. Boundary dispute resolved. (Jun03 DJ) On track SOA Jun12. (Jun10 DJ) Leased del Jun9. On track SOA Jun12. > SOA!! |  | 2009-06-12 |  |  |  |  | 2009-05-06 | 2009-05-13 | [11 empty] | FALSE |  | 2670474 | 6478582 | LPR Garden Rd Cnr Garden Rd & Remuera Rd (Adjacent to 312 Remuera Rd) Remuera Auckland |  |  | CELLSITE |  |  | 2014-08-12 |  |  |  |  | 2009-05-04 | 2009-05-04 | [8 empty] | 2008-10-24
0 | AKL | 205 | AKL-007-019 |  | AKL-007-019-C | Blockhouse Bay East | Auckland City |  | TIER_1_ALL | ACTIVE | COLO | A6 | COLO | grey |  | COLO | 12 | 12 |  | -36.9214 | 174.7126 |  |  |  |  | Leased Line | AKL-007-106-A | [11 empty] | 2007-11-16 | 4 | 2008-12-01 | 2008-12-01 |  |  | 2009-04-01 | 2009-03-31 | 2 | 2009-04-03 | 2009-03-31 |  |  |  | 2008-06-30 |  |  | 2009-02-27 | 2009-03-05 |  | 2008-03-12 |  | 2008-05-20 | 3 |  | 2009-01-29 | 2009-01-29 | [5 empty] | 2009-03-27 | 2009-03-12 | 2009-04-03 | 2009-04-03 |  | 2009-04-30 | 2009-04-30 | [8 empty] | 2009-05-18 | 2009-05-15 | 2009-05-18 |  |  |  |  | Awaiting LL fro Telecom 23/04. LL not yet delivered (JL 11/5) | TNZ | 2009-05-15 | [17 empty] | FALSE |  | 2662965 | 6474184 | TNZ Colocation 139 Boundary Rd (opp 176 Boundary Rd) Blockhouse Bay Auckland |  |  | CELLSITE |  |  | 2014-08-12 |  |  |  |  | 2009-03-17 | 2009-03-12 | [8 empty] | 2007-10-31
0 | AKL | 206 | AKL-007-020 |  | AKL-007-020-A | St Johns | Auckland City |  | TIER_1_ALL | ACTIVE | RT | B6 | NOPOLE | grey |  |  | 10.3 | 10.3 |  | -36.8762 | 174.8261 |  |  |  |  | Microwave | AKL-007-106-A | [5 empty] | 2009-05-08 | [5 empty] | 2008-03-20 | 10 | 2009-04-24 | 2009-07-31 |  |  | 2008-02-18 | 2008-02-18 | 7 | 2008-02-18 | 2009-08-14 |  |  |  | 2008-11-28 |  |  | 2009-08-31 | 2009-06-09 | 2008-12-16 | 2008-03-28 |  | 2008-05-14 | 4 | 9 | 2009-01-16 | 2009-07-15 | [5 empty] | 2009-04-06 | 2009-04-06 | 2009-04-29 | 2009-04-28 |  | 2009-08-14 | 2009-08-14 | [8 empty] | 2009-08-20 | 2009-08-19 | 2009-08-20 |  |  |  |  | On Air |  | 2009-08-19 | [17 empty] | FALSE |  | 2673177 | 6478988 | Crn Meadowbank & St Johns Rd Suburb Auckland City Post Code |  |  | CELLSITE |  |  | 2014-08-12 |  |  |  |  | 2009-04-06 | 2009-04-06 | [8 empty] | 2008-01-22
0 | AKL | 207 | AKL-007-021 |  | AKL-007-021-E | Sylvia Park | Auckland City |  | TIER_1_ALL | ACTIVE | GF | A6 | P1 | grey |  |  | 15 | 15 |  | -36.913 | 174.8455 |  |  |  |  | Microwave | AKL-008-014-C | [5 empty] | 2009-04-15 | [5 empty] | 2008-03-13 | 4 |  | 2015-12-01 |  |  | 2008-02-22 | 2008-02-22 | 2 | 2008-02-22 | 2008-02-22 |  |  |  | 2008-07-18 |  |  | 2008-07-18 | 2008-07-18 |  | 2008-03-14 |  | 2008-11-17 | 2 | 2 | 2009-01-19 | 2009-01-19 | 2008-12-15 | [5 empty] | 2008-12-15 | 2009-01-29 | 2009-01-29 |  | 2009-01-30 | 2009-01-02 | [8 empty] | 2009-05-25 | 2009-05-26 | 2009-05-25 |  |  |  |  | On Air |  | 2009-05-26 | [5 empty] | 2008-12-15 | [11 empty] | FALSE |  | 2674823 | 6474872 | 31 Carbine Road Mt Wellington Auckland |  |  | CELLSITE |  |  | 2014-08-12 | [5 empty] | 2008-11-24 | [8 empty] | 2008-01-24
0 | AKL | 208 | AKL-007-022 |  | AKL-007-022-B | St Georges Bay | Auckland City |  | TIER_1_ALL | ACTIVE | RT | B6 | NOPOLE | grey |  |  | 18.8 | 18.8 |  | -36.8523 | 174.783 |  |  |  |  | Microwave | AKL-007-042-A | [5 empty] | 2009-05-12 | [5 empty] | 2007-09-28 | 4 | 2009-03-20 | 2009-03-09 |  |  | 2007-11-30 | 2007-11-30 | 2 | 2009-03-27 | 2009-03-20 |  |  |  | 2008-06-30 |  |  | 2009-03-31 | 2009-04-09 |  | 2007-10-18 |  | 2007-11-28 | 6 | 4 | 2009-03-24 | 2009-04-01 | [6 empty] | 2008-07-23 | 2008-08-15 | 2008-08-20 |  | 2008-08-29 | 2008-08-23 | [8 empty] | 2009-05-29 | 2009-05-28 | 2009-05-29 |  |  |  |  | Build proceeding 26/05 |  | 2009-05-28 | [17 empty] | FALSE |  | 2669394 | 6481724 | 91 St Georges Bay Rd Parnell Auckland City |  |  | CELLSITE |  |  | 2014-06-16 | [5 empty] | 2008-06-24 | [8 empty] | 2007-07-02
0 | AKL | 209 | AKL-007-023 |  | AKL-007-023-C | Quay Park | Auckland City |  | TIER_1_ALL | ACTIVE | RT | B6 | NOPOLE | grey |  |  | 38 | 38 |  | -36.8486 | 174.7741 |  |  |  |  | Microwave | AKL-007-085-A | [5 empty] | 2009-05-12 | [5 empty] | 2007-07-23 | 4 |  | 2015-09-07 |  |  | 2007-09-27 | 2007-09-27 | 1 | 2007-09-27 | 2007-09-27 |  |  |  | 2007-10-05 |  |  | 2007-10-05 | 2007-10-05 |  | 2008-01-21 |  | 2007-09-21 | 4 |  | 2007-09-21 | 2015-11-11 | [6 empty] | 2007-11-23 | 2007-12-11 | 2007-12-11 |  | 2008-01-15 | 2008-01-15 | [8 empty] | 2008-02-04 |  | 2008-02-04 |  |  |  |  | On Air Note - BBU 3900 INSTALLED ON 17/10/2012. |  | 2008-02-04 | [17 empty] | FALSE |  | 2668606 | 6482154 | Jade Travel Building 121-123 Beach Rd Auckland City Post Code |  |  | CELLSITE |  |  | 2014-06-16 | [5 empty] | 2007-11-23 | [8 empty] | 2007-07-02
0 | AKL | 210 | AKL-007-024 |  | AKL-007-024-D | Viaduct | Auckland City |  | TIER_1_ALL | ACTIVE | RT | B8 | NOPOLE | grey |  |  | 1 | 1 |  | -36.8453 | 174.7604 | [17 empty] | 2007-09-12 | 7 | 2008-07-02 | 2015-04-22 |  |  | 2008-06-10 | 2008-03-13 | 4 | 2008-06-10 | 2008-03-13 |  | 2007-09-21 |  | 2008-11-13 |  |  | 2008-12-05 | 2008-12-10 |  | 2007-10-04 |  | 2008-09-03 | 4 |  | 2008-09-03 | 2015-11-11 | [6 empty] | 2009-01-20 | 2009-02-18 | 2009-02-18 |  | 2009-03-13 | 2009-03-13 | [8 empty] | 2009-03-27 | 2009-03-30 | 2009-03-27 |  |  |  |  | Integration imminent 26/03 |  | 2009-03-30 | [17 empty] | FALSE |  | 2667391 | 6482545 | 7-9 Fanshawe street Auckland City |  |  | CELLSITE |  |  | 2014-06-16 | [5 empty] | 2008-12-17 | [8 empty] | 2007-08-22
0 | AKL | 211 | AKL-007-025 |  | AKL-007-025-A | Grafton Gully | Auckland City |  | TIER_1_ALL | ACTIVE | RT | B8 | NOPOLE | grey |  |  | 40 | 40 |  | -36.8587 | 174.7671 |  |  |  |  | Microwave | AKL-007-106-A | [5 empty] | 2009-05-15 | [5 empty] | 2007-08-31 | 4 |  | 2015-05-29 |  |  | 2008-06-30 | 2008-06-23 | 3 | 2008-06-30 | 2008-06-23 |  |  |  | 2008-05-31 |  |  | 2008-05-31 | 2008-06-18 |  | 2007-11-05 |  | 2008-05-20 | 5 |  | 2008-05-20 | 2016-02-10 | [6 empty] | 2008-07-16 | 2008-07-28 | 2008-07-29 |  | 2008-08-12 | 2008-08-08 | [8 empty] | 2008-08-26 |  | 2008-08-26 |  |  |  |  | On Air | [19 empty] | FALSE |  | 2667964 | 6481042 | eCOM Building 3 Ferncroft St Auckland |  |  | CELLSITE |  |  | 2014-06-16 | [5 empty] | 2008-06-24 | [8 empty] | 2007-08-20
0 | AKL | 212 | AKL-007-026 |  | AKL-007-026-B | Mayoral Cnr | Auckland City |  | TIER_1_ALL | ACTIVE | RT | B8 | NOPOLE | grey |  |  | 28 | 28 |  | -36.8545 | 174.7625 |  |  |  |  | Microwave | AKL-007-087-A | [5 empty] | 2009-05-11 | [5 empty] | 2008-08-21 | 6 | 2009-03-13 | 2015-12-17 |  |  | 2008-08-30 | 2008-11-18 | 1 | 2008-08-30 | 2008-11-18 |  |  |  | 2009-04-03 |  |  | 2009-04-03 | 2009-04-07 | 2016-01-29 | 2008-09-08 |  | 2008-10-14 | 3 | 3 | 2009-03-27 | 2009-03-23 | [6 empty] | 2009-04-06 | 2009-05-08 | 2009-05-08 |  | 2009-05-15 | 2009-05-15 | [8 empty] | 2009-06-03 | 2009-05-29 | 2009-06-03 |  |  |  |  | Build proceeding 26/05. Note - BBU 3900 Installed on 17/10/2012. |  | 2009-05-29 | [17 empty] | FALSE |  | 2667560 | 6481516 | 345-361 Queen St, Auckland City |  |  | CELLSITE |  |  | 2014-06-16 |  |  |  |  | 2009-04-06 | 2009-04-06 | [8 empty] | 2008-06-20
0 | AKL | 213 | AKL-007-027 |  | AKL-007-027-D | Waikowhai | Auckland City |  | TIER_1_ALL | ACTIVE | RSR | D6 | P4C | green |  |  | 14.2 | 14.2 |  | -36.9301 | 174.7407 |  |  |  |  | Leased Line | AKL-007-106-A | [11 empty] | 2008-02-22 | 5 | 2009-02-12 | 2009-02-12 |  |  | 2008-03-11 | 2008-03-11 | 2 | 2008-03-11 | 2008-03-11 |  | 2009-02-13 |  | 2009-05-15 |  |  | 2009-05-15 | 2009-05-21 |  | 2008-12-04 |  | 2008-03-28 | 3 | 4 | 2009-02-04 | 2009-02-04 | 2009-04-20 |  |  |  |  | 2009-05-18 | 2009-05-18 | 2009-06-12 | 2009-06-10 |  | 2009-06-12 | 2009-06-11 | [8 empty] | 2009-06-20 | 2009-06-24 | 2009-06-20 |  |  |  |  | Build progressing (pole assembly problem with middle section joint) 04/06 MB |  | 2009-06-24 |  |  |  |  | 2009-04-20 | 2009-04-20 | [11 empty] | FALSE |  | 2665449 | 6473171 | 387 Hillsborough Rd, Waikowhai, Auckland |  |  | CELLSITE |  |  | 2014-08-12 |  |  |  |  | 2009-05-18 | 2009-05-18 | [8 empty] | 2008-01-16
0 | AKL | 214 | AKL-007-028 |  |  |  | Auckland City |  | TIER_1_ALL
0 | AKL | 215 | AKL-007-029 |  | AKL-007-029-A | Owairaka | Auckland City |  | TIER_1_ALL | ACTIVE | GF | A6 | P3 | grey |  | COLO | 25 | 25 |  | -36.8883 | 174.7108 | [17 empty] | 2007-03-28 | 6 |  | 2009-05-19 |  |  | 2007-03-30 | 2007-03-30 | 4 | 2007-03-30 | 2007-03-30 |  |  |  | 2007-12-06 |  |  | 2007-12-06 | 2009-06-09 |  | 2008-01-21 |  | 2008-04-21 | 3 | 5 | 2008-04-24 | 2009-03-23 | [6 empty] | 2008-04-21 | 2008-05-30 | 2008-05-30 |  | 2008-09-01 | 2008-09-01 | [8 empty] | 2008-11-26 | 2008-12-04 | 2008-11-26 |  |  |  |  | On Air | WO | 2008-11-20 | [17 empty] | FALSE |  | 2662876 | 6477860 | 955 New North Rd Suburb Auckland City Post Code |  |  | CELLSITE |  |  | 2014-06-16 | [5 empty] | 2008-04-22 | [8 empty] | 2007-04-01
0 | AKL | 216 | AKL-007-030 |  | AKL-007-030-G | Mt Eden Village | Auckland City |  | TIER_1_ALL | ACTIVE | RSR | D6 | P4C | taupe |  |  | 9.4 | 9.4 |  | -36.8808 | 174.762 |  |  |  |  | Leased Line | AKL-007-106-A | [11 empty] | 2009-04-21 | 2 | 2009-04-15 | 2009-06-05 |  |  | 2009-06-05 | 2009-05-29 |  | 2009-06-05 | 2009-06-08 |  | 2009-04-20 |  | 2009-06-30 |  |  | 2009-06-30 | 2009-06-24 |  | 2009-05-04 |  | 2009-05-04 | 2 | 2 | 2009-05-06 | 2009-07-21 | 2009-07-09 |  |  |  |  | 2009-07-01 | 2009-07-03 | 2009-07-17 | 2009-07-17 |  | 2009-07-24 | 2009-07-21 | [8 empty] | 2009-07-29 | 2009-07-29 | 2009-07-29 |  |  |  |  | BER problem being TS at present MB09/07 |  | 2009-07-29 |  |  |  |  | 2009-07-08 | 2009-07-09 | [11 empty] | FALSE |  | 2667459 | 6478599 | Cnr Mt Eden Rd and Oakland |  |  | CELLSITE |  |  | 2014-06-16 |  |  |  |  | 2009-07-01 | 2009-07-03 | [8 empty] | 2009-04-07
0 | AKL | 217 | AKL-007-032 |  | AKL-007-032-A | Shortland St CBD | Auckland City |  | TIER_1_ALL | ACTIVE | RT | B8 | NOPOLE | grey |  |  | 1 | 1 |  | -36.8464 | 174.767 |  |  |  |  | Microwave | AKL-007-105-A | [5 empty] | 2009-05-12 | [5 empty] | 2007-03-31 | 4 |  | 2015-12-17 |  |  | 2007-10-15 | 2007-10-15 | 1 | 2007-10-15 | 2007-10-15 |  |  |  | 2007-04-01 |  |  | 2007-04-01 | 2007-04-01 | 2016-01-29 |  |  | 2007-09-21 | 1 | 1 |  | 2007-09-21 | [6 empty] | 2007-11-05 | 2007-11-20 | 2007-11-20 |  | 2007-12-04 | 2007-12-04 | [8 empty] | 2008-04-11 |  | 2008-04-11 |  |  |  |  | On Air. Note - BBU 3900 INSTALLED ON 17/10/2012. |  | 2008-04-11 | [17 empty] | FALSE |  | 2667979 | 6482407 | Loundes House 18 Shortland St Auckland CBD |  |  | CELLSITE |  |  | 2014-06-16 | [5 empty] | 2007-11-05 | [8 empty] | 2007-04-01
0 | AKL | 218 | AKL-007-033 |  | AKL-007-033-B | Mechanics Bay | Auckland City |  | TIER_1_ALL | ACTIVE | GF | A6 | P2 | green |  |  | 20 | 20 |  | -36.848 | 174.7839 |  |  |  |  | Microwave | AKL-007-023-C | [5 empty] | 2009-05-12 | [5 empty] | 2008-03-04 | 4 | 2009-03-05 | 2015-05-07 |  |  | 2008-06-30 | 2008-10-24 | 2 | 2009-04-30 | 2009-09-15 |  |  |  | 2008-10-15 |  |  | 2008-08-09 | 2008-10-15 |  | 2008-10-07 |  | 2008-12-22 | 3 |  | 2008-12-22 | 2015-10-27 | 2008-12-19 | [5 empty] | 2009-02-12 | 2009-03-13 | 2009-03-13 |  | 2009-03-20 | 2009-03-13 | [8 empty] | 2009-03-20 | 2009-03-20 | 2009-03-20 |  |  |  |  | TNZ co-site application outstanding. High chance of interference, lower risk due to signing of On Track lease. On track for completion. |  | 2009-03-20 |  |  |  |  | 2008-12-22 | 2008-12-19 | [11 empty] | FALSE |  | 2669482 | 6482198 | Cnr Tamaki Drive and The Strand Auckland City Auckland |  |  | CELLSITE |  |  | 2014-06-16 |  |  |  |  | 2009-02-16 | 2009-02-12 | [8 empty] | 2008-01-17
0 | AKL | 219 | AKL-007-034 |  | AKL-007-034-E | Westhaven | Auckland City |  | TIER_1_ALL | ACTIVE | RT | B6 | NOPOLE | grey |  |  | 20.9 | 20.9 |  | -36.8427 | 174.7534 | [17 empty] | 2008-11-12 | 7 | 2009-04-01 | 2015-05-14 |  |  | 2009-03-06 | 2009-03-05 | 3 | 2009-03-27 | 2009-03-23 |  | 2008-12-05 |  | 2009-03-20 |  |  | 2009-05-15 | 2009-04-22 | 2008-12-19 | 2008-12-16 |  | 2009-02-09 | 4 |  | 2009-02-16 | 2015-11-11 | [6 empty] | 2009-03-18 | 2009-04-10 | 2009-03-31 |  | 2009-04-20 | 2009-04-23 | [8 empty] | 2009-04-23 | 2009-04-30 | 2009-04-23 |  |  |  |  | SA: awaiting Woosh Co Site Approval Sector 2 will be moved. no 127 required. Move and install. 2/04 MW link to Sky Tower ok - require IDU6 configuration (JL 21/4) |  | 2009-04-30 | [17 empty] | FALSE |  | 2666775 | 6482840 | Orams Marine, 142-148 Beaumont St, Westhaven, Auckland |  |  | CELLSITE |  |  | 2014-06-16 |  |  |  |  | 2009-03-16 | 2009-03-18 | [8 empty] | 2008-10-09
0 | AKL | 220 | AKL-007-035 |  | AKL-007-035-A | Grey Lynn Shops | Auckland City |  | TIER_1_ALL | ACTIVE | RT | A6 | NOPOLE | grey |  |  | 14 | 14 |  | -36.8594 | 174.7327 |  |  |  |  | Leased Line | AKL-007-106-A | [11 empty] | 2007-07-05 | 2 | 2007-06-30 | 2007-06-30 |  |  | 2007-06-20 | 2007-06-20 | 2 | 2007-06-20 | 2007-06-20 |  |  |  | 2007-09-24 |  |  | 2007-09-24 | 2007-09-24 |  | 2008-01-21 |  | 2008-01-09 | 1 | 2 | 2008-01-09 | 2008-01-09 | [6 empty] | 2008-04-01 | 2008-06-23 | 2008-06-20 |  | 2008-07-24 | 2008-07-24 | [8 empty] | 2009-08-03 | 2009-08-08 | 2009-08-03 |  |  |  |  | Trouble ticket raised to Telecom 02/07MB |  | 2009-08-08 | [17 empty] | FALSE |  | 2664892 | 6481029 | 486-490 Richmond Rd Grey Lynn Auckland |  |  | CELLSITE |  |  | 2014-06-16 | [5 empty] | 2008-03-12 | [8 empty] | 2007-05-30
0 | AKL | 221 | AKL-007-036 |  | AKL-007-036-A | Kohimarama | Auckland City |  | TIER_1_ALL | ACTIVE | RT | B | NOPOLE | grey |  |  | 8 | 8 |  | -36.8533 | 174.8439 |  |  |  |  | Leased Line | AKL-007-106-A | [11 empty] | 2007-07-10 | 1 |  | 2007-07-10 |  |  | 2007-09-24 | 2007-09-24 | 1 | 2007-09-24 | 2007-09-24 |  |  |  | 2007-09-17 |  |  | 2007-09-17 | 2007-09-17 |  | 2008-01-21 |  | 2007-09-21 | 1 | 1 | 2007-09-21 | 2007-09-21 | [6 empty] | 2007-11-12 | 2007-12-14 | 2007-12-14 |  | 2008-01-30 | 2008-01-30 | [8 empty] | 2008-12-04 | 2009-02-27 | 2008-12-04 |  |  |  |  | None |  | 2009-02-27 | [17 empty] | FALSE |  | 2674817 | 6481500 | 43 Melanesia Rd Kohimarama Auckland |  |  | CELLSITE |  |  | 2015-11-24 | [5 empty] | 2007-11-12 | [8 empty] | 2007-06-01
0 | AKL | 222 | AKL-007-037 |  | AKL-007-037-A | Victoria St West | Auckland City |  | TIER_1_ALL | ACTIVE | RT | B6 | NOPOLE | grey |  |  | 16.5 | 16.5 |  | -36.8479 | 174.7594 |  |  |  |  | Leased Line | AKL-007-106-A | [11 empty] | 2007-07-15 | 3 |  | 2015-12-16 |  |  | 2007-08-22 | 2007-08-22 | 1 | 2007-08-22 | 2007-08-22 |  |  |  | 2007-10-08 |  |  | 2007-10-08 | 2007-10-08 | 2016-01-29 | 2008-01-21 |  | 2007-09-27 | 1 | 1 | 2007-09-27 | 2007-09-27 | [6 empty] | 2007-11-05 | 2007-11-23 | 2007-11-23 |  | 2007-12-03 | 2007-12-03 | [8 empty] | 2008-03-17 |  | 2008-03-17 |  |  |  |  | On Air |  | 2008-03-17 | [17 empty] | FALSE |  | 2667296 | 6482252 | Rainger House 150 Victoria St Auckland Post Code |  |  | CELLSITE |  |  | 2014-06-16 | [5 empty] | 2007-11-05 | [8 empty] | 2007-06-01
0 | AKL | 223 | AKL-007-038 |  | AKL-007-038-E | St Heliers | Auckland City |  | TIER_1_ALL | ACTIVE | RT | B6 | NOPOLE | grey | [5 empty] | -36.8593 | 174.8612 |  |  |  |  | Leased Line | AKL-007-106-A | [11 empty] | 2008-02-15 | 2 |  | 2008-03-04 |  |  | 2008-02-19 | 2008-02-19 | 2 | 2008-02-19 | 2008-02-19 |  |  |  | 2008-06-30 |  |  | 2008-06-30 | 2008-05-27 |  | 2008-02-27 |  | 2008-03-27 | 1 | 2 | 2008-03-27 | 2008-03-27 | [6 empty] | 2008-06-09 | 2008-06-26 | 2008-07-07 |  | 2008-06-30 | 2008-07-11 | [8 empty] | 2009-03-20 | 2009-04-06 | 2009-03-20 |  |  |  |  | On Air |  | 2009-04-06 | [17 empty] | FALSE |  | 2676345 | 6480800 | 15 Maskell Street St Heliers Auckland |  |  | CELLSITE |  |  | 2014-06-16 | [5 empty] | 2008-05-28 | [8 empty] | 2008-01-22
0 | AKL | 224 | AKL-007-039 |  | AKL-007-039-A | Panmure | Auckland City |  | TIER_1_ALL | ACTIVE | RT | B6 | NOPOLE | grey |  |  | 10 | 10 |  | -36.8979 | 174.8526 |  |  |  |  | Microwave, Leased Line | AKL-008-024-A, AKL-007-106-A | [11 empty] | 2007-08-16 | 1 | 2007-08-16 | 2007-08-16 |  |  | 2007-07-31 | 2007-07-31 | 1 | 2007-07-31 | 2007-07-31 |  |  |  | 2007-10-17 |  |  | 2007-10-17 | 2007-10-17 |  | 2007-09-21 |  | 2007-09-28 | 2 | 1 | 2007-11-22 | 2007-11-22 | [6 empty] | 2007-11-26 | 2007-12-11 | 2007-12-11 |  | 2007-12-20 | 2007-12-20 | [8 empty] | 2009-03-25 | 2009-04-30 | 2009-03-25 |  |  |  |  | (Mar25 DJ) Site On Air 29/10/13 Bhan Amarsee new owner - Asked JL to contact him 09 2723341 |  | 2009-04-30 | [17 empty] | FALSE |  | 2675493 | 6476532 | 11 Pleasant View Rd, Panmure, Auckland |  |  | CELLSITE |  |  | 2014-08-12 | [5 empty] | 2007-11-26 | [8 empty] | 2007-06-21
0 | AKL | 225 | AKL-007-040 |  | AKL-007-040-A | Grey Lynn | Auckland City |  | TIER_1_ALL | ACTIVE | RT | B6 | NOPOLE | grey |  |  | 14.45 | 14.45 |  | -36.8645 | 174.738 |  |  |  |  | Microwave | AKL-007-144-A | [11 empty] | 2007-08-31 | 3 | 2008-12-18 | 2008-12-18 |  |  | 2007-12-12 | 2007-12-12 | 1 | 2007-12-12 | 2007-12-12 |  |  |  | 2009-01-30 |  |  | 2009-01-30 | 2009-01-27 |  | 2007-10-18 |  | 2008-12-18 | 1 | 3 | 2008-01-16 | 2008-12-18 | [6 empty] | 2009-02-09 | 2009-02-26 | 2009-02-25 |  | 2009-03-17 | 2009-03-13 | [8 empty] | 2009-05-18 | 2009-05-29 | 2009-05-18 |  |  |  |  | SA:MD confirmed co site application approved. Build: Integration may be brought forward if possible Linked to Arch Hill 01/05MB. No movement on Arch Hill brackets (JL4/5) |  | 2009-05-29 | [17 empty] | FALSE |  | 2665350 | 6480447 | Theatre Building Cnr Williamson Ave and Selbourne St Suburb Auckland City Post Code |  |  | CELLSITE |  |  | 2014-06-16 |  |  |  |  | 2009-02-09 | 2009-02-09 | [8 empty] | 2007-07-11
0 | AKL | 226 | AKL-007-041 |  | AKL-007-041-B | Newcall Hub | Auckland City |  | TIER_1_ALL | ACTIVE | RT | TX | NOPOLE | grey | [5 empty] | -36.8637 | 174.7623 |  |  |  |  | Microwave | AKL-007-106-A | [11 empty] | 2008-12-12 | 1 | 2008-12-12 | 2008-12-12 |  |  | 2009-01-30 | 2009-01-30 | 1 | 2009-04-08 | 2009-04-08 |  | 2008-12-19 |  | 2009-04-17 |  |  | 2009-04-17 | 2009-04-15 | 2009-01-06 | 2009-01-08 |  | 2009-02-20 | 1 | 1 | 2009-02-20 | 2009-02-20 | [6 empty] | 2009-04-22 | 2009-06-12 | 2009-06-12 |  | 2009-06-15 | 2009-06-16 | [8 empty] | 2009-06-17 | 2009-06-16 | 2009-06-17 |  |  |  |  | Build proceeding 26/05 |  | 2009-06-16 | [17 empty] | FALSE |  | 2667517 | 6480499 | NewCall Tower: 42 Khyber Pass Road, Grafton, Auckland Access via - Building Manager and Landowner Representative: Richard Brunton 09 377 7951 or 021 981 247 richard.brunton@xtra.co.nz Brunton & Associates Limited, PO Box 108-126, Auckland Roof Technical Assistance: JDA, Warren Harding, 021 383 406, He MUST attend the Site Design Visit as he will be able to answer questions relating to location and installation of equipment. |  |  | TXSITE | [7 empty] | 2009-04-20 | 2009-04-22 | [8 empty] | 2008-11-28
0 | AKL | 227 | AKL-007-042 |  | AKL-007-042-A | Parnell | Auckland City |  | TIER_1_ALL | ACTIVE | RT | B6 | NOPOLE | grey |  |  | 20 | 20 |  | -36.8562 | 174.7812 |  |  |  |  | Microwave | AKL-007-025-A | [5 empty] | 2009-05-12 | [5 empty] | 2007-09-06 | 5 |  | 2015-12-16 |  |  | 2007-08-28 | 2007-08-28 | 1 | 2007-08-28 | 2007-08-28 |  |  |  | 2008-08-31 |  |  | 2008-08-31 | 2008-10-15 | 2016-01-29 | 2008-01-21 |  | 2007-09-27 | 3 | 2 | 2009-01-19 | 2009-01-19 | [6 empty] | 2008-11-15 | 2008-11-24 | 2008-11-21 |  | 2008-12-12 | 2008-12-08 | [8 empty] | 2008-12-09 | 2008-12-31 | 2008-12-09 |  |  |  |  | On Air. NOTE - BBU 3806 SWAPPED OUT FOR NEW 3900 UNIT 15/11/2012. |  | 2008-12-31 | [17 empty] | FALSE |  | 2669222 | 6481296 | 272 Parnell Rd Parnell Auckland City Post Code |  |  | CELLSITE |  |  | 2014-06-16 | [5 empty] | 2008-10-30 | [8 empty] | 2007-08-13
0 | AKL | 228 | AKL-007-043 |  | AKL-007-043-A | Okahu Bay | Auckland City |  | TIER_1_ALL | ACTIVE | RT | A6 | NOPOLE | grey |  |  | 9.8 | 9.8 |  | -36.8528 | 174.82 |  |  |  |  | Leased Line | AKL-007-106-A | [11 empty] | 2007-08-31 | 4 | 2009-05-04 | 2009-05-05 |  |  | 2007-12-05 | 2007-12-05 | 1 | 2008-02-27 | 2009-02-27 |  |  |  | 2008-08-31 |  |  | 2009-05-08 | 2009-05-07 | 2009-04-07 | 2007-10-18 |  | 2007-11-30 | 3 | 4 | 2009-03-18 | 2009-05-07 | [6 empty] | 2008-09-12 | 2008-09-30 | 2008-09-26 |  | 2009-06-17 | 2009-06-17 | [8 empty] | 2009-06-22 | 2009-06-19 | 2009-06-22 |  |  |  |  | (May20 DJ) Agreement reached for amended design. On track (May28 DJ) Telecom co-site approval not forthcoming, no explanation. SOA on track. (Jun03 DJ) On track SOA Jun12. (Jun10 DJ) Noise testing required at site. TI bumped to Jun17, SOA to Jun19 (Jun18 DJ) still holding SOA Jun19. Jun22 > SOA!! |  | 2009-06-19 | [17 empty] | FALSE |  | 2672690 | 6481598 | O/s 36 Reihana St, Orakei, Auckland |  |  | CELLSITE |  |  | 2014-08-12 | [5 empty] | 2008-09-01 | [8 empty] | 2007-08-20
0 | AKL | 229 | AKL-007-044 |  | AKL-007-044-F | Point England | Auckland City |  | TIER_1_ALL | ACTIVE | GF | A6 | P2 | grey |  |  | 20 | 20 |  | -36.8788 | 174.8529 |  |  |  |  | Leased Line | AKL-007-106-A | [11 empty] | 2008-11-21 | 2 | 2008-12-19 | 2008-12-19 |  |  | 2009-01-12 | 2009-01-16 | 1 | 2008-12-24 | 2009-01-12 |  |  |  | 2009-03-13 |  |  | 2009-03-13 | 2009-03-12 | 2008-12-22 | 2009-01-05 |  | 2009-02-04 | 1 | 2 | 2009-02-04 | 2009-02-04 | 2009-03-20 |  |  |  |  | 2009-03-20 | 2009-03-23 | 2009-04-14 | 2009-04-08 |  | 2009-04-14 | 2009-04-08 | [8 empty] | 2009-05-15 | 2009-05-22 | 2009-05-15 |  |  |  |  | Power and LL duct in. Telecom advised to install LL (May14 DJ) Telecom did not deliver LL. Fcst SOA pushes out to May22 |  | 2009-05-15 |  |  |  |  | 2009-03-20 | 2009-03-20 | [11 empty] | FALSE |  | 2675559 | 6478655 | Unit E, 124 Felton Matthew Ave, Glen Innes, Auckland |  |  | CELLSITE |  |  | 2014-08-12 |  |  |  |  | 2009-03-16 | 2009-03-16 | [8 empty] | 2008-11-11
0 | AKL | 230 | AKL-007-045 |  | AKL-007-045-J | Otahuhu North | Auckland City |  | TIER_1_ALL | ACTIVE | GF | A6 | P2 | grey |  |  | 18.8 | 18.8 |  | -36.9397 | 174.8387 |  |  |  |  | Microwave | AKL-008-003-A | [11 empty] | 2009-03-05 | 3 | 2009-02-26 | 2015-09-17 |  |  | 2009-03-12 | 2009-03-27 |  | 2009-04-14 | 2009-04-02 |  | 2009-04-27 |  | 2009-06-15 |  |  | 2009-06-15 | 2009-06-04 | 2009-04-06 | 2009-04-08 |  | 2009-05-11 | 1 | 1 | 2009-05-08 | 2009-05-11 | 2009-04-17 |  |  |  |  | 2009-06-17 | 2009-06-09 | 2009-07-03 | 2009-07-02 |  | 2009-07-17 | 2009-07-14 | [8 empty] | 2009-07-20 | 2009-07-21 | 2009-07-20 |  |  |  |  | On Air |  | 2009-07-21 |  |  |  |  | 2009-04-17 | 2009-04-17 | [11 empty] | FALSE |  | 2674152 | 6471922 | 161 Great South Rd |  |  | CELLSITE |  |  | 2014-08-12 |  |  |  |  | 2009-06-17 | 2009-06-09 | [8 empty] | 2009-02-11
0 | AKL | 231 | AKL-007-046 |  | AKL-007-046-F | Oranga | Auckland City |  | TIER_1_ALL | ACTIVE | GF | A6 | P1 | grey |  |  | 9 | 9 |  | -36.9064 | 174.7925 |  |  |  |  | Leased Line | AKL-007-106-A | [11 empty] | 2008-11-20 | 2 | 2008-11-27 | 2008-11-27 |  |  | 2008-12-20 | 2008-12-19 |  | 2008-12-20 | 2008-12-19 |  | 2008-11-28 |  | 2009-04-10 |  |  | 2009-04-10 | 2009-04-07 | 2008-12-23 | 2009-01-05 |  | 2009-02-20 | 1 | 2 | 2009-02-20 | 2009-02-20 | 2009-03-13 |  |  |  |  | 2009-04-15 | 2009-04-15 | 2009-04-30 | 2009-04-30 |  | 2009-04-30 | 2009-04-30 | [8 empty] | 2009-06-16 | 2009-06-10 | 2009-06-16 |  |  |  |  | (May14 DJ) On track Only current outstanding issue is power - due for resolution May22. (Jun03 DJ) On track SOA Jun10. (Jun10 DJ) At risk due to lack of Leased delivery date advice. Telecom being chased. SOA scheduled Jun10. (Jun18 DJ) Telecom LL bumped to Jun12, bumps SOA to Jun16. Jun16 > SOA!! |  | 2009-06-10 |  |  |  |  | 2009-03-27 | 2009-03-13 | [11 empty] | FALSE |  | 2670113 | 6475700 | Belaire Dairy 76 Rawhiti Rd Oranga Auckland |  |  | CELLSITE |  |  | 2014-08-12 |  |  |  |  | 2009-04-15 | 2009-04-15 | [8 empty] | 2008-10-08
0 | AKL | 232 | AKL-007-047 |  | AKL-007-047-H | Te Papapa | Auckland City |  | TIER_1_ALL | ACTIVE | GF | A6 | P2 | grey |  |  | 20 | 20 |  | -36.9258 | 174.8102 |  |  |  |  | Microwave | AKL-007-114-D | [11 empty] | 2008-09-19 | 3 | 2009-06-05 | 2009-02-02 |  |  |  | 2008-09-05 | 3 | 2009-06-12 | 2009-06-10 |  |  |  | 2009-03-27 |  |  | 2009-03-27 | 2009-03-25 | 2009-01-30 | 2009-01-14 |  | 2009-01-20 | 1 | 2 | 2009-01-20 | 2009-01-20 | 2009-03-20 |  |  |  |  | 2009-06-15 | 2009-06-15 | 2009-07-14 | 2009-07-13 |  | 2009-07-17 | 2009-07-17 | [8 empty] | 2009-07-20 | 2009-07-20 | 2009-07-20 |  |  |  |  | On Air |  | 2009-07-20 |  |  |  |  | 2009-03-20 | 2009-03-20 | [11 empty] | FALSE |  | 2671650 | 6473513 | 323 Neilson St, Te Papapa, Auckland Owner Contact: Mike Malcolm 027 474 6790 mike@ailinvestments.co.nz |  |  | CELLSITE |  |  | 2014-08-12 |  |  |  |  | 2009-06-15 | 2009-06-15 | [8 empty] | 2008-08-22
0 | AKL | 233 | AKL-007-048 |  | AKL-007-048-A | Avondale AKL | Auckland City |  | TIER_1_ALL | ACTIVE | RT | A6 | NOPOLE | grey |  |  | 14 | 14 |  | -36.8987 | 174.698 | [17 empty] | 2007-08-23 | 1 |  | 2007-08-23 |  |  | 2007-08-08 | 2007-08-08 | 1 | 2007-08-08 | 2007-08-08 |  |  |  | 2007-12-03 |  |  | 2007-12-03 | 2007-12-03 |  | 2007-09-21 |  | 2007-11-06 | 2 | 1 | 2007-11-06 | 2007-11-06 | [6 empty] | 2008-01-14 | 2008-04-09 | 2008-04-09 |  | 2008-03-28 | 2008-03-28 | [8 empty] | 2009-03-10 | 2009-03-10 | 2009-03-10 |  |  |  |  | On Air |  | 2009-03-10 | [17 empty] | FALSE |  | 2661708 | 6476724 | 9 St Jude St Avondale Auckland City Post Code |  |  | CELLSITE |  |  | 2014-06-16 | [5 empty] | 2008-01-14 | [8 empty] | 2007-07-15
0 | AKL | 234 | AKL-007-049 |  | AKL-007-049-F | Avondale South | Auckland City |  | TIER_1_ALL | ACTIVE | RSR | A6 | P4A | green | [5 empty] | -36.9061 | 174.7033 |  |  |  |  | Microwave | AKL-006-013-B | [5 empty] | 2009-05-12 | [5 empty] | 2008-02-27 | 5 |  | 2015-09-09 |  |  | 2008-06-30 | 2008-06-23 | 3 | 2008-06-30 | 2008-06-23 |  | 2008-04-30 |  | 2008-01-02 |  |  | 2008-01-02 | 2008-06-13 |  | 2008-04-10 |  | 2008-04-30 | 2 | 4 | 2008-05-14 | 2008-05-14 | [6 empty] | 2008-07-28 | 2008-08-12 | 2008-08-08 |  | 2008-08-30 | 2008-08-14 | [8 empty] | 2008-12-11 | 2008-12-31 | 2008-12-11 |  |  |  |  | On Air |  | 2008-12-31 | [17 empty] | FALSE |  | 2662164 | 6475902 | 21 Tiverton Road New Windsor Auckland |  |  | CELLSITE |  |  | 2014-06-16 | [5 empty] | 2008-07-03 | [8 empty] | 2008-01-16
0 | AKL | 235 | AKL-007-050 |  | AKL-007-050-B | St Johns South | Auckland City |  | TIER_1_ALL | ACTIVE | GF | A6 | P1 | grey |  |  | 12 | 12 |  | -36.8852 | 174.8482 |  |  |  |  | Leased Line | AKL-007-106-A | [11 empty] | 2008-02-09 | 1 | 2008-02-09 | 2008-02-09 |  |  | 2008-03-31 | 2008-03-31 | 1 | 2008-03-31 | 2008-03-31 |  |  |  | 2008-08-31 |  |  | 2008-08-31 | 2008-09-02 |  | 2008-02-27 |  | 2008-09-12 | 2 | 1 | 2008-10-01 | 2008-10-01 | [6 empty] | 2008-10-13 | 2008-10-24 | 2008-10-24 |  | 2008-10-29 | 2008-10-28 | [8 empty] | 2009-03-19 | 2009-04-08 | 2009-03-19 |  |  |  |  | (Mar19 DJ) Site On Air |  | 2009-04-08 | [17 empty] | FALSE |  | 2675129 | 6477947 | 145a Morrin Road Panumure Auckland |  |  | CELLSITE |  |  | 2014-08-12 | [5 empty] | 2008-09-16 | [8 empty] | 2008-01-22
0 | AKL | 236 | AKL-007-051 |  | AKL-007-051-I | Patiki Rd | Auckland City |  | TIER_1_ALL | ACTIVE | RSR | D6 | P4F | green |  |  | 14 | 14 |  | -36.8721 | 174.6682 |  |  |  |  | Leased Line, Microwave | AKL-007-106-A, AKL-007-006-E | [5 empty] | 2009-03-31 | [5 empty] | 2008-09-17 | 2 | 2008-12-01 | 2008-12-01 |  |  | 2009-03-27 | 2009-03-27 | 2 | 2009-03-27 | 2009-03-30 |  | 2009-02-06 |  | 2009-02-06 |  |  | 2009-02-11 | 2009-02-11 | 2008-12-19 | 2008-12-23 |  | 2009-03-10 | 1 | 2 | 2009-03-11 | 2009-03-10 | 2009-05-01 | [5 empty] | 2009-03-19 | 2009-05-08 | 2009-05-08 |  | 2009-05-08 | 2009-05-08 | [8 empty] | 2009-05-29 | 2009-06-05 | 2009-05-29 |  |  |  |  | (May14 DJ) On track. |  | 2009-06-05 |  |  |  |  | 2009-04-22 | 2009-05-01 | [11 empty] | FALSE |  | 2659111 | 6479732 | LPR on Patiki Rd o/s Wattyl Industries 2-14 Patiki Rd Avondale Auckland |  |  | CELLSITE |  |  | 2014-09-05 |  |  |  |  | 2009-03-19 | 2009-03-19 | [8 empty] | 2008-08-21
0 | AKL | 237 | AKL-007-052 |  | AKL-007-052-A | St Lukes | Auckland City |  | TIER_1_ALL | ACTIVE | RT | B6 | NOPOLE | grey |  |  | 0 | 0 |  | -36.8829 | 174.7339 | [17 empty] | 2007-10-05 | 4 | 2008-09-10 | 2010-05-13 |  |  | 2008-04-30 | 2008-04-30 | 1 | 2008-04-30 | 2008-04-30 |  |  |  | 2008-09-29 |  |  | 2008-08-29 | 2008-09-29 |  | 2007-10-18 |  | 2008-11-21 | 1 | 3 | 2008-11-21 | 2008-11-21 | [6 empty] | 2009-01-19 | 2009-02-13 | 2009-02-13 |  | 2009-02-27 | 2009-02-27 | [8 empty] | 2009-03-31 | 2009-04-15 | 2009-03-31 |  |  |  |  | TI complete. Mounts to be relocated at owners request re MD. Pending far end sites for integration. 26/03 |  | 2009-04-09 | [17 empty] | FALSE |  | 2664945 | 6478412 | St Lukes Shopping Centre - Westfield 80 St Lukes Rd St Lukes Auckland |  |  | CELLSITE |  |  | 2014-06-16 |  |  |  |  | 2009-01-23 | 2009-01-23 | [8 empty] | 2007-09-06
0 | AKL | 238 | AKL-007-053 |  | AKL-007-053-D | Greenwoods Cnr | Auckland City |  | TIER_1_ALL | ACTIVE | RSR | A6 | P4A | green |  |  | 14 | 14 |  | -36.9002 | 174.7734 |  |  |  |  | Leased Line | AKL-007-106-A | [11 empty] | 2007-07-20 | 3 | 2008-12-18 | 2008-12-18 |  |  | 2009-03-27 | 2009-03-27 | 2 | 2009-03-30 | 2009-03-30 |  | 2008-10-16 |  | 2009-02-20 |  |  | 2009-02-20 | 2009-02-12 |  | 2007-11-05 |  | 2008-04-30 | 3 | 3 | 2009-01-06 | 2009-01-06 | 2008-04-30 |  |  |  |  | 2009-03-16 | 2009-03-16 | 2009-04-03 | 2009-04-03 |  | 2009-04-03 | 2009-04-03 | [8 empty] | 2009-04-23 | 2009-04-24 | 2009-04-23 |  |  |  |  | SA: Approval letter from Council Property received. Await lease. Letter to proceed with build recieved. Final due 27/03 Construction ongoing 02/04. LL delivered 15/4 but fault on it (JL 21/4) |  | 2009-04-24 | [5 empty] | 2008-04-30 | [11 empty] | FALSE |  | 2668429 | 6476429 | 594-598 Manukau Rd, Greenwoods Cnr, Epsom, Auckland |  |  | CELLSITE |  |  | 2014-08-12 |  |  |  |  | 2009-03-02 | 2009-03-03 | [8 empty] | 2007-07-09
0 | AKL | 239 | AKL-007-054 |  | AKL-007-054-E | Market Rd | Auckland City |  | TIER_1_ALL | ACTIVE | GF | A6 | P1 | green |  |  | 12.5 | 12.5 |  | -36.8833 | 174.7854 | [17 empty] | 2008-04-18 | 1 | 2008-04-18 | 2008-04-18 |  |  | 2008-06-30 | 2008-05-30 | 1 | 2008-06-30 | 2008-05-30 |  |  |  | 2008-09-26 |  |  | 2008-09-26 | 2008-09-29 |  | 2008-11-25 |  | 2008-11-27 | 2 | 1 | 2009-02-03 | 2009-02-03 | 2008-12-23 | [5 empty] | 2009-02-04 | 2009-02-27 | 2009-02-27 |  | 2009-02-27 | 2009-02-27 | [8 empty] | 2009-06-22 | 2009-06-24 | 2009-06-22 |  |  |  |  | (Jun03 DJ) ref'cast SOA Jun24. (Jun10 DJ) dep on Alex Park. No probs anticipated. On track SOA Jun24. (Jun18 DJ) still holding SOA Jun24. Jun22 > SOA!! |  | 2009-06-24 |  |  |  |  | 2008-12-31 | 2008-12-23 | [11 empty] | FALSE |  | 2669532 | 6478282 | 93 Great South Rd, Greenlane |  |  | CELLSITE |  |  | 2014-06-16 | [5 empty] | 2008-12-05 | [8 empty] | 2008-04-03
0 | AKL | 240 | AKL-007-055 |  | AKL-007-055-A | Penrose West | Auckland City |  | TIER_1_ALL | ACTIVE | GF | A6 | P2 | grey |  |  | 15 | 15 |  | -36.915 | 174.8042 |  |  |  |  | Microwave | AKL-007-113-A | [5 empty] | 2009-05-13 | [5 empty] | 2007-11-23 | 1 |  | 2007-11-23 |  |  | 2008-01-27 | 2008-01-27 | 1 | 2008-01-27 | 2008-01-27 |  |  |  | 2008-06-30 |  |  | 2008-06-30 | 2008-06-11 |  | 2008-02-19 |  | 2008-05-16 | 3 | 1 | 2008-07-23 | 2008-07-23 | [6 empty] | 2008-07-10 | 2008-08-27 | 2008-08-25 |  | 2008-09-05 | 2008-09-06 | [8 empty] | 2009-04-02 | 2009-04-30 | 2009-04-02 |  |  |  |  | On Air |  | 2009-04-30 | [17 empty] | FALSE |  | 2671141 | 6474726 | 265 Mt Smart Rd Oranga Auckland |  |  | CELLSITE |  |  | 2014-08-12 | [5 empty] | 2008-06-12 | [8 empty] | 2007-10-24
0 | AKL | 241 | AKL-007-056 |  | AKL-007-056-I | James and Wells Building - Ellerslie | Auckland City |  | TIER_1_ALL | ACTIVE | RT | B6 | NOPOLE | grey |  |  | 36.8 | 36.8 |  | -36.9026 | 174.812 |  |  |  |  | Microwave | AKL-007-003-A | [10 empty] | 2009-04-07 | 2009-04-16 | 5 | 2009-04-16 | 2015-06-03 |  |  | 2009-05-29 | 2009-05-29 | 1 | 2009-05-29 | 2009-06-09 |  | 2009-04-17 |  | 2009-06-30 |  |  | 2009-06-30 | 2009-05-15 | 2009-04-17 | 2009-04-15 |  | 2009-05-15 | 3 | 3 | 2009-05-22 | 2015-05-05 | [5 empty] | 2009-06-08 | 2009-06-09 | 2009-07-29 | 2009-07-29 |  | 2009-08-14 | 2009-08-14 | [8 empty] | 2009-08-17 | 2009-08-21 | 2009-08-17 |  |  |  |  | On Air Note - BBU 3900 INSTALLED ON 17/10/2012. |  | 2009-08-21 | [17 empty] | FALSE |  | 2671858 | 6476086 | 56 Cawley St Ellerslie Auckland |  |  | CELLSITE |  |  | 2014-08-12 |  |  |  |  | 2009-06-08 | 2009-06-09 | [8 empty] | 2009-03-20
0 | AKL | 242 | AKL-007-057 |  | AKL-007-057-B | Ellerslie North | Auckland City |  | TIER_1_ALL | ACTIVE | RSR | A6 | P4A | green |  |  | 7.5 | 7.5 |  | -36.8869 | 174.8201 |  |  |  |  | Microwave | AKL-007-113-A | [5 empty] | 2009-05-13 | [5 empty] | 2007-08-02 | 4 |  | 2008-09-15 |  |  | 2008-03-11 | 2008-03-11 | 3 | 2008-03-11 | 2008-03-11 |  |  |  | 2008-10-30 |  |  | 2008-10-30 | 2008-09-29 |  | 2008-03-11 |  | 2008-04-25 | 2 | 4 | 2008-10-07 | 2008-10-07 | [6 empty] | 2008-10-28 | 2008-11-14 | 2008-11-14 |  | 2008-12-14 | 2008-11-14 | [8 empty] | 2008-11-28 | 2008-12-10 | 2008-11-28 |  |  |  |  | None |  | 2008-11-26 | [17 empty] | FALSE |  | 2672620 | 6477810 | Cnr Abbots Way & Grand Drv, Ellerslie North, Auckland |  |  | CELLSITE |  |  | 2014-08-12 | [5 empty] | 2008-09-29 | [8 empty] | 2007-07-05
0 | AKL | 243 | AKL-007-058 |  | AKL-007-058-A | Orakei Basin | Auckland City |  | TIER_1_ALL | ACTIVE | RT | B6 | NOPOLE | grey |  |  | 8 | 8 |  | -36.8735 | 174.8105 |  |  |  |  | Microwave | AKL-007-112-A | [5 empty] | 2009-05-08 | [5 empty] | 2008-08-21 | 4 | 2008-12-16 | 2008-12-16 |  |  | 2008-08-31 | 2008-09-19 | 4 | 2008-08-31 | 2009-02-04 |  |  |  | 2009-02-06 |  |  | 2009-02-06 | 2009-10-07 |  | 2008-09-26 |  | 2008-10-30 | 1 | 4 | 2008-10-30 | 2008-10-30 | [6 empty] | 2008-12-02 | 2009-01-27 | 2009-01-27 |  | 2009-02-11 | 2009-02-09 | [8 empty] | 2009-03-30 | 2009-04-10 | 2009-03-30 |  |  |  |  | (Mar30 DJ) SOA achieved Mar30 (ahead of fcst) |  | 2009-04-10 | [17 empty] | FALSE |  | 2671792 | 6479321 | 91-97 Upland Rd Remuera Auckland |  |  | CELLSITE |  |  | 2014-08-12 | [5 empty] | 2008-12-01 | [8 empty] | 2008-06-16
0 | AKL | 244 | AKL-007-059 |  | AKL-007-059-A | Hobson Bay South | Auckland City |  | TIER_1_ALL | ACTIVE | RSR | A6 | P4A | green | [5 empty] | -36.8638 | 174.8098 |  |  |  |  | Microwave | AKL-007-113-A | [5 empty] | 2009-05-13 | [5 empty] | 2007-08-17 | 3 | 2008-03-31 | 2008-03-31 |  |  | 2008-06-30 | 2008-06-23 | 3 | 2008-06-30 | 2008-06-23 |  |  |  | 2008-06-28 |  |  | 2008-06-28 | 2008-05-12 |  | 2008-04-10 |  | 2008-06-27 | 1 | 3 | 2008-06-27 | 2008-06-27 | [6 empty] | 2008-08-15 | 2008-09-10 | 2008-09-03 |  | 2008-09-24 | 2008-09-03 | [8 empty] | 2009-04-02 | 2009-04-06 | 2009-04-02 |  |  |  |  | (Mar27 DJ) Dep on Rem hub. F'cst SOA Apr6. |  | 2009-04-06 | [17 empty] | FALSE |  | 2671756 | 6480394 | Pole outside entrance to Orakei Basin Entrance Orakei Auckland |  |  | CELLSITE |  |  | 2014-08-12 | [5 empty] | 2008-08-05 | [8 empty] | 2007-07-24
0 | AKL | 245 | AKL-007-060 |  | AKL-007-060-E | Kohimarama South | Auckland City |  | TIER_1_ALL | ACTIVE | RSR | A6 | P4A | green |  |  | 13.8 | 13.8 |  | -36.868 | 174.8454 |  |  |  |  | Microwave | AKL-007-113-A | [5 empty] | 2009-05-12 | [5 empty] | 2008-09-04 | 3 | 2008-11-26 | 2010-04-21 |  |  | 2009-03-27 | 2009-03-27 | 2 | 2009-03-27 | 2009-03-30 |  |  |  | 2009-01-05 |  |  | 2009-01-22 | 2009-01-22 |  | 2008-12-04 |  | 2009-01-06 | 1 | 2 | 2009-01-06 | 2009-01-06 | 2009-03-24 |  |  |  |  | 2009-03-20 | 2009-03-23 | 2009-04-14 | 2009-04-07 |  | 2009-04-27 | 2009-04-27 | [8 empty] | 2009-05-14 | 2009-05-12 | 2009-05-14 |  |  |  |  | (May14 DJ) M/W link to Rem Hub. Site On Air May14 |  | 2009-05-12 |  |  |  |  | 2009-03-27 | 2009-03-24 | [11 empty] | FALSE |  | 2674923 | 6479863 | Cnr Kohimarama & St Heliers Bay Rds, Between 368 Kohimarama & 353 St Heliers Bay Rds, St Johns, Auckland |  |  | CELLSITE |  |  | 2014-08-12 |  |  |  |  | 2009-03-23 | 2009-02-27 | [8 empty] | 2008-06-26
0 | AKL | 246 | AKL-007-061 |  | AKL-007-061-D | Southdown | Auckland City |  | TIER_1_ALL | ACTIVE | GF | A6 | P3 | grey |  |  | 20 | 20 |  | -36.9289 | 174.8326 |  |  |  |  | Microwave | AKL-007-002-A | [5 empty] | 2009-05-12 | [5 empty] | 2008-02-15 | 1 |  | 2008-02-15 |  |  | 2007-12-21 | 2007-12-21 | 1 | 2007-12-21 | 2007-12-21 |  |  |  | 2008-05-31 |  |  | 2008-05-31 | 2008-05-30 |  | 2008-02-18 |  | 2008-06-26 | 1 | 1 | 2008-06-26 | 2008-06-26 | [6 empty] | 2008-07-15 | 2008-09-04 | 2008-09-05 |  | 2008-09-09 | 2008-09-05 | [8 empty] | 2009-04-03 | 2009-04-06 | 2009-04-03 |  |  |  |  | On Air |  | 2009-04-06 | [17 empty] | FALSE |  | 2673637 | 6473128 | Just Trucks 809 Great South Road Southdown Auckland |  |  | CELLSITE |  |  | 2014-08-12 | [5 empty] | 2008-07-15 | [8 empty] | 2007-12-03
0 | AKL | 247 | AKL-007-062 |  | AKL-007-062-C | Mt Wellington South | Auckland City |  | TIER_1_ALL | ACTIVE | GF | A6 | P1 | green |  |  | 15 | 15 |  | -36.9254 | 174.849 |  |  |  |  | Microwave, Microwave, Leased Line | AKL-008-030-C, AKL-008-030-C, AKL-007-106-A | [5 empty] | 2009-05-12, 2009-03-31 | [5 empty] | 2007-12-13 | 3 | 2008-12-10 | 2008-12-10 |  |  | 2008-02-25 | 2008-02-25 | 1 | 2008-01-24 | 2009-02-04 |  |  |  | 2009-04-06 |  |  | 2009-04-06 | 2009-04-14 |  | 2008-02-27 |  | 2008-12-16 | 2 | 3 | 2008-12-16 | 2009-03-09 | 2009-02-26 |  |  |  |  | 2009-04-09 | 2009-04-09 | 2009-04-24 | 2009-04-23 |  | 2009-04-29 | 2009-04-23 | [8 empty] | 2009-05-21 | 2009-05-21 | 2009-05-21 |  |  |  |  | (May14 DJ) Telecom LL fcst RFS May15 - Fcst SOA dependancy. |  | 2009-05-21 | [5 empty] | 2009-02-26 | [11 empty] | FALSE |  | 2675103 | 6473486 | 6 Te Apunga Place Mt Wellington Auckland |  |  | CELLSITE |  |  | 2014-08-12 |  |  |  |  | 2009-04-09 | 2009-04-09 | [8 empty] | 2007-10-25
0 | AKL | 248 | AKL-007-063 |  | AKL-007-063-A | Otahuhu East | Auckland City |  | TIER_1_ALL | ACTIVE | GF | A6 | P1 | grey |  |  | 15 | 15 |  | -36.9353 | 174.8518 |  |  |  |  | Leased Line | AKL-007-106-A | [11 empty] | 2008-08-22 | 2 | 2009-01-30 | 2008-12-16 |  |  | 2008-04-08 | 2008-04-08 |  | 2008-01-30 | 2008-04-08 |  |  |  | 2009-04-24 |  |  | 2009-04-24 | 2009-04-23 |  | 2008-09-16 |  | 2008-10-10 | 1 | 1 | 2008-10-10 | 2008-10-10 | 2009-03-20 |  |  |  |  | 2009-04-27 | 2009-04-27 | 2009-05-22 | 2009-05-21 |  | 2009-05-22 | 2009-05-12 | [8 empty] | 2009-06-05 | 2009-06-12 | 2009-06-05 |  |  |  |  | SOA possibly bring forward to May (JL 11/5) (May14 DJ) On track. (Jun03 DJ) ref'cast LL RFS Jun10. Jun5 > SOA!! |  | 2009-06-12 |  |  |  |  | 2009-03-27 | 2009-03-20 | [11 empty] | FALSE |  | 2675333 | 6472380 | 64 Luke St, Otahuhu, Auckland |  |  | CELLSITE |  |  | 2014-08-12 |  |  |  |  | 2009-04-27 | 2009-04-27 | [8 empty] | 2008-08-12
0 | AKL | 249 | AKL-007-065 |  | AKL-007-065-D | Harbour Bridge South | Auckland City |  | TIER_1_ALL | ACTIVE | GF | A6 | P2 | grey |  |  | 15 | 15 |  | -36.8362 | 174.7417 |  |  |  |  | Microwave | AKL-007-112-A | [5 empty] | 2009-05-08 | [5 empty] | 2008-12-23 | 2 | 2008-12-23 | 2013-08-29 |  |  | 2009-02-20 | 2009-02-11 |  | 2009-03-06 | 2009-03-12 |  | 2009-01-06 |  | 2009-04-17 |  |  | 2009-04-17 | 2009-04-09 | 2009-01-30 | 2009-01-20 |  | 2009-04-08 | 1 | 1 | 2009-04-04 | 2009-04-08 | 2009-02-02 |  |  |  |  | 2009-04-20 | 2009-04-20 | 2009-05-29 | 2009-05-28 |  | 2009-06-23 | 2009-06-24 | [8 empty] | 2009-06-24 | 2009-06-24 | 2009-06-24 |  |  |  |  | awiting power to enable power up and integration 04/06 MB Antenna swap out completed 2/6/13. |  | 2009-06-24 |  |  |  |  | 2009-01-21 | 2009-02-02 | [11 empty] | FALSE |  | 2665748 | 6483586 | Adjacent to 105 - 125 Curren Street Auckland Harbour Bridge South AUckland |  |  | CELLSITE |  |  | 2014-06-16 |  |  |  |  | 2009-04-20 | 2009-04-20 | [8 empty] | 2008-12-09
0 | AKL | 250 | AKL-007-068 |  | AKL-007-068-B | Glen Innes | Auckland City |  | TIER_1_ALL | ACTIVE | RT | B | NOPOLE | grey | [5 empty] | -36.8696 | 174.8747 |  |  |  |  | Leased Line | AKL-007-106-A | [11 empty] | 2008-05-16 | 3 | 2009-04-14 | 2009-04-20 |  |  | 2008-06-30 | 2008-05-26 | 1 | 2009-04-30 | 2008-05-26 |  | 2008-11-11 |  | 2009-01-30 |  |  | 2009-01-22 | 2009-01-22 |  | 2008-08-08 |  | 2008-09-19 | 1 | 1 | 2008-09-19 | 2008-09-19 | [6 empty] | 2009-02-03 | 2009-02-27 | 2009-02-25 |  | 2009-03-13 | 2009-03-13 | [8 empty] | 2009-04-29 | 2009-05-06 | 2009-04-29 |  |  |  |  | On Air |  | 2009-05-06 | [17 empty] | FALSE |  | 2677531 | 6479626 | 233 West Tamaki Road Glendowie Auckland |  |  | CELLSITE | [8 empty] | 2009-01-30 | [8 empty] | 2008-01-31
0 | AKL | 251 | AKL-007-069 |  | AKL-007-069-B | Franklin, Ponsonby | Auckland City |  | TIER_1_ALL | ACTIVE | RSR | A6 | P4A | green |  |  | 13.5 | 13.5 |  | -36.8527 | 174.7453 |  |  |  |  | Microwave | AKL-007-015-C | [5 empty] | 2009-05-11 | [5 empty] | 2008-09-12 | 4 | 2008-12-23 | 2008-12-24 |  |  | 2009-02-27 | 2009-01-30 | 4 | 2009-03-30 | 2009-03-30 |  | 2008-09-05 |  | 2009-03-20 |  |  | 2009-03-20 | 2009-03-12 |  | 2008-12-04 |  | 2008-12-17 | 3 | 4 | 2008-12-24 | 2008-12-24 | 2009-03-24 |  |  |  |  | 2009-03-30 | 2009-03-30 | 2009-04-28 | 2009-04-28 |  | 2009-05-06 | 2009-05-01 | [8 empty] | 2009-05-22 | 2009-05-22 | 2009-05-22 |  |  |  |  | Build ongoing. Site requires Arborist report to be presented to council TP, Ron Bush to address. 07/05 MB |  | 2009-05-22 |  |  |  |  | 2009-03-27 | 2009-03-24 | [11 empty] | FALSE |  | 2666030 | 6481750 | Pole o/s 199 Ponsonby Rd Ponsonby Auckland |  |  | CELLSITE |  |  | 2014-06-16 |  |  |  |  | 2009-03-30 | 2009-03-30 | [8 empty] | 2008-08-27
0 | AKL | 252 | AKL-007-070 |  | AKL-007-070-C | Westmere | Auckland City |  | TIER_1_ALL | ACTIVE | RSR | A6 | P4A | grey |  |  | 10 | 10 |  | -36.8544 | 174.7184 |  |  |  |  | Microwave, Leased Line | AKL-007-008-A, AKL-007-106-A | [11 empty] | 2007-08-16 | 4 | 2008-03-25 | 2008-03-25 |  |  | 2008-06-30 | 2008-06-23 | 4 | 2008-06-30 | 2008-06-23 |  |  |  | 2008-03-12 |  |  | 2008-03-12 | 2008-03-12 |  | 2008-02-26 |  | 2008-03-25 | 1 | 4 | 2008-03-25 | 2008-03-25 | [6 empty] | 2008-11-13 | 2008-11-28 | 2008-11-28 |  | 2008-12-12 | 2008-12-05 | [8 empty] | 2009-03-09 | 2009-03-13 | 2009-03-09 |  |  |  |  | TI Completed |  | 2009-03-13 | [17 empty] | FALSE |  | 2663631 | 6481602 | Streetlight replacement Corner of Garnet road and Oban road Westmere Auckland |  |  | CELLSITE |  |  | 2014-06-16 | [5 empty] | 2008-09-19 | [8 empty] | 2007-07-24
0 | AKL | 253 | AKL-007-071 |  | AKL-007-071-A | Arch Hill | Auckland City |  | TIER_1_ALL | ACTIVE | RT | B6 | NOPOLE | grey |  |  | 12.9 | 12.9 |  | -36.8651 | 174.7468 |  |  |  |  | Microwave | AKL-007-015-C | [5 empty] | 2009-05-11 | [5 empty] | 2007-08-08 | 6 | 2008-03-27 | 2010-06-18 |  |  | 2008-04-29 | 2008-04-29 | 3 | 2008-04-30 | 2009-09-15 |  |  |  | 2008-08-15 |  |  | 2008-08-15 | 2008-08-01 |  | 2008-01-21 |  | 2007-09-28 | 4 | 4 | 2009-02-11 | 2009-04-01 | [6 empty] | 2008-09-12 | 2008-09-30 | 2008-09-30 |  | 2009-03-20 | 2009-03-20 | [8 empty] | 2009-03-23 | 2009-03-23 | 2009-03-23 |  |  |  |  | SA: Design dwgs omitted RRUs. LL met on site - configuration confirmed - Drawings: CDs completed. Build: New CW works complete date: 6/3, TI 20/3 |  | 2009-03-23 | [17 empty] | FALSE |  | 2666137 | 6480364 | 2 King St Grey Lynn Auckland Post Code |  |  | CELLSITE |  |  | 2014-06-16 | [5 empty] | 2008-09-01 | [8 empty] | 2007-07-02
0 | AKL | 254 | AKL-007-072 |  | AKL-007-072-A | Newmarket Central | Auckland City |  | TIER_1_ALL | ACTIVE | RT | B8 | NOPOLE | grey |  |  | 28 | 28 |  | -36.8646 | 174.779 |  |  |  |  | Microwave | AKL-007-106-A | [5 empty] | 2009-05-12 | [5 empty] | 2007-09-07 | 7 |  | 2014-05-01 |  |  | 2008-01-28 | 2008-01-28 | 4 | 2008-01-28 | 2008-01-28 |  |  |  | 2008-07-30 |  |  | 2008-07-30 | 2008-07-23 |  | 2008-01-20 |  | 2008-02-20 | 2 | 6 | 2008-07-02 | 2008-07-02 | [6 empty] | 2008-07-07 | 2008-07-30 | 2008-07-30 |  | 2008-08-22 | 2008-08-27 | [8 empty] | 2008-10-06 |  | 2008-10-06 |  |  |  |  | On Air | [19 empty] | FALSE |  | 2669005 | 6480365 | Creazoni 25 Broadway Rd Newmarket Auckland City |  |  | CELLSITE |  | 2014-10-01 | 2014-06-16 | [5 empty] | 2008-07-23 | [8 empty] | 2007-09-25
0 | AKL | 255 | AKL-007-073 |  | AKL-007-073-C | Remuera West | Auckland City |  | TIER_1_ALL | ACTIVE | RSR | A6 | P4A | green |  |  | 14.5 | 14.5 |  | -36.8752 | 174.7848 |  |  |  |  | Microwave, Microwave | AKL-007-004-A, AKL-007-004-A | [5 empty] | 2009-05-12, 2009-03-31 | [5 empty] | 2007-08-16 | 5 | 2008-04-10 | 2008-04-10 |  |  | 2008-05-31 | 2008-06-23 | 5 | 2008-05-31 | 2008-06-23 |  |  |  | 2008-10-31 |  |  | 2008-10-31 | 2008-08-13 |  | 2007-11-05 |  | 2008-04-10 | 2 | 5 | 2008-05-12 | 2008-05-12 | [6 empty] | 2008-09-01 | 2008-09-15 | 2008-09-15 |  | 2008-09-29 | 2008-09-16 | [8 empty] | 2009-04-27 | 2009-04-24 | 2009-04-27 |  |  |  |  | Awaiting Integration reliant on Eden St Car park 9/04 |  | 2009-04-24 | [17 empty] | FALSE |  | 2669498 | 6479182 | 155 Remuera Road Auckland |  |  | CELLSITE |  |  | 2014-06-16 | [5 empty] | 2008-08-13 | [8 empty] | 2007-07-23
0 | AKL | 256 | AKL-007-074 |  | AKL-007-074-A | Mt Smart | Auckland City |  | TIER_1_ALL | ACTIVE | GF | A6 | P3 | green |  |  | 20 | 20 |  | -36.9156 | 174.8174 |  |  |  |  | Microwave | AKL-007-002-A | [5 empty] | 2009-05-12 | [5 empty] | 2007-11-15 | 3 |  | 2008-06-13 |  |  | 2007-12-04 | 2007-12-04 | 1 | 2007-12-04 | 2007-12-04 |  |  |  | 2008-06-09 |  |  | 2008-06-09 | 2008-06-11 |  | 2008-01-21 |  | 2008-05-06 | 2 | 3 | 2008-06-12 | 2008-06-12 | [6 empty] | 2008-06-30 | 2008-07-29 | 2008-07-30 |  | 2008-08-22 | 2008-08-27 | [8 empty] | 2009-03-17 | 2009-03-20 | 2009-03-17 |  |  |  |  | On Air |  | 2009-03-20 | [17 empty] | FALSE |  | 2672311 | 6474640 | 38 O'Rorke Road Mt Smart Auckland |  |  | CELLSITE |  |  | 2014-08-12 | [5 empty] | 2008-06-12 | [8 empty] | 2007-10-26
0 | AKL | 257 | AKL-007-075 |  | AKL-007-075-A | Lynfield | Auckland City | 3 | TIER_1_ALL | ACTIVE | GF | A6 | P2 | green |  |  | 20 | 20 |  | -36.9261 | 174.7255 |  |  |  |  | Microwave, Microwave | AKL-007-080-A, AKL-007-080-A | FALSE | FALSE |  |  | FALSE | 2009-05-12, 2009-05-11 | [5 empty] | 2008-02-20 | 2 | 2008-10-03 | 2008-10-03 |  |  | 2007-10-10 | 2007-10-10 | 2 | 2007-10-10 | 2009-03-23 | [6 empty] | 2009-02-13 | 2008-12-19 | 2008-02-26 | 2008-02-26 |  | 2008-06-17 | 2 | 2 | 2008-11-21 | 2008-11-21 | 2009-01-30 | [5 empty] | 2009-01-27 | 2009-02-13 | 2009-02-13 |  | 2009-02-20 | 2009-02-13 | [8 empty] | 2009-03-27 | 2009-04-10 | 2009-03-27 |  |  |  |  | awaiting linking to network completion 26/03 Linking to Woodlands Park Tier 1 Infill new site. 2011 REQUIRE 600mmØ |  | 2009-04-10 |  |  |  |  | 2009-02-16 | 2009-01-30 | [11 empty] | FALSE |  | 2664103 | 6473638 | Maungakiekie Golf Course Auckland |  |  | CELLSITE |  |  | 2014-08-12 | [5 empty] | 2009-01-14 | [8 empty] | 2007-10-01
0 | AKL | 258 | AKL-007-077 |  | AKL-007-077-B | Avondale East | Auckland City |  | TIER_1_ALL | ACTIVE | RSR | A6 | P4A | green |  |  | 14.8 | 14.8 |  | -36.8948 | 174.7048 |  |  |  |  | Microwave, Leased Line | AKL-007-029-A, AKL-007-106-A | [11 empty] | 2008-02-23 | 2 |  | 2008-04-09 |  |  | 2008-03-11 | 2008-03-11 | 2 | 2008-03-11 | 2008-03-11 |  |  |  | 2008-09-26 |  |  | 2008-09-26 | 2008-08-14 |  | 2008-03-11 |  | 2008-04-09 | 1 | 2 | 2008-04-09 | 2008-04-09 | [6 empty] | 2008-08-18 | 2008-09-26 | 2008-09-25 |  |  | 2008-09-26 | [8 empty] | 2009-02-18 | 2009-02-19 | 2009-02-18 |  |  |  |  | TI Completed |  | 2009-02-19 | [17 empty] | FALSE |  | 2662327 | 6477152 | Streetlight outside 1203 New North Road Mount Albert |  |  | CELLSITE |  |  | 2014-06-16 | [5 empty] | 2008-08-18 | [8 empty] | 2007-07-24
0 | AKL | 259 | AKL-007-079 |  | AKL-007-079-A | Glendowie Water Tower | Auckland City | 3 | TIER_1_ALL | ACTIVE | RT | Ab | NOPOLE | grey | [5 empty] | -36.8492 | 174.8678 |  |  |  |  | Microwave | AKL-007-113-A | FALSE | FALSE |  |  | FALSE | 2009-05-12 | [5 empty] | 2007-11-22 | 7 | 2009-08-28 | 2009-09-01 |  |  | 2008-05-16 | 2008-09-02 | 6 | 2009-12-10 |  |  |  |  | 2008-11-21 |  |  | 2009-11-04 | 2009-11-20 | 2008-12-12 | 2008-02-27 |  | 2008-12-12 | 4 |  | 2009-09-08 | 2009-09-07 | [5 empty] | 2009-09-14 | 2009-09-16 | 2009-10-09 | 2009-09-30 |  | 2009-10-27 | 2009-10-27 | [8 empty] | 2009-11-24 | 2009-11-25 | 2009-11-24 |  |  |  |  | WOOSH CO-SITE APPROVED. No spare power capacity for 2degrees at site. New supply require. Easment agreed in principle and terms agreed - signed undertaking received from LL for easement. Design to do survey easement once installed. Cabinet type Ab required, amendment required to lease area & S127. JB to follow up LL re extended lease area and if a S127 is required. Sean will do retrospective S127 and given go-ahead for build. Easement signed & sent to our legal. JB to follow up S127. Survey and plans required for easement completion. Link to Musick Point REQUIRE 600mmØ |  | 2009-11-25 | [17 empty] | FALSE |  | 2676964 | 6481911 | Metro Water Tower Waimarie St Glendowie Auckland |  |  | CELLSITE |  |  | 2015-11-25 | [5 empty] | 2009-09-16 | [8 empty] | 2007-11-06
0 | AKL | 260 | AKL-007-080 |  | AKL-007-080-A | Lynfield North | Auckland City |  | TIER_1_ALL | ACTIVE | RT | B6 | NOPOLE | grey |  |  | 11.7 | 11.7 |  | -36.9129 | 174.7278 |  |  |  |  | Microwave | AKL-007-016-B | [5 empty] | 2009-05-11 |  |  |  |  | 2009-02-03 | 2007-06-18 | 6 | 2009-02-03 | 2009-04-23 |  |  | 2008-12-30 | 2008-05-05 | 2 | 2009-03-30 | 2009-09-15 |  |  |  | 2008-08-15 |  |  | 2009-06-26 | 2009-07-06 |  | 2007-09-21 |  | 2008-06-10 | 1 | 3 | 2008-06-10 | 2008-06-10 | [6 empty] | 2008-11-17 | 2008-11-28 | 2008-11-30 |  | 2008-12-19 | 2009-01-09 | [8 empty] | 2009-03-27 | 2009-04-03 | 2009-03-27 |  |  |  |  | Telecom Co Site pending. Discussion re down conductor between Telecom and Doug. NZCL standards in use. Approval to Co Site pending. 26/03 |  | 2009-04-03 | [17 empty] | FALSE |  | 2664334 | 6475101 | 445 Richardson Road Auckland |  |  | CELLSITE |  |  | 2014-06-16 | [5 empty] | 2008-10-15 | [8 empty] | 2007-04-01
0 | AKL | 261 | AKL-007-081 |  | AKL-007-081-B | Tamaki | Auckland City |  | TIER_1_ALL | ACTIVE | RSR | D6 | P4F | green |  |  | 10.3 | 10.3 |  | -36.8929 | 174.8591 |  |  |  |  | Leased Line | AKL-007-106-A | [11 empty] | 2009-03-17 | 4 | 2009-06-11 | 2009-07-03 |  |  | 2009-08-17 | 2009-08-03 | 4 | 2009-08-19 | 2009-08-19 |  | 2009-03-20 |  | 2009-07-31 |  |  | 2009-07-31 | 2009-07-23 | 2009-04-20 | 2009-03-25 |  | 2009-04-06 | 5 | 4 | 2009-06-11 | 2009-07-27 | 2009-05-26 |  |  |  |  | 2009-08-10 | 2009-08-10 | 2009-08-28 | 2009-08-28 |  | 2009-08-27 | 2009-08-28 | [8 empty] | 2009-09-01 | 2009-09-11 | 2009-09-01 |  |  |  |  | On Air |  | 2009-09-11 |  |  |  |  | 2009-05-22 | 2009-05-26 | [11 empty] | FALSE |  | 2676078 | 6477075 | Hobson Reserve Corner Hobson Dr & Court Cres Tamaki Auckland |  |  | CELLSITE |  |  | 2014-08-12 |  |  |  |  | 2009-08-10 | 2009-08-10 | [8 empty] | 2009-03-01
0 | AKL | 262 | AKL-007-082 |  | AKL-007-082-B | Ponsonby South | Auckland City |  | TIER_1_ALL | ACTIVE | RT | A6 | NOPOLE | grey |  |  | 12.9 | 12.9 |  | -36.8575 | 174.7475 |  |  |  |  | Microwave | AKL-007-040-A | [5 empty] | 2009-05-11 |  |  |  |  | 2008-12-23 | 2008-12-23 | 3 | 2009-02-19 | 2009-02-20 |  |  | 2008-12-20 | 2008-12-15 | 3 |  | 2008-12-20 |  | 2009-01-14 |  | 2009-04-10 |  |  | 2009-04-10 | 2009-04-07 | 2008-12-19 | 2009-01-08 |  | 2009-03-03 | 1 | 1 | 2009-03-06 | 2009-03-03 | [5 empty] | 2009-03-31 | 2009-03-31 | 2009-05-11 | 2009-05-08 |  | 2009-05-15 | 2009-05-11 | [8 empty] | 2009-05-18 | 2009-05-22 | 2009-05-18 |  |  |  |  | Awaiting RMA approval. special pole required, LL connection to this Site. Final linking path to be updated and confirmed 17/04 |  | 2009-05-22 | [17 empty] | FALSE |  | 2666218 | 6481213 | 116 Ponsonby Rd, Ponsonby, Auckland |  |  | CELLSITE |  |  | 2014-06-16 |  |  |  |  | 2009-03-31 | 2009-03-31 | [8 empty] | 2008-12-04
0 | AKL | 263 | AKL-007-083 |  | AKL-007-083-C | Spaghetti Junction | Auckland City |  | TIER_1_ALL | ACTIVE | RT | B | NOPOLE | grey | [5 empty] | -36.8616 | 174.7567 |  |  |  |  | Microwave | AKL-007-112-A | [5 empty] | 2009-05-08 | [5 empty] | 2008-03-17 | 1 | 2008-03-17 | 2008-03-17 |  |  | 2008-03-17 | 2008-03-17 | 1 | 2009-03-30 | 2009-03-23 |  |  |  | 2008-10-31 |  |  | 2008-10-31 | 2008-08-11 |  | 2008-03-28 |  | 2008-05-07 | 1 | 1 | 2008-05-07 | 2008-05-07 | [6 empty] | 2008-09-15 | 2008-10-17 | 2008-10-17 |  | 2009-01-30 | 2009-02-02 | [8 empty] | 2009-04-15 | 2009-04-14 | 2009-04-15 |  |  |  |  | Need co-site appr from TNZ. TRS: 38 Ghz solution available 2/04 |  | 2009-04-14 | [17 empty] | FALSE |  | 2667027 | 6480735 | 9 Karaka Street Newton Auckland |  |  | CELLSITE | [8 empty] | 2008-09-01 | [8 empty] | 2008-01-23
0 | AKL | 264 | AKL-007-084 |  | AKL-007-084-A | Wellesley St East | Auckland City |  | TIER_1_ALL | ACTIVE | RSR | D6 | P4F | green |  |  | 12.8 | 12.8 |  | -36.8525 | 174.767 |  |  |  |  | Microwave | AKL-007-112-A | [5 empty] | 2009-05-08 | [5 empty] | 2008-11-20 | 2 | 2008-11-20 | 2015-05-14 |  |  | 2009-03-27 | 2009-03-27 | 1 | 2009-03-30 | 2009-03-30 |  | 2009-02-16 |  | 2009-02-16 |  |  | 2009-02-16 | 2009-10-07 | 2016-01-29 | 2009-01-08 |  | 2009-03-03 | 1 | 1 | 2009-02-27 | 2009-03-03 | 2009-04-20 |  |  |  |  | 2009-04-20 | 2009-04-22 | 2009-04-30 | 2009-04-30 |  | 2009-04-30 | 2009-04-30 | [8 empty] | 2009-05-29 | 2009-05-28 | 2009-05-29 |  |  |  |  | Awaiting Integration 26/05 |  | 2009-05-28 |  |  |  |  | 2009-04-17 | 2009-04-20 | [11 empty] | FALSE |  | 2667970 | 6481730 | AUT, Gate 2 O/s Early Childhood Centre, Wellesley St, Auckland City |  |  | CELLSITE |  |  | 2014-06-16 |  |  |  |  | 2009-04-14 | 2009-04-14 | [8 empty] | 2008-10-10
0 | AKL | 265 | AKL-007-085 |  | AKL-007-085-A | Parnell Rise | Auckland City |  | TIER_1_ALL | ACTIVE | RT | B6 | NOPOLE | grey |  |  | 19.8 | 19.8 |  | -36.8519 | 174.7786 |  |  |  |  | Microwave | AKL-007-112-A | [11 empty] | 2006-04-18 | 5 |  | 2015-12-16 |  |  | 2007-04-01 | 2007-04-01 | 1 | 2007-04-01 | 2007-04-01 |  |  |  | 2007-04-01 |  |  | 2007-04-01 | 2007-04-01 | 2016-01-29 | 2008-01-21 |  | 2007-08-31 | 3 | 1 | 2007-10-12 | 2007-10-19 | [6 empty] | 2007-11-03 | 2007-11-22 | 2007-11-22 |  | 2007-12-21 | 2007-12-21 | [8 empty] | 2008-01-18 |  | 2008-01-18 |  |  |  |  | On Air |  | 2008-01-18 | [17 empty] | FALSE |  | 2669003 | 6481779 | Targetti Building 60 Parnell road Parnell Auckland |  |  | CELLSITE |  |  | 2014-06-16 | [5 empty] | 2007-11-03 | [8 empty] | 2007-04-01
0 | AKL | 266 | AKL-007-086 |  | AKL-007-086-A | Kingston St CBD | Auckland City |  | TIER_1_ALL | ACTIVE | RT | B8 | NOPOLE | grey |  |  | 1 | 1 |  | -36.8476 | 174.763 |  |  |  |  | Leased Line, Microwave | AKL-007-106-A, AKL-007-024-D | [5 empty] | 2009-05-11 | [5 empty] | 2007-03-31 | 3 |  | 2015-12-17 |  |  | 2007-10-11 | 2007-10-11 | 1 | 2007-10-11 | 2007-10-11 |  |  |  | 2007-04-01 |  |  | 2007-04-01 | 2007-04-01 | 2016-01-29 | 2007-08-29 |  | 2007-08-30 | 2 | 1 | 2007-08-30 | 2007-09-14 | [6 empty] | 2007-10-29 | 2007-11-16 | 2007-11-16 |  | 2007-11-29 | 2007-11-29 | [8 empty] | 2008-03-17 |  | 2008-03-17 |  |  |  |  | On Air Note - BBU 3900 INSTALLED ON 17/10/2012. |  | 2008-03-17 | [17 empty] | FALSE |  | 2667620 | 6482281 | Telco Building, 16 Kingston St, Auckland CBD |  |  | CELLSITE |  |  | 2014-06-16 | [5 empty] | 2007-10-29 | [8 empty] | 2007-04-01
0 | AKL | 267 | AKL-007-087 | Beca House | AKL-007-087-A | Union St | Auckland City |  | TIER_1_ALL | ACTIVE | RT | B8 | NOPOLE | grey |  |  | 25.9 | 25.9 |  | -36.8551 | 174.7581 |  |  |  |  | Microwave | AKL-007-112-A | [5 empty] | 2009-05-13 | [5 empty] | 2007-03-31 | 3 |  | 2015-05-29 |  |  | 2007-07-26 | 2007-07-26 | 1 | 2007-07-26 | 2007-07-26 |  |  |  | 2007-04-01 |  |  | 2007-04-01 | 2007-04-01 |  | 2007-08-31 |  | 2007-09-01 | 6 |  | 2007-09-01 | 2015-10-22 | [6 empty] | 2007-10-23 | 2007-11-12 | 2007-11-12 |  | 2007-11-15 | 2007-11-15 | [8 empty] | 2008-01-16 |  | 2008-01-16 |  |  |  |  | On Air |  | 2008-01-16 | [17 empty] | FALSE |  | 2667168 | 6481457 | Beca House 21 Pitt Street Auckland |  |  | CELLSITE |  |  | 2014-06-16 | [5 empty] | 2007-10-22 | [8 empty] | 2007-04-01
0 | AKL | 268 | AKL-007-088 |  | AKL-007-088-A | Upper Wakefield | Auckland City |  | TIER_1_ALL | ACTIVE | RT | B6 | NOPOLE | grey |  |  | 1 | 1 |  | -36.8561 | 174.767 |  |  |  |  | Microwave | AKL-007-025-A | [5 empty] | 2009-05-11 | [5 empty] | 2007-03-31 | 3 |  | 2015-12-17 |  |  | 2007-12-13 | 2007-12-13 | 1 | 2007-12-13 | 2007-12-13 |  |  |  | 2007-04-01 |  |  | 2007-04-01 | 2007-04-01 | 2016-01-29 | 2008-01-21 |  | 2007-09-01 | 1 | 1 | 2007-09-01 | 2007-09-01 | [6 empty] | 2007-12-04 | 2008-01-18 | 2008-01-18 |  | 2008-01-30 | 2008-01-30 | [8 empty] | 2008-03-17 |  | 2008-03-17 |  |  |  |  | On Air Note - BBU 3900 INSTALLED ON 17/10/2012. |  | 2008-03-17 | [17 empty] | FALSE |  | 2667957 | 6481331 | UNI House 70 Symonds St Auckland CBD |  |  | CELLSITE |  |  | 2014-06-16 | [5 empty] | 2007-12-04 | [8 empty] | 2007-04-01
0 | AKL | 269 | AKL-007-089 |  | AKL-007-089-B | Newton | Auckland City |  | TIER_1_ALL | ACTIVE | RT | B6 | NOPOLE | grey |  |  | 12.5 | 12.5 |  | -36.8598 | 174.753 |  |  |  |  | Microwave | AKL-007-083-C | [5 empty] | 2009-05-11 | [5 empty] | 2008-10-21 | 3 | 2009-02-18 | 2009-02-18 |  |  | 2008-02-26 | 2008-02-26 |  | 2009-03-13 | 2009-03-20 |  |  |  | 2009-02-05 |  |  | 2009-02-05 | 2009-02-02 |  | 2008-11-26 |  | 2009-01-16 | 2 | 3 | 2009-03-17 | 2009-03-23 | [6 empty] | 2009-02-23 | 2009-03-27 | 2009-03-27 |  | 2009-06-30 | 2009-06-24 | [8 empty] | 2009-04-24 | 2009-04-24 | 2009-04-24 |  |  |  |  | Co-site approved. Antennas required to be ordered A.P. John Challinor Site will be integrated with dummy load solution 02/04 Should be tracked as an expansion Site after on Air. Sector 1 only f'cast on air 30/2 - sectors 2 & 3 f'cast end May (JL 6Apr) |  | 2009-04-24 | [17 empty] | FALSE |  | 2666700 | 6480951 | 2 Newton Rd/582 Karangahape Rd Cnr Newton & Karangahape Rds, Newton, Auckland |  |  | CELLSITE |  |  | 2014-06-16 |  |  |  |  | 2009-03-20 | 2009-03-16 | [8 empty] | 2008-02-14
0 | AKL | 270 | AKL-007-090 |  |  |  | Auckland City |  | TIER_1_ALL
0 | AKL | 271 | AKL-007-091 |  | AKL-007-091-A | Three Lamps | Auckland City |  | TIER_1_ALL | ACTIVE | RT | B6 | NOPOLE | grey |  |  | 8.3 | 8.3 |  | -36.8469 | 174.7442 |  |  |  |  | Microwave | AKL-007-144-A | [11 empty] | 2008-10-07 | 7 | 2009-04-17 | 2013-08-29 |  |  | 2007-07-31 | 2008-07-21 | 5 | 2009-05-22 | 2009-05-28 |  | 2008-01-19 |  | 2009-05-22 |  |  | 2009-05-22 | 2009-05-22 |  | 2008-12-01 |  | 2009-01-21 | 2 | 4 | 2009-04-24 | 2009-04-27 | [5 empty] | 2009-05-25 | 2009-05-28 | 2009-06-23 | 2009-06-25 |  | 2009-07-14 | 2009-07-13 | [8 empty] | 2009-07-16 | 2009-07-17 | 2009-07-16 |  |  |  |  | TI to complete 09/09MB Aiming for integration 15/07 - RB 14/7 |  | 2009-07-17 | [17 empty] | FALSE |  | 2665942 | 6482394 | Radioworks Building, 1 Jervois Rd, Ponsonby, Auckland |  |  | CELLSITE |  |  | 2014-06-16 |  |  |  |  | 2009-05-25 | 2009-05-28 | [8 empty] | 2007-10-30
0 | AKL | 272 | AKL-007-092 |  | AKL-007-092-A | Downtown South | Auckland City |  | TIER_1_ALL | ACTIVE | RT | D6 | NOPOLE | grey |  |  | 21 | 21 |  | -36.8442 | 174.766 | [17 empty] | 2007-10-31 | 5 |  | 2009-03-12 |  |  |  | 2009-04-30 |  |  | 2009-05-13 | [7 empty] | 2009-04-27 |  | 2009-02-24 |  | 2009-04-01 | 1 | 5 |  | 2009-04-01 | [6 empty] | 2009-05-15 | 2009-06-22 | 2009-06-20 |  | 2009-07-03 | 2009-06-27 | [8 empty] | 2009-06-27 | 2009-07-03 | 2009-06-27 |  |  |  |  | Build Proceeding 26/05 |  | 2009-07-03 | [17 empty] | FALSE |  | 2667891 | 6482651 | 11-27 Customs St West (Also known as 7 Queen Street) Corner Customs St West and Albert St Auckland City |  |  | CELLSITE |  |  | 2014-06-16 | [5 empty] | 2009-05-15 | [8 empty] | 2007-08-06
0 | AKL | 273 | AKL-007-093 |  | AKL-007-093-A | Downtown North | Auckland City |  | TIER_1_ALL | ACTIVE | RT | D6 | NOPOLE | grey |  |  | 21 | 21 |  | -36.8442 | 174.766 |  |  |  |  | Leased Line | AKL-007-106-A | [11 empty] | 2007-10-31 | 6 | 2009-03-10 | 2010-06-11 |  |  | 2009-05-14 | 2009-04-30 |  | 2009-05-14 | 2009-05-13 |  |  |  | 2009-03-27 |  |  | 2009-04-28 | 2009-04-27 | 2009-02-27 | 2009-02-24 |  | 2009-04-01 | 1 | 4 | 2009-03-27 | 2009-04-01 | [5 empty] | 2009-05-15 | 2009-05-15 | 2009-06-22 | 2009-06-20 |  | 2009-07-03 | 2009-06-27 | [8 empty] | 2009-06-27 | 2009-07-03 | 2009-06-27 |  |  |  |  | Build proceeding 26/05 |  | 2009-07-03 | [17 empty] | FALSE |  | 2667891 | 6482651 | 11-27 Customs St West (Also known as 7 Queen Street) Corner Customs St West and Albert St Auckland City |  |  | CELLSITE |  |  | 2014-06-16 |  |  |  |  | 2009-05-15 | 2009-05-15 | [8 empty] | 2007-08-06
0 | AKL | 274 | AKL-007-094 |  | AKL-007-094-B | Newmarket South | Auckland City |  | TIER_1_ALL | ACTIVE | RT | B8 | NOPOLE | grey |  |  | 28 | 28 |  | -36.8698 | 174.7767 |  |  |  |  | Microwave | AKL-007-106-A | [5 empty] | 2009-05-08 | [5 empty] | 2008-11-13 | 4 | 2009-03-17 | 2015-04-30 |  |  | 2008-11-28 | 2008-11-27 | 1 | 2009-03-13 | 2009-03-20 |  |  |  | 2009-01-27 |  |  | 2009-01-27 | 2009-01-27 |  | 2008-12-01 |  | 2008-12-22 | 4 |  | 2009-03-24 | 2015-10-22 | [6 empty] | 2009-02-16 | 2009-04-17 | 2009-04-16 |  | 2009-04-30 | 2009-04-23 | [8 empty] | 2009-04-24 | 2009-04-24 | 2009-04-24 |  |  |  |  | SA: VFNZ co-site application approved. Build: Transmission, Linking to NZCL. 2/04. NOTE - BBU 3806 SWAPPED OUT FOR NEW 3900 UNIT 17/10/2012 |  | 2009-04-24 | [17 empty] | FALSE |  | 2668790 | 6479789 | Eden St Carpark, 2-4 Eden St, Newmarket, Auckland |  |  | CELLSITE |  |  | 2014-06-16 | [5 empty] | 2009-02-03 | [8 empty] | 2008-10-10
0 | AKL | 275 | AKL-007-095 |  | AKL-007-095-A | Queen St CBD | Auckland City |  | TIER_1_ALL | ACTIVE | RT | B8 | NOPOLE | grey |  |  | 1 | 1 |  | -36.8492 | 174.7655 |  |  |  |  | Microwave | AKL-007-032-A | [5 empty] | 2009-05-12 | [5 empty] | 2007-03-31 | 4 |  | 2015-12-17 |  |  | 2007-08-28 | 2007-08-28 | 1 | 2007-08-28 | 2007-08-28 |  |  |  | 2007-04-01 |  |  | 2007-04-01 | 2007-04-01 | 2016-01-29 | 2007-09-20 |  | 2007-09-21 | 1 | 1 | 2007-09-21 | 2007-09-21 | [6 empty] | 2007-11-09 | 2007-12-07 | 2007-12-07 |  | 2007-12-20 | 2007-12-20 | [8 empty] | 2008-04-11 |  | 2008-04-11 |  |  |  |  | On Air Note - BBU 3900 INSTALLED ON 17/10/2012. F3 Dual RRU installed 3/4/13. |  | 2008-04-11 | [17 empty] | FALSE |  | 2667840 | 6482095 | FAI Building 220 Queen Street Auckland CBD | Varied on 8 August 2014, to: - Provide for additional antennas for LTE700 (rent increase associated once initiated) - Provide for a micro site to be installed on the canopy at Level 1 ((rent increase associated once initiated) - Increase Lease a further 6 year term, final expiry 2036. BB 12/08/14 - 12/08/2014 |  | CELLSITE |  |  | 2014-06-16 | [5 empty] | 2007-11-09 | [8 empty] | 2007-04-01
0 | AKL | 276 | AKL-007-096 |  | AKL-007-096-C | Remuera North | Auckland City |  | TIER_1_ALL | ACTIVE | RSR | A6 | P4A | green |  |  | 10.5 | 10.5 |  | -36.8684 | 174.8 |  |  |  |  | Microwave | AKL-007-113-A | [5 empty] | 2009-05-12 | [5 empty] | 2007-08-09 | 4 | 2008-03-27 | 2008-03-27 |  |  | 2008-05-31 | 2008-06-23 | 4 | 2008-05-31 | 2008-06-23 |  |  |  | 2008-10-31 |  |  | 2008-10-31 | 2008-09-12 |  | 2008-04-10 |  | 2008-04-30 | 2 | 3 | 2008-05-14 | 2008-05-14 | [6 empty] | 2008-11-17 | 2008-11-28 | 2008-11-28 |  | 2008-12-15 | 2008-11-28 | [8 empty] | 2009-04-01 | 2009-04-03 | 2009-04-01 |  |  |  |  | (Mar27 DJ) F'cst SOA Mar 30 |  | 2009-04-03 | [17 empty] | FALSE |  | 2670875 | 6479905 | Pole outside 203 Victoria Ave Remuera Auckland |  |  | CELLSITE |  |  | 2014-08-12 | [5 empty] | 2008-09-16 | [8 empty] | 2007-07-05
0 | AKL | 277 | AKL-007-098 |  | AKL-007-098-B | Western Springs | Auckland City |  | TIER_1_ALL | ACTIVE | GF | A6 | P1 | green |  |  | 13.8 | 13.8 |  | -36.8683 | 174.7278 |  |  |  |  | Microwave | AKL-007-015-C | [5 empty] | 2009-05-11 | [5 empty] | 2008-11-10 | 3 | 2009-03-20 | 2009-03-23 |  |  | 2009-03-12 | 2009-03-30 |  | 2009-03-30 | 2009-03-30 | PERMITTED |  |  | 2009-04-10 |  |  | 2009-04-10 | 2009-04-08 | 2009-02-13 | 2009-02-16 |  | 2009-04-24 | 1 | 2 | 2009-04-24 | 2009-04-24 | 2009-03-20 |  |  |  |  | 2009-04-20 | 2009-04-20 | 2009-05-29 | 2009-05-29 |  | 2009-06-02 | 2009-06-04 | [8 empty] | 2009-06-05 | 2009-06-05 | 2009-06-05 |  |  |  |  | Build proceeding 26/05 |  | 2009-06-05 |  |  |  |  | 2009-03-20 | 2009-03-20 | [11 empty] | FALSE |  | 2664439 | 6480047 | Behind Caltex Western Springs (Transit NZ) Gt North Rd Western Springs Auckland |  |  | CELLSITE |  |  | 2014-06-16 |  |  |  |  | 2009-04-20 | 2009-04-20 | [8 empty] | 2008-10-10
0 | AKL | 278 | AKL-007-100 |  | AKL-007-100-E | Point Chevalier | Auckland City |  | TIER_1_ALL | ACTIVE | RSR | D6 | P4F | green |  |  | 14 | 14 |  | -36.8639 | 174.7053 |  |  |  |  | Microwave | AKL-007-008-A | [5 empty] | 2009-04-15 | [5 empty] | 2009-03-31 | 2 | 2009-03-06 | 2009-04-06 |  |  | 2009-05-15 | 2009-05-29 |  | 2009-05-15 | 2009-09-15 | [7 empty] | 2009-04-07 | 2009-08-31 | 2009-04-01 |  | 2009-04-17 | 1 | 1 | 2009-04-17 | 2009-04-17 | 2009-05-26 |  |  |  |  | 2009-05-18 | 2009-05-18 | 2009-06-19 | 2009-06-19 |  | 2009-06-26 | 2009-06-26 | [8 empty] | 2009-06-27 | 2009-06-29 | 2009-06-27 |  |  |  |  | (Jun03 DJ) All Site Acq cmplt - On track SOA Jun30. (Jun10 DJ) On track for SOA Jun29 (Jun18 DJ) ASAC issues but still holding SOA Jun29. (Jun24 DJ) on track SOA Jun29. |  | 2009-06-29 |  |  |  |  | 2009-05-22 | 2009-05-26 | [11 empty] | FALSE |  | 2662435 | 6480580 | LPR situated on opposite side of intersection on Point Chev Road |  |  | CELLSITE |  |  | 2014-06-16 |  |  |  |  | 2009-05-18 | 2009-05-18 | [8 empty] | 2009-03-16
0 | AKL | 279 | AKL-007-101 | Mission Bay | AKL-007-101-A | Mission Bay | Auckland City |  | TIER_1_ALL | ACTIVE | RT | B6 | NOPOLE | grey |  |  | 9 | 9 |  | -36.8485 | 174.8315 |  |  |  |  | Leased Line | AKL-007-106-A | [11 empty] | 2007-08-17 | 8 | 2008-08-06 | 2015-06-03 |  |  | 2008-07-31 | 2008-08-11 | 5 | 2008-07-31 | 2008-08-11 |  |  | 2015-08-06 | 2008-04-30 | 2015-08-06 | 8 | 2008-04-30 | 2008-06-19 |  | 2008-01-21 |  | 2008-09-02 | 4 |  | 2008-09-02 | 2015-07-30 | [6 empty] | 2008-09-09 | 2008-09-30 | 2008-09-30 |  | 2008-10-17 | 2008-10-17 | [8 empty] | 2009-07-03 | 2009-07-06 | 2009-07-03 |  |  |  |  | Telecom fibre f'cast 20/5 - SOA f'cast date pending this (JL 27/4) (May14 DJ) Awaiting approval of ACC RON. (Jun03 DJ) ref'cast LL RFS Jun10. (Jun10 DJ) On track SOA Jun17. (Jun18 DJ) Telecom prevented from access by Landowner, bumps link prov to Jun22, SOA to Jun24. (Jun24 DJ) delay to fibre access bumps SOA Jun29. (Jul01 DJ) weather issue delays fibre, bumps SOA f'cst to Jul03 |  | 2009-07-06 | [17 empty] | FALSE |  | 2673722 | 6482058 | 65-71 Tamaki Drive Mission Bay Auckland City Post Code |  |  | CELLSITE |  |  | 2014-08-12 | [5 empty] | 2008-09-01 | [8 empty] | 2007-07-17
0 | AKL | 280 | AKL-007-103 |  | AKL-007-103-E | Mt Wellington | Auckland City |  | TIER_1_ALL | ACTIVE | RSR | D6 | P4A | green |  |  | 13 | 13 |  | -36.9081 | 174.8374 |  |  |  |  | Microwave, Leased Line | AKL-007-021-E, AKL-007-106-A | [11 empty] | 2008-09-05 | 5 | 2008-12-09 | 2009-10-16 |  |  | 2009-03-27 | 2009-03-27 | 4 | 2009-03-27 | 2009-03-30 |  |  |  | 2009-03-06 |  |  | 2009-03-13 | 2009-02-26 |  | 2008-09-26 |  | 2008-10-30 | 3 | 3 | 2008-12-01 | 2008-12-01 | 2009-04-20 |  |  |  |  | 2009-04-15 | 2009-04-15 | 2009-04-29 | 2009-04-28 |  | 2009-05-15 | 2009-05-19 | [8 empty] | 2009-05-27 | 2009-05-22 | 2009-05-27 |  |  |  |  | (May20 DJ) On schedule |  | 2009-05-22 |  |  |  |  | 2009-04-17 | 2009-04-20 | [11 empty] | FALSE |  | 2674112 | 6475429 | Lightpole Cnr Wilson Way and Penrose Rd Mt Wellington Auckland |  |  | CELLSITE |  |  | 2014-08-12 |  |  |  |  | 2009-04-14 | 2009-04-14 | [8 empty] | 2008-08-15
0 | AKL | 281 | AKL-007-104 |  | AKL-007-104-A | Hillsborough | Auckland City |  | TIER_1_ALL | ACTIVE | RSR | A6 | P4A | green | [5 empty] | -36.9268 | 174.7501 |  |  |  |  | Leased Line | AKL-007-106-A | [11 empty] | 2007-07-28 | 5 | 2008-03-31 | 2009-10-16 |  |  | 2008-05-31 | 2008-06-23 | 4 | 2008-05-31 | 2008-06-23 |  |  |  | 2008-05-31 |  |  | 2008-05-31 | 2008-06-24 |  | 2008-04-10 |  | 2008-04-30 | 2 | 4 | 2008-05-14 | 2008-05-14 | 2008-07-03 | [5 empty] | 2008-07-23 | 2008-08-15 | 2008-08-15 |  | 2008-08-26 | 2008-08-23 | [8 empty] | 2009-03-04 | 2009-03-11 | 2009-03-04 |  |  |  |  | TI Completed |  | 2009-03-11 | [5 empty] | 2008-07-03 | [11 empty] | FALSE |  | 2666289 | 6473522 | Streetlight replacement 5 ALex Boyd Link Hillsborough Auckland |  |  | CELLSITE |  |  | 2014-08-12 | [5 empty] | 2008-07-03 | [8 empty] | 2007-05-24
0 | AKL | 282 | AKL-007-105 |  | AKL-007-105-A | Princes St North | Auckland City |  | TIER_1_ALL | ACTIVE | RT | B8 | NOPOLE | grey | [5 empty] | -36.8477 | 174.7699 |  |  |  |  | Microwave | AKL-007-112-A | [5 empty] | 2009-05-13 | [5 empty] | 2008-02-28 | 4 |  | 2015-05-20 |  |  | 2008-02-27 | 2008-02-27 | 1 | 2008-02-27 | 2008-02-27 |  |  |  | 2007-04-01 |  |  | 2007-04-01 | 2007-04-01 |  | 2007-12-05 |  | 2007-12-06 | 5 |  | 2007-12-06 | 2015-11-13 | [6 empty] | 2008-03-07 | 2008-03-19 | 2008-03-19 |  | 2008-04-11 | 2008-04-11 | [8 empty] | 2008-04-11 |  | 2008-04-11 |  |  |  |  | On Air. Note - Add new BBU 3900 to site on 17/10/2012. F3 VDual RRU installed on 14/6/13. |  | 2008-04-11 | [17 empty] | FALSE |  | 2668232 | 6482261 | Fonterra Building 9 Princess Street Auckland CBD |  |  | CELLSITE |  |  | 2014-06-16 | [5 empty] | 2008-02-28 | [8 empty] | 2007-04-01
0 | AKL | 283 | AKL-007-106 |  | AKL-007-106-A | Khyber Pass | Auckland City |  | TIER_1_ALL | ACTIVE | RT | A6 | NOPOLE | grey |  |  | 14 | 14 |  | -36.865 | 174.765 | [17 empty] | 2008-03-31 | 7 |  | 2015-12-17 |  |  | 2007-08-01 | 2007-08-01 | 1 | 2007-08-01 | 2007-08-01 |  |  |  | 2007-10-17 |  |  | 2007-10-17 | 2007-10-17 | 2016-01-29 | 2008-04-01 |  | 2008-04-03 | 1 | 1 | 2008-04-03 | 2008-04-03 | [6 empty] | 2007-11-09 | 2007-11-16 | 2007-11-16 |  | 2007-11-27 | 2007-11-27 | [8 empty] | 2007-12-20 |  | 2007-12-20 |  |  |  |  | On Air COC for antenna was not obtained. 24/09/2010 CoC submitted 27/09/2010 Chq $1000 paid to ACC |  | 2007-12-20 | [17 empty] | FALSE |  | 2667763 | 6480343 | 131 Khyber Pass Road Newton Auckland |  |  | CELLSITE |  |  | 2014-06-16 | [5 empty] | 2007-11-09 | [8 empty] | 2007-06-25
0 | AKL | 284 | AKL-007-107 |  | AKL-007-107-A | Onehunga West | Auckland City |  | TIER_1_ALL | ACTIVE | RSR | A6 | P4A | green |  |  | 1 | 1 |  | -36.921 | 174.768 |  |  |  |  | Leased Line, Microwave | AKL-007-106-A, AKL-007-001-B | [5 empty] | 2009-05-12 | [5 empty] | 2007-09-13 | 4 | 2008-04-01 | 2008-04-01 |  |  | 2007-05-31 | 2008-06-23 | 4 | 2007-05-31 | 2008-06-23 |  |  |  | 2008-10-31 |  |  | 2008-10-31 | 2008-08-11 |  | 2007-11-05 |  | 2008-03-31 | 2 | 4 | 2008-08-22 | 2008-08-22 | [6 empty] | 2008-09-01 | 2008-09-19 | 2008-09-08 |  | 2008-09-19 | 2008-09-12 | [8 empty] | 2009-03-09 | 2009-03-09 | 2009-03-09 |  |  |  |  | TI Completed. |  | 2009-03-09 | [17 empty] | FALSE |  | 2667897 | 6474126 | Streetlight pole next to bus stop Corner of Beachcroft Ave and Queenstown road |  |  | CELLSITE |  |  | 2014-08-12 | [5 empty] | 2008-08-14 | [8 empty] | 2007-08-22
0 | AKL | 285 | AKL-007-108 |  | AKL-007-108-B | Pah Rd | Auckland City |  | TIER_1_ALL | ACTIVE | RSR | A6 | P4A | green | [5 empty] | -36.9099 | 174.7699 |  |  |  |  | Microwave | AKL-007-014-A | [5 empty] | 2009-05-12 | [5 empty] | 2008-01-17 | 1 |  | 2008-01-17 |  |  | 2008-03-11 | 2008-03-11 | 1 | 2008-03-11 | 2008-03-11 |  |  |  | 2008-08-31 |  |  | 2008-08-31 | 2008-05-09 |  | 2008-04-10 |  | 2008-04-28 | 3 | 1 | 2008-09-03 | 2008-09-03 | [6 empty] | 2008-06-09 | 2008-08-22 | 2008-08-14 |  | 2008-08-22 | 2008-08-19 | [8 empty] | 2008-12-03 | 2009-02-27 | 2008-12-03 |  |  |  |  | On Air |  | 2009-02-27 | [17 empty] | FALSE |  | 2668092 | 6475352 | 86 Pah Rd, Epsom, Auckland |  |  | CELLSITE |  |  | 2014-08-12 | [5 empty] | 2008-05-12 | [8 empty] | 2007-12-21
0 | AKL | 286 | AKL-007-110 |  | AKL-007-110-F | Blockhouse Bay | Auckland City |  | TIER_1_ALL | ACTIVE | RSR | D6 | P4C | green |  |  | 13.8 | 13.8 |  | -36.9231 | 174.701 |  |  |  |  | Microwave | AKL-006-013-B | [5 empty] | 2009-05-11 | [5 empty] | 2008-09-04 | 5 | 2008-12-17 | 2009-10-16 |  |  | 2009-03-27 | 2009-03-27 | 3 | 2009-03-27 | 2009-03-30 |  | 2009-02-06 |  | 2009-02-27 |  |  | 2009-02-11 | 2009-02-04 |  | 2008-09-26 |  | 2008-10-07 | 2 | 4 | 2008-12-22 | 2008-12-22 | 2009-04-30 |  |  |  |  | 2009-04-20 | 2009-04-20 | 2009-05-13 | 2009-05-13 |  | 2009-05-20 | 2009-05-19 | [8 empty] | 2009-05-22 | 2009-05-22 | 2009-05-22 |  |  |  |  | (May20 DJ) On track. Will be first site type D to be integrated. |  | 2009-05-22 |  |  |  |  | 2009-04-23 | 2009-04-30 | [11 empty] | FALSE |  | 2661924 | 6474014 | LPR adj to 507-509 Blockhouse Bay Rd o/s Westpac Bank Kinross St Blockhouse Bay Auckland |  |  | CELLSITE |  |  | 2014-08-12 |  |  |  |  | 2009-04-20 | 2009-04-20 | [8 empty] | 2008-08-15
0 | AKL | 287 | AKL-007-112 |  | AKL-007-112-A | Sky Tower | Auckland City |  | TIER_1_ALL | ACTIVE | BO | TX | NOPOLE | [6 empty] | -36.8484 | 174.7617 |  |  |  |  | Microwave, Microwave | AKL-007-106-A, AKL-007-106-A | [5 empty] | 2009-05-06, 2009-05-06 | [5 empty] | 2007-10-01 | 1 |  | 2007-10-01 |  |  | 2007-11-28 | 2007-11-28 | 1 | 2007-11-28 | 2007-11-28 |  |  |  | 2007-11-28 |  |  | 2007-11-28 | 2007-11-28 |  | 2007-10-01 |  | 2007-09-20 | 1 | 1 | 2007-09-20 | 2007-09-20 | [6 empty] | 2007-11-29 | 2007-12-05 | 2007-12-05 |  | 2007-12-11 | 2007-12-11 | [8 empty] | 2007-12-20 |  | 2007-12-20 |  |  |  |  | None |  | 2007-12-20 | [17 empty] | FALSE |  | 2667500 | 6482200 | Sky City Hobson Street |  |  | TXSITE | [8 empty] | 2007-11-29 | [8 empty] | 2007-10-31
0 | AKL | 288 | AKL-007-113 |  | AKL-007-113-A | Remuera Hub (L Orakei) | Auckland City | 3 | TIER_1_ALL | ACTIVE | RT | TX | NOPOLE | [6 empty] | -36.8806 | 174.8013 |  |  |  |  | Microwave | AKL-007-106-A | FALSE | FALSE |  |  | FALSE | 2009-05-12 | [5 empty] | 2008-02-14 | 3 |  | 2011-08-25 |  |  | 2008-01-01 | 2008-01-01 | 1 | 2008-01-01 | 2008-01-01 |  |  |  | 2008-06-30 |  |  | 2008-06-30 | 2008-06-30 |  | 2008-02-19 |  | 2008-06-27 | 4 | 1 | 2008-10-17 | 2008-10-17 | [6 empty] | 2008-10-16 | 2008-10-28 | 2008-10-28 |  | 2008-11-21 | 2008-11-14 | [8 empty] | 2008-11-21 |  | 2008-11-21 |  |  |  |  | Link to Orakie. REQUIRE : 300mmØ | [19 empty] | FALSE |  | 2670963 | 6478553 | 460 Remuera Rd, Remuera, Auckland |  |  | TXSITE | [8 empty] | 2008-10-03 | [8 empty] | 2007-10-31
0 | AKL | 289 | AKL-007-114 |  | AKL-007-114-D | Penrose Hub (Penrose East | Auckland City | 3 | TIER_1_ALL | ACTIVE | RT | TX | [7 empty] | -36.9154 | 174.8162 |  |  |  |  | Microwave | AKL-007-112-A | FALSE | FALSE |  |  | FALSE | [6 empty] | 2009-04-24 | 5 | 2009-04-30 | 2012-04-03 |  |  | 2009-05-15 | 2009-05-18 | 1 | 2009-06-17 | 2009-09-15 |  | 2009-05-06 |  | 2009-06-05 |  |  | 2009-06-05 | 2009-06-11 | 2009-04-17 | 2009-04-30 |  | 2009-05-07 | 2 | 1 | 2009-05-06 | 2009-05-20 | [5 empty] | 2009-06-01 | 2009-05-25 | 2009-06-24 | 2009-06-24 |  | 2009-07-17 | 2009-07-09 | [8 empty] | 2009-07-09 | 2009-07-17 | 2009-07-09 |  |  |  |  | link to skytower to be installed and commissioned MB09/09 Link to Penrose East Tier 1 infill 2011 REQUIRE : 600mmØ |  | 2009-07-17 | [17 empty] | FALSE |  | 2672204 | 6474664 | 45 O'Rourke Rd Penrose Auckland |  |  | TXSITE | [7 empty] | 2009-06-01 | 2009-05-25 | [8 empty] | 2009-04-06
0 | AKL | 290 | AKL-007-116 | Matiatia | AKL-007-116-E | Matiatia MC | Auckland City | 22 | 2015 | ACTIVE | RSR | MC | NOPOLE | [6 empty] | -36.7809 | 174.9938 |  |  |  |  | Fibre Optic | AKL-007-192-A | TRUE | FALSE | 2010-03-16 |  | FALSE |  | 2014-12-01 | 2014-12-02 | 2014-12-03 | 2014-12-03 | 2014-12-19 | 2014-12-15 | 1 | 2015-01-16 | 2014-12-15 |  | 2015-01-13 | 2015-04-30 | 2015-04-29 |  | 2015-04-30 | 2015-04-29 | DISCRETIONARY_FULL | 2014-12-19 | 2014-12-19 | 2015-02-20 | 2015-01-29 | 1 | 2015-02-27 | 2015-01-29 | 2015-01-13 | 2015-01-13 | 2015-02-13 | 2015-02-05 | 1 |  | 2015-02-20 | 2015-02-05 | [5 empty] | 2015-05-18 | 2015-05-19 | 2015-05-19 | 2015-05-19 | 2015-05-19 | 2015-05-19 | 2015-05-19 | 2015-05-18 | 2015-05-19 | [7 empty] | 2015-05-26 | 2015-05-27 |  |  |  |  | awaiting fibre feasability. 28/1/15 - 2 degrees to do IBT - chorus to provide fibre to pit on road. Telco notice sent 28/1/15 - JL to prepare AT application 4/2/15 - Site placed to Hardmatch only by Brendon/Trevor on review with Ron 6/3/15 - site back into build programme - AT application to be submitted when I have calcs and PS1 from Ritchie. 20/4/15 - AT application sent today. | [10 empty] | 2015-05-22 | 2015-05-25 | 2015-01-13 | LOW |  | 2015-05-15 | 2015-05-19 | BUILD | 2015-05-19 | FALSE |  | 2688370 | 6489235 | Roadside Ferry Carpark Ocean View Rd, Waiheke |  |  | CELLSITE |  |  |  | SMALL CELLS | [13 empty] | 2014-12-03
0 | AKL | 291 | AKL-007-117 | Oneroa Township North | AKL-007-117-B | Oneroa North | Auckland City | 12 | 2014 | ACTIVE | RSR | MC | NOPOLE | Grey | [5 empty] | -36.7816 | 175.0084 |  | 2010-03-25 |  | 2010-04-06 | Fibre Optic | AKL-007-192-A | TRUE | FALSE | 2010-03-16 |  | FALSE |  | 2014-08-11 | 2014-08-12 | 2014-08-20 | 2014-08-21 | 2014-09-05 | 2014-09-01 | 3 | 2014-09-12 | 2014-10-16 | 2014-10-31 | 2014-10-29 | 2014-11-07 | 2014-11-18 |  | 2014-11-14 | 2014-11-18 | DISCRETIONARY_FULL | 2014-09-09 | 2014-09-08 | 2014-11-07 | 2014-10-29 | 3 | 2014-11-14 | 2014-10-29 | 2014-10-21 | 2014-09-30 | 2014-10-24 | 2014-10-24 | 1 |  | 2014-10-31 | 2014-10-24 | [5 empty] | 2014-11-24 | 2014-11-14 | 2014-12-18 | 2014-12-16 | 2014-12-16 | 2014-12-18 | 2014-12-16 | 2014-12-18 | 2014-12-16 | [7 empty] | 2014-12-19 | 2014-12-19 |  |  |  |  | Proposed site behind shops in parking area, although LO tentative about site. SITE PLACED ON HOLD 27/04/2010. 25.06.14 Propose the LPR infront of the shops 01.08.14 BC Approved. Progress to build ASAP 21.08.14 - council recommended LPR next to bus stop - outside 137 Oceanview rd - PDI issued today | [10 empty] | 2014-12-18 | 2014-12-19 | 2014-09-08 | HIGH |  | 2014-12-12 | 2014-12-12 | BUILD |  | FALSE |  | 2689668 | 6489130 | outside 139 Ocean View Road Oneroa (next to bus stop) |  |  | CELLSITE | [17 empty] | 2014-08-21
0 | AKL | 292 | AKL-007-118 | Ostend East |  |  | Auckland City |  | TIER_9 | [22 empty] | FALSE | [60 empty] | Ostend Option A: LEASED GF option at 2a Tahi Rd Ostend. Grid: 2693757 6487404 Option B: Colo on 10m Vodafone option. Grid: 2693527 6487657 After site search 1/12/09: We looked at 24 Tahi Rd - not 2a!! - mistakenly thought this was the property with a lease Options above still valid plus other possible options in commercial area on Tahi Rd
0 | AKL | 293 | AKL-007-119 | Onetangi Beach |  |  | Auckland City |  | TIER_9 | [22 empty] | FALSE | [60 empty] | Coverage to Onetangi Beach
0 | AKL | 294 | AKL-007-122 | Bastion Point | AKL-007-122-A | Bastion Point (LPR) | Auckland City |  | TIER_1_ALL | ACTIVE | BO | D6 | NOPOLE | green |  |  | 6.3 | 6.3 |  | -36.8454 | 174.817 |  |  |  |  | Microwave | AKL-007-112-A | [11 empty] | 2008-08-29 | 7 | 2009-08-13 | 2009-08-21 |  |  | 2009-03-27 | 2009-03-27 | 3 | 2009-09-18 | 2009-09-17 |  | 2008-09-24 |  | 2009-04-30 |  |  | 2009-04-30 | 2009-05-04 | 2008-12-19 | 2008-12-04 |  | 2008-12-19 | 3 | 6 | 2009-08-28 | 2009-08-31 | [5 empty] | 2009-09-21 | 2009-09-21 | 2009-11-13 | 2009-11-13 |  | 2009-11-18 | 2009-11-18 | [8 empty] | 2009-11-20 | 2009-11-20 | 2009-11-20 |  |  |  |  | On Air |  | 2009-11-20 | [17 empty] | FALSE |  | 2672436 | 6482426 | Opp Kelly Tarltons Aquatic World exit, Tamaki Drv, Orakei Warf, Auckland |  |  | CELLSITE |  |  | 2014-08-12 |  |  |  |  | 2009-09-21 | 2009-09-21 | [8 empty] | 2008-06-26
0 | AKL | 295 | AKL-007-123 | Victoria Gully | AKL-007-123-C | Victoria Gully | Auckland City |  | TIER_1_ALL | ACTIVE | RT | B6 | NOPOLE | grey |  |  | 15 | 15 |  | -36.8496 | 174.7539 |  |  |  |  | Microwave | AKL-007-144-A | [11 empty] | 2009-05-19 | 4 | 2009-05-14 | 2015-12-17 |  |  | 2009-05-29 | 2009-05-29 | 1 | 2009-05-29 | 2009-05-29 |  | 2009-05-21 |  | 2009-06-19 |  |  | 2009-06-19 | 2009-05-22 | 2016-01-29 | 2009-05-25 |  | 2009-06-15 | 1 | 1 | 2009-06-15 | 2009-06-15 | [5 empty] | 2009-06-25 | 2009-06-25 | 2009-08-18 | 2009-08-18 |  | 2009-08-28 | 2009-08-31 | [8 empty] | 2009-09-01 | 2009-09-01 | 2009-09-01 | [6 empty] | 2009-09-01 | [17 empty] | FALSE |  | 2666808 | 6482071 | 45 Sale Street, Auckland |  |  | CELLSITE |  |  | 2014-06-16 |  |  |  |  | 2009-06-25 | 2009-06-25 | [8 empty] | 2009-05-12
0 | AKL | 296 | AKL-007-124 |  | AKL-007-124-E | Grey Lynn North | Auckland City |  | TIER_1_ALL | ACTIVE | RT | B6 | NOPOLE | grey |  |  | 9.7 | 9.7 |  | -36.8553 | 174.7309 |  |  |  |  | Microwave | AKL-007-112-A | [5 empty] | 2009-05-08 |  |  |  |  | 2009-01-30 | 2009-01-30 | 1 | 2009-01-30 | 2009-01-30 |  |  | 2008-12-24 | 2009-01-13 | 1 | 2009-03-13 | 2009-03-20 |  | 2009-02-13 |  | 2009-04-24 |  |  | 2009-04-24 | 2009-04-23 | 2009-02-10 | 2009-02-16 |  | 2009-03-11 | 1 | 1 | 2009-03-19 | 2009-03-11 | [5 empty] | 2009-04-27 | 2009-04-27 | 2009-05-22 | 2009-05-22 |  | 2009-06-12 | 2009-06-12 | [8 empty] | 2009-06-12 | 2009-06-16 | 2009-06-12 |  |  |  |  | Build proceeding 26/05 |  | 2009-06-16 | [17 empty] | FALSE |  | 2664745 | 6481488 | 316-318 Richmond Rd Grey Lynn Auckland |  |  | CELLSITE |  |  | 2014-06-16 |  |  |  |  | 2009-04-27 | 2009-04-27 | [8 empty] | 2009-01-15
0 | AKL | 297 | AKL-007-125 | Ostend Town |  |  | Auckland City |  | TIER_9 | [22 empty] | FALSE | [60 empty] | Commercial Area for New pole or co-lo with Vodafone.
0 | AKL | 298 | AKL-007-126 |  | AKL-007-126-F | Balmoral Road | Auckland City |  | TIER_1_ALL | ACTIVE | RSR | D6 | P4C | green |  |  | 9.8 | 9.8 |  | -36.8902 | 174.7614 |  |  |  |  | Leased Line | AKL-007-106-A | [11 empty] | 2009-03-26 | 5 | 2009-03-27 | 2009-06-15 |  |  | 2009-06-05 | 2009-05-29 |  | 2009-06-05 | 2009-06-08 |  | 2009-03-04 |  | 2009-07-07 |  |  | 2009-07-07 | 2009-06-30 | 2009-03-24 | 2009-04-01 |  | 2009-04-17 | 2 | 5 | 2009-04-17 | 2009-07-23 | 2009-06-17 |  |  |  |  | 2009-08-03 | 2009-07-29 | 2009-08-15 | 2009-08-18 |  | 2009-08-15 | 2009-08-18 | [8 empty] | 2009-08-21 | 2009-08-21 | 2009-08-21 | [6 empty] | 2009-08-21 |  |  |  |  | 2009-06-12 | 2009-06-17 | [11 empty] | FALSE |  | 2667380 | 6477553 | 46 Balmoral Road Mt Eden Auckland |  |  | CELLSITE |  |  | 2014-06-16 |  |  |  |  | 2009-08-03 | 2009-07-29 | [8 empty] | 2009-03-24
0 | AKL | 299 | AKL-007-127 |  | AKL-007-127-E | Dominion Rd Central | Auckland City |  | TIER_1_ALL | ACTIVE | RT | B6 | NOPOLE | grey |  |  | 11.2 | 11.2 |  | -36.8936 | 174.7451 |  |  |  |  | Microwave | AKL-007-015-C | [5 empty] | 2009-05-11 | [5 empty] | 2009-01-13 | 3 | 2009-03-13 | 2009-03-17 |  |  |  | 2008-07-25 |  | 2009-06-05 | 2009-06-08 |  | 2009-01-20 |  | 2009-04-15 |  |  | 2009-04-17 | 2009-03-25 | 2009-01-19 | 2009-01-23 |  | 2009-04-01 | 1 | 1 | 2009-03-27 | 2009-04-01 | [5 empty] | 2009-06-08 | 2009-06-08 | 2009-06-26 | 2009-06-26 |  | 2009-07-10 | 2009-07-15 | [8 empty] | 2009-07-22 | 2009-07-22 | 2009-07-22 |  |  |  |  | Build ready awaiting full access to Site. Matt Daly to confirm 26/05 (Jul14 RB) Integration after SKY OSN Integration |  | 2009-07-22 | [17 empty] | FALSE |  | 2665920 | 6477213 | Cnr Calgarry & 771 Dominion Rd Balmoral Auckland |  |  | CELLSITE |  |  | 2014-06-16 |  |  |  |  | 2009-06-08 | 2009-06-08 | [8 empty] | 2008-07-15
0 | AKL | 300 | AKL-007-128 |  | AKL-007-128-C | Sandringham | Auckland City |  | TIER_1_ALL | ACTIVE | RT | B6 | NOPOLE | grey |  |  | 11 | 11 |  | -36.8916 | 174.736 |  |  |  |  | Microwave | AKL-007-071-A | [5 empty] | 2009-05-11 | [5 empty] | 2008-09-16 | 3 | 2008-12-10 | 2009-03-24 |  |  |  | 2008-07-25 | 2 |  | 2008-07-25 |  |  |  | 2008-11-28 |  |  | 2008-11-28 | 2008-11-24 |  | 2008-09-26 |  | 2008-10-21 | 3 | 3 | 2009-03-27 | 2009-04-01 | [6 empty] | 2008-12-08 | 2009-01-21 | 2009-01-21 |  | 2009-02-27 | 2009-02-27 | [8 empty] | 2009-03-27 | 2009-03-31 | 2009-03-27 |  |  |  |  | TI complete Trabnsmission Path pending connection to network 26/03 |  | 2009-03-31 | [17 empty] | FALSE |  | 2665110 | 6477450 | Gordon Buildings 519 Sandringham Rd Shops Sandringham Auckland |  |  | CELLSITE |  |  | 2014-06-16 | [5 empty] | 2008-12-03 | [8 empty] | 2008-07-22
0 | AKL | 301 | AKL-007-129 |  | AKL-007-129-B | Point Chevalier South | Auckland City | 3 | TIER_1_ALL | ACTIVE | GF | A6 | P3 | grey |  |  | 21.2 | 21.2 |  | -36.8711 | 174.7107 |  |  |  |  | Microwave | AKL-007-008-A | FALSE | FALSE |  |  | FALSE | [6 empty] | 2009-03-30 | 4 | 2009-03-31 | 2015-09-08 |  |  | 2009-04-03 | 2009-03-24 |  | 2009-04-15 | 2009-04-15 |  | 2009-04-07 |  | 2009-05-29 |  |  | 2009-05-29 | 2009-06-03 | 2009-04-06 | 2009-03-25 |  | 2009-04-21 | 1 | 1 | 2009-05-12 | 2009-04-21 | 2009-04-28 |  |  |  |  | 2009-06-08 | 2009-06-10 | 2009-06-29 | 2009-06-30 |  | 2009-06-29 | 2009-06-29 | [8 empty] | 2009-06-30 | 2009-07-30 | 2009-06-30 |  |  |  |  | On Air Link to Birkenhead S REQUIRE : 600mmØ |  | 2009-07-30 | [5 empty] | 2009-04-28 | [11 empty] | FALSE |  | 2662904 | 6479773 | 1218 Great North Rd Pt Chevalier |  |  | CELLSITE |  |  | 2014-06-16 |  |  |  |  | 2009-06-08 | 2009-06-10 | [8 empty] | 2009-03-16
0 | AKL | 302 | AKL-007-130 | Waiheke Island Hub |  |  | Auckland City |  | TIER_9 | [22 empty] | FALSE | [60 empty] | Hub site. Used by Vodafone. coverage for Orapiu Rd.
0 | AKL | 303 | AKL-007-131 |  | AKL-007-131-A | Mission Bay Upper | Auckland City |  | TIER_1_ALL | ACTIVE | RT | B6 | NOPOLE | grey |  |  | 15.2 | 15.2 |  | -36.8498 | 174.8302 | [17 empty] | 2008-09-19 | 7 | 2009-04-02 | 2009-04-08 |  |  |  | 2008-11-12 | 3 | 2009-04-30 | 2009-06-24 |  | 2008-09-30 |  | 2009-05-01 |  |  | 2009-05-01 | 2009-05-04 | 2009-03-27 | 2008-11-18 |  | 2008-12-03 | 2 | 6 | 2009-04-30 | 2009-04-28 | [5 empty] | 2009-05-04 | 2009-05-04 | 2009-06-05 | 2009-05-29 |  | 2009-06-19 | 2009-06-19 | [8 empty] | 2009-07-03 | 2009-07-06 | 2009-07-03 |  |  |  |  | On Air Contact: Richard & Jean Whittington dickw@woosh.co.nz Ph: (09) 528 3451 |  | 2009-07-06 | [17 empty] | FALSE |  | 2673603 | 6481907 | 10 Tagalad Rd Mission Bay Auckland 1071 |  |  | CELLSITE |  |  | 2014-08-12 |  |  |  |  | 2009-05-04 | 2009-05-04 | [8 empty] | 2008-08-19
0 | AKL | 304 | AKL-007-132 |  | AKL-007-132-C | New Windsor | Auckland City |  | TIER_1_ALL | ACTIVE | RSR | D6 | P4C | green |  |  |  | 15 |  | -36.9074 | 174.7139 | [12 empty] | 2009-10-21 | 2009-10-21 |  |  |  | 2009-10-29 | 1 | 2009-10-30 | 2009-10-29 |  |  | 2009-12-11 | 2009-12-14 |  | 2010-02-05 |  |  | 2009-11-04 |  | 2009-11-04 |  |  | 2009-11-04 | 2009-11-04 | 2009-11-16 | 2009-11-10 |  | 2009-11-30 | 1 | 1 | 2009-11-30 | 2009-11-30 | 2009-11-24 |  |  |  |  | 2010-01-18 | 2010-01-18 | 2010-02-05 | 2010-02-04 |  | 2010-02-05 | 2010-02-04 | [8 empty] | 2010-02-09 | 2010-02-10 | 2010-02-09 |  |  |  |  | Noticiation closed with no resident lodgements/feedback to consultation letters. Early access given by Council, Kelly advised Council of our commencement date for license agreement. |  | 2010-02-10 |  |  |  |  | 2009-11-30 | 2009-11-24 | [11 empty] | FALSE |  | 2663110 | 6475732 | 188 New Windsor Rd, New Windsor |  |  | CELLSITE |  |  | 2014-06-16 |  |  |  |  | 2010-01-18 | 2010-01-18 | [8 empty] | 2009-10-21
0 | AKL | 305 | AKL-007-133 |  | AKL-007-133-A | Avondale Racecourse | Auckland City |  | TIER_1_ALL | ACTIVE | RT | B6 | NOPOLE | green |  |  | 16.7 | 16.7 |  | -36.8951 | 174.6926 | [17 empty] | 2008-12-05 | 5 | 2009-01-30 | 2009-03-26 |  |  | 2009-04-28 | 2009-05-05 | 5 | 2009-04-30 | 2009-06-24 |  | 2008-12-24 |  | 2009-04-30 |  |  | 2009-04-30 | 2009-05-04 | 2009-01-08 | 2008-12-24 |  | 2009-01-30 | 3 | 5 | 2009-04-09 | 2009-04-01 | [5 empty] | 2009-05-11 | 2009-05-11 | 2009-05-29 | 2009-05-29 |  | 2009-06-19 | 2009-06-19 | [8 empty] | 2009-06-28 | 2009-06-30 | 2009-06-28 |  |  |  |  | On Air |  | 2009-06-30 | [17 empty] | FALSE |  | 2661240 | 6477140 | Avondale Racecourse, 2-48 Ash St, Avondale, Auckland |  |  | CELLSITE |  |  | 2014-06-16 |  |  |  |  | 2009-05-07 | 2009-05-07 | [8 empty] | 2008-09-09
0 | AKL | 306 | AKL-007-134 |  | AKL-007-134-A | Kingsland | Auckland City |  | TIER_1_ALL | ACTIVE | BO | A6 | NOPOLE | green |  |  | 6 | 6 |  | -36.8689 | 174.7463 |  |  |  |  | Leased Line, Microwave | AKL-007-106-A, AKL-007-071-A | [11 empty] | 2008-10-07 | 4 | 2009-02-16 | 2009-02-16 |  |  | 2009-03-12 | 2009-02-11 | 4 | 2009-03-31 | 2009-04-09 |  |  |  | 2009-04-10 |  |  | 2009-04-10 | 2009-04-08 | 2009-02-13 | 2009-02-16 |  | 2009-03-16 | 1 | 3 | 2009-03-20 | 2009-03-16 | [5 empty] | 2009-04-16 | 2009-04-16 | 2009-05-08 | 2009-04-29 |  | 2009-05-22 | 2009-05-22 | [8 empty] | 2009-05-22 | 2009-05-29 | 2009-05-22 |  |  |  |  | SA: license and HOA to be signed. TNZ Approval recieved LL has been ordered for this Site 2/04 |  | 2009-05-29 | [17 empty] | FALSE |  | 2666086 | 6479951 | Bond St Overbridge (Over SH16), End of New Bond St (Access and Cabinet location), Kingsland, Auckland |  |  | CELLSITE |  |  | 2014-06-16 |  |  |  |  | 2009-04-14 | 2009-04-14 | [8 empty] | 2008-09-16
0 | AKL | 307 | AKL-007-135 |  | AKL-007-135-G | Mt Eden | Auckland City |  | TIER_1_ALL | ACTIVE | RT | DU5 | NOPOLE | grey |  |  | 12.7 | 12.7 |  | -36.8784 | 174.75 |  |  |  |  | Microwave | AKL-007-015-C | [11 empty] | 2009-05-14 | 2 | 2009-05-21 | 2009-05-21 |  |  | 2009-06-01 | 2009-05-26 | 1 | 2009-06-01 | 2009-05-26 | DISCRETIONARY_FULL | 2009-05-22 | 2012-06-01 | 2009-06-26 |  | 2 | 2009-06-26 | 2009-06-24 | 2009-05-21 | 2009-05-25 |  | 2009-06-16 | 1 | 2 | 2009-06-15 | 2009-06-16 | [5 empty] | 2009-06-29 | 2009-06-25 | 2009-08-14 | 2009-08-14 |  | 2009-08-21 | 2009-08-21 | [8 empty] | 2009-08-25 | 2009-08-25 | 2009-08-25 |  |  |  |  | Lease ok, Awaiting TP approval. 26/5 Cabinets swapped out for new DU EQUIPMENT. |  | 2009-08-25 | [17 empty] | FALSE |  | 2666395 | 6478888 | Metropolitan Rentals 317 - 319 Dominion Road Mt Eden |  | Lodged with rev 3 plans on the 1 June 2012 with Auckland Council - 01/06/2012 | CELLSITE |  |  | 2014-06-16 |  |  |  |  | 2009-06-29 | 2009-06-25 | [8 empty] | 2009-05-12
0 | AKL | 308 | AKL-007-136 |  | AKL-007-136-E | Morningside | Auckland City |  | TIER_1_ALL | ACTIVE | GF | A6 | P1 | grey |  |  | 15 | 15 |  | -36.8733 | 174.7367 | [17 empty] | 2008-11-27 | 1 | 2008-11-27 | 2008-11-27 |  |  | 2009-01-30 | 2009-01-23 | 1 | 2009-04-02 | 2009-04-08 |  | 2008-12-11 |  | 2009-02-27 |  |  | 2009-02-27 | 2009-02-19 | 2008-12-23 | 2009-01-16 |  | 2009-01-16 | 1 | 1 | 2009-01-27 | 2009-01-16 | 2009-02-18 |  |  |  |  | 2009-04-06 | 2009-04-08 | 2009-04-30 | 2009-04-28 |  | 2009-05-08 | 2009-04-28 | [8 empty] | 2009-04-30 | 2009-05-01 | 2009-04-30 |  |  |  |  | Proceeding awaiting power for integration MB01/05 |  | 2009-05-01 |  |  |  |  | 2009-02-18 | 2009-02-18 | [11 empty] | FALSE |  | 2665213 | 6479472 | Motorhaus Motorcycles, 6 Western Springs Rd, Morningside, Auckland |  |  | CELLSITE |  |  | 2014-06-16 |  |  |  |  | 2009-04-06 | 2009-04-06 | [8 empty] | 2008-10-08
0 | AKL | 309 | AKL-007-137 | Orakei LPR | AKL-007-137-B | Orakei, LPR | Auckland City | 3 | TIER_1_INFILL | ACTIVE | RSR | DU5 | P4C | green | INLINE | STANDALONE | 9 | 10.8 | 1 | -36.8518 | 174.7961 |  |  |  |  | Microwave | AKL-007-113-A | FALSE | FALSE |  |  | FALSE |  |  | 2011-02-17 |  | 2011-02-17 |  | 2009-05-07 | 6 | 2010-02-05 | 2011-06-30 | 2009-09-02 | 2009-09-08 | 2009-10-07 | 2009-09-16 | 1 | 2010-03-12 | 2010-03-12 | NES | 2009-05-29 | 2009-06-04 | 2009-08-07 | 2009-07-30 | 1 | 2010-02-12 | 2010-02-18 | 2010-02-12 | 2009-05-25 |  | 2009-06-17 | 6 |  | 2009-09-30 | 2011-08-12 | 2011-08-22 |  |  |  |  | 2011-06-13 | 2011-06-13 | 2011-07-01 | 2011-08-15 | 2011-08-11 | 2011-08-31 | 2011-09-01 | [8 empty] | 2011-09-14 | 2011-10-28 | 2011-09-16 | 2011-10-28 | 2011-10-07 | 2012-01-05 | 2012-03-06 | 12.06.2014 : "D" configuration build. (APM, Battery, & 2 x RFC) using version "B" cabinets. Thus making it a "DU" Site. (As per Ron Bush/blr) |  | 2011-08-31 | 2011-06-09 | 2011-06-09 | 2011-06-13 | 2011-08-22 | 2009-09-04 | 2011-08-22 | 2011-07-01 | 2011-08-15 | [8 empty] | 2011-08-11 | FALSE |  | 2670562 | 6481755 | Light Pole on roading reserve situated beside coffee cart in the mini golf carpark 3-5 Tamaki Drive Auckland |  |  | CELLSITE |  |  | 2014-08-12 |  |  |  |  | 2010-03-15 | 2010-03-15 | [6 empty] | 2011-09-16 | 2011-09-23 | 2009-04-17
0 | AKL | 310 | AKL-007-140 |  | AKL-007-140-C | Auckland University | Auckland City |  | TIER_1_ALL | ACTIVE | BO | D6 | NOPOLE | green |  |  | 6 | 6 |  | -36.8516 | 174.7695 |  |  |  |  | Leased Line | AKL-007-106-A | [10 empty] | 2009-02-04 | 2009-02-04 | 4 | 2009-04-03 | 2015-05-14 |  |  | 2009-06-05 | 2009-05-29 |  | 2009-06-05 | 2009-06-08 |  | 2009-03-06 |  | 2009-04-10 |  |  | 2009-04-10 | 2009-04-22 | 2009-02-17 | 2009-02-16 |  | 2009-04-07 | 2 | 3 | 2009-04-03 | 2009-04-27 | [5 empty] | 2009-05-22 | 2009-05-22 | 2009-06-05 | 2009-05-28 |  | 2009-06-10 | 2009-06-08 | [8 empty] | 2009-06-20 | 2009-06-18 | 2009-06-20 |  |  |  |  | build complete awaiting TI and Integration 04/06MB |  | 2009-06-18 | [17 empty] | FALSE |  | 2668188 | 6481820 | 5 Alfred St (outside Library ground floor entrance) Auckland CBD |  |  | CELLSITE |  |  | 2014-06-16 |  |  |  |  | 2009-05-22 | 2009-05-22 | [8 empty] | 2009-01-12
0 | AKL | 311 | AKL-007-142 |  | AKL-007-142-A | Remuera Rd | Auckland City |  | TIER_1_ALL | ACTIVE | RSR | D6 | P4C | green |  |  | 13 | 13 |  | -36.8811 | 174.8012 |  |  |  |  | Leased Line | AKL-007-106-A | [10 empty] | 2009-02-24 | 2009-02-24 | 1 | 2009-02-24 | 2009-02-24 |  |  | 2009-06-05 | 2009-05-29 |  | 2009-06-05 | 2009-06-23 |  | 2009-02-27 |  | 2009-03-31 |  |  | 2009-03-31 | 2009-02-25 | 2009-02-18 | 2009-02-18 |  | 2009-03-16 | 1 | 1 | 2009-03-12 | 2009-03-16 | 2009-05-26 |  |  |  |  | 2009-05-25 | 2009-05-25 | 2009-06-26 | 2009-06-26 |  | 2009-06-30 | 2009-06-30 | [8 empty] | 2009-06-30 | 2009-07-03 | 2009-06-30 |  |  |  |  | (Jun03 DJ) On track SOA Jun30. (Jun10 DJ) UG svcs encountered - hold dates conditional on Chris A response. On track for SOA Jun30 (Jun18 DJ) CI & TI delayed 1 wk (LL issue), still holding SOA Jun30. (Jun24 DJ) On track SOA Jun30. (Jul01 DJ) SOA !! |  | 2009-07-03 |  |  |  |  | 2009-05-22 | 2009-05-26 | [11 empty] | FALSE |  | 2670946 | 6478495 | 439 Remuera Rd (cnr Cotter ave) Remuera Auckland |  |  | CELLSITE |  |  | 2014-08-12 |  |  |  |  | 2009-05-25 | 2009-05-25 | [8 empty] | 2009-01-12
0 | AKL | 312 | AKL-007-143 |  | AKL-007-143-A | Remuera East | Auckland City |  | TIER_1_ALL | ACTIVE | RSR | D6 | P4F | grey |  |  | 13.8 | 13.8 |  | -36.8801 | 174.8126 |  |  |  |  | Leased Line | AKL-007-106-A | [10 empty] | 2009-02-16 | 2009-02-16 | 3 | 2009-02-16 | 2009-07-24 |  |  | 2009-06-05 | 2009-05-29 |  | 2009-06-05 |  |  | 2009-02-20 |  | 2009-02-20 |  |  | 2009-02-20 | 2009-02-20 | 2009-02-18 | 2009-02-18 |  | 2009-03-04 | 2 | 2 | 2009-03-19 | 2009-03-25 | 2009-05-26 |  |  |  |  | 2009-06-08 | 2009-06-08 | 2009-06-19 | 2009-06-18 |  | 2009-06-19 | 2009-06-18 | [8 empty] | 2009-06-24 | 2009-06-24 | 2009-06-24 |  |  |  |  | (May28 DJ) Pole OK. Holding SOA date but there is some potential to complete sooner. --taupe (Jun03 DJ) On track SOA Jun30. (Jun10 DJ) On track for SOA Jun30 (Jun18 DJ) still holding SOA Jun30. (Jun24 DJ) SOA brought fwd to Jun24. > SOA!! |  | 2009-06-30 |  |  |  |  | 2009-05-22 | 2009-05-26 | [11 empty] | FALSE |  | 2671971 | 6478583 | 636 Remuera Rd Remuera Auckland |  |  | CELLSITE |  |  | 2014-08-12 |  |  |  |  | 2009-06-08 | 2009-06-08 | [8 empty] | 2009-01-13
0 | AKL | 313 | AKL-007-144 |  | AKL-007-144-A | Ponsonby Hub | Auckland City |  | TIER_1_ALL | ACTIVE | RT | TX | [7 empty] | -36.8586 | 174.7525 |  |  |  |  | Microwave | AKL-007-041-B | [11 empty] | 2009-04-15 | 1 | 2009-04-15 | 2009-04-15 |  |  | 2009-05-25 | 2009-05-22 | 1 | 2009-05-25 | 2009-05-27 |  | 2009-04-15 |  | 2009-05-28 |  |  | 2009-05-28 | 2009-05-28 | 2009-04-06 | 2009-04-14 |  | 2009-04-21 | 2 | 1 | 2009-04-22 | 2009-06-30 | [5 empty] | 2009-05-25 | 2009-05-25 | 2009-06-30 | 2009-06-30 |  | 2009-07-07 | 2009-07-07 | [8 empty] | 2009-07-07 | 2009-07-07 | 2009-07-07 |  |  |  |  | Build Ready awaiting prototype cabinet due to headspace in Telecoms room. SBS order made. Cabinet due in 3 weeks 26/05 |  | 2009-07-07 | [17 empty] | FALSE |  | 2666655 | 6481084 | 9 Hopetoun St Ponsonby Auckland |  |  | TXSITE | [7 empty] | 2009-05-25 | 2009-05-25 | [8 empty] | 2009-04-02
0 | AKL | 314 | AKL-007-145 |  | AKL-007-145-C | Mt Wellington North | Auckland City |  | TIER_1_ALL | ACTIVE | RSR | D6 | P4C | green | [5 empty] | -36.8997 | 174.839 |  |  |  |  | Microwave | AKL-007-103-E | [6 empty] | 2009-08-17 |  |  |  |  | 2009-08-27 | 1 | 2009-08-21 | 2009-08-27 |  |  | 2009-10-30 | 2009-10-28 |  | 2009-11-20 |  |  | 2009-08-28 |  | 2009-08-28 |  |  | 2009-08-28 | 2009-08-28 | 2009-09-09 | 2009-09-17 |  | 2009-09-23 | 1 |  | 2009-09-30 | 2009-09-23 | 2009-11-25 |  |  |  |  | 2009-11-11 | 2009-11-11 | 2009-12-02 | 2009-12-02 |  | 2009-12-03 | 2009-12-03 | [8 empty] | 2009-12-04 | 2009-12-04 | 2009-12-04 |  |  |  |  | Pole on hold until acquisition expect to know about Council policy. Lease ready and council sent hardcopy to us. Early access email from Kelly. Pole delays, no response from CSP. KH & JB to follow up Council for lease documents. |  | 2009-12-04 |  |  |  |  | 2009-11-11 | 2009-11-25 | [11 empty] | FALSE |  | 2674270 | 6476363 | Lightpole replacement outside of property located at 60 Barrack Road, Mount Wellington |  |  | CELLSITE |  |  | 2014-08-12 | [5 empty] | 2009-11-11 | [8 empty] | 2009-08-26
0 | AKL | 315 | AKL-007-146 |  | AKL-007-146-A | Karangahape Rd | Auckland City |  | TIER_1_ALL | ACTIVE | RT | D6 | NOPOLE | grey |  |  | 31.1 | 31.1 |  | -36.8584 | 174.7604 |  |  |  |  | Microwave | AKL-007-041-B | [11 empty] | 2009-06-05 | 4 | 2009-05-29 | 2015-05-20 |  |  | 2009-06-30 | 2009-06-26 | 3 | 2009-08-10 | 2009-08-10 |  | 2009-06-05 |  | 2009-07-15 |  |  | 2009-08-21 | 2009-08-25 | 2009-06-24 | 2009-06-18 |  | 2009-07-16 | 4 |  | 2009-07-15 | 2015-10-22 | [5 empty] | 2009-08-10 | 2009-08-12 | 2009-09-11 | 2009-09-11 |  | 2009-09-22 | 2009-09-23 | [8 empty] | 2009-09-25 | 2009-09-25 | 2009-09-25 |  |  |  |  | S127 complete. Tim confirmed rev2 CD's are latest. |  | 2009-09-25 | [17 empty] | FALSE |  | 2667364 | 6481090 | 150 - 166 Karangahape Road Auckland City |  |  | CELLSITE |  |  | 2014-06-16 |  |  |  |  | 2009-08-10 | 2009-08-12 | [8 empty] | 2009-05-21
0 | AKL | 316 | AKL-007-147 |  | AKL-007-147-A | Dalmation Society, Eden Terrace | Auckland City |  | TIER_1_ALL | ACTIVE | RT | B6 | NOPOLE | grey |  |  | 17.5 | 17.5 |  | -36.8659 | 174.7605 |  |  |  |  | Microwave | AKL-007-015-C | [11 empty] | 2009-05-19 | 2 | 2009-05-20 | 2009-06-16 |  |  | 2009-06-05 | 2009-05-29 | 1 | 2009-06-05 | 2009-05-29 |  | 2009-05-22 |  | 2009-06-30 |  |  | 2009-06-30 | 2009-06-30 | 2009-05-17 | 2009-05-25 |  | 2009-06-16 | 1 | 1 | 2009-06-15 | 2009-06-16 | [5 empty] | 2009-07-20 | 2009-07-21 | 2009-08-19 | 2009-08-19 |  | 2009-08-25 | 2009-08-31 | [8 empty] | 2009-08-31 | 2009-08-31 | 2009-08-31 |  |  |  |  | NOTE - BBU 3806 SWAPPED OUR FOR NEW 3900 UNIT 17/10/2012 |  | 2009-08-31 | [17 empty] | FALSE |  | 2667355 | 6480253 | 12 New North Road Eden Terrace Auckland |  |  | CELLSITE |  |  | 2014-06-16 |  |  |  |  | 2009-07-20 | 2009-07-21 | [8 empty] | 2009-05-11
0 | AKL | 317 | AKL-007-148 |  |  |  | Auckland City |  | TIER_1_ALL
0 | AKL | 318 | AKL-007-149 | Blackpool Beach W/T |  |  | Auckland City |  | TIER_9 | [22 empty] | FALSE | [60 empty] | Coverage to Blackpool Beach, Oneroa,Kennedy Point & some of church Bay.
0 | AKL | 319 | AKL-007-150 | Surfdale |  |  | Auckland City |  | TIER_9 | [22 empty] | FALSE | [60 empty] | Surfdale Waiheke Island. Strategic Option if we can get it covers both Surfdale and Blackpool from a ridgeline. Option A: GF/LP Option at End of Burrell Road Extension where road ends and Park track starts Grid: 2690814 6488389 (GOOD Location) Option B: LP Option near HV pole No: 279735 Burrell Road Extension Grid; 2690718 6488191 NOTE: If we cannot get a single site on this on ridge line of Burrall Road Extension then Site will need to be split in two with a site in 'Surfdale' and 'Blackpool' . The Surfdale options would then revert to: Option A: The Surfdale option would therefore be centred on the Surfdale Shopping Centre area Grid: 2690987 6487733 Option B: Off Ocean View Rd 31 Wellington Road potential to swapout telegraph pole 55m AMSL E 2691768 N 6487950 (on good ridge for coverage , preferred area) After site search 1/12/09: Option A: LPR - Tetley Rd - opposite Lannan Rd - cabinets to be located cnr Tetley and Lannan Option B: RT on Bowling Club - Hamilton Rd Option C: GF behind Ao Place Takeaways - Miami Ave After site search 16/03/10: Option A: Rooftop at Recreation center Option B: Green field pole at Stefano's Pizza
0 | AKL | 320 | AKL-007-151 | Surfdale North |  |  | Auckland City |  | TIER_9 | [22 empty] | FALSE | [60 empty] | High Locations for new pole site. To provide RF coverage for Goodwin Ave, Hekenua Rd residents.
0 | AKL | 321 | AKL-007-152 | Onetangi Rd |  |  | Auckland City |  | TIER_9 | [22 empty] | FALSE | [60 empty] | Areas to the South of Onetangi Township. Wineries, Golf Course, Aerodrome
0 | AKL | 322 | AKL-007-153 |  |  |  | Auckland City |  | TIER_9 | [22 empty] | FALSE
0 | AKL | 323 | AKL-007-154 |  |  |  | Auckland City |  | TIER_9 | [22 empty] | FALSE
0 | AKL | 324 | AKL-007-155 | Omiha |  |  | Auckland City |  | TIER_9 | [22 empty] | FALSE | [60 empty] | Omiha, Waiheke Island Option A: GF Pole at Glenbrook Reserve on Okoka Road, Omiha. Grid: 2694148 6485151 After site search 1/12/09: Option A: 41 Okoka Rd
0 | AKL | 325 | AKL-007-156 | Oneroa Bay |  |  | Auckland City |  | TIER_9 | [22 empty] | FALSE | [60 empty] | Coverage to Oneroa Bay & Little Oneroa Beach. Also residential areas to the east across oneroa Bay.
0 | AKL | 326 | AKL-007-157 | Onetangi Town |  |  | Auckland City |  | TIER_9 | [22 empty] | FALSE | [60 empty] | Onetangi Option A: GF 10m P)ole side of road adjacent to the wall of the hay Paddock Winery (on Bend in Seaveiw Road. (Makes full use of elevated Terrain to peek over seashore and entire Onetangi Beach. (GOOD if we can get this) PREFERRED. Grid: 2695589 6487922 Option B: 10m Vodafone Colo adj to Shell Station Cnr of Onetangi Rd and Seaveiw Rd Onetangi Town Grid: 2695988 6487805 NOTE: Do not use the distant 'AKL-007-119 Onetangi' site colo poles of Voda and TNZ at Fountain Health Farm Contact Diana Goldman 09 372 8873 for appointment. BUT these options well off to the east of the town and away from service area. KEEP AS BACKUP if we CANNOT get the town options under AKL-007-157 Onetangi Town. After site search 1/12/09: Option A above still preference otherwise may need 2 sites to cover settlment and beach which would be VFNZ co-lo as mentioned above to cover the town with the beach being coverd by VFNZ co-lo from Man O War Rd. Option B: GF or RT at Backpackers on top of hill opposite 7th Ave Option C: LPR along beach & GF in industrial area site visit 16/3/10 Option A: Ind. building at Totara Td.
0 | AKL | 327 | AKL-007-158 |  |  |  | Auckland City |  | TIER_9 | [22 empty] | FALSE
0 | AKL | 328 | AKL-007-159 | Motutapu Island |  |  | Auckland City |  | TIER_9 | [22 empty] | FALSE
0 | AKL | 329 | AKL-007-160 | Palm Beach |  |  | Auckland City |  | TIER_9 | [22 empty] | FALSE | [60 empty] | Coverage to Palm Beach Area to the west and east.
0 | AKL | 330 | AKL-007-161 | Rotoroa Island |  |  | Auckland City |  | TIER_9 | [22 empty] | FALSE
0 | AKL | 331 | AKL-007-162 | Sky City Carpark | AKL-007-162-A | Sky City Carpark | Auckland City | 2 | TIER_3 | ACTIVE | IB | DF | NOPOLE | grey | STACK_A | COSITE |  |  | 1 | -36.849 | 174.762 |  |  |  |  | Fibre Optic, Fibre Optic | AKL-007-112-A | TRUE | TRUE | 2012-06-20 |  | TRUE |  | 2010-02-09 | 2012-06-20 |  | 2012-10-01 |  | 2010-03-24 | 2 | 2010-03-24 | 2012-11-01 | 2013-02-21 | 2013-02-18 | 2013-04-12 | 2013-04-04 |  | 2013-04-19 | 2013-04-18 | PERMITTED |  | 2012-10-31 |  | 2012-10-31 | 1 |  | 2012-10-31 |  |  | 2010-10-29 | 2010-04-06 | 2 |  | 2010-10-29 | 2012-11-01 | [5 empty] | 2013-03-19 | 2013-03-19 | 2013-04-30 | 2013-05-03 | 2013-04-12 | 2013-05-15 | 2013-05-15 | 2013-04-22 | 2013-05-01 | [6 empty] | 2013-05-15 | 2013-05-24 | 2013-05-15 | 2013-06-22 | 2013-05-28 | 2013-09-20 | 2013-10-10 | 17/2/13 - Lease terms agreed. Permission to start build but not to go live until lease and licence is complete. 18/03/13 - Pre-start meeting completed, and works now underway. Additional 4-50 cable required - Jackie to order / sort with Abdul | VNZ | 2013-05-15 | [6 empty] | 2013-04-23 | 2013-04-23 | 2013-05-24 | 2013-05-15 |  |  | TIER_1_INFILL | 2012-12-10 | 2012-11-01 | BUILD | 2013-04-19 | FALSE |  | 2667524 | 6482126 | Hobson Street entry or Federal Street entry |  |  | CELLSITE | [15 empty] | 2013-05-17 | 2013-05-16 | 2010-03-23
0 | AKL | 332 | AKL-007-163 | Kingsland Shops | AKL-007-163-C | Kingsland Shops | Auckland City | 3 | TIER_1_INFILL | ACTIVE | BO | Ab6 | NOPOLE | grey | INLINE | COSITE |  |  | 1 | -36.8726 | 174.744 | [6 empty] | FALSE | FALSE |  |  | FALSE |  |  | 2011-03-25 |  | 2011-03-25 |  | 2010-08-24 | 3 | 2010-08-26 | 2011-03-10 | 2010-08-27 | 2010-08-27 | 2010-08-27 | 2010-08-28 |  | 2010-09-06 | 2010-09-22 | DISCRETIONARY_FULL | 2010-09-03 | 2011-04-27 | 2010-10-13 | 2011-05-13 | 3 | 2011-05-24 | 2011-05-13 |  |  |  | 2011-06-16 | 1 |  |  | 2011-06-16 | 2011-07-04 |  |  |  |  | 2011-06-22 | 2011-06-22 | 2011-07-08 | 2011-07-20 | 2011-07-14 | 2011-07-21 | 2011-07-27 | [8 empty] | 2011-07-31 | 2011-08-01 | 2011-08-16 | 2011-08-01 | 2011-08-24 | 2011-11-01 | 2011-11-24 | split site.Cabinets on 478 New North Road in the shed. Antenna on 476 New North Road roof top. Access via 478 New North Road. Cabinet lease with landlord (Revised rental) Antenna lease with Landlord soliciters - minor changes to be forwarded in writing 26.08. 28.08 Both leases signed by Landlords. Bevan to submit RMA. 20/09/2010 Leases executed by 2degrees. 22/09 Both leases - all site aqu complete 08/10 RMA approved - site hardmatched. Tier 1 infill so - Vendor to do CD's and build 14.03.2011 WO2 withdrawn - Added capacity cabinets and antenna change required. NOTE- Swap out BBU 3806 for new 3900 on 17/10/2012. |  | 2011-07-21 | 2011-06-08 | 2011-06-08 | 2011-06-13 | 2011-06-13 | 2011-08-01 | 2011-07-04 | 2011-07-15 | 2011-07-22 | [8 empty] | 2011-07-08 | FALSE |  | 2665869 | 6479542 | 476 - 478 New North Road Kingsland |  | s127 application for amended sector 2 antenna & additional cabinet - 13/05/2011 | CELLSITE |  |  | 2014-06-16 | [12 empty] | 2011-08-01 | 2011-08-03
0 | AKL | 333 | AKL-007-164 | Victoria Park Tunnel | AKL-007-164-A | Victoria Park Tunnel Repeater | Auckland City | 3 | TIER_6 | ACTIVE | BO | X | NOPOLE |  | INLINE | COSITE |  |  |  | -36.8496 | 174.7529 | [6 empty] | FALSE | FALSE |  |  | FALSE |  | 2011-07-11 | 2011-07-11 |  |  |  | 2011-08-19 | 1 |  | 2011-08-19 | 2011-09-30 |  | 2011-09-30 | 2012-11-06 |  | 2011-10-17 | 2012-11-06 |  | 2011-09-12 |  | 2011-10-31 | [7 empty] | 2011-08-19 | 1 |  |  | 2011-08-19 | [22 empty] | 2011-11-07 |  |  |  |  | This is a Macro Repeater site, utilising special repeater kit. Leaky feeder through tunnel, with panels at entry &exit. Expected to open Mid-2011. JV with VF and TNZ. 22/06 JC to discuss with Telecom the requirements from our side. Most likely go with cabinets outside to combiner in Telecom shelter and feeders to antenna and ends of tunnel. | [19 empty] | FALSE |  | 2666716 | 6482079 | SH1 Victoria Park Tunnel Auckland CBD Auckland |  |  | REPEATER
0 | AKL | 334 | AKL-007-165 | Waterview Tunnel | AKL-007-165-A | Waterview Tunnel | Auckland City | 3 | TIER_6 | ACTIVE | BO | X | NOPOLE |  |  | COSITE | [11 empty] | FALSE | FALSE |  |  | FALSE | [60 empty] | Kick off meeting BR & JB 22/4. BR TO ATTEND SECOND MEETING 29/10/2010 | [17 empty] | HARDMATCH |  | FALSE |  |  |  | SH16-20 WVT AKL |  |  | CELLSITE | WIPACTIVE
0 | AKL | 335 | AKL-007-166 | Khyber Pass 3G Inbuilding | AKL-007-166-A | 131 Khyber Pass Rd Inbuilding | Auckland City |  | TIER_6 | ACTIVE | IB | X | RT |  |  | STANDALONE |  |  | 1 | -36.865 | 174.765 | [17 empty] | 2010-10-07 | 1 |  | 2010-10-07 | [18 empty] | 2010-10-14 | 1 | 1 |  | 2010-10-14 | [22 empty] | 2010-05-21 | [26 empty] | 2667763 | 6480343 | 131 Khyber Pass Rd Grafton Auckland 1023 |  |  | CELLSITE
0 | AKL | 336 | AKL-007-167 | 126 Khyber Pass MW Link |  |  | Auckland City |  | TIER_6
0 | AKL | 337 | AKL-007-168 | City Rd MW Link |  |  | Auckland City |  | TIER_6
0 | AKL | 338 | AKL-007-169 | Upper Queen St MW Link |  |  | Auckland City |  | TIER_6
0 | AKL | 339 | AKL-007-170 | Britomart Train Station | AKL-007-170-B | Britomart - permanent | Auckland City | 2 | TIER_1_INFILL | ACTIVE | IB | B | BO |  | INLINE | COSITE |  |  |  | -36.844 | 174.7675 |  | 2010-03-08 |  |  |  |  | TRUE | TRUE |  |  | TRUE |  | 2011-04-08 | 2011-04-08 |  | 2011-04-08 | 2011-05-31 | 2011-05-27 | 1 | 2011-06-03 | 2011-05-27 | 2013-01-25 |  | 2013-01-25 | 2013-04-17 |  | 2013-01-25 |  | PERMITTED |  | 2012-04-04 | 2012-03-01 | 2012-05-04 | 1 |  | 2012-05-04 |  | 2011-11-04 | [12 empty] | 2011-12-27 |  | 2012-01-13 | 2012-01-13 |  | 2012-01-20 |  | 2012-02-10 | [7 empty] | 2012-04-19 | 2012-04-12 |  | 2012-05-04 |  | 2012-05-25 | 28/04/11 - Design will now feed upper antenna off main RRU by 4-50 cable 16/06/11 - New Form agreement required and currently under legal reviews etc 14/07/11 - Lease with Transport - still caught up in Britomart domain 1/9/11 - Lease with Paul K 22/09/11 - ACC happy to proceed with lease (with condition tunnel antenna to be sorted later). They are obtaining valuation for rent 29/09/11 - Lease with 2 Degrees legal for review and comment 6/10/11 - RF may want to change design and overall configuration. Verapol to call meeting next week 27/10/11 - Lease still with 2D for review. Rf plan is now agreed and in place 03/11/11 - Brad to help arrange Contractor pre-build access and induction for end Nov/Early Dec so build can occur in Britomart shutdown period 24/11/11 - Draft lease (with significant changes) done. Brad to hand deliver. Will require significant period to conclude, so Brad is trying to extend temp agreement to allow access and build in December. 15/12/11 - Trying for access to build over New Year. AK Transport rejected latest lease changes 16/02/12 - ATC approved turning on site while lease concluded over next 3 months. Planned integration 19 April 19/04/12 - site is now live. Walk test OK. Still to do tunnel antenna when area available |  | 2011-01-28 | [9 empty] | 2012-04-05 |  |  |  |  | 2012-02-10 |  |  | FALSE |  | 2668028 | 6482668 | Britomart Train Station Auckland |  | No RMA was assessed as being required - 04/05/2012 | CELLSITE | [8 empty] | 2011-11-04 | [8 empty] | 2011-04-08
0 | AKL | 340 | AKL-007-175 | Penrose East | AKL-007-175-F | Stockman Civils | Auckland City | 3 | TIER_1_INFILL | ACTIVE | GF | Ab6 | P3 |  | INLINE | STANDALONE |  | 26 |  | -36.9051 | 174.8248 | [6 empty] | FALSE | FALSE |  |  | FALSE |  | 2011-09-28 | 2011-09-28 | 2011-10-10 | 2011-10-07 | 2011-11-04 | 2011-11-03 | 1 | 2011-11-04 | 2011-11-03 | 2011-11-09 | 2011-11-02 | 2011-12-08 | 2011-12-13 | 1 | 2011-12-08 | 2011-12-13 | DISCRETIONARY_FULL | 2011-11-10 | 2011-11-10 | 2012-02-06 | 2011-12-08 | 1 | 2012-02-13 | 2011-12-08 |  |  | 2012-03-09 | 2012-03-09 | 2 |  |  | 2012-04-03 | 2012-04-18 |  |  |  |  | 2012-04-16 | 2012-04-10 | 2012-04-30 | 2012-04-30 | 2012-05-07 | 2012-05-15 | 2012-05-21 | [8 empty] | 2012-05-16 | 2012-05-28 | 2012-05-16 | 2012-06-06 | 2012-05-31 | 2012-08-29 | 2012-09-26 | Landlord willing. Met us on site. Wants to be able to fly company flag from pole - will have to make this possible. Also needs to be fenced. Situated in civil contracting storage yard. Big trucks and Forklifts. |  | 2012-05-16 | 2012-04-02 | 2012-04-02 | 2012-04-02 | 2012-04-18 | 2012-04-17 | 2012-04-18 | 2012-05-14 | 2012-05-11 | [8 empty] | 2012-05-07 | FALSE |  | 2672995 | 6475782 | 38 Leonard Road Mt Wellington |  | Lodged with council on the 10.11.11 with Aimee Buckingham at AC - 11/11/2011 | CELLSITE |  |  | 2014-08-12 | [12 empty] | 2012-05-22 | 2012-05-22
0 | AKL | 341 | AKL-007-176 | Test_nomimal_01 |  |  | Auckland City |  | TIER_9
0 | AKL | 342 | AKL-007-177 | Ellerslie Central | AKL-007-177-E | Ellerslie Central | Auckland City | 3 | TIER_1_INFILL | ACTIVE | RSR | DU5 | P4J | Grey | INLINE |  | 9.9 | 12 |  | -36.8925 | 174.8283 |  |  |  |  | Microwave | AKL-007-114-D | FALSE | FALSE |  |  | FALSE |  | 2011-09-08 | 2011-09-06 | 2011-10-25 | 2011-10-19 | 2011-11-09 | 2011-11-16 | 2 | 2011-11-09 | 2011-12-15 | 2012-02-15 | 2012-02-09 | 2012-02-17 | 2012-03-01 |  | 2012-02-29 | 2012-03-01 | DISCRETIONARY_FULL | 2011-12-12 | 2011-12-13 | 2012-02-22 | 2012-02-17 | 1 | 2012-02-29 | 2012-02-17 |  |  | 2012-06-11 | 2012-05-30 | 1 |  | 2012-06-11 | 2012-05-30 | 2012-07-03 |  |  |  |  | 2012-07-10 | 2012-07-10 | 2012-07-16 | 2012-07-20 | 2012-07-18 | 2012-07-24 | 2012-07-24 | [8 empty] | 2012-07-26 | 2012-08-14 | 2012-08-14 | 2012-08-28 | 2012-08-15 | 2013-04-12 | 2013-04-09 |  |  | 2012-07-27 | 2012-07-03 | 2012-07-03 | 2012-07-03 | 2012-07-03 | 2012-07-03 | 2012-07-03 | 2012-07-19 | 2012-07-19 |  | 2012-08-06 | [5 empty] | BUILD | 2012-07-18 | FALSE |  | 2673337 | 6477175 | 150 Mauru Road |  | Lodged on the 13.12.2011 with Mark Ross of Auckland Council processing planner. Lodged with rev 1 plans. - 14/12/2011. Rev 1 plans swapped out for rev 2 plans. Approved on the 17.2.2012, council reference: R/LUC/2011/4574 with rev 2 plans. - 20/02/2012 | CELLSITE |  |  | 2014-08-12 | [12 empty] | 2012-08-03 | 2012-08-01
0 | AKL | 343 | AKL-007-178 | Queens Wharf | AKL-007-178-A | Queens Wharf | Auckland City | 3 | TIER_1_INFILL | ACTIVE | RT | DU5 | NOPOLE |  | INLINE |  |  |  |  | -36.8415 | 174.7681 | [6 empty] | FALSE | FALSE |  |  | FALSE |  |  | 2012-04-12 |  | 2012-04-12 |  | 2011-06-27 | 5 |  | 2015-08-04 |  | 2011-08-10 |  | 2011-08-18 |  |  | 2011-08-18 | DISCRETIONARY_FULL |  | 2011-08-11 |  | 2011-09-01 | 3 | [5 empty] | 2015-09-14 | 3 |  |  | 2015-11-11 | [6 empty] | 2012-03-15 |  | 2012-03-30 | 2012-03-30 |  | 2012-03-30 | [10 empty] | 2012-04-09 |  | 2012-04-09 |  | 2012-07-09 | [12 empty] | 2012-03-30 | [5 empty] | BUILD |  | FALSE |  | 2668093 | 6482946 | 99 Quay Street Auckland CBD |  | Lodged on the 11.8.2011, processing with Mark Ross of Auckland Council. The site is located within the CMA and is zoned Port Management Area 1C. Therefore a coastal permit has been applied for. - 12/08/2011 | CELLSITE |  |  | 2014-06-16
0 | AKL | 344 | AKL-007-179 | RBI - Claris Great Barrier |  |  | Auckland City |  | RBI | [22 empty] | FALSE
0 | AKL | 345 | AKL-007-180 | Marua Rd Mini-Repeater | AKL-007-180-A | Turf Tech Mini | Auckland City |  | TIER_6 | ACTIVE | IB | 900_MINI_RPTR | NOPOLE | [6 empty] | -36.8944 | 174.8382 | [13 empty] | 2012-02-17 | [35 empty] | 2012-02-22 |  | 2012-02-22 |  |  | 2012-02-24 | [10 empty] | 2012-02-24 | 2012-02-17 | [23 empty] | 2012-02-22 | FALSE |  | 2674213 | 6476949 | Turf Tech Unit 6 248 Marua Road , Mt Wellington |  |  | REPEATER
0 | AKL | 346 | AKL-007-181 | 65 Upper Queen Street |  |  | Auckland City | 9 | TIER_6 | [22 empty] | FALSE
0 | AKL | 347 | AKL-007-182 | 65 Upper Queen Street Repeater | AKL-007-182-A | RUQS | Auckland City |  | TIER_6 | ACTIVE | RT | 900_2100_MINI_RPTR | RT | [6 empty] | -36.8623 | 174.7588 | [71 empty] | Installed 2012-07-06, decomissioned 10/12/13 when corporate office relocated | [19 empty] | FALSE |  | 2667212 | 6480654
0 | AKL | 348 | AKL-007-183 | 42 Upper Queens St Repeater |  |  | Auckland City |  | TIER_6 | [83 empty] | Repeater required for in-building coverage in 42 Upper Queens St office
0 | AKL | 349 | AKL-007-184 | NZVIF Repeater (AOG) | AKL-007-184-A | AOG | Auckland City |  | TIER_6 | ACTIVE
0 | AKL | 350 | AKL-007-185 | Mayoral Drive MDR | AKL-007-185-A | Chorus colocation MDR | Auckland City |  | TIER_6 | ACTIVE | COLO | TX |  |  |  | COLO | [71 empty] | 2012-03-01 |  | 2012-03-01 |  |  | SOA and PAC dates entered to reflect status | [19 empty] | FALSE |  |  |  | 31 Airedale Street, Auckland |  |  | TXSITE
0 | AKL | 351 | AKL-007-186 | Greenlane Interchange | AKL-007-186-B | Kiwirail GF | Auckland City | 12 | 2014 | ACTIVE | GF | DU5 | P1 | grey | STACK_A | STANDALONE |  | 15 |  | -36.8892 | 174.7968 |  |  |  |  | Fibre Optic | AKL-007-192-A | FALSE | FALSE |  |  | FALSE |  | 2013-08-13 | 2013-08-13 | 2013-08-14 | 2013-08-14 | 2013-08-29 | 2013-09-13 | 3 | 2013-09-06 | 2014-01-15 | 2013-10-31 | 2013-12-18 | 2014-01-24 | 2014-01-29 |  | 2014-01-31 | 2014-01-29 | CONTROLLED | 2013-10-15 | 2013-10-14 | 2013-11-19 | 2013-10-25 | 2 | 2013-11-26 | 2013-10-25 | 2013-11-04 | 2013-11-06 | 2013-11-28 | 2013-12-17 | 2 |  | 2014-01-17 | 2014-01-15 |  | 2014-01-17 | 2014-01-16 | 2014-01-17 |  | 2014-02-17 | 2014-02-18 | 2014-04-02 | 2014-04-02 | 2014-03-25 | 2014-04-14 | 2014-04-17 | 2014-04-14 | 2014-04-17 | [7 empty] | 2014-04-30 | 2014-04-30 |  |  |  |  | 15/8 - Caravan done, PDI given, Ritchie getting quotes for heights survey, topo survey, boundary survey & desktop geotech. PD rev 1 issued 13 Sept 2013. Ben lodging RMA with rev 2 showing future cabs 15/10/13 - design accepted by kiwirail, commercials/lease agreements underway with Brad. | [10 empty] | 2014-04-17 | 2014-04-17 | 2013-10-14 | MEDIUM | AUCKLAND | 2014-04-02 | 2014-04-01 | BUILD | 2014-03-24 | TRUE | 2014-01-17 | 2670539 | 6477607 | 114-118 Greenlane Rd, Kiwirail yard Greenlane, Auckland |  |  | CELLSITE |  |  | 2014-06-16 |  |  |  |  | 2014-01-24 | 2014-01-24 | [8 empty] | 2013-08-14
0 | AKL | 352 | AKL-007-187 | Onehunga Central | AKL-007-187-A | Shopping Mall Car Park 1 | Auckland City | 3 | 2014 | ACTIVE | RT | DU5 | RT | Grey | STACK_A | COSITE |  |  |  | -36.9215 | 174.786 |  |  |  |  | Microwave | AKL-007-114-D | FALSE | FALSE |  |  | FALSE |  | 2014-01-30 | 2014-01-30 | 2014-02-24 | 2014-02-20 | 2014-04-16 | 2014-04-17 | 1 | 2014-04-16 | 2014-04-17 | 2014-07-11 | 2014-07-09 | 2014-07-15 | 2014-07-11 |  | 2014-07-31 | 2014-07-23 | DISCRETIONARY_FULL | 2014-05-27 | 2014-05-30 | 2014-06-26 | 2014-06-20 | 1 | 2014-07-03 | 2014-06-20 | 2014-05-27 |  | 2014-06-23 | 2014-06-30 | 1 |  | 2014-06-30 | 2014-06-30 | [5 empty] | 2014-09-09 | 2014-09-11 | 2014-09-19 | 2014-09-19 | 2014-09-19 | 2014-10-01 | 2014-10-01 |  | 2014-10-01 | [7 empty] | 2014-10-09 | 2014-10-10 |  |  |  |  | 29.01.14 Leasing Manager happy to see us. Caravan arranged with him on 30.01.14 31.01.14 Leasing Manager would like a proposal first - Mock upped photos. We did measure up. 12.01.14 Proposal sent to Building manager (by Liz) 24.02.14 PDI Issued. Await plans. 24.03 Revisit site with Alex J to clarify power and earthing today. 24.03.14 Revist - Building manager wants single pole solution. Drawings to change. 01.04.14 Design resourse down to Reuben and GHD in WLG 16.04.14 RF changed design made 2m higher. Long discussion. Makes bracing extensive, may require Build C. Ugly. BR spk to Parviz and Tim L. Back to 5m pole, plans to be finalised today. 06.05.14 Plans with Landlord for a while now. Await terms agreed. Then will issue CDI & Apply for RMA 07.05.14 Liz handed over to John Watson 23.05.14 Still await Lease terms agreed. Rob to submit RMA (SUBMITTED) 04.06.14 John battling to get response from Centres legal. Still await Lease terms agreed. 13.06.14 Received legal response. Pages and pages of Special cond. Reviewed - made changes - returned. 01.07.14 Generator plug to be installed within cabinets. Site on air date changed to Nov as the MW are only available then 9/10/14 - Site on air 2G and 3G. 4G still to be tested | [10 empty] | 2014-10-02 | 2014-10-06 | 2014-05-30 | LOW | AUCKLAND |  |  | BUILD | 2014-09-17 | FALSE |  | 2669497 | 6474044 | Onhunga Mall Roof Top Car Park Top Left Corner | 30 April - General lease terms are with LO lawyers they are drafting special conditons which we will need to review when they come back. 11April - Vaughan has advised that he will be on leave until after 22/4. The general lease cond. are still with their lawyers. We can contact Rachel (lease admin)Rachel.Jackson@Oystergroup.co.nz if we need an update. In Negotiations. Have spoken with Lease manager regarding acces. After hours access we will be charged as security firm will have to allow us onto site. General lease conditions have been sent to the LO for review. Will await issue of the PD's - 19/03/2014 - 20/03/2014 - 14/04/2014 - 30/04/2014 |  | CELLSITE |  |  | 2014-10-10 | [14 empty] | 2014-02-20
0 | AKL | 353 | AKL-007-188 | Albert St | AKL-007-188-A | Crown Plaza | Auckland City | 3 | 2014 | ACTIVE | RT | DF5 | RT | Grey | STACK_A | COSITE |  |  |  | -36.8498 | 174.7631 |  |  |  |  | Fibre Optic | AKL-007-185-A | FALSE | FALSE |  |  | FALSE |  | 2014-02-25 | 2014-02-25 | 2014-03-04 | 2014-02-26 | 2014-04-10 | 2014-04-11 | 3 | 2014-04-17 | 2015-05-20 | 2014-05-15 | 2014-05-12 | 2014-05-26 | 2014-05-23 | 2 | 2014-06-06 | 2014-06-06 | PERMITTED | 2014-05-16 | 2014-05-16 | 2014-06-16 | 2014-06-05 | 2 | 2014-06-20 | 2014-06-05 | 2014-05-30 | 2014-05-08 | 2014-06-20 | 2014-06-24 | 4 |  | 2014-06-27 | 2015-11-11 | [5 empty] | 2014-08-18 | 2014-08-15 | 2014-09-05 | 2014-09-12 | 2014-08-18 | 2014-09-16 | 2014-09-18 | 2014-09-15 | 2014-09-15 | [7 empty] | 2014-09-25 | 2014-09-29 |  |  |  |  | 29.01.14 : Ben has made contact. To meet with building manager to finalise position of cabinets. 10.02.14 Ben busy discussing commerials withBuilding manager. To caravan ASAP. Have asked Liz to get cosite docs from VNZ & TNZ 12.02.14 Rec VNZ cosite details. Have circulated. Caravan date scheduled 19.02.14 25.02.14 Caravaned. PDI to be issued 26.02.14 PDI Issied. Await plans 01.04.14 Plans under circulation, feeder runs long. Making sure all good 22.05.14 Landlord away until 02.06. Cant get fibre run approved until then. 22.05.14 Signed lease received today. 05.06.14 Executed by 2d but still waiting on legal review 17.06.14 Legal review still not done. Discussed with legal. They are happy with teh risk. Visiting site toady at 1.30 with Alex J Re Lightning protection. and Rob the Fibre guy. fIBRE INSTALLED. RF panels have a delay. Will place a load on them and integrate anyway | [10 empty] | 2014-09-17 | 2014-09-22 | 2014-05-16 | LOW | AUCKLAND | 2014-08-06 | 2014-06-19 | BUILD | 2014-08-18 | FALSE |  | 2667623 | 6482040 | Crown Plaza Cabinets on Level 13 or 14 Antenna on Level 11 | Basic lease terms are agreed upon (rent, term) Lease documents with LO for more detailed review. Understand this review is complete but awaiting Director sign off before documents are returned for us. Will then draft up special conditions and send for signing. - 10/04/2014 |  | CELLSITE |  |  | 2014-09-29 | [14 empty] | 2014-02-26
0 | AKL | 354 | AKL-007-189 | Aotea Square | AKL-007-189-I | Export Building | Auckland City | 3 | 2014 | ACTIVE | RT | DU5 | RT | Grey | STACK_A |  |  |  |  | -36.854 | 174.7602 |  |  |  |  | Fibre Optic | AKL-007-185-A | FALSE | FALSE |  |  | FALSE |  | 2014-06-30 | 2014-06-20 |  | 2014-06-23 | 2014-07-25 | 2014-07-31 | 4 | 2014-07-31 | 2015-12-17 | 2014-08-15 | 2014-08-01 | 2014-10-03 | 2014-10-23 |  | 2014-10-08 | 2014-10-23 | PERMITTED | 2014-08-06 | 2014-08-07 | 2014-09-17 | 2014-09-01 | 1 | 2014-09-01 | 2014-09-01 | 2016-01-29 | 2014-08-01 | 2014-08-22 | 2014-09-01 | 2 |  | 2014-08-29 | 2014-11-07 | [5 empty] | 2014-11-17 | 2014-11-17 | 2014-12-08 | 2014-11-28 | 2014-11-24 | 2014-12-10 | 2014-12-10 | 2014-12-08 | 2014-12-08 | [7 empty] | 2014-12-19 | 2014-12-18 | [15 empty] | 2014-12-10 | 2014-12-12 | 2014-08-07 | LOW | AUCKLAND | 2014-12-01 | 2014-12-01 | BUILD | 2014-12-04 | FALSE |  | 2667355 | 6481581 | 126 Vincent St |  |  | CELLSITE |  |  | 2014-12-18 | [14 empty] | 2014-06-23
0 | AKL | 355 | AKL-007-190 | Sky City Macro | AKL-007-190-A | Sky City | Auckland City | 12 | 2014 | ACTIVE | RT | DF5 | RT | Grey | INLINE | STANDALONE |  |  |  | -36.8494 | 174.7613 |  |  |  |  | Fibre Optic | AKL-007-112-A | FALSE | FALSE |  |  | FALSE |  | 2013-08-02 | 2013-08-13 | 2013-08-09 | 2013-08-15 | 2013-08-30 | 2013-09-13 | 6 | 2014-02-04 | 2015-08-24 | 2013-10-31 | 2014-01-10 | 2014-03-28 | 2014-03-31 |  | 2014-03-28 | 2014-03-31 | PERMITTED | 2013-10-15 | 2013-10-14 | 2013-11-22 | 2013-11-05 | 1 | 2013-11-29 | 2013-11-05 | 2013-11-04 | 2013-11-06 | 2014-01-31 | 2014-02-03 | 6 |  | 2014-02-14 | 2015-11-11 | [5 empty] | 2014-04-14 | 2014-04-14 | 2014-06-06 | 2014-06-09 | 2014-06-03 | 2014-06-16 | 2014-06-17 | 2014-06-04 | 2014-06-03 | [7 empty] | 2014-07-03 | 2014-07-02 |  |  |  |  | sky city have accepted the plans, commercials are underway with Brad. Ben lodging RMA 15/10/13. sky city have put the cabinet lift on hold until they get an independant review of the design of 13/5/14, all go date tbc. | [10 empty] | 2014-06-30 | 2014-07-04 | 2013-10-14 | LOW | AUCKLAND | 2014-06-02 | 2014-06-03 | BUILD | 2014-06-02 | FALSE |  | 2667468 | 6482079 | Cnr Federal & Victoria Streets, Auckland 1010 |  |  | CELLSITE |  |  | 2014-07-07 |  |  |  |  | 2014-03-28 | 2014-03-28 | [8 empty] | 2013-08-15
0 | AKL | 356 | AKL-007-191 | Mt Albert Chorus Exchange | AKL-007-191-A | Mt Albert Chorus Exchange | Auckland City |  | TIER_6 | ACTIVE | COLO | TX | COLO |  |  | COLO | [71 empty] | 2013-11-29 | [28 empty] | Mt Albert |  |  | TXSITE
0 | AKL | 357 | AKL-007-192 | Remuera Chorus Exchange | AKL-007-192-A | Remuera Chorus Exchange | Auckland City |  | TIER_6 | ACTIVE | COLO | TX | COLO |  |  | COLO | [71 empty] | 2013-11-29 | [5 empty] | TNZ | [22 empty] | Remuera |  |  | TXSITE
0 | AKL | 358 | AKL-007-193 | Sylvia Park Shopping Centre | AKL-007-193-A | Sylvia Park COLO | Auckland City | 3 | 2014 | ACTIVE | COLO | DU5 | COLO | Grey | STACK_A | COLO |  |  |  | -36.9196 | 174.843 |  |  |  |  | Fibre Optic | AKL-008-091-A | FALSE | FALSE |  |  | FALSE |  | 2014-02-10 | 2014-02-10 | 2014-02-11 | 2014-02-11 | 2014-02-21 | 2014-02-26 | 3 | 2014-02-26 | 2014-05-08 | 2014-03-28 | 2014-03-28 | 2014-07-18 | 2014-06-06 | 3 | 2014-07-25 | 2014-07-01 | DISCRETIONARY_RESTRICT | 2014-04-07 | 2014-04-08 | 2014-05-19 | 2014-05-15 | 3 | 2014-05-26 | 2014-05-15 | 2014-04-16 |  | 2014-05-07 | 2014-05-07 | 4 |  | 2014-05-14 | 2014-07-07 | [5 empty] | 2014-06-10 | 2014-06-10 | 2014-08-11 | 2014-08-17 | 2014-07-31 | 2014-08-22 | 2014-09-01 | 2014-08-22 | 2014-08-22 | [7 empty] | 2014-10-31 | 2014-10-24 |  |  |  |  | 29.01.14 We have received the Data Pack. BR has forwarded to Design for a structural analysis. BR to follow up with Tim B 31.01.14 Structural passes. Colo application to be done. 10.02 Caravan done. PDI issued. Await PD's 13.02.14 Await PD's 27.02.2014 VNZ Colocation application made 21.03.14 VNZ want cabs moved and cable tray = trip hazard. Looking into solutions. 06.05.14 Sub lease received and sent to Kiwi rail. RMA Approval due 19.05.14. Construction dwngs to be updated with new cab position and details re head frame flange after riggers climb mast. 120 WORKING DAY EXPIRE : 18 September 2014 06.05.14 Kiwi rail very pedantic about new electrificaton of rail. Not allowed within 4m. We will most likely have to do the rigging work on a Sunday night after 10pm - For build 07.05.14 Ryan C says we can remove MW from application. VNZ Charge us for it even the bracket. We can and will apply for it when we need it. 07.05.14 Liz handed over to Rob M 20.05.14 Kiwi rail held onto lease for ages, when opened realised we had not signed. They insist VNZ + 2d sign first. Plans changed with extra cabs. VNZ to review and approve. Tender Pricing due in today. Tender awarded to Transfield. 22.05 We have received the amended sub lease. We will sign, then give back to VNZ to sign, then get Kiwi rail to sign. 05.06.014 Still waiting on VNZ to sign sub lease. Rob M is chasing up. Johan and I have commenced with the Project plan and the H&S docs have been received. 12.06.14 VNZ still have not signed the sub lease. 17.06.14 VNZ Still have not signed the sub lease. BR to escalate today. | VNZ | [9 empty] | 2014-09-22 | 2014-09-25 | 2014-05-16 | LOW | AUCKLAND | 2014-08-15 | 2014-08-18 | BUILD | 2014-08-04 | FALSE |  | 2674579 | 6474141 | Clemow Dr Mt Wellington | 30/4 Sublease had incorrect rent. Vodafone re-drafting. BUT have recevied approval from Kiwirail for the co-locaiton. 11/4 Waiting for renewal and rent to be finalised before Kiwirail can provide thoughts on Co-location. VDFN and Kiwiwrail have been advised. Expiry of Vodaofne lease is 30 June 2020. have discussed with PM and Jason Britten and it has been ok'd as Head lease held by ontrack/kiwirail. - 19/03/2014 - 14/04/2014 - 30/04/2014 |  | CELLSITE |  |  | 2014-10-28 | [14 empty] | 2014-02-11
0 | AKL | 359 | AKL-007-194 | Quay Street | AKL-007-194-G | Own Pole | Auckland City | 3 | 2014 | ACTIVE | RSR | DU5 | P4F | Grey | INLINE | STANDALONE |  |  |  | -36.845 | 174.7741 |  |  |  |  | Fibre Optic | AKL-007-185-A | FALSE | FALSE |  |  | FALSE |  | 2014-02-03 | 2014-02-03 | 2014-02-04 | 2014-02-04 | 2014-03-10 | 2014-03-24 | 6 | 2014-03-14 | 2015-05-29 | 2014-04-22 | 2014-05-14 | 2014-06-13 | 2014-06-11 |  | 2014-07-04 | 2014-07-01 | DISCRETIONARY_FULL | 2014-04-02 | 2014-04-02 | 2014-05-07 | 2014-05-05 | 1 |  | 2014-05-05 | 2016-01-29 |  | 2014-06-30 | 2014-06-23 | 1 |  | 2014-06-30 | 2014-06-23 | [5 empty] | 2014-08-04 | 2014-08-04 | 2014-08-14 | 2014-08-15 | 2014-08-15 | 2014-09-10 | 2014-09-18 | 2014-08-21 | 2014-08-21 | [7 empty] | 2014-09-30 | 2014-10-07 |  |  |  |  | 29.01.14 : We need to Caravan a position for an alternative to the LPR ASAP. 11.02.14 PDI issued - await Rev 0 12.02.14 Company decided to only submit LPR Telco Notice. Plans to continue but not a priority. 18.02 Council advised this is not a preferred option. John W advised design not to prioritze dwngs 26.02.14 BR instructed Tim B in design to finish drawings as they may be required. (Elliot St T.Notice requires a paymnt - Quay St TN may too) 10.03.14 Await PD's 21.03.14 LPR Going ahead. 22.03.14 BR instructed Design to complete the PD's and issue. 27.03.14. LPR not going ahead. Telco Notice submitted on this one. 07.05.14 This site is within the LTE zone. It must be LTE, Plans to be amended and S127 submitted. 20.05.14 Rob Busy with S127 22.05.14 Council advise S127 not required. Just need to update plans. Rob picked up squ m on plans incorrect, have now been amended. 01.09.14 All tests on feeder fail. Have to remove all feeder and replace then integrate | [10 empty] | 2014-09-18 | 2014-09-18 | 2014-05-06 | LOW | AUCKLAND | 2014-08-04 | 2014-07-22 | BUILD | 2014-08-14 | FALSE |  | 2668613 | 6482545 | 23 Quay St |  |  | CELLSITE |  |  | 2014-10-07 | [14 empty] | 2014-02-04
0 | AKL | 360 | AKL-007-195 | Oranga | AKL-007-195-A | Customer Experience | Auckland City |  | TIER_6 | ACTIVE | [100 empty] | HARDMATCH
0 | AKL | 361 | AKL-007-196 | Eden Park Stadium |  |  | Auckland City |  | TIER_9
0 | AKL | 362 | AKL-007-197 | Halsey Street | AKL-007-197-F | Sanford Ltd | Auckland City | 3 | 2014 | ACTIVE | RT | DU5 | RT | Grey | STACK_A |  |  |  |  | -36.8409 | 174.7562 |  |  |  |  | Fibre Optic | AKL-007-185-A | FALSE | FALSE |  |  | FALSE |  | 2014-02-26 | 2014-02-19 | 2014-03-19 | 2014-03-11 | 2014-04-11 | 2014-04-11 | 3 | 2014-04-18 | 2015-08-13 | 2014-05-27 | 2014-05-26 | 2014-05-27 | 2014-05-27 | 1 | 2014-06-13 | 2014-06-20 | DISCRETIONARY_FULL | 2014-05-27 | 2014-05-20 | 2014-06-30 | 2014-06-17 | 1 | 2014-07-04 | 2014-06-17 | 2014-05-20 | 2014-05-08 | 2014-06-30 | 2014-06-26 | 4 |  | 2014-07-11 | 2015-11-11 | [5 empty] | 2014-08-18 | 2014-08-19 | 2014-08-29 | 2014-09-12 | 2014-08-21 | 2014-09-05 | 2014-09-09 | 2014-09-05 | 2014-08-29 | [7 empty] | 2014-09-30 | 2014-09-30 |  |  |  |  | 29.01.14 : Team have surveyed. Tim Lau is happy with new search area. Ben busy negotiating. Once we have some confidence we will Caravan. 12.02.14 Sanford regard split antenna as 2 sites. Rent high. Tim Lau to reconcider 2 sector site only + need to shroud. Tim to advise 20.02.14 Caravaned. Photomontage proposal to go to LL first before PDI 21.02.14 Tim L placed on hold. Reassessing RF plan. 27.02.14 Tim L adviss to go with 2 sector site, taller shroud. Girma happy to move MW out shroud. Ben to ask Landlord. 10.03.14 Landlord happy with proposal. BR to submit PDI asap 24.03 Planning drawings Rev 0 due for circulation today 01.04.14 Looking at chnaging from DF to DU. (Too many RRu's and combiners) 06.05.014 Waterfront have approved. Now with Sanford. | [10 empty] | 2014-09-09 | 2014-09-09 | 2014-05-20 | LOW | AUCKLAND | 2014-07-14 | 2014-07-14 | BUILD | 2014-08-19 | FALSE |  | 2667027 | 6483038 | 22 Jelicoe St Auckland 1010 | Lease terms are broadly agreed. Currently waiting on drawings and license clauses regarding head-lease from Legal before submitting to Head Lessor Auckland Waterfront for their approval. Once AW approval received, full documents will be sent to Sanford for their signing. - 10/04/2014 |  | CELLSITE |  |  | 2014-09-30 |  |  |  |  | 2014-08-04 | [9 empty] | 2014-03-11
0 | AKL | 363 | AKL-007-198 | Herne Bay Relocation | AKL-007-198-A | Herne Bay Relocation | Auckland City | 3 | 2014 | ACTIVE | RT | DU5 | NOPOLE | Grey | INLINE |  | 15 | 10 |  | -36.8451 | 174.7383 |  |  |  |  | Fibre Optic | AKL-005-078-A | TRUE | TRUE |  |  | FALSE |  | 2013-08-01 | 2013-08-01 |  | 2013-08-01 |  | 2013-08-23 | 3 |  | 2013-08-23 |  | 2013-09-15 | 2013-10-15 | 2013-10-15 |  | 2013-10-15 | 2013-10-15 | DISCRETIONARY_FULL |  | 2013-07-15 | 2013-08-14 | 2013-08-21 | 3 |  | 2013-08-21 |  | 2014-07-30 |  | 2014-08-05 | 1 |  |  | 2014-08-05 | [5 empty] | 2014-08-21 | 2014-08-19 |  | 2014-09-04 | 2014-08-19 | 2014-09-04 | 2014-09-02 | 2014-09-04 | 2014-09-04 | [7 empty] | 2014-09-17 | 2014-09-12 |  |  |  |  | 05.02.14 From teh Developer Marcus : We are progressing well, I will ask the site manager roughly when we will be requiring the move to the scaffolding and get back to you. 18.02.14 Developer advised would like antenna moved last week of March / First week of April. BR set up meeting with F/Ops to discuss - 27.02.14 27.02.14 BR spoke to Max M of Transfield. BR and Verapol to finalise a few details for Max, then he will quote. 10.03.04 Rec quote. Raised POR. To do Move order. 24.03 PO Rec for T/Field to do the work. MO done for equipment to T/Field. Antenna Relocation planned for Sat 5 April 2014 | [10 empty] | 2014-09-11 | 2014-09-11 | 2014-02-05 | LOW |  | 2014-08-11 | 2014-08-29 | BUILD | 2014-08-21 | FALSE |  | 2665421 | 6482603 | Jervois Road Herne Bay Auckland |  |  | CELLSITE |  |  | 2014-09-12 | [14 empty] | 2013-08-01
0 | AKL | 364 | AKL-007-199 | Three Kings - Relocation | AKL-007-199-B | Three Kings LPR | Auckland City | 22 | 2015P | ACTIVE | RSR | DU5 | P4F |  | STACK_A |  |  |  |  | -36.9095 | 174.7544 |  |  |  |  | Fibre Optic | AKL-007-191-A | FALSE | FALSE |  |  | FALSE |  | 2015-04-01 | 2015-04-01 | 2015-04-07 | 2015-04-02 | 2015-05-05 | 2015-04-28 | 2 | 2015-05-12 | 2015-08-25 | 2015-06-03 | 2015-05-12 | 2015-06-17 | 2015-05-18 |  | 2015-06-24 | 2015-06-09 | DISCRETIONARY_FULL | 2015-06-02 | 2015-06-02 | 2015-07-17 | 2015-07-03 | 1 | 2015-07-17 | 2015-07-03 | 2015-06-09 | 2015-06-09 | 2015-06-23 | 2015-06-11 | 1 |  | 2015-06-30 | 2015-06-11 |  |  |  | 2015-07-20 |  | 2015-11-09 | 2015-11-09 | 2015-12-02 | 2015-12-01 |  | 2015-12-03 | 2015-12-07 | 2015-12-02 | [8 empty] | 2015-12-17 | 2015-12-16 | 2015-12-22 | 2015-12-22 |  |  | 18.2.15 - site search brief to be issued by Trevor Possible LPR down by countdown area - site search to be scheduled 7/10/15 - northpower can only schedule power to site on 20th Nov! | [10 empty] | 2015-12-10 | 2015-12-10 |  |  | AUCKLAND | 2015-10-08 | 2015-10-07 | BUILD |  | TRUE | 2015-07-20 | 2666713 | 6475429 | cnr Dornwell Rd & Mt Albert Rd outside 3 Kings Takeaways 501 Mt Albert Rd, Three Kings, Auckland |  |  | CELLSITE |  |  | 2015-12-16 | RELOCATION |  | 2015-06-22 | 2015-07-23 | 2015-07-31 | 2015-07-15 |  | 2015-04-01 |  | 2015-06-10 | 2015-09-11 | 2015-09-15 |  |  | 2015-04-02
0 | AKL | 365 | AKL-007-200 | Eden Park - permanent site | AKL-007-200-A | Eden Park - Stadium North Stand | Auckland City | 12 | 2014 | ACTIVE | RT | DF5 | RT | Grey | INLINE | COSITE |  |  |  | -36.8749 | 174.7446 |  |  |  |  | Fibre Optic | AKL-007-191-A | FALSE | FALSE |  |  | FALSE |  | 2014-03-21 | 2014-03-21 | 2014-03-25 | 2014-03-25 | 2014-04-11 | 2014-05-01 | 3 | 2014-04-21 | 2014-06-18 | 2014-07-18 | 2014-09-18 | 2014-09-26 | 2014-10-13 |  | 2014-10-03 | 2014-10-13 | DISCRETIONARY_FULL | 2014-06-23 | 2014-06-23 | 2014-07-23 | 2014-07-21 | 3 | 2014-07-30 | 2014-07-21 | 2014-06-03 | 2014-06-03 | 2014-07-25 | 2014-07-25 | 2 |  | 2014-07-31 | 2014-09-03 | [5 empty] | 2014-10-10 | 2014-10-08 | 2014-10-31 | 2014-10-30 | 2014-11-11 | 2014-11-28 | 2014-11-24 | 2014-11-28 | 2014-11-24 | [7 empty] | 2014-12-12 | 2014-12-04 |  |  |  |  | site visit with Viv from Eden park 17/10 - proposal with photo montage sent to Eden park 25/10. RF updated/new proposal (sitll being finalised) communicated to JL 29/10 - this plan is significantly different and larger than initially planned with 6 x sectors around whole stadium. Awaiting full scope from RF - 31/10/13. (meeting with RF 1/11/13). Caravan measure up scheduled for 21 March 2014 with final design (2 site build - 6 sectors, 2 sets of DF cabinets) DAS negotiations are still underway in parallel to pursuing our own sites here. 28 Aug - co-site agreements and letters of comfort have been given from both VF and Spark | [10 empty] | 2014-12-05 | 2014-12-02 | 2014-06-23 | LOW | AUCKLAND | 2014-11-07 | 2014-11-07 | BUILD | 2014-11-14 | FALSE |  | 2665918 | 6479281 | Eden Park, Reimers Ave, Kingsland, Auckland |  |  | CELLSITE |  |  | 2014-12-04 | [14 empty] | 2014-03-25
0 | AKL | 366 | AKL-007-201 | Eden Park Stadium - 2nd site | AKL-007-201-A | Eden Park - Stadium South Stand | Auckland City | 12 | 2014 | ACTIVE | RT | DF5 | RT | Grey | INLINE | COSITE |  |  |  | -36.8749 | 174.7446 |  |  |  |  | Fibre Optic | AKL-007-191-A | FALSE | FALSE |  |  | FALSE |  | 2014-03-21 | 2014-03-21 | 2014-03-25 | 2014-03-25 | 2014-04-11 | 2014-05-01 | 3 | 2014-04-21 | 2014-06-18 | 2014-07-18 | 2014-09-18 | 2014-09-26 | 2014-10-13 |  | 2014-10-03 | 2014-10-13 | DISCRETIONARY_FULL | 2014-06-23 | 2014-06-23 | 2014-07-23 | 2014-07-21 | 3 | 2014-07-30 | 2014-07-21 | 2014-06-03 | 2014-06-03 | 2014-07-25 | 2014-07-25 | 2 |  | 2014-07-31 | 2014-09-03 | [5 empty] | 2014-10-10 | 2014-10-08 | 2014-10-31 | 2014-10-30 | 2014-11-11 | 2014-11-28 | 2014-11-24 | 2014-11-28 | 2014-11-24 | [7 empty] | 2014-12-12 | 2014-12-04 | [15 empty] | 2014-12-05 | 2014-12-02 | 2014-06-23 | LOW |  | 2014-11-07 | 2014-11-07 | BUILD | 2014-11-14 | FALSE |  | 2665918 | 6479281 | Reimers Ave, Kingsland, Auckland |  |  | CELLSITE |  |  | 2014-12-04 | [14 empty] | 2014-03-25
0 | AKL | 367 | AKL-007-202 | 47 George St | AKL-007-202-A | TX - 47 George Street | Auckland City |  | TIER_6 | ACTIVE | IB | TX | [26 empty] | 2013-11-06 | 1 |  | 2013-11-06 | [45 empty] | 2013-12-13 |  | 2013-12-13 |  |  | TX only site for IT | [19 empty] | FALSE |  |  |  | 47 George Street, Newmarket, Auckland |  |  | TXSITE
0 | AKL | 368 | AKL-007-203 | Elliot St |  |  | Auckland City |  | TIER_9 | [22 empty] | FALSE | [75 empty] | AUCKLAND
0 | AKL | 369 | AKL-007-204 | Anzac | AKL-007-204-C | Tasman Building | Auckland City | 23 | 2015P | ACTIVE | RT | DF5 | NOPOLE |  | STACK_A | COSITE |  |  |  | -36.8464 | 174.7721 |  |  |  |  | Fibre Optic | AKL-007-185-A | FALSE | FALSE |  |  | FALSE |  | 2015-01-26 | 2015-02-04 | 2015-02-10 | 2015-02-09 | 2015-03-06 | 2015-03-02 | 1 | 2015-03-13 | 2015-03-02 | 2015-05-22 | 2015-05-20 | 2015-06-16 | 2015-06-10 |  | 2015-06-23 | 2015-06-11 | PERMITTED | 2015-05-25 | 2015-05-20 | 2015-07-28 | 2015-06-19 | 1 | 2015-07-31 | 2015-06-22 | 2015-05-22 | 2015-05-20 | 2015-06-26 | 2015-06-25 | 1 |  | 2015-06-26 | 2015-06-25 | [12 empty] | 2016-04-06 | [14 empty] | 09.12.14 Site Search at Tasman Building, we could make it work. LL keen to see our proposal. Next step is CARAVAN. Brad to set up. 04/2/15 - Caravanned. Good options available 12/5/15 - Alternative sites have same relocation requirements. Pressing on with this site. 20/05/15 - Lease with 2 Degrees. CDI issued 25/05/15 - Co-site application lodged with Spark 26/05/15 - Owner signed lease, now with 2 D. Ron + Ritchell to visit 27/5 for CD measure 11/06/15 - Spark co-site approval received 29/06/15 - Build delayed to 2016 | [15 empty] | 2016-04-06 |  | BUILD |  | FALSE |  | 2668430 | 6482393 | Tasman Building Anzac Street Auckland | All SA complete ticked off by Liz - checked Co-site approval from Spark no SFA advised. - 11/06/2015 |  | CELLSITE | WIPACTIVE |  |  | CAPACITY | [13 empty] | 2015-02-09
0 | AKL | 370 | AKL-007-205 | Brittomart Microcell | AKL-007-205-B | Brittomart (Galway St) | Auckland City | 22 | 2014 | ACTIVE | RSR | MC | SP | [6 empty] | -36.8448 | 174.7689 |  |  |  |  | Fibre Optic | AKL-007-185-A | FALSE | FALSE |  |  | FALSE |  | 2014-06-23 | 2014-06-23 | 2014-06-23 | 2014-06-23 | 2014-07-11 | 2014-07-18 | 2 | 2014-07-18 | 2014-10-13 | 2014-11-28 | 2014-11-18 | 2014-12-04 | 2014-11-18 | 2 | 2014-12-04 | 2014-11-18 | DISCRETIONARY_FULL | 2014-09-17 | 2014-09-17 | 2014-10-29 | 2014-10-08 | 1 | 2014-10-30 | 2014-10-08 | 2014-09-23 | 2014-09-23 | 2014-10-10 | 2014-10-28 | 1 |  |  | 2014-10-28 | [5 empty] | 2014-12-01 | 2014-11-14 | 2014-12-08 | 2014-12-11 | 2014-12-11 | 2014-12-05 | 2014-12-11 | 2014-12-15 | 2014-12-11 | [7 empty] | 2015-01-20 | 2015-01-20 |  |  |  |  | 23.05.14 Took Mark the AKL Planner out, reviewed 4 own pole sites. Await his feedback. 18.06.14 After much discussion this appears to be the best solution. AT have reolved their issues with us, thus this is now viable. Also has the potential to be come a macro site. Have AT approval and TN approval and RMA. Await Fibre, Transfield + STL to do civils and TI - Integratioh checksheet in circulation on CR 39442 | [10 empty] | 2015-01-16 | 2015-01-16 | 2014-09-17 | LOW |  | 2014-12-15 | 2014-12-10 | BUILD | 2014-12-08 | FALSE |  | 2668152 | 6482583 | Corner of Galway and Gore St City Centre Auckland | Date Lease Issued is the date the Telco notice was sent out. - 18/09/2014 | Won't comply with NES and unlikely to comply with special precinct rules - 03/07/2014 | CELLSITE | [17 empty] | 2014-06-23
0 | AKL | 371 | AKL-007-206 | Fort & Queen Microcell | AKL-007-206-B | LPR | Auckland City | 22 | 2015 | ACTIVE | RSR | MC | NOPOLE | [6 empty] | -36.8458 | 174.7663 |  |  |  |  | Fibre Optic | AKL-007-185-A | FALSE | FALSE |  |  | FALSE |  |  | 2014-09-05 |  | 2014-09-08 | 2014-09-18 | 2014-09-25 | 2 | 2014-09-26 | 2014-11-11 | 2015-02-27 | 2015-02-25 | 2015-03-06 | 2015-02-25 |  | 2015-03-06 | 2015-02-25 | NON_COMPLYING_FULL | 2014-11-14 | 2014-11-13 | 2014-12-12 | 2014-12-01 | 2 | 2014-12-12 | 2014-12-01 | 2014-09-30 | 2014-09-30 | 2014-11-07 | 2014-11-11 | 1 |  | 2014-11-14 | 2014-11-11 | [5 empty] | 2015-04-16 | 2015-04-16 | 2015-04-16 | 2015-04-22 | 2015-04-16 | 2015-04-16 | 2015-04-22 | 2015-04-16 | [8 empty] | 2015-05-01 | 2015-05-01 |  |  |  |  | 30.09 PD's complete STD 914 to be amended until AT happy - then we can submit. Required STD 914 for TN and RMA submission. 01.12.2014 RMA approved AT Applications to be submitted - need TMP from Johan and PS1 from Chris A 18.2.15 - awaiting AT approval | [10 empty] | 2015-04-23 | 2015-04-23 | 2014-11-12 | LOW |  | 2015-02-27 | 2015-02-25 | BUILD | 2015-04-16 | FALSE |  | 2667918 | 6482472 | Traffic Light Pole Cnr of Fort and Queen St Auckland CBD | Date Lease Issued is the date the Telco Notice was sent. - 24/10/2014 | Sight Line No.7 - 13/11/2014 | CELLSITE |  |  |  | SMALL CELLS | [13 empty] | 2014-09-08
0 | AKL | 372 | AKL-007-207 | Wyndham & Queen Microcell | AKL-007-207-B | Light Pole | Auckland City | 22 | 2015 | ACTIVE | RSR | MC | NOPOLE | [6 empty] | -36.8474 | 174.7656 |  |  |  |  | Fibre Optic | AKL-007-185-A | FALSE | FALSE |  |  | FALSE |  | 2014-09-02 | 2014-09-02 | 2014-09-05 | 2014-09-04 | 2014-09-19 | 2014-09-15 | 2 | 2014-09-30 | 2014-11-12 | 2015-02-27 | 2015-02-25 | 2015-03-06 | 2015-02-25 |  | 2015-03-13 | 2015-02-25 | DISCRETIONARY_FULL | 2014-11-14 | 2014-10-30 | 2014-12-12 | 2014-11-25 | 2 | 2014-12-12 | 2014-11-25 | 2014-09-30 | 2014-09-30 | 2014-11-07 | 2014-11-12 | 1 |  | 2014-11-14 | 2014-11-12 | [5 empty] | 2015-04-20 | 2015-04-20 | 2015-04-20 | 2015-04-20 | 2015-04-20 | 2015-04-20 | 2015-04-20 | 2015-04-20 | 2015-04-20 | [7 empty] | 2015-05-01 | 2015-05-01 |  |  |  |  | Measured back up pole, Lease taking long and we are getting unsure. progressing pole. 30.09 PD's complete STD 914 to be amended until AT happy - then we can submit. Required STD 914 for TN and RMA submission 01.12.2014 RMA approved AT Applications to be submitted - need TMP from Johan and PS1 from Chris A 18.2.15 - awaiting AT approvals | [10 empty] | 2015-04-23 | 2015-04-23 | 2014-11-25 | LOW |  | 2015-02-27 | 2015-02-25 | BUILD | 2015-04-20 | FALSE |  | 2667854 | 6482296 | Light Pole on Wyndham & Queen corner Outside Esquires | Date Lease Issued is the date the Telco Notice was sent. - 24/10/2014 |  | CELLSITE |  |  |  | SMALL CELLS | [13 empty] | 2014-09-04
0 | AKL | 373 | AKL-007-208 | Victoria & Queen Microcell | AKL-007-208-B | Lightpole outside Starbucks | Auckland City | 22 | 2015 | ACTIVE | RSR | MC | NOPOLE | [6 empty] | -36.8492 | 174.7653 |  |  |  |  | Fibre Optic | AKL-007-185-A | FALSE | FALSE |  |  | FALSE |  | 2014-09-04 | 2014-09-04 | 2014-09-04 | 2014-09-04 | 2014-09-16 | 2014-09-24 | 2 | 2014-09-26 | 2014-11-11 | 2015-02-27 | 2015-02-25 | 2015-03-06 | 2015-02-25 |  | 2015-03-13 | 2015-02-25 | DISCRETIONARY_FULL | 2014-11-14 | 2014-11-12 | 2014-12-12 | 2014-12-01 | 2 | 2014-12-12 | 2014-12-01 | 2014-09-30 | 2014-09-30 | 2014-11-07 | 2014-11-11 | 1 |  | 2014-11-14 | 2014-11-11 | [5 empty] | 2015-04-17 | 2015-04-17 | 2015-04-17 | 2015-04-20 | 2015-04-17 | 2015-04-17 | 2015-04-17 | 2015-04-17 | [8 empty] | 2015-04-24 | 2015-04-24 |  |  |  |  | 01.12.2014 RMA approved AT Applications to be submitted - need TMP from Johan and PS1 from Chris A 18.2.15 - awaiting AT approval | [10 empty] | 2015-04-23 | 2015-04-22 | 2014-11-12 | LOW |  | 2015-02-27 | 2015-02-25 | BUILD | 2015-04-17 | FALSE |  | 2667825 | 6482100 | Cnr Victoria and Queen Str. - outside Starbucks | Date Lease Issued is the date the Telco Notice was sent. - 24/10/2014 |  | CELLSITE |  |  |  | SMALL CELLS | [13 empty] | 2014-09-04
0 | AKL | 374 | AKL-007-209 | Wellesley & Queen Microcell | AKL-007-209-B | Bangkok Cafe | Auckland City | 3 | 2014 | ACTIVE | BO | MC | RT | Grey |  | STANDALONE |  |  |  | -36.8507 | 174.7644 |  |  |  |  | Fibre Optic | AKL-007-185-A | FALSE | FALSE |  |  | FALSE |  | 2014-05-22 | 2014-05-22 | 2014-05-22 | 2014-05-22 | 2014-06-20 | 2014-06-16 | 1 | 2014-06-27 | 2014-06-16 |  | 2014-06-19 | 2014-07-11 | 2014-07-03 |  | 2014-07-18 | 2014-07-03 | PERMITTED | 2014-07-18 | 2014-07-18 | 2014-08-29 | 2014-08-01 | 1 | 2014-09-05 | 2014-08-01 | 2014-06-19 | 2014-07-01 |  | 2014-07-09 | 1 |  | 2014-07-09 | 2014-07-09 | [5 empty] | 2014-10-08 | 2014-10-08 |  | 2014-10-08 | 2014-10-08 | 2014-10-08 | 2014-12-16 | 2014-11-03 | 2014-12-08 | [7 empty] | 2014-12-19 | 2014-12-19 |  |  |  |  | 22.05.14We met Matt the S&C facilities manager. Showed us into the roof. Looks very promising. Need to do a presentation. | [10 empty] | 2014-12-18 |  | 2014-07-22 | LOW |  | 2014-10-27 | 2014-12-08 | BUILD | 2014-10-08 | FALSE |  | 2667740 | 6481930 | 267 Bangkok Cafe Queen Street |  | Dependent on Council interpretation of rooftop projection rule - 03/07/2014 | CELLSITE | [17 empty] | 2014-05-22
0 | AKL | 375 | AKL-007-210 | Oneroa Township South | AKL-007-210-A | 132 Oceanview Road | Auckland City | 12 | 2014 | ACTIVE | RSR | MC | NOPOLE | Grey |  |  | 10 |  |  | -36.7836 | 175.011 |  |  |  |  | Fibre Optic | AKL-007-192-A | FALSE | FALSE |  |  | FALSE |  | 2014-08-11 | 2014-08-12 | 2014-08-12 | 2014-08-13 | 2014-08-27 | 2014-08-28 | 3 | 2014-09-05 | 2014-10-16 | 2014-10-31 | 2014-10-29 | 2014-11-07 | 2014-11-18 | 3 | 2014-11-14 | 2014-11-18 | DISCRETIONARY_FULL | 2014-09-09 | 2014-09-08 | 2014-11-07 | 2014-10-29 | 3 | 2014-11-14 | 2014-10-29 | 2014-10-21 | 2014-09-30 | 2014-10-24 | 2014-10-24 | 1 |  | 2014-10-31 | 2014-10-24 | [5 empty] | 2014-11-24 | 2014-11-14 | 2014-12-18 | 2014-12-16 | 2014-12-02 | 2014-12-18 | 2014-12-16 | 2015-02-18 | 2014-12-16 | [7 empty] | 2014-12-19 | 2014-12-19 |  |  |  |  | 01.08.2014 BC Approved. Progress to build ASAP | [10 empty] | 2014-12-19 | 2014-12-19 | 2014-09-08 | HIGH |  | 2014-12-12 | 2014-12-12 | BUILD | 2014-12-02 | FALSE |  | 2689895 | 6488903 | LPR Outside Oneroa Accident and Medical 132 Oceanview Road Oneroa | Date Lease Issued is the date the Telco notice was sent out. - 18/09/2014 |  | CELLSITE | [17 empty] | 2014-08-13
0 | AKL | 376 | AKL-007-211 | Mt Eden Microcell | AKL-007-211-A | Mt Eden Microcell | Auckland City | 12 | 2014 | ACTIVE | RSR | MC | NOPOLE | Grey |  |  | 10 | 12.3 |  | -36.8781 | 174.7612 |  |  |  |  | Fibre Optic | AKL-007-191-A | FALSE | FALSE |  |  | FALSE |  | 2014-08-26 | 2014-08-26 | 2014-08-28 | 2014-08-26 | 2014-09-11 | 2014-09-04 | 2 | 2014-09-18 | 2014-10-15 | 2014-10-31 | 2014-10-29 | 2014-11-07 | 2014-11-18 | 2 | 2014-11-14 | 2014-11-18 | DISCRETIONARY_FULL | 2014-09-15 | 2014-09-10 | 2014-11-07 | 2014-11-07 | 2 | 2014-11-14 | 2014-11-07 | 2014-10-20 | 2014-09-30 | 2014-10-24 | 2014-10-24 | 1 |  | 2014-10-31 | 2014-10-24 | [5 empty] | 2014-11-24 | 2014-11-14 | 2014-12-16 | 2014-12-08 | 2014-12-02 | 2014-12-16 | 2014-12-08 | 2014-12-16 | 2014-12-08 | [7 empty] | 2014-12-19 | 2014-12-17 |  |  |  |  | 18.07.14 Scoping done for MC RF = Michael Lai and TX = Ryan. Pole identified .Tx Prequal done. Budget approved at Gov. NEXT STEP = Caravan by Jackie | [10 empty] | 2014-12-16 | 2014-12-16 | 2014-09-10 | LOW | AUCKLAND | 2014-12-05 | 2014-12-01 | BUILD | 2014-11-28 | FALSE |  | 2667390 | 6478895 | Lightpole outside 335 Mt Eden Rd | Date Lease Issue is the date the Telco notice was sent out. - 18/09/2014 |  | CELLSITE | [17 empty] | 2014-08-26
0 | AKL | 377 | AKL-007-212 | Ellerslie West | AKL-007-212-C | 624-626 Great South Rd | Auckland City | 22 | 2015P | ACTIVE | RT | DF5 | RT |  | STACK_A | COSITE |  |  |  | -36.8987 | 174.8041 |  |  |  |  | Fibre Optic | AKL-007-192-A | FALSE | FALSE |  |  | FALSE |  | 2014-11-13 | 2014-11-24 | 2014-11-25 | 2014-11-25 | 2014-12-19 | 2014-12-15 | 2 | 2015-01-16 | 2015-02-17 | 2015-04-30 | 2015-06-09 | 2015-05-14 | 2015-06-12 |  | 2015-05-21 | 2015-07-03 | PERMITTED | 2015-04-30 | 2015-04-30 | 2015-05-29 | 2015-05-21 | 2 | 2015-06-08 | 2015-05-21 | 2015-04-30 | 2015-04-30 | 2015-11-30 |  |  |  | 2015-11-30 | [28 empty] | 16/1/15 - awaiting feedback from Argosy on proposed design 28/1/15 - still awaiting feeback from Argosy 19.2.15 - VF co-site agreement lodged 13/8/15 - fibre order cancelled - site will not be built until 2016 | [17 empty] | BUILD |  | FALSE |  | 2671162 | 6476540 | 624-626 Great South Rd, Ellerslie West |  |  | CELLSITE | WIPACTIVE |  |  | CAPACITY | [6 empty] | 2015-04-29 |  | 2015-03-26 |  |  |  |  | 2014-11-25
0 | AKL | 378 | AKL-007-213 | Downtown West | AKL-007-213-B | DT West AT Downtown Carpark | Auckland City | 23 | 2015P | ACTIVE |  | DF5 | [15 empty] | FALSE | FALSE |  |  | FALSE |  | 2015-08-28 | 2015-08-25 | 2015-08-31 | 2015-08-25 | 2015-10-09 | 2015-10-12 | 2 | 2015-10-09 | 2016-01-13 | 2016-02-05 | 2016-02-09 | 2016-03-25 |  |  | 2016-03-25 |  | PERMITTED | 2016-01-25 | 2015-12-15 | 2016-02-26 | 2016-01-26 | 2 | 2016-02-26 | 2016-01-26 | 2015-12-21 | 2016-01-11 | 2016-02-19 |  |  |  | 2016-02-19 | [6 empty] | 2016-04-04 | [15 empty] | 2016-05-20 | [5 empty] | 07/07/15 - New candidate to be found. 04/08/15 - Brad to visit area with Kevin to look at options - with time getting short, need couple good candidates to progress 11/08/15 - Been for drive - list candidates available - Kevin to prioritise 24/08/15 - Downtown Carpark caravanned and drawings underway 4/11/15 - Resource Consent drafted and ready to lodge when adised. 10/11/15 - Council to come back on design asap 08/12/15 - Council OK, and providing proposed license agreement. Will require Detailed Design sign-offs. Brad to send through the questions 9/2/16 - Had prelim meeting with AT re CD's and a number of amendments required. Lease will not be signed until CD's approved. | [10 empty] | 2016-05-06 | [6 empty] | BUILD |  | FALSE |  |  |  | AT Downtown Carpark Customs Street Auckland |  |  | CELLSITE | WIPACTIVE |  |  | RELOCATION |  |  |  | 2016-03-14 | [5 empty] | 2016-03-25 |  |  |  | 2015-08-25
0 | AKL | 379 | AKL-007-214 | Downtown East | AKL-007-214-A | Rabo Direct | Auckland City | 23 | 2015P | ACTIVE | RT | DF5 | NOPOLE |  | STACK_A | COSITE |  |  |  | -36.8441 | 174.7629 |  |  |  |  | Fibre Optic | AKL-007-185-A | FALSE | FALSE |  |  | FALSE |  | 2015-06-19 | 2015-06-23 | 2015-06-23 | 2015-06-24 | 2015-09-04 | 2015-09-03 | 2 |  | 2016-01-12 | 2016-02-19 |  | 2016-03-18 |  |  | 2016-03-18 |  | PERMITTED | 2015-10-13 | 2015-10-13 | 2016-03-18 |  | 1 | 2016-03-18 |  | 2016-02-29 |  | 2016-03-18 |  |  |  | 2016-03-18 | [6 empty] | 2016-04-04 | [15 empty] | 2016-05-20 | [5 empty] | Replacement for Downtown South which is being demolished end 2015/2016 26/05/15 - Caravan Thursday, for the confirmed 2 sectors and options for 3rd 23/06/15 - Caravanned for 2 sector option. Build 2016 4/11/15 - Concerns on Design, asthetics and potential impact on future signage. Consent ready to be issued, but asked to hold in case plans change 10/11/15 - Discussing what they need of us in terms of relocation provisions 8/12/15 - coming back to Brad in couple days. Consent on hold at our request to cope with design changes. 9/2/16 - Lease with owners lawyers. Not responding as yet. CoC on hold ready to sub out plans and issue. Need backup alternatives (Kevin) | [10 empty] | 2016-05-06 | [6 empty] | BUILD |  | FALSE |  | 2667619 | 6482664 | Rabo Direct Building 2 Commerce St Auckland |  |  | CELLSITE | WIPACTIVE |  |  | RELOCATION |  |  |  | 2016-03-14 | [5 empty] | 2016-03-25 |  |  |  | 2015-06-24
0 | AKL | 380 | AKL-007-215 | Khyber Pass South | AKL-007-215-A | Khyber Pass South | Auckland City | 23 | 2015P | ACTIVE | RT | DF5 |  |  | INLINE |  |  |  |  | -36.8681 | 174.7613 |  |  |  | 2015-06-18 | Fibre Optic | AKL-007-185-A | FALSE | FALSE |  |  | FALSE |  | 2015-06-05 | 2015-06-08 | 2015-06-17 | 2015-06-17 | 2015-07-24 | 2015-07-14 | 1 | 2015-07-24 | 2015-07-14 | 2015-08-13 | 2015-08-13 | 2016-02-19 | 2016-01-26 |  | 2016-02-26 |  | NON_COMPLYING_FULL | 2015-10-06 | 2016-01-06 | 2016-05-20 |  | 1 | 2016-05-20 |  | 2016-03-18 |  | 2016-04-15 |  |  |  | 2016-04-15 | [28 empty] | 26/05/15 - Advised Jordan on leave till 1 July - Ben/John to advise if replacement acq required 03/06/15 - Caravan 05 June 23/06/15 - Pre-meeting with Council when PD's available - to discuss view shaft concerns 08/09/15 - LA4 landscape to do assessment - Contract required. Likely to be notified. Need to look at smaller shrouds, in which case all drawings need to be updated 22/09/15 - Survey to be undertaken to confirm view shaft position - if site clear the consent will be OK. If site inside, then need to deal with visuals 29/9/15 - Survey confirmed outside view shaft. Consent will be CoC. dates revised 4/11/15 - Lease OK. New build starts April/May, so need to be ready to build 17/11/15 - Council view site as being in viewshaft - likely now to be notified. Also need to look for alternatives 9/2/16 - Iwi consultation (Maunga Authority) needed before Council will issue decision on Notification. Landscape peer review is being undertaken internally by Council | [17 empty] | HARDMATCH |  | FALSE |  | 2667420 | 6480007 |  |  |  | CELLSITE | WIPACTIVE |  |  | CAPACITY | [13 empty] | 2015-06-17
0 | AKL | 381 | AKL-008-001 |  | AKL-008-001-F | Mangere Bridge GF | Manukau City |  | TIER_1_ALL | ACTIVE | GF | A6 | P3 | green |  |  | 24 | 24 |  | -36.9471 | 174.7935 | [17 empty] | 2007-08-31 | 1 | 2007-08-31 | 2007-08-31 |  |  | 2007-10-05 | 2007-10-05 | 1 | 2007-10-05 | 2007-10-05 |  |  |  | 2008-06-30 |  |  | 2008-06-30 | 2008-05-29 |  | 2007-10-21 |  | 2007-10-24 | 2 | 1 | 2007-11-02 | 2007-11-02 | [6 empty] | 2008-06-16 | 2008-06-30 | 2008-06-30 |  | 2008-07-14 | 2008-07-10 | [8 empty] | 2009-05-26 | 2009-05-29 | 2009-05-26 |  |  |  |  | (May14 DJ) (on schedule). SOA end of May |  | 2009-05-29 | [17 empty] | FALSE |  | 2670110 | 6471186 | 36 Hastie Ave Mangere |  |  | CELLSITE |  |  | 2014-08-12 | [5 empty] | 2008-05-30 | [8 empty] | 2007-08-22
0 | AKL | 382 | AKL-008-002 |  | AKL-008-002-F | Mangere | Manukau City |  | TIER_1_ALL | ACTIVE | GF | A6 | P3 | grey |  |  | 20 | 20 |  | -36.971 | 174.803 |  |  |  |  | Microwave, Leased Line | AKL-007-074-A, AKL-007-106-A | [5 empty] | 2009-05-12 | [5 empty] | 2008-02-09 | 3 |  | 2008-08-21 |  |  | 2007-12-14 | 2007-12-14 | 3 | 2007-12-14 | 2007-12-14 |  |  |  | 2008-09-30 |  |  | 2008-09-30 | 2008-08-29 |  | 2008-02-13 |  | 2008-09-09 | 1 | 3 | 2008-09-09 | 2008-09-09 | [6 empty] | 2008-09-29 | 2008-10-16 | 2008-10-16 |  | 2008-10-17 | 2008-10-17 | [8 empty] | 2009-03-17 | 2009-03-20 | 2009-03-17 |  |  |  |  | On Air |  | 2009-03-20 | [17 empty] | FALSE |  | 2670903 | 6468519 | 9 Wanstead Way Mangere Auckland |  |  | CELLSITE |  |  | 2014-08-12 | [5 empty] | 2008-09-18 | [8 empty] | 2007-12-12
0 | AKL | 383 | AKL-008-003 |  | AKL-008-003-A | Otahuhu | Manukau City |  | TIER_1_ALL | ACTIVE | RT | B6 | NOPOLE | grey |  |  | 24 | 24 |  | -36.9463 | 174.8438 |  |  |  |  | Microwave | AKL-007-114-D | [11 empty] | 2007-08-28 | 6 | 2009-03-13 | 2009-03-26 |  |  | 2009-02-27 | 2009-02-27 | 2 | 2009-04-15 | 2009-06-24 |  | 2009-03-02 |  | 2009-04-15 |  |  | 2009-04-15 | 2009-04-17 | 2009-03-02 | 2009-03-01 |  | 2009-04-02 | 1 | 2 | 2009-04-06 | 2009-04-02 | [5 empty] | 2009-05-11 | 2009-05-11 | 2009-06-19 | 2009-06-16 |  | 2009-07-10 | 2009-07-10 | [8 empty] | 2009-07-20 | 2009-07-21 | 2009-07-20 |  |  |  |  | On Air |  | 2009-07-21 | [17 empty] | FALSE |  | 2674591 | 6471181 | 18 Park Ave Otahuhu Auckland |  |  | CELLSITE |  |  | 2014-08-12 |  |  |  |  | 2009-05-11 | 2009-05-11 | [8 empty] | 2007-08-16
0 | AKL | 384 | AKL-008-004 |  | AKL-008-004-A | Puhinui Motorway Junction | Manukau City |  | TIER_1_ALL | ACTIVE | GF | A6 | P3 | grey |  |  | 20 | 20 |  | -36.9946 | 174.8464 |  |  |  |  | Microwave | AKL-008-018-A | [5 empty] | 2009-05-13 | [5 empty] | 2007-08-29 | 1 |  | 2007-08-29 |  |  | 2008-01-18 | 2008-01-18 | 1 | 2008-01-18 | 2008-01-18 |  |  |  | 2008-08-31 |  |  | 2008-08-31 | 2008-10-14 |  | 2007-11-20 |  | 2008-04-25 | 1 | 1 | 2008-04-25 | 2008-04-25 | [6 empty] | 2008-11-05 | 2008-11-24 | 2008-11-21 |  | 2008-11-20 | 2008-11-21 | [8 empty] | 2008-12-31 | 2009-02-27 | 2008-12-31 |  |  |  |  | None |  | 2009-02-27 | [17 empty] | FALSE |  | 2674708 | 6465798 | Safe Store Public Storage Auckland |  |  | CELLSITE |  |  | 2014-09-12 | [5 empty] | 2008-10-30 | [8 empty] | 2007-08-13
0 | AKL | 385 | AKL-008-005 |  | AKL-008-005-F | Otara | Manukau City |  | TIER_1_ALL | ACTIVE | GF | A6 | P3 | grey |  |  | 20 | 20 |  | -36.9583 | 174.8751 |  |  |  |  | Microwave, Leased Line | AKL-008-024-A, AKL-007-106-A | [11 empty] | 2007-11-15 | 1 |  | 2007-11-15 |  |  | 2007-11-28 | 2007-11-28 | 1 | 2007-11-28 | 2007-11-28 |  |  |  | 2008-05-31 |  |  | 2008-05-31 | 2008-06-11 |  | 2007-12-10 |  | 2008-04-30 | 2 | 1 | 2008-06-04 | 2008-06-04 | [6 empty] | 2008-06-16 | 2008-08-08 | 2008-08-08 |  | 2008-08-22 | 2008-08-28 | [8 empty] | 2009-03-11 | 2009-03-12 | 2009-03-11 |  |  |  |  | On Air |  | 2009-03-12 | [17 empty] | FALSE |  | 2677349 | 6469789 | Trans Space 12 Lovegrove Crescent Otara Auckland |  |  | CELLSITE |  |  | 2014-09-12 | [5 empty] | 2008-06-12 | [8 empty] | 2007-10-27
0 | AKL | 386 | AKL-008-006 |  | AKL-008-006-F | Southmall | Manukau City |  | TIER_1_ALL | ACTIVE | GF | A6 | P2 | grey |  |  | 20 | 20 |  | -37.021 | 174.8927 |  |  |  |  | Microwave | AKL-008-018-A | [5 empty] | 2009-05-13 | [5 empty] | 2008-04-22 | 1 |  | 2008-04-22 |  |  | 2008-04-04 | 2008-04-04 | 1 | 2008-04-04 | 2008-04-04 | [7 empty] | 2008-06-10 |  | 2008-04-22 |  | 2008-06-06 | 1 | 1 | 2008-06-06 | 2008-06-06 | [6 empty] | 2008-07-03 | 2008-08-25 | 2008-08-15 |  | 2008-08-29 | 2008-08-28 | [8 empty] | 2008-12-31 | 2009-02-27 | 2008-12-31 |  |  |  |  | None |  | 2009-02-27 | [17 empty] | FALSE |  | 2678769 | 6462796 | 18A Maich Road Southmall Auckland |  |  | CELLSITE |  |  | 2014-09-12 | [5 empty] | 2008-06-12 | [8 empty] | 2008-03-28
0 | AKL | 387 | AKL-008-008 |  | AKL-008-008-C | Mangere West | Manukau City |  | TIER_1_ALL | ACTIVE | GF | A6 | P3 | grey |  |  | 21.8 | 21.8 |  | -36.9753 | 174.7869 |  |  |  |  | Microwave | AKL-008-001-F | [11 empty] | 2008-06-26 | 5 | 2009-02-18 | 2015-09-03 |  |  | 2009-05-15 | 2009-05-15 | 4 | 2009-06-30 | 2009-06-15 | [6 empty] | 2009-06-04 | 2009-06-03 | 2009-03-30 | 2008-11-03 |  | 2009-02-09 | 4 | 4 | 2009-06-10 | 2009-06-23 | 2009-03-23 |  |  |  |  | 2009-06-22 | 2009-06-22 | 2009-07-03 | 2009-07-03 |  | 2009-07-24 | 2009-07-24 | [8 empty] | 2009-07-28 | 2009-07-28 | 2009-07-28 |  |  |  |  | On Air |  | 2009-07-28 |  |  |  |  | 2009-03-20 | 2009-03-23 | [11 empty] | FALSE |  | 2669458 | 6468067 | 13 Freight Place Mangere Auckland |  |  | CELLSITE |  |  | 2014-08-12 |  |  |  |  | 2009-06-22 | 2009-06-22 | [8 empty] | 2008-04-30
0 | AKL | 388 | AKL-008-009 |  | AKL-008-009-A | Takanini Junction | Manukau City |  | TIER_1_ALL | ACTIVE | GF | A6 | P3 | grey |  |  | 25 | 25 |  | -37.0356 | 174.9131 |  |  |  |  | Microwave | AKL-009-002-B | [5 empty] | 2009-05-13 | [5 empty] | 2007-10-16 | 2 |  | 2007-10-16 |  |  | 2008-02-20 | 2008-02-20 | 2 | 2008-02-20 | 2008-02-20 |  |  |  | 2008-03-26 |  |  | 2008-03-26 | 2008-03-26 |  | 2007-10-31 |  | 2008-03-27 | 1 | 2 | 2008-03-27 | 2008-03-27 | [6 empty] | 2008-05-13 | 2008-05-30 | 2008-05-29 |  | 2008-06-06 | 2008-06-06 | [8 empty] | 2008-11-21 | 2008-12-08 | 2008-11-21 |  |  |  |  | None |  | 2008-11-24 | [17 empty] | FALSE |  | 2680542 | 6461139 | 20 Spartan Rd Takanini Auckland |  |  | CELLSITE |  |  | 2014-09-12 | [5 empty] | 2008-03-28 | [8 empty] | 2007-09-05
0 | AKL | 389 | AKL-008-010 |  | AKL-008-010-A | Clendon Town Centre | Manukau City | 3 | TIER_1_ALL | ACTIVE | GF | A6 | P3 | grey |  |  | 20 | 20 |  | -37.0333 | 174.8689 |  |  |  |  | Microwave | AKL-008-018-A | FALSE | FALSE |  |  | FALSE | 2009-05-12 | [5 empty] | 2008-02-27 | 2 | 2008-03-17 | 2008-03-17 |  |  | 2008-02-25 | 2008-02-25 | 2 | 2008-02-25 | 2008-02-25 |  |  |  | 2008-08-29 |  |  | 2008-08-29 | 2008-08-29 |  | 2008-02-29 |  | 2008-09-26 | 1 | 2 | 2008-09-26 | 2008-09-26 | 2009-01-30 | [5 empty] | 2008-10-02 | 2009-02-20 | 2009-02-17 |  | 2009-02-20 | 2009-02-18 | [8 empty] | 2009-03-18 | 2009-03-26 | 2009-03-18 |  |  |  |  | (Mar18 DJ) Site On Air Link to Weymouth REQUIRE : 300mmØ |  | 2009-03-26 |  |  |  |  | 2009-01-20 | 2009-01-30 | [11 empty] | FALSE |  | 2676614 | 6461476 | Clendon Town Centre Auckland |  |  | CELLSITE |  |  | 2014-09-12 | [5 empty] | 2008-10-01 | [8 empty] | 2007-12-20
0 | AKL | 390 | AKL-008-013 |  | AKL-008-013-F | Middlemore Hospital | Manukau City | 3 | TIER_1_ALL | ACTIVE | RT | B6 | NOPOLE | grey |  |  | 28.2 | 28.2 |  | -36.9637 | 174.8407 |  |  |  |  | Microwave | AKL-007-114-D | FALSE | FALSE |  |  | FALSE | [6 empty] | 2009-04-22 | 3 | 2009-04-17 | 2009-05-29 |  |  | 2009-06-08 | 2009-06-10 | 2 | 2009-06-08 | 2009-06-10 |  | 2009-05-07 |  | 2009-06-19 |  |  | 2009-06-19 | 2009-06-11 | 2009-04-30 | 2009-04-15 |  | 2009-05-06 | 3 | 3 | 2009-05-15 | 2009-06-29 | [5 empty] | 2009-06-22 | 2009-06-22 | 2009-07-24 | 2009-07-24 |  | 2009-08-05 | 2009-08-05 | [8 empty] | 2009-08-14 | 2009-10-22 | 2009-08-14 |  |  |  |  | On Air Link to Mangere E REQUIRE : 300mmØ |  | 2009-10-22 | [17 empty] | FALSE |  | 2674271 | 6469253 | Hospital Road Otahuhu |  |  | CELLSITE |  |  | 2014-09-12 |  |  |  |  | 2009-06-22 | 2009-06-22 | [8 empty] | 2009-03-19
0 | AKL | 391 | AKL-008-014 |  | AKL-008-014-C | Highbrook | Manukau City |  | TIER_1_ALL | ACTIVE | GF | A6 | P3 | grey |  |  | 23.8 | 23.8 |  | -36.9384 | 174.8815 |  |  |  |  | Microwave | AKL-008-043-C | [11 empty] | 2008-12-05 | 7 | 2009-02-16 | 2015-09-03 |  |  | 2009-03-20 | 2009-03-24 | 5 | 2009-03-20 | 2009-03-24 | DISCRETIONARY_FULL | 2009-02-10 | 2011-07-27 | 2009-03-30 | 2011-08-17 | 6 | 2009-03-06 | 2011-08-18 | 2009-03-20 | 2009-03-18 |  | 2009-04-28 | 4 |  | 2009-04-23 | 2011-10-18 | 2009-02-13 |  |  |  |  | 2009-04-27 | 2009-04-27 | 2009-06-05 | 2009-06-05 |  | 2009-06-17 | 2009-06-12 | [8 empty] | 2009-06-17 | 2009-06-18 | 2009-06-17 |  |  |  |  | (May20 DJ) On track (May28 DJ) CI TI delayed 1wk. Maintaining SOA (Jun03 DJ) On track SOA re-f'cast Jun18. (Jun10 DJ) TI delayed to Jun17 due to TX linking. Holding SOA Jun18 (Jun18 DJ) still holding SOA Jun18. Jun17 > SOA!! |  | 2009-06-18 | [5 empty] | 2009-02-13 | [11 empty] | FALSE |  | 2677967 | 6471981 | 3 Ra Ora Drive East Tamaki Auckland |  | Lodged on the 21.7.2011 Approved on the 17.8.2011 Council reference number: 39180 - 18/08/2011 | CELLSITE |  |  | 2014-09-12 |  |  |  |  | 2009-04-27 | 2009-04-27 | [8 empty] | 2008-11-25
0 | AKL | 392 | AKL-008-015 |  | AKL-008-015-E | Papatoetoe Central | Manukau City |  | TIER_1_ALL | ACTIVE | RT | B6 | NOPOLE | grey |  |  | 17 | 17 |  | -36.9681 | 174.8622 |  |  |  |  | Microwave | AKL-008-043-C | [11 empty] | 2009-04-24 | 5 | 2009-09-04 | 2009-09-02 |  |  | 2009-05-15 | 2009-04-30 |  | 2009-10-01 | 2009-09-24 |  | 2009-05-07 |  | 2009-06-26 |  |  | 2009-10-21 | 2009-10-27 | 2009-04-30 | 2009-04-15 |  | 2009-09-03 | 1 | 1 | 2009-09-04 | 2009-09-03 | [5 empty] | 2009-08-24 | 2009-09-02 | 2009-10-13 | 2009-10-13 |  | 2009-10-20 | 2009-10-20 | [8 empty] | 2009-10-29 | 2009-10-30 | 2009-10-29 |  |  |  |  | On Air |  | 2009-10-30 | [17 empty] | FALSE |  | 2676174 | 6468727 | 19 Charles St, Papatoetoe |  |  | CELLSITE |  |  | 2014-09-12 |  |  |  |  | 2009-09-02 | 2009-09-02 | [8 empty] | 2009-03-19
0 | AKL | 393 | AKL-008-016 |  | AKL-008-016-G | James Fletcher Drive | Manukau City |  | TIER_1_ALL | ACTIVE | GF | Ab6 | P3 | green | [5 empty] | -36.9476 | 174.8283 |  |  |  |  | Microwave | AKL-008-003-A | [11 empty] | 2009-08-18 | 3 | 2009-09-09 | 2009-09-09 |  |  |  | 2009-03-31 |  | 2009-09-25 | 2009-09-30 |  | 2009-09-02 |  | 2009-10-14 |  |  | 2009-10-30 | 2009-10-21 | 2009-08-24 | 2009-08-26 |  | 2009-10-16 | 1 |  | 2009-10-16 | 2009-10-16 | 2009-02-02 |  |  |  |  | 2009-11-02 | 2009-11-02 | 2009-11-20 | 2009-11-20 |  | 2009-11-25 | 2009-11-23 | [8 empty] | 2009-11-25 | 2009-11-30 | 2009-11-25 |  |  |  |  | On Air |  | 2009-11-30 | [5 empty] | 2009-02-02 | [11 empty] | FALSE |  | 2673206 | 6471061 | 266 James Fletcher Drive Otahuhu |  |  | CELLSITE |  |  | 2014-08-12 | [5 empty] | 2009-11-02 | [8 empty] | 2009-08-06
0 | AKL | 394 | AKL-008-017 |  | AKL-008-017-E | Wiri | Manukau City |  | TIER_1_ALL | ACTIVE | GF | A6 | P2 | grey |  |  | 20 | 20 |  | -37.0008 | 174.8746 |  |  |  |  | Microwave | AKL-008-036-J | [5 empty] | 2009-05-13 | [5 empty] | 2008-07-31 | 2 | 2008-11-18 | 2008-11-18 |  |  |  | 2008-07-10 | 1 |  | 2008-07-10 | [6 empty] | 2008-11-28 | 2008-11-28 |  | 2008-08-27 |  | 2008-09-17 | 2 | 2 | 2008-11-18 | 2008-11-18 | 2009-01-30 | [5 empty] | 2008-11-04 | 2009-02-20 | 2009-02-20 |  | 2009-02-20 | 2009-02-20 | [8 empty] | 2009-02-26 | 2009-02-27 | 2009-02-26 |  |  |  |  | Site On Air |  | 2009-02-27 |  |  |  |  | 2009-02-10 | 2009-01-30 | [11 empty] | FALSE |  | 2677205 | 6465079 | 20 Hobill Avenue Manukau South Auckland |  |  | CELLSITE |  |  | 2014-09-12 |  |  |  |  | 2008-11-03 | 2008-11-03 | [8 empty] | 2008-07-16
0 | AKL | 395 | AKL-008-018 |  | AKL-008-018-A | Manukau Central | Manukau City | 3 | TIER_1_ALL | ACTIVE | RT | B6 | NOPOLE | grey |  |  | 42.2 | 42.2 |  | -36.9919 | 174.8786 | [6 empty] | FALSE | FALSE |  |  | FALSE | [6 empty] | 2007-08-30 | 6 |  | 2011-11-14 |  |  | 2008-02-04 | 2008-02-04 | 4 | 2008-02-04 | 2008-02-04 | DISCRETIONARY_FULL |  | 2012-03-08 | 2008-01-25 | 2012-04-05 | 6 | 2008-01-25 | 2009-05-08 |  | 2007-10-23 |  | 2008-02-19 | 6 |  | 2009-04-09 | 2012-10-02 | [6 empty] | 2008-05-30 | 2008-06-06 | 2008-06-06 |  | 2008-06-14 | 2008-06-20 | [8 empty] | 2008-12-31 | 2009-02-27 | 2008-12-31 |  |  |  |  | Linking to Papatoetoe East and Central REQUIRE : 2 x 300mmØ |  | 2009-02-27 | [17 empty] | FALSE |  | 2677581 | 6466059 | Rd Suburb Manukau City Post Code |  | Section 127 approved on 5 April 2012 - council reference 40009 - 11/04/2012 | CELLSITE |  |  | 2014-09-12 | [5 empty] | 2008-03-25 | [8 empty] | 2007-08-30
0 | AKL | 396 | AKL-008-019 |  | AKL-008-019-B | Papatoetoe West | Manukau City |  | TIER_1_ALL | ACTIVE | RSR | A6 | P4C | green |  |  | 14.2 | 14.2 |  | -36.9737 | 174.8371 |  |  |  |  | Leased Line, Microwave | AKL-007-106-A, AKL-008-024-A | [11 empty] | 2008-02-27 | 5 | 2009-01-08 | 2009-01-08 |  |  | 2008-06-30 | 2008-06-30 | 3 | 2008-06-30 | 2008-06-30 |  |  |  | 2008-11-28 |  |  | 2009-03-06 | 2009-03-13 |  | 2008-04-29 |  | 2008-05-20 | 3 | 5 | 2009-01-08 | 2009-01-08 | 2009-01-19 | [5 empty] | 2009-01-27 | 2009-02-13 | 2009-02-12 |  | 2009-02-13 | 2009-02-13 | [8 empty] | 2009-03-20 | 2009-03-24 | 2009-03-20 |  |  |  |  | On Air |  | 2009-03-24 | [5 empty] | 2009-01-19 | [11 empty] | FALSE |  | 2673929 | 6468150 | O/s 30B Franklin Ave, Mangere East, Auckland |  |  | CELLSITE |  |  | 2014-09-12 | [5 empty] | 2008-12-05 | [8 empty] | 2008-01-31
0 | AKL | 397 | AKL-008-020 |  | AKL-008-020-C | Homai West | Manukau City |  | TIER_1_ALL | ACTIVE | GF | A6 | P2 | grey |  |  | 20 | 20 |  | -37.0149 | 174.8618 |  |  |  |  | Microwave | AKL-008-018-A | [5 empty] | 2009-05-12 | [5 empty] | 2008-08-20 | 1 | 2008-08-20 | 2008-08-20 |  |  |  | 2008-08-26 | 1 |  | 2008-08-26 | [6 empty] | 2008-10-22 | 2008-10-22 |  | 2008-09-26 |  | 2008-10-23 | 1 | 1 | 2008-10-23 | 2008-10-23 | 2009-01-30 | [5 empty] | 2008-11-03 | 2009-02-17 | 2009-02-17 |  | 2009-02-17 | 2009-02-17 | [8 empty] | 2009-04-29 | 2009-04-30 | 2009-04-29 |  |  |  |  | Using extended mount - installed (JL 21/4) (Apr23 DJ) Extended mount delayed - places SOA Apr30 at risk, but at this time, still potentially acheiveable. Bracket at Manukau CBD - is going in tomorrow 28/4. SOA at risk for end month. (JL 27/4) |  | 2009-04-30 |  |  |  |  | 2009-02-10 | 2009-01-30 | [11 empty] | FALSE |  | 2676030 | 6463530 | 254A Roscommon Rd, Wiri, Auckland |  |  | CELLSITE |  |  | 2014-09-12 | [5 empty] | 2008-10-30 | [8 empty] | 2008-07-28
0 | AKL | 398 | AKL-008-021 |  | AKL-008-021-A | Totara Heights | Manukau City |  | TIER_1_ALL | ACTIVE | RSR | A6 | P4C | green |  |  | 7 | 7 |  | -37.0069 | 174.8973 |  |  |  |  | Microwave | AKL-008-018-A | [5 empty] | 2009-05-13 | [5 empty] | 2007-08-14 | 3 | 2008-06-28 | 2008-06-28 |  |  | 2008-05-31 | 2007-07-01 | 3 | 2008-05-31 | 2008-06-30 |  |  |  | 2008-11-20 |  |  | 2008-11-20 | 2008-10-17 |  | 2008-04-29 |  | 2008-06-28 | 1 | 3 | 2008-06-28 | 2008-06-28 | [6 empty] | 2008-12-10 | 2008-12-19 | 2008-12-19 |  | 2009-01-28 | 2009-01-22 | [8 empty] | 2009-02-19 | 2009-02-26 | 2009-02-19 |  |  |  |  | Site On Air |  | 2009-02-26 | [17 empty] | FALSE |  | 2679204 | 6464350 | Streetlight swap, Cnr David Ave & Orams Rd Manukau City, Auckland |  |  | CELLSITE |  |  | 2014-09-12 | [5 empty] | 2008-11-19 | [8 empty] | 2007-07-23
0 | AKL | 399 | AKL-008-024 |  | AKL-008-024-A | Otara West | Manukau City |  | TIER_1_ALL | ACTIVE | RT | B6 | NOPOLE | grey |  |  | 23.8 | 23.8 |  | -36.9583 | 174.8534 |  |  |  |  | Microwave | AKL-008-018-A | [5 empty] | 2009-05-12 | [5 empty] | 2008-11-18 | 1 | 2008-11-18 | 2008-11-18 |  |  | 2009-03-30 | 2009-03-31 | 1 | 2009-05-29 | 2009-09-15 |  | 2008-11-27 |  | 2009-02-27 |  |  | 2009-02-27 | 2009-02-25 | 2009-02-13 | 2009-02-13 |  | 2009-03-11 | 2 | 1 | 2009-05-08 | 2009-05-11 | [6 empty] | 2009-04-27 | 2009-06-23 | 2009-06-23 |  | 2009-06-30 | 2009-07-02 | [8 empty] | 2009-07-02 | 2009-07-01 | 2009-07-02 |  |  |  |  | (Jun03 DJ) On track SOA Jun30. (Jun10 DJ) CI bumped 1wk. Holding for SOA Jun30 (Jun18 DJ) still holding SOA Jun30. (Jun24 DJ) on track SOA Jun30. (Jul01 DJ) on track SOA Jul01 |  | 2009-06-30 | [17 empty] | FALSE |  | 2675415 | 6469833 | 1 Bairds Rd, Otahuhu, Auckland |  |  | CELLSITE |  |  | 2014-09-12 |  |  |  |  | 2009-04-27 | 2009-04-06 | [8 empty] | 2008-10-10
0 | AKL | 400 | AKL-008-026 |  | AKL-008-026-H | Golflands | Manukau City |  | TIER_1_ALL | ACTIVE | GF | A6 | P3 | grey |  |  | 25 | 25 |  | -36.9176 | 174.899 |  |  |  |  | Microwave | AKL-008-045-A | [5 empty] | 2009-05-12 | [5 empty] | 2008-08-29 | 1 | 2008-08-29 | 2008-08-29 |  |  | 2008-07-31 | 2008-07-23 | 1 | 2008-07-31 | 2008-07-23 |  |  |  | 2008-10-17 |  |  | 2008-10-17 | 2008-10-17 |  | 2008-09-26 |  | 2008-10-21 | 1 | 1 | 2008-10-21 | 2008-10-21 | 2009-02-18 | [5 empty] | 2008-11-03 | 2009-02-27 | 2009-02-23 |  | 2009-02-27 | 2009-02-23 | [8 empty] | 2009-04-07 | 2009-04-09 | 2009-04-07 |  |  |  |  | (Mar27 DJ) f'cst SOA Apr6 |  | 2009-04-09 |  |  |  |  | 2009-02-18 | 2009-02-18 | [11 empty] | FALSE |  | 2679578 | 6474258 | 47 Ben Lomond Cres, Pakuranga, Auckland |  |  | CELLSITE |  |  | 2014-09-12 | [5 empty] | 2008-10-30 | [8 empty] | 2008-08-13
0 | AKL | 401 | AKL-008-027 |  | AKL-008-027-B | Cockle Bay | Manukau City |  | TIER_1_ALL | ACTIVE | COLO | Ab | NOPOLE | grey |  | COLO |  |  |  | -36.9064 | 174.9401 | [17 empty] | 2008-01-21 | 2 | 2009-11-11 | 2009-11-11 |  |  | 2007-12-03 | 2007-12-03 | 1 | 2010-04-30 | 2010-04-27 |  |  |  | 2008-05-31 |  |  | 2009-12-18 | 2009-11-27 |  | 2009-10-21 |  | 2009-12-17 | 1 |  | 2009-12-16 | 2009-12-17 | [5 empty] | 2010-04-27 | 2010-04-27 | 2010-05-07 | 2010-05-10 |  | 2010-05-21 | 2010-05-19 | [8 empty] | 2010-05-19 | 2010-05-26 | 2010-05-19 |  |  |  |  | Woosh confirmed 1.4 degs deflection ok. Plans being revised for S127 to show dishes between antenna to allow LOS. Meeting with Woosh 19/11. Generic Woosh Lease Agreement being modified to bring in line with other co-lo leases and to account for 1.5degs deflection clause (as deflection changed to 1.5 with cable ladder). Woosh Brown-out starts 18Dec. Lease still being finalised with Woosh 23.12. Email from Woosh giving permission to share but condition requiring pole swap should they ever require WiMax network. Meeting with Woosh 28/01 & will ask for early access and to move dish early. 14/4 - Lease with Steven Fast - yet to be executed. 19/04 Steven not to execute until budget approved. Commenced with build 4 May - construction underway with completion due 21 May | WO | 2010-05-26 | [17 empty] | FALSE |  | 2683264 | 6475415 | 30 Sandspit Rd Cockle Bay Auckland |  |  | CELLSITE | [7 empty] | 2010-04-30 | 2010-04-27 | [8 empty] | 2007-10-12
0 | AKL | 402 | AKL-008-028 |  | AKL-008-028-D | Highland Park | Manukau City |  | TIER_1_ALL | ACTIVE | GF | A | P2 | grey |  |  | 20 | 20 |  | -36.8989 | 174.9049 |  |  |  |  | Leased Line, Microwave | AKL-007-106-A, AKL-008-026-H | [11 empty] | 2008-09-11 | 2 | 2008-10-31 | 2008-10-31 |  |  | 2009-01-16 | 2009-01-13 | 2 | 2009-02-13 | 2009-03-23 |  |  |  | 2009-01-22 |  |  | 2009-01-22 | 2009-01-21 |  | 2008-10-07 |  | 2009-01-09 | 1 | 1 | 2009-01-09 | 2009-01-09 | 2009-01-30 | [5 empty] | 2009-02-05 | 2009-03-10 | 2009-02-27 |  | 2009-03-06 | 2009-03-06 | [8 empty] | 2009-05-25 | 2009-05-29 | 2009-05-25 |  |  |  |  | (May14 DJ) Telecom fcst LL RFS May20, dependency for F'cst SOA May29. |  | 2009-05-29 | [5 empty] | 2009-01-30 | [11 empty] | FALSE |  | 2680151 | 6476324 | Highland Park 499 Pakuranga Rd Highland Park Auckland |  |  | CELLSITE | [7 empty] | 2009-02-13 | 2009-02-05 | [8 empty] | 2008-08-19
0 | AKL | 403 | AKL-008-029 |  | AKL-008-029-D | Howick West | Manukau City |  | TIER_1_ALL | ACTIVE | GF | A | P2 | grey |  |  | 17 | 17 |  | -36.8995 | 174.9194 |  |  |  |  | Leased Line | AKL-007-106-A | [11 empty] | 2008-03-25 | 5 | 2009-04-02 | 2009-04-07 |  |  | 2008-04-21 | 2008-04-21 | 1 | 2008-04-21 | 2008-04-21 |  |  |  | 2008-10-31 |  |  | 2009-03-06 | 2009-03-13 |  | 2008-04-21 |  | 2008-09-29 | 2 | 3 | 2008-12-12 | 2008-12-12 | 2009-02-02 | [5 empty] | 2008-12-10 | 2009-02-27 | 2009-02-12 |  | 2009-02-27 | 2009-02-12 | [8 empty] | 2009-05-12 | 2009-05-15 | 2009-05-12 |  |  |  |  | On Air |  | 2009-05-15 |  |  |  |  | 2009-01-28 | 2009-02-02 | [11 empty] | FALSE |  | 2681439 | 6476222 | 6 Botany Road Howick Auckland |  |  | CELLSITE | [8 empty] | 2008-11-19 | [8 empty] | 2008-02-21
0 | AKL | 404 | AKL-008-030 |  | AKL-008-030-C | Pakuranga | Manukau City |  | TIER_1_ALL | ACTIVE | RT | B6 | NOPOLE | grey |  |  | 20.5 | 20.5 |  | -36.9125 | 174.8723 |  |  |  |  | Microwave | AKL-008-024-A | [5 empty] | 2009-05-12 | [5 empty] | 2008-03-20 | 10 | 2009-05-14 | 2009-05-14 |  |  | 2009-05-07 | 2009-05-04 | 6 | 2009-05-20 | 2009-05-20 | [6 empty] | 2009-03-19 | 2009-03-13 | 2009-03-20 | 2009-03-18 |  | 2009-04-30 | 2 | 9 | 2009-05-18 | 2009-05-19 | [5 empty] | 2009-05-25 | 2009-05-25 | 2009-06-19 | 2009-06-19 |  | 2009-07-07 | 2009-07-08 | [8 empty] | 2009-07-09 | 2009-07-10 | 2009-07-09 |  |  |  |  | On Air |  | 2009-07-10 | [17 empty] | FALSE |  | 2677208 | 6474873 | Corner Pakuranga Drive and Ti Rakau Drive Pakuranga |  |  | CELLSITE |  |  | 2014-08-12 |  |  |  |  | 2009-05-25 | 2009-05-25 | [8 empty] | 2008-02-20
0 | AKL | 405 | AKL-008-031 |  | AKL-008-031-B | Meadowlands | Manukau City |  | TIER_1_ALL | ACTIVE | RSR | A | P4C | green |  |  | 15 | 15 |  | -36.9147 | 174.9284 |  |  |  |  | Leased Line | AKL-007-106-A | [11 empty] | 2007-09-17 | 2 | 2008-04-24 | 2008-04-24 |  |  | 2008-06-30 | 2008-06-30 | 2 | 2008-06-30 | 2008-06-30 |  |  |  | 2008-06-30 |  |  | 2008-06-30 | 2008-07-03 |  | 2008-04-29 |  | 2008-05-22 | 1 | 2 | 2008-05-22 | 2008-05-22 | [6 empty] | 2008-08-01 | 2008-09-30 | 2008-09-22 |  | 2008-10-10 | 2008-09-24 | [8 empty] | 2009-04-24 | 2009-04-24 | 2009-04-24 |  |  |  |  | LL delivery slipped - F'cst SOA pushed to Apr24. LL due 14 Apr (JL 6Apr) (Apr23 DJ) On track |  | 2009-04-24 | [17 empty] | FALSE |  | 2682207 | 6474520 | Streetlight swap out 112 Whitford Rd Meadowlands Auckland |  |  | CELLSITE | [8 empty] | 2008-07-23 | [8 empty] | 2007-08-31
0 | AKL | 406 | AKL-008-032 |  | AKL-008-032-C | Dannemora | Manukau City |  | TIER_1_ALL | ACTIVE | RT | B6 | NOPOLE | grey |  |  | 11.8 | 11.8 |  | -36.9282 | 174.912 |  |  |  |  | Microwave | AKL-008-045-A | [11 empty] | 2008-08-19 | 6 | 2008-12-12 | 2008-12-12 |  |  | 2008-12-20 | 2008-12-18 | 6 | 2009-05-22 | 2009-05-25 |  |  |  | 2009-01-07 |  |  | 2009-01-07 | 2009-01-07 | 2008-12-30 | 2008-09-26 |  | 2008-10-24 | 3 | 5 | 2009-01-30 | 2009-01-30 | [5 empty] | 2009-05-28 | 2009-05-28 | 2009-06-26 | 2009-06-26 |  | 2009-07-17 | 2009-07-14 | [8 empty] | 2009-07-24 | 2009-07-30 | 2009-07-24 |  |  |  |  | On Air |  | 2009-07-30 | [17 empty] | FALSE |  | 2680707 | 6473051 | Paradice Ice Skating Cnr Ti Rakau Drive and Botany Road Botany Downs Auckland |  |  | CELLSITE |  |  | 2014-09-12 |  |  |  |  | 2009-05-28 | 2009-05-28 | [8 empty] | 2008-06-25
0 | AKL | 407 | AKL-008-033 |  | AKL-008-033-D | Half Moon Bay | Manukau City |  | TIER_1_ALL | ACTIVE | RSR | D | P4C | green |  |  |  | 9.4 |  | -36.8851 | 174.9005 |  |  |  |  | Microwave | AKL-007-113-A | [11 empty] | 2009-06-05 | 3 | 2009-08-21 | 2009-10-20 |  |  | 2009-09-28 | 2009-09-25 |  | 2009-10-02 | 2009-10-01 |  | 2009-09-29 |  | 2009-09-29 |  |  | 2009-09-29 | 2009-09-25 | 2009-06-15 | 2009-06-15 |  | 2009-06-23 | 1 | 2 | 2009-06-30 | 2009-06-23 | 2009-11-17 |  |  |  |  | 2010-01-11 | 2010-01-11 | 2010-01-18 | 2010-01-15 |  | 2010-01-20 | 2010-01-15 | [8 empty] | 2010-01-18 | 2010-01-18 | 2010-01-18 |  |  |  |  | Site in build, security camera may be fitted to site. Extra dish required as part of the lease line migration for Felton Matthews, extra DMR cable will be run at time of build but lease variation and installation will require a MAC. |  | 2010-01-18 |  |  |  |  | 2009-11-12 | 2009-11-17 | [11 empty] | FALSE |  | 2679791 | 6477866 | OS 25 Pigeon Mountain Road, Half Moon Bay |  |  | CELLSITE | [7 empty] | 2010-01-11 | 2010-01-11 | [8 empty] | 2009-06-04
0 | AKL | 408 | AKL-008-034 |  | AKL-008-034-D | Bucklands Beach South | Manukau City |  | TIER_1_ALL | ACTIVE | RSR | A | P4C | green | [5 empty] | -36.8827 | 174.9139 |  |  |  |  | Leased Line | AKL-007-106-A | [11 empty] | 2008-05-22 | 2 | 2008-07-07 | 2008-07-07 |  |  | 2008-06-30 | 2008-06-30 | 2 | 2008-06-30 | 2008-06-30 |  |  |  | 2008-11-28 |  |  | 2008-12-19 | 2008-11-28 |  | 2008-06-05 |  | 2008-07-08 | 2 | 2 | 2009-03-12 | 2009-03-12 | 2008-11-07 | [5 empty] | 2009-02-16 | 2009-04-07 | 2009-04-07 |  | 2009-04-07 | 2009-04-07 | [8 empty] | 2009-04-22 | 2009-04-24 | 2009-04-22 |  |  |  |  | On Air |  | 2009-04-24 | [5 empty] | 2008-11-07 | [11 empty] | FALSE |  | 2680993 | 6478097 | O/s 45 Macleans Rd, Howick, Auckland |  |  | CELLSITE | [7 empty] | 2009-02-12 | 2009-02-11 | [8 empty] | 2008-04-04
0 | AKL | 409 | AKL-008-035 |  | AKL-008-035-C | Farm Cove | Manukau City |  | TIER_1_ALL | ACTIVE | RSR | A | P4C | green | [5 empty] | -36.8979 | 174.8875 |  |  |  |  | Microwave, Leased Line | AKL-008-028-D, AKL-007-106-A | [5 empty] | 2009-04-15 | [5 empty] | 2008-05-22 | 3 | 2008-11-07 | 2008-11-07 |  |  | 2008-06-30 | 2008-06-30 | 3 | 2008-06-30 | 2008-06-30 |  |  |  | 2009-03-06 |  |  | 2009-03-06 | 2009-03-06 |  | 2008-06-05 |  | 2008-07-17 | 1 | 2 | 2008-07-17 | 2008-07-17 | 2008-10-21 |  |  |  |  | 2009-03-11 | 2009-03-11 | 2009-03-20 | 2009-03-19 |  | 2009-03-20 | 2009-03-19 | [8 empty] | 2009-04-08 | 2009-04-20 | 2009-04-08 |  |  |  |  | On Air |  | 2009-04-20 | [5 empty] | 2008-10-21 | [11 empty] | FALSE |  | 2678604 | 6476467 | O/s 2 Elimar Drv, Farm Cove, Auckland |  |  | CELLSITE | [7 empty] | 2009-03-13 | 2009-03-09 | [8 empty] | 2008-04-04
0 | AKL | 410 | AKL-008-036 |  | AKL-008-036-J | Manukau Junction | Manukau City |  | TIER_1_ALL | ACTIVE | GF | A6 | P3 | grey |  |  | 20 | 20 |  | -36.9938 | 174.8882 |  |  |  |  | Microwave | AKL-008-018-A | [5 empty] | 2009-05-13 | [5 empty] | 2008-04-22 | 1 |  | 2008-04-22 |  |  | 2008-07-31 | 2008-08-20 | 1 | 2008-07-31 | 2008-08-20 |  |  |  | 2008-09-30 |  |  | 2008-09-30 | 2008-09-18 |  | 2008-04-29 |  | 2008-06-27 | 2 | 1 | 2008-09-16 | 2008-09-16 | [6 empty] | 2008-10-01 | 2008-10-08 | 2008-10-08 |  | 2008-11-10 | 2008-11-10 | [8 empty] | 2008-12-31 | 2009-02-27 | 2008-12-31 |  |  |  |  | None |  | 2009-02-27 | [17 empty] | FALSE |  | 2678426 | 6465825 | 20 Lakewood Court Manukau City Auckland |  |  | CELLSITE |  |  | 2014-09-12 | [5 empty] | 2008-09-30 | [8 empty] | 2008-03-12
0 | AKL | 411 | AKL-008-037 |  | AKL-008-037-A | Weymouth | Manukau City |  | TIER_1_ALL | ACTIVE | GF | A | P2 | grey |  |  | 15 | 15 |  | -37.0424 | 174.8826 |  |  |  |  | Microwave | AKL-009-004-B | FALSE | FALSE |  |  | FALSE | 2009-05-13 | [5 empty] | 2008-06-11 | 2 |  | 2008-06-11 |  |  | 2007-11-30 | 2007-11-30 | 1 | 2007-11-30 | 2007-11-30 |  |  |  | 2008-09-30 |  |  | 2008-09-30 | 2008-09-22 |  | 2008-01-21 |  | 2008-04-17 | 2 | 2 | 2008-09-26 | 2008-09-26 | [6 empty] | 2008-09-25 | 2008-10-17 | 2008-10-13 |  | 2008-10-24 | 2008-10-17 | [8 empty] | 2008-11-24 | 2008-12-08 | 2008-11-24 |  |  |  |  | None |  | 2008-11-24 | [17 empty] | FALSE |  | 2677811 | 6460443 | Weymouth Cosmopolitan Club 151 Sykes road Auckland |  |  | CELLSITE |  |  | 2015-12-10 | [5 empty] | 2008-09-22 | [8 empty] | 2007-08-13
0 | AKL | 412 | AKL-008-038 |  | AKL-008-038-A | Manurewa East | Manukau City |  | TIER_1_ALL | ACTIVE | RSR | A6 | P4C | green |  |  | 13.5 | 13.5 |  | -37.0145 | 174.9066 |  |  |  |  | Microwave, Microwave | AKL-008-018-A, AKL-008-018-A | [5 empty] | 2009-05-12, 2009-03-31 | [5 empty] | 2007-09-13 | 2 | 2008-07-09 | 2008-07-09 |  |  | 2008-05-31 | 2008-06-30 | 2 | 2008-05-31 | 2008-06-30 |  |  |  | 2009-03-13 |  |  | 2009-03-13 | 2009-03-02 |  | 2008-12-23 |  | 2008-06-25 | 4 | 2 | 2008-12-19 | 2008-12-19 | 2009-03-02 |  |  |  |  | 2009-03-24 | 2009-03-13 | 2009-04-24 | 2009-04-16 |  | 2009-04-24 | 2009-04-17 | [8 empty] | 2009-05-26 | 2009-05-29 | 2009-05-26 |  |  |  |  | On Air |  | 2009-05-29 |  |  |  |  | 2009-02-28 | 2009-03-02 | [11 empty] | FALSE |  | 2680016 | 6463488 | Streetlight replacement o/s 98 Hill Rd, Manurewa East, Manukau, Auckland |  |  | CELLSITE |  |  | 2014-09-12 |  |  |  |  | 2009-03-13 | 2009-03-09 | [8 empty] | 2007-09-06
0 | AKL | 413 | AKL-008-039 |  | AKL-008-039-C | Puhinui | Manukau City |  | TIER_1_ALL | ACTIVE | GF | A6 | P2 | grey |  |  | 20 | 20 |  | -36.9883 | 174.8662 |  |  |  |  | Microwave | AKL-008-004-A | [5 empty] | 2009-05-13 | [5 empty] | 2008-09-02 | 1 | 2008-09-02 | 2008-09-02 |  |  |  | 2008-10-14 | 1 | 2009-01-30 | 2009-09-15 |  |  |  | 2008-10-17 |  |  | 2008-10-17 | 2008-10-17 |  | 2008-09-26 |  | 2008-10-17 | 1 | 1 | 2008-10-17 | 2008-10-17 | 2008-12-19 | [5 empty] | 2009-01-07 | 2009-02-27 | 2009-01-28 |  | 2009-01-29 | 2009-02-02 | [8 empty] | 2009-02-03 | 2009-02-26 | 2009-02-03 |  |  |  |  | Site On Air |  | 2009-02-26 |  |  |  |  | 2008-12-22 | 2008-12-19 | [11 empty] | FALSE |  | 2676482 | 6466480 | Forward Plastics Limited 50-52 Grayson Avenue Puhinui Auckland |  |  | CELLSITE |  |  | 2014-09-12 | [5 empty] | 2008-11-19 | [8 empty] | 2008-08-14
0 | AKL | 414 | AKL-008-041 |  | AKL-008-041-H | 9 Airpark Drive | Manukau City |  | TIER_1_ALL | ACTIVE | GF | Ab6 | P3 | grey | [5 empty] | -36.9855 | 174.7821 |  |  |  |  | Microwave | AKL-008-008-C | [6 empty] | 2009-09-03 | 2009-09-03 |  |  |  | 2009-09-08 | 2 | 2009-10-15 | 2009-10-19 |  |  | 2009-09-30 | 2009-09-29 |  | 2009-11-20 | 2009-11-19 |  | 2009-09-29 |  | 2009-11-20 |  |  | 2009-11-20 | 2009-11-24 | 2009-10-23 | 2009-09-24 |  | 2009-10-23 | 1 |  | 2009-10-23 | 2009-10-23 | 2009-01-30 |  |  |  |  | 2009-11-30 | 2009-11-30 | 2009-12-22 | 2009-12-22 |  | 2010-01-25 | 2010-01-22 | [8 empty] | 2010-01-25 | 2010-01-28 | 2010-01-25 |  |  |  |  | Site in build |  | 2010-01-28 |  |  |  |  | 2009-01-30 | 2009-01-30 | [11 empty] | FALSE |  | 2669004 | 6466950 | 9 Airpark Drive, Ihumatao |  |  | CELLSITE |  |  | 2014-08-12 |  |  |  |  | 2009-11-30 | 2009-11-30 | [8 empty] | 2009-09-03
0 | AKL | 415 | AKL-008-042 |  | AKL-008-042-A | International Terminal | Manukau City |  | TIER_1_ALL | ACTIVE | RT | B6 | NOPOLE | grey |  |  | 28 | 28 |  | -37.0053 | 174.7832 |  |  |  |  | Microwave | AKL-008-018-A | [5 empty] | 2009-05-12 | [5 empty] | 2007-07-05 | 1 |  | 2007-07-05 |  |  | 2007-10-05 | 2007-10-05 | 1 | 2007-10-05 | 2007-10-05 |  |  |  | 2007-04-01 |  |  | 2007-04-01 | 2007-04-01 |  | 2007-10-24 |  | 2007-10-25 | 1 | 1 | 2007-10-25 | 2007-10-25 | [6 empty] | 2007-11-30 | 2008-01-11 | 2008-01-11 |  | 2008-01-16 | 2008-01-16 | [8 empty] | 2008-01-16 |  | 2008-01-16 |  |  |  |  | None |  | 2008-01-16 | [17 empty] | FALSE |  | 2669062 | 6464748 | Airport |  |  | CELLSITE |  |  | 2014-08-12 | [5 empty] | 2007-11-30 | [8 empty] | 2007-06-19
0 | AKL | 416 | AKL-008-043 | 007-104 | AKL-008-043-C | East Tamaki | Manukau City | 3 | TIER_1_ALL | ACTIVE | GF | A6 | P3 | grey |  |  | 25 | 25 |  | -36.9593 | 174.8939 |  |  |  |  | Microwave | AKL-008-018-A | FALSE | FALSE |  |  | FALSE | 2009-05-12 | [5 empty] | 2008-06-11 | 3 | 2008-06-11 | 2011-07-21 |  |  | 2008-08-31 | 2008-05-30 | 3 | 2008-08-31 | 2008-05-30 |  |  |  | 2008-09-30 |  |  | 2008-09-08 | 2008-09-08 |  | 2008-07-02 |  | 2008-07-16 | 6 |  | 2008-07-29 | 2011-10-18 | 2008-12-23 | [5 empty] | 2008-12-10 | 2009-02-03 | 2009-02-03 |  | 2009-02-04 | 2009-02-03 | [8 empty] | 2009-03-19 | 2009-03-21 | 2009-03-19 |  |  |  |  | (Mar19 DJ) Site On Air Linking to Flat Bush REQUIRE : 300mmØ |  | 2009-03-21 |  |  |  |  | 2008-12-31 | 2008-12-23 | [11 empty] | FALSE |  | 2679020 | 6469640 | 22 Ormiston Road East Tamaki Auckland |  |  | CELLSITE |  |  | 2014-09-12 | [5 empty] | 2008-12-05 | [8 empty] | 2008-05-06
0 | AKL | 417 | AKL-008-044 |  | AKL-008-044-E | Te Irirangi | Manukau City |  | TIER_1_ALL | ACTIVE | GF | A6 | P3 | grey |  |  | 25 | 25 |  | -36.9517 | 174.9051 |  |  |  |  | Microwave | AKL-008-043-C | [5 empty] | 2009-05-13 | [5 empty] | 2008-07-24 | 1 | 2008-07-24 | 2008-07-24 |  |  | 2008-07-31 | 2008-08-26 | 1 | 2008-07-31 | 2008-08-26 | [7 empty] | 2008-09-24 |  | 2008-09-08 |  | 2008-09-29 | 1 | 1 | 2008-09-29 | 2008-09-29 | 2008-12-23 | [5 empty] | 2008-10-28 | 2009-02-18 | 2009-02-18 |  | 2009-02-20 | 2009-02-19 | [8 empty] | 2009-03-19 | 2009-03-21 | 2009-03-19 |  |  |  |  | (Mar19 DJ) Site On Air |  | 2009-03-21 |  |  |  |  | 2008-12-23 | 2008-12-23 | [11 empty] | FALSE |  | 2680038 | 6470464 | Street Properties, 11 Reg Savory Plc, Te Irirangi, Auckland |  |  | CELLSITE |  |  | 2014-09-12 | [5 empty] | 2008-10-24 | [8 empty] | 2008-06-18
0 | AKL | 418 | AKL-008-045 |  | AKL-008-045-A | Greenmount | Manukau City |  | TIER_1_ALL | ACTIVE | GF | A6 | P3 | grey |  |  | 20 | 20 |  | -36.9313 | 174.8982 |  |  |  |  | Microwave, Leased Line | AKL-008-014-C, AKL-007-106-A | [11 empty] | 2007-08-21 | 5 |  |  |  |  | 2008-01-18 | 2008-01-18 | 2 | 2008-01-18 | 2008-01-18 | DISCRETIONARY_FULL |  | 2011-07-20 | 2008-07-30 | 2011-08-17 | 4 | 2008-07-30 | 2011-08-18 |  | 2007-11-20 |  | 2008-04-25 | 1 | 3 | 2008-04-25 | 2008-04-25 | [6 empty] | 2008-07-21 | 2008-08-22 | 2008-08-22 |  | 2008-08-29 | 2008-08-28 | [8 empty] | 2009-03-25 | 2009-04-10 | 2009-03-25 |  |  |  |  | On Air |  | 2009-04-10 | [17 empty] | FALSE |  | 2679476 | 6472742 | 147 Harris Road, Auckland |  | Lodged on the 20.7.11. Approved on the 17.8.2011. - 17/08/2011 resource consent number: 39181 - 18/08/2011 | CELLSITE |  |  | 2014-09-12 | [5 empty] | 2008-07-03 | [8 empty] | 2007-08-28
0 | AKL | 419 | AKL-008-046 |  | AKL-008-046-F | Picton Centre | Manukau City |  | TIER_1_ALL | ACTIVE | RT | B | NOPOLE | grey | [5 empty] | -36.8948 | 174.9332 | [17 empty] | 2009-10-06 | 4 | 2010-03-10 | 2010-03-10 |  |  | 2009-12-04 | 2009-12-07 | 4 | 2009-12-04 | 2009-12-07 |  | 2009-11-05 |  | 2009-12-07 |  |  | 2009-12-07 | 2009-11-27 | 2009-10-26 | 2009-10-20 |  | 2009-12-23 | 2 | 4 | 2010-03-18 | 2010-03-18 | [5 empty] | 2010-05-12 | 2010-05-12 | 2010-06-11 | 2010-06-08 |  | 2010-06-14 | 2010-06-15 | [8 empty] | 2010-06-15 | 2010-06-15 | 2010-06-15 |  |  |  |  | ALL CO-SITE's approved. BC required! Cabinets to be painted same colour as building. NRL testing required once site complete. BC lodged 7/01/2010 and due 29/01. BC complete. Police have lodged co-site with RF have approved but require our ladder moved, PD & CD being revised. 10 May construction commenced. On track |  | 2010-06-15 | [17 empty] | FALSE |  | 2682676 | 6476716 | 120 Picton Street Howick Manukau City |  |  | CELLSITE | [7 empty] | 2010-02-15 | 2010-05-12 | [8 empty] | 2009-09-07
0 | AKL | 420 | AKL-008-047 |  | AKL-008-047-A | Sunnyhills | Manukau City |  | TIER_1_ALL | ACTIVE | GF | A | P1 | green |  |  | 15.8 | 15.8 |  | -36.9086 | 174.884 |  |  |  |  | Microwave, Leased Line | AKL-008-045-A, AKL-007-106-A | [5 empty] | 2009-05-12 | [5 empty] | 2007-07-15 | 2 |  | 2008-07-21 |  |  | 2007-03-30 | 2007-03-30 | 2 | 2007-03-30 | 2007-03-30 |  |  |  | 2008-08-31 |  |  | 2008-08-31 | 2008-08-29 |  | 2007-10-31 |  | 2008-05-20 | 1 | 2 | 2008-05-20 | 2008-05-20 | [6 empty] | 2008-09-15 | 2008-10-17 | 2008-10-17 |  | 2008-10-23 | 2008-10-17 | [8 empty] | 2009-03-19 | 2009-03-18 | 2009-03-19 |  |  |  |  | On Air |  | 2009-03-18 | [17 empty] | FALSE |  | 2678261 | 6475289 | 2 Johns Lane Auckland |  |  | CELLSITE | [8 empty] | 2008-09-18 | [8 empty] | 2007-03-30
0 | AKL | 421 | AKL-008-049 |  | AKL-008-049-D | Eastern Beach | Manukau City |  | TIER_1_ALL | ACTIVE | RSR | D | P4C | green |  |  |  | 11.7 |  | -36.8689 | 174.9059 |  |  |  |  | Microwave | AKL-007-113-A | [11 empty] | 2009-06-05 | 1 | 2009-06-09 | 2009-06-05 |  |  | 2009-09-28 | 2009-09-25 |  | 2009-10-21 | 2009-10-01 |  | 2009-09-29 |  | 2009-09-29 |  |  | 2009-09-29 | 2009-09-25 | 2009-06-15 | 2009-06-15 |  | 2009-06-26 | 1 | 1 | 2009-06-30 | 2009-06-26 | 2009-10-23 |  |  |  |  | 2010-01-11 | 2010-01-11 | 2010-01-18 | 2010-01-15 |  | 2010-01-20 | 2010-01-15 | [8 empty] | 2010-01-15 | 2010-01-25 | 2010-01-15 |  |  |  |  | Site in build, security camera may be fitted to site. |  | 2010-01-25 |  |  |  |  | 2009-10-23 | 2009-10-23 | [11 empty] | FALSE |  | 2680313 | 6479651 | OS 145 Clovelly Road |  |  | CELLSITE | [7 empty] | 2010-01-11 | 2010-01-11 | [8 empty] | 2009-06-04
0 | AKL | 422 | AKL-008-055 |  | AKL-008-055-A | Domestic Terminal | Manukau City |  | TIER_1_ALL | ACTIVE | RT | B6 | NOPOLE | grey |  |  | 11 | 11 |  | -37.0059 | 174.7897 |  |  |  |  | Leased Line, Microwave | AKL-007-106-A, AKL-008-042-A | [5 empty] | 2009-05-13 | [5 empty] | 2007-07-05 | 1 |  | 2007-07-05 |  |  | 2007-10-05 | 2007-10-05 | 1 | 2007-10-05 | 2007-10-05 |  |  |  | 2007-07-01 |  |  | 2007-07-01 | 2007-07-01 |  | 2008-01-21 |  | 2007-10-25 | 1 | 1 | 2007-10-25 | 2007-10-25 | [6 empty] | 2007-11-26 | 2007-12-07 | 2007-12-07 |  | 2007-12-18 | 2007-12-18 | [8 empty] | 2008-02-27 |  | 2008-02-27 |  |  |  |  | None |  | 2008-02-27 | [17 empty] | FALSE |  | 2669639 | 6464670 | Airport |  |  | CELLSITE |  |  | 2014-08-12 | [5 empty] | 2007-11-26 | [8 empty] | 2007-06-29
0 | AKL | 423 | AKL-008-056 |  | AKL-008-056-B | Huntington Park | Manukau City |  | TIER_1_ALL | ACTIVE | RSR | A6 | P4C | green |  |  | 11 | 11 |  | -36.9358 | 174.9146 |  |  |  |  | Leased Line | AKL-007-106-A | [11 empty] | 2007-09-28 | 3 |  | 2008-10-16 |  |  | 2008-05-31 | 2008-06-30 | 2 | 2008-05-31 | 2008-06-30 |  |  |  | 2008-11-14 |  |  | 2008-11-14 | 2008-11-14 |  | 2008-07-07 |  | 2008-09-19 | 1 | 2 | 2008-09-19 | 2008-09-19 | [6 empty] | 2008-12-04 | 2008-12-19 | 2008-12-18 |  | 2008-12-19 | 2008-12-19 | [8 empty] | 2009-04-08 | 2009-04-09 | 2009-04-08 |  |  |  |  | On Air |  | 2009-04-09 | [17 empty] | FALSE |  | 2680918 | 6472213 | Streetlight swapout Opposite 557 Chapel Road Huntington Park Manukau City |  |  | CELLSITE |  |  | 2014-09-12 | [5 empty] | 2008-12-02 | [8 empty] | 2007-09-17
0 | AKL | 424 | AKL-008-058 |  | AKL-008-058-D | Homai Central | Manukau City | 3 | TIER_1_ALL | ACTIVE | GF | A6 | P2 | grey |  |  | 20 | 20 |  | -37.0131 | 174.8746 |  |  |  |  | Microwave | AKL-008-018-A | FALSE | FALSE |  |  | FALSE | 2009-05-12 | [5 empty] | 2008-03-17 | 1 |  | 2008-03-17 |  |  | 2008-07-31 | 2008-07-03 | 1 | 2008-07-31 | 2008-07-03 |  |  |  | 2008-11-12 |  |  | 2008-11-12 | 2008-11-18 |  | 2008-04-29 |  | 2008-07-23 | 1 | 1 | 2008-07-23 | 2008-07-23 | 2008-12-19 | [5 empty] | 2008-12-08 | 2009-01-23 | 2009-01-20 |  | 2009-01-27 | 2009-01-19 | [8 empty] | 2009-02-20 | 2009-02-26 | 2009-02-20 |  |  |  |  | On Air Linking to the Gardens REQUIRE 300mmØ |  | 2009-02-26 |  |  |  |  | 2008-12-19 | 2008-12-19 | [11 empty] | FALSE |  | 2677174 | 6463713 | 12 Dalgety Drive Homai Central Auckland |  |  | CELLSITE |  |  | 2014-09-12 | [5 empty] | 2008-11-19 | [8 empty] | 2008-02-15
0 | AKL | 425 | AKL-008-059 |  | AKL-008-059-B | Manurewa Central | Manukau City |  | TIER_1_ALL | ACTIVE | RSR | A6 | P4C | green |  |  | 14 | 14 |  | -37.0367 | 174.8895 |  |  |  |  | Microwave | AKL-009-005-B | [5 empty] | 2009-05-13 | [5 empty] | 2008-02-15 | 2 |  | 2008-04-23 |  |  | 2008-06-30 | 2008-06-30 | 1 | 2008-06-30 | 2008-06-30 |  |  |  | 2008-06-30 |  |  | 2008-06-30 | 2008-06-13 |  | 2008-04-29 |  | 2008-05-20 | 2 | 2 | 2008-09-12 | 2008-09-12 | [6 empty] | 2008-09-03 | 2008-09-30 | 2008-09-23 |  | 2008-10-10 | 2008-09-23 | [8 empty] | 2008-11-21 | 2008-12-10 | 2008-11-21 |  |  |  |  | None |  | 2008-11-26 | [17 empty] | FALSE |  | 2678444 | 6461064 | 101 Friedlanders Road Manurewa Central Auckland |  |  | CELLSITE |  |  | 2014-09-12 | [5 empty] | 2008-07-30 | [8 empty] | 2008-01-31
0 | AKL | 426 | AKL-008-060 |  | AKL-008-060-B | Favona | Manukau City |  | TIER_1_ALL | ACTIVE | RT | B6 | NOPOLE | grey |  |  | 15 | 15 |  | -36.9556 | 174.8044 |  |  |  |  | Microwave, Leased Line | AKL-007-114-D, AKL-007-106-A | [11 empty] | 2008-02-20 | 3 | 2008-10-08 | 2008-10-08 |  |  | 2008-05-31 | 2008-05-14 | 1 | 2008-05-31 | 2008-05-14 |  |  |  | 2008-08-31 |  |  | 2008-08-31 | 2008-08-25 |  | 2008-04-01 |  | 2008-07-29 | 2 | 2 | 2008-10-06 | 2008-10-06 | [6 empty] | 2008-09-11 | 2008-10-17 | 2008-10-17 |  | 2009-01-12 | 2009-01-09 | [8 empty] | 2009-03-02 | 2009-03-11 | 2009-03-02 |  |  |  |  | (Mar2 DJ) Site On Air |  | 2009-03-11 | [17 empty] | FALSE |  | 2671058 | 6470221 | Assembly of God Church 38 Robertson Road Favona Auckland |  |  | CELLSITE |  |  | 2014-08-12 | [5 empty] | 2008-09-01 | [8 empty] | 2007-12-27
0 | AKL | 427 | AKL-008-061 |  | AKL-008-061-D | Tidal Rd | Manukau City |  | TIER_1_ALL | ACTIVE | GF | A6 | P3 | grey |  |  | 23.8 | 23.8 |  | -36.978 | 174.8233 |  |  |  |  | Microwave | AKL-008-024-A | [11 empty] | 2008-09-12 | 2 | 2009-02-18 | 2009-02-18 |  |  |  | 2008-09-22 | 2 | 2009-04-14 | 2009-04-14 |  | 2009-02-20 |  | 2009-04-03 |  |  | 2009-04-17 | 2009-04-21 | 2009-04-14 | 2009-04-15 |  | 2009-05-05 | 2 | 2 | 2009-04-30 | 2009-06-16 | 2009-02-02 |  |  |  |  | 2009-05-18 | 2009-05-18 | 2009-07-24 | 2009-07-24 |  | 2009-07-24 | 2009-07-24 | [8 empty] | 2009-07-31 | 2009-07-30 | 2009-07-31 |  |  |  |  | On Air |  | 2009-07-30 |  |  |  |  | 2009-01-19 | 2009-02-02 | [11 empty] | FALSE |  | 2672687 | 6467696 | 65 Tidal Rd Mangere Auckland |  |  | CELLSITE |  |  | 2014-09-12 |  |  |  |  | 2009-05-18 | 2009-05-18 | [8 empty] | 2008-09-01
0 | AKL | 428 | AKL-008-064 |  | AKL-008-064-A | Manurewa West | Manukau City |  | TIER_1_ALL | ACTIVE | RT | B6 | NOPOLE | grey |  |  | 9.2 | 9.2 |  | -37.0295 | 174.881 |  |  |  |  | Leased Line | AKL-007-106-A | [11 empty] | 2007-09-07 | 1 |  | 2007-09-07 |  |  | 2007-08-27 | 2007-08-27 | 1 | 2007-08-27 | 2007-08-27 |  |  |  | 2008-05-31 |  |  | 2008-05-31 | 2008-05-30 |  | 2007-10-23 |  | 2007-11-22 | 2 | 1 | 2007-11-22 | 2008-07-14 | [6 empty] | 2008-06-12 | 2008-06-27 | 2008-06-27 |  | 2008-07-04 | 2008-07-22 | [8 empty] | 2009-03-10 | 2009-03-09 | 2009-03-10 |  |  |  |  | On Air |  | 2009-03-09 | [17 empty] | FALSE |  | 2677706 | 6461877 | Manurewa Squash Club 171 Weymouth road Manurewa |  |  | CELLSITE |  |  | 2014-09-12 | [5 empty] | 2008-06-03 | [8 empty] | 2007-08-27
0 | AKL | 429 | AKL-008-066 |  | AKL-008-066-I | Botany East | Manukau City |  | TIER_1_ALL | ACTIVE | RSR | D | P4C | green |  |  | 9.9 | 9.9 |  | -36.9093 | 174.9177 | [17 empty] | 2009-06-12 | 2 | 2009-06-12 | 2009-07-13 |  |  | 2009-08-21 | 2009-07-31 |  | 2009-10-16 | 2009-08-21 |  | 2009-08-03 |  | 2009-08-03 |  |  | 2009-08-03 | 2009-07-31 | 2009-06-22 | 2009-06-23 |  | 2009-06-26 | 2 | 2 | 2009-07-10 | 2009-08-10 | 2009-09-25 |  |  |  |  | 2009-10-20 | 2009-10-20 | 2009-11-09 | 2009-11-02 |  | 2009-11-10 | 2009-11-02 | [8 empty] | 2009-11-09 | 2009-11-13 | 2009-11-09 |  |  |  |  | On Air |  | 2009-11-13 |  |  |  |  | 2009-09-25 | 2009-09-25 | [11 empty] | FALSE |  | 2681259 | 6475141 | OS 106 Botany Road, Howick |  |  | CELLSITE |  |  | 2015-12-10 |  |  |  |  | 2009-10-20 | 2009-10-20 | [8 empty] | 2009-06-04
0 | AKL | 430 | AKL-008-068 | Beachlands South |  |  | Manukau City |  | TIER_1_ALL | [83 empty] | Beachlands Vodafone Colocation to be able to cover the
0 | AKL | 431 | AKL-008-069 | Clevedon | AKL-008-069-B | Clevedon VF Colo | Manukau City | 22 | TIER_4 | ACTIVE | COLO | DU | COLO |  | STACK_A | COLO | 20 | 20 | 1 | -36.988 | 175.0562 | 2010-06-15 | 2012-05-29 | 2010-06-25 | 2010-06-21 | Fibre Optic | AKL-008-091-A | FALSE | FALSE |  | 2010-07-02 | FALSE |  | 2012-08-08 | 2012-08-08 | 2012-08-09 | 2012-08-09 | 2012-08-30 | 2012-09-04 | 3 | 2015-02-23 | 2015-04-30 | 2015-04-24 | 2015-03-31 | 2015-07-07 | 2015-07-03 |  | 2015-07-28 | 2015-07-03 | DISCRETIONARY_FULL | 2015-04-30 | 2015-05-01 | 2015-06-11 | 2015-06-10 | 3 | 2015-06-11 | 2015-06-10 | 2015-04-30 | 2015-04-30 | 2015-06-04 | 2015-05-28 | 1 |  | 2015-06-08 | 2015-05-28 | [5 empty] | 2015-07-27 | 2015-07-20 | 2015-08-20 | 2015-08-24 | 2015-08-24 | 2015-08-28 | 2015-08-28 | 2015-09-15 | [8 empty] | 2015-09-25 | 2015-09-24 | 2015-10-06 | 2015-10-06 |  |  | Clearspan are owner (LO does not want new GF) LOS probable to a T1 site - to be investigated Requested VF info on resource consent - they could not find anything & nor could Council. Visual assessment done. Site no longer "build", work stopped as hard match colo. VF want to add dish, structural being redone. 12/2/15 - new data pack to be requested - up rev plans to include L700 16.2.15 - data pack requested Rossburn Farm Holdens Road GF site candidate A- owner does not want site here. 18.02.15 - with Tim for site search brief and decision on co-lo submission - all go on co-lo 19.02.15 - PD up rev's request with design - co-lo application ready to submit when these are issued 24.02.15 - VF co-lo application submitted 2/3/15 - visited proposed site - has been confirmed this is the preferred site, John to start arranging sub-lease with clearspan. 30/3/15 - received VF prelim approval. 7/5/15 - Tender instruction given to Huawei 10/7/15 - awaiting final approval & approval to build from VF 16/7/16 - received approval to build - still waiting for final approval doc 17/7/15 - final approval received - clock starts 20/7/15 - steel work ordered, work onsite scheduled for 10 Aug. | VNZ | 2015-08-19 | [6 empty] | 2015-08-14 | 2015-08-27 | 2015-09-21 | 2015-09-18 |  |  |  | 2015-09-15 | 2015-09-11 | BUILD | 2015-08-13 | FALSE |  | 2693392 | 6466133 | 147 Holdens Rd Clevedon |  |  | CELLSITE |  |  |  | ROAMING |  |  | 2015-05-04 | 2015-08-10 | 2015-05-07 |  | 2015-04-01 | 2015-04-20 | 2015-04-29 | 2015-07-16 | 2015-07-16 | 2015-09-14 |  | 2012-08-09
0 | AKL | 432 | AKL-008-070 | Kawakawa Bay |  |  | Manukau City |  | TIER_9 | [22 empty] | FALSE | [60 empty] | Kawakawa Bay The site is designed to provide service primarily to Kawakawa bay residential area. Secondary requirement is to provide coverage to the Kawakawa Orerei road and the roads going westwards. A small boatyard to the East is observed which indicates an opportunity for marine coverage (albeit small, good to have for marine emergencies though). A road going Eastwards is currently being built. In terms of primary coverage requirements, both Vodafone site (or Vodafone Colo) and 2 degrees greenfield option have almost similar coverage performance. On secondary coverage requirements, Vodafone site (Vodafone Colo) has the slight advantage for marine coverage and on the roads just beneath the peninsula hill because 2 degrees is located in a thicker portion of the ridge and farther out from the sea. It is fortunate that there are only a few trees located beneath the ridge. Care should be taken in maintaining isolation with nearby co-sites. Kawakawa Bay Option A: Vodafone colocation with 2 degrees on top. Apparently a more economical solution (-36.939400°, 175.178000°) Option B: Leased property. May require slightly higher pole to meet Vodafone for the secondary coverage requirements. (-36.938579°, 175.179302°) -CMM comments
0 | AKL | 433 | AKL-008-071 |  | AKL-008-071-A | Auckland Airport IB | Manukau City |  | TIER_1_ALL | ACTIVE | BO | A6 | NOPOLE | grey |  |  | 0 | 0 |  | -37.0076 | 174.7818 | [17 empty] | 2007-06-19 | 1 |  | 2007-06-19 |  |  | 2007-10-05 | 2007-10-05 | 1 | 2007-10-05 | 2007-10-05 |  |  |  | 2007-04-01 |  |  | 2007-04-01 | 2007-04-01 |  | 2007-09-03 |  | 2007-10-25 | 2 | 1 | 2007-09-07 | 2007-09-07 | [6 empty] | 2008-03-10 | 2008-03-13 | 2008-03-13 |  | 2009-08-10 | 2009-08-10 | [8 empty] | 2009-06-19 | 2009-06-19 | 2009-06-19 |  |  |  |  | New link pole at Congita required to get linking up and back to network. 09/04 |  | 2009-06-19 | [17 empty] | FALSE |  | 2668930 | 6464490 | Auckland International Airport Cyril Kay Drive Mangere Auckland |  |  | CELLSITE |  |  | 2014-08-12 | [5 empty] | 2008-03-05 | [8 empty] | 2007-06-19
0 | AKL | 434 | AKL-008-073 |  | AKL-008-073-A | Puhinui West | Manukau City |  | TIER_1_ALL | ACTIVE | GF | A6 | P1 | grey |  |  | 11 | 11 |  | -36.9988 | 174.8268 |  |  |  |  | Microwave | AKL-008-042-A | [5 empty] | 2009-05-12 | [5 empty] | 2008-05-19 | 2 | 2008-06-24 | 2008-06-24 |  |  | 2008-06-30 | 2008-05-15 | 2 | 2008-06-30 | 2008-05-15 |  |  |  | 2008-11-14 |  |  | 2008-11-14 | 2008-11-07 |  | 2008-09-08 |  | 2008-09-29 | 2 | 2 | 2008-10-02 | 2008-10-02 | 2009-02-23 | [5 empty] | 2008-12-11 | 2009-02-28 | 2009-02-26 |  | 2009-02-28 | 2009-02-28 | [8 empty] | 2009-06-05 | 2009-06-03 | 2009-06-05 |  |  |  |  | SOA at risk for end May (JL 21/4) (May14 DJ) on track for SOA May29. (Jun03 DJ) ref'cast SOA Jun03. Jun5 > SOA!! |  | 2009-06-03 |  |  |  |  | 2009-02-23 | 2009-02-23 | [11 empty] | FALSE |  | 2672958 | 6465385 | Cnr Campana & Puhinui Rd, Puhinui West, Auckland |  |  | CELLSITE |  |  | 2014-09-12 | [5 empty] | 2008-11-19 | [8 empty] | 2008-03-27
0 | AKL | 435 | AKL-008-074 |  | AKL-008-074-A | Mellons Bay | Manukau City |  | TIER_1_ALL | ACTIVE | RSR | D | P4C | green |  | STANDALONE |  |  |  | -36.8834 | 174.9269 | [17 empty] | 2008-05-21 | 3 | 2009-05-28 | 2010-02-03 |  |  | 2008-06-30 | 2008-06-30 | 1 | 2008-06-30 | 2008-06-30 |  | 2009-10-01 |  | 2009-11-27 |  |  | 2009-12-23 | 2009-12-21 | 2009-11-18 | 2009-11-18 |  | 2008-06-27 | 2 |  | 2009-12-16 | 2009-12-15 | 2009-12-08 |  |  |  |  | 2010-01-11 | 2010-01-11 | 2010-01-18 | 2010-01-15 |  | 2010-01-20 | 2010-01-15 | [8 empty] | 2010-02-17 | 2010-03-26 | 2010-02-17 |  |  |  |  | Site in build but on air may be delayed due to Telecom fibre connection. Security camera may be fitted to site. Telecom leased line in mid February - looking at MW option to Beachlands. JB to speak to council and advise property and RC requirements for adding the dish. Revised drawings circulated for sign off and issued. 14/4 - replacing pole with modified/correct pole onsite in one day. |  | 2010-03-26 |  |  |  |  | 2009-12-24 | 2009-12-08 | [11 empty] | FALSE |  | 2682148 | 6477993 | Outside 5 Page Point Mellons Bay Manukau Auckland |  |  | CELLSITE | [7 empty] | 2010-01-11 | 2010-01-11 | [8 empty] | 2008-04-18
0 | AKL | 436 | AKL-008-075 |  | AKL-008-075-B | Shamrock Park | Manukau City |  | TIER_1_ALL | ACTIVE | RSR | D | P4C | green |  |  | 13.6 | 13.6 |  | -36.9253 | 174.9206 |  |  |  |  | Microwave | AKL-008-014-C | [5 empty] | 2009-06-22 | [5 empty] | 2009-06-05 | 3 | 2009-06-30 | 2009-06-30 |  |  | 2009-08-21 | 2009-07-31 |  | 2009-08-19 | 2009-08-21 |  | 2009-06-19 |  | 2009-09-01 |  |  | 2009-09-01 | 2009-08-17 | 2009-06-15 | 2009-06-15 |  | 2009-06-26 | 2 | 3 | 2009-07-10 | 2009-07-13 | 2009-09-14 |  |  |  |  | 2009-09-22 | 2009-09-22 | 2009-10-01 | 2009-10-01 |  | 2009-10-05 | 2009-10-01 | [8 empty] | 2009-10-06 | 2009-10-06 | 2009-10-06 |  |  |  |  | On Air |  | 2009-10-06 |  |  |  |  | 2009-09-18 | 2009-09-14 | [11 empty] | FALSE |  | 2681478 | 6473366 | OS 739 Chapel Road, Shamrock Park |  |  | CELLSITE | [7 empty] | 2009-09-22 | 2009-09-22 | [8 empty] | 2009-06-04
0 | AKL | 437 | AKL-008-076 | Ngai Tai - Te Naupata | AKL-008-076-E | Musick Point - Ngai Tai- Te Naupata | Manukau City | 3 | TIER_1_INFILL | ACTIVE | RT | B | RT | grey | INLINE | COLO | 18.2 | 16 | 1 | -36.8473 | 174.9014 |  |  |  |  | Microwave | AKL-007-079-A | FALSE | FALSE |  |  | FALSE | 2010-05-07 | 2011-02-02 | 2011-02-03 | 2011-04-27 | 2011-04-27 |  | 2010-05-25 | 4 | 2010-09-10 | 2010-09-13 |  | 2011-03-30 | 2011-04-29 | 2011-03-30 |  | 2011-12-23 | 2013-03-01 | DISCRETIONARY_FULL | 2010-09-23 | 2010-10-29 | 2010-11-30 | 2010-12-24 | 4 | 2010-11-30 | 2010-12-24 |  |  | 2011-07-22 | 2011-07-22 | 1 |  | 2011-07-22 | 2011-07-22 | 2011-08-25 |  |  |  |  | 2011-08-25 | 2011-08-31 | 2011-09-16 | 2011-09-14 | 2011-09-08 | 2011-09-28 | 2011-09-28 | [8 empty] | 2011-10-06 | 2011-10-28 | 2011-10-18 | 2011-10-28 | 2011-10-28 | 2012-01-26 | 2012-03-06 | 14/4 - Jason awaiting feedback from Historic Places trust re going on building. 21/4 - Ok with Historic places trust - now the active site Chris and Alex to measure site Wednesday 19 May - drwings complete thereafter 07/07 Craig B advises that MCC have requested we withdraw initial app. 22/07 Jason B has met with IWI. They have concerns re their income security if we go on the building and they get the land in April next year but not the building. Jason has also met with LINZ, who feel without IWI support it may be difficult to secure. Busy with touching up the drawings to accuratly reflect the size of the shrouds on the sides. 28/7 Plans still with HPT. 05/08 HPT request we concider placing antennas ontop. To be discussed with Amet Radio Club. However Ian has passed away - to find new contact next week.01/09 Visited site, met new contacts Leith and David. Design to make changes to antenna positions - above the parapet. 23/04 New antenna positions approved by HPT. Craig B to submit to MCC. Received Telecom co lo approval. Have verbal approval from Radio Club, await written, Then Craig can submit. 2011 - RC from AKL rec 24/12/2010. Require : Iwi, Crown and Trust approval. 16.02.2011 Received Iwi approval. 08.03.2011 Application still with crown, should have approval by 21 March 2011 11.03.11 Crown approval received. To advise TNZ we have complied and await their final approval. hAVE tnz APPROVAL Have TNZ approval. To raise PO for antenna as they are out of spec. Let Mana know the Musick Point Schedule so he can organise the Po. | TNZ | 2011-09-28 | 2011-08-22 | 2011-09-14 | 2011-08-25 | 2011-08-25 | 2011-08-25 | 2011-08-25 | 2011-09-16 | 2011-09-20 |  | 2011-10-07 | [6 empty] | 2011-09-01 | FALSE |  | 2679965 | 6482053 | Musick Point Reserve Musick Point Road Bucklands Beach |  | Likely to be limited notified on original submitters who wont sign off on new location. - 19/05/2010 | CELLSITE | [15 empty] | 2011-10-14 | 2011-09-30
0 | AKL | 438 | AKL-008-078 |  | AKL-008-078-B | Manukau East | Manukau City |  | TIER_1_ALL | ACTIVE | RSR | D6 | P4C | green |  |  | 14.3 | 14.3 |  | -36.9778 | 174.8974 |  |  |  |  | Microwave | AKL-008-044-E | [5 empty] | 2009-06-22 | [5 empty] | 2009-06-05 | 1 | 2009-06-08 | 2009-06-05 |  |  | 2009-08-21 | 2009-07-31 |  | 2009-08-19 | 2009-08-21 |  | 2009-08-03 |  | 2009-08-03 |  |  | 2009-08-03 | 2009-07-31 | 2009-06-15 | 2009-06-15 |  | 2009-06-26 | 1 | 1 | 2009-06-30 | 2009-06-26 | 2009-09-21 |  |  |  |  | 2009-10-07 | 2009-10-07 | 2009-10-16 | 2009-10-16 |  | 2009-10-16 | 2009-10-16 | [8 empty] | 2009-10-19 | 2009-10-19 | 2009-10-19 | [6 empty] | 2009-10-19 |  |  |  |  | 2009-09-18 | 2009-09-21 | [11 empty] | FALSE |  | 2679284 | 6467584 | Cnr Dawson`Rd & Te Irirangi Drive, Manukau |  |  | CELLSITE |  |  | 2014-09-12 |  |  |  |  | 2009-10-07 | 2009-10-07 | [8 empty] | 2009-06-04
0 | AKL | 439 | AKL-008-079 |  | AKL-008-079-A | Takanini East | Manukau City |  | TIER_1_ALL | ACTIVE | RSR | D | P4C | green |  |  | 13.6 | 13.6 |  | -37.022 | 174.9223 |  |  |  |  | Microwave | AKL-008-009-A | [5 empty] | 2009-06-22 | [5 empty] | 2009-06-12 | 2 | 2009-06-16 | 2009-07-14 |  |  | 2009-08-21 | 2009-07-31 |  | 2009-08-19 | 2009-08-21 |  | 2009-08-03 |  | 2009-08-03 |  |  | 2009-08-03 | 2009-07-31 | 2009-07-14 | 2009-07-06 |  | 2009-07-14 | 1 | 1 | 2009-07-10 | 2009-07-14 | 2009-09-21 |  |  |  |  | 2009-09-30 | 2009-09-30 | 2009-10-12 | 2009-10-09 |  | 2009-10-12 | 2009-10-09 | [8 empty] | 2009-10-13 | 2009-10-14 | 2009-10-13 |  |  |  |  | On Air |  | 2009-10-14 |  |  |  |  | 2009-09-18 | 2009-09-21 | [11 empty] | FALSE |  | 2681392 | 6462625 | Outside 490 Porchester Rd |  |  | CELLSITE |  |  | 2015-12-10 |  |  |  |  | 2009-09-30 | 2009-09-30 | [8 empty] | 2009-06-04
0 | AKL | 440 | AKL-008-080 | Maraetai |  |  | Manukau City |  | TIER_9 | [22 empty] | FALSE | [60 empty] | Maraetai Two primary objectives would be commercial and residential areas at Omana Beach and Maraetai Beach. Secondary objective would be roads and highways linking Beachlands area with Omana Beach area. Care should be taken in maintaining isolation with nearby co-sites especially with Telecom. Maraetai A ridge and a forest park with apparently tall trees partly separate Omana and Maraetai Beach. The nominal is located on an ideal but difficult point. Maraetai Option A: A co-site (hopefully this is not Telecom co-site) or a rooftop site near an unknown existing site located at (-36.880697°, 175.033940°) appear to be one of the better options based on simulations. Option B: Existing light pole and electrical pole (NES) appear to provide adequate coverage to Omana beach but would not provide satisfactory coverage to Maraetai beach due to a ridge. Therefore it is important to locate a better candidate before considering this one (-36.883426°, 175.031567°). -CMM comments
0 | AKL | 441 | AKL-008-081 | Papatoetoe Central CoLo | AKL-008-081-C | Papatoetoe Central VNZ Co Lo | Manukau City | 3 | TIER_1_INFILL | ACTIVE | COLO | Ab6 | COLO | Grey | STACK_A | COLO | 29.1 | 29.6 | 1 | -36.9767 | 174.8482 |  |  |  |  | Microwave | AKL-008-018-A | FALSE | FALSE |  |  | FALSE |  | 2011-05-03 | 2011-05-03 | 2011-05-20 | 2011-05-17 | 2011-07-05 | 2011-07-01 | 5 | 2011-07-01 | 2012-10-02 | 2011-08-29 | 2011-08-08 | 2011-11-04 | 2011-10-21 |  | 2011-11-30 | 2011-11-22 | CONTROLLED | 2011-08-26 | 2012-09-12 | 2011-10-07 | 2012-10-09 | 4 | 2011-10-14 | 2011-09-29 |  |  |  | 2011-11-23 | 1 |  |  | 2011-11-23 | 2012-02-28 |  |  |  |  | 2012-01-16 | 2012-01-16 | 2012-02-08 | 2012-01-19 | 2012-01-23 | 2012-02-22 | 2012-02-28 | [8 empty] | 2012-02-28 | 2012-02-24 | 2012-02-29 | 2012-02-20 | 2012-03-15 | 2013-04-15 | 2013-03-26 | FAC SIGNED | VNZ | 2012-02-23 | 2012-02-28 | 2012-02-28 | 2012-02-28 | 2012-02-28 | 2012-02-28 | 2012-02-28 | 2012-02-07 | 2012-02-08 | 2012-02-10 | 2012-02-10 | [6 empty] | 2012-02-10 | FALSE |  | 2674913 | 6467798 | 23 Station Street VNZ Co location at the Station |  | Lodged on the 26.8.11 - 29/08/2011 Lodged S127 with rev 5 plans - 12.9.12 - 12/09/2012 - 10/10/2012 | CELLSITE |  |  | 2014-09-12 | [12 empty] | 2012-02-27 | 2012-02-27
0 | AKL | 442 | AKL-008-082 | Weymouth LPR | AKL-008-082-A | Weymouth Corner LPR | Manukau City | 3 | TIER_1_INFILL | ACTIVE | RSR | DU | P4C | Green | INLINE | STANDALONE | 14 | 14.5 | 1 | -37.0449 | 174.864 |  |  |  |  | Microwave | AKL-008-010-A | FALSE | FALSE |  |  | FALSE | 2011-04-28 | 2011-05-16 | 2011-05-03 | 2011-05-24 | 2011-05-05 | 2011-06-27 | 2011-06-22 | 4 | 2011-08-08 | 2015-04-21 | 2012-02-15 | 2012-02-09 | 2012-02-17 | 2012-02-24 |  | 2012-02-24 | 2012-03-01 | DISCRETIONARY_FULL | 2011-08-19 | 2011-08-19 | 2011-09-26 | 2011-09-21 | 2 | 2011-10-03 | 2011-09-21 |  |  | 2012-06-13 | 2012-05-30 | 1 |  | 2012-06-13 | 2012-05-30 | 2012-07-03 |  |  |  |  | 2012-08-20 | 2012-08-20 | 2012-08-24 | 2012-08-27 | 2012-08-24 | 2012-08-31 | 2012-08-30 | [8 empty] | 2012-09-05 | 2012-09-24 | 2012-09-13 | 2012-10-09 | 2012-09-25 | 2013-08-30 | 2013-09-26 | 12.06.2014 : "D" configuration build. (APM, Battery, & 2 x RFC) using version "B" cabinets. Thus making it a "DU" Site. (As per Ron Bush/blr) |  | 2012-08-30 | 2012-07-03 | 2012-07-03 | 2012-07-03 | 2012-07-03 | 2012-07-03 | 2012-07-03 | 2012-08-27 | 2012-08-27 | 2012-09-07 | 2012-09-07 | [5 empty] | BUILD | 2012-08-24 | FALSE |  | 2676151 | 6460200 | 1a Blanes Road Corner LPR Blanes / Gibbons and Weymouth Roads |  | Full discretionary consent Lodged on the 19.8.2011 - 22/08/2011 | CELLSITE | [15 empty] | 2012-09-10 | 2012-09-10
0 | AKL | 443 | AKL-008-083 | Papatoetoe East | AKL-008-083-A | Papatoetoe East Alanby Park | Manukau City | 3 | TIER_1_INFILL | ACTIVE | RSR | DU5 | P4C | Green | INLINE | STANDALONE | 14.5 | 15 | 1 | -36.9783 | 174.8719 |  |  |  |  | Fibre Optic | AKL-008-091-A | FALSE | FALSE |  |  | FALSE |  | 2011-05-16 | 2011-05-03 | 2011-05-24 | 2011-05-05 | 2011-06-27 | 2011-06-20 | 5 | 2011-07-08 | 2011-10-31 | 2012-02-15 | 2012-02-09 | 2012-02-17 | 2012-02-24 |  | 2012-02-24 | 2012-03-01 | NES | 2011-07-28 | 2011-07-29 | 2011-09-08 | 2011-08-19 | 2 | 2011-09-15 | 2011-08-19 |  |  | 2012-05-10 | 2012-05-10 | 1 |  |  | 2012-05-10 | 2012-06-05 |  |  |  |  | 2012-06-05 | 2012-06-05 | 2012-06-12 | 2012-06-12 | 2012-06-12 | 2012-06-21 | 2012-06-25 | [8 empty] | 2012-06-26 | 2012-07-13 | 2012-06-27 | 2012-07-21 | 2012-07-16 | 2013-04-12 | 2013-03-27 | 12.06.2014 : "D" configuration build. (APM, Battery, & 2 x RFC) using version "B" cabinets. Thus making it a "DU" Site. (As per Ron Bush/blr) |  | 2012-06-26 | 2012-05-08 | 2012-05-08 | 2012-06-04 | 2012-06-04 | 2012-06-05 | 2012-06-05 | 2012-06-14 | 2012-06-14 | [8 empty] | 2012-06-12 | FALSE |  | 2677015 | 6467574 | Opposite 496A Great South Road Next to the bus stop adjacent to Alanby Park |  | Lodged 29.7.11, Processing with Aimee Buckingham at Auckland Council. - 01/08/2011 | CELLSITE |  |  | 2014-09-12 | [12 empty] | 2012-07-04 | 2012-07-03
0 | AKL | 444 | AKL-008-084 | Mangere Bridge | AKL-008-084-E | Mangere Bridge RT | Manukau City | 3 | TIER_1_INFILL | ACTIVE | RT | Ab6 | RT | green | INLINE | COSITE |  | 10 | 1 | -36.9479 | 174.7772 | [6 empty] | FALSE | FALSE |  |  | FALSE |  | 2011-05-03 | 2011-05-03 | 2011-07-04 | 2011-07-04 | 2011-09-19 | 2011-09-21 | 4 | 2011-09-19 | 2012-05-21 | 2011-08-30 | 2011-08-11 | 2011-12-08 | 2011-12-02 |  | 2011-12-08 | 2011-12-02 | DISCRETIONARY_FULL | 2011-11-03 | 2011-11-02 | 2012-03-23 | 2012-03-30 | 1 | 2012-03-23 | 2012-03-30 |  |  |  | 2012-05-02 | 1 |  |  | 2012-05-02 | 2012-06-11 |  |  |  |  | 2012-05-17 | 2012-05-22 | 2012-06-11 | 2012-06-14 | 2012-06-13 | 2012-06-25 | 2012-06-25 | [8 empty] | 2012-07-02 | 2012-07-13 | 2012-07-05 | 2012-07-20 | 2012-07-19 | 2013-03-18 | 2013-03-21 | FAC SIGNED |  | 2012-07-02 | 2012-06-11 | 2012-06-11 | 2012-06-11 | 2012-06-11 | 2012-05-11 | 2012-06-11 | 2012-06-18 | 2012-06-28 | [8 empty] | 2012-05-15 | FALSE |  | 2668660 | 6471125 | 103 Taylor Road Chinese Community Centre |  | Lodged 2.11.2011 with rev 2 plans - 02/11/2011 | CELLSITE |  |  | 2014-08-12 | [12 empty] | 2012-07-06 | 2012-07-06
0 | AKL | 445 | AKL-008-085 | Flat Bush | AKL-008-085-C | Flat Bush - Jeffs Rd | Manukau City | 3 | TIER_1_INFILL | ACTIVE | RSR | Ab6 | P4C | Green | INLINE | STANDALONE | 14.1 | 14.6 | 1 | -36.9615 | 174.9261 |  |  |  |  | Microwave | AKL-008-043-C | FALSE | FALSE |  |  | FALSE | 2011-04-13 | 2011-05-04 | 2011-05-04 | 2011-05-10 | 2011-05-05 | 2011-06-27 | 2011-06-22 | 3 | 2011-06-27 | 2011-09-08 | 2012-02-15 | 2012-02-09 | 2012-02-17 | 2012-02-24 |  | 2012-02-24 | 2012-03-01 | DISCRETIONARY_FULL | 2011-07-28 | 2011-07-29 | 2011-09-08 | 2011-08-30 | 1 | 2011-09-15 | 2011-08-30 |  |  | 2012-03-12 | 2012-03-22 | 1 |  |  | 2012-03-22 | 2012-04-02 |  |  |  |  | 2012-04-02 | 2012-03-27 | 2012-04-05 | 2012-04-05 | 2012-04-05 | 2012-04-13 | 2012-04-12 | [8 empty] | 2012-04-13 | 2012-04-13 | 2012-04-14 | 2012-05-23 | 2012-05-04 | 2012-08-02 | 2012-09-03 | 17.02.2011 LPR - 142 Murphys Road Grassy patch on the corner of Jeffs and Murphys road DP 340629 Lot 251. LOS complete. Caravan complete |  | 2012-04-13 | 2012-04-02 | 2012-04-02 | 2012-04-02 | 2012-04-02 | 2012-04-02 | 2012-04-02 | 2012-04-05 | 2012-04-11 | [8 empty] | 2012-04-05 | FALSE |  | 2681881 | 6469329 | LPR Cnr of Murphys and Jeffs Rd Opposite 300 Murphys Road |  | Discretionary activity located in road reserve. Lodged with council on the 29.7.11 - 01/08/2011 | CELLSITE |  |  | 2014-09-12 | [12 empty] | 2012-04-24 | 2012-04-24
0 | AKL | 446 | AKL-008-086 | Mangere East | AKL-008-086-F | Buckland Road | Manukau City | 3 | TIER_1_INFILL | ACTIVE | RSR | DU5 | P4C | Green | INLINE | STANDALONE | 15.5 | 16 | 1 | -36.9652 | 174.8151 |  |  |  |  | Microwave | AKL-008-013-F | FALSE | FALSE |  |  | FALSE | 2011-06-02 | 2011-05-03 | 2011-05-03 | 2011-06-14 | 2011-06-08 | 2011-07-28 | 2011-08-01 | 1 | 2011-07-28 | 2011-08-01 | 2012-02-15 | 2012-02-09 | 2012-02-17 | 2012-02-24 |  | 2012-02-24 | 2012-03-01 | NES | 2011-08-01 | 2011-08-04 | 2011-09-12 | 2011-08-24 | 1 | 2011-09-19 | 2011-09-07 |  |  |  | 2012-07-13 | 1 |  |  | 2012-07-13 | 2012-07-21 |  |  |  |  | 2012-07-17 | 2012-07-19 | 2012-07-27 | 2012-07-31 | 2012-07-24 | 2012-08-03 | 2012-08-06 | [8 empty] | 2012-08-07 | 2012-08-14 | 2012-08-14 | 2012-10-06 | 2012-08-28 | 2013-03-28 | 2013-03-21 | 12.06.2014 : "D" configuration build. (APM, Battery, & 2 x RFC) using version "B" cabinets. Thus making it a "DU" Site. (As per Ron Bush/blr) |  | 2012-08-06 | 2012-07-21 | 2012-07-21 | 2012-07-21 | 2012-07-21 | 2012-07-21 | 2012-07-21 | 2012-08-09 | 2012-08-06 |  | 2012-08-06 | [5 empty] | BUILD | 2012-07-24 | FALSE |  | 2671991 | 6469136 | opposite 252 Buckland Road, Mangere East, Auckland |  | Approved on the 24.8.2011 - 07/09/2011 | CELLSITE |  |  | 2014-09-12 | [12 empty] | 2012-08-16 | 2012-08-10
0 | AKL | 447 | AKL-008-087 | The Gardens | AKL-008-087-C | The Gardens | Manukau City | 3 | TIER_1_INFILL | ACTIVE | RSR | DU | P4C | Green | INLINE | STANDALONE | 11.2 | 11.7 | 1 | -37.0055 | 174.9247 |  |  |  |  | Microwave | AKL-008-058-D | FALSE | FALSE |  |  | FALSE |  | 2011-05-04 | 2011-05-04 | 2011-05-10 | 2011-05-11 | 2011-06-27 | 2011-06-22 | 7 | 2011-06-27 | 2015-05-01 | 2012-02-15 | 2012-02-09 | 2012-02-17 | 2012-02-24 |  | 2012-02-24 | 2012-03-01 | NES | 2011-07-22 | 2011-07-29 | 2011-09-02 | 2011-08-25 | 1 | 2011-09-09 | 2011-08-25 |  |  | 2012-05-31 | 2012-05-28 | 1 |  | 2012-05-31 | 2012-05-28 | 2012-07-03 |  |  |  |  | 2012-07-02 | 2012-07-02 | 2012-08-17 | 2012-08-15 | 2012-08-20 | 2012-08-24 | 2012-08-28 |  | 2012-08-28 | [6 empty] | 2012-08-28 | 2012-09-24 | 2012-09-13 | 2012-10-02 | 2012-09-14 | 2013-05-17 | 2013-05-10 |  |  | 2012-08-27 | 2012-07-03 | 2012-07-03 | 2012-07-03 | 2012-07-03 | 2012-07-03 | 2012-07-03 | 2012-08-21 | 2012-08-22 | 2012-09-10 | 2012-09-28 | [5 empty] | BUILD | 2012-08-20 | FALSE |  | 2681651 | 6464458 | 287 Hill Road The Gardens |  | NES Application lodged with Aimee Buckingham of council for processing on the 29.7.11 - 01/08/2011 | CELLSITE |  |  | 2015-12-10 | [12 empty] | 2012-08-31 | 2012-08-31
0 | AKL | 448 | AKL-008-088 | Hunter Plaza Mini-Repeater | AKL-008-088-A | Hunters Plaza | Manukau City |  | TIER_6 | ACTIVE | RT | 2100_MINI_RPTR | RT |  |  | STANDALONE |  |  |  | -36.9718 | 174.8604 | [71 empty] | 01.05.14 We have installed a Microcell above the Noel Leeming sign. 12.05.14 Microcell to be walk tested and if all good Mini repeater will be switched off and later removed. | [19 empty] | FALSE |  | 2676006 | 6468322 | 217 Great South Rd, Papatoetoe |  |  | REPEATER
0 | AKL | 449 | AKL-008-089 | RBI - Beachlands East |  |  | Manukau City |  | RBI | [22 empty] | FALSE
0 | AKL | 450 | AKL-008-090 | 121 Phillips Rd Mini-Repeater | AKL-008-090-A | Phillips Rd Mini Repeater | Manukau City |  | TIER_6 | ACTIVE | IB | 900_MINI_RPTR | NOPOLE |  |  | STANDALONE |  |  |  | -37.0214 | 174.9576 | [12 empty] | 2011-10-10 | 2011-10-10 | [52 empty] | 2011-10-12 |  |  |  |  | 10.10.2011. Mwet Landlord and Wife on site. (With Mike and Simon) and Michael, Tim Lau) Explained what we can do and showed them the equipment. We agreed to install a bracket on the gable end of the roof above the kitchen and instal the jagi. Pointing back towards the roundabout (Existing site) We will run the cables internally to the space above the trapdoor in the laundry. Power would be hard wired in and the internal antenna (Cone shapes disc) will be installed on the low flat white ceiling aoutside the Kitchen. This should provide added coverage to the lounge and kitchen areas. Landlord was happy with this. Installation to be done on Wednesday 12.10.2011. | [17 empty] | BUILD |  | FALSE |  | 2684540 | 6462628 | 121 Phillips Rd |  |  | REPEATER
0 | AKL | 451 | AKL-008-091 | Papatoetoe Exchange | AKL-008-091-A | Chorus Exchange | Manukau City |  | TIER_6 | ACTIVE | COLO | TX |  |  |  | COLO |  |  |  | -36.9774 | 174.8536 | [66 empty] | 2012-03-01 |  | 2012-03-01 |  |  | SOA and PAC dates to reflecty status | TNZ | [18 empty] | FALSE |  | 2675386 | 6467709 | 11 Norfolk Pl, Papatoetoe, Auckland |  |  | TXSITE
0 | AKL | 452 | AKL-008-092 | Beachlands Relocation | AKL-008-092-A | Beachlands VF Co-Lo Relocation | Manukau City | 2 | TIER_3 | ACTIVE | COLO | DU | COLO |  | STACK_A | COLO |  |  | 1 | -36.8909 | 174.9908 |  |  |  |  | Microwave | AKL-007-112-A | FALSE | FALSE |  |  | FALSE | 2013-01-22 |  | 2012-09-03 |  | 2012-09-03 | 2012-10-24 | 2012-10-19 | 1 | 2012-10-24 | 2012-10-19 | 2012-11-14 | 2012-11-13 | 2013-02-21 | 2013-02-07 |  | 2013-05-17 | 2013-08-06 | DISCRETIONARY_FULL | 2012-11-06 | 2012-11-07 | 2012-12-18 | 2012-11-29 | 1 | 2012-12-18 | 2012-11-29 | 2012-11-15 | 2012-11-15 | 2012-11-30 | 2012-12-21 | 1 |  | 2012-12-14 | 2012-12-21 | 2013-03-04 |  |  |  |  | 2013-01-23 | 2013-01-23 | 2013-03-15 | 2013-03-18 | 2013-03-20 | 2013-03-26 | 2013-04-03 | [8 empty] | 2013-03-27 | 2013-03-28 | 2013-04-04 | 2013-04-30 | 2013-04-30 | 2013-08-30 | 2013-09-10 | 06/03/13 - VF mast running late and not due until 13-15 March. Tight to finish in March 09/04/13 - Site is on air and existing site to be decommissioned. Still awaiting PAD 07/05/13 - Final Lerase doc with VF to complete | VNZ | 2013-03-27 | 2013-02-04 | 2013-02-04 | 2013-02-28 | 2013-02-28 | 2013-03-04 | 2013-03-04 | 2013-03-26 | 2013-03-26 | 2013-04-12 | 2013-04-08 |  |  | TIER_1_INFILL |  |  | BUILD | 2013-03-20 | FALSE |  | 2687823 | 6477041 | Formosa Golf Resort Beachlands |  | Lodged at council with Aimee Simons - major infrastructure team on the 7.11.2012 - 08/11/2012. Approved on 29.11.2012 by Mark Ross (processing planner) - 29/11/2012 | CELLSITE | [7 empty] | 2013-01-07 | [7 empty] | 2013-04-22 | 2013-04-19
0 | AKL | 453 | AKL-008-093 | Homai | AKL-008-093-A | Homai | Manukau City |  | TIER_6 | ACTIVE | [100 empty] | HARDMATCH
0 | AKL | 454 | AKL-008-094 | Maraetai |  |  | Manukau City |  | TIER_9
0 | AKL | 455 | AKL-008-095 | Hunters Plaza | AKL-008-095-A | Hunters Plaza - Micro | Manukau City | 3 | 2014 | ACTIVE | BO | MC | OTHERS | Grey | [5 empty] | -36.9708 | 174.8605 |  |  |  |  | Fibre Optic | AKL-008-091-A | FALSE | FALSE |  |  | FALSE |  |  | 2013-11-20 |  | 2013-11-22 | 2014-01-14 | 2014-01-14 | 1 | 2014-01-14 | 2014-01-14 |  | 2014-01-30 |  | 2014-01-30 |  |  | 2014-01-30 | PERMITTED |  | 2014-02-05 |  | 2014-02-05 | 1 |  | 2014-02-05 | 2014-02-18 | 2014-02-18 | 2014-03-04 | 2014-03-12 | 1 |  | 2014-03-07 | 2014-03-12 | [5 empty] | 2014-03-24 | 2014-03-31 | 2014-05-01 | 2014-05-01 | 2014-05-01 | 2014-05-01 | 2014-05-01 | 2014-04-28 | 2014-04-28 | [7 empty] | 2014-05-13 | 2014-05-12 |  |  |  |  | Commercials Agreed. BR has collected requested equipment from Albany for Trevor F and Brendon to inspect. Await Trevor and Brendon feed back. 12.02.14 Require internal antenna. POR raised. 18.02 Issued CDI - Await plans. Need to meet with Centre Manager and Chorus Fibre 20.02.14 PO Issued and sent to maser for antenna. 28.02.14 CD's in circulation. BR to arrange meeting on site re Fibre 10.03.14 BR requested Ben to set up meeting with Landlord and Builder for Monday 17th - Visionstream also requested to send a field manager. 24.03 PO rec for trap door to be cut. Andrea advises she has instructed the contractor. POR raised for electrical point. Once trapdoor cut - contrators can meet to price. Small antenna due 6 April. 01.04.14 Hatch cut in ceiling on 31.03.14. To meet contractors on site 8.30am Friday. They are to quote on work by Wed 9.04.14. 01.05.14 Infratel install at 9pm when centre closed. Integration problems. Took long but done by 5pm. 12.05.14 Walk test to be done. | [10 empty] | 2014-05-01 | 2014-05-01 |  |  | AUCKLAND |  | 2014-04-02 | BUILD | 2014-05-01 | FALSE |  | 2676022 | 6468434 | Hunters Plaza Mall 217 Great South Rd, Papatoetoe 2025 |  | Indoor site - 05/02/2014 | CELLSITE | [7 empty] | 2014-03-17 | [9 empty] | 2013-11-22
0 | AKL | 456 | AKL-008-096 | Botany Junction | AKL-008-096-B | Storage King Botany South | Manukau City | 3 | 2014 | ACTIVE | GF | DU5 | P1 | Grey | INLINE | COSITE | 18.2 | 20 |  | -36.9625 | 174.9014 |  |  |  |  | Fibre Optic | AKL-008-091-A | FALSE | FALSE |  |  | FALSE |  | 2014-05-05 | 2014-04-30 | 2014-05-01 | 2014-04-30 | 2014-05-26 | 2014-05-28 | 1 | 2014-05-30 | 2014-05-28 | 2014-07-14 | 2014-07-09 | 2014-07-21 | 2014-07-11 | 1 | 2014-07-25 | 2014-10-08 | DISCRETIONARY_FULL | 2014-06-25 | 2014-06-25 | 2014-08-06 | 2014-07-24 | 1 | 2014-08-08 | 2014-07-24 | 2014-06-20 | 2014-06-17 | 2014-07-04 | 2014-07-04 | 2 |  | 2014-07-11 | 2014-07-14 | [5 empty] | 2014-09-08 | 2014-09-10 | 2014-10-01 | 2014-09-26 | 2014-09-26 | 2014-10-06 | 2014-10-06 | 2014-10-02 | 2014-10-02 | [7 empty] | 2014-10-17 | 2014-10-15 |  |  |  |  | 28.02.14 Storage King keen. Liz to try arrange Caravan for 14 March 10.03.14 Survey arranged for Friday 14.03 24.03.14 Storage King keen to have us. Proposal to be submitted 24.03.14 07.05.014 PDI issued 01.05 GHD given drawings to do 07.05. (PO and resoursing issues) 17.06.14 Ben confident we will get signed lease this week (Skipped LTA). So issued CDI and Rob to submit RMA next monday | [10 empty] | 2014-10-06 | 2014-10-06 | 2014-06-25 | LOW |  | 2014-09-29 | 2014-09-22 | BUILD | 2014-09-29 | TRUE | 2014-08-06 | 2679680 | 6469266 | Storage King Botany South 100 Ormiston Road, BOTANY, AUCKLAND 2016 NEW ZEALAND | 30/4 Proposal has been approved by trust prefered the back corner position. General terms are with the LO's lawyrs. 11/4 Checked with Mark he has advsied that the proposal is with the Trust. It may take time to asses. He will chase on our behalf. The property is owned by Perpetual Trustees who are part of the Abacus Group in Australia. Storage King manages the property and business on behalf of Abacus. - 19/03/2014 - 14/04/2014 - 30/04/2014 |  | CELLSITE |  |  | 2014-10-15 | [14 empty] | 2014-04-30
0 | AKL | 457 | AKL-008-097 | Highbrook South | AKL-008-097-B | Highbrook GF - 19 Andromeda Drv | Manukau City | 23 | 2015P | ACTIVE | GF | DU5 | T2 20 UF |  | STACK_A |  |  |  |  | -36.948 | 174.8863 |  |  |  |  | Fibre Optic | AKL-008-081-C | FALSE | FALSE |  |  | FALSE |  | 2015-08-21 | 2015-08-05 | 2015-08-10 | 2015-08-12 | 2015-09-18 | 2015-09-17 | 1 | 2015-09-18 | 2015-09-17 | 2015-10-30 | 2015-11-04 | 2015-11-27 | 2015-12-08 |  | 2015-11-27 | 2015-12-15 | DISCRETIONARY_FULL | 2015-10-14 | 2015-10-13 | 2015-11-27 | 2015-11-19 | 1 | 2015-11-27 | 2015-11-19 | [35 empty] | 24/7/15 - new candidate as original not approved to proceed by owner 16/09/15 - PD ready to issue 4/11/15 - Lease terms agreed. Consent processing OK | [17 empty] | HARDMATCH |  | FALSE |  | 2678372 | 6470913 | 19 Andromeda Drive Highbrook Auckland |  |  |  | WIPACTIVE |  |  | CAPACITY | [13 empty] | 2015-08-12
0 | AKL | 458 | AKL-008-098 | Mangere Exchange Co-Lo | AKL-008-098-A | Exchange Co-Lo | Manukau City |  | TIER_6 | ACTIVE | COLO | TX | [104 empty] | 63 Ashgrove Rd (Cnr Bader Dr), Mangere |  |  | TXSITE | WIPACTIVE
0 | AKL | 459 | AKL-008-099 | Whitford | AKL-008-099-A | Not known | Manukau City |  | TIER_5 | ACTIVE |  |  |  |  | STACK_A | [12 empty] | FALSE | FALSE |  |  | FALSE |  | 2015-10-13 |  | 2015-10-16 |  | 2015-11-13 |  |  |  |  | 2015-11-27 |  | 2015-12-18 | [5 empty] | 2015-11-20 |  | 2015-12-18 |  |  |  |  | 2015-12-18 |  | 2016-01-29 | [10 empty] | 2016-03-04 |  | 2016-04-08 |  |  | 2016-04-15 | [10 empty] | 2016-04-29 | [16 empty] | 2016-04-22 | [6 empty] | ONHOLD |  | FALSE | [6 empty] | CELLSITE |  |  |  | ROAMING |  |  |  | 2016-02-02 | [5 empty] | 2016-02-29
0 | AKL | 460 | AKL-009-002 |  | AKL-009-002-B | Takanini South | Papakura City |  | TIER_1_ALL | ACTIVE | GF | A | P3 | grey |  |  | 25 | 25 |  | -37.0501 | 174.9326 |  |  |  |  | Microwave | AKL-009-005-B | [5 empty] | 2009-05-13 | [5 empty] | 2007-10-30 | 2 |  | 2015-09-03 |  |  | 2007-11-14 | 2007-11-14 | 1 | 2007-11-14 | 2007-11-14 |  |  |  | 2008-03-31 |  |  | 2008-03-31 | 2008-03-31 |  | 2007-12-08 |  | 2008-03-27 | 1 | 1 | 2008-03-27 | 2008-03-27 | [6 empty] | 2008-04-16 | 2008-05-30 | 2008-05-30 |  | 2008-05-30 | 2008-05-30 | [8 empty] | 2008-11-21 | 2008-12-09 | 2008-11-21 |  |  |  |  | None |  | 2008-11-25 | [17 empty] | FALSE |  | 2682241 | 6459493 | 14 Tironui Road Southgate Auckland |  |  | CELLSITE |  |  | 2015-12-10 | [5 empty] | 2008-03-28 | [8 empty] | 2007-10-19
0 | AKL | 461 | AKL-009-003 |  | AKL-009-003-C | Ardmore | Papakura City |  | TIER_1_ALL | ACTIVE | GF | A | P3 | grey |  |  | 25 | 25 |  | -37.034 | 174.9536 |  |  |  |  | Microwave | AKL-009-005-B | [5 empty] | 2009-05-12 | [5 empty] | 2008-08-25 | 4 | 2009-02-27 | 2009-03-02 |  |  |  | 2008-09-19 | 4 | 2009-04-15 | 2009-03-30 |  |  |  | 2008-12-05 |  |  | 2009-03-20 | 2009-04-03 |  | 2008-09-08 |  | 2008-09-26 | 4 | 2 | 2009-03-13 | 2009-01-19 | 2009-02-11 | [5 empty] | 2008-12-05 | 2009-03-27 | 2009-03-13 |  | 2009-03-27 | 2009-03-13 | [8 empty] | 2009-04-07 | 2009-04-15 | 2009-04-07 |  |  |  |  | On Air |  | 2009-04-15 |  |  |  |  | 2009-02-16 | 2009-02-11 | [11 empty] | FALSE |  | 2684146 | 6461235 | Ross T Bennett Fertilisers, VNZ Site, 237 Airfield Rd, Ardmore Rd, Ardmore, Auckland |  |  | CELLSITE | [8 empty] | 2008-12-10 | [8 empty] | 2008-07-29
0 | AKL | 462 | AKL-009-004 |  | AKL-009-004-B | Papakura Central | Papakura City |  | TIER_1_ALL | ACTIVE | RT | A | NOPOLE | grey |  |  | 0 | 0 |  | -37.0619 | 174.9419 |  |  |  |  | Microwave | AKL-009-005-B | [5 empty] | 2009-05-13 | [5 empty] | 2007-06-20 | 4 |  | 2009-04-14 |  |  | 2007-01-21 | 2007-01-21 | 2 | 2007-01-21 | 2007-01-21 |  |  |  | 2008-01-21 |  |  | 2008-01-21 | 2008-01-21 |  | 2007-11-08 |  | 2008-01-17 | 3 | 4 | 2008-01-17 | 2009-04-22 | [6 empty] | 2008-03-10 | 2008-04-30 | 2008-04-30 |  | 2008-05-06 | 2008-05-09 | [8 empty] | 2008-11-24 | 2008-12-09 | 2008-11-24 |  |  |  |  | On Air |  | 2008-11-25 | [17 empty] | FALSE |  | 2683040 | 6458168 | Rd Suburb Papakura City Post Code |  |  | CELLSITE |  |  | 2015-12-10 | [5 empty] | 2008-01-22 | [8 empty] | 2007-06-01
0 | AKL | 463 | AKL-009-005 |  | AKL-009-005-B | Red Hill | Papakura City |  | TIER_1_ALL | ACTIVE | BO | A | NOPOLE | green | [5 empty] | -37.0611 | 174.9848 | [17 empty] | 2007-12-04 | 6 |  | 2011-08-03 |  |  | 2008-07-31 | 2008-07-10 | 2 | 2008-07-31 | 2008-07-10 |  |  |  | 2008-08-29 |  |  | 2008-08-29 | 2008-10-14 |  | 2008-04-22 |  | 2008-08-08 | 4 |  | 2008-08-08 | 2011-10-18 | [6 empty] | 2008-09-01 | 2008-09-23 | 2008-09-19 |  | 2008-10-17 | 2008-10-17 | [8 empty] | 2008-11-24 | 2008-12-31 | 2008-11-24 |  |  |  |  | None | [19 empty] | FALSE |  | 2686857 | 6458166 | Kaipara Rd Red Hill Papakura |  |  | CELLSITE |  |  | 2015-12-10 | [5 empty] | 2008-08-21 | [8 empty] | 2007-10-31
0 | AKL | 464 | AKL-009-006 |  | AKL-009-006-A | Papakura Junction | Papakura City |  | TIER_1_ALL | ACTIVE | GF | A | P3 | green |  |  | 24.2 | 24.2 |  | -37.0745 | 174.9308 |  |  |  |  | Microwave | AKL-009-005-B | [5 empty] | 2009-05-13 | [5 empty] | 2007-07-13 | 5 |  | 2008-09-18 |  |  | 2008-02-25 | 2008-02-25 | 5 | 2008-02-25 | 2008-02-25 |  |  |  | 2008-09-30 |  |  | 2008-09-30 | 2008-08-29 |  | 2008-03-06 |  | 2008-04-16 | 3 | 4 | 2008-09-15 | 2008-09-15 | [6 empty] | 2008-09-11 | 2008-09-26 | 2008-09-26 |  | 2008-10-10 | 2008-09-26 | [8 empty] | 2008-11-21 | 2008-12-10 | 2008-11-21 |  |  |  |  | None |  | 2008-11-26 | [17 empty] | FALSE |  | 2682024 | 6456792 | o/s 5 Dumas Place, Papakura, Auckland 1702 |  |  | CELLSITE |  |  | 2015-12-10 | [5 empty] | 2008-09-09 | [8 empty] | 2007-05-11
0 | AKL | 465 | AKL-009-007 |  | AKL-009-007-C | Papakura South | Papakura City |  | TIER_1_ALL | ACTIVE | RSR | A | P4A | green |  |  | 7 | 7 |  | -37.0767 | 174.9427 |  |  |  |  | Leased Line | AKL-007-106-A | [11 empty] | 2007-07-19 | 1 |  | 2007-07-19 |  |  | 2008-06-30 | 2008-08-25 | 1 | 2008-06-30 | 2008-08-25 |  |  |  | 2007-10-09 |  |  | 2007-10-09 | 2008-06-19 |  | 2008-03-14 |  | 2008-05-23 | 1 | 1 | 2008-05-23 | 2008-05-23 | [6 empty] | 2008-08-25 | 2008-09-30 | 2008-09-30 |  | 2008-10-03 | 2008-09-30 | [8 empty] | 2008-12-18 | 2009-03-31 | 2008-12-18 |  |  |  |  | None |  | 2009-03-31 | [17 empty] | FALSE |  | 2683071 | 6456519 | Outside 374 Great South Road Papakura South Auckland |  |  | CELLSITE |  |  | 2015-12-10 | [5 empty] | 2008-08-27 | [8 empty] | 2007-06-13
0 | AKL | 466 | AKL-009-008 |  | AKL-009-008-A | Drury | Papakura City |  | TIER_1_ALL | ACTIVE | GF | A | P3 | grey |  |  | 25 | 25 |  | -37.1052 | 174.9465 |  |  |  |  | Microwave | AKL-009-005-B | [5 empty] | 2009-05-13 | [5 empty] | 2007-05-30 | 1 |  | 2007-05-30 |  |  | 2007-06-30 | 2007-06-30 | 1 | 2007-06-30 | 2007-06-30 |  |  |  | 2008-01-21 |  |  | 2008-01-21 | 2008-01-21 |  | 2007-10-23 |  | 2007-10-24 | 1 | 1 | 2007-10-24 | 2007-10-24 | [6 empty] | 2008-03-17 | 2008-04-23 | 2008-04-23 |  | 2008-05-16 | 2008-05-09 | [8 empty] | 2008-11-21 |  | 2008-11-21 |  |  |  |  | None | [19 empty] | FALSE |  | 2683339 | 6453347 | 87 Creek St Papakura City Post Code |  |  | CELLSITE |  |  | 2015-12-10 | [5 empty] | 2008-01-22 | [8 empty] | 2007-05-11
0 | AKL | 467 | AKL-009-009 |  | AKL-009-009-A | Papakura East | Papakura City |  | TIER_1_ALL | ACTIVE | GF | A | P3 | grey |  |  | 25 | 25 |  | -37.0718 | 174.964 |  |  |  |  | Microwave | AKL-009-005-B | [5 empty] | 2009-05-13 | [5 empty] | 2007-08-30 | 1 |  | 2007-08-30 |  |  | 2007-08-14 | 2007-08-14 | 1 | 2007-08-14 | 2007-08-14 |  |  |  | 2007-10-31 |  |  | 2007-10-31 | 2007-10-31 |  | 2007-10-31 |  | 2008-01-29 | 2 | 1 | 2008-01-29 | 2008-01-29 | [6 empty] | 2008-02-18 | 2008-04-04 | 2008-04-04 |  | 2008-04-11 | 2008-04-11 | [8 empty] | 2008-11-21 | 2008-12-09 | 2008-11-21 |  |  |  |  | None |  | 2008-11-25 | [17 empty] | FALSE |  | 2684983 | 6457026 | The Papakura Club, 5 Croskery Rd, Papakura, Auckland |  |  | CELLSITE |  |  | 2015-12-10 | [5 empty] | 2008-01-30 | [8 empty] | 2007-09-12
0 | AKL | 468 | AKL-009-010 | Conifer Grove | AKL-009-010-A | Conifer Grove Shopping Center | Papakura City | 3 | TIER_1_INFILL | ACTIVE | RT | DU | RT | green | INLINE | COSITE | 11.3 | 12 | 1 | -37.0473 | 174.9101 |  |  |  |  | Fibre Optic | AKL-007-106-A | FALSE | FALSE |  |  | FALSE |  | 2011-06-28 | 2011-06-28 | 2011-07-05 | 2011-06-29 | 2011-07-28 | 2011-08-01 | 3 | 2011-07-28 | 2011-11-07 | 2011-10-17 | 2011-10-19 | 2011-12-14 | 2011-12-09 | 3 | 2011-12-14 | 2012-03-15 | DISCRETIONARY_FULL | 2011-11-07 | 2011-11-11 | 2011-12-19 | 2011-11-29 | 3 | 2011-12-19 | 2011-12-15 |  |  |  | 2012-06-22 | 1 |  |  | 2012-06-22 | 2012-07-21 |  |  |  |  | 2012-07-26 | 2012-07-26 | 2012-08-15 | 2012-08-06 | 2012-08-03 | 2012-08-31 | 2012-09-03 | 2012-08-31 | 2012-09-04 | [6 empty] | 2012-09-05 | 2012-09-24 | 2012-09-13 | 2012-09-28 | 2012-09-25 | 2013-04-12 | 2013-03-27 | FAC SIGNED |  | 2012-09-04 | 2012-07-03 | 2012-07-03 | 2012-07-03 | 2012-07-21 | 2012-07-12 | 2012-07-21 | 2012-08-09 | 2012-08-09 | 2012-09-06 | 2012-09-06 |  |  |  | 2012-08-24 | 2012-09-03 | BUILD | 2012-08-03 | FALSE |  | 2680248 | 6459849 | 68 Walter Strevens Drive Conifer Grove shopping Centre, Auckland |  | Lodged with Eilish Gardner in Papakura as an away transaction on the 11.11.11 with rev 3 plans. - 11/11/2011 | CELLSITE |  |  | 2015-12-10 | [12 empty] | 2012-09-10 | 2012-09-10
0 | AKL | 469 | AKL-009-012 | Red Hill | AKL-009-012-A | Customer Experience | Papakura City |  | TIER_6 | ACTIVE | [100 empty] | HARDMATCH
0 | AKL | 470 | AKL-009-013 | Papakura Exchange Co-Lo | AKL-009-013-A | Exchange Co-Lo | Papakura City |  | TIER_6 | ACTIVE | COLO | TX | [104 empty] | 40 O'Shannessey St, Papakura |  |  | TXSITE | WIPACTIVE
0 | AKL | 471 | AKL-010-001 |  |  |  | Franklin District |  | TIER_9
0 | AKL | 472 | AKL-010-002 | Glenbrook | AKL-010-002-A | Glenbrook Greenfield | Franklin District | 22 | TIER_4 | ACTIVE | GF | DF | T2 25 RF |  | STACK_A | COSITE | 25 | 25 |  | -37.199 | 174.7335 | 2010-06-15 |  | 2010-06-25 | 2010-06-18 | Fibre Optic | AKL-008-091-A | FALSE | FALSE |  | 2010-07-02 | FALSE |  | 2014-11-11 | 2014-11-11 | 2014-11-11 | 2014-11-11 | 2014-12-05 | 2008-07-11 | 3 | 2014-12-12 | 2014-12-02 | 2015-06-15 | 2015-06-16 | 2015-08-07 | 2015-08-13 |  | 2015-09-10 | 2015-09-21 | PERMITTED | 2015-04-14 | 2015-04-07 | 2015-05-22 | 2015-05-12 | 3 | 2015-05-22 | 2015-05-12 | 2015-04-20 | 2015-04-20 | 2015-06-09 | 2015-07-22 | 1 |  | 2015-06-09 | 2015-07-22 | [5 empty] | 2015-09-21 | 2015-09-21 | 2015-10-23 | 2015-10-23 |  | 2015-10-16 | 2015-10-16 | 2015-10-13 | 2015-10-15 | [7 empty] | 2015-10-30 | 2015-10-30 | 2015-11-18 | 2015-11-18 |  |  | COC and plan check against new equipment supplier. 01.21.2014 New redlines back with GHD last week. Waiting on Upreved plans to be issued. Then Brad can get lease signed and James can submit the CoC. Fibre has been requested. 18.12.2014 PD's have been issued and Brad is in discussion with LL. CoC to be submitted 3/2/15 - now pursuing Spark co-lo - will keep this as back up 12.2.15 - this back to the active site - awaiting feedback on spark co-lo suitability 10/3/15 - In review with their lawyers 17/3/15 - still in review | [10 empty] | 2015-10-23 | 2015-10-23 |  |  |  | 2015-10-12 | 2015-10-06 | BUILD |  | FALSE |  | 2664206 | 6443343 | NZ Steel Limited Corner Brookside Road and Glenbrook Beach Road Glenbrook |  | Permitted to None - 20/05/2010 | CELLSITE |  |  |  | ROAMING |  | 2015-05-05 | 2015-04-24 | 2015-07-14 | 2015-07-17 |  | 2015-04-13 |  | 2015-04-28 | 2015-08-20 | 2015-08-26 |  |  | 2008-06-04
0 | AKL | 473 | AKL-010-003 | Waiuku |  |  | Franklin District |  | TIER_9 | [22 empty] | FALSE | [60 empty] | Waiuku Primary objective is Urban Waiuku and immediate Waiuku suburban areas. Secondary objective are residential areas going North through Awhitu Road. Includes roads and highways that handover to adjacent sites. Waiuku. -CMM comment Possible Vodafone colocate and greenfield backup. Tower in industrial area close to VNZ and TNZ preferred. -Bevan comment Care should be taken in maintaining isolation with nearby co-sites especially with Telecom. CMM Option A: Vodafone collocate preferably extension to the top of Vodafone monopole or at similar height compared to Vodafone antenna. This would apparently be a more economical solution. (-37.250900°, 174.728000°) Option B: Proposed monopole located at 15A Martyn Street would be another similarly strong option (-37.251885°, 174.728251°). -CMM comment
0 | AKL | 474 | AKL-010-005 | Patumahoe |  |  | Franklin District |  | TIER_9 | [22 empty] | FALSE
0 | AKL | 475 | AKL-010-006 | Pukekohe West |  |  | Franklin District | 1 | TIER_3 | [22 empty] | FALSE | [75 empty] | AUCKLAND
0 | AKL | 476 | AKL-010-007 | Pukekohe Raceway | AKL-010-007-A | Pukekohe Raceway | Franklin District | 22 | TIER_4 | ACTIVE | GF | DU | T2 25 UF |  | STACK_A | COSITE | 25 | 25 | 1 | -37.2197 | 174.9077 | 2010-06-15 |  | 2010-06-25 | 2010-06-18 | Fibre Optic | AKL-007-185-A | FALSE | FALSE |  | 2010-07-02 | FALSE |  | 2012-02-29 | 2012-02-29 |  | 2012-03-01 | 2012-03-26 | 2012-04-18 | 3 | 2012-05-25 | 2012-05-30 | 2012-05-18 | 2012-05-18 | 2012-08-17 | 2012-08-17 | 1 | 2012-08-24 | 2012-08-17 | PERMITTED | 2012-06-01 | 2012-06-01 | 2012-07-27 | 2012-07-27 | 3 | 2012-08-03 | 2012-07-30 | 2014-10-21 | 2014-10-21 | 2015-01-30 | 2015-02-04 | 1 | 1 | 2015-02-06 | 2015-02-04 | [5 empty] | 2015-05-11 | 2015-05-11 | 2015-06-19 | 2015-06-23 | 2015-06-12 | 2015-06-25 | 2015-06-23 | 2015-06-05 | [8 empty] | 2015-07-14 | 2015-07-17 | 2015-07-21 | 2015-07-30 |  |  | VF and TNZ co-site approved HAIL activity site, excavted dirt to be confirmed removed from site. 01.12.2014 Rev 0 CD on circulation. Fibre feasability is underway (Ryan) - ready for NC Await CD issue - geotech done 9/3/15 - pole ordered, fibre ordered, equipment ordered - ready for tender 26/3/15 - BI given to Huawei 5/5/15 - PO approved for build start (PO35468) |  | 2015-06-23 | [6 empty] | 2015-06-21 | 2015-06-18 | 2015-06-26 | 2015-07-07 |  |  | AUCKLAND | 2015-05-22 | 2015-06-08 | BUILD | 2015-06-12 | TRUE |  | 2679614 | 6440725 | 4 Webb Street Pukekohe Raceway |  | Permitted to 25.00 AGL - 20/05/2010 Council Ref: L12059 - 30/07/2012 | CELLSITE |  |  |  | ROAMING |  | 2015-03-13 | 2015-02-04 | 2015-03-26 | 2015-03-26 |  |  |  | 2015-03-05 |  | 2015-05-07 | 2015-07-10 |  | 2012-03-01
0 | AKL | 477 | AKL-010-008 | Tuakau North |  |  | Franklin District |  | TIER_9 | [22 empty] | FALSE | [60 empty] | Primary objective is to provide coverage to residential and industrial (green house areas) at upper Tuakau (North). Use this site to complement AKL-10-020 for Harrisville and while doing so limit interference from all other adjacent sites in this area (Due to the uneven terrain Harrisville could not be covered completely by any one site). AKL-10-019 and AKL-10-028 shall cover the Eastern side of the ridge while AKL-10-020 and AKL-010-008 shall cover the Western side. Secondary objective is to provide coverage continuity along roads and railways from Pokekohe Raceway to Tuakau. Tuakau Greenfield. VNZ site is not suitable due to location, nearby trees. Bevan Confirming Bevans observation during the site visit. Apparently, it was only Telecom's tower and antennas that can be observed because of the trees while going uphill towards the site. Pathway to the site has not been found. It is suggested to propose a monopole that is higher than those of the existing operators and future proof against the growth of the trees. CMM Option 1: Current leased site initial assessment point to an apparent isolation concern. From the plans, it is computed that the Telecom antennas are only 15 meters from the currently leased monopole position. Additional information from Telecom may be required to further assess isolation problem. In case problem is confirmed, further study is required in maximizing isolation between 2 degrees and Telecom antennas to acceptable levels. This might require either moving 2 degrees site away from Telecom, azimuth change, additional filters or additional antenna height (for vertical isolation).
0 | AKL | 478 | AKL-010-009 | Bombay | AKL-010-009-G | Transpower | Franklin District | 22 | TIER_4 | ACTIVE | COLO | DF | COLO |  | STACK_A | COLO |  |  |  | -37.1881 | 174.9993 | [6 empty] | FALSE | FALSE |  |  | FALSE |  |  | 2015-07-27 | 2015-07-29 | 2015-08-04 | 2015-09-04 | 2015-09-03 | 2 | 2015-09-07 | 2015-11-27 | 2016-03-31 |  | 2016-04-29 |  |  | 2016-04-29 |  | DISCRETIONARY_FULL | 2016-02-29 |  | 2016-03-31 |  |  | 2016-04-04 |  | 2016-02-29 |  | 2016-04-04 |  |  |  | 2016-04-04 | [6 empty] | 2016-05-30 |  | 2016-06-27 |  |  | 2016-07-11 | [10 empty] | 2016-08-08 | [5 empty] | 4/9/15 - Matt submitted Transpower application | TRP | [9 empty] | 2016-07-25 | [6 empty] | BUILD |  | FALSE |  | 2687821 | 6444045 | Bombay Transpower substation Barber Rd |  |  | CELLSITE | WIPACTIVE |  |  | ROAMING |  |  |  | 2016-04-11 |  | 2015-07-29 | 2015-08-21 | 2015-11-30 |  | 2016-05-09 |  |  |  | 2015-08-04
0 | AKL | 479 | AKL-010-010 | Ramarama |  |  | Franklin District |  | TIER_9 | [22 empty] | FALSE | [60 empty] | Primary objective is the coverage for Ramarama industrial (including a nearby open mining pit) and residential area and both Southern Motorway and Great South Road which go from North to South. Secondary objective are the coverage for secondary roads to and from adjacent sites. Ramarama. Serve SH1 motorway to Bombay. TNZ co-location mast is low prefer greenfield. Bevan Site position should be chosen so that the gap between Bombay and Drury sites could be well covered. Option 1: Leased site AKL-010-010-D located at (-37.145642°, 174.969786°). CMM
0 | AKL | 480 | AKL-010-011 |  |  |  | Franklin District |  | TIER_9
0 | AKL | 481 | AKL-010-013 | Hunua | AKL-010-013-D | Hunua, Stevens Rd | Franklin District | 22 | TIER_4 | ACTIVE | GF | DF | T2 25 RH |  |  | COSITE | 25 | 28 |  | -37.0958 | 175.0775 | 2010-06-15 |  | 2010-06-25 | 2010-06-18 | Fibre Optic | AKL-008-091-A | FALSE | FALSE |  | 2010-07-02 | FALSE |  | 2015-03-24 | 2015-03-24 | 2015-03-27 | 2015-03-26 | 2015-04-30 | 2008-06-24 | 3 | 2015-04-30 | 2015-05-01 | 2015-05-29 | 2015-05-11 | 2015-07-27 | 2015-05-11 | 1 | 2015-07-31 |  | NON_COMPLYING_FULL | 2015-05-15 | 2015-05-07 | 2015-06-18 | 2015-06-09 | 3 | 2015-06-25 | 2015-06-09 | 2015-05-29 | 2015-05-12 | 2015-07-01 | 2015-07-07 | 1 |  | 2015-07-08 | 2015-07-07 | [5 empty] | 2015-08-10 | 2015-08-10 | 2015-10-23 | 2015-10-23 | 2015-09-03 | 2015-10-16 | 2015-10-15 | 2015-09-21 | 2015-09-22 | [7 empty] | 2015-10-28 | 2015-10-30 | 2015-11-30 | 2015-11-30 |  |  | COC and plans to be reviewed against new equipment. 19.2.15 - Tim L to confirm if this is the preferred site location 23.2.15 - Tim confirmed GF site is preferred option but would like to visit to confirm distance and isolation between this and spark site. Matt to arrange access. 2/3/15 - own GF site identified - LO seems amenable - will caravan asap 10/3/15 - caravan 24th March - will cherry pick for LOS at same time. Take tier 2 key for daisy chain for our own access. pole arrived 3/9 - site finished and waiting for power 16/9 |  | 2015-09-16 | [6 empty] | 2015-09-06 |  | 2015-10-23 | 2015-10-23 |  |  |  | 2015-09-21 | 2015-09-22 | BUILD | 2015-09-02 | FALSE |  | 2695005 | 6454121 | 197 Stevens Rd, Hunua | Joelyn Lee - We had a lease commenced on 6/10/2008 but terminated on 15/11/2011. - 18/03/2014 | Permitted to 25.00 - 20/05/2010 | CELLSITE |  |  |  | ROAMING |  | 2015-07-09 | 2015-04-24 | 2015-07-17 | 2015-06-11 |  | 2015-04-03 |  | 2015-04-17 | 2015-07-24 | 2015-07-27 |  |  | 2015-03-26
0 | AKL | 482 | AKL-010-014 | Karaka |  |  | Franklin District | 1 | TIER_9 | [22 empty] | FALSE | [75 empty] | TIER_1_INFILL
0 | AKL | 483 | AKL-010-015 | Pukekohe Township | AKL-010-015-J | Farmers Building | Franklin District | 3 | 2014 | ACTIVE | RT | DU | RT | Grey | INLINE | STANDALONE |  |  |  | -37.2015 | 174.9021 | 2010-06-15 |  | 2010-06-25 |  | Fibre Optic | AKL-007-185-A | FALSE | FALSE |  | 2010-07-02 | FALSE |  | 2012-06-14 | 2012-06-14 | 2012-06-28 | 2012-06-28 | 2012-08-16 | 2012-08-17 | 2 | 2012-08-16 | 2012-08-28 | 2012-10-12 | 2012-10-31 | 2013-04-30 | 2013-03-09 |  | 2013-04-30 | 2013-03-09 | PERMITTED | 2012-09-07 | 2012-09-07 | 2012-10-19 | 2012-10-17 | 2 | 2012-10-26 | 2012-10-19 | 2014-03-12 |  | 2014-04-23 | 2014-04-28 | 2 |  | 2014-04-30 | 2014-05-09 | [5 empty] | 2014-06-05 | 2014-06-05 | 2014-07-11 | 2014-07-07 | 2014-07-07 | 2014-07-14 | 2014-07-14 | 2014-07-14 | 2014-07-14 | [7 empty] | 2014-07-31 | 2014-07-29 |  |  |  |  | Structural review required by LO's structural engineers once WO2 issued. In legal review with LO, waiting comments. LO commited to us legal review to be completed before the end of the year. 13.02.14 - BR and team to visit Wednesday 12.03.14 @ 1pm 24.03 CD in progress. CD complete and forwarded to Landlord. 01.05.14 Tim L confirms its LTE site. HOWEVER we have not got LTE cabinets for it. So will build DU and upgrade later. Build will make provision for LTE. | [10 empty] | 2014-07-16 | 2014-07-15 |  |  | AUCKLAND | 2014-04-01 | 2014-04-01 | BUILD | 2014-07-07 | FALSE |  | 2679165 | 6442749 | Farmers Building 5-9 Wesley Street Pukekohe |  | Activity status TBC - could be permitted or restricted discretionary (AT - 29.3.12) - 29/03/2012 Application No. 41543 - 13/09/2012 | CELLSITE | [17 empty] | 2012-06-28
0 | AKL | 484 | AKL-010-016 | Pokeno | AKL-010-016-A | Cole Rd, Pokeno GF | Franklin District | 22 | TIER_4 | ACTIVE | GF | DF | T2 25 RH |  | STACK_A | COSITE | 25 | 25 |  | -37.2585 | 175.02 | 2010-06-15 |  | 2010-06-25 | 2010-06-18 | Fibre Optic | AKL-008-091-A | FALSE | FALSE |  | 2010-07-02 | FALSE |  | 2014-11-17 | 2014-11-05 | 2014-11-06 | 2014-11-06 | 2014-12-08 | 2008-09-18 | 3 | 2014-12-11 | 2014-11-26 | 2015-04-03 | 2015-04-07 | 2015-05-05 | 2015-05-07 |  | 2015-05-12 | 2015-07-03 | PERMITTED | 2015-04-10 | 2015-04-02 | 2015-05-15 | 2015-05-05 | 3 | 2015-05-22 | 2015-05-05 | 2015-04-10 | 2015-04-14 | 2015-06-03 | 2015-06-11 | 1 |  | 2015-06-10 | 2015-06-11 | [5 empty] | 2015-08-04 | 2015-08-04 | 2015-09-16 | 2015-09-17 | 2015-09-10 | 2015-09-21 | 2015-09-21 | 2015-09-21 | [8 empty] | 2015-09-29 | 2015-09-29 | 2015-10-28 | 2015-10-28 |  |  | If option used equipment and antenna change required. 16/9/14 - looks like lease was never executed and RC has now expired 16/1/15 - PDs with LO - under legal review 3/2/15 - now pursuing spark co-lo will keep this as back up 10/3/15 - lease terms with LO lawyer for review - spark & VF leases also under review for renewal |  | 2015-08-31 | [6 empty] | 2015-08-27 | 2015-09-04 | 2015-09-25 | 2015-09-25 |  |  |  | 2015-08-20 | 2015-08-26 | BUILD | 2015-09-10 | FALSE |  | 2689475 | 6436194 | Cole Rd, Pokeno, Franklin, Auckland |  | Permitted to 25.00 None - 20/05/2010 | CELLSITE |  |  |  | ROAMING |  | 2015-05-05 | 2015-04-24 | 2015-06-15 | 2015-05-07 |  | 2015-04-06 |  | 2015-04-13 | 2015-07-17 | 2015-07-23 | 2015-09-14 |  | 2014-11-06
0 | AKL | 485 | AKL-010-017 | Clarks Beach |  |  | Franklin District |  | TIER_9 | [22 empty] | FALSE | [60 empty] | Primary coverage are residential and some commercial areas at Clark's beach, Waiau Beach to the West and Waiau Pa to the East as well as lifestyle residential areas in between. Secondary coverage are the roads towards adjacent sites. Bonus coverage over the opposite shore Te Toro and portions of Glenbrook Bridge. Apparently the residential areas are expanding outwards from their current areas and therefore prudent to position the site at the center to balance traffic. Priority should be given for candidates at a higher elevation. Option A: Vodafone colocation preferably with 2 degrees antennas on top (-37.140100°, 174.732000°). Option B: Candidate no AKL-10-001-A (There is discrepancy between nominal and candidate numbers) with lease agreement (-37.137400°, 174.711000°).
0 | AKL | 486 | AKL-010-018 | Bombay North |  |  | Franklin District |  | TIER_9 | [22 empty] | FALSE | [60 empty] | Primary objective are the lifestyle residential areas and a few industrial areas (green houses) to the North, East and South West. Also includes a portion of the Great South Road. Secondary objectives are secondary roads towards adjacent sites. The site has been relocated from its former position because it was formerly located at the side of the hill and is limiting its coverage. Also, since it was close to AKL-010-019 some of the coverage is redundant. The search ring is small due to the small size of the hill. It is best to keep the site near the top for maximum effectivity. The site is located at the top of the hill but we may end up on the side of the hill slightly lower in elevation. Adjustment in tower height should be able to compensate this. This should be considered in the site search. Sector 1 towards the West will be 209R. This limits coverage redundancy and pilot pollution to AKL-10-019. Option A: Consider some vacant lots or spare lots on apparently a green house at the top of the hill (-37.185967°, 174.958950°).
0 | AKL | 487 | AKL-010-019 | Bombay |  |  | Franklin District |  | TIER_9 | [22 empty] | FALSE | [60 empty] | Primary objectives are the commercial and residential areas to the East around Mill road, to the West along Paparata road and Bombay road. It also provides coverage service to Southern Motorway. Vodafone tower is apparently too low. Further study required to determine adequacy of height due not only because part of the coverage area goes uphill but also due to the trees that have already grown in the area. Option 1: AKL-010-009-D (Apparently there is a discrepancy between the ID of candidates and nominals). -37.192616°, 174.983048°.
0 | AKL | 488 | AKL-010-020 | Pokeno North |  |  | Franklin District |  | TIER_9 | [22 empty] | FALSE | [60 empty] | Primary coverage objective are the residential and industrial (green house) facilities at Harrisville This site complements AKL-10-008 for Harrisville while limiting interference from all other adjacent sites in this area (Due to the uneven terrain Harrisville could not be covered completely by any one site). Also covers residential areas around Whangarata road, railways and the Great South Road. Secondary coverage are the by roads and other remote rural residential areas up on the hill. The search area is very much limited to the hill where Vodafone located because it has a commanding view of Harrisville, residents along Whangarata Road and railway and the Great South Road. AKL-10-019 and AKL-10-028 shall cover the Eastern side of the ridge while AKL-10-020 and AKL-010-008 shall cover the Western side. Sector 2 pointing South will be 209R plus another high band 30 deg antenna (when 2100 is chosen) in order to limit pilot pollution to Tuakau sites. Option 1: Vodafone Colocation (-37.231697°, 174.987276°).
0 | AKL | 489 | AKL-010-021 | Kingseat |  |  | Franklin District |  | TIER_9 | [22 empty] | FALSE | [60 empty] | Primary coverage are residential areas at Kingseat, eastern part of Linwood road and northern part of Kingseat road. Located on a very flat ground, the search area is at maximum possible. It should prefereably be between AKL-010-027 and AKL-010-017. Option 1: Co-site with Telecom but care should be taken regarding isolation (-37.130713°, 174.808847°).
0 | AKL | 490 | AKL-010-023 | Pukekohe West |  |  | Franklin District |  | TIER_9 | [22 empty] | FALSE | [60 empty] | Primary objective is to provide coverage to residential and commercial establishments South West of Pukekohe. Secondary objective are the roads towards adjacent sites. The search area would be limited to the top part of the hill which is approximately 20m. above the surrounding plain. Option 1: Telecom Colo (-37.218800°, 174.867000°). Option 2: AKL-010-006-A (Inactive but with Lease) Telecom Co-site. Possibility of isolation problem with Telecom. Requires further study. Assuming this site has no isolation problem then it has a height advantage over Telecom Colo (-37.218677°, 174.867726°).
0 | AKL | 491 | AKL-010-025 | Pukekohe North | AKL-010-025-A | Puke North LPR | Franklin District | 1 | TIER_3 | ACTIVE | RSR | DU | P4F |  | INLINE | STANDALONE |  |  | 1 | -37.1857 | 174.9136 | 2010-06-15 |  | 2010-06-25 | 2010-06-21 | Fibre Optic | AKL-007-106-A | FALSE | FALSE |  | 2010-07-02 | FALSE |  | 2012-05-09 | 2012-05-09 | 2012-05-22 | 2012-05-22 | 2012-07-04 | 2012-07-04 | 2 | 2012-11-08 | 2012-11-09 | 2012-12-03 | 2012-12-03 | 2013-02-15 | 2013-02-01 |  | 2013-02-28 | 2013-02-25 | NES | 2012-08-20 | 2012-08-16 | 2012-09-24 | 2012-09-20 | 2 | 2012-10-01 | 2012-09-25 | [35 empty] | NES design Telco notice submitted to Council 13/08/2012 - 15 days expires 3/9. Council requested to move cabinet location - revised plans requested 10/10 with GPR. Revised plans sent to council for RMA amendment. Telco notice resubmitted 03/12/2012 to AT - 15 days expires 24/12 (moved to 14/01/2013 for council shutdown period. Follow up with Jason/John first due to recent council relationship challenges | [14 empty] | AUCKLAND |  |  | HARDMATCH |  | TRUE |  | 2680217 | 6444489 | Corner Cape Hill & Valley Roads Pukekohe North |  | LPR NES Design - COC (Anna 29.3.12) - 29/03/2012 Application No. 41507 (File L12091) - 13/09/2012 - 25/09/2012 | CELLSITE | WIPHOLDING
0 | AKL | 492 | AKL-010-026 | Tuakau |  |  | Franklin District |  | TIER_9 | [22 empty] | FALSE | [75 empty] | AUCKLAND
0 | AKL | 493 | AKL-010-027 | Linwood Road | AKL-010-027-C | GF - VF Co-site | Franklin District | 1 | TIER_3 | ACTIVE | GF | DU |  |  | STACK_A | COSITE |  |  | 1 | -37.1036 | 174.8509 | 2010-06-15 |  | 2010-06-25 | 2010-06-21 | Microwave | AKL-008-059-B | FALSE | FALSE |  | 2010-07-02 | FALSE |  | 2012-08-08 | 2012-08-08 | 2012-08-09 | 2012-08-09 | 2012-08-30 | 2012-09-04 | 1 | 2012-08-30 | 2012-09-04 | 2012-09-14 | 2012-09-21 | 2012-11-15 | 2012-11-16 | 1 | 2012-11-22 | 2012-11-16 | PERMITTED | 2012-09-21 | 2012-09-19 | 2012-10-19 | 2012-10-12 | 1 | 2012-10-26 | 2012-10-17 | [29 empty] | 2013-02-15 |  | 2013-02-15 |  |  |  | VF co-site approved HAIL activity site - excavated soil to be removed. Note: 1 off payment required to the LO's tenant for disruption to crops. | VNZ | [13 empty] | TIER_1_INFILL |  |  | HARDMATCH |  | FALSE |  | 2674851 | 6453713 | 574 Linwood road Karaka |  | Council Ref L12116 (No. 41551) - 17/10/2012 | CELLSITE | WIPHOLDING | [16 empty] | 2012-08-09
0 | AKL | 494 | AKL-010-029 | Wellington Street |  |  | Franklin District |  | TIER_9 | [22 empty] | FALSE | [60 empty] | Primary coverage objectives are commercial and residential areas at Puketutu. Pak n Save, Bledisloe Park, Pukekohe Cosmopolitan Club and Rosa Birch park. Secondary coverage are secondary roads to the adjacent sites. Compared to the rural sites at the outskirts this site has a relatively small coverage area. Option 1: NES light pole at -37.210998°, 174.896702°.
0 | AKL | 495 | AKL-010-030 | Meremere |  |  | Franklin District |  | TIER_9 | [22 empty] | FALSE
0 | AKL | 496 | AKL-010-031 | Bombay Hub |  |  | Franklin District |  | TIER_9 | [22 empty] | FALSE | [60 empty] | Might required one Sector with azimuth of 70 degrees (towards North East of Paparata Road)
0 | AKL | 497 | AKL-010-032 | Bombay North |  |  | Franklin District |  | TIER_9 | [22 empty] | FALSE | [60 empty] | Main objective is to provide coverage around the curving section at the Southern Motorway (between Ramarama and Bombay sites).
0 | AKL | 498 | AKL-010-033 | RBI - Kingseat |  |  | Franklin District |  | RBI | [22 empty] | FALSE
0 | AKL | 499 | AKL-010-034 | RBI - Port Waikato |  |  | Franklin District |  | RBI | [22 empty] | FALSE
0 | AKL | 500 | AKL-010-035 | RBI - Clarks Beach Central |  |  | Franklin District |  | RBI | [22 empty] | FALSE
0 | AKL | 501 | AKL-010-036 | Waiuku | AKL-010-036-C | Waiuku Industrial | Franklin District | 22 | TIER_4 | ACTIVE | GF | DU | T2 25 UF |  | STACK_A | STANDALONE |  |  | 1 | -37.2517 | 174.7278 |  |  |  |  | Fibre Optic | AKL-007-106-A | FALSE | FALSE |  |  | FALSE |  | 2012-05-09 | 2012-05-09 | 2012-06-11 | 2012-06-18 | 2012-08-15 | 2012-08-16 | 2 | 2012-08-15 | 2012-08-29 | 2012-08-31 | 2012-08-29 | 2012-11-15 | 2012-11-13 | 2 | 2012-11-22 | 2012-11-13 | PERMITTED | 2012-09-07 | 2012-09-06 | 2012-10-19 | 2012-10-16 | 2 | 2012-10-26 | 2012-10-17 | 2014-10-24 | 2014-10-21 | 2015-02-13 | 2015-02-12 | 1 |  | 2015-02-13 | 2015-02-12 | 2015-03-18 |  |  |  |  | 2015-04-13 | 2015-04-13 | 2015-05-07 | 2015-05-15 | 2015-05-04 | 2015-05-07 | 2015-05-11 | 2015-04-30 | [7 empty] | 2015-05-19 | 2015-06-10 | 2015-06-10 | 2015-06-17 | 2015-06-19 |  |  | 2degress to install ducts, pits and cable for LO. 6 month commencement and payment for tar seal after construction. 01.12.2014 Rev 0 CD on circulation. Fibre feasability is underway (Ryan) 18.12.2014 Await CD issue15/1/15 - pole is ready at DUCO 28/1/15 - geotech done, fibre feasability ok 9/3/15 - all equipment and pole ordered, awaiting tender pricing feedback. |  | 2015-05-18 |  |  |  |  | 2015-03-18 | 2015-03-18 | 2015-05-08 | 2015-05-22 | 2015-05-25 | 2015-05-26 |  |  | AUCKLAND | 2015-05-07 | 2015-05-12 | BUILD | 2015-05-04 | TRUE |  | 2663583 | 6437505 | 15-15A Martyn Street Waiuku |  | Application Ref L12104 - 17/10/2012 | CELLSITE |  |  |  | ROAMING |  | 2014-12-18 | 2014-12-11 |  | 2015-03-30 |  |  |  | 2014-12-18 |  | 2015-03-30 | 2015-06-10 |  | 2012-06-11
0 | AKL | 502 | AKL-010-037 | Pukekohe Outer | AKL-010-037-D | Puke Outer Workshop | Franklin District | 22 | TIER_4 | ACTIVE | GF | DU | T2 25 RF |  | STACK_A | STANDALONE |  |  |  | -37.2527 | 174.7704 |  |  |  |  | Fibre Optic | AKL-007-185-A | FALSE | FALSE |  |  | FALSE |  | 2012-04-19 | 2012-04-19 | 2012-04-26 | 2012-04-26 | 2012-05-22 | 2011-11-04 | 2 | 2012-06-05 | 2012-08-15 | 2012-08-27 | 2012-08-22 | 2012-09-14 | 2012-09-03 | 2 | 2012-09-21 | 2012-09-03 | PERMITTED | 2012-07-12 | 2012-07-12 | 2012-09-14 | 2012-09-06 | 2 | 2012-09-21 | 2012-09-17 | 2015-01-21 | 2015-01-21 | 2015-03-13 | 2015-03-31 | 1 |  | 2015-03-20 | 2015-03-31 | [5 empty] | 2015-05-11 | 2015-05-07 | 2015-06-19 | 2015-06-23 | 2015-06-04 | 2015-06-19 | 2015-06-24 | 2015-06-19 | [8 empty] | 2015-07-10 | 2015-07-09 | 2015-07-21 | 2015-07-30 |  |  | HAIL activity site - excavated soil to be removed. Power from LO's cable, sufficient capacity available. $10k payment made to LO for power and access. 28/01/15 - fibre feasibility underway, CDI given 21/1/15 6.3.15 - fibre ordered and IBT accepted due to going over a few different properties - RFS 1/5 9/3/15 - pole & RF equipment orders all underway - POs not yet approved. TX ordered 13/2/15 7/5/15 - PO6 for build approved and sent to Huawei - civil build has started |  | 2015-06-29 | [6 empty] | 2015-06-24 |  | 2015-07-03 | 2015-07-03 |  |  | AUCKLAND | 2015-06-15 | 2015-06-04 | BUILD | 2015-06-15 | FALSE |  | 2667360 | 6437320 | 139A Masters Rd, Waiuku, Auckland |  | LUC20023/13 - Processed by Waikato DC under Franklin District Plan. - 14/09/2012 | CELLSITE |  |  |  | ROAMING |  | 2015-03-13 | 2015-03-13 | 2015-01-30 | 2015-03-30 |  |  |  | 2015-03-06 |  | 2015-05-07 | 2015-07-10 |  | 2012-04-26
0 | AKL | 503 | AKL-010-038 | Pukekohe | AKL-010-038-C | Pukekohe - GF 125 Blake Rd | Franklin District | 22 | TIER_4 | ACTIVE | GF | DF | T2 25 RF |  |  | STANDALONE | 24 | 25 |  | -37.2263 | 174.8781 | [6 empty] | FALSE | FALSE |  |  | FALSE |  | 2015-10-07 | 2015-10-07 | 2015-10-12 | 2015-10-09 | 2015-11-12 | 2015-11-27 | 1 | 2015-11-19 | 2015-11-27 | 2016-03-31 |  | 2016-04-29 |  |  | 2016-04-29 |  |  | 2016-03-31 |  | 2016-04-29 |  |  | 2016-04-29 | [52 empty] | 2016-02-29 |  | ONHOLD |  | FALSE |  | 2676972 | 6440049 | 123 Blake Rd, Pukekohe |  |  | CELLSITE | WIPACTIVE |  |  | ROAMING | [5 empty] | 2015-09-21 |  | 2015-11-30 | [5 empty] | 2015-10-09
0 | AKL | 504 | AKL-010-039 | Tuakau |  |  | Franklin District |  | TIER_9 | [22 empty] | FALSE
0 | BOP | 505 | BOP-022-001 | Te Puke Town | BOP-022-001-C | BoucherAve/Slater Pl cnr | Western BOP | 20 | TIER_2 | ACTIVE | GF | DU | P2 | Grey | STACK_A | STANDALONE | 19.5 | 20 | 1 | -37.7838 | 176.3245 | 2011-01-21 | 2011-01-25 | 2011-01-21 | 2011-01-25 |  |  | FALSE | TRUE | 2011-01-18 | 2011-02-11 | FALSE |  |  | 2011-04-04 | 2011-07-26 | 2011-07-26 | 2011-08-12 | 2011-08-25 | 1 | 2011-08-12 | 2011-08-25 | 2011-10-19 | 2011-10-27 | 2011-11-18 | 2011-11-16 | 1 | 2011-11-18 | 2011-11-16 | PERMITTED | 2011-10-31 | 2011-11-01 | 2011-12-08 | 2011-11-15 | 1 | 2011-12-13 | 2011-11-18 |  |  |  | 2012-03-01 | 1 |  |  | 2012-03-01 | 2012-03-06 |  |  |  |  | 2012-03-05 | 2012-03-05 | 2012-03-22 | 2012-03-23 | 2012-03-21 | 2012-03-23 | 2012-03-23 | [8 empty] | 2012-03-29 | 2012-04-11 | 2012-04-10 | 2012-03-22 | 2012-04-10 | 2012-07-09 | 2012-08-28 | Work Order 2 ready and Jackie will issue 21 November. 18/11/11 - Site now fully hard matched 30/03/12 - PAD submitted. Drive test Tues 10 April, and on air then. Site audit/inspections completed with Design and Operations |  | 2012-03-23 | 2012-03-06 | 2012-03-06 | 2012-03-06 | 2012-03-06 | 2012-03-06 | 2012-03-06 | 2012-03-23 | 2012-03-22 |  | 2012-03-30 | [6 empty] | 2012-03-22 | FALSE |  | 2802974 | 6374446 | cnr Boucher Avenue and Slater Place |  | Council Ref: 4074 - 18/11/2011 | CELLSITE |  |  | 2015-05-27 | [12 empty] | 2012-04-05 | 2012-03-30 | 2011-07-26
0 | BOP | 506 | BOP-022-002 | Katikati Hilltop | BOP-022-002-A | Katikati VF Co-lo | Western BOP | 2 | TIER_3 | ACTIVE | COLO | DU | COLO |  | STACK_A | COLO | 0 | 0 | 1 | -37.5675 | 175.8618 | 2011-06-01 |  |  | 2011-06-01 | Microwave | BOP-022-019-A | TRUE | TRUE | 2011-06-01 |  | TRUE |  | 2011-07-21 | 2011-07-14 | 2011-07-22 | 2011-07-14 | 2011-07-29 | 2011-07-25 | 1 | 2011-07-29 | 2011-07-25 | 2011-08-05 | 2011-08-04 | 2011-09-09 | 2011-08-23 |  | 2012-02-17 | 2012-02-08 | PERMITTED | 2011-08-12 | 2011-08-11 | 2011-08-31 | 2011-08-24 | 1 | 2011-09-02 | 2011-08-29 | 2012-02-16 | 2012-02-16 | 2012-04-20 | 2012-04-24 | 1 |  | 2012-04-20 | 2012-04-24 | 2012-05-24 | 2012-04-18 |  |  |  | 2012-05-13 | 2012-05-10 | 2012-05-18 | 2012-05-18 | 2012-05-24 | 2012-06-02 | 2012-06-01 | [8 empty] | 2012-06-01 | 2012-06-15 | 2012-06-08 | 2012-06-23 | 2012-06-21 | 2013-03-13 | 2013-03-25 | 13/03/13 - FAN all signed - ready to issue FAC 25/03/13 - FAC signed | VNZ | 2012-06-02 | 2012-05-24 | 2012-05-24 | 2012-05-24 | 2012-05-24 | 2012-05-16 | 2012-05-24 | 2012-05-25 | 2012-05-25 |  | 2012-06-12 |  |  | THAMES_TAURANGA |  |  | BUILD | 2012-05-25 | FALSE |  | 2763016 | 6399856 | 468, RD 2, Wharawhara Road, Katikati |  | Council Ref RC3936 - 29/08/2011 | CELLSITE |  |  | 2015-05-27 |  |  |  |  | 2012-04-20 | [7 empty] | 2012-06-11 | 2012-06-12 | 2011-07-14
0 | BOP | 507 | BOP-022-003 | Katikati Town | BOP-022-003-B | Rear 30 Main Road | Western BOP | 2 | TIER_3 | ACTIVE | GF | DU | P2 |  | STACK_A |  | 16.9 | 17.4 | 1 | -37.5531 | 175.917 |  |  |  | 2011-06-01 | Fibre Optic |  | TRUE | TRUE | 2011-06-01 |  | TRUE |  | 2012-02-24 | 2012-02-21 | 2012-02-27 | 2012-02-22 | 2012-03-26 | 2012-03-29 | 2 | 2012-03-26 | 2012-05-22 | 2012-04-12 | 2012-04-04 | 2012-05-16 | 2012-05-08 |  | 2012-05-23 | 2012-05-08 | PERMITTED | 2012-05-29 | 2012-05-29 | 2012-07-03 | 2012-06-13 | 2 | 2012-07-10 | 2012-06-14 |  |  | 2012-07-05 | 2012-07-17 | 1 |  |  | 2012-07-17 | 2012-09-08 |  |  |  |  | 2012-08-20 | 2012-08-20 | 2012-09-14 | 2012-09-07 | 2012-09-05 | 2012-09-12 | 2012-09-10 | 2012-09-10 | 2012-09-20 | [6 empty] | 2012-09-20 | 2012-10-03 | 2012-09-27 | 2012-10-18 | 2012-10-08 | 2013-05-10 | 2013-05-08 | 18/03/13 - Snags to clear before FAN issue 29/04/13 - FAN in sign off |  | 2012-09-20 | 2012-07-03 | 2012-07-03 | 2012-08-17 | 2012-08-31 | 2012-08-22 | 2012-09-08 | 2012-09-12 | 2012-09-10 | 2012-09-19 | 2012-09-25 | 2012-03-13 | MEDIUM | THAMES_TAURANGA | 2012-09-07 | 2012-09-13 | BUILD | 2012-09-05 | FALSE |  | 2767940 | 6401290 | Rear 30 Main Road Katikati |  |  | CELLSITE |  |  | 2015-05-27 | [12 empty] | 2012-09-26 | 2012-09-26 | 2012-02-22
0 | BOP | 508 | BOP-022-004 | Te Puke Hilltop | BOP-022-004-A | Te Puke Hilltop - VF cosite | Western BOP | 20 | TIER_2 | ACTIVE | GF | DU | T2 15 RFH | green | STACK_A | COSITE | 13.5 | 15 | 1 | -37.7685 | 176.2616 | 2011-01-21 | 2011-01-21 | 2011-01-21 | 2011-01-21 | Microwave | BOP-022-007-A | FALSE | TRUE | 2011-01-18 | 2011-02-11 | FALSE | 2011-02-17 | 2011-02-18 | 2011-02-09 | 2011-02-18 | 2011-02-21 | 2011-03-04 | 2011-03-10 | 2 | 2011-03-04 | 2015-06-04 | 2011-04-15 | 2011-03-31 | 2011-04-21 | 2011-04-15 |  | 2011-04-29 | 2011-04-26 | DISCRETIONARY_FULL | 2011-04-18 | 2011-04-19 | 2011-05-24 | 2011-05-17 | 1 | 2011-05-31 | 2011-05-20 |  |  | 2011-08-30 | 2011-09-02 | 1 |  | 2011-08-30 | 2011-09-02 | 2011-09-05 |  |  |  |  | 2011-09-05 | 2011-09-05 | 2011-09-29 | 2011-09-30 | 2011-09-27 | 2011-10-05 | 2011-10-11 | [8 empty] | 2011-10-11 | 2011-09-30 | 2011-10-14 | 2011-10-01 | 2011-11-02 | 2012-01-31 | 2012-05-04 | 26/06/11 VF cosite approved and issued 15/9/11 - Pile poured. All Good. Owner and farmer request track is left in. 14/10/11 - Site on aire. Design Audit inspectiojn completed |  | 2011-10-05 | 2011-09-01 | 2011-09-01 | 2011-09-05 | 2011-09-05 | 2011-09-05 | 2011-09-05 | 2011-09-30 | 2011-09-30 |  | 2011-10-13 | [6 empty] | 2011-09-27 | FALSE |  | 2797496 | 6376349 | 179 Upper Papamoa Road Te Puke |  | Council Ref: 3839 - 20/05/2011 | CELLSITE | [15 empty] | 2011-10-19 | 2011-10-19 | 2011-02-21
0 | BOP | 509 | BOP-022-005 |  |  |  | Western BOP |  | TIER_9
0 | BOP | 510 | BOP-022-007 | Papamoa - Kordia | BOP-022-007-A | Kopukairua - Kordia | Western BOP | 20 | TIER_2 | ACTIVE | COLO | DU | COLO | grey | STACK_A | COLO | 13 | 48.2 | 1 | -37.7306 | 176.2377 |  | 2009-12-17 |  | 2009-12-17 | Microwave | BOP-023-004-A | TRUE | TRUE | 2010-03-01 | 2010-03-19 | TRUE | 2010-02-19 | 2010-03-05 | 2010-03-01 |  |  | 2010-04-09 | 2010-04-08 | 1 | 2010-04-09 | 2010-04-08 |  | 2010-04-15 | 2010-04-16 | 2010-04-15 |  | 2010-04-23 | 2010-04-15 | PERMITTED | 2010-04-19 | 2010-04-15 | 2010-06-04 | 2010-05-26 | 1 | 2010-06-04 | 2010-05-26 |  |  |  | 2011-07-01 | 1 |  |  | 2011-07-01 | 2011-07-13 |  |  |  |  | 2011-06-27 | 2011-06-27 | 2011-07-08 | 2011-07-14 | 2011-07-14 | 2011-08-04 | 2011-08-05 | [8 empty] | 2011-08-05 | 2011-08-22 | 2011-08-24 | 2011-08-22 | 2011-08-26 | 2011-11-24 | 2012-04-10 | 24/8/11 Site on air | KDA | 2011-08-04 | 2011-06-20 | 2011-07-14 | 2011-07-04 | 2011-07-13 | 2011-07-04 | 2011-07-13 | 2011-07-08 | 2011-07-19 |  | 2011-08-08 | [6 empty] | 2011-07-14 | FALSE |  | 2795546 | 6380635 | Rocky Cutting Road Waitao Bay of Plenty |  |  | CELLSITE |  |  | 2015-10-13 | [12 empty] | 2011-08-08 | 2011-08-08 | 2010-03-05
0 | BOP | 511 | BOP-022-008 |  |  |  | Western BOP |  | TIER_9
0 | BOP | 512 | BOP-022-010 |  |  |  | Western BOP |  | TIER_9
0 | BOP | 513 | BOP-022-011 |  |  |  | Western BOP |  | TIER_9
0 | BOP | 514 | BOP-022-012 |  |  |  | Western BOP |  | TIER_9
0 | BOP | 515 | BOP-022-013 |  |  |  | Western BOP |  | TIER_9
0 | BOP | 516 | BOP-022-014 |  |  |  | Western BOP |  | TIER_9
0 | BOP | 517 | BOP-022-015 |  |  |  | Western BOP |  | TIER_9
0 | BOP | 518 | BOP-022-016 |  |  |  | Western BOP |  | TIER_9
0 | BOP | 519 | BOP-022-017 |  |  |  | Western BOP |  | TIER_9 | [22 empty] | FALSE
0 | BOP | 520 | BOP-022-018 |  |  |  | Western BOP |  | TIER_9
0 | BOP | 521 | BOP-022-019 | Minden | BOP-022-019-A | Tony Rhind Property (near VF) | Western BOP | 20 | TIER_2 | ACTIVE | GF | DU | P8 | grey | STACK_A | COSITE | 13 | 14 | 1 | -37.7101 | 176.0479 |  | 2009-12-17 |  | 2009-12-17 | Microwave | BOP-023-004-A | TRUE | TRUE | 2010-02-04 | 2010-02-02 | TRUE | 2010-02-19 | 2010-02-12 | 2010-02-10 |  | 2010-02-10 | 2010-02-26 | 2010-03-02 | 3 | 2010-02-26 | 2014-11-28 | 2010-04-30 | 2010-04-23 | 2010-05-07 | 2010-05-06 |  | 2010-06-11 | 2010-06-10 | DISCRETIONARY_FULL | 2010-03-19 | 2010-03-11 | 2010-05-21 | 2010-04-16 | 1 | 2010-06-11 | 2010-06-18 |  |  | 2011-05-18 | 2011-05-27 | 1 |  | 2011-05-18 | 2011-05-27 | 2011-07-20 |  |  |  |  | 2011-05-31 | 2011-06-02 | 2011-07-08 | 2011-07-08 | 2011-07-13 | 2011-07-18 | 2011-07-26 | [8 empty] | 2011-07-26 | 2011-08-15 | 2011-08-24 | 2011-08-15 | 2011-08-15 | 2011-11-14 | 2012-04-30 | Note: This was 023-019 - now 022-019. 26/07/11 - Site Integrated |  | 2011-08-01 |  | 2011-04-14 | 2011-06-06 | 2011-06-30 | 2011-07-18 | 2011-07-20 | 2011-07-20 | 2011-07-20 |  | 2011-08-03 | [6 empty] | 2011-07-13 | FALSE |  | 2778908 | 6383490 | 502 Minden Road, Te Puna, RD6 Tauranga |  |  | CELLSITE |  |  | 2015-05-27 | [12 empty] | 2011-07-03 | 2011-08-03 | 2010-02-10
0 | BOP | 522 | BOP-022-020 | Wairoa Rd | BOP-022-020-A | Lloyd Property | Western BOP | 20 | TIER_2 | ACTIVE | GF | DU | P3 | green | STACK_A | STANDALONE | 18.5 | 19 | 1 | -37.7279 | 176.0884 | 2010-06-24 |  | 2010-06-24 | 2010-06-24 | Microwave | BOP-022-007-A | TRUE | TRUE | 2010-06-29 | 2010-06-29 | TRUE | 2010-07-20 | 2010-06-29 | 2010-06-29 |  | 2010-06-29 | 2010-07-08 | 2010-07-20 | 1 | 2010-07-08 | 2010-07-20 | 2010-08-13 | 2010-08-10 | 2010-09-06 | 2010-09-03 |  | 2010-09-06 | 2010-09-03 | PERMITTED | 2010-07-14 | 2010-07-15 | 2010-08-20 | 2010-08-23 | 1 | 2010-08-31 | 2010-08-27 |  |  | 2011-06-24 | 2011-07-05 | 2 |  | 2011-06-24 | 2011-12-05 | 2012-01-11 |  |  |  |  | 2011-11-14 | 2011-11-22 | 2012-01-27 | 2012-01-24 | 2012-01-12 | 2012-01-27 | 2012-02-02 | [8 empty] | 2012-02-02 | 2012-02-17 | 2012-02-15 | 2012-02-24 | 2012-02-17 | 2013-05-28 | 2013-05-31 | 15/12/11 - Construction well underway. Pads down, fence up, waiting for pole. Drive test maybe 13 Jan 14/02/12 - Site integrated last week. Drive tested Friday. QA inspection 14/2. Look at results and if no service affecting snags, then site will be released to Air |  | 2012-02-02 | 2011-06-20 | 2011-06-20 | 2011-12-01 | 2011-11-26 | 2011-11-15 | 2012-01-11 | 2012-01-19 | 2012-01-19 |  | 2012-02-13 | [5 empty] | BUILD | 2012-01-12 | FALSE |  | 2782404 | 6381396 | 350 Wairoa Road, Te Puna, Western Bay Of Plenty |  |  | CELLSITE |  |  | 2015-05-27 | [12 empty] | 2012-02-13 | 2012-02-13 | 2010-06-29
0 | BOP | 523 | BOP-022-021 | Waihi Beach | BOP-022-021-A | Hilltop around Telecom | Western BOP | 2 | TIER_3 | ACTIVE | GF | DU | T2 15 RFH |  | STACK_A | COSITE | 14.2 | 15 | 1 | -37.4045 | 175.9299 |  |  |  |  | Fibre Optic |  | FALSE | FALSE |  |  | FALSE |  | 2012-02-23 | 2012-02-21 | 2012-02-27 | 2012-02-22 | 2012-03-26 | 2012-03-29 | 2 | 2012-03-26 | 2012-04-12 | 2012-04-12 | 2012-04-04 | 2012-05-25 | 2012-05-14 |  | 2012-07-10 | 2012-08-08 | PERMITTED | 2012-04-23 | 2012-05-14 | 2012-06-25 | 2012-05-17 | 2 | 2012-06-28 | 2012-05-17 | 2012-07-09 | 2012-07-09 | 2012-08-03 | 2012-08-09 | 1 |  | 2012-08-03 | 2012-08-09 | 2012-08-30 |  |  |  |  | 2012-08-20 | 2012-08-21 | 2012-09-07 | 2012-09-07 | 2012-09-04 | 2012-09-11 | 2012-09-11 | 2012-09-10 | 2012-09-20 | [6 empty] | 2012-09-19 | 2012-10-05 | 2012-09-27 | 2012-10-18 | 2012-10-08 | 2013-04-26 | 2013-04-23 | 18/03/13 - Snags to clear for FAN issue 23/04/13 - FAC signed |  | 2012-09-19 | 2012-07-02 | 2012-07-02 | 2012-08-30 | 2012-08-30 | 2012-08-23 | 2012-08-30 | 2012-09-07 | 2012-09-07 | 2012-09-14 | 2012-09-25 |  | LOW | THAMES_TAURANGA | 2012-09-07 | 2012-09-13 | BUILD | 2012-09-05 | FALSE |  | 2769624 | 6417737 | End Tohra View Road Waihi Beach |  |  | CELLSITE | [15 empty] | 2012-09-25 | 2012-09-25 | 2012-02-22
0 | BOP | 524 | BOP-022-022 | Athenree | BOP-022-022-A | Athenree - VF Co-lo | Western BOP | 22 | TIER_5 | ACTIVE | COLO | DF | COLO |  | STACK_A | COLO | 35 | 35 | 1 | -37.4517 | 175.9437 |  |  |  |  | Microwave | BOP-022-021-A | FALSE | FALSE |  |  | FALSE |  | 2012-02-23 | 2012-02-21 | 2012-02-28 | 2012-02-22 | 2012-03-26 | 2012-03-29 | 7 | 2015-10-30 | 2015-12-02 | 2016-03-14 |  | 2016-03-28 |  |  | 2016-04-04 |  | DISCRETIONARY_FULL | 2016-01-28 | 2016-01-28 | 2016-02-29 |  | 7 | 2016-02-29 |  | 2016-01-25 | 2016-01-27 | 2016-02-29 |  |  |  | 2016-03-07 | [6 empty] | 2016-04-18 |  | 2016-05-16 |  |  | 2016-05-30 | [10 empty] | 2016-06-16 | [5 empty] | 19/06/12 - VF preliminary Approval granted and 2D have accepted 31/07/12 - Submit VF Project Plan 10/9, VF approval by 24/9 - subject to CD's 06/08/12 - WO2 in sign off 23/08/12 - VF Lease (Historical)ammendments- Kelly 18/10/12 - Lease Dates pushed out 25/8/15 - new VF data pack ordered 23/9/15 - up rev redlines issued - pole up 23/11/15 - VF Colo application submitted 20/1/16 - received VF prelim approval | VNZ | 2012-12-10 | 2012-10-06 | 2012-10-06 | 2012-11-22 |  | 2012-11-12 |  | 2012-12-03 |  | 2016-06-06 |  |  |  | THAMES_TAURANGA |  |  | BUILD |  | FALSE |  | 2770673 | 6412459 | 234 Athenree Road Athenree Katikati |  |  | CELLSITE | WIPACTIVE |  |  | ROAMING |  |  | 2016-02-10 | 2016-03-07 | [5 empty] | 2016-04-04 |  | 2012-12-19 |  | 2012-02-22
0 | BOP | 525 | BOP-022-023 | RBI - Pyes Pa |  |  | Western BOP |  | RBI | [22 empty] | FALSE
0 | BOP | 526 | BOP-022-024 | RBI - Paengaroa | BOP-022-024-A | Paengaroa RBI | Western BOP | 25 | TIER_5 | ACTIVE | RBI | DF | COLO |  | STACK_A | COLO | 28 | 30 |  | -37.8184 | 176.4064 |  |  |  |  | Fibre Optic | BOP-023-004-A | FALSE | FALSE |  |  | FALSE |  | 2015-10-16 | 2015-10-14 | 2015-10-23 | 2015-10-26 | 2015-11-13 | 2015-11-02 | 1 | 2015-10-28 | 2015-11-02 | 2016-02-12 |  | 2016-02-26 |  |  | 2016-02-26 |  | PERMITTED | 2015-11-25 | 2015-11-25 | 2015-11-26 | 2015-12-21 | 1 | 2015-12-10 | 2015-12-21 | 2015-11-20 | 2015-11-23 | 2015-12-18 | 2016-01-15 | 1 |  | 2016-01-15 | 2016-01-15 | [5 empty] | 2016-03-07 |  | 2016-03-11 |  |  | 2016-03-11 |  | 2016-03-04 |  | 2016-02-17 |  | 2016-02-17 |  | 2016-02-10 | 2016-01-25 |  | 2016-03-30 | [5 empty] | 16 Oct: CD1 requested. 19 Oct: Letter to planner drafted. Send when VF advises LO of co-lo request. 21 Oct: VF co-lo & Spark co-site lodged & Pre-qual requested. 7 Dec: RFS date 2 March. Waiting for VF pre-build approval. ATN ordered. Antenna quote requested 12 Jan: Waiting on VF approval & antenna quote 17 Jan: Contractor site visit. Quotes pending. 27 Jan: PO6 approved 3 Feb: Waiting for VF pre-approval & revised quote for Paengaroa diplexer (+ air freight) | VNZ | [9 empty] | 2016-03-18 |  | 2016-01-28 | LOW |  | 2016-03-08 |  | BUILD | 2016-03-07 | FALSE |  | 2810038 | 6370342 | State Highway 33 Paengaroa |  |  | CELLSITE |  |  |  | ROAMING |  |  | 2016-02-10 | 2015-12-09 | 2015-12-09 | 2015-10-19 | 2015-10-19 | 2015-11-24 | 2015-11-25 | 2016-02-09 | 2016-02-02 |  |  | 2015-10-26
0 | BOP | 527 | BOP-022-025 | RBI - Aongatete | BOP-022-025-A | Aongatete RBI | Western BOP | 25 | TIER_5 | ACTIVE | RBI | DF | COLO |  | STACK_A | COLO | 28 | 30 |  | -37.6135 | 175.9413 |  |  |  |  | Fibre Optic | BOP-023-004-A | FALSE | FALSE |  |  | FALSE |  | 2015-10-16 | 2015-10-16 | 2015-10-21 | 2015-10-23 | 2015-10-21 | 2015-11-02 | 1 | 2015-10-27 | 2015-11-02 | 2015-11-17 | 2015-11-17 | 2015-11-20 | 2015-11-20 |  | 2016-02-12 |  | PERMITTED | 2015-11-19 | 2015-11-18 | 2015-12-03 | 2015-11-25 | 1 | 2015-12-03 | 2015-11-25 | 2015-11-24 | 2015-11-24 | 2015-11-25 | 2016-01-15 | 1 |  | 2015-11-25 | 2016-01-15 | [5 empty] | 2016-03-14 |  | 2016-03-18 |  |  | 2016-03-18 |  | 2016-02-19 |  | 2016-02-24 |  | 2016-02-24 |  | 2016-03-02 | 2016-01-25 |  | 2016-03-30 | [5 empty] | 16 Oct: VF co-lo & Spark co-site lodged & Pre-qual requested. CD1 requested. 19 Oct: Letter to planner drafted. Will be sent when VF advises LO of co-lo request. 29 Oct: Draft CD1 issued for review. 2 Nov: ATN PO raised. 16 Nov: Pre-build approval granted. Letter sent to LO. Tender Instruction issued 15 Dec: VF Antenna PO requested. Antennas ordered. 22 Dec: VF PO sent through to order antennas 20 Jan: Tender visit completed. Quote pending. Waiting for Huawei & VF antenna ETA. 2 Feb: PO6 issued. Waiting on VF quote for replacement antennas. 10 Feb: CX Config raised for 24th Feb | VNZ | [9 empty] | 2016-03-25 |  |  |  |  | 2016-03-15 |  | BUILD | 2016-03-14 | FALSE |  | 2769864 | 6394528 | 12 Wright Road |  | Letter to confirm compliance sent to Council - 25/01/2016 | CELLSITE |  |  |  | ROAMING |  |  | 2016-02-10 | 2015-11-20 | 2015-11-19 | 2015-10-15 | 2015-10-16 | 2015-10-30 | 2015-10-30 | 2016-02-02 | 2016-02-02 |  |  | 2015-10-23
0 | BOP | 528 | BOP-022-026 | RBI - Maketu | BOP-022-026-A | Maketu RBI | Western BOP | 23 | TIER_4 | ACTIVE | RBI | DF | RBI Pole | Grey |  | COLO |  |  |  | -37.7666 | 176.4673 |  |  |  |  | Fibre Optic | BOP-023-004-A | FALSE | FALSE |  |  | FALSE |  | 2015-05-21 | 2015-05-21 | 2015-05-21 | 2015-05-21 | 2015-05-21 | 2015-05-21 | 1 | 2015-05-21 | 2015-05-21 | 2015-05-21 | 2015-05-21 | 2015-07-24 | 2015-07-14 |  | 2015-07-24 | 2015-07-16 | PERMITTED | 2015-05-29 | 2015-05-29 | 2015-06-12 | 2015-06-25 | 1 | 2015-06-12 | 2015-06-25 | 2015-05-21 | 2015-05-21 | 2015-06-04 | 2015-05-26 | 2 |  | 2015-06-19 | 2015-10-21 | [5 empty] | 2015-08-10 | 2015-08-10 | 2015-08-13 | 2015-08-14 | 2015-08-10 | 2015-08-17 | 2015-08-17 | 2015-08-11 | 2015-08-12 | 2015-07-03 | 2015-07-23 | 2015-07-17 | 2015-07-29 | 2015-07-30 | 2015-07-31 |  | 2015-08-31 | 2015-08-31 |  | 2015-09-24 |  | 2015-09-24 | Rapid Access RBI site. 03 July: PO6 issued 14 July: VF Final approval LO approval received 11 Aug: RFS date 5 Aug: Weather delayed build start until 10th Aug 17th Aug: Target Integration date 12 Aug: Fibre delivered to site 17 Aug: Integrated 20 Aug: Vol4 due (need to turn around quickly to get SOA by end of the month) | VNZ | [9 empty] | 2015-08-28 | 2015-08-20 |  |  |  | 2015-08-11 | 2015-08-12 | BUILD | 2015-08-10 | FALSE |  | 2815618 | 6375877 | Arawa Ave, Maketu |  |  | CELLSITE |  |  |  | ROAMING |  |  | 2015-06-18 | 2015-05-21 | 2015-05-21 | 2015-05-21 | 2015-05-21 | 2015-05-29 | 2015-06-03 | 2015-07-03 | 2015-07-03 |  |  | 2015-05-21
0 | BOP | 529 | BOP-022-027 | RBI - Oropi |  |  | Western BOP |  | RBI | [22 empty] | FALSE
0 | BOP | 530 | BOP-022-028 | Pukehina | BOP-022-028-A | Pukehina | Western BOP | 22 | TIER_5 | ACTIVE | GF | DF | T2 25 RH |  | STACK_A | COSITE | 28 | 28 | [7 empty] | Fibre Optic | BOP-023-004-A | FALSE | FALSE |  |  | FALSE |  | 2015-09-17 | 2015-09-17 | 2015-09-25 | 2015-09-25 | 2015-10-30 | 2015-11-20 | 1 | 2015-10-30 | 2015-11-20 | 2016-03-21 |  | 2016-04-18 |  |  | 2016-04-25 |  | DISCRETIONARY_FULL | 2016-03-21 |  | 2016-04-25 |  |  | 2016-04-29 |  | 2016-03-21 |  | 2016-04-25 |  |  |  | 2016-04-29 | [6 empty] | 2016-06-06 |  | 2016-07-04 |  |  | 2016-07-18 | [10 empty] | 2016-08-08 | [5 empty] | 25/8/15 - VF data pack ordered 18/8/15 - proposed 25m RH pole with double stack headframe with 3 x 742266 antenna at top - approx. 28m 13/1/16 - using tower manufactured previously which we have in stock - just need to modify headframe 9/2/16 - Vega antenna due approx. 28th March | [10 empty] | 2016-08-01 | [6 empty] | BUILD |  | FALSE | [6 empty] | CELLSITE | WIPACTIVE |  |  | ROAMING |  |  |  | 2016-04-25 |  |  | 2015-10-13 |  |  | 2016-05-23 |  |  |  | 2015-09-25
0 | BOP | 531 | BOP-022-029 | Kaimai Middle |  |  | Western BOP |  | TIER_5 | [22 empty] | FALSE | [60 empty] | Road coverage on SH29
0 | BOP | 532 | BOP-022-030 | Kaimai Lower | BOP-022-030-A | Kaimai Lower VF Co-Lo | Western BOP | 22 | TIER_5 | ACTIVE | COLO | DF | COLO |  | STACK_A | COLO | 19 | 20 | [7 empty] | Microwave | WKT-015-012-C | FALSE | FALSE |  |  | FALSE |  | 2015-11-27 | 2015-11-27 | 2015-12-02 | 2015-12-02 | 2016-01-14 | 2016-01-15 | 1 | 2016-01-19 | 2016-01-15 | 2016-03-14 |  | 2016-05-02 |  |  | 2016-05-16 |  | DISCRETIONARY_FULL | 2016-02-22 |  | 2016-03-28 |  |  | 2016-03-28 |  | 2016-02-22 |  | 2016-03-07 |  |  |  | 2016-03-14 | [6 empty] | 2016-06-06 |  | 2016-07-04 |  |  | 2016-07-18 | [10 empty] | 2016-08-18 | [5 empty] | RF to decide if Kaimai Middle or Kaimai Lower to be pursued as the Active T5 candidate 2/12/15 - Kaimai lower chosen as better option 18/1/16 - VF co-lo application submitted | VNZ | [9 empty] | 2016-08-01 | [6 empty] | BUILD |  | FALSE |  |  |  | 29 Thorn Rd, Kaimai Tauranga |  |  | CELLSITE | WIPACTIVE |  |  | ROAMING |  |  |  | 2016-04-25 |  |  | 2015-11-11 |  |  | 2016-05-23 |  |  |  | 2015-12-02
0 | BOP | 533 | BOP-023-001 | Mt Maunganui North | BOP-023-001-D | Grand Pacific | Tauranga | 20 | TIER_2 | ACTIVE | RT | DU | RT | grey | INLINE | STANDALONE | 33 | 33.5 | 2 | -37.6328 | 176.1782 |  | 2009-12-17 |  | 2009-12-17 | Microwave | BOP-023-007-B | TRUE | TRUE | 2010-03-30 | 2010-04-16 | TRUE | 2010-07-02 | 2010-03-30 | 2010-03-30 |  |  | 2010-04-12 | 2010-04-14 | 4 | 2011-06-23 | 2014-09-25 | 2010-06-11 | 2010-04-29 | 2010-05-14 | 2010-04-29 |  | 2010-06-11 | 2010-06-10 | PERMITTED | 2010-04-30 | 2010-05-06 | 2010-06-09 | 2010-05-24 | 1 | 2011-09-08 | 2011-08-31 |  |  | 2011-05-17 | 2011-05-19 | 1 |  | 2011-05-17 | 2011-05-19 | 2011-05-09 |  |  |  |  | 2011-05-02 | 2011-05-02 | 2011-07-08 | 2011-07-08 | 2011-06-22 | 2011-07-01 | 2011-07-01 | [8 empty] | 2011-07-26 | 2011-08-15 | 2011-08-24 | 2011-08-15 | 2011-08-22 | 2011-11-15 | 2012-01-17 | 26/07/11 - Site Integrated 28/07/11 - Lodging consent for S127 extra MW dish 31/08/11 - Council have issued S127 for 3rd MW dish on site |  | 2011-07-27 |  | 2011-04-14 | 2011-06-06 | 2011-06-30 | 2011-05-30 | 2011-05-09 | 2011-06-23 | 2011-07-01 |  | 2011-08-02 | [7 empty] | FALSE |  | 2790693 | 6391669 | 15 Maunganui Road Mount Maunganui |  |  | CELLSITE |  |  | 2014-12-05 | [12 empty] | 2011-08-01 | 2011-08-01 | 2010-03-30
0 | BOP | 534 | BOP-023-002 | Ngatai Rd | BOP-023-002-E | LPR Ngatai/Otumoetai | Tauranga | 20 | TIER_2 | ACTIVE | RSR | DU | P4F | green | INLINE | STANDALONE | 14.2 | 14.7 | 1 | -37.6657 | 176.1397 |  | 2009-12-17 |  | 2009-12-17 | Microwave | BOP-022-019-A | TRUE | TRUE | 2010-01-20 |  | TRUE | 2010-03-25 | 2010-03-16 | 2010-03-18 |  |  | 2010-04-01 | 2010-03-29 | 3 | 2010-04-01 | 2014-12-11 | 2010-05-14 | 2010-05-06 | 2010-06-18 | 2010-06-18 |  | 2010-06-18 | 2010-06-18 | NES | 2010-04-09 | 2010-03-31 | 2010-05-07 | 2010-04-15 | 1 | 2010-05-14 | 2010-04-15 |  |  | 2011-05-17 | 2011-05-20 | 1 |  | 2011-05-17 | 2011-05-20 | 2011-05-31 |  |  | 2011-06-07 |  | 2011-07-04 | 2011-07-04 | 2011-07-12 | 2011-07-12 | 2011-07-12 | 2011-07-14 | 2011-07-29 | [8 empty] | 2011-07-29 | 2011-08-15 | 2011-08-24 | 2011-08-15 | 2011-08-15 | 2011-11-15 | 2012-01-17 | Dec - FAN issued |  | 2011-08-01 |  | 2011-04-14 | 2011-06-06 | 2011-06-30 |  | 2011-05-31 | 2011-07-14 | 2011-07-14 |  | 2011-08-04 | [6 empty] | 2011-07-13 | TRUE |  | 2787169 | 6388137 | LPR cnr Otumoetai and Ngatai Roads Beside Overbridge Tauranga |  |  | CELLSITE |  |  | 2015-05-27 | [12 empty] | 2011-07-25 | 2011-08-03 | 2010-03-18
0 | BOP | 535 | BOP-023-003 | Tauranga Hospital - TX Hub | BOP-023-003-A | Tauranga Hospital | Tauranga | 20 | TIER_2 | ACTIVE | RT | DU | RT | grey | STACK_A | COSITE | 24.9 | 26.3 | 1 | -37.708 | 176.147 |  | 2009-12-17 |  | 2009-12-17 | Fibre Optic | BOP-023-004-A | TRUE | TRUE | 2010-02-18 |  | TRUE | 2010-03-12 | 2010-02-26 | 2010-02-24 |  |  | 2010-03-12 | 2010-03-12 | 4 | 2010-03-19 | 2015-01-16 | 2010-05-07 | 2010-05-06 | 2010-09-16 | 2010-09-13 |  | 2010-09-16 | 2010-09-13 | DISCRETIONARY_FULL | 2010-03-19 | 2012-07-25 | 2010-05-07 | 2012-08-27 | 3 | 2010-05-07 | 2010-05-06 |  |  | 2011-06-02 | 2011-06-03 | 2 |  | 2011-05-30 | 2011-06-28 | 2011-07-14 |  |  |  |  | 2011-06-27 | 2011-07-14 | 2011-08-04 | 2011-08-04 | 2011-07-26 | 2011-08-04 | 2011-08-05 | [8 empty] | 2011-08-05 | 2011-08-22 | 2011-08-24 | 2011-08-22 | 2011-08-26 | 2011-11-24 | 2012-05-01 | 11/5/10 - VF and Telecom Co-site approvals received |  | 2011-08-04 | 2011-06-08 | 2011-06-08 | 2011-06-13 | 2011-06-27 | 2011-08-01 | 2011-07-14 | 2011-08-01 | 2011-07-29 |  | 2011-08-08 | [6 empty] | 2011-07-23 | FALSE |  | 2787646 | 6383423 | Tauranga Hospital 829 Cameron Road Tauranga |  | Section 127 Approved on the 27.8.12 with rev 3 plans - 29/08/2012 | CELLSITE |  |  | 2015-05-27 | [12 empty] | 2011-08-08 | 2011-08-08 | 2010-02-24
0 | BOP | 536 | BOP-023-004 | Tauranga Westpac - Main Hub | BOP-023-004-A | Westpac Building | Tauranga | 20 | TIER_2 | ACTIVE | RT | DU | RT | grey | INLINE | COSITE | 28 | 30.6 | 1 | -37.6847 | 176.17 |  | 2009-12-17 |  | 2009-12-17 | Fibre Optic | AKL-007-106-A | TRUE | TRUE | 2010-02-26 | 2010-03-26 | TRUE | 2010-03-12 | 2010-03-19 | 2010-03-15 |  |  | 2010-04-01 | 2010-04-01 | 2 | 2010-04-01 | 2010-06-15 | 2010-05-21 | 2010-05-12 | 2010-07-27 | 2010-07-27 | 2 | 2010-07-27 | 2010-07-27 | DISCRETIONARY_FULL | 2010-04-09 | 2010-04-07 | 2010-05-14 | 2010-05-10 | 1 | 2010-05-21 | 2010-05-10 |  |  | 2011-06-17 | 2011-07-08 | 1 |  | 2011-06-17 | 2011-07-08 | 2011-06-26 |  |  |  |  | 2011-05-27 | 2011-06-08 | 2011-06-30 | 2011-07-11 | 2011-07-07 | 2011-07-15 | 2011-07-22 | [8 empty] | 2011-07-22 | 2011-08-15 | 2011-08-24 | 2011-08-15 | 2011-08-26 | 2011-11-24 | 2012-05-04 | 22/07/11 - Site integrated |  | 2011-07-29 | 2011-06-08 | 2011-06-08 | 2011-06-13 | 2011-06-27 | 2011-06-26 | 2011-06-26 | 2011-06-22 | 2011-07-04 |  | 2011-08-01 | [6 empty] | 2011-07-07 | FALSE |  | 2789762 | 6385933 | Westpac Building 2 Devonport Road Tauranga |  |  | CELLSITE |  |  | 2014-12-05 | [12 empty] | 2011-08-01 | 2011-08-01 | 2010-03-15
0 | BOP | 537 | BOP-023-005 | Mt Maunganui | BOP-023-005-A | Cnr Rata St & Nikau Cres, Mount South | Tauranga | 20 | TIER_2 | ACTIVE | GF | DU | P2 | grey | STACK_A | COSITE | 20.1 | 20.6 | 1 | -37.643 | 176.1844 |  | 2009-12-17 |  | 2009-12-17 | Microwave | BOP-023-001-D | TRUE | TRUE | 2010-01-20 |  | TRUE | 2010-07-02 | 2010-01-22 | 2010-01-20 |  |  | 2010-02-04 | 2010-02-08 | 4 | 2010-03-18 | 2014-09-25 | 2010-04-30 | 2010-04-23 | 2010-07-29 | 2010-07-29 |  | 2010-08-03 | 2010-08-05 | PERMITTED | 2010-02-12 | 2010-02-11 | 2010-03-26 | 2010-03-24 | 2 | 2010-04-05 | 2010-03-24 |  |  | 2011-05-03 | 2011-05-09 | 1 |  |  | 2011-05-09 | 2011-05-23 |  |  | 2011-04-19 |  | 2011-05-09 | 2011-05-09 | 2011-06-17 | 2011-06-16 | 2011-06-22 | 2011-06-12 | 2011-07-01 | [8 empty] | 2011-07-29 | 2011-08-15 | 2011-08-24 | 2011-08-15 | 2011-08-23 | 2011-11-21 | 2012-02-07 | 11/5/10 - Telecom Co-site approval received 19/4/11 - Letter drop today, but found the houses are all boarded up, and on instructions from SPM, the letter drop was aborted. |  | 2011-07-25 |  | 2011-04-14 | 2011-06-06 | 2011-06-15 | 2011-05-23 | 2011-05-23 | 2011-06-22 | 2011-07-01 |  | 2011-08-03 | [6 empty] | 2011-06-20 | TRUE |  | 2791197 | 6390513 | Cnr Rata St & Nikau Crs, Mt Maunganui, Bay of Plenty |  | Permitted to None None - 20/05/2010 | CELLSITE |  |  | 2014-12-05 | [12 empty] | 2011-07-13 | 2011-08-03 | 2010-01-20
0 | BOP | 538 | BOP-023-006 | Totara Street | BOP-023-006-A | 100 Hull Road | Tauranga | 20 | TIER_2 | ACTIVE | GF | DU | P2 | grey | STACK_A | COSITE | 20.7 | 21.2 | 1 | -37.6541 | 176.1889 |  | 2009-12-17 |  | 2009-12-17 | Microwave | BOP-023-014-B | TRUE | TRUE | 2010-02-11 |  | TRUE | 2010-03-25 | 2010-02-10 | 2010-02-10 |  |  | 2010-02-26 | 2010-02-26 | 2 | 2010-02-26 | 2010-06-17 | 2010-04-30 | 2010-04-23 | 2010-05-21 | 2010-05-25 |  | 2010-05-21 | 2010-05-25 | PERMITTED | 2010-03-12 | 2010-03-05 | 2010-04-16 | 2010-04-12 | 1 | 2010-04-23 | 2010-04-12 |  |  | 2011-05-13 | 2011-05-20 | 1 |  | 2011-05-13 | 2011-05-20 | 2011-06-04 |  |  |  |  | 2011-05-23 | 2011-05-24 | 2011-06-17 | 2011-06-16 | 2011-06-22 | 2011-06-17 | 2011-07-01 | [8 empty] | 2011-07-27 | 2011-08-15 | 2011-08-24 | 2011-08-15 | 2011-08-15 | 2011-11-15 | 2012-01-17 | 11/5/10 - Telecom Co-site approval received 28/07/11 - Site Integrated |  | 2011-07-25 |  | 2011-04-14 | 2011-06-06 | 2011-06-15 | 2011-06-04 | 2011-06-04 | 2011-06-22 | 2011-07-01 |  | 2011-08-03 | [7 empty] | FALSE |  | 2791548 | 6389271 | 100 Hull Road Mount Maunganui |  |  | CELLSITE |  |  | 2014-12-05 | [12 empty] | 2011-08-01 | 2011-08-03 | 2010-02-10
0 | BOP | 539 | BOP-023-007 | Arataki - TX Hub | BOP-023-007-B | 8 Titoki Place | Tauranga | 20 | TIER_2 | ACTIVE | GF | DU | P3 | grey | STACK_A | COSITE | 23 | 24.5 | 1 | -37.6813 | 176.2221 |  | 2009-12-17 |  | 2009-12-17 | Fibre Optic | BOP-023-004-A | TRUE | TRUE | 2010-02-18 |  | TRUE | 2010-03-12 | 2010-02-26 | 2010-02-26 |  |  | 2010-03-19 | 2010-03-18 | 2 | 2010-03-19 | 2010-06-17 |  | 2010-03-24 | 2010-04-01 | 2010-03-24 |  | 2010-07-27 | 2010-07-27 | PERMITTED | 2010-03-19 | 2010-03-19 | 2010-04-09 | 2010-03-29 | 1 | 2010-04-16 | 2010-03-29 |  |  | 2011-05-17 | 2011-06-10 | 1 |  | 2011-05-17 | 2011-06-10 | 2011-07-06 |  |  |  |  | 2011-05-30 | 2011-05-24 | 2011-07-22 | 2011-08-01 | 2011-07-11 | 2011-07-12 | 2011-07-11 | [8 empty] | 2011-08-05 | 2011-08-15 | 2011-08-24 | 2011-08-15 | 2011-08-15 | 2011-11-14 | 2012-06-29 | 11/5/10 - VF and Telecom Co-site approvals received |  | 2011-07-30 |  | 2011-04-14 | 2011-07-03 | 2011-07-06 | 2011-07-05 | 2011-07-06 | 2011-07-14 | 2011-07-11 |  | 2011-08-02 | [6 empty] | 2011-07-11 | FALSE |  | 2794369 | 6386146 | 8 Titoki Place Tauranga |  |  | CELLSITE |  |  | 2014-12-05 | [12 empty] | 2011-07-24 | 2011-08-01 | 2010-03-05
0 | BOP | 540 | BOP-023-008 | Tauranga Docks | BOP-023-008-B | Rail Land - Marsh street | Tauranga | 20 | TIER_2 | ACTIVE | GF | DU | P3 | grey | STACK_A | COSITE | 19.5 | 20 | 1 | -37.6731 | 176.1662 |  | 2009-12-17 |  | 2009-12-17 | Microwave | BOP-022-007-A | TRUE | TRUE | 2010-02-18 |  | TRUE | 2010-03-25 | 2010-03-12 | 2010-02-17 |  |  | 2010-02-22 | 2010-02-22 | 2 | 2010-02-22 | 2014-09-25 | 2010-04-30 | 2010-04-23 | 2010-07-28 | 2010-07-29 |  | 2010-08-03 | 2010-08-05 | PERMITTED | 2010-03-24 | 2010-03-25 | 2010-04-28 | 2010-04-15 | 1 | 2010-04-30 | 2010-04-15 |  |  | 2011-06-02 | 2011-06-09 | 1 |  | 2011-05-30 | 2011-06-09 | 2011-07-04 |  |  |  |  | 2011-07-04 | 2011-07-08 | 2011-07-15 | 2011-07-19 | 2011-07-19 | 2011-07-25 | 2011-07-29 | [8 empty] | 2011-07-28 | 2011-08-22 | 2011-08-24 | 2011-08-22 | 2011-08-15 | 2011-11-22 | 2012-02-01 | 11/5/10 - VF Co-site approval received 28/04/11 - Geotech to be undertaken - maybe fill on site. Quote for Power Route received |  | 2011-08-03 | 2011-06-20 | 2011-07-14 | 2011-07-04 | 2011-07-14 | 2011-07-04 | 2011-07-04 | 2011-07-15 | 2011-07-19 |  | 2011-08-02 | [6 empty] | 2011-07-19 | FALSE |  | 2789472 | 6387232 | Rail Land East Coast Main Railway Access - Marsh Street Tauranga |  |  | CELLSITE |  |  | 2014-12-05 | [12 empty] | 2011-08-01 | 2011-08-01 | 2010-01-21
0 | BOP | 541 | BOP-023-009 | Otumoetai Road North | BOP-023-009-D | LPR Brookfield - Otumoetai cnr | Tauranga | 20 | TIER_2 | ACTIVE | RSR | DU | P4F | green | INLINE | STANDALONE | 12.3 | 12.8 | 1 | -37.6839 | 176.1356 |  | 2009-12-17 |  | 2009-12-17 | Microwave | BOP-023-015-A | TRUE | TRUE | 2010-02-26 |  | TRUE | 2011-01-19 | 2010-05-04 | 2010-04-26 |  |  | 2010-05-03 | 2010-04-30 | 3 | 2010-05-03 | 2014-11-28 | 2010-06-14 | 2010-05-14 | 2011-02-11 | 2011-02-09 |  | 2011-02-18 | 2011-02-11 | NES | 2010-05-07 | 2010-05-05 | 2010-06-25 | 2010-06-25 | 1 | 2010-07-02 | 2010-07-02 |  |  | 2011-06-02 | 2011-06-10 | 1 |  | 2011-05-30 | 2011-06-10 | 2011-06-27 |  |  | 2011-06-07 |  | 2011-06-20 | 2011-06-20 | 2011-06-30 | 2011-07-11 | 2011-07-07 | 2011-07-24 | 2011-07-29 | [8 empty] | 2011-07-29 | 2011-08-15 | 2011-08-24 | 2011-08-15 | 2011-08-22 | 2011-11-21 | 2012-02-02 | 28/04/11 - GPR done. Power plinth to be identified by Authority 13/06/11 - Council Officer wants to relocate cabinets - 2 Degrees working on Council for NO changes, otherwise Lease and RMA impacted |  | 2011-08-02 | 2011-06-08 | 2011-06-08 | 2011-06-13 | 2011-06-27 | 2011-06-20 | 2011-06-27 | 2011-07-06 | 2011-07-15 |  | 2011-08-02 | [6 empty] | 2011-07-07 | TRUE |  | 2786735 | 6386135 | Cnr Broofield Tce and Otumoetai Road Otumoetai Tauranga |  |  | CELLSITE |  |  | 2015-05-27 | [12 empty] | 2011-08-01 | 2011-08-01 | 2010-04-26
0 | BOP | 542 | BOP-023-010 | Bethlehem | BOP-023-010-E | Transit Land SH2 Bethlehem shops | Tauranga | 20 | TIER_2 | ACTIVE | GF | DU | P2 | grey | STACK_A | COSITE | 20.6 | 21.1 | 1 | -37.6958 | 176.1107 |  | 2009-12-17 |  | 2009-12-17 | Microwave | BOP-022-019-A | TRUE | TRUE | 2010-01-29 |  | TRUE | 2010-10-18 | 2010-05-11 | 2010-05-11 |  |  | 2010-05-28 | 2010-05-28 | 3 | 2010-05-28 | 2015-01-16 | 2010-06-25 | 2010-06-24 | 2011-03-18 | 2011-03-18 |  | 2011-03-25 | 2011-03-24 | PERMITTED | 2010-07-16 | 2010-07-08 | 2010-09-09 | 2010-09-01 | 1 | 2010-09-09 | 2010-09-10 |  |  | 2011-05-27 | 2011-05-27 | 1 |  | 2011-05-27 | 2011-05-27 | 2011-06-23 |  |  | 2011-04-21 |  | 2011-06-13 | 2011-06-09 | 2011-07-22 | 2011-07-22 | 2011-07-08 | 2011-07-13 | 2011-07-08 | [8 empty] | 2011-07-26 | 2011-08-15 | 2011-08-24 | 2011-08-15 | 2011-08-15 | 2011-11-14 | 2012-06-06 | 26/07/11 - Site integrated |  | 2011-07-27 |  | 2011-04-14 | 2011-06-06 | 2011-06-06 | 2011-06-23 | 2011-06-23 | 2011-07-13 | 2011-07-08 |  | 2011-08-02 | [6 empty] | 2011-07-11 | TRUE |  | 2784490 | 6384894 | Transit land Cnr SH2 and Moffat Bethlehem Tauranga |  |  | CELLSITE |  |  | 2015-05-27 | [12 empty] | 2011-08-01 | 2011-08-01 | 2010-05-11
0 | BOP | 543 | BOP-023-011 | Greerton | BOP-023-011-B | 22 Sherson Street | Tauranga | 20 | TIER_2 | ACTIVE | GF | DU | P2 | grey | STACK_A | STANDALONE | 20.2 | 20.7 | 2 | -37.7244 | 176.1276 |  | 2009-12-17 |  | 2009-12-17 | Microwave | BOP-022-019-A | TRUE | TRUE | 2010-01-29 |  | TRUE | 2010-02-19 | 2010-02-12 | 2010-01-28 |  |  | 2010-02-12 | 2010-02-16 | 3 | 2010-02-12 | 2011-03-10 |  | 2010-03-17 | 2010-03-22 | 2010-03-17 |  | 2010-03-29 | 2010-03-17 | PERMITTED | 2010-02-26 | 2010-02-23 | 2010-04-09 | 2010-03-16 | 1 | 2010-04-16 | 2010-03-16 |  |  | 2011-05-13 | 2011-05-20 | 1 |  | 2011-05-13 | 2011-05-20 | 2011-06-04 |  |  |  |  | 2011-05-16 | 2011-05-16 | 2011-06-17 | 2011-06-16 | 2011-06-22 | 2011-06-29 | 2011-07-01 | [8 empty] | 2011-08-07 | 2011-08-22 | 2011-08-24 | 2011-08-22 | 2011-08-25 | 2011-11-23 | 2012-06-27 | 15/12/11 - Headframe still to be swapped out. To be done in New Year. Drive Team need to be kept informed so they can test after the work done |  | 2011-08-10 |  | 2011-04-14 | 2011-06-06 | 2011-06-06 | 2011-06-04 | 2011-06-04 | 2011-06-23 | 2011-07-01 |  | 2011-08-08 | [7 empty] | FALSE |  | 2785872 | 6381663 | 23 Sherson Street, Gate Pa |  |  | CELLSITE |  |  | 2015-05-27 | [12 empty] | 2011-08-08 | 2011-08-08 | 2010-01-28
0 | BOP | 544 | BOP-023-012 | Papamoa Beach | BOP-023-012-B | Mitre 10, Palm Beach Shopping Centre | Tauranga | 20 | TIER_2 | ACTIVE | GF | DU | P2 | grey | STACK_A | STANDALONE | 20.2 | 20.7 | 1 | -37.7024 | 176.2829 |  | 2009-12-17 |  | 2009-12-17 | Microwave | BOP-023-018-B | TRUE | TRUE | 2010-04-07 | 2010-04-23 | TRUE | 2010-05-06 | 2010-03-19 | 2010-03-15 |  |  | 2010-04-01 | 2010-04-07 | 3 | 2010-04-01 | 2010-06-15 | 2010-04-23 | 2010-04-22 | 2010-04-23 | 2010-04-22 |  | 2010-08-26 | 2010-08-13 | DISCRETIONARY_RESTRICT | 2010-04-09 | 2010-04-07 | 2010-05-14 | 2010-05-10 | 1 | 2010-05-21 | 2010-05-10 |  |  | 2011-05-20 | 2011-06-01 | 1 |  | 2011-05-20 | 2011-06-01 | 2011-06-20 |  |  |  |  | 2011-05-23 | 2011-05-25 | 2011-07-22 | 2011-07-27 | 2011-06-30 | 2011-07-13 | 2011-07-13 | [8 empty] | 2011-07-27 | 2011-08-15 | 2011-08-24 | 2011-08-15 | 2011-08-15 | 2011-11-14 | 2012-04-13 | 28/07/11 - Site integrated |  | 2011-07-27 |  | 2011-04-14 | 2011-06-06 | 2011-06-06 | 2011-06-04 | 2011-06-20 | 2011-07-06 | 2011-07-06 |  | 2011-08-02 | [7 empty] | FALSE |  | 2799641 | 6383609 | Mitre 10 off Gravatt Road Palm Beach Shopping Centre Papamoa |  |  | CELLSITE |  |  | 2014-12-05 | [12 empty] | 2011-08-01 | 2011-08-01 | 2010-03-15
0 | BOP | 545 | BOP-023-013 | Papamoa East | BOP-023-013-A | Papamoa East | Tauranga | 20 | TIER_2 | ACTIVE | GF | DU | P2 | grey | STACK_A | STANDALONE | 20.4 | 20.9 |  | -37.7114 | 176.3167 |  | 2009-12-17 |  | 2009-12-17 | Microwave | BOP-022-007-A | TRUE | TRUE | 2010-01-22 |  | TRUE | 2010-02-19 | 2010-01-22 | 2010-01-20 |  |  | 2010-02-04 | 2010-02-08 | 4 | 2010-02-04 | 2010-06-17 |  | 2010-03-10 | 2010-03-19 | 2010-03-10 |  | 2010-03-26 | 2010-03-10 | PERMITTED | 2010-02-12 | 2010-02-11 | 2010-03-12 | 2010-02-23 | 2 | 2010-03-19 | 2010-02-23 |  |  | 2011-06-02 | 2011-06-09 | 1 |  | 2011-05-30 | 2011-06-09 | 2011-06-09 |  |  |  |  | 2011-06-15 | 2011-06-20 | 2011-07-08 | 2011-07-11 | 2011-07-07 | 2011-07-22 | 2011-07-29 | [8 empty] | 2011-07-30 | 2011-08-22 | 2011-08-24 | 2011-08-22 | 2011-08-15 | 2011-11-22 | 2012-01-17 | 2/3 - new headframe design required 11/3/10 - site is hardmatched 30/4 - RMA lodgment version should be 2. Version 3 was not submitted as no changes affected RMA |  | 2011-08-03 | 2011-06-08 | 2011-06-08 | 2011-06-13 | 2011-06-27 | 2011-06-09 | 2011-06-09 | 2011-07-15 | 2011-07-15 |  | 2011-08-02 | [6 empty] | 2011-07-07 | FALSE |  | 2802581 | 6382509 | 1 Market Place Papamoa |  | Permitted to None None - 20/05/2010 | CELLSITE |  |  | 2014-12-05 | [12 empty] | 2011-08-01 | 2011-08-01 | 2010-01-20
0 | BOP | 546 | BOP-023-014 | Omanu | BOP-023-014-B | Ontrack beside KFC | Tauranga | 20 | TIER_2 | ACTIVE | GF | DU | P3 | grey | STACK_A | STANDALONE | 23.4 | 23.9 |  | -37.6644 | 176.2074 |  | 2009-12-17 |  | 2009-12-17 | Microwave | BOP-023-007-B | TRUE | TRUE | 2010-02-18 |  | TRUE | 2010-03-25 | 2010-03-15 | 2010-03-15 |  |  | 2010-03-26 | 2010-03-26 | 5 | 2010-06-30 | 2014-09-25 | 2010-04-30 | 2010-04-23 | 2010-07-28 | 2010-07-29 |  | 2011-08-12 | 2011-08-25 | PERMITTED | 2010-04-12 | 2010-04-15 | 2010-06-10 | 2010-06-10 | 2 | 2011-09-15 | 2011-09-02 |  |  | 2011-06-24 | 2011-06-30 | 1 |  | 2011-06-24 | 2011-06-30 | 2011-07-07 |  |  |  |  | 2011-06-02 | 2011-06-02 | 2011-07-13 | 2011-07-29 | 2011-07-15 | 2011-07-18 | 2011-07-19 | [8 empty] | 2011-07-29 | 2011-08-15 | 2011-08-24 | 2011-08-15 | 2011-08-15 | 2011-11-14 | 2012-02-07 | 2/9/11 - Council have advised site is in general accordance. Email is filed in Site Folder |  | 2011-07-31 |  | 2011-04-14 | 2011-06-06 | 2011-06-06 | 2011-07-05 | 2011-07-07 | 2011-07-18 | 2011-07-19 |  | 2011-08-04 | [7 empty] | FALSE |  | 2793140 | 6388065 | Ontrack Land Cnr of Hewletts Rd, & Maunganui Rd, Tauranga, Bay of Plenty |  | Permitted to 20.00 AGL - 20/05/2010 | CELLSITE |  |  | 2014-12-05 | [12 empty] | 2011-07-20 | 2011-08-03 | 2010-03-15
0 | BOP | 547 | BOP-023-015 | Tauranga South | BOP-023-015-A | Telecom Co-Locate | Tauranga | 20 | TIER_2 | ACTIVE | COLO | DU | COLO | grey | STACK_A | COLO | 27.6 | 35.5 |  | -37.6995 | 176.1592 |  | 2009-12-17 |  | 2009-12-17 | Microwave | BOP-023-004-A | TRUE | TRUE | 2010-02-18 |  | TRUE | 2010-02-19 | 2010-03-15 | 2010-03-15 |  |  | 2010-04-06 | 2010-04-01 | 3 | 2010-04-06 | 2014-11-28 | 2010-05-14 | 2010-05-07 | 2011-04-04 | 2011-02-28 |  | 2011-04-11 | 2011-02-28 | DISCRETIONARY_FULL | 2010-04-30 | 2010-04-22 | 2010-05-28 | 2010-05-24 | 1 | 2010-05-31 | 2010-05-24 |  |  | 2011-07-01 | 2011-06-28 | 1 |  | 2011-07-01 | 2011-06-28 | 2011-07-20 |  |  |  |  | 2011-07-13 | 2011-07-13 | 2011-07-15 | 2011-07-20 | 2011-07-20 | 2011-07-22 | 2011-07-29 | [8 empty] | 2011-07-31 | 2011-08-15 | 2011-08-24 | 2011-08-15 | 2011-08-22 | 2011-11-21 | 2012-02-02 | 15/12/11 - SOA. Telecom have double allocated some space with Police. Ron sorted with Roger Collinge. Police will supply some info for adding to as builts | TNZ | 2011-08-04 | 2011-06-20 | 2011-07-20 | 2011-07-04 | 2011-07-14 | 2011-07-20 | 2011-07-20 | 2011-07-14 | 2011-07-20 |  | 2011-08-02 | [6 empty] | 2011-07-20 | FALSE |  | 2788757 | 6384333 | Telecom Tauranga Exchange MTCE 540 Cameron Road Tauranga |  | Permitted to 20.00 AGL - 20/05/2010 | CELLSITE |  |  | 2015-05-27 | [12 empty] | 2011-08-01 | 2011-08-01 | 2010-03-15
0 | BOP | 548 | BOP-023-016 | Parkvale | BOP-023-016-C | LPR Fraser/Kesteven cnr | Tauranga | 20 | TIER_2 | ACTIVE | RSR | DU | P4F | green | INLINE | STANDALONE | 14.4 | 14.9 |  | -37.7208 | 176.1454 |  | 2010-03-31 |  | 2009-12-17 | Microwave | BOP-022-007-A | TRUE | TRUE | 2010-03-30 | 2010-04-02 | TRUE | 2011-01-19 | 2010-03-31 | 2010-03-30 |  |  | 2010-04-16 | 2010-04-21 | 4 | 2010-04-16 | 2014-11-27 | 2010-05-14 | 2010-05-06 | 2010-06-18 | 2010-06-18 |  | 2010-06-18 | 2010-06-18 | NES | 2010-04-30 | 2010-05-06 | 2010-06-25 | 2010-06-24 | 1 | 2010-06-25 | 2010-06-24 |  |  | 2011-06-02 | 2011-06-10 | 1 |  | 2011-05-30 | 2011-06-10 | 2011-07-14 |  |  | 2011-06-07 |  | 2011-07-04 | 2011-06-29 | 2011-07-15 | 2011-07-14 | 2011-07-09 | 2011-07-21 | 2011-07-29 | [8 empty] | 2011-08-04 | 2011-08-22 | 2011-08-24 | 2011-08-22 | 2011-08-23 | 2011-11-21 | 2012-02-27 | 15/12/11 - Site all good |  | 2011-08-03 | 2011-06-08 | 2011-06-08 | 2011-06-13 | 2011-06-27 | 2011-07-21 | 2011-07-14 | 2011-07-11 | 2011-07-15 |  | 2011-08-08 | [6 empty] | 2011-07-09 | TRUE |  | 2787453 | 6382010 | Cnr Fraser St and Kesteven Avenue Greerton Tauranga |  |  | CELLSITE |  |  | 2015-05-27 | [12 empty] | 2011-08-08 | 2011-08-08 | 2010-03-30
0 | BOP | 549 | BOP-023-017 | Poike | BOP-023-017-B | 46 Maleme Street (VF Co-Lo) | Tauranga | 20 | TIER_2 | ACTIVE | COLO | DU | COLO | grey | STACK_A | COLO | 19 | 23 |  | -37.7367 | 176.1368 |  | 2009-12-17 |  | 2009-12-17 | Microwave | BOP-022-007-A | TRUE | TRUE | 2010-01-28 |  | TRUE | 2010-02-19 | 2010-01-20 | 2010-01-20 |  |  | 2010-03-12 | 2010-03-03 | 4 | 2010-03-12 | 2010-04-06 | 2010-05-28 | 2010-05-20 | 2010-12-01 | 2010-11-19 |  | 2010-12-01 | 2010-11-19 | PERMITTED | 2010-03-19 | 2010-03-05 | 2010-04-09 | 2010-03-24 | 1 | 2010-04-16 | 2010-03-24 |  |  | 2011-06-02 | 2011-06-14 | 1 |  | 2011-05-30 | 2011-06-14 | 2011-07-18 |  |  |  |  | 2011-07-04 | 2011-07-01 | 2011-07-21 | 2011-07-29 | 2011-07-20 | 2011-07-22 | 2011-07-29 | [8 empty] | 2011-08-03 | 2011-08-22 | 2011-08-24 | 2011-08-22 | 2011-08-24 | 2011-11-22 | 2012-07-31 | 15/12/11 - Shroud to be completed. Rain has delayed work until new year | VNZ | 2011-08-03 | 2011-06-20 | 2011-07-14 | 2011-07-04 | 2011-07-14 | 2011-07-15 | 2011-07-18 | 2011-07-20 | 2011-07-29 |  | 2011-08-08 | [6 empty] | 2011-07-20 | FALSE |  | 2786637 | 6380273 | 46 Melane Street |  |  | CELLSITE |  |  | 2015-05-27 | [12 empty] | 2011-08-08 | 2011-08-08 | 2010-02-17
0 | BOP | 550 | BOP-023-018 | Papamoa North | BOP-023-018-B | Vodafone Papamoa Nth Co-locate | Tauranga | 20 | TIER_2 | ACTIVE | COLO | DU | COLO | grey | STACK_A | COLO | 17.1 | 20 |  | -37.697 | 176.2529 |  | 2009-12-17 |  | 2009-12-17 | Microwave | BOP-023-007-B | TRUE | TRUE | 2010-02-25 | 2010-03-12 | TRUE | 2010-03-12 | 2010-03-12 | 2010-02-25 |  |  | 2010-03-05 | 2010-03-05 | 4 | 2010-03-05 | 2010-06-17 | 2010-05-28 | 2010-05-20 | 2010-12-23 | 2010-12-06 |  | 2010-12-23 | 2010-12-06 | PERMITTED | 2010-04-12 | 2010-04-15 | 2010-05-20 | 2010-05-21 | 3 | 2010-05-27 | 2010-05-21 |  |  | 2011-04-27 | 2011-04-01 | 1 |  |  | 2011-04-01 | 2011-05-04 |  |  |  |  | 2011-06-22 | 2011-06-22 | 2011-07-04 | 2011-07-01 | 2011-07-08 | 2011-07-13 | 2011-07-19 | [8 empty] | 2011-07-29 | 2011-08-15 | 2011-08-24 | 2011-08-15 | 2011-08-25 | 2011-11-15 | 2012-01-17 | 27/07/11 - Site integrated | VNZ | 2011-07-31 |  | 2011-04-14 | 2011-06-06 | 2011-06-06 |  | 2011-05-04 | 2011-07-04 | 2011-07-05 |  | 2011-08-02 | [6 empty] | 2011-07-08 | FALSE |  | 2797016 | 6384305 | VF Papamoa North site SH29 Papamoa |  |  | CELLSITE |  |  | 2014-12-05 | [12 empty] | 2011-08-01 | 2011-08-01 | 2010-02-25
0 | BOP | 551 | BOP-023-019 | Minden |  |  | Tauranga |  | TIER_9 | [22 empty] | TRUE | [60 empty] | General coverage to the North West of Tauranga. Co-location opportunity.
0 | BOP | 552 | BOP-023-020 | Welcome Bay | BOP-023-020-B | Transit land, Taupari St/Maungatapu cnr | Tauranga | 20 | TIER_2 | ACTIVE | GF | DU | P2 | green | STACK_A | COSITE | 20.2 | 20.7 | 1 | -37.7166 | 176.181 |  | 2009-12-17 |  | 2009-12-17 | Microwave | BOP-023-015-A | TRUE | TRUE | 2010-01-20 |  | TRUE | 2010-02-19 | 2010-01-20 | 2010-01-20 | 2010-01-20 | 2010-01-20 | 2010-02-08 | 2010-02-09 | 3 | 2010-02-08 | 2010-10-13 | 2010-04-16 | 2010-05-12 | 2011-07-22 | 2011-07-22 |  | 2011-07-29 | 2011-07-22 | DISCRETIONARY_FULL | 2010-03-30 | 2010-03-31 | 2011-05-20 | 2011-05-18 | 1 | 2011-05-27 | 2011-05-18 |  |  | 2011-08-22 | 2011-08-16 | 1 |  | 2011-08-22 | 2011-08-16 | 2011-07-15 |  |  |  |  | 2011-07-18 | 2011-08-18 | 2011-09-21 | 2011-09-21 | 2011-09-08 | 2011-09-18 | 2011-09-19 | [8 empty] | 2011-09-20 | 2011-10-07 | 2011-10-11 | 2011-10-22 | 2011-10-21 | 2012-01-19 | 2012-05-01 | 29/09/11 - Site has been integrated, but suffering RF issues on sectors. Huawei working through options and problem solving. SOA date extended 06/10/11 - SOA with 2100 only. 900 has interference. |  | 2011-09-20 | 2011-07-11 | 2011-08-15 | 2011-08-23 | 2011-08-23 | 2011-07-15 | 2011-07-15 | 2011-08-31 | 2011-09-08 |  | 2011-10-05 | [6 empty] | 2011-08-29 | FALSE |  | 2790609 | 6382367 | Taupiri Street, Mangatapu road intersection Welcome bay Tauranga |  |  | CELLSITE |  |  | 2015-05-27 | [12 empty] | 2011-10-04 | 2011-10-04 | 2010-01-20
0 | BOP | 553 | BOP-023-021 | Tauranga Airport |  |  | Tauranga |  | TIER_9 | [22 empty] | TRUE | [60 empty] | Metro Coverage in all directions. New Greenfield Site at Airport.
0 | BOP | 554 | BOP-023-022 | Hairini Heights | BOP-023-022-B | LPR Ohauiti Road | Tauranga | 20 | TIER_2 | ACTIVE | RSR | DU | P4F | green | INLINE | STANDALONE | 13.5 | 14 |  | -37.7498 | 176.1652 | 2010-03-12 | 2010-03-08 | 2010-03-12 | 2010-03-08 | Microwave | BOP-023-003-A | TRUE | TRUE | 2010-03-18 | 2010-04-02 | TRUE | 2010-05-20 | 2010-05-11 | 2010-05-11 |  |  | 2010-05-18 | 2010-05-20 | 5 | 2010-05-21 | 2014-12-11 | 2010-05-28 | 2010-05-14 | 2010-06-18 | 2010-06-18 |  | 2010-06-18 | 2010-06-18 | NES | 2010-05-21 | 2010-05-26 | 2010-07-01 | 2010-07-06 | 1 | 2010-07-01 | 2010-07-21 |  |  | 2011-06-02 | 2011-06-03 | 3 |  | 2011-05-30 | 2011-06-27 | 2011-06-27 |  |  | 2011-06-07 |  | 2011-07-04 | 2011-06-29 | 2011-07-15 | 2011-07-11 | 2011-07-09 | 2011-07-25 | 2011-07-29 | [8 empty] | 2011-08-05 | 2011-08-22 | 2011-08-24 | 2011-08-22 | 2011-08-23 | 2011-11-21 | 2012-04-10 | 15/12/11 - Council have accepted high hatch on pole but "we are pushing it" |  | 2011-08-05 | 2011-06-08 | 2011-06-08 | 2011-06-13 | 2011-06-27 | 2011-06-20 | 2011-06-27 | 2011-07-16 | 2011-07-15 |  | 2011-08-08 | [6 empty] | 2011-07-09 | TRUE |  | 2789085 | 6378732 | LPR Ohauiti Rd, Opposite Buxton Place Hairini Tauranga |  | COC reference - RC15146 - 21/07/2010 | CELLSITE |  |  | 2015-05-27 | [12 empty] | 2011-08-08 | 2011-08-08 | 2010-05-11
0 | BOP | 555 | BOP-023-023 | Barkes Corner | BOP-023-023-A | LPR - opp 78 Pyes Pa Rd | Tauranga | 20 | TIER_2 | ACTIVE | RSR | DU | P4F | green | INLINE | STANDALONE | 14.6 | 15.1 |  | -37.7418 | 176.1222 | 2010-03-12 | 2010-03-04 | 2010-03-12 | 2010-03-04 | Microwave | BOP-022-007-A | TRUE | TRUE | 2010-03-16 | 2010-03-26 | TRUE | 2010-03-25 | 2010-03-19 | 2010-03-16 |  |  | 2010-04-05 | 2010-03-26 | 3 | 2010-04-05 | 2014-11-28 | 2010-05-14 | 2010-05-06 | 2011-07-08 | 2011-06-23 |  | 2011-07-08 | 2011-06-23 | NES | 2010-05-03 | 2010-05-05 | 2010-07-27 | 2010-07-16 | 1 | 2010-07-27 | 2010-07-21 |  |  | 2011-09-08 | 2011-09-08 | 1 |  | 2011-07-01 | 2011-09-08 | 2011-09-05 |  |  |  |  | 2011-08-31 | 2011-09-05 | 2011-09-19 | 2011-09-19 | 2011-09-09 | 2011-09-21 | 2011-09-23 | [8 empty] | 2011-09-29 | 2011-10-07 | 2011-10-04 | 2011-10-22 | 2011-10-21 | 2012-01-19 | 2012-05-29 | 29/09/11 - Site has been integrated, but suffering RF issues on sectors. Huawei working through options and problem solving. SOA date extended |  | 2011-09-22 | 2011-08-30 | 2011-08-30 | 2011-08-31 | 2011-08-31 | 2011-08-31 | 2011-09-05 | 2011-09-13 | 2011-09-15 |  | 2011-10-05 | [6 empty] | 2011-09-06 | FALSE |  | 2785327 | 6379748 | LPR Over Road from 78 Pyres Pa Road Pyes Pa Tauranga |  | COC reference - RC15107 - 21/07/2010 | CELLSITE |  |  | 2015-05-27 | [12 empty] | 2011-10-04 | 2011-10-04 | 2010-03-16
0 | BOP | 556 | BOP-023-024 | Tauriko | BOP-023-024-A | Tauriko Business Estate | Tauranga | 20 | TIER_2 | ACTIVE | GF | DU | P3 | grey | STACK_A | COSITE | 20.65 | 21.15 |  | -37.7421 | 176.1044 |  | 2009-12-17 |  | 2009-12-17 | Fibre Optic | BOP-023-003-A | TRUE | TRUE | 2010-03-19 | 2010-03-30 | TRUE |  | 2010-03-16 | 2010-03-16 |  |  | 2010-04-06 | 2010-04-06 | 2 | 2010-04-06 | 2010-11-16 | 2010-06-18 | 2010-06-11 | 2010-09-16 | 2010-09-10 |  | 2010-09-16 | 2010-09-10 | DISCRETIONARY_FULL | 2010-04-23 | 2010-04-21 | 2010-05-25 | 2010-05-26 | 1 | 2010-05-28 | 2010-05-26 |  |  | 2011-05-16 | 2011-05-17 | 1 |  | 2011-05-16 | 2011-05-17 | 2011-05-23 |  |  |  |  | 2011-05-09 | 2011-05-11 | 2011-06-17 | 2011-06-16 | 2011-06-22 | 2011-06-29 | 2011-07-01 | [8 empty] | 2011-08-08 | 2011-08-22 | 2011-08-24 | 2011-08-22 | 2011-08-25 | 2011-11-22 | 2012-01-17 | 23/06/11 - Owners have sent through email re requiring power and telco to be 2m deep. To find out why and what can be done |  | 2011-07-25 |  | 2011-04-14 | 2011-06-06 | 2011-06-06 | 2011-05-23 | 2011-05-23 | 2011-06-23 | 2011-07-01 |  | 2011-08-08 | [7 empty] | FALSE |  | 2783755 | 6379769 | Tauriko Business Estate 5 Taurikura Drive Tauranga |  | Permitted to 20.00 AGL - 20/05/2010 | CELLSITE |  |  | 2015-05-27 | [12 empty] | 2011-07-14 | 2011-08-08 | 2010-03-16
0 | BOP | 557 | BOP-023-025 | Matua | BOP-023-025-B | LPR - Levers Rd / Heron Ave cnr | Tauranga | 20 | TIER_2 | ACTIVE | RSR | DU | P4F | green | INLINE | STANDALONE | 13.2 | 13.7 |  | -37.6692 | 176.1237 |  | 2009-12-17 |  | 2009-12-17 | Microwave | BOP-022-019-A | TRUE | TRUE | 2010-02-18 |  | TRUE | 2010-05-20 | 2010-05-11 | 2010-05-11 |  |  | 2010-05-20 | 2010-05-20 | 4 | 2010-05-21 | 2015-05-01 | 2010-05-21 | 2010-05-14 | 2010-06-18 | 2010-06-18 |  | 2010-06-18 | 2010-06-18 | NES | 2010-05-28 | 2015-05-05 | 2010-07-02 |  | 4 | 2010-07-09 | 2010-06-18 |  |  | 2011-03-29 | 2011-04-01 | 1 |  |  | 2011-04-01 | 2011-05-30 |  |  | 2011-06-07 |  | 2011-07-14 | 2011-07-13 | 2011-07-18 | 2011-07-29 | 2011-07-19 | 2011-07-22 | 2011-07-29 | [8 empty] | 2011-07-29 | 2011-08-15 | 2011-08-24 | 2011-08-15 | 2011-08-15 | 2011-11-14 | 2012-02-20 | 15/12/11 - Site Good. FAN issued |  | 2011-08-01 |  | 2011-04-14 | 2011-06-06 | 2011-06-20 | 2011-05-30 | 2011-05-30 | 2011-07-21 | 2011-07-29 |  | 2011-08-04 | [6 empty] | 2011-07-19 | TRUE |  | 2785742 | 6387800 | LPR cnr Levers Rd/Heron st Matua |  |  | CELLSITE |  |  | 2015-10-13 | [12 empty] | 2011-07-19 | 2011-08-03 | 2010-05-11
0 | BOP | 558 | BOP-023-026 | Cambridge Heights | BOP-023-026-B | Cambridge Road (LPR) | Tauranga | 20 | TIER_2 | ACTIVE | RSR | DU | P4F | green | INLINE | STANDALONE | 15.5 | 16 |  | -37.699 | 176.132 |  |  |  | 2009-12-17 | Microwave | BOP-023-003-A | TRUE | TRUE | 2010-02-11 |  | TRUE | 2010-03-25 | 2010-03-16 | 2010-03-16 |  |  | 2010-03-26 | 2010-03-26 | 2 | 2010-03-26 | 2014-11-28 | 2010-05-14 | 2010-05-06 | 2010-06-18 | 2010-06-18 |  | 2010-06-18 | 2010-06-18 | NES | 2010-04-01 | 2010-03-31 | 2010-05-06 | 2010-04-28 | 1 | 2010-05-13 | 2010-04-28 |  |  | 2011-06-02 | 2011-06-10 | 1 |  | 2011-05-30 | 2011-06-10 | 2011-06-27 |  |  | 2011-06-07 |  | 2011-07-04 | 2011-06-22 | 2011-07-15 | 2011-07-11 | 2011-07-07 | 2011-07-20 | 2011-07-29 | [8 empty] | 2011-08-05 | 2011-08-22 | 2011-08-24 | 2011-08-22 | 2011-08-23 | 2011-11-21 | 2012-04-30 | 15/12/11 - Site Good. 30/03/12 - FAN in circulation for sign-off |  | 2011-08-05 | 2011-06-08 | 2011-06-08 | 2011-06-13 | 2011-06-27 | 2011-06-20 | 2011-06-27 | 2011-07-15 | 2011-07-15 |  | 2011-08-08 | [6 empty] | 2011-07-07 | TRUE |  | 2786354 | 6384468 | TCC Lightpole cnr Cambridge Road and Te Atatu Place Tauranga |  |  | CELLSITE |  |  | 2015-05-27 | [12 empty] | 2011-08-08 | 2011-08-08 | 2010-03-16
0 | BOP | 559 | BOP-023-027 | Cambridge Road |  |  | Tauranga |  | TIER_9 | [22 empty] | TRUE | [60 empty] | Metro Coverage to the SW of Tauranga. New Greenfield Site.
0 | BOP | 560 | BOP-023-028 | Grange Rd | BOP-023-028-B | 126 Grange Road | Tauranga | 20 | TIER_2 | ACTIVE | GF | DU | P4B | grey | INLINE | STANDALONE | 10 | 10.5 |  | -37.6767 | 176.1471 |  | 2009-12-17 |  | 2009-12-17 | Microwave | BOP-023-015-A | TRUE | TRUE | 2010-03-18 | 2010-03-19 | TRUE | 2010-03-10 |  | 2010-02-24 |  |  | 2010-03-19 | 2010-03-19 | 1 | 2010-03-19 | 2010-03-19 | 2010-06-25 | 2010-06-24 | 2010-08-06 | 2010-08-04 |  | 2010-08-06 | 2010-08-04 | DISCRETIONARY_FULL | 2010-03-23 | 2010-03-19 | 2010-04-23 | 2010-04-26 | 1 | 2010-04-30 | 2010-04-26 |  |  | 2011-06-02 | 2011-06-03 | 1 |  | 2011-05-30 | 2011-06-03 | 2011-07-11 |  |  | 2011-06-20 |  | 2011-07-27 | 2011-06-29 | 2011-08-04 | 2011-08-04 | 2011-07-12 | 2011-08-04 | 2011-08-04 | [8 empty] | 2011-08-05 | 2011-08-22 | 2011-08-24 | 2011-08-22 | 2011-08-24 | 2011-11-22 | 2012-04-11 | 15/12/11 Site OK |  | 2011-08-05 | 2011-06-08 | 2011-06-08 | 2011-06-13 | 2011-06-27 | 2011-06-27 | 2011-07-11 | 2011-08-04 | 2011-07-22 |  | 2011-08-08 | [6 empty] | 2011-07-12 | TRUE |  | 2787773 | 6386896 | 126 Grange Road Otumoetai Tauranga |  |  | CELLSITE |  |  | 2015-05-27 | [12 empty] | 2011-08-08 | 2011-08-08 | 2010-02-24
0 | BOP | 561 | BOP-023-029 | Bureta | BOP-023-029-B | LPR Bureta/Ngatea Rd | Tauranga | 20 | TIER_2 | ACTIVE | RSR | DU | P4F | green | INLINE | STANDALONE | 13.4 | 13.9 | 1 | -37.6677 | 176.1533 | 2010-03-12 | 2010-03-12 |  | 2010-03-12 | Microwave | BOP-023-001-D | TRUE | TRUE | 2010-03-18 |  | TRUE |  | 2011-05-24 | 2011-05-24 | 2011-06-02 | 2011-06-02 | 2011-07-15 | 2011-07-19 | 2 | 2011-07-15 | 2014-11-28 | 2011-07-15 | 2011-07-11 | 2011-09-12 | 2011-09-09 |  | 2011-09-12 | 2011-09-09 | DISCRETIONARY_FULL | 2011-08-12 | 2011-08-16 | 2011-09-08 | 2011-09-07 | 1 | 2011-09-08 | 2011-09-07 |  |  |  | 2011-09-13 | 1 |  |  | 2011-09-13 | 2011-09-01 |  |  |  |  | 2011-09-14 | 2011-09-14 | 2011-09-26 | 2011-09-23 | 2011-09-23 | 2011-10-20 | 2011-11-11 | [8 empty] | 2011-10-27 | 2011-10-14 | 2011-11-08 | 2012-02-24 | 2011-11-15 | 2012-02-13 | 2012-05-29 | 29/09/11 - Site under construction. Pole in, cabinets to be wired up. SOA date extended from 30 Sept to 14 Oct - resources short to complete job 27/10/11 - Initial link was installed to TGA Docks !!. Now correct to Mt Maunganui. However passing ships sometimes will break link. TX aware but will monitor. Lease line is expensive option |  | 2011-10-20 | 2011-08-22 | 2011-08-22 | 2011-09-01 | 2011-09-01 | 2011-09-01 | 2011-09-01 | 2011-09-30 | 2011-09-30 |  | 2011-11-14 | [6 empty] | 2011-09-21 | FALSE |  | 2788358 | 6387872 | LPR cnr Bureta and Ngatea Roads 25 Bureta Rd, Bureta, Tauranga |  | TCC Ref: RC15683 - 09/09/2011 | CELLSITE |  |  | 2015-05-27 | [12 empty] | 2011-10-20 | 2011-11-11 | 2011-06-02
0 | BOP | 562 | BOP-023-030 | Hairini |  |  | Tauranga |  | TIER_9 | [22 empty] | FALSE | [60 empty] | Coverage to match up with surrounding sites. Welcome Bay, Hairini Heights, Poike, & Kordia (Papamoa).
0 | BOP | 563 | BOP-023-031 | Wairoa |  |  | Tauranga |  | TIER_9 | [22 empty] | FALSE | [60 empty] | New Nominal to provide coverage to the west of Cambridge Rd.
0 | BOP | 564 | BOP-023-032 | Maungatapu |  |  | Tauranga |  | TIER_9 | [22 empty] | FALSE | [60 empty] | Coverage to the south part of the Maungatapu Peninsula. Linking up coverage with Maungatapu North, Hairini Heights, Poike, Papamoa, Parkvale & Tauranga Hospital.
0 | BOP | 565 | BOP-023-033 | Maungatapu North |  |  | Tauranga |  | TIER_9 | [22 empty] | FALSE | [60 empty] | Coverage to the following areas. The Northern part of Maungatapu (North of Taipari St), Welcome Bay to the SW , Metapihi and State Hwy 2 to the NW & Tauranga South to the NE. The following locations areas can be considered for a pole site. Te Wati Park, a LPR on high ground near 311 Maungatapu Rd, pole near SH2 at the rear of 311 Maungatapu Rd, an LPR near Te Wati Park. A pole site that overlooks Maungatapu North (across Water to the East near Ranginui Rd). Plus any other site that maximizes coverage to the coverage area. Preference for sites that maximize coverage to the coverage areas as predicted on the prediction tool. LPR identified on site visit 18/1/11 - Te Wati St
0 | BOP | 566 | BOP-023-034 | Mt Maunganui Chorus Co-Lo | BOP-023-034-A | Mt Maunganui Chorus TX only | Tauranga |  | TIER_6 | ACTIVE | COLO | TX | COLO |  |  | COLO | [103 empty] | TXSITE | WIPACTIVE
0 | BOP | 567 | BOP-023-035 | PAPAMOA WEST | BOP-023-035-A | Papamoa West LPR | Tauranga | 23 | 2015P | ACTIVE | RSR | DU5 |  |  | INLINE | [10 empty] | Fibre Optic | BOP-023-034-A | FALSE | FALSE |  |  | FALSE |  | 2015-06-03 | 2015-06-03 | 2015-06-05 | 2015-06-04 | 2015-07-07 | 2015-06-26 | 1 | 2015-07-14 | 2015-06-26 | 2015-08-28 | 2015-08-19 | 2015-08-28 | 2015-08-19 |  | 2015-08-28 | 2015-08-19 | DISCRETIONARY_FULL | 2015-08-21 | 2015-08-19 | 2015-10-09 | 2015-09-25 | 1 | 2015-10-09 | 2015-09-25 | [35 empty] | 03/06/15 - Caravanned. Road Reserve not yet with Council, but advised to proceed. Telco notice site 30/06/15 - PD's are issued and sent to James/Brad/Melissa for Telco notice and consenting 07/07/15 - Telco notice to lodge by 31/07 04/08/15 - Telco Notice lodged. Consent in drafting (James) 11/08/15 - Telco notice expires17/08. The issue 1 page letter 18/08/15 - Letter issued. Lodge consent application 25/9/15 - Consent received | [17 empty] | HARDMATCH |  | TRUE | [6 empty] | CELLSITE | WIPACTIVE |  |  | CAPACITY | [13 empty] | 2015-06-04
0 | BOP | 568 | BOP-023-036 | Bayfair Plaza Repeater | BOP-023-036-A | Bayfair Plaza MC | Tauranga | 23 | 2015P | ACTIVE | RT | MC | BO |  |  | COSITE | [9 empty] | Fibre Optic | BOP-023-034-A | FALSE | FALSE |  |  | FALSE |  | 2015-04-30 | 2015-04-08 | 2015-05-04 | 2015-04-15 | 2015-06-18 | 2015-06-17 | 2 | 2015-06-18 | 2015-08-14 | 2015-11-20 | 2015-11-17 | 2016-04-29 |  |  | 2016-04-29 |  |  | 2016-05-02 |  | 2016-06-17 |  |  | 2016-06-17 | [36 empty] | 26/05/15 - 2 Degrees now doing drawings in-house. Visit 3/6 when caravan Papamoa west. May not need a consent - James will check. Ron to check MC order 23/06/15 - rent will be 2-3k per year, and starts on signing. Good breakthrough with AMP. Ron/Steve/Kevin to review status 04/08/15 - Solution now Microcell into 266 Antennas - PD up-rev underway. Matt to be given drws when available 25/08/15 - Drawings issued to Matt and James - James to give RMA assessment | [17 empty] | BUILD |  | FALSE | [6 empty] | CELLSITE | WIPACTIVE |  |  | CAPACITY | [13 empty] | 2015-04-15
0 | BOP | 569 | BOP-024-001 | Rotorua Central | BOP-024-001-B | Chubb Greenfield | Rotorua | 2 | TIER_2 | ACTIVE | GF | DU | P2 | Grey | STACK_A | COSITE | 20.6 | 21.1 | 1 | -38.127 | 176.2328 |  | 2010-05-10 |  | 2010-04-28 | Microwave | BOP-024-003-A | TRUE | FALSE | 2010-05-10 |  | FALSE |  | 2011-02-09 | 2011-02-09 | 2011-04-19 | 2011-04-19 | 2011-05-06 | 2011-05-12 | 1 | 2011-05-06 | 2011-05-12 | 2011-06-17 | 2011-06-02 | 2011-06-10 | 2011-06-10 | 1 | 2011-06-17 | 2011-06-14 | NON_COMPLYING_LIMITED | 2011-06-24 | 2011-06-24 | 2011-07-28 | 2011-07-08 | 1 | 2011-08-04 | 2011-07-11 |  |  | 2011-09-12 | 2011-09-27 | 1 |  | 2011-09-12 | 2011-09-27 | 2011-09-30 |  |  |  |  | 2011-10-04 | 2011-09-29 | 2011-11-14 | 2011-11-16 | 2011-11-02 | 2011-11-04 | 2011-11-12 | [8 empty] | 2011-11-12 | 2011-11-23 | 2011-11-23 | 2011-11-19 | 2011-12-05 | 2012-03-05 | 2012-06-27 | 27/10/11 - Mast in. Cabinets in soon, expecting integration 29/10 5/12/11 - PAC, with snags signed |  | 2011-11-04 | 2011-08-22 | 2011-08-22 | 2011-09-21 | 2011-09-30 | 2011-09-21 | 2011-09-30 | 2011-11-02 | 2011-11-02 |  | 2011-11-21 | [6 empty] | 2011-10-26 | FALSE |  | 2793525 | 6336688 | Behind Chubb storage Old Taupo Road Rotorua |  | Consent No. RC14037 - 11/07/2011 | CELLSITE |  |  | 2015-05-26 | [12 empty] | 2011-11-21 | 2011-11-21 | 2011-04-19
0 | BOP | 570 | BOP-024-002 | Pukehangi | BOP-024-002-B | AutoMart | Rotorua | 2 | TIER_2 | ACTIVE | GF | DU | P2 | grey | STACK_A | COSITE | 19.5 | 20 | 1 | -38.1374 | 176.2147 |  | 2010-05-10 |  | 2010-04-28 | Microwave | BOP-024-017-A | FALSE | FALSE | 2010-05-10 |  | FALSE | 2011-02-17 |  | 2010-12-07 | 2011-01-18 | 2011-01-25 | 2011-02-21 | 2011-03-02 | 3 | 2011-10-17 | 2011-10-31 | 2011-03-23 | 2011-03-17 | 2011-06-10 | 2011-06-10 | 1 | 2011-06-10 | 2011-06-14 | LIMITED_NOTIFIED | 2011-10-28 | 2011-10-28 | 2012-02-28 | 2012-02-10 | 3 | 2012-02-29 | 2012-02-29 |  |  | 2012-03-29 | 2012-03-29 | 1 |  | 2012-03-29 | 2012-03-29 | 2012-04-02 |  |  |  |  | 2012-04-12 | 2012-04-12 | 2012-05-02 | 2012-05-02 | 2012-05-02 | 2012-05-11 | 2012-05-11 | [8 empty] | 2012-05-11 | 2012-06-16 | 2012-05-16 | 2012-06-18 | 2012-05-29 | 2012-08-27 | 2012-09-18 | 08/11/11 - Council will advise on 14/11 on notification 24/11/11 - Submissions close 14 Dec. Hearing will be in Jan 15/12/11 - Submissions closed yesterday with noe received. Wait for any late submissions 10/02/11 - Consent granted today. Docs out Monday 14/02/12 - WO2 done and in for signing |  | 2012-05-14 | 2012-04-02 | 2012-04-02 | 2012-04-02 | 2012-04-10 | 2012-04-02 | 2012-04-02 | 2012-05-03 | 2012-05-03 |  | 2012-05-21 | [6 empty] | 2012-05-02 | FALSE |  | 2791897 | 6335586 | 38 Edmund Rd, Rotorua |  |  | CELLSITE |  |  | 2015-05-26 | [12 empty] | 2012-05-25 | 2012-05-18 | 2011-01-26
0 | BOP | 571 | BOP-024-003 | Rotorua CBD - Main Hub | BOP-024-003-A | 1154 Hinemoa Street | Rotorua | 2 | TIER_2 | ACTIVE | RT | DU | RT | grey | STACK_A | COSITE | 35 | 35 | 1 | -38.1382 | 176.2522 |  | 2010-05-10 |  | 2010-04-28 | Fibre Optic | AKL-007-106-A | FALSE | FALSE | 2010-05-10 |  | FALSE |  |  | 2010-12-07 | 2011-01-26 | 2011-01-25 | 2011-03-15 | 2011-03-15 | 3 | 2011-04-29 | 2014-12-04 | 2011-04-08 | 2011-04-07 | 2011-06-17 | 2011-06-16 | 2 | 2011-06-17 | 2011-06-17 | DISCRETIONARY_FULL | 2011-04-11 | 2011-04-13 | 2011-05-23 | 2011-05-16 | 2 | 2011-05-30 | 2011-05-18 |  |  | 2011-10-05 | 2011-11-18 | 1 |  | 2011-09-01 | 2011-11-18 | 2011-09-30 |  |  |  |  | 2011-09-28 | 2011-09-26 | 2011-10-06 | 2011-10-07 | 2011-10-05 | 2011-11-07 | 2011-11-12 | [8 empty] | 2011-11-12 | 2011-11-23 | 2011-11-23 | 2011-11-19 | 2011-12-05 | 2013-06-19 | 2013-06-14 | 18/03/13 - Generator functional test to be carried out before FAN can be issues and processed 09/04/13 - FAC reforecasted - No FAN received yet 01/05/13 - No FAN yet. FAC reforecasted 14/6/13 - FAC Signed. THis was the last site in Rotorua to achieve FAC |  | 2011-11-03 | 2011-08-22 | 2011-08-22 | 2011-08-29 | 2011-09-30 | 2011-09-05 | 2011-09-30 | 2011-10-13 | 2011-10-14 |  | 2011-11-21 | [5 empty] | BUILD | 2011-10-04 | FALSE |  | 2795173 | 6335377 | 1154 Hinemoa Street, Rotorua CBD |  | Consent No. RC13968 - 18/05/2011 | CELLSITE |  |  | 2015-05-26 | [12 empty] | 2011-11-21 | 2011-11-21 | 2011-01-26
0 | BOP | 572 | BOP-024-004 | Rotorua West | BOP-024-004-A | West End Medical | Rotorua | 2 | TIER_2 | ACTIVE | GF | DU | P2 | grey | STACK_A | STANDALONE | 15 | 15.4 | 1 | -38.1453 | 176.2373 |  | 2010-05-10 |  | 2010-04-28 | Microwave | BOP-024-017-A | FALSE | FALSE | 2010-05-10 |  | FALSE | 2011-03-03 | 2011-02-18 | 2011-02-09 | 2011-02-18 | 2011-02-21 | 2011-03-15 | 2011-03-18 | 3 | 2011-03-15 | 2015-01-19 | 2011-05-27 | 2011-05-26 | 2011-06-30 | 2011-06-24 | 1 | 2011-06-30 | 2011-07-11 | CONTROLLED | 2011-04-27 | 2011-04-26 | 2011-06-17 | 2011-06-01 | 1 | 2011-06-07 | 2011-06-03 |  |  | 2011-10-05 | 2011-10-05 | 1 |  | 2011-09-08 | 2011-10-05 | 2011-10-18 |  |  |  |  | 2011-10-18 | 2011-10-17 | 2011-11-22 | 2011-11-26 | 2011-11-12 | 2011-11-05 | 2011-11-12 | [8 empty] | 2011-11-11 | 2011-11-23 | 2011-11-23 | 2011-11-19 | 2011-12-05 | 2012-03-05 | 2012-06-27 | 16/06/11 - Owner hopefully over the line now. Lease amendment required to ref WHO emmission standards 23/06/11 - Signed documents now with 2D for signing 5/12/11 - PAC, with snags signed |  | 2011-11-05 | 2011-08-22 | 2011-08-22 | 2011-10-07 | 2011-11-02 | 2011-10-05 | 2011-10-18 | 2011-11-04 | 2011-11-12 |  | 2011-11-21 | [6 empty] | 2011-11-03 | FALSE |  | 2793838 | 6334641 | 227 Old Taupo Rd (near Malfroy Rd), Rotorua |  | Consent No. RC13976 - 04/06/2011 | CELLSITE |  |  | 2015-05-26 | [12 empty] | 2011-11-21 | 2011-11-21 | 2011-02-21
0 | BOP | 573 | BOP-024-005 | Mangakakahi | BOP-024-005-A | Roadmaster | Rotorua | 2 | TIER_2 | ACTIVE | GF | DU | P3 | grey | STACK_A | STANDALONE | 20.6 | 21.1 | 1 | -38.132 | 176.236 |  | 2010-05-10 |  | 2010-04-28 | Microwave | BOP-024-001-A | FALSE | FALSE | 2010-05-10 |  | FALSE | 2011-02-02 |  | 2010-12-07 | 2011-01-21 | 2011-01-26 | 2011-02-24 | 2011-03-01 | 2 | 2011-03-07 | 2011-03-09 | 2011-03-31 | 2011-03-23 | 2011-06-23 | 2011-06-16 | 1 | 2011-06-28 | 2011-06-17 | CONTROLLED | 2011-03-17 | 2011-03-21 | 2011-04-20 | 2011-04-21 | 2 | 2011-04-29 | 2011-04-26 |  |  | 2011-10-05 | 2011-11-03 | 1 |  | 2011-09-05 | 2011-11-03 | 2011-11-02 |  |  |  |  | 2011-11-02 | 2011-11-02 | 2011-11-21 | 2011-11-24 | 2011-11-18 | 2011-11-26 | 2011-11-26 | [8 empty] | 2011-11-28 | 2011-12-09 | 2011-12-07 | 2011-11-19 | 2011-12-16 | 2012-03-15 | 2012-06-27 | 1/12/11 - SOA delayed due to late completion and Vol 4 not avail until 30/11 07/12/11 - Site Audits and inspections completed. Site now on air 16/12/11 - PAC signed |  | 2011-11-26 | 2011-08-22 | 2011-08-22 | 2011-10-07 | 2011-11-02 | 2011-10-07 | 2011-11-02 | 2011-11-18 | 2011-11-18 |  | 2011-11-30 | [6 empty] | 2011-11-21 | FALSE |  | 2793782 | 6336116 | 35 Biak Street Rotorua |  | Consent No.: RC13937 - 26/04/2011 | CELLSITE |  |  | 2015-05-26 | [12 empty] | 2011-12-02 | 2011-12-05 | 2011-01-26
0 | BOP | 574 | BOP-024-006 | Pukehangi Heights | BOP-024-006-D | Diamond Street GF | Rotorua | 2 | TIER_2 | ACTIVE | GF | DU | T2 15 UF |  | STACK_A | STANDALONE |  | 15 | 1 | -38.1373 | 176.2027 |  | 2010-05-10 |  | 2010-04-28 | Microwave | BOP-024-017-A | FALSE | FALSE | 2010-05-10 |  | FALSE |  | 2011-06-30 | 2011-06-22 | 2011-06-24 | 2011-06-27 | 2011-07-26 | 2011-07-27 | 2 | 2011-09-16 | 2011-09-14 | 2011-08-12 | 2011-08-11 | 2011-09-30 | 2011-09-30 | 2 | 2011-10-18 | 2011-10-18 | DISCRETIONARY_FULL | 2011-09-29 | 2011-09-28 | 2011-11-11 | 2011-11-09 | 2 | 2011-11-18 | 2011-11-09 |  |  |  | 2012-01-25 | 1 |  |  | 2012-01-25 | 2012-03-02 |  |  |  |  | 2012-02-09 | 2012-02-09 | 2012-02-15 | 2012-02-28 | 2012-02-24 | 2012-02-29 | 2012-03-02 | [8 empty] | 2012-03-06 | 2012-03-09 | 2012-03-12 | 2012-02-23 | 2012-03-23 | 2012-06-21 | 2012-08-31 | 15/12/11 - Site with Huawei for construction. Power to come from road. Lat jan drive 10/02/12 - REvised dates from Infratel has pushed out SOA till after PAC 08/03/12 - Site integrated and Vol 4 delivered. Teams checking site 09/03/12 - PAD submitted and under review |  | 2012-03-02 | 2012-03-02 | 2012-03-02 | 2012-03-02 | 2012-03-02 | 2011-12-09 | 2012-03-02 | 2012-02-24 | 2012-03-01 |  | 2012-03-08 | [6 empty] | 2012-02-24 | FALSE |  | 2790842 | 6335642 | 17 Diamond Street, Rotorua |  | Council Ref: RC14149 - 14/11/2011 | CELLSITE | [15 empty] | 2012-03-15 | 2012-03-09 | 2011-06-27
0 | BOP | 575 | BOP-024-008 | Rotorua South | BOP-024-008-A | LPR Mokoia Drive | Rotorua | 2 | TIER_2 | ACTIVE | RSR | DU | P4F | green | INLINE | STANDALONE | 14.5 | 15 | 1 | -38.1701 | 176.2432 |  | 2010-05-10 |  | 2010-04-28 | Microwave | BOP-024-003-A | FALSE | FALSE | 2010-05-10 |  | FALSE |  |  | 2011-05-24 | 2011-06-03 | 2011-06-01 | 2011-06-22 | 2011-06-16 | 2 | 2011-06-22 | 2011-06-28 | 2011-08-19 | 2011-08-25 | 2011-09-23 | 2011-09-16 | 2 | 2011-09-23 | 2011-09-27 | NES | 2011-06-23 | 2011-06-17 | 2011-07-21 | 2011-07-13 | 2 | 2011-07-26 | 2011-07-21 |  |  | 2011-10-03 | 2011-10-04 | 1 |  | 2011-10-03 | 2011-10-04 | 2011-09-26 |  |  |  |  | 2011-10-03 | 2011-10-03 | 2011-10-11 | 2011-10-06 | 2011-10-12 | 2011-12-09 | 2011-12-12 | [8 empty] | 2011-12-12 | 2011-12-16 | 2011-12-15 | 2011-12-01 | 2012-01-27 | 2012-04-26 | 2012-06-28 | 28/10/11 - Site built, but weaiting for quote on power provision. Power will be the delay on this site 14/11/11 - SOA changed to Dec, due to issues with getting power to site 15/12/11 - Site under Drive test today. Site went to air after test |  | 2011-12-14 | 2011-08-22 | 2011-08-22 | 2011-10-04 | 2011-11-02 | 2011-09-26 | 2011-09-26 | 2011-12-09 | 2011-12-08 |  | 2011-12-16 | [6 empty] | 2011-10-12 | FALSE |  | 2794260 | 6331876 | Mokoia Drive Rotorua |  | NES pole - 21/05/2010 Consent No. RC14031 - 15/07/2011 | CELLSITE | [15 empty] | 2011-12-23 | 2011-12-23 | 2011-06-01
0 | BOP | 576 | BOP-024-010 | Ngapuna |  |  | Rotorua |  | TIER_9 | [22 empty] | FALSE
0 | BOP | 577 | BOP-024-011 | Kawaha Point | BOP-024-011-B | Rugby Club GF site | Rotorua | 2 | TIER_2 | ACTIVE | GF | DU | P2 | grey | STACK_A | COSITE | 19.5 | 20 | 1 | -38.1145 | 176.2322 |  | 2010-05-10 |  | 2010-04-28 | Microwave | BOP-024-017-A | FALSE | FALSE | 2010-05-10 |  | FALSE | 2011-02-02 |  | 2010-12-07 | 2011-02-11 | 2011-01-26 | 2011-03-04 | 2011-03-08 | 1 | 2011-03-04 | 2011-03-08 | 2011-04-15 | 2011-03-24 | 2011-08-12 | 2011-07-29 | 1 | 2011-08-12 | 2011-08-01 | LIMITED_NOTIFIED | 2011-04-07 | 2011-04-07 | 2012-01-27 | 2011-12-21 | 1 | 2012-01-27 | 2012-02-10 |  |  | 2012-04-02 | 2012-03-27 | 1 |  | 2012-04-02 | 2012-03-27 | 2012-04-10 |  |  |  |  | 2012-04-02 | 2012-03-28 | 2012-04-19 | 2012-04-18 | 2012-04-20 | 2012-05-02 | 2012-05-02 | [8 empty] | 2012-05-07 | 2012-05-25 | 2012-05-08 | 2012-05-23 | 2012-05-18 | 2012-08-16 | 2012-08-28 | 08/11/11 - Notification out. Submissions close 01 December 24/11/11 - 3 sumissions (1 was joint) received to date. Hearing set for 21 Dec 15/12/11 - Hearing next Wed 21/12 - 2D will be available on teleconf if required by commissioner 18/05/12. Site Audited this week, and only 1 minor snag found. PAD good. PAC issued today |  | 2012-05-03 | 2012-04-02 | 2012-04-02 | 2012-04-02 | 2012-04-10 | 2012-04-02 | 2012-04-10 | 2012-04-18 | 2012-04-20 |  | 2012-05-08 | [6 empty] | 2012-04-18 | FALSE |  | 2793523 | 6338075 | Rugby Club, End of Bellvue Rd, Kawaha, Rotorua |  | Consent No. RC13957 - 09/01/2012 | CELLSITE |  |  | 2015-05-26 | [12 empty] | 2012-05-11 | 2012-05-08 | 2011-01-26
0 | BOP | 578 | BOP-024-012 | Te Ngae Shopping Centre | BOP-024-012-B | LPR Te Ngae Road - opp shell | Rotorua | 2 | TIER_2 | ACTIVE | RSR | DU | P4A | green | INLINE | STANDALONE | 15.4 | 15.9 | 1 | -38.131 | 176.3005 |  | 2010-05-10 |  | 2010-04-28 | Microwave | BOP-024-003-A | FALSE | FALSE | 2010-05-10 |  | FALSE |  | 2011-05-24 | 2011-05-24 | 2011-05-31 | 2011-05-27 | 2011-06-17 | 2011-06-30 | 1 | 2011-06-17 | 2011-06-30 | 2011-08-19 | 2011-08-25 | 2011-09-23 | 2011-09-16 |  | 2011-09-23 | 2011-10-06 | NES | 2011-07-08 | 2011-07-12 | 2011-08-08 | 2011-07-29 | 1 | 2011-08-15 | 2011-08-01 |  |  | 2011-10-03 | 2011-10-04 | 1 |  | 2011-10-03 | 2011-10-04 | 2011-09-26 |  |  |  |  | 2011-10-06 | 2011-10-03 | 2011-10-15 | 2011-10-12 | 2011-10-13 | 2011-10-28 | 2011-11-02 | [8 empty] | 2011-11-02 | 2011-12-02 | 2011-11-23 | 2011-11-19 | 2011-12-05 | 2013-05-10 | 2013-05-07 | 18/03/13 - FAN in sign-off process. No dwg on CD, and dish is still non-NES compliant 20/03/13 - FAC ready to sign if 2D accepts non-compliant dish 09/14/13 - Huawei advised that correct dish needs to be installed to comply with NES. FAC not to be signed till then. |  | 2011-10-30 | 2011-08-22 | 2011-08-22 | 2011-10-04 | 2011-11-02 | 2011-09-26 | 2011-09-26 | 2011-10-19 | 2011-10-21 |  | 2011-11-21 | [5 empty] | BUILD | 2011-10-17 | FALSE |  | 2799437 | 6336026 | Wharenui Road, Te Ngae Road cnr, Owhata, Rotorua |  | Consent No. RC14045 - 01/08/2011 | CELLSITE | [15 empty] | 2011-11-21 | 2011-11-21 | 2011-05-27
0 | BOP | 579 | BOP-024-013 | Owhata |  |  | Rotorua |  | TIER_9 | [22 empty] | FALSE
0 | BOP | 580 | BOP-024-015 | Lake Rotoiti | BOP-024-015-A | VF Colocation | Rotorua | 22 | TIER_5 | ACTIVE | COLO | DF | COLO |  | STACK_A | COLO | 30 | 30.65 |  | -38.0428 | 176.397 |  |  |  |  | Microwave | BOP-024-016-A | FALSE | FALSE |  |  | FALSE |  | 2012-03-23 | 2012-03-09 | 2012-05-11 | 2012-05-11 | 2012-06-21 | 2012-06-06 | 5 | 2015-10-08 | 2015-11-20 | 2016-02-22 |  | 2016-03-28 |  |  | 2016-04-04 |  | DISCRETIONARY_FULL | 2016-01-28 | 2016-01-28 | 2016-02-29 |  | 5 | 2016-02-29 |  | 2016-01-28 | 2016-01-27 | 2016-02-29 |  |  |  | 2016-02-29 | [6 empty] | 2016-04-18 |  | 2016-05-16 |  |  | 2016-06-20 | [10 empty] | 2016-08-08 | [5 empty] | 24/05/12 - Using 224 antennas, structure will work. Rev0 drawings should be avail 25/5 01/06/12 - Redlines done, drws updated and confirmed for issue as REV 1 14/06/12 - lost drawings - but now found. To be issued 21/06/12 - Drawings in final circulation. Colo application to be undertaken 05/10/12 - Taken out of Build programme 25/8/15 - new VF data pack ordered 23/9/15 - PD up rev issued 23/11/15 - VF co-lo application submitted 12/1/16 - awaiting VF prelim approval - once we have this we can send riggers for LOS and tower measure ups - when LOS confirmed we will order the TX equipment. 26/1/16 - received VF prelim approval 27/1/16 - dependant on Okere Falls for transmission - have pushed dates out to reflect this | VNZ | [9 empty] | 2016-07-18 |  |  |  | ROTORUA_TAUPO |  |  | BUILD |  | FALSE |  | 2808264 | 6345485 | Forestry Rd, Tikitere Hill Lake Rotoiti |  |  | CELLSITE | WIPACTIVE |  |  | ROAMING |  |  |  | 2016-03-01 | [5 empty] | 2016-03-28 |  |  |  | 2012-05-11
0 | BOP | 581 | BOP-024-016 | Okere Falls | BOP-024-016-A | Okere Falls VF Co-Lo | Rotorua | 22 | TIER_5 | ACTIVE | COLO | DF | COLO |  | STACK_A | COLO | 24 | 25 | [7 empty] | Microwave | BOP-024-027-C | FALSE | FALSE |  |  | FALSE |  | 2015-11-27 | 2015-11-27 | 2015-12-02 | 2015-12-03 | 2016-01-18 | 2016-01-14 | 1 | 2016-01-25 | 2016-01-14 | 2016-02-29 |  | 2016-04-25 |  |  | 2016-05-02 |  | PERMITTED | 2016-02-22 |  | 2016-03-28 |  |  | 2016-04-04 |  | 2016-02-22 |  | 2016-03-28 |  |  |  | 2016-04-04 | [6 empty] | 2016-05-09 |  | 2016-06-13 |  |  | 2016-06-27 | [10 empty] | 2016-08-08 | [5 empty] | 23/10/15 - data pack received 15/1/16 - VF c-lo application submitted | VNZ | [9 empty] | 2016-07-18 | [6 empty] | BUILD |  | FALSE |  |  |  | Hamurana Road, Okere Falls |  |  | CELLSITE | WIPACTIVE |  |  | ROAMING |  |  |  | 2016-04-04 | [5 empty] | 2016-05-02 |  |  |  | 2015-12-03
0 | BOP | 582 | BOP-024-017 | Pukepoto - Kordia | BOP-024-017-A | Pukepoto Kordia co-lo | Rotorua | 2 | TIER_2 | ACTIVE | COLO | DU | COLO |  | STACK_A | COLO |  |  | 1 | -38.1317 | 176.3484 |  | 2010-05-10 |  | 2010-04-28 | Microwave | BOP-024-003-A | FALSE | FALSE | 2010-05-10 |  | FALSE | 2011-03-24 | 2011-04-08 | 2010-07-06 | 2011-04-15 | 2011-03-22 | 2011-05-27 | 2011-05-26 | 1 | 2011-05-27 | 2011-05-26 | 2011-05-27 | 2011-05-12 | 2011-06-24 | 2011-06-17 |  | 2011-06-24 | 2011-06-30 | OPW | 2011-05-30 | 2011-05-25 | 2011-06-03 | 2011-06-01 | 1 | 2011-06-03 | 2011-06-01 |  |  | 2011-09-01 | 2011-09-30 | 1 |  | 2011-09-01 | 2011-09-30 | 2011-09-30 |  |  |  |  | 2011-09-19 | 2011-09-13 | 2011-10-01 | 2011-09-22 | 2011-10-05 | 2011-11-03 | 2011-11-12 | [8 empty] | 2011-11-12 | 2011-11-23 | 2011-11-23 | 2011-11-19 | 2011-12-05 | 2012-03-05 | 2012-08-31 | 28/10/11 - Link 5dB out of spec. Ron has requested Kordia resources continue to build Tuhingamata and return afterwards to re-pan/tilt link before SOA. 5/12/11 - PAC, with snags signed | KDA | 2011-11-03 | 2011-08-22 | 2011-11-02 | 2011-10-04 | 2011-09-30 | 2011-09-01 | 2011-09-30 | 2011-10-18 | 2011-10-21 |  | 2011-11-21 | [6 empty] | 2011-10-10 | FALSE |  | 2803633 | 6335792 | Pukepoto Access off Gee Rd, Rotorua Airport |  |  | CELLSITE | [15 empty] | 2011-11-21 | 2011-11-21 | 2011-03-22
0 | BOP | 583 | BOP-024-018 | Ngongotaha | BOP-024-018-A | VF & TNZ co-site | Rotorua | 22 | TIER_5 | ACTIVE | GF | DF |  |  | STACK_A | COSITE | [8 empty] | 2010-04-28 |  |  | FALSE | FALSE | 2010-05-10 |  | FALSE |  | 2016-02-29 |  | 2016-03-01 |  | 2016-03-29 |  |  | 2016-04-04 |  | 2016-05-16 |  | 2016-06-27 |  |  | 2016-07-04 |  |  | 2016-05-23 |  | 2016-07-04 |  |  | 2016-07-11 |  | 2016-05-23 |  | 2016-06-27 |  |  |  | 2016-07-04 | [6 empty] | 2016-08-22 |  | 2016-09-19 |  |  | 2016-10-03 | [10 empty] | 2016-11-01 | [5 empty] | Mast location will be critical to achieve coverage and avoid interference with other operators. 13/1/11 - Maori Trust land. May look at option to also co-lo RF on Telecom, and sep mast for Transmission 17/2/11 - Owner all OK. Need to site visit to confirm options for our build 3/3 - site pending strategic review by RF 10/3/11 - Site/nominal removed from Tier 2 due to RF strategy on high sites. Ngongotaha Township nominal created as new area for Tier 2 25/8/15 - VF & Spark data packs ordered | [10 empty] | 2016-10-17 | [6 empty] | BUILD |  | FALSE |  |  |  | Ngongotaha Hilltop, Access off Paradise Valley Rd & State Highway Interchange |  |  | CELLSITE | WIPACTIVE |  |  | ROAMING |  |  |  | 2016-07-04 | [5 empty] | 2016-08-01
0 | BOP | 584 | BOP-024-019 | Whakarewarewa | BOP-024-019-A | VF Co-lo Whakarewarewa | Rotorua | 2 | TIER_3 | ACTIVE | COLO | DU | COLO | grey | STACK_A | COLO | 24.7 | 25.25 | 1 | -38.2108 | 176.2779 |  |  |  | 2011-06-01 | Microwave | BOP-024-003-A | TRUE | TRUE | 2011-06-01 |  | TRUE |  | 2011-07-21 | 2011-07-18 | 2011-07-22 | 2011-07-20 | 2011-07-29 | 2011-07-29 | 1 | 2011-07-29 | 2011-07-29 | 2011-08-12 | 2011-08-11 | 2012-05-02 | 2012-04-17 |  | 2012-05-02 | 2012-07-11 | DISCRETIONARY_FULL | 2011-08-05 | 2011-08-08 | 2011-09-05 | 2011-09-01 | 1 | 2011-09-09 | 2011-09-05 | 2012-02-18 | 2012-02-18 | 2012-04-30 | 2012-04-27 | 1 |  | 2012-04-30 | 2012-04-27 | 2012-05-21 | 2012-04-18 |  |  |  | 2012-05-12 | 2012-05-12 | 2012-05-17 | 2012-05-18 | 2012-05-21 | 2012-05-29 | 2012-05-25 | [8 empty] | 2012-05-25 | 2012-06-15 | 2012-06-08 | 2012-06-15 | 2012-06-21 | 2013-03-13 | 2013-03-25 | 13/03/13 - FAN all signed - ready to issue FAC 25/03/13 - FAC signed | VNZ | 2012-05-29 | 2012-05-21 | 2012-05-21 | 2012-05-21 | 2012-05-21 | 2012-05-16 | 2012-05-21 | 2012-05-22 | 2012-05-22 |  | 2012-06-08 |  |  | ROTORUA_TAUPO |  |  | BUILD | 2012-05-17 | FALSE |  | 2797135 | 6327241 | State Highway 5 Whakawerawera, Kakapiko Lookout, Whakawerawera Forest Kakapiko Rotorua |  | Consent No. RC14097 - 05/09/2011 | CELLSITE | [7 empty] | 2012-04-20 | [7 empty] | 2012-06-08 | 2012-06-08 | 2011-07-20
0 | BOP | 585 | BOP-024-020 | Paeroa Range | BOP-024-020-A | Kordia Paeroa range | Rotorua | 23 | TIER_3 | ACTIVE | COLO | DU | COLO |  | STACK_A | COLO | 34 | 45 | 1 | -38.3805 | 176.2585 |  |  |  |  | Leased Line |  | FALSE | FALSE |  |  | FALSE |  | 2012-03-16 | 2012-03-13 | 2012-05-21 | 2012-05-22 | 2012-05-25 | 2012-05-22 | 1 | 2012-05-25 | 2012-05-22 | 2012-06-04 | 2012-05-22 | 2012-06-18 | 2012-05-22 |  | 2012-09-30 | 2012-11-01 | OPW | 2012-06-04 | 2012-06-08 | 2012-07-15 | 2012-06-27 | 1 | 2012-07-15 | 2012-06-27 | 2012-06-13 | 2012-06-13 | 2012-07-31 | 2012-08-23 | 1 |  | 2012-07-31 | 2012-08-23 | 2012-08-22 |  |  |  |  | 2012-09-03 | 2012-08-21 | 2012-09-14 | 2012-09-12 | 2012-09-12 | 2012-09-21 | 2012-09-21 | 2012-09-21 | 2012-09-21 | [6 empty] | 2012-09-24 | 2012-10-12 | 2012-10-05 | 2012-10-26 | 2012-10-16 | 2013-04-11 | 2013-04-11 | 15/03/2013 - FAN all sign off FAC ready for signing | KDA | 2012-09-24 |  |  | 2012-08-31 | 2012-08-31 | 2012-08-22 | 2012-08-22 | 2012-09-13 | 2012-09-14 | 2012-10-03 | 2012-10-02 |  |  | ROTORUA_TAUPO | 2012-09-21 | 2012-09-21 | BUILD | 2012-09-13 | FALSE |  | 2794748 | 6308488 | Kordia Transmission Site |  |  | CELLSITE | [15 empty] | 2012-09-28 | 2012-10-02 | 2012-05-17
0 | BOP | 586 | BOP-024-021 | Rainbow Mountain | BOP-024-021-D | Rainbow Mountain 2015 Project | Rotorua | 23 | TIER_5 | ACTIVE | COLO | DF |  |  | INLINE | [12 empty] | FALSE | FALSE |  |  | FALSE |  | 2015-12-04 | 2015-12-01 | 2015-12-11 | 2015-12-04 | 2016-02-19 |  |  | 2016-02-19 |  | 2016-04-01 |  | 2016-05-20 |  |  | 2016-05-27 |  |  | 2016-05-02 |  | 2016-07-29 |  |  | 2016-07-29 |  | 2016-06-06 |  | 2016-07-29 |  |  |  | 2016-07-29 | [6 empty] | 2016-08-08 | [15 empty] | 2016-11-11 | [5 empty] | 03/11/15 - Site requires revisit with Structural Engineer to look at potential options for upgrading/replacing existing lattice mast and consolidating all users onto one structure (Timberlands, DOC, Spark, VF, 2D and others). Site will require extensive IWI, DOC and colo consultation. 01/12/15 - Site visited - good options available 9/2/16 - PD rev ) issued - Brad to respond with changes, then iwi consultation to start | [10 empty] | 2016-11-04 |  |  |  | ROTORUA_TAUPO |  |  | BUILD |  | FALSE |  |  |  | Rainbow Mountain SH38 off Rotorua/Taupo SH5 |  |  | CELLSITE | WIPACTIVE |  |  | ROAMING | [9 empty] | 2016-07-29 |  |  |  | 2015-12-04
0 | BOP | 587 | BOP-024-022 | Mamaku |  |  | Rotorua |  | TIER_9 | [22 empty] | FALSE | [60 empty] | q
0 | BOP | 588 | BOP-024-023 | Fenton Park | BOP-024-023-A | Racecourse - RT site | Rotorua | 2 | TIER_2 | ACTIVE | RT | DF | RT | grey | INLINE | COSITE | 16.6 | 17.7 | 1 | -38.1499 | 176.2573 |  | 2010-05-10 |  | 2010-04-28 | Microwave | BOP-024-003-A | FALSE | FALSE | 2010-05-10 |  | FALSE | 2011-03-03 | 2011-05-05 | 2011-03-10 | 2011-03-18 | 2011-03-14 | 2011-04-08 | 2011-04-13 | 2 | 2011-04-08 | 2014-12-08 | 2011-05-27 | 2011-05-26 | 2011-06-21 | 2011-06-16 | 1 | 2011-06-21 | 2011-06-17 | DISCRETIONARY_FULL | 2011-05-06 | 2011-05-06 | 2011-06-17 | 2011-05-30 | 1 | 2011-06-24 | 2011-06-02 |  |  | 2011-10-07 | 2011-10-27 | 2 |  | 2011-10-07 | 2011-10-27 | 2011-10-18 |  |  |  |  | 2011-10-17 | 2011-10-17 | 2011-11-21 | 2011-11-21 | 2011-11-15 | 2011-11-26 | 2011-11-26 | [8 empty] | 2011-11-29 | 2011-12-09 | 2011-12-07 | 2011-11-19 | 2011-12-16 | 2012-03-15 | 2012-09-18 | 07/12/11 - Site Audits and inspections completed. Site now on air 14/12/11 - Club reports leaking roof - Amediate to attend to on site 15/12 16/12/11 - PAC signed |  | 2011-11-28 | 2011-08-22 | 2011-08-22 | 2011-10-04 | 2011-11-02 | 2011-10-10 | 2011-10-18 | 2011-11-18 | 2011-11-18 |  | 2011-12-05 | [6 empty] | 2011-11-16 | FALSE |  | 2795579 | 6334070 | Fenton Street Rotorua |  | Consent No. RC13986 - 01/06/2011 | CELLSITE | [15 empty] | 2011-12-02 | 2011-12-05 | 2011-03-14
0 | BOP | 589 | BOP-024-024 | Hillcrest | BOP-024-024-B | Rotorua Sports GF | Rotorua | 2 | TIER_2 | ACTIVE | GF | DU | P2 | grey | STACK_A | COSITE | 19.5 | 20 | 1 | -38.1531 | 176.2263 |  | 2010-05-10 |  | 2010-04-28 | Microwave | BOP-024-003-A | FALSE | FALSE | 2010-05-10 |  | FALSE |  | 2011-03-11 | 2011-03-10 | 2011-03-18 | 2011-03-14 | 2011-04-11 | 2011-04-07 | 4 | 2011-04-18 | 2015-01-16 | 2011-05-27 | 2011-05-26 | 2011-09-23 | 2011-09-22 |  | 2011-09-30 | 2011-09-27 | DISCRETIONARY_FULL | 2011-10-14 | 2011-10-14 | 2011-11-15 | 2011-11-10 | 3 | 2011-11-22 | 2011-11-14 |  |  |  | 2012-02-07 | 1 |  |  | 2012-02-07 | 2012-03-06 |  |  |  |  | 2012-02-02 | 2012-03-02 | 2012-03-30 | 2012-04-05 | 2012-03-29 | 2012-03-31 | 2012-04-05 | [8 empty] | 2012-04-05 | 2012-04-13 | 2012-04-12 | 2012-04-30 | 2012-04-19 | 2012-07-18 | 2012-08-31 | 14/11/11 - Lease commenced Nov 15/12/11 - Large costs for getting power to site 06/04/12 - Site integrated. PAD expected today, Drive test next week and on-air by Friday. Site will be on generator until perm power available 12/04/12 - SOA, but will need to have antennas re-aligned to spec on 13/4 |  | 2012-03-31 | 2012-03-06 | 2012-03-06 | 2012-03-06 | 2012-03-06 | 2012-03-06 | 2012-03-06 | 2012-04-10 | 2012-05-18 |  | 2012-04-05 | [6 empty] | 2012-03-30 | FALSE |  | 2792846 | 6333809 | Rotorua Sports Devon Street West, Rotorua |  | Council Ref: RC14168 - 14/11/2011 | CELLSITE |  |  | 2015-05-26 | [12 empty] | 2012-04-06 | 2012-04-05 | 2011-03-14
0 | BOP | 590 | BOP-024-025 | Pomare |  |  | Rotorua |  | TIER_9 | [22 empty] | FALSE
0 | BOP | 591 | BOP-024-026 | Ngapuna Commercial | BOP-024-026-A | Verda NZ | Rotorua | 2 | TIER_2 | ACTIVE | GF | DU | P2 | grey | STACK_A | STANDALONE | 20.6 | 21.1 | 1 | -38.1438 | 176.2822 |  | 2010-05-10 |  | 2010-04-28 | Microwave | BOP-024-023-A | FALSE | FALSE | 2010-05-10 |  | FALSE | 2011-02-02 |  | 2010-12-08 | 2011-01-26 | 2011-01-25 | 2011-02-24 | 2011-03-01 | 1 | 2011-02-24 | 2011-03-01 | 2011-04-01 | 2011-03-24 | 2011-05-06 | 2011-05-05 |  | 2011-05-13 | 2011-05-11 | CONTROLLED | 2011-03-25 | 2011-03-25 | 2011-04-20 | 2011-04-27 | 1 | 2011-04-29 | 2011-04-29 |  |  | 2011-10-07 | 2011-11-03 | 1 |  | 2011-10-07 | 2011-11-03 | 2011-11-02 |  |  |  |  | 2011-10-19 | 2011-10-20 | 2011-11-09 | 2011-11-12 | 2011-11-09 | 2011-11-26 | 2011-11-26 | [8 empty] | 2011-11-29 | 2011-12-09 | 2011-12-07 | 2011-11-19 | 2011-12-16 | 2012-03-15 | 2012-07-31 | 07/12/11 - Site Audits and inspections completed. Site now on air 16/12/11 - PAC signed 31/07/12 - FAC signed |  | 2011-11-27 | 2011-08-22 | 2011-08-22 | 2011-10-19 | 2011-11-02 | 2011-10-19 | 2011-11-02 | 2011-11-24 | 2011-11-23 |  | 2011-11-30 | [6 empty] | 2011-11-07 | FALSE |  | 2797780 | 6334661 | Verda New Zealand xxx Te Ngae Rd Rotorua |  | Consent No. RC13944 - 29/04/2011 | CELLSITE |  |  | 2015-05-26 | [12 empty] | 2011-12-02 | 2011-12-05 | 2011-01-26
0 | BOP | 592 | BOP-024-027 | Rotorua Airport | BOP-024-027-C | Airport GF - Option 1 | Rotorua | 2 | TIER_2 | ACTIVE | GF | DU | P3 | grey | STACK_A | COSITE | 19.5 | 20 | 1 | -38.1108 | 176.3177 |  | 2010-05-10 |  | 2010-04-28 | Microwave | BOP-024-017-A | FALSE | FALSE | 2010-05-10 |  | FALSE |  |  | 2010-12-08 | 2011-03-28 | 2011-03-24 | 2011-04-18 | 2011-10-07 | 1 | 2011-04-18 | 2011-10-07 | 2011-06-03 | 2011-06-02 | 2011-09-09 | 2011-09-09 | 1 | 2011-09-09 | 2011-09-16 | NON_COMPLYING_FULL | 2011-06-07 | 2011-06-10 | 2011-07-14 | 2011-07-08 | 1 | 2011-07-21 | 2011-07-11 |  |  | 2011-10-07 | 2011-11-03 | 1 |  | 2011-10-07 | 2011-11-03 | 2011-10-12 |  |  |  |  | 2011-10-09 | 2011-10-10 | 2011-11-04 | 2011-11-12 | 2011-11-02 | 2011-11-05 | 2011-11-12 | [8 empty] | 2011-11-12 | 2011-11-23 | 2011-11-23 | 2011-11-19 | 2011-12-05 | 2012-03-05 | 2012-06-27 | 28/10/11 - Redlines sent back 6/10. No CD's issued yet. Site under construction. Pole stands this week 5/12/11 - PAC, with snags signed |  | 2011-11-05 | 2011-08-22 | 2011-08-22 | 2011-10-04 | 2011-11-02 | 2011-10-12 | 2011-10-12 | 2011-11-02 | 2011-11-02 |  | 2011-11-21 | [6 empty] | 2011-10-27 | FALSE |  | 2801029 | 6338211 | Rotorua Airport Te Ngae Road Rotorua |  | Consent No. RC14025 - 11/07/2011 | CELLSITE | [15 empty] | 2011-11-21 | 2011-11-21 | 2011-03-24
0 | BOP | 593 | BOP-024-028 | Punaromia (Blue + Green Lakes) |  |  | Rotorua |  | TIER_9 | [22 empty] | FALSE
0 | BOP | 594 | BOP-024-029 |  |  |  | Rotorua |  | TIER_9
0 | BOP | 595 | BOP-024-030 | Ngongotaha Township | BOP-024-030-A | 6 Wikarata Street | Rotorua | 2 | TIER_2 | ACTIVE | GF | DU | T2 25 UF | grey | STACK_A | STANDALONE | 22 | 22.5 | 1 | -38.0792 | 176.2155 | 2011-03-10 | 2011-03-10 | 2011-03-10 | 2011-03-10 | Microwave | BOP-024-017-A | TRUE | TRUE | 2011-03-10 | 2011-03-10 | TRUE |  | 2011-03-10 | 2011-03-10 | 2011-03-18 | 2011-03-14 | 2011-04-11 | 2011-04-11 | 3 | 2011-04-11 | 2011-08-04 | 2011-04-29 | 2011-05-04 | 2011-05-30 | 2011-05-31 |  | 2011-05-30 | 2011-05-31 | CONTROLLED | 2011-07-11 | 2011-07-08 | 2011-08-09 | 2011-08-03 | 3 | 2011-08-08 | 2011-08-08 |  |  | 2011-10-07 | 2011-10-17 | 1 |  | 2011-10-07 | 2011-10-17 | 2011-12-08 |  |  |  |  | 2011-10-31 | 2011-10-18 | 2011-12-09 | 2011-12-12 | 2011-12-08 | 2011-12-12 | 2011-12-12 | [8 empty] | 2011-12-14 | 2011-12-16 | 2011-12-15 | 2011-12-01 | 2012-01-27 | 2012-04-26 | 2012-07-31 | 15/12/11 - Site on drive test today, and now on air |  | 2011-12-15 | 2011-08-22 | 2011-08-22 | 2011-10-04 | 2011-11-02 | 2011-12-02 | 2011-12-08 | 2011-12-08 | 2011-12-08 |  | 2011-12-15 | [6 empty] | 2011-12-02 | FALSE |  | 2792195 | 6342044 | 6 Wikarata Street Ngongotaha |  | Consent No. RC14043 - 03/08/2011 | CELLSITE | [15 empty] | 2011-12-23 | 2011-12-23 | 2011-03-14
0 | BOP | 596 | BOP-024-031 | RBI - Lake Rotoma |  |  | Rotorua |  | RBI | [22 empty] | FALSE
0 | BOP | 597 | BOP-024-032 | RBI - Ngongotaha North |  |  | Rotorua |  | RBI | [22 empty] | FALSE
0 | BOP | 598 | BOP-024-033 | RBI - Reporoa | BOP-024-033-A | RBI Reporoa | Rotorua |  | TIER_5 | ACTIVE | RBI | DF | COLO |  | STACK_A | COSITE | [11 empty] | FALSE | FALSE |  |  | FALSE |  | 2015-10-16 |  | 2015-10-23 |  | 2015-11-13 | [72 empty] | ONHOLD |  | FALSE | [6 empty] | CELLSITE |  |  |  | ROAMING
0 | BOP | 599 | BOP-024-034 | Mamaku |  |  | Rotorua |  | TIER_9
0 | BOP | 600 | BOP-025-001 | Ohope Beach | BOP-025-001-D | Kohi Point Roadside | Whakatane | 2 | TIER_3 | ACTIVE | RSR | DU | P4B |  | INLINE | STANDALONE |  |  | 1 | -37.9574 | 177.0194 | 2010-06-30 | 2010-07-01 |  | 2010-06-06 | Fibre Optic |  | FALSE | FALSE |  | 2010-10-29 | FALSE |  | 2012-05-13 | 2012-05-13 | 2012-06-12 | 2012-06-12 | 2012-07-06 | 2012-07-10 | 3 | 2012-07-06 | 2015-04-28 | 2012-08-10 | 2012-08-15 | 2012-08-10 | 2012-08-15 |  | 2012-08-17 | 2012-08-16 | NES | 2012-08-15 | 2012-08-13 | 2012-09-14 | 2012-08-27 | 2 | 2012-09-21 | 2012-08-27 | 2012-08-17 |  | 2012-09-20 | 2012-09-13 | 1 |  | 2012-09-20 | 2012-09-13 |  |  |  | 2012-09-03 |  | 2012-10-02 | 2012-10-02 | 2012-10-25 | 2012-10-25 | 2012-10-09 | 2012-11-09 | 2012-11-09 | 2012-11-08 | 2012-11-07 | [6 empty] | 2012-11-12 | 2012-11-26 | 2012-11-15 | 2012-12-12 | 2012-11-27 | 2013-04-26 | 2013-04-26 | 18/03/13 - snags to clear for FAN issue. 09/04/13 - FAN in process - only need Boundary survey confirmation email to design 26/04/13 - FAC signed |  | 2012-11-10 | 2012-10-06 | 2012-10-06 | 2012-10-03 | 2012-10-03 | 2012-10-15 |  | 2012-11-02 | 2012-11-02 | 2012-11-12 | 2012-11-13 | 2012-07-12 | LOW | WHAKATANE | 2012-10-29 | 2012-11-07 | BUILD | 2012-10-09 | TRUE |  | 2863266 | 6352696 | Kohi Point Lookout Road beside Otarawairere Road Ohope |  |  | CELLSITE |  |  | 2015-10-21 | [12 empty] | 2012-11-13 | 2012-11-15 | 2012-06-12
0 | BOP | 601 | BOP-025-002 | Whakatane North | BOP-025-002-A | Kakahoroa LPR | Whakatane | 2 | TIER_3 | ACTIVE | RSR | DU | P4F |  | INLINE | STANDALONE | 11.5 | 13 | 1 | -37.9503 | 176.9949 | 2010-07-01 |  |  | 2010-06-06 | Fibre Optic |  | FALSE | FALSE | 2010-07-01 |  | FALSE |  | 2012-06-07 | 2012-06-07 | 2012-06-11 | 2012-06-12 | 2012-07-06 | 2012-07-10 | 3 | 2012-07-06 | 2015-05-15 | 2012-08-17 | 2012-08-15 | 2012-08-17 | 2012-08-15 |  | 2012-08-24 | 2012-08-21 | NES | 2012-08-17 | 2012-08-17 | 2012-09-21 | 2012-09-18 | 2 | 2012-09-28 | 2012-09-18 | 2012-08-17 |  | 2012-09-25 | 2012-09-25 | 1 |  | 2012-09-25 | 2012-09-25 | 2012-10-24 |  |  | 2012-09-13 |  | 2012-10-16 | 2012-10-15 | 2012-10-25 | 2012-10-25 | 2012-10-24 | 2012-10-30 | 2012-10-30 | 2012-11-07 | 2012-11-07 | [6 empty] | 2012-11-12 | 2012-11-26 | 2012-11-15 | 2012-12-12 | 2012-11-27 | 2013-04-26 | 2013-04-26 | 18/03/13 - snags to clear for FAN issue 26/04/13 - FAC signed |  | 2012-11-10 | 2012-10-06 | 2012-10-06 | 2012-10-03 | 2012-10-03 | 2012-10-16 | 2012-10-24 | 2012-10-30 | 2012-10-30 | 2012-11-13 | 2012-11-13 | 2012-08-08 | LOW | WHAKATANE | 2012-10-23 | 2012-10-24 | BUILD | 2012-10-24 | TRUE | 2012-09-04 | 2861149 | 6353581 | Kakahoroa Drive Whakatane |  |  | CELLSITE |  |  | 2015-10-21 | [12 empty] | 2012-11-15 | 2012-11-15 | 2012-06-12
0 | BOP | 602 | BOP-025-003 | Whakatane South | BOP-025-003-C | Whakatane South | Whakatane | 2 | TIER_3 | ACTIVE | GF | DU | T2 25 RF |  | STACK_A | STANDALONE |  | 25 | 1 | -37.9727 | 176.965 | 2010-07-01 |  |  | 2010-06-06 | Fibre Optic |  | FALSE | FALSE | 2010-07-01 |  | FALSE |  | 2012-07-16 | 2012-08-01 | 2012-07-31 | 2012-08-03 | 2012-09-04 | 2012-08-24 | 3 | 2012-09-04 | 2012-09-26 | 2012-10-12 | 2012-10-12 | 2012-10-19 | 2012-10-30 | 3 | 2012-10-26 | 2012-10-30 | PERMITTED | 2012-09-17 | 2012-09-17 | 2012-10-18 | 2012-10-01 | 2 | 2012-10-25 | 2012-10-05 |  | 2012-10-31 | 2012-11-30 | 2012-11-30 | 1 |  | 2012-11-30 | 2012-11-30 | 2013-01-07 |  |  | 2012-11-20 |  | 2012-12-04 | 2012-12-03 | 2013-01-23 | 2013-01-23 | 2013-01-24 | 2013-02-05 | 2013-02-04 | 2013-01-30 | 2013-02-04 | [6 empty] | 2013-02-08 | 2013-02-14 | 2013-02-14 | 2013-03-08 | 2013-02-22 | 2013-06-04 | 2013-05-30 | 18/03/13 - Snags to clear and PSVP to pass before FAN issue 30/05/13 - FAC signed |  | 2013-02-07 | 2012-12-11 | 2012-12-11 | 2012-12-10 | 2012-12-10 | 2013-01-07 | 2013-01-07 | 2013-01-24 | 2013-01-24 | 2013-02-08 | 2013-02-08 | 2012-09-01 | LOW | WHAKATANE | 2013-01-22 | 2013-01-25 | BUILD | 2013-01-24 | TRUE | 2012-11-15 | 2858417 | 6351213 | 408-426 Te Rahu Road, Poroporo Whakatane |  |  | CELLSITE |  |  | 2015-10-21 | [12 empty] | 2013-02-11 | 2013-02-11
0 | BOP | 603 | BOP-025-004 | Kohi Point Lookout |  |  | Whakatane |  | TIER_9 | [22 empty] | FALSE
0 | BOP | 604 | BOP-025-005 | Putauaki | BOP-025-005-A | Putauaki (Kordia) | Whakatane | 22 | TIER_4 | ACTIVE | COLO | DF | COLO |  | STACK_A | COLO |  |  |  | -38.1048 | 176.737 |  |  |  |  | Leased Line, Microwave | BOP-025-009-B | FALSE | FALSE |  |  | FALSE |  | 2014-10-15 | 2014-10-15 | 2014-11-14 | 2014-11-14 | 2015-01-30 | 2015-01-16 | 1 | 2015-01-30 | 2015-01-16 | 2014-12-19 | 2015-01-13 | 2015-05-13 | 2015-04-21 |  | 2015-05-20 | 2015-04-21 | OPW | 2015-01-30 | 2015-01-16 | 2015-02-27 | 2015-02-26 | 1 | 2015-03-06 | 2015-02-26 | 2015-02-16 | 2015-02-13 | 2015-03-23 | 2015-05-01 | 1 |  | 2015-03-30 | 2015-05-01 | [5 empty] | 2015-08-10 | 2015-08-11 | 2015-08-17 | 2015-08-13 | 2015-08-13 | 2015-08-21 | 2015-08-24 | [9 empty] | 2015-09-16 | 2015-09-11 | 2015-09-28 | 2015-09-29 |  |  | 13/03/12 - Colocation documents have been sent through to Kordia. However thay now are required to lower the mast to 24m by 2016, so looking at our options 16/10/14 - Kordia happy to reconsider application - revised application lodged with Shane Gerraty for processing in Kordia. 2 antenna options requested. Cabinets will need to go indoors. 16/12/2014 - this is named as one of the top 13 roaming sites to build next year. Awaiting Kordia feedback on our proposal. 15/1/15 - design agreed with Kordia, RC to be submitted by Kordia - PO emailed to Shane for this 28/1/15 - lease agreement and costs to be finalised when Shane returns from AL next week 25.2.15 - with Kordia for RC and CD's 9/3/15 - cabs & TX ordered - antenna order with Huawei 1/4/15 - BI issued to Hawei | KDA | 2015-08-20 | [6 empty] | 2015-08-15 | 2015-08-15 | 2015-09-15 | 2015-09-08 |  |  | WHAKATANE |  |  | BUILD | 2015-08-13 | FALSE |  | 2837795 | 6337423 | Off McKee Rd, Kawerau |  |  | CELLSITE |  |  |  | ROAMING |  |  | 2015-02-09 |  | 2015-04-01 | [5 empty] | 2015-05-18 | 2015-09-04 |  | 2014-11-14
0 | BOP | 605 | BOP-025-006 | Murupara | BOP-025-006-B | Fell Property Greenfield | Whakatane | 22 | TIER_4 | ACTIVE | GF | DU | T2 20 RF |  | STACK_A | COSITE | 19.5 | 20 |  | -38.498 | 176.6962 |  |  |  |  | Microwave | BOP-025-010-B | FALSE | FALSE |  |  | FALSE |  | 2012-03-06 | 2012-03-06 | 2012-04-10 | 2012-04-10 | 2012-05-21 | 2012-05-24 | 1 | 2012-05-23 | 2012-05-24 | 2012-06-08 | 2012-04-12 | 2012-06-29 | 2012-05-10 |  | 2012-07-06 | 2012-05-10 | PERMITTED | 2012-05-28 | 2012-05-29 | 2012-07-04 | 2012-06-14 | 1 | 2012-07-09 | 2012-06-14 | 2014-10-24 | 2014-10-21 | 2015-02-13 | 2015-02-10 | 1 |  | 2015-02-13 | 2015-02-10 | [5 empty] | 2015-06-08 | 2015-06-08 | 2015-07-24 | 2015-07-23 | 2015-07-14 | 2015-07-22 | 2015-07-23 | [8 empty] | 2015-08-24 | 2015-08-18 | 2015-08-11 | 2015-08-17 | 2015-08-28 |  |  | 25/05/12 - Co-site application lodged with VF 14/06/12 - Hardmatched 07/08/12 - WO2 forecasted 05/10/12 - Taken out of Build programme Hardmatch 16/1/15 - awaiting CD 1 issue 9/3/15 - Cabs & tX equipment ordered, pole PO in signoff, antenna order with Huawei |  | 2015-07-24 | [6 empty] | 2015-07-02 | 2015-07-09 | 2015-08-06 | 2015-08-05 |  |  | ROTORUA_TAUPO |  |  | BUILD | 2015-07-21 | FALSE |  | 2832419 | 6293969 | Cnr Golf and Fells Road Murupara |  | Rural 2 zone on farm. Can do 20m mast as a permitted activity - 05/06/2012 | CELLSITE |  |  |  | ROAMING |  | 2015-03-13 | 2015-02-09 |  | 2015-03-30 | [5 empty] | 2015-05-20 |  |  | 2012-04-10
0 | BOP | 606 | BOP-025-007 | Whakatane North |  |  | Whakatane |  | TIER_9 | [22 empty] | FALSE
0 | BOP | 607 | BOP-025-008 | Whakatane South |  |  | Whakatane |  | TIER_9
0 | BOP | 608 | BOP-025-009 | Kawerau | BOP-025-009-B | Kawerau CBD | Whakatane | 2 | TIER_3 | ACTIVE | GF | DU | T2 25 UF |  | STACK_A | STANDALONE |  | 25 | 1 | -38.0867 | 176.7006 | 2012-06-05 | 2012-05-29 | 2012-06-06 |  | Fibre Optic |  | FALSE | FALSE |  | 2012-06-29 | FALSE |  | 2012-09-17 | 2012-09-17 | 2012-09-21 | 2012-09-21 | 2012-10-19 | 2012-10-18 | 2 | 2012-10-19 | 2012-10-25 | 2012-10-12 | 2012-10-12 | 2012-10-19 | 2012-10-31 |  | 2012-10-26 | 2012-11-30 | PERMITTED | 2012-10-19 | 2012-10-25 | 2012-11-20 | 2012-11-15 | 2 | 2012-11-27 | 2012-11-15 |  | 2012-10-31 | 2012-11-30 | 2012-11-30 | 1 |  | 2012-11-30 | 2012-11-30 | 2013-01-07 |  |  | 2012-11-30 |  | 2013-01-21 | 2013-01-21 | 2013-02-12 | 2013-02-12 | 2013-02-07 | 2013-03-07 | 2013-03-05 | 2013-02-21 | 2013-02-25 | [6 empty] | 2013-03-05 | 2013-03-15 | 2013-03-11 | 2013-03-28 | 2013-03-22 | 2013-08-23 | 2013-10-17 | 26/02/12 - Anteanna pinched by 'Himitangi". Jon getting one specially couriered in 12/03/12 - SOA 18/03/13 - Snags to clear and PSVP to pass before FAN issue 17/10/13 - FAC signed |  | 2013-03-07 | 2012-12-10 | 2012-12-10 | 2012-12-11 | 2012-12-11 | 2013-01-02 | 2013-01-07 | 2013-02-13 | 2013-02-13 | 2013-03-12 | 2013-03-06 |  |  | WHAKATANE | 2013-02-19 | 2013-02-25 | BUILD | 2013-02-07 | TRUE | 2012-11-30 | 2834683 | 6339560 | Council Carpark Off Plunket Street Kawerau |  |  | CELLSITE | [15 empty] | 2013-03-13 | 2013-03-07
0 | BOP | 609 | BOP-025-010 | Murupara Exchange (TX) | BOP-025-010-B | Telecom Exchange (TX) | Whakatane | 22 | TIER_4 | ACTIVE | COLO | TX | COLO |  |  | COLO | [9 empty] | Fibre Optic | BOP-024-003-A | TRUE | FALSE |  |  | FALSE |  | 2012-06-11 | 2012-06-07 | 2012-06-13 | 2012-06-12 | 2012-06-27 | 2012-08-03 | 2 | 2012-06-28 | 2012-08-10 | 2015-03-03 | 2015-03-20 | 2015-04-01 | 2015-04-22 |  | 2015-04-08 | 2015-06-03 | DISCRETIONARY_FULL | 2012-09-07 | 2012-08-29 | 2012-10-12 | 2012-10-03 | 1 | 2012-10-01 | 2012-10-08 | 2015-01-30 | 2015-01-30 | 2015-02-27 | 2015-02-19 | 1 |  | 2015-02-27 | 2015-02-19 | [5 empty] | 2015-06-25 | 2015-06-25 | 2015-07-20 | 2015-07-23 |  | 2015-07-24 | 2015-07-24 | [9 empty] | 2015-08-18 | 2015-08-11 | 2015-08-17 | 2015-08-28 |  |  | 01/06/12 - Candidate initiated for linking option of Murupara 25-006 to Telecom fibre network 08/06/12 - Site caravaned and WO1 to be issued 12/06/12 - Work order 1 issued 27/06/12 - Lodge Telecom co-lo and Chorus colo when drawings available 24/07/12 - where are the PD Rev 1 9/3/15 - TX equipment ordered 23/08/12 - Telecom approval required to Lodge RMA 05/10/12 - Taken out of Build programme Hardmatch 08/10/12 - COC granted 16/1/15 - awaiting chorus feedback on co-lo application for MW dish on pole - sent 13/11/14 28/1/15 - still awaiting chorus feedback - once recieved we can send a rigger to measure pole for structural analysis for our MW dish 19.2.15 - prelim approval received, awaiting CD's from Ritchie 25.2.15 - have submitted to Huawei for Project Plan 20/5/15 - Submitted PP from Kordia to Chorus via Jordan | TNZ | [9 empty] | 2015-08-06 | 2015-08-05 | 2012-08-06 | LOW | TRANSMISSION_ONLY |  |  | BUILD |  | FALSE |  |  |  | Telecom Exchange 46 Pine Drive Murupara |  |  | TXSITE |  |  |  | ROAMING |  |  | 2015-02-09 |  | 2015-03-30 | [5 empty] | 2015-05-20 |  |  | 2012-06-12
0 | BOP | 610 | BOP-025-011 | Manawahe | BOP-025-011-A | Chorus RBI Manawahe | Whakatane | 22 | TIER_4 | ACTIVE | RBI | DU | LATTICE |  | STACK_A | COLO |  |  |  | -37.9815 | 176.6821 |  |  |  |  | Microwave | BOP-025-003-C | FALSE | FALSE |  |  | FALSE |  | 2014-12-09 | 2014-12-04 | 2014-11-24 | 2014-11-21 | 2014-11-28 | 2012-10-31 | 3 | 2014-12-05 | 2015-04-15 | 2015-06-12 | 2015-06-09 | 2015-07-31 | 2015-07-16 |  | 2015-08-07 | 2015-09-08 | DISCRETIONARY_FULL | 2015-06-12 | 2015-06-16 | 2015-07-24 | 2015-07-17 | 3 | 2015-07-31 | 2015-07-17 | 2015-06-12 | 2015-06-25 | 2015-07-30 | 2015-08-26 | 1 |  | 2015-07-31 | 2015-08-26 | [5 empty] | 2015-10-16 | 2015-10-14 | 2015-11-13 | 2015-11-16 |  | 2015-11-16 | 2015-11-17 | [9 empty] | 2015-11-30 | 2015-11-30 | 2015-12-18 | 2015-12-16 |  |  | 01/02/12 - RBI site being managed by Vodafone. Acq and Planning will be done by them 14/02/12 - This is a Telecom site, which VF is using for RBI. We will obtain access in Oct once RBI completed. Ron to talk with Jason re options to move forward faster 06/08/12 - Caravaned Structural to be done first if ok then W01 05/10/12 - Taken out of Build programme Hardmatch 16/1/15 - initial application sent to Vchorus 8/12/14 - awaiting feedback 18.2.14 - VF co-lo application with Trevor to fill in RF information 19.2.15 - RBI application submitted to VF 27.02.15 - Re-sent co-lo submission to Chorus after feedback from VF | TNZ | [9 empty] | 2015-11-25 | 2015-11-25 |  |  | RBI |  |  | BUILD |  | FALSE |  | 2833545 | 6351299 | Manawahe 1595A MANAWAHE ROAD MATATA-MANAWAHE |  |  | CELLSITE |  |  |  | ROAMING |  |  | 2015-04-24 | 2015-07-24 | 2015-08-07 |  |  |  |  | 2015-09-25 | 2015-09-15 |  |  | 2014-11-21
0 | BOP | 611 | BOP-025-012 | RBI - Waimana | BOP-025-012-A | Waimana RBI | Whakatane | 25 | TIER_5 | ACTIVE | RBI | DF | COLO |  | STACK_A | COLO | 23 | 25 |  | -38.1356 | 177.1024 |  |  |  |  | Fibre Optic | BOP-023-004-A | FALSE | FALSE |  |  | FALSE |  | 2015-10-14 | 2015-10-14 | 2015-10-23 | 2015-11-23 | 2015-10-23 | 2015-11-02 | 1 | 2015-10-27 | 2015-11-02 | 2016-02-04 |  | 2016-02-26 |  |  | 2016-02-26 |  | PERMITTED | 2016-01-29 |  | 2016-02-04 |  |  | 2016-02-05 |  | 2015-11-16 | 2015-11-16 | 2016-02-09 | 2016-01-22 | 1 |  | 2016-02-11 | 2016-01-22 | [5 empty] | 2016-04-11 |  | 2016-04-15 |  |  | 2016-04-15 |  | 2016-03-11 |  | 2016-03-09 |  | 2016-03-30 |  | 2016-03-31 |  |  | 2016-04-28 | [5 empty] | 8 Oct: SDP received 16 Oct: VF co-lo & Spark co-site lodged & Pre-qual requested. CD1 requested. 19 Oct: Letter to planner drafted. Will be sent when VF advises LO of co-lo request. 7 Dec: Waiting for VF approval. ATN & antenna ordered 17 Dec: VF Pre-approval granted 13 Jan: Waiting for formal VF approval & VF antenna quote. 3 Feb: Waiting on VF pre-approval & antenna quote. | VNZ | [9 empty] | 2016-04-22 |  |  |  |  | 2016-04-12 |  | BUILD | 2016-04-11 | FALSE |  | 2869653 | 6332612 | Eagles Road, Waimana Whakatane |  |  | CELLSITE |  |  |  | ROAMING |  |  | 2016-02-10 | 2015-12-22 | 2015-12-22 | 2015-10-16 | 2015-10-19 | 2015-11-13 | 2015-11-13 | 2016-02-12 | 2016-02-02 |  |  | 2015-10-16
0 | BOP | 612 | BOP-025-013 | RBI - Nukuhou North |  |  | Whakatane |  | RBI | [22 empty] | FALSE
0 | BOP | 613 | BOP-025-014 | RBI - Whakatane West |  |  | Whakatane |  | RBI | [22 empty] | FALSE
0 | BOP | 614 | BOP-025-015 | RBI - Thornton BOP | BOP-025-015-A | Thornton RBI | Whakatane | 25 | TIER_5 | ACTIVE | RBI | DF | COLO |  | STACK_A | COLO | 28 | 30 |  | -37.9317 | 176.8303 |  |  |  |  | Fibre Optic | BOP-023-004-A | FALSE | FALSE |  |  | FALSE |  | 2015-10-13 | 2015-10-14 | 2015-10-16 | 2015-10-19 | 2015-10-19 | 2015-11-02 | 1 | 2015-10-27 | 2015-11-02 | 2016-01-21 | 2015-11-23 | 2015-11-24 | 2015-11-26 |  | 2016-02-12 | 2016-02-05 | PERMITTED | 2015-11-26 | 2015-11-26 | 2015-11-30 | 2015-12-12 | 1 | 2015-11-30 | 2015-12-03 | 2015-11-17 | 2015-12-16 | 2015-12-22 | 2016-01-15 | 1 |  | 2015-12-23 | 2016-01-15 | [5 empty] | 2016-02-29 |  | 2016-03-04 |  |  | 2016-03-04 |  | 2016-02-24 |  | 2016-01-28 |  | 2016-02-17 |  | 2016-02-17 | 2016-01-25 |  | 2016-03-18 | [5 empty] | 8 Oct: Site data pack received 16 Oct: VF co-lo & Spark co-site lodged & Pre-qual requested. CD1 requested. 19 Oct: Letter to planner drafted. Will be sent when VF advises LO of co-lo request. 9 Dec: TI issued to Huawei 12 Jan: Waiting to hear about antenna ETA 17 Jan: Tender quote visit scheduled. 21 Jan: Contractor quotes due. 3 Feb: PO6 Issued. VF approval received. Start construction 29th Feb. 10 Feb: CX Config raised for 17th Feb | VNZ | [9 empty] | 2016-03-11 |  | 2016-01-28 | LOW |  | 2016-03-01 |  | BUILD | 2016-02-29 | FALSE |  | 2846789 | 6356272 | 312 West Bank Road, Thornton, Edgecumbe |  |  | CELLSITE |  |  |  | ROAMING |  |  | 2016-02-10 | 2015-11-23 | 2015-12-09 | 2015-10-16 | 2015-10-20 | 2015-11-18 | 2015-11-18 | 2016-01-29 | 2016-02-02 |  |  | 2015-10-19
0 | BOP | 615 | BOP-025-016 | RBI - Ruatoki | BOP-025-016-A | Ruatoki - RBI | Whakatane | 23 | TIER_4 | ACTIVE | RBI | DF |  |  | INLINE | COLO | 28 | 30 |  | -38.1371 | 176.9885 |  | 2015-07-16 |  |  | Fibre Optic | BOP-023-004-A | FALSE | FALSE |  |  | FALSE |  | 2015-07-13 | 2015-07-13 | 2015-07-30 | 2015-07-30 | 2015-07-30 | 2015-08-18 | 1 | 2015-07-30 | 2015-08-18 | 2015-08-14 | 2015-08-19 | 2015-09-15 | 2015-09-21 |  | 2015-09-16 | 2015-11-04 | PERMITTED | 2015-08-18 | 2015-09-03 | 2015-08-21 | 2015-09-03 | 1 | 2015-08-21 | 2015-11-30 | 2015-07-20 | 2015-07-20 | 2015-08-04 | 2015-08-04 | 3 |  | 2015-08-06 | 2015-08-11 | [5 empty] | 2015-11-30 | 2015-11-30 | 2015-12-04 | 2015-12-14 | 2015-12-03 | 2015-12-07 | 2015-12-07 | 2015-12-08 | 2015-12-08 | 2015-08-25 |  | 2015-09-30 |  |  |  |  | 2015-12-21 | 2015-12-21 |  |  |  |  | 20 July: lodged VF/Spark co-site application 31 Jul: e-mailed Mike Parker at VF re replacement antennas 5 Aug: Fibre ordered & TI issued to Huawei 12 Aug: RFS 28 Aug (need to push out to coincide with cabinet delivery date) 18 Aug: PO for VF raised (waiting for approval) 19 Aug: Prelim approval received 28/8/15 - POR raised. Issued 03 Sept. 21/09/15 - Lodged for final approval 20/10/15 - Lodged for build approval - Received 4/11/15 24/11/15 - Transfield delayed start to 30 Nov 7/12/15 - power to be connected, Integration, Testing | VNZ | [9 empty] | 2015-12-14 | 2015-12-15 |  |  |  | 2015-12-08 | 2015-12-08 | BUILD | 2015-11-30 | FALSE |  | 2859669 | 6332894 | 168 Ohotu Road, Ruatoki North |  |  | CELLSITE |  |  |  | ROAMING |  |  | 2015-07-03 | 2015-08-13 | 2015-08-07 | 2015-07-20 | 2015-07-20 | 2015-07-31 | 2015-08-05 | 2015-09-04 | 2015-09-03 |  |  | 2015-07-23
0 | BOP | 616 | BOP-026-001 |  |  |  | Kawerau |  | TIER_9
0 | BOP | 617 | BOP-027-001 |  |  |  | Opotiki |  | TIER_9
0 | BOP | 618 | BOP-027-002 | Opotiki | BOP-027-002-A | Mitre 10 Greenfield | Opotiki | 2 | TIER_3 | ACTIVE | GF | DU | T2 15 UF |  | STACK_A | STANDALONE | 14.4 | 15 | 1 | -38.0078 | 177.2852 |  |  |  |  | Fibre Optic |  | FALSE | FALSE |  |  | FALSE |  | 2012-04-30 | 2012-04-23 | 2012-05-04 | 2012-05-02 | 2012-05-30 | 2012-06-06 | 1 | 2012-05-30 | 2012-06-06 | 2012-06-15 | 2012-05-29 | 2012-09-07 | 2012-09-10 |  | 2012-09-07 | 2012-09-10 | PERMITTED | 2012-07-09 | 2012-07-11 | 2012-08-20 | 2012-08-15 | 1 | 2012-08-27 | 2012-08-21 | 2012-08-14 |  | 2012-10-08 | 2012-10-04 | 1 |  | 2012-10-08 | 2012-10-04 | 2012-11-14 |  |  | 2012-09-29 |  | 2012-10-31 | 2012-10-31 | 2012-11-21 | 2012-11-21 | 2012-11-20 | 2012-11-26 | 2012-11-26 | 2012-11-22 | 2012-11-26 | [6 empty] | 2012-11-27 | 2012-12-07 | 2012-12-03 | 2012-12-12 | 2012-12-05 | 2013-05-28 | 2013-05-24 | 18/03/13 - snags to clear and PSVP to pass before FAN issue 24/05/13 - FAC signed |  | 2012-11-27 | 2012-10-06 | 2012-10-06 | 2012-10-29 | 2012-11-14 | 2012-10-22 | 2012-11-14 | 2012-11-22 | 2012-11-22 | 2012-11-28 | 2012-11-28 | 2012-03-30 | MEDIUM | WHAKATANE | 2012-11-08 | 2012-11-13 | BUILD | 2012-11-20 | TRUE | 2012-09-28 | 2886339 | 6346036 | Abbot Lane Opotiki |  |  | CELLSITE | [15 empty] | 2012-11-28 | 2012-11-28 | 2012-05-02
0 | BOP | 619 | BOP-027-003 | RBI - Te Kaha |  |  | Opotiki |  | RBI | [22 empty] | FALSE
0 | BOP | 620 | BOP-027-004 | RBI - Kutarere |  |  | Opotiki |  | RBI | [22 empty] | FALSE
South Island | OTG | 1211 | OTG-070-004 | Queenstown Kordia POP | OTG-070-004-A | Kordia POP | Queenstown |  | TIER_1_ALL | ACTIVE | COLO | TX | COLO | [6 empty] | -45.029 | 168.6582 | [12 empty] | 2009-02-11 | 2009-02-11 |  |  |  | 2009-04-21 | 1 | 2009-04-21 | 2009-04-21 |  |  | 2009-05-20 | 2009-05-15 |  | 2009-05-20 | 2009-05-15 |  | 2009-04-29 |  | 2009-05-18 |  |  | 2009-06-16 | 2009-05-19 |  | 2009-04-07 |  | 2009-05-14 | 1 | 1 | 2009-05-01 | 2009-05-14 | [5 empty] | 2009-04-27 | 2009-04-27 | 2009-05-27 | 2009-05-22 |  | 2009-05-28 | 2009-05-23 | [8 empty] | 2009-06-05 | 2009-06-10 | 2009-06-05 | [6 empty] | 2009-06-10 | [17 empty] | FALSE |  | 2167959 | 5566431 | 1 Isle Street Queenstown Otago |  |  | TXSITE | [7 empty] | 2009-05-01 | 2009-04-15 | [8 empty] | 2009-04-07
South Island | OTG | 1208 | OTG-070-001 | Peninsula Hill | OTG-070-001-A | Peninsula Hill | Queenstown |  | TIER_1_ALL | ACTIVE | GF | A | P8 | grey |  |  | 13.8 | 13.8 |  | -45.0407 | 168.724 |  |  |  |  | Microwave | OTG-070-004-A | [6 empty] | 2009-02-11 | 2009-02-11 |  |  |  | 2008-02-20 | 7 | 2009-03-04 | 2009-03-26 |  |  | 2009-04-01 | 2008-10-06 |  | 2009-05-30 | 2009-06-02 |  | 2009-03-11 |  | 2009-03-18 |  |  | 2009-04-03 | 2009-04-02 | 2009-03-09 | 2009-03-13 |  | 2009-03-30 | 1 | 7 | 2009-03-20 | 2009-03-30 | 2009-04-08 | [5 empty] | 2009-04-06 | 2009-05-15 | 2009-05-08 |  | 2009-05-22 | 2009-05-15 | [8 empty] | 2009-06-08 | 2009-06-12 | 2009-06-08 |  |  |  |  | Hub Site |  | 2009-06-12 |  |  |  |  | 2009-04-20 | 2009-04-08 | [11 empty] | FALSE |  | 2173202 | 5565412 | Deer Park Heights 432 Peninsula Road Peninsula Hill Queenstown |  |  | CELLSITE | [7 empty] | 2009-03-27 | 2009-03-27 | [8 empty] | 2009-02-19
South Island | OTG | 1212 | OTG-070-005 | Frankton | OTG-070-005-A | Frankton | Queenstown |  | TIER_1_ALL | ACTIVE | GF | A | OTHERS | grey |  |  | 15 | 15 |  | -45.01 | 168.7395 | [12 empty] | 2009-02-11 | 2009-02-11 |  |  |  | 2009-03-26 | 4 | 2009-04-03 | 2009-05-05 |  |  | 2009-06-04 | 2009-05-29 | 4 | 2009-06-04 | 2009-06-04 |  | 2009-04-23 |  | 2009-05-20 |  |  | 2009-05-27 | 2009-05-28 | 2009-04-14 | 2009-04-21 |  | 2009-05-04 | 3 | 4 | 2009-05-08 | 2009-06-30 | 2009-03-31 |  |  |  |  | 2009-06-08 | 2009-06-08 | 2009-07-17 | 2009-07-17 |  | 2009-07-24 | 2009-07-22 | [8 empty] | 2009-07-31 | 2009-07-29 | 2009-07-31 |  |  |  |  | Awaiting update on snags. We need the acceptance report from Aurecon to complete Kerry's report. |  | 2009-07-29 |  |  |  |  | 2009-04-07 | 2009-03-31 | [11 empty] | FALSE |  | 2174243 | 5568873 | Transpower site 93 Frankton - Ladies Mile Highway Frankton Otago |  |  | CELLSITE | [7 empty] | 2009-06-04 | 2009-06-04 | [8 empty] | 2009-02-19
South Island | OTG | 1209 | OTG-070-002 | Gondola | OTG-070-002-A | Gondola | Queenstown |  | TIER_1_ALL | ACTIVE | BO | D | NOPOLE | green |  |  | 0 | 0 |  | -45.027 | 168.6498 |  |  |  |  | Microwave | OTG-070-001-A | [6 empty] | 2009-02-11 | 2009-02-11 |  |  |  | 2009-03-26 | 6 | 2009-03-20 | 2010-06-28 |  |  | 2009-06-04 | 2009-06-08 | 3 | 2009-06-04 | 2009-06-08 |  | 2009-03-23 |  | 2009-05-11 |  |  | 2009-05-15 | 2009-05-13 | 2009-04-14 | 2009-04-08 |  | 2009-05-13 | 2 | 5 | 2009-05-12 | 2009-05-27 | [5 empty] | 2009-05-08 | 2009-05-30 | 2009-07-23 | 2009-06-29 |  | 2009-07-28 | 2009-07-30 | [8 empty] | 2009-07-31 | 2009-07-30 | 2009-07-31 |  |  |  |  | In Build. 2 Sectors initially. Sector 3 to be advised. S127: RMA access tidy up. |  | 2009-07-30 | [17 empty] | FALSE |  | 2167287 | 5566623 | Skyline Restaurant/Gondola Bob's Peak Brecon Street Queenstown |  |  | CELLSITE |  |  | 2015-05-26 |  |  |  |  | 2009-06-02 | 2009-06-02 | [8 empty] | 2009-02-19
South Island | OTG | 1210 | OTG-070-003 | Coronet Peak | OTG-070-003-A | Coronet | Queenstown |  | TIER_1_ALL | ACTIVE | GF | D | P2 | grey |  |  | 15 | 15 |  | -44.927 | 168.7369 |  |  |  |  | Microwave | OTG-070-001-A | [6 empty] | 2009-02-11 | 2009-02-11 |  |  |  | 2009-03-09 | 5 | 2009-07-17 | 2011-05-11 |  |  | 2009-05-07 | 2009-04-30 | 2 | 2009-11-27 |  |  | 2009-03-09 |  | 2009-11-27 |  |  | 2009-11-27 | 2009-11-25 | 2009-05-03 | 2009-02-11 |  | 2009-04-29 | 4 | 4 | 2009-11-20 | 2009-12-01 | 2009-07-08 |  |  |  |  | 2009-11-30 | 2009-12-02 | 2010-01-27 | 2010-01-27 |  | 2010-02-03 | 2010-01-31 | [8 empty] | 2010-02-02 | 2010-02-05 | 2010-02-02 |  |  |  |  | Land owner wants build in January 10, but will allow start in December, providing ground is solid enough for the plant. December dates at risk to the weather. (P Bunnage) |  | 2010-02-05 |  |  |  |  | 2009-07-29 | 2009-07-08 | [11 empty] | FALSE |  | 2173567 | 5578074 | Coronet Peak Ski Area Coronet Peak Road Queenstown |  |  | CELLSITE | [7 empty] | 2009-11-30 | 2009-12-02 | [8 empty] | 2009-02-19
South Island | STH | 1305 | STH-075-001 | Waikiwi | STH-075-001-B | Waikiwi GF | Invercargill City | 5 | TIER_2 | ACTIVE | GF | DU | T2 25 RF | grey | INLINE | COSITE | 26.1 | 28 | 1 | -46.3868 | 168.3494 | 2010-05-27 | 2010-05-27 | 2010-06-04 | 2010-06-04 | Microwave | STH-075-002-C | FALSE | FALSE | 2010-03-05 | 2010-03-05 | TRUE |  | 2011-02-11 | 2011-02-11 | 2011-02-18 | 2011-03-11 | 2011-04-19 | 2011-04-16 | 1 | 2011-04-19 | 2011-04-16 |  | 2011-04-18 | 2011-05-27 | 2011-04-18 | 1 |  | 2011-11-30 | PERMITTED | 2011-04-26 | 2011-04-18 | 2011-06-07 | 2011-05-11 | 1 |  | 2011-05-11 |  | 2011-06-23 | 2011-08-26 | 2011-08-25 | 1 |  | 2011-08-26 | 2011-08-25 | 2011-10-14 |  |  | 2011-08-18 |  | 2011-09-07 | 2011-09-08 | 2011-10-27 | 2011-10-27 | 2011-10-05 | 2011-10-27 | 2011-11-27 |  |  |  | 2011-07-07 |  |  |  |  | 2011-11-06 | 2011-11-14 | 2011-11-14 | 2011-11-23 | 2011-12-09 | 2012-03-08 | 2012-06-29 | snag clearance. |  | 2011-11-06 | 2011-08-05 | 2011-08-05 | 2011-09-23 | 2011-09-23 | 2011-10-14 | 2011-10-14 | 2011-09-28 | 2011-09-28 |  | 2011-11-09 | [6 empty] | 2011-09-28 | TRUE |  | 2152192 | 5414447 | 29 Preston Road, Invercargill |  | • Riverine Inundation Level 1 • Low degree of risk in sea level rise storm surge event • Located - 08/04/2011 | CELLSITE | [15 empty] | 2011-12-02 | 2011-11-28
South Island | STH | 1306 | STH-075-002 | Invercargill | STH-075-002-C | OnTrack monopole (HUB) | Invercargill City | 5 | TIER_2 | ACTIVE | GF | DU | SP | grey | STACK_A | COSITE | 35 | 35.5 |  | -46.4143 | 168.3451 | 2010-05-27 | 2012-06-07 | 2010-06-04 | 2010-06-04 | Microwave | STH-075-004-A | FALSE | FALSE | 2010-03-05 | 2010-03-05 | FALSE |  | 2011-04-01 | 2011-03-18 | 2011-03-23 | 2011-03-23 | 2011-05-06 | 2011-04-20 | 2 | 2011-05-06 | 2011-10-05 | 2011-05-16 | 2011-05-16 | 2011-07-04 | 2011-07-01 | 1 |  | 2011-07-01 | DISCRETIONARY_FULL | 2011-06-02 | 2011-05-27 | 2011-07-17 | 2011-06-23 | 1 |  | 2011-06-23 |  |  | 2011-09-08 | 2011-09-12 | 1 |  | 2011-09-08 | 2011-09-12 | 2011-10-21 |  |  |  |  | 2011-09-30 | 2011-10-03 | 2011-11-23 | 2011-11-23 | 2011-10-22 | 2011-11-02 | 2011-11-05 | [8 empty] | 2011-11-05 | 2011-11-14 | 2011-11-14 | 2011-12-28 | 2011-12-12 | 2013-10-04 | 2013-12-06 | Lighting design with HG - costs and timeline from skycomms. Generator to be installed but held up with legal - ongoing. 01/05 waiting for Wayne's response on lighting for KWR. |  | 2011-11-02 | 2011-08-12 | 2011-08-12 | 2011-09-23 | 2011-09-23 | 2011-10-21 | 2011-10-21 | 2011-10-28 | 2011-10-28 |  | 2011-11-08 | [5 empty] | BUILD | 2011-10-22 | FALSE |  | 2152039 | 5411377 | Opposite 70 Liddel Street Invercargill |  | over the permitted height limit (28m) - 27/05/2011 | CELLSITE |  |  | 2015-12-01 | [12 empty] | 2011-12-02 | 2011-11-29
South Island | STH | 1308 | STH-075-004 | Invercargill South | STH-075-004-A | Super Liquor Colo | Invercargill City | 5 | TIER_2 | ACTIVE | COLO | DU | COLO | grey | INLINE | COLO | 18.9 | 20 |  | -46.4349 | 168.3621 | 2010-05-27 | 2010-05-27 | 2010-06-04 | 2010-06-04 | Microwave | STH-075-008-B | FALSE | FALSE | 2010-03-05 | 2010-03-05 | FALSE |  | 2011-02-11 | 2011-02-11 | 2011-02-18 | 2011-03-11 | 2011-04-20 | 2011-04-20 | 3 | 2011-04-20 | 2011-08-22 | 2011-06-07 | 2011-06-07 | 2011-08-05 | 2011-08-04 | 1 |  | 2011-08-04 | DISCRETIONARY_FULL | 2011-05-06 | 2011-08-30 | 2011-09-27 | 2011-09-16 | 1 | 2011-09-27 | 2011-09-23 |  |  | 2011-08-25 | 2011-08-26 | 3 |  | 2011-09-12 | 2011-10-05 | 2011-10-07 |  |  | 2011-09-02 |  | 2011-10-14 | 2011-10-17 | 2011-10-23 | 2011-10-28 | 2011-10-22 | 2011-10-03 | 2011-11-07 |  |  |  | 2011-07-17 |  |  |  |  | 2011-11-07 | 2011-11-14 | 2011-11-14 | 2011-11-21 | 2011-12-12 | 2012-03-12 | 2012-05-17 | snag clearance | VNZ | 2011-11-08 | 2011-08-05 | 2011-08-05 | 2011-09-23 | 2011-09-23 | 2011-09-05 | 2011-10-07 | 2011-10-28 | 2011-10-28 |  | 2011-11-14 | [6 empty] | 2011-10-21 | TRUE |  | 2153472 | 5409163 | Super Liquor 406 Elles Road Invercargill |  | Within the approach slope to Invercargill Airport - 08/04/2011 antennas above permitted height limit - 29/04/2011 | CELLSITE | [15 empty] | 2011-12-02 | 2011-11-29
South Island | STH | 1310 | STH-075-006 | Invercargill SW | STH-075-006-B | RSR Invercargill SW | Invercargill City | 5 | TIER_2 | ACTIVE | RSR | DU | P4J | grey | INLINE | STANDALONE | 14.4 | 15.5 |  | -46.4373 | 168.2932 | 2010-05-27 | 2010-05-27 | 2010-06-04 | 2010-06-04 | Microwave | STH-075-004-A | FALSE | FALSE | 2010-03-05 | 2010-03-05 | FALSE | 2011-03-01 | 2011-04-01 | 2011-03-18 | 2011-04-08 | 2011-03-21 | 2011-04-19 | 2011-04-15 | 2 | 2011-04-19 | 2011-05-02 | 2011-05-16 | 2011-05-16 | 2011-06-24 | 2011-08-05 | 1 |  | 2011-08-05 | DISCRETIONARY_FULL | 2011-05-10 | 2011-05-06 | 2011-06-10 | 2011-06-03 | 2 |  | 2012-01-09 |  |  | 2011-08-02 | 2011-08-02 | 1 |  | 2011-08-02 | 2011-08-02 | 2011-09-26 |  |  | 2011-08-18 |  | 2011-09-19 | 2011-09-08 | 2011-10-03 | 2011-09-27 | 2011-10-16 | 2011-10-31 | 2011-11-07 | [8 empty] | 2011-11-09 | 2011-11-14 | 2011-11-14 | 2011-12-04 | 2011-12-09 | 2012-03-08 | 2012-05-17 | snag clearance |  | 2011-11-11 | 2011-08-02 | 2011-08-02 | 2011-09-26 | 2011-09-26 | 2011-09-08 | 2011-09-26 | 2011-10-07 | 2011-10-04 |  | 2011-11-16 | [6 empty] | 2011-10-13 | TRUE |  | 2148202 | 5408602 | Cnr of Vyner Rd & Taiepa Invercargill |  | Non complying NEs site, Discretionary Activity due to height of structure and within an Outstanding Landscape Area. Within the approach slope to Invercargill Airport • Located within Outstanding Natural Feature and Landscape - 08/04/2011 - 06/05/2011 | CELLSITE | [15 empty] | 2011-12-02 | 2011-11-28
South Island | STH | 1312 | STH-075-008 | Strathern | STH-075-008-B | Strathern GF Harvey Tanks | Invercargill City | 5 | TIER_2 | ACTIVE | GF | DU | T2 25 RF | grey | INLINE | STANDALONE |  | 28 |  | -46.414 | 168.379 | 2010-05-27 | 2010-05-27 | 2010-06-04 | 2010-06-04 | Microwave | STH-075-009-A | FALSE | FALSE | 2010-03-05 | 2010-03-05 | FALSE |  | 2011-02-11 | 2011-02-11 | 2011-02-18 | 2011-03-11 | 2011-04-28 | 2011-04-27 | 1 | 2011-04-28 | 2011-04-27 | 2011-05-27 | 2011-05-31 | 2011-06-21 | 2011-07-15 | 1 |  | 2011-08-09 | PERMITTED | 2011-05-27 | 2011-05-23 | 2011-06-17 | 2011-06-21 | 1 |  | 2011-06-21 |  |  | 2011-08-25 | 2011-08-29 | 1 |  | 2011-08-25 | 2011-08-29 | 2011-10-21 |  |  |  |  | 2011-10-06 | 2011-10-06 | 2011-10-30 | 2011-11-16 | 2011-10-28 | 2011-10-04 | 2011-11-07 |  |  |  | 2011-08-26 |  |  |  |  | 2011-11-09 | 2011-11-14 | 2011-11-14 | 2011-12-19 | 2011-12-09 | 2012-03-08 | 2012-05-17 |  |  | 2011-11-10 | 2011-08-05 | 2011-08-05 | 2011-09-23 | 2011-09-23 | 2011-10-21 | 2011-10-21 | 2011-10-29 | 2011-10-28 |  | 2011-11-17 | [6 empty] | 2011-10-28 | FALSE |  | 2154637 | 5411564 | Otepuni Avenue Invercargill |  |  | CELLSITE | [15 empty] | 2011-12-02 | 2011-11-28
South Island | STH | 1316 | STH-075-012 | Richmond | STH-075-012-B | Saint Andrews St pole Tavern RSR | Invercargill City | 5 | TIER_2 | ACTIVE | RSR | DU | P4J | grey | INLINE | STANDALONE | 14.4 | 15.5 |  | -46.4033 | 168.364 | 2010-05-27 | 2010-05-27 | 2010-06-04 | 2010-06-04 | Microwave | STH-075-009-A | FALSE | FALSE | 2010-03-05 | 2010-03-05 | FALSE |  | 2011-04-01 | 2011-03-18 | 2011-03-21 | 2011-03-21 | 2011-04-19 | 2011-04-20 | 1 | 2011-04-19 | 2011-04-20 |  | 2011-05-30 | 2011-05-27 | 2011-08-05 | 1 |  | 2011-08-05 | NES | 2011-05-11 | 2011-05-09 | 2011-06-20 | 2011-05-18 | 1 |  | 2011-05-18 |  |  | 2011-08-02 | 2011-08-02 | 1 |  | 2011-08-02 | 2011-08-02 | 2011-09-08 |  |  | 2011-08-18 |  | 2011-09-21 | 2011-09-22 | 2011-10-05 | 2011-10-04 | 2011-10-03 | 2011-10-31 | 2011-11-08 |  |  |  | 2011-06-17 |  |  |  |  | 2011-11-11 | 2011-11-14 | 2011-11-14 | 2011-12-19 | 2011-12-09 | 2012-03-08 | 2012-06-29 | Link to Strathern. |  | 2011-11-11 | 2011-07-05 | 2011-07-05 | 2011-09-23 | 2011-09-07 | 2011-09-08 | 2011-09-08 | 2011-09-05 | 2011-10-06 |  | 2011-11-16 | [6 empty] | 2011-10-04 | TRUE |  | 2153417 | 5412685 | St Andrew Street Invercargill |  | Within the Airport approach slopes - 08/04/2011 | CELLSITE | [15 empty] | 2011-12-02 | 2011-11-28
South Island | OTG | 1223 | OTG-071-001 | Taieri Plains | OTG-071-001-C | Airport TC Cosite | Dunedin | 4 | TIER_2 | ACTIVE | GF | DU | T2 20 RH |  | INLINE | COSITE | 16 | 16 | 1 | -45.9422 | 170.226 | 2010-05-27 |  | 2010-04-28 | 2010-04-28 | Microwave | OTG-071-004-D | FALSE | FALSE | 2009-12-17 | 2009-12-17 | FALSE | 2011-05-13 | 2011-04-01 | 2011-04-01 | 2011-04-08 | 2011-04-07 | 2011-05-20 | 2011-05-19 | 2 | 2011-05-20 | 2011-06-01 |  | 2011-06-14 | 2011-07-08 | 2011-07-01 | 2 |  | 2011-11-30 | PERMITTED | 2011-05-27 | 2011-05-27 | 2011-07-15 | 2011-07-01 | 2 |  | 2011-07-01 |  | 2011-07-22 | 2011-09-26 | 2011-09-27 | 1 |  | 2011-09-26 | 2011-09-27 | 2011-11-07 |  |  | -287862 |  | 2011-10-17 | 2011-10-17 | 2011-11-18 | 2011-11-16 | 2011-11-14 | 2011-11-21 | 2011-11-19 | [8 empty] | 2011-11-22 | 2011-11-30 | 2011-11-30 | 2011-12-27 | 2011-12-20 | 2012-03-19 | 2012-06-25 | Liz to follow up shared facilities agreement with TC. It won't be required to resolve this before FAC. 27/02 Shared access track agreement delayed due to Telecom / Chorus split - Liz. 01/05 FAN due soon. |  | 2011-11-22 | 2011-07-21 | 2011-07-21 | 2011-10-04 | 2011-10-20 | 2011-11-07 | 2011-11-07 | 2011-11-22 | 2011-11-22 |  | 2011-11-24 | [6 empty] | 2011-11-13 | TRUE |  | 2294763 | 5470319 | 909 Allanton Waihola Road RD2 Mosgiel |  | Airport Zone maimum height 10m, additional height is discretionary, up to 3m Dish is permitted. CAA will need to be approached for consent - umlikely to be an issue. - 24/03/2011 | CELLSITE | [15 empty] | 2011-12-12 | 2011-12-12
South Island | OTG | 1224 | OTG-071-002 | Abbotsford | OTG-071-002-E | Church Hill Rd | Dunedin | 4 | TIER_2 | ACTIVE | GF | DU | P2 |  | INLINE | COSITE |  | 16 | 1 | -45.9096 | 170.4328 | 2010-05-27 |  | 2010-04-28 | 2010-04-28 | Microwave | OTG-071-022-A | FALSE | FALSE | 2009-12-17 | 2009-12-17 | FALSE |  | 2011-05-13 | 2011-05-13 | 2011-05-20 | 2011-05-19 | 2011-06-09 | 2011-06-10 | 2 | 2011-06-09 | 2011-06-24 |  | 2011-07-19 | 2011-08-19 | 2011-08-10 | 2 |  | 2011-08-10 | PERMITTED | 2011-06-24 | 2011-06-24 | 2011-07-29 | 2011-07-22 | 2 |  | 2011-07-22 |  |  | 2011-09-06 | 2011-09-06 | 1 |  | 2011-09-06 | 2011-09-06 | 2011-09-30 |  |  | 2011-08-29 |  | 2011-11-04 | 2011-09-22 | 2011-10-28 | 2011-11-05 | 2011-10-11 | 2011-10-26 | 2011-10-26 | [8 empty] | 2011-10-27 | 2011-11-30 | 2011-11-30 | 2011-11-23 | 2011-11-25 | 2012-02-23 | 2012-07-31 | Rail lock has been modified. 01/05 No further complaints from neighbour. FAN due soon. |  | 2011-10-28 | 2011-07-13 | 2011-07-13 | 2011-09-25 | 2011-10-07 | 2011-10-04 | 2011-09-30 | 2011-10-26 | 2011-10-27 |  | 2011-11-01 | [6 empty] | 2011-10-11 | TRUE |  | 2310675 | 5474451 | Church Hill Road |  |  | CELLSITE | [15 empty] | 2011-11-15 | 2011-11-14 | 2011-05-19
South Island | OTG | 1226 | OTG-071-004 | Mosgiel Town | OTG-071-004-D | 127 Gordon Road | Dunedin | 4 | TIER_2 | ACTIVE | GF | DU | P2 | grey | INLINE | STANDALONE | 12 | 12.5 | 1 | -45.8745 | 170.3487 | 2010-05-27 |  | 2010-04-28 | 2010-04-28 | Microwave | OTG-071-005-A | FALSE | FALSE | 2009-12-17 | 2009-12-17 | FALSE | 2011-03-08 | 2011-03-09 | 2011-03-09 | 2011-04-19 | 2011-04-14 | 2011-05-11 | 2011-05-04 | 1 | 2011-05-11 | 2011-05-04 |  | 2011-05-05 | 2011-05-27 | 2011-05-27 | 1 |  | 2011-05-27 | PERMITTED | 2011-05-11 | 2011-05-06 | 2011-06-15 | 2011-05-20 | 1 |  | 2011-05-20 |  | 2011-07-22 | 2011-09-26 | 2011-09-27 | 1 |  | 2011-09-26 | 2011-09-27 | 2011-10-07 |  |  | 2011-09-08 |  | 2011-10-03 | 2011-10-03 | 2011-11-10 | 2011-11-16 | 2011-10-31 | 2011-11-22 | 2011-11-19 | [8 empty] | 2011-11-23 | 2011-11-30 | 2011-11-30 | 2011-12-27 | 2011-12-13 | 2012-03-12 | 2012-06-28 | Link to Halfway bush site requires equipment that is currently installed elsewhere. 07/02 Wait until Carisbrook + St Kilda are live until TX equip can be redeployed as per original plan for Mt Cargill. 07/05 construction starts this week. |  | 2011-11-24 | 2011-07-13 | 2011-07-13 | 2011-10-04 | 2011-10-04 | 2011-10-07 | 2011-10-07 | 2011-11-02 | 2011-11-02 |  | 2011-11-25 | [6 empty] | 2011-10-29 | TRUE |  | 2304036 | 5478141 | 127 Gordon Road, Mosgiel |  | Permitted activity if mast is not taller then 12m and cabinets meet noise requirements distances for 40dBA - is a house 25m to the North on landowners land - may need affected party approval if breech 12m in height, also nearby house 30m to the South East - 24/03/2011 | CELLSITE | [15 empty] | 2011-12-05 | 2011-11-30
South Island | OTG | 1230 | OTG-071-008 | MacAndrew Bay | OTG-071-008-A | Vodafone Colo | Dunedin | 4 | TIER_2 | ACTIVE | COLO | DU | COLO | grey | INLINE | COLO | 16 | 17.4 | 1 | -45.8834 | 170.5957 | 2010-05-27 |  | 2010-04-28 | 2010-04-28 | Microwave | OTG-071-010-A | FALSE | FALSE | 2009-12-17 | 2009-12-17 | FALSE |  | 2011-04-01 | 2011-04-01 | 2011-04-08 | 2011-04-07 | 2011-05-06 | 2011-05-06 | 1 | 2011-05-06 | 2011-05-06 |  | 2011-06-01 | 2011-08-31 | 2011-08-30 | 1 |  | 2011-09-08 | PERMITTED | 2011-07-12 | 2011-07-12 | 2011-08-09 | 2011-07-22 | 1 |  | 2011-07-22 |  | 2011-07-22 | 2011-09-12 | 2011-09-14 | 2 |  | 2011-09-12 | 2011-10-14 | 2011-10-20 |  |  | 2011-09-22 |  | 2011-11-01 | 2011-11-02 | 2011-11-26 | 2011-12-02 | 2011-11-21 | 2011-11-25 | 2011-11-25 | [8 empty] | 2011-11-26 | 2011-11-30 | 2011-11-30 | 2011-12-16 | 2011-12-20 | 2012-03-19 | 2012-06-29 | ok | VNZ | 2011-11-26 | 2011-07-14 | 2011-07-14 | 2011-10-04 | 2011-10-04 | 2011-10-13 | 2011-10-20 | 2011-11-23 | 2011-11-23 |  | 2011-11-30 | [6 empty] | 2011-11-21 | TRUE |  | 2323232 | 5477729 | 420 Highcliffe Road Dunedin |  | Site located on a VPA area, colo is an excellent option in terms of minimising visual impacts on the site - DCC town planning definitly in favor of no additional masts on the property - 08/04/2011 | CELLSITE | [15 empty] | 2011-12-06 | 2011-12-06
South Island | OTG | 1231 | OTG-071-009 | Dunedin CBD North | OTG-071-009-C | Westpac Building | Dunedin | 4 | TIER_2 | ACTIVE | RT | DU | RT |  | INLINE | STANDALONE | 35 | 38 | 1 | -45.8727 | 170.5045 | 2010-05-27 |  | 2010-04-28 | 2010-04-28 | Microwave | OTG-071-043-G | FALSE | FALSE | 2009-12-17 | 2009-12-17 | FALSE |  | 2011-03-10 | 2011-03-11 | 2011-03-18 | 2011-03-18 | 2011-06-03 | 2011-06-01 | 1 | 2011-06-03 | 2011-06-01 | 2011-07-04 | 2011-07-04 | 2011-10-10 | 2011-10-06 | 1 |  | 2011-10-14 | DISCRETIONARY_FULL | 2011-06-24 | 2011-06-24 | 2011-08-01 | 2011-07-28 | 1 |  | 2011-07-28 |  | 2011-08-15 | 2011-09-20 | 2011-10-21 | 1 |  | 2011-09-27 | 2011-10-21 | 2011-11-01 |  |  | -287862 |  | 2011-10-28 | 2011-10-27 | 2011-11-14 | 2011-11-16 | 2011-11-05 | 2011-11-23 | 2011-11-23 | [8 empty] | 2011-11-27 | 2011-11-30 | 2011-11-30 | 2012-01-21 | 2011-12-20 | 2012-03-19 | 2013-04-08 | 26/03 FAN delayed due to design snags |  | 2011-11-26 | 2011-09-19 | 2011-09-19 | 2011-11-07 | 2011-11-01 | 2011-10-10 | 2011-11-01 | 2011-11-22 | 2011-11-22 |  | 2011-12-07 | [6 empty] | 2011-11-05 | TRUE |  | 2316119 | 5478715 | Westpac Bldg 106 George St Dunedin, 9016 |  | Discretionary as above maximum build height (17m) and also within Heritage Precinct (Discretionary). Planners happy with proposal proving they dishes are kept away from the parapets and do not extend above the height of the existing structure or other RF equipment. Colour coding required. Intelligent designs preferred in terms of visual impacts please. THIS WILL ALSO NEED TO GO BEFORE THE HERITAGE PLANNERS!!!!! at REV0 - 24/03/2011 | CELLSITE |  |  | 2015-04-02 | [12 empty] | 2011-12-07 | 2011-12-08 | 2011-03-18
South Island | OTG | 1232 | OTG-071-010 | Dunedin CBD South (Main HUB) | OTG-071-010-A | John Wickliffe Building | Dunedin | 4 | TIER_2 | ACTIVE | RT | DF | RT |  | STACK_A | COLO | 50 | 50 | 1 | -45.8783 | 170.5015 | 2010-05-27 |  | 2010-04-28 | 2010-04-28 |  |  | FALSE | FALSE | 2009-12-17 | 2009-12-17 | FALSE |  | 2011-03-10 | 2011-03-11 | 2011-03-17 | 2011-03-18 | 2011-06-03 | 2011-06-01 | 2 | 2011-06-09 | 2011-06-10 |  | 2011-06-08 | 2011-08-30 | 2011-08-31 | 2 | 2012-01-17 | 2012-02-13 | DISCRETIONARY_FULL | 2011-06-17 | 2011-06-17 | 2011-07-24 | 2011-07-22 | 2 |  | 2011-07-22 |  | 2011-07-22 | 2011-10-14 | 2011-09-26 | 1 |  | 2011-09-27 | 2011-09-26 | 2011-09-09 |  |  | -287862 |  | 2011-08-27 | 2011-09-08 | 2011-10-15 | 2011-10-18 | 2011-10-18 | 2011-10-27 | 2011-10-28 | [8 empty] | 2011-11-05 | 2011-11-30 | 2011-11-30 | 2011-11-30 | 2011-11-25 | 2013-04-23 | 2013-04-22 | 20/02 agreement in writing to be sought before painting is carried out. 05/03 Hatch to be installed -ongoing. 19/03 Jason B is working on terms of agreement. 03/04 2d agree to be responsible for the guarrantee from the painter and ongoing maintenance but Peter M to arrange initial paint job after clarifying quote. Cost to be forwarded to 2d as a variation. 01/05 Paint worst parts before winter. Fast track agreement then paint remainder with scaffolding and traffic management. | TCL | 2011-11-03 | 2011-07-14 | 2011-07-14 | 2011-10-04 | 2011-10-18 | 2011-09-09 | 2011-09-09 | 2011-10-27 | 2011-10-27 |  | 2011-11-09 | [6 empty] | 2011-10-17 | TRUE |  | 2315902 | 5478092 | 265 Princes St. Dunedin, 9016 |  | Discretionary as above maximum build height (17m) and also within South Octagon Precinct (Discretionary). Planners happy with proposal proving they dishes are kept away from the parapets and do not extend above the height of the existing structure or other RF equipment. Colour coding required. Intelligent designs preferred in terms of visual impacts please. - 24/03/2011 | CELLSITE |  |  | 2015-04-02 | [12 empty] | 2011-11-17 | 2011-11-16 | 2011-03-18
South Island | OTG | 1236 | OTG-071-014 | Port Chalmers | OTG-071-014-B | Telecom Cosite GF | Dunedin | 4 | TIER_2 | ACTIVE | GF | DU | P2 |  | INLINE | COSITE | 16 | 16 | 1 | -45.8125 | 170.6166 | 2010-05-27 |  | 2010-04-28 | 2010-04-28 | Microwave | OTG-071-008-A | FALSE | FALSE | 2009-12-17 | 2009-12-17 | FALSE |  | 2011-04-01 | 2011-04-01 | 2011-04-21 | 2011-04-26 | 2011-05-20 | 2011-05-19 | 2 | 2011-05-20 | 2013-09-23 |  | 2011-06-08 | 2011-07-11 | 2011-07-12 | 1 |  | 2011-07-12 | DISCRETIONARY_FULL | 2011-06-03 | 2011-05-27 | 2011-07-08 | 2011-06-14 | 1 |  | 2011-06-14 |  | 2011-07-22 | 2011-10-14 | 2011-10-06 | 1 |  | 2011-09-19 | 2011-10-06 | 2011-10-23 |  |  | 2011-09-08 |  | 2011-10-03 | 2011-10-04 | 2011-11-11 | 2011-11-09 | 2011-10-23 | 2011-11-22 | 2011-11-23 | [8 empty] | 2011-11-24 | 2011-11-30 | 2011-11-30 | 2011-12-16 | 2011-12-15 | 2012-03-14 | 2012-07-31 | ok |  | 2011-11-24 | 2011-10-07 | 2011-10-07 | 2011-10-04 | 2011-10-04 | 2011-10-17 | 2011-10-23 | 2011-11-14 | 2011-11-16 |  | 2011-11-30 | [6 empty] | 2011-10-22 | TRUE |  | 2324632 | 5485660 | Blueskin Road Port Chalmers |  | Council less supportive of this option than colo with TCNZ. - Maximum Height: (16m) - Setbacks: 20m front/rear boundary, 6m side boundary (applies only to cabinets masts can be at any distance) - Max Dish Diameter: (1.2m) - Maximum Panel Antenna Surface Area: (1.2m2) - Max Cabinet Dimension: (2m high, 10m2) - Maximum mast diameters: (1.5m dia up to 10m, 0.75m dia above 10m) - Radio frequency standards: As normally required - no issues with public or third party access - Existing consent to consider: Existing Vodafone Mast - Applicable additional overlay rules? VPA (Visual Protection Area – all dimensions Discretionary in terms of Visual Appearance/design/location- existing permitted baselines of limited weight) - 08/04/2011 - 22/06/2011 | CELLSITE | [15 empty] | 2011-12-05 | 2011-12-02
South Island | OTG | 1237 | OTG-071-015 | Mt Cargill | OTG-071-015-A | Kordia Colo | Dunedin | 4 | TIER_2 | ACTIVE | COLO | DF | COLO |  | INLINE | COLO | 15 | 70 | 1 | -45.8132 | 170.5552 | 2010-05-27 |  | 2010-04-28 | 2010-04-28 | Microwave | OTG-071-043-G | FALSE | FALSE | 2009-12-17 | 2009-12-17 | FALSE |  | 2011-04-01 | 2011-04-01 | 2011-05-20 | 2011-05-19 | 2011-09-30 | 2011-09-28 | 1 | 2011-09-30 | 2011-09-28 | 2011-07-15 | 2011-07-15 | 2011-10-26 | 2011-09-27 |  |  | 2012-02-10 | OPW | 2011-09-30 | 2011-10-23 | 2011-09-30 | 2011-09-23 | 1 |  | 2011-10-23 |  |  | 2011-10-20 | 2011-12-20 | 1 |  | 2011-10-20 | 2011-12-20 | 2011-10-20 |  |  | -287862 |  | 2011-10-25 | 2011-10-20 | 2011-10-29 | 2011-11-09 | 2011-10-20 | 2011-11-08 | 2011-11-09 | [8 empty] | 2011-11-15 | 2011-11-30 | 2011-11-30 | 2011-12-20 | 2011-12-20 | 2012-03-19 | 2012-07-31 | ok | KDA | 2011-11-15 | 2011-10-20 | 2011-10-20 | 2011-10-04 | 2011-10-20 | 2011-10-20 | 2011-10-20 | 2011-10-29 | 2011-10-26 |  | 2011-11-22 | [6 empty] | 2011-10-28 | TRUE |  | 2319862 | 5485439 | Mt Cargill, Cowan Road Dunedin |  | Kordia in house - 08/04/2011 | CELLSITE | [15 empty] | 2011-12-06 | 2011-12-06
South Island | OTG | 1241 | OTG-071-019 | Balaclava | OTG-071-019-G | Kaikorai Valley Properties West | Dunedin | 4 | TIER_2 | ACTIVE | GF | DU | T2 20 UF | green | INLINE | STANDALONE | 15.5 | 16 | 1 | -45.893 | 170.4475 | 2010-05-27 |  | 2010-04-28 | 2010-04-28 | Microwave | OTG-071-002-E | FALSE | FALSE | 2009-12-17 | 2009-12-17 | FALSE |  | 2011-07-01 | 2011-07-01 | 2011-07-04 | 2011-07-04 | 2011-07-13 | 2011-07-14 | 1 | 2011-07-13 | 2011-07-14 |  | 2011-07-12 | 2011-08-04 | 2011-07-29 | 1 |  | 2011-07-29 | PERMITTED | 2011-07-15 | 2011-07-15 | 2011-08-18 | 2011-08-11 | 1 |  | 2011-08-11 |  |  | 2011-09-05 | 2011-09-07 | 1 |  | 2011-09-05 | 2011-09-07 | 2011-10-21 |  |  | 2011-08-25 |  | 2011-09-15 | 2011-09-15 | 2011-10-27 | 2011-10-22 | 2011-10-18 | 2011-10-27 | 2011-10-27 | [8 empty] | 2011-10-28 | 2011-11-30 | 2011-11-30 | 2011-11-23 | 2011-11-25 | 2012-02-23 | 2012-06-29 | Jason to confirm plant care arrangement. 16/04 Pines to be planted in winter. |  | 2011-10-28 | 2011-08-26 | 2011-08-26 | 2011-10-14 | 2011-10-07 | 2011-10-21 | 2011-10-21 | 2011-10-14 | 2011-10-18 |  | 2011-11-02 | [6 empty] | 2011-10-12 | TRUE |  | 2311764 | 5476329 | 19 Boundary Rd, Balaclava, Dunedin |  | Permitted activity, recommending that mast be painted green to blend in with proposed Douglas Fir plantings once 4 years old - mitigate interferance of neighbouring house view of non built environmnetal structures - 12/07/2011 | CELLSITE | [15 empty] | 2011-11-15 | 2011-11-14
South Island | OTG | 1243 | OTG-071-021 | Brockville | OTG-071-021-C | VF Colo | Dunedin | 4 | TIER_2 | ACTIVE | COLO | DU | NOPOLE |  | INLINE | COLO | 12 | 12 | 1 | -45.8763 | 170.4599 | 2010-05-27 |  | 2010-04-28 | 2010-04-28 | Microwave | OTG-071-002-E | FALSE | FALSE | 2009-12-17 | 2009-12-17 | FALSE |  | 2011-04-01 | 2011-03-11 | 2011-04-08 | 2011-03-17 | 2011-04-21 | 2011-04-20 | 2 | 2011-05-17 | 2011-05-16 |  | 2011-07-14 | 2011-08-31 | 2011-08-30 | 2 |  | 2011-09-08 | PERMITTED | 2011-04-21 | 2011-04-27 | 2011-06-02 | 2011-05-20 | 1 |  | 2011-05-20 |  | 2011-07-22 | 2011-09-27 | 2011-09-19 | 1 |  | 2011-09-27 | 2011-09-19 | 2011-10-29 |  |  | 2011-09-23 |  | 2011-10-14 | 2011-10-16 | 2011-11-07 | 2011-11-10 | 2011-11-12 | 2011-11-18 | 2011-11-17 | [8 empty] | 2011-11-21 | 2011-11-30 | 2011-11-30 | 2011-11-23 | 2011-12-15 | 2012-03-14 | 2012-07-13 | VF closure notice received. | VNZ | 2011-11-21 | 2011-07-14 | 2011-07-14 | 2011-10-04 | 2011-10-25 | 2011-10-29 | 2011-10-29 | 2011-11-17 | 2011-11-17 |  | 2011-11-22 | [6 empty] | 2011-11-12 | TRUE |  | 2312669 | 5478217 | Off Marshall Street, Brockville/Bradford Dunedin |  |  | CELLSITE | [15 empty] | 2011-12-02 | 2011-12-02
South Island | OTG | 1244 | OTG-071-022 | Halfway Bush | OTG-071-022-A | Halfway Bush (Tx Hub) | Dunedin | 4 | TIER_2 | ACTIVE | GF | DU | P2 |  | INLINE | STANDALONE | 12 | 16 | 1 | -45.866 | 170.4306 | 2010-05-27 |  | 2010-04-28 | 2010-04-28 | Fibre Optic | OTG-071-010-A | FALSE | FALSE | 2009-12-17 | 2009-12-17 | FALSE |  | 2011-04-10 | 2011-03-11 | 2011-04-17 | 2011-03-17 | 2011-05-06 | 2011-05-06 | 2 | 2011-05-06 | 2011-07-07 |  | 2011-06-01 | 2011-06-27 | 2011-06-24 | 1 |  | 2011-07-05 | DISCRETIONARY_FULL | 2011-07-01 | 2011-06-30 | 2011-08-01 | 2011-08-02 | 2 |  | 2011-08-02 |  |  | 2011-09-05 | 2011-09-19 | 1 |  | 2011-09-05 | 2011-09-19 | 2011-09-30 |  |  | 2011-08-19 |  | 2011-09-07 | 2011-09-08 | 2011-10-28 | 2011-10-30 | 2011-10-12 | 2011-10-19 | 2011-10-17 | [8 empty] | 2011-10-20 | 2011-11-30 | 2011-11-30 | 2011-11-23 | 2011-11-25 | 2013-05-15 | 2013-05-14 | 26/03 earthing pit work to be completed to LL satisfaction. |  | 2011-10-21 | 2011-08-26 | 2011-08-26 | 2011-10-04 | 2011-10-07 | 2011-09-30 | 2011-09-30 | 2011-10-12 | 2011-10-14 |  | 2011-10-27 | [5 empty] | BUILD | 2011-10-11 | TRUE |  | 2310358 | 5479287 | Halfway Bush Rd West Dunedin |  | Discretionary due to VPA location, planners appear happy with 12m mast with smallest possible dishes, landowner on the Western side of the road is not deemed affected, however Houses in distance to the east are potentially. 12m colour coded mast with 2x600mm dishes would be a good visual solution if possible. - 24/03/2011 | CELLSITE | [15 empty] | 2011-11-15 | 2011-11-14
South Island | OTG | 1245 | OTG-071-023 | Corstorphine | OTG-071-023-A | Clemiston Ave & Corstorphine St Junction LPR | Dunedin | 4 | TIER_2 | ACTIVE | RSR | DU | P4F | green | INLINE | STANDALONE | 12.09 | 12.59 | 1 | -45.9083 | 170.4697 | 2010-05-27 |  | 2010-04-28 | 2010-04-28 | Microwave | OTG-071-021-C | FALSE | FALSE | 2009-12-17 | 2009-12-17 | FALSE |  | 2011-03-10 | 2011-03-10 | 2011-03-17 | 2011-03-17 | 2011-04-21 | 2011-04-20 | 4 | 2011-05-18 | 2011-05-25 |  | 2011-06-01 | 2011-11-08 | 2011-10-31 | 3 |  | 2012-03-20 | NES | 2011-08-29 | 2011-05-02 | 2011-06-06 | 2011-05-25 | 3 |  | 2011-05-25 |  | 2011-08-15 | 2011-10-10 | 2011-10-07 | 1 |  | 2011-09-27 | 2011-10-07 | 2011-09-30 |  |  | 2011-09-16 |  | 2011-10-14 | 2011-10-17 | 2011-11-02 | 2011-11-01 | 2011-10-31 | 2011-11-17 | 2011-11-17 | [8 empty] | 2011-11-18 | 2011-11-30 | 2011-11-30 | 2011-12-21 | 2011-12-20 | 2012-03-19 | 2012-06-29 | ok. DCC have inspected. Site is showing an alarm to be sorted. |  | 2011-11-18 | 2011-08-29 | 2011-08-29 | 2011-11-05 | 2011-11-01 | 2011-10-07 | 2011-09-30 | 2011-11-17 | 2011-11-17 |  | 2011-11-21 | [6 empty] | 2011-10-31 | TRUE |  | 2313540 | 5474680 | Junction of Clermiston and Corstorphine St Dunedin |  | NES compliant appliocation providing highest point of proposal is no more the the lesser of 30% or 3m higher than the existing structure, the new mast is no more than 50% more than the existing mast's diameter, NES compliant Cabinet design is installed, NES Katherine 1.9m antennas are used along with NES compliant 300mm microwaves and microwaves do not stick out more then 600mm from the centre of the mast respectively. Looks like a good option as cabinets are mkore than 4m away from a habitable residential unit. - 24/03/2011 | CELLSITE | [15 empty] | 2011-12-07 | 2011-12-06
South Island | OTG | 1251 | OTG-071-029 | Airport Terminal | OTG-071-029-B | Carpark Monopole GF | Dunedin | 4 | TIER_2 | ACTIVE | GF | DU | T2 20 UF | blackbean green | INLINE | COSITE |  | 15.3 | 1 | -45.9226 | 170.1999 |  |  |  |  | Microwave, Microwave | OTG-071-001-C, OTG-071-022-A | FALSE | FALSE |  |  | FALSE |  | 2011-04-01 | 2011-04-01 | 2011-04-19 | 2011-04-20 | 2011-05-30 | 2011-05-27 | 1 | 2011-05-30 | 2011-05-27 |  | 2011-07-15 | 2011-09-12 | 2011-09-20 | 1 |  | 2011-09-20 | PERMITTED | 2011-06-03 | 2011-06-03 | 2011-07-08 | 2011-06-17 | 1 |  | 2011-06-17 |  | 2011-07-22 | 2011-10-03 | 2011-09-22 | 1 |  | 2011-09-27 | 2011-09-22 | 2011-11-17 |  |  | -287862 |  | 2011-10-07 | 2011-10-04 | 2011-11-20 | 2011-11-20 | 2011-11-03 | 2011-11-19 | 2011-11-19 | [8 empty] | 2011-11-22 | 2011-11-30 | 2011-11-30 | 2011-11-23 | 2011-12-19 | 2012-03-19 | 2012-07-31 | ok |  | 2011-11-28 | 2011-07-12 | 2011-07-12 | 2011-10-04 | 2011-10-04 | 2011-11-17 | 2011-11-17 | 2011-11-14 | 2011-11-14 |  | 2011-11-30 | [6 empty] | 2011-10-25 | TRUE |  | 2292668 | 5472423 | Dunedin International Airport |  | Good option from a planning perspective - design need to consider landowner preferences - CAA likely affected party - 08/04/2011 | CELLSITE | [15 empty] | 2011-12-06 | 2011-12-02 | 2011-04-20
South Island | OTG | 1265 | OTG-071-043 | Dunedin Stadium (TX HUB) | OTG-071-043-G | Kiwirail (HUB) | Dunedin | 4 | TIER_2 | ACTIVE | GF | DU | T2 25 UF Plus | grey | INLINE | STANDALONE | 24.45 | 25 | 1 | -45.8711 | 170.5168 |  |  |  |  | Microwave | OTG-071-010-A | FALSE | FALSE |  |  | FALSE |  | 2011-07-21 | 2011-07-21 | 2011-07-26 | 2011-07-26 | 2011-08-02 | 2011-08-03 | 2 | 2011-08-02 | 2014-11-17 | 2011-10-10 | 2011-10-07 | 2011-10-10 | 2011-10-07 |  |  | 2011-10-18 | PERMITTED | 2011-08-10 | 2011-08-10 | 2011-10-17 | 2011-10-13 | 1 |  | 2011-10-13 |  |  | 2011-10-19 | 2011-10-18 | 1 |  | 2011-10-19 | 2011-10-18 | 2011-11-09 |  |  | 2011-10-14 |  | 2011-10-28 | 2011-10-27 | 2011-12-14 | 2012-01-23 | 2011-12-09 | 2011-12-12 | 2011-12-14 | [8 empty] | 2011-12-14 | 2011-12-14 | 2011-12-14 | 2012-01-21 | 2012-02-23 | 2013-05-28 | 2013-05-24 | ok |  | 2011-12-12 | 2011-09-15 | 2011-09-15 | 2011-11-05 | 2011-11-17 | 2011-11-06 | 2011-11-09 | 2011-12-12 | 2011-12-13 |  | 2012-02-10 | [5 empty] | BUILD | 2011-11-10 | TRUE |  | 2317066 | 5478919 | Kiwirail, Behind 3 Wickliffe Street, Dunedin |  | CoC s.176 required from Transit not yet supplied will need before approval - 11/08/2011 - 11/08/2011 | CELLSITE |  |  | 2015-04-02 | [12 empty] | 2012-01-27 | 2012-02-10
South Island | OTG | 1235 | OTG-071-013 | University | OTG-071-013-H | Gowland Street | Dunedin | 4 | TIER_2 | ACTIVE | RSR | DU | P4F |  | INLINE | STANDALONE |  | 13.4 | 1 | -45.8672 | 170.5107 | 2010-05-27 |  | 2010-04-28 | 2010-04-28 | Microwave | OTG-071-043-G | FALSE | FALSE | 2009-12-17 | 2009-12-17 | FALSE |  | 2011-06-10 | 2011-06-10 | 2011-06-16 | 2011-06-16 | 2011-07-29 | 2011-08-01 | 4 | 2011-07-29 | 2015-02-17 |  | 2011-08-10 | 2011-08-31 | 2011-08-26 | 1 |  | 2011-08-26 | NES | 2011-08-15 | 2011-08-12 | 2011-09-23 | 2011-09-21 | 1 |  | 2011-09-21 |  |  | 2011-10-19 | 2011-11-11 | 1 |  | 2011-10-19 | 2011-11-11 | 2011-11-01 |  |  | 2011-11-17 |  | 2011-12-01 | 2011-12-02 | 2011-12-20 | 2012-01-20 | 2011-12-18 | 2011-12-20 | 2012-01-09 | [8 empty] | 2012-01-11 | 2011-12-15 | 2012-01-17 | 2012-01-27 | 2012-02-08 | 2012-05-08 | 2012-07-31 | ok |  | 2011-12-20 | 2011-09-19 | 2011-09-19 | 2011-11-29 | 2011-11-17 | 2011-11-01 | 2011-11-01 | 2011-12-20 | 2012-01-09 |  | 2012-01-24 | [6 empty] | 2011-12-17 | TRUE |  | 2316584 | 5479338 | cnr Gowland and Albany St |  |  | CELLSITE |  |  | 2015-04-02 | [12 empty] | 2012-01-24 | 2012-01-24
South Island | OTG | 1239 | OTG-071-017 | Leith Valley | OTG-071-017-A | Vodafone Colo Cowan Road | Dunedin | 4 | TIER_2 | ACTIVE | COLO | DU | NOPOLE | grey | INLINE | COLO | 18.1 | 18.6 | 1 | -45.8264 | 170.5214 | 2010-05-27 |  | 2010-04-28 | 2010-04-28 | Microwave | OTG-071-026-B | FALSE | FALSE | 2009-12-17 | 2009-12-17 | FALSE |  | 2011-03-09 | 2011-03-10 | 2011-04-13 | 2011-04-13 | 2011-05-06 | 2011-05-04 | 1 | 2011-05-06 | 2011-05-04 |  | 2011-07-13 | 2011-08-12 | 2011-08-11 | 1 |  | 2011-09-08 | DISCRETIONARY_FULL | 2011-06-13 | 2011-05-06 | 2011-06-24 | 2011-06-14 | 1 |  | 2011-06-14 |  |  | 2011-09-12 | 2011-09-14 | 2 |  | 2011-09-12 | 2011-11-07 | 2011-10-25 |  |  | 2011-08-25 |  | 2011-11-15 | 2011-11-15 | 2011-12-02 | 2011-12-05 | 2011-11-28 | 2011-12-17 | 2011-12-10 | [8 empty] | 2011-12-15 | 2011-12-15 | 2011-12-15 | 2012-01-04 | 2012-01-20 | 2012-04-19 | 2012-07-31 | ok | VNZ | 2011-12-17 | 2011-08-17 | 2011-08-17 | 2011-10-04 | 2011-10-04 | 2011-10-20 | 2011-10-25 | 2011-12-06 | 2011-12-09 |  | 2012-01-09 | [6 empty] | 2011-11-28 | TRUE |  | 2317278 | 5483898 | Off Cowan Rd, Leith Valley Dunedin |  | Double stack head frame colo on existing Vodafone 15m monopole, breaches maximum height for Zone of 16m (approx. height of ptroposal 17-18m). VPA overlay (Discretionary), colour coding with existing mast to match VF required. - 24/03/2011 | CELLSITE | [15 empty] | 2012-01-13 | 2012-01-09
South Island | OTG | 1242 | OTG-071-020 | Kaikorai | OTG-071-020-E | Highgate Stuart Rd junction | Dunedin | 4 | TIER_2 | ACTIVE | RSR | DU | P4F |  | INLINE | STANDALONE | 12 | 12 |  | -45.8668 | 170.4906 | 2010-05-27 |  | 2010-04-28 | 2010-04-28 | Microwave | OTG-071-043-G | FALSE | FALSE | 2009-12-17 | 2009-12-17 | FALSE |  | 2011-07-21 | 2011-07-21 | 2011-07-25 | 2011-07-25 | 2011-08-11 | 2011-08-15 | 1 | 2011-08-11 | 2011-08-15 |  | 2011-08-02 | 2011-09-12 | 2011-09-12 | 1 |  | 2011-09-16 | PERMITTED | 2011-08-18 | 2011-08-18 | 2011-09-22 | 2011-09-08 | 1 |  | 2011-09-08 |  |  | 2011-09-27 | 2011-09-30 | 1 |  | 2011-09-27 | 2011-09-30 | 2011-09-29 |  |  | 2011-09-23 |  | 2011-11-28 | 2011-11-30 | 2011-12-05 | 2011-12-10 | 2011-12-05 | 2011-12-05 | 2011-12-10 | [8 empty] | 2011-12-14 | 2011-12-15 | 2011-12-14 | 2011-12-24 | 2012-03-21 | 2012-06-19 | 2012-07-31 | ok |  | 2011-12-15 | 2011-09-14 | 2011-09-14 | 2011-09-18 | 2011-11-09 | 2011-09-29 | 2011-09-29 | 2011-12-05 | 2011-12-10 |  | 2012-03-21 | [6 empty] | 2011-12-02 | TRUE |  | 2315021 | 5479343 | Roadside reserve Junction of Highgate and Stuart St North East of Highgate roundabout |  |  | CELLSITE | [15 empty] | 2012-03-22 | 2012-03-08 | 2011-07-25
South Island | OTG | 1247 | OTG-071-025 | Mornington | OTG-071-025-B | Mailer Street LPR | Dunedin | 4 | TIER_2 | ACTIVE | RSR | DU | P4J |  | INLINE | STANDALONE | 11 | 13.4 | 1 | -45.8813 | 170.48 | 2010-05-27 |  | 2010-04-28 | 2010-04-28 | Microwave | OTG-071-043-G | FALSE | FALSE | 2009-12-17 | 2009-12-17 | FALSE |  | 2011-04-15 | 2011-04-15 | 2011-04-26 | 2011-04-27 | 2011-05-25 | 2011-05-25 | 1 | 2011-05-25 | 2011-05-25 |  | 2011-06-01 | 2011-11-10 | 2011-10-31 | 1 |  | 2012-03-20 | NES | 2011-05-27 | 2011-05-26 | 2011-07-01 | 2011-06-16 | 1 |  | 2011-06-16 |  | 2011-08-15 | 2011-10-03 | 2011-09-30 | 1 |  | 2011-09-27 | 2011-09-30 | 2011-09-30 |  |  | 2011-10-04 |  | 2011-11-03 | 2011-11-03 | 2011-11-30 | 2011-12-02 | 2011-11-28 | 2011-12-15 | 2011-12-10 | [8 empty] | 2011-12-14 | 2011-12-15 | 2011-12-14 | 2012-01-21 | 2012-01-20 | 2012-04-19 | 2012-07-31 | ok. |  | 2011-12-17 | 2011-08-31 | 2011-08-31 | 2011-11-15 | 2011-11-15 | 2011-10-07 | 2011-09-30 | 2011-12-02 | 2011-12-05 |  | 2012-01-09 | [6 empty] | 2011-11-28 | TRUE |  | 2314243 | 5477702 | Mailer St Dunedin |  |  | CELLSITE | [15 empty] | 2011-12-23 | 2012-01-09 | 2011-04-27
South Island | OTG | 1248 | OTG-071-026 | Helensburgh | OTG-071-026-B | Transpower Cosite | Dunedin | 4 | TIER_2 | ACTIVE | GF | DU | P1 | grey | INLINE | COSITE |  | 12 | 1 | -45.8556 | 170.4757 | 2010-05-27 |  | 2010-04-28 | 2010-04-28 | Microwave | OTG-071-020-E | FALSE | FALSE | 2009-12-17 | 2009-12-17 | FALSE |  | 2011-06-02 | 2011-06-02 | 2011-06-09 | 2011-06-09 | 2011-06-28 | 2011-06-28 | 1 | 2011-06-28 | 2011-06-28 |  | 2011-07-27 | 2011-09-12 | 2011-09-13 | 1 |  | 2011-09-13 | PERMITTED | 2011-08-23 | 2011-08-10 | 2011-09-17 | 2011-09-08 | 1 |  | 2011-09-08 |  | 2011-08-15 | 2011-10-10 | 2011-10-11 | 1 |  | 2011-09-27 | 2011-10-11 | 2011-11-08 |  |  | 2011-10-07 |  | 2011-11-04 | 2011-11-04 | 2011-11-20 | 2011-11-19 | 2011-11-19 | 2011-12-14 | 2011-12-10 | [8 empty] | 2011-12-15 | 2011-12-15 | 2011-12-15 | 2012-01-21 | 2012-01-20 | 2012-04-19 | 2012-06-29 | ok |  | 2011-12-15 | 2011-09-16 | 2011-09-16 | 2011-11-05 | 2011-11-05 | 2011-11-07 | 2011-11-08 | 2011-11-25 | 2011-12-05 |  | 2012-01-09 | [6 empty] | 2011-11-19 | TRUE |  | 2313829 | 5480551 | 48 Wakari Rd Helensburgh Dunedin |  |  | CELLSITE | [15 empty] | 2011-12-23 | 2012-01-09
South Island | MBN | 989 | MBN-051-008 | Mapua | MBN-051-008-A | TNZ Colo | Tasman District | 7 | TIER_2 | ACTIVE | COLO | DU | COLO |  | STACK_A | COLO | 19 | 25 | 2 | -41.2477 | 173.0905 |  | 2010-10-02 | 2010-06-09 |  | Leased Line | MBN-052-003-B | FALSE | FALSE | 2010-06-15 | 2010-06-15 | FALSE |  | 2011-03-11 | 2011-09-07 | 2011-03-18 | 2011-09-09 |  | 2011-09-05 | 2 | 2011-09-30 | 2011-09-30 | 2011-10-03 | 2011-09-26 | 2011-11-25 | 2011-10-28 |  | 2012-02-23 |  | PERMITTED | 2011-10-21 | 2011-10-13 | 2011-11-25 | 2011-10-17 | 1 |  | 2011-10-17 |  |  | 2011-11-15 | 2011-11-18 | 1 |  | 2011-11-11 | 2011-11-18 | 2011-12-20 |  |  |  |  | 2011-12-07 | 2011-12-07 | 2012-02-03 | 2012-02-02 | 2011-12-12 | 2011-12-21 | 2011-12-23 | [8 empty] | 2011-12-23 | 2011-12-21 | 2011-12-23 | 2012-03-15 | 2012-03-15 | 2013-06-17 | 2013-06-11 |  | TNZ | 2011-12-21 | 2011-12-12 | 2011-12-12 | 2011-12-12 | 2011-12-12 | 2011-12-17 | 2011-12-20 | 2011-12-16 | 2012-01-13 | 2012-01-31 | 2012-01-09 | [5 empty] | BUILD | 2011-11-27 | FALSE |  | 2517571 | 5995445 | 149 Aranui Rd Mapua |  | Jack Andrew TDC processing planner - 15/12/2011 | CELLSITE | [15 empty] | 2012-02-20 | 2012-03-02
South Island | STH | 1313 | STH-075-009 | Waihopai | STH-075-009-A | VF Colo Waihopai | Invercargill City | 5 | TIER_2 | ACTIVE | COLO | DU | NOPOLE | grey | INLINE | COLO | 21.2 | 24 |  | -46.3944 | 168.3889 | 2010-05-27 | 2010-05-27 | 2010-06-04 | 2010-06-04 | Microwave | STH-075-001-B | FALSE | FALSE | 2010-03-05 | 2010-03-05 | FALSE | 2011-03-01 | 2011-03-18 | 2011-03-18 | 2011-03-25 | 2011-03-21 | 2011-04-29 | 2011-04-29 | 1 | 2011-04-29 | 2011-04-29 | 2011-06-17 | 2011-06-15 | 2011-11-08 | 2011-11-01 | 1 |  | 2011-12-21 | DISCRETIONARY_FULL | 2011-06-14 | 2011-06-20 | 2011-07-19 | 2011-07-06 | 1 |  | 2011-07-06 |  | 2011-07-22 | 2011-09-08 | 2011-09-13 | 2 |  | 2011-09-08 | 2011-11-08 | 2011-11-01 |  |  |  |  | 2011-11-28 | 2011-11-28 | 2011-12-16 | 2011-12-15 | 2011-12-08 | 2011-12-09 | 2011-12-09 |  |  |  | 2011-07-07 |  |  |  |  | 2011-12-09 | 2011-12-22 | 2011-12-20 | 2012-01-19 | 2012-01-19 | 2013-05-20 | 2013-05-17 | 01/05 Council have refused consent uintil at least June. Jaco and Stuart to check costs for colo & if relocated link is required. | VNZ | 2011-12-09 | 2011-08-09 | 2011-08-09 | 2011-10-04 | 2011-11-01 | 2011-10-12 | 2011-11-01 | 2011-12-08 | 2011-12-08 |  | 2011-12-15 | [5 empty] | BUILD | 2011-12-06 | FALSE |  | 2155274 | 5413774 | Racecourse Rd Invercargill |  | Versatile Soils - 08/04/2011 | CELLSITE | [15 empty] | 2011-12-22 | 2012-01-09
South Island | OTG | 1233 | OTG-071-011 | Carisbrook | OTG-071-011-E | Kiwi Rail GF | Dunedin | 4 | TIER_2 | ACTIVE | GF | DU | T2 25 UF Plus |  | INLINE | STANDALONE | 20 | 25 | 1 | -45.8955 | 170.4925 | 2010-05-27 |  | 2010-04-28 | 2010-04-28 | Microwave | OTG-071-007-A | FALSE | FALSE | 2009-12-17 | 2009-12-17 | FALSE |  | 2011-04-15 | 2011-04-01 | 2011-04-26 | 2011-04-26 | 2011-05-17 | 2011-05-18 | 2 | 2011-10-07 | 2014-11-17 |  | 2011-05-25 | 2011-06-28 | 2011-06-24 | 1 |  | 2011-07-01 | PERMITTED | 2011-05-27 | 2011-05-23 | 2011-06-17 | 2011-06-21 | 1 |  | 2011-06-21 |  | 2011-07-22 | 2011-09-12 | 2011-09-30 | 1 |  | 2011-09-12 | 2011-09-30 | 2011-12-12 |  |  | 2011-08-26 |  | 2011-10-10 | 2011-10-18 | 2011-12-16 | 2011-12-19 | 2011-11-10 | 2011-12-08 | 2011-12-19 | [8 empty] | 2011-12-19 | 2012-01-12 | 2011-12-21 | 2011-11-23 | 2012-01-31 | 2012-04-30 | 2013-04-08 | MW reconfig once St Kilda comes online. |  | 2012-01-16 | 2011-07-12 | 2011-07-12 | 2011-10-04 | 2011-10-21 | 2011-12-12 | 2011-12-12 | 2011-11-15 | 2011-11-14 |  | 2012-01-23 | [6 empty] | 2011-11-04 | TRUE |  | 2315261 | 5476152 | Kiwi Rail Hillside Road Dunedin |  | Good option as in Industrial 1 area - would be good to keep mast below 25m, ensure cabinet locations comply with noise to boundary requirements - 08/04/2011 | CELLSITE |  |  | 2015-04-02 | [12 empty] | 2012-01-26 | 2012-01-23
South Island | OTG | 1264 | OTG-071-042 | North East Valley | OTG-071-042-F | Great King Street | Dunedin | 4 | TIER_2 | ACTIVE | RSR | DU | P4J | blackbean green | INLINE | STANDALONE | 13 | 13.8 | 1 | -45.8563 | 170.5152 | 2010-05-27 |  | 2010-04-28 | 2010-04-28 | Microwave | OTG-071-009-C | FALSE | FALSE | 2009-12-17 | 2009-12-17 | FALSE |  | 2011-05-13 | 2011-05-13 | 2011-05-18 | 2011-05-17 | 2011-06-10 | 2011-06-10 | 4 | 2011-06-10 | 2014-11-18 |  | 2011-08-10 | 2011-09-07 | 2011-09-07 | 3 |  | 2011-09-07 | PERMITTED | 2011-08-10 | 2011-08-12 | 2011-09-23 | 2011-09-21 | 3 |  | 2011-09-21 |  |  | 2011-11-18 | 2011-11-24 | 1 |  | 2011-11-18 | 2011-11-24 | 2011-11-16 |  |  | 2011-10-20 |  | 2011-12-09 | 2011-12-12 | 2011-12-18 | 2012-01-17 | 2011-12-18 | 2011-12-21 | 2012-01-09 | [8 empty] | 2012-01-09 | 2012-01-27 | 2012-01-17 | 2012-01-27 | 2012-02-08 | 2013-09-06 | 2013-09-03 | ok |  | 2011-12-21 | 2011-09-14 | 2011-09-14 | 2011-12-05 | 2011-11-08 | 2011-11-29 | 2011-11-16 | 2011-12-20 | 2012-01-04 |  | 2012-01-24 | [5 empty] | BUILD | 2011-12-19 | TRUE |  | 2316893 | 5480559 | Great King Street, North Valley East, Dunedin |  |  | CELLSITE | [15 empty] | 2012-01-24 | 2012-01-24 | 2011-05-17
South Island | CAN | 678 | CAN-063-004 | Ashburton | CAN-063-004-A | VNZ Colo Ashburton Electricty (HUB) | Ashburton District | 5 | TIER_2 | ACTIVE | COLO | DU | LATTICE |  | INLINE | COLO |  | 35 |  | -43.9058 | 171.7407 | [6 empty] | FALSE | FALSE |  |  | FALSE |  |  | 2011-05-19 | 2011-07-08 | 2011-07-08 | 2011-07-29 | 2011-08-02 | 2 | 2011-08-31 | 2011-09-08 | 2011-09-12 | 2011-09-12 | 2011-11-14 | 2011-11-16 | 2 | 2011-11-29 | 2011-12-08 | DISCRETIONARY_FULL | 2011-09-09 | 2011-09-08 | 2011-10-14 | 2011-09-28 | 2 |  | 2011-09-30 |  |  | 2011-11-25 | 2011-12-05 | 1 |  | 2011-11-25 | 2011-12-05 | 2012-01-09 |  |  |  |  | 2012-01-09 | 2011-12-19 | 2012-01-20 | 2012-01-23 | 2011-12-18 | 2012-01-20 | 2012-01-27 | [8 empty] | 2012-01-23 | 2012-01-31 | 2012-01-31 | 2012-03-02 | 2012-03-01 | 2012-05-30 | 2012-10-11 | Snag clearing to be done. | VNZ | 2012-01-20 | 2011-09-14 | 2011-09-14 | 2011-12-09 | 2011-12-14 | 2011-12-22 | 2012-01-09 | 2012-01-11 | 2012-01-09 |  | 2012-02-16 | [6 empty] | 2012-01-10 | FALSE |  | 2408850 | 5699431 | Dobson Street West Ashburton |  |  | CELLSITE |  |  | 2015-03-19 | [12 empty] | 2012-02-15 | 2012-02-16 | 2011-07-08
South Island | CAN | 681 | CAN-063-007 | Ashburton North | CAN-063-007-E | Kingan Commercials | Ashburton District | 5 | TIER_2 | ACTIVE | GF | DU | SP |  | INLINE | STANDALONE | 35 | 35 |  | -43.8893 | 171.7745 |  |  |  |  | Fibre Optic | CAN-063-004-A | FALSE | FALSE |  |  | FALSE |  | 2011-06-08 | 2011-06-08 | 2011-06-28 | 2011-06-28 | 2011-07-13 | 2011-07-13 | 1 | 2011-07-13 | 2011-07-13 |  | 2011-07-14 | 2011-08-10 | 2011-08-16 | 1 |  | 2011-08-30 | DISCRETIONARY_FULL | 2011-07-15 | 2011-07-15 | 2011-08-18 | 2011-08-12 | 1 |  | 2011-08-12 |  |  | 2011-12-09 | 2011-11-18 | 2 |  | 2011-12-09 | 2011-11-23 | 2011-12-12 |  |  | 2011-12-16 |  | 2011-11-29 | 2011-11-29 | 2012-01-31 | 2012-02-01 | 2011-12-13 | 2012-01-14 | 2012-01-20 | [8 empty] | 2012-01-26 | 2012-01-31 | 2012-01-31 | 2012-02-20 | 2012-02-29 | 2012-05-29 | 2013-04-08 | SPM to send ABs to SA re Earthing route. 16/04 Waiting for updated ABs with correct earthing + extensions. 16/04 SA to chase NRL for LL. 01/05 Need drawings showing earthing. |  | 2012-01-23 | 2011-09-14 | 2011-09-14 | 2011-12-12 | 2011-12-07 | 2011-12-12 | 2011-12-12 | 2011-12-15 | 2011-12-13 |  | 2012-02-16 | [6 empty] | 2011-12-15 | TRUE |  | 2411539 | 5701301 | 76 Bremners Rd |  |  | CELLSITE |  |  | 2015-03-18 | [12 empty] | 2012-02-15 | 2012-02-16
South Island | STH | 1309 | STH-075-005 | Heidelberg | STH-075-005-H | Pomona St RSR | Invercargill City | 5 | TIER_2 | ACTIVE | RSR | DU | P4F |  | INLINE | STANDALONE |  | 13 |  | -46.4227 | 168.3694 | 2010-05-27 | 2010-05-27 | 2010-06-04 | 2010-06-04 | Microwave | STH-075-008-B | FALSE | FALSE | 2010-03-05 | 2010-03-05 | FALSE | 2011-07-27 | 2011-07-28 | 2011-07-28 | 2011-08-18 | 2011-08-18 | 2011-08-26 | 2011-08-26 | 3 | 2011-08-26 | 2011-12-15 |  | 2011-08-29 | 2011-11-29 | 2011-12-09 |  | 2011-11-29 | 2011-12-09 | CONTROLLED | 2011-08-31 | 2011-09-01 | 2011-10-05 | 2011-09-30 | 2 | 2011-10-05 | 2011-10-05 |  |  | 2011-11-02 | 2011-11-14 | 1 |  | 2011-11-17 | 2011-11-14 | 2011-11-16 |  |  | 2011-11-17 |  | 2011-12-07 | 2011-12-07 | 2012-01-20 | 2012-01-19 | 2012-01-11 | 2012-01-20 | 2012-01-19 |  |  |  | 2011-08-26 |  |  |  |  | 2012-01-21 | 2012-01-31 | 2012-01-25 | 2012-02-14 | 2012-02-27 | 2013-04-30 | 2013-04-22 | snag clearance |  | 2012-01-20 | 2011-10-03 | 2011-10-03 | 2011-11-24 | 2011-11-24 | 2011-11-15 | 2011-11-16 | 2011-12-16 | 2012-01-16 |  | 2012-02-13 | [6 empty] | 2012-01-13 | TRUE |  | 2153956 | 5410554 | Pomona Street (Opposite Centre St) Invercargill |  |  | CELLSITE | [15 empty] | 2012-02-10 | 2012-02-13 | 2011-08-18
South Island | CAN | 675 | CAN-063-001 | Mt Hutt | CAN-063-001-A | Mt Hutt - VF Cosite | Ashburton District | 5 | TIER_2 | ACTIVE | GF | DU | T2 20 RH | grey | INLINE | COSITE | 18 | 20 |  | -43.5944 | 171.4913 |  |  |  |  | Microwave | CAN-063-004-A | FALSE | FALSE |  |  | FALSE |  | 2011-04-08 | 2011-04-08 | 2011-04-15 | 2011-04-12 | 2011-05-16 | 2011-05-16 | 2 | 2011-05-16 | 2013-02-21 | 2011-06-07 | 2011-05-17 | 2011-08-12 | 2011-08-16 | 1 |  | 2011-08-16 | PERMITTED | 2011-05-31 | 2011-05-27 | 2011-07-05 | 2011-06-21 | 1 |  | 2011-06-21 |  |  | 2011-12-19 | 2011-12-21 | 1 |  | 2011-12-19 | 2011-12-21 | 2011-12-20 |  |  |  |  | 2012-01-10 | 2012-01-10 | 2012-02-10 | 2012-02-13 | 2012-01-26 | 2012-02-11 | 2012-02-13 | [8 empty] | 2012-02-14 | 2012-02-28 | 2012-02-27 | 2012-02-29 | 2012-03-30 | 2013-06-12 | 2013-06-17 | 19/03 Earthing mat to be done. Site to be tidied. 03/04 ABs for LL asap. 16/04 Lease area update - SPM. Metal cover plates required - send photos. 01/05 Earthing extensions required with drawings. |  | 2012-02-14 | 2011-09-14 | 2011-09-14 | 2011-12-09 | 2011-12-14 | 2011-12-21 | 2011-12-20 | 2012-01-27 | 2012-02-01 |  | 2012-03-16 | [5 empty] | BUILD | 2012-01-26 | FALSE |  | 2388191 | 5733688 | Mt Alford, Mid Canterbury |  | Controlled Activity – if located within the Rural C zone or Permitted if located within the Rural B zone - All Zoning to be confirmed - 08/04/2011 | CELLSITE | [15 empty] | 2012-03-14 | 2012-03-16
South Island | CAN | 679 | CAN-063-005 | Hinds | CAN-063-005-A | VNZ Colo | Ashburton District | 5 | TIER_2 | ACTIVE | COLO | DU | COLO | grey | INLINE | COLO | 28.4 | 40 |  | -44.0064 | 171.5719 |  |  |  |  | Microwave | CAN-063-004-A | FALSE | FALSE |  |  | FALSE |  | 2011-02-18 | 2011-02-18 | 2011-02-25 | 2011-03-11 | 2011-04-27 | 2011-04-21 | 1 | 2011-06-17 | 2011-04-21 | 2011-06-15 | 2011-06-20 | 2011-08-12 | 2011-08-05 | 1 |  | 2011-09-01 | DISCRETIONARY_FULL | 2011-05-11 | 2011-05-09 | 2011-06-16 | 2011-06-03 | 1 |  | 2011-06-29 |  |  | 2011-11-25 | 2011-12-13 | 1 |  | 2011-11-25 | 2011-12-13 | 2012-01-11 |  |  |  |  | 2012-01-11 | 2012-01-10 | 2012-01-30 | 2012-01-30 | 2012-01-10 | 2012-02-10 | 2012-02-10 | [8 empty] | 2012-02-10 | 2012-02-28 | 2012-02-14 | 2012-03-12 | 2012-03-23 | 2013-04-30 | 2013-04-23 | 19/03 Peter to detail progress to SPM to talk to Alex re earthing results. 16/04 Waiting for updated ABs with correct earthing + extensions. 01/05 Need electrician update for project closure. | VNZ | 2012-02-13 | 2011-09-14 | 2011-09-14 | 2011-12-19 | 2011-12-14 | 2012-01-20 | 2012-01-11 | 2012-01-31 | 2012-01-31 |  | 2012-03-09 | [6 empty] | 2012-01-12 | FALSE |  | 2395482 | 5688037 | 34 Isleworth Road Hinds Canterbury |  | Discretionary Activity due to the height which the antennas will be attached at - 29/04/2011 | CELLSITE | [15 empty] | 2012-03-15 | 2012-03-09
South Island | CAN | 682 | CAN-063-009 | Cavendish | CAN-063-009-A | Kordia Colo | Ashburton District | 5 | TIER_2 | ACTIVE | COLO | DU | COLO |  | INLINE | COLO |  | 40 |  | -43.7473 | 171.3603 |  |  |  |  | Microwave | CAN-063-001-A | FALSE | FALSE |  |  | FALSE |  | 2011-04-01 | 2011-03-25 | 2011-04-08 | 2011-04-01 | 2011-08-01 | 2011-08-05 | 2 | 2011-08-01 | 2011-09-22 | 2011-07-22 | 2011-07-13 | 2011-11-30 | 2011-10-28 |  |  | 2012-03-21 | OPW | 2011-09-09 | 2011-09-05 | 2011-10-18 | 2011-10-17 | 1 |  | 2011-10-17 |  |  |  | 2011-07-27 | 1 |  |  | 2011-07-27 | 2011-11-22 |  |  |  |  | 2011-11-21 | 2011-11-22 | 2011-12-14 | 2011-11-30 | 2011-12-14 | 2012-02-13 | 2012-02-13 |  |  |  | 2011-09-08 |  |  |  |  | 2012-02-15 | 2012-02-28 | 2012-02-28 | 2012-03-15 | 2012-03-12 | 2012-06-13 | 2012-08-31 | Kordia issues final schedule of costs. 19/03 Asbuilts to be gained from Kordia. 03/04 Skycomms instructed to not pay Kordia until sector is moved. 16/04 SPM still working with Kordia on sector move. 01/05 Chris to follow up on snags. | KDA | 2012-02-14 | 2011-09-14 | 2011-09-14 | 2011-12-05 | 2011-12-08 | 2011-11-22 | 2011-11-22 | 2011-12-15 | 2011-12-16 |  | 2012-02-29 | [6 empty] | 2011-12-14 | FALSE |  | 2377950 | 5716499 | Gawler Downs Mid Canterbury |  | The site is designated (No. 398) for telecommunications and broadcasting purposes and Broadcast Communications Ltd are the Requiring Authority - 08/04/2011 | CELLSITE | [15 empty] | 2012-02-28 | 2012-02-29
South Island | STH | 1307 | STH-075-003 | Avenal | STH-075-003-A | Avenal VF colo | Invercargill City | 5 | TIER_2 | ACTIVE | COLO | DU | COLO | grey | INLINE | COLO | 20 | 28.4 |  | -46.3979 | 168.3392 | 2010-05-27 | 2010-05-27 | 2010-06-04 | 2010-06-04 | Microwave | STH-075-002-C | FALSE | FALSE | 2010-03-05 | 2010-03-05 | FALSE | 2011-08-22 | 2011-07-27 | 2011-07-27 | 2011-07-29 | 2011-07-29 | 2011-08-24 | 2011-08-24 | 1 | 2011-08-24 | 2011-08-24 | 2011-10-14 | 2011-10-17 | 2011-10-07 | 2011-09-23 | 1 |  | 2011-10-10 | DISCRETIONARY_FULL | 2011-09-09 | 2011-09-08 | 2011-10-12 | 2011-09-23 | 1 |  | 2011-09-30 |  |  | 2012-01-30 | 2012-01-17 | 4 |  | 2012-01-30 | 2012-03-13 | 2012-02-09 |  |  |  |  | 2012-02-09 | 2012-02-09 | 2012-02-14 | 2012-02-22 | 2012-02-09 | 2012-02-17 | 2012-02-22 | [8 empty] | 2012-02-22 | 2012-02-28 | 2012-02-28 | 2012-02-22 | 2012-03-14 | 2013-05-07 | 2013-05-01 | Agreed with VF as part of Colo approval that this will be a power down site when they require access, due to plumes & ladder access (BS). | VNZ | 2012-02-17 | 2011-09-14 | 2011-09-14 | 2011-12-16 | 2012-01-06 | 2012-02-07 | 2012-02-09 | 2012-02-17 | 2012-02-22 |  | 2012-03-01 | [5 empty] | BUILD | 2012-02-09 | FALSE |  | 2151485 | 5413171 | Cnr Beatrice St and Bill Richardson Drive Invercargill |  |  | CELLSITE | [15 empty] | 2012-03-02 | 2012-03-01 | 2011-07-29
South Island | CAN | 668 | CAN-062-014 | Round Top | CAN-062-014-A | Transpower colo | Selwyn District | 8 | TIER_2 | ACTIVE | COLO | DU | COLO | grey | INLINE | COLO | 21 | 30.6 |  | -43.4899 | 171.7098 |  |  |  |  | Microwave | CAN-063-001-A | FALSE | FALSE |  |  | FALSE | 2011-03-14 | 2011-02-18 | 2011-02-18 | 2011-03-28 | 2011-03-23 | 2011-04-28 | 2011-04-28 | 6 | 2011-04-28 | 2012-05-10 | 2011-07-29 | 2011-05-30 | 2011-11-10 | 2011-11-08 | 4 |  | 2011-11-08 | DISCRETIONARY_FULL | 2011-08-23 | 2012-05-08 | 2011-09-23 | 2012-05-17 | 6 |  | 2011-09-20 |  |  | 2012-02-06 | 2012-02-03 | 4 |  | 2012-02-06 | 2012-05-22 | 2012-02-15 |  |  |  |  | 2012-02-06 | 2012-02-07 | 2012-03-09 | 2012-03-16 | 2012-02-16 | 2012-02-29 | 2012-02-29 | [8 empty] | 2012-03-02 | 2012-03-14 | 2012-03-12 | 2012-03-09 | 2012-04-03 | 2013-06-14 | 2013-06-12 | Radio to be swapped out. George to confirm delivery date. Skycomms to tidy up site asap. 16/04 ice sheild bracing tbc by TX. 01/05 Chris waiting for date from ABB. Skycomms to provide extra bracing detail on tx ice shields. | TRP | 2012-03-02 | 2011-09-14 | 2011-09-14 | 2012-01-13 | 2012-01-16 | 2012-02-15 | 2012-02-15 | 2012-02-29 | 2012-02-29 |  | 2012-03-21 | [5 empty] | BUILD | 2012-02-15 | FALSE |  | 2405652 | 5745588 | Roundtop Off Coleridge Road Mid Canterbury |  | Within an Outstanding Landscape - 09/05/2011 | CELLSITE | [15 empty] | 2012-03-21 | 2012-03-21
South Island | CAN | 677 | CAN-063-003 | Rakaia | CAN-063-003-A | Rakaia VNZ CoLo | Ashburton District | 5 | TIER_2 | ACTIVE | COLO | DF | COLO | grey | INLINE | COLO | 33 | 41 |  | -43.7735 | 171.9938 |  |  |  |  | Microwave | CAN-062-014-A | FALSE | FALSE |  |  | FALSE |  | 2011-02-18 | 2011-02-18 | 2011-02-25 | 2011-03-21 | 2011-06-26 | 2011-06-24 | 2 | 2011-06-26 | 2011-07-11 | 2011-08-05 | 2011-08-01 | 2011-09-23 | 2011-09-23 | 2 |  | 2011-10-10 | DISCRETIONARY_FULL | 2011-07-08 | 2011-07-08 | 2011-08-12 | 2011-07-19 | 1 |  | 2011-07-21 |  |  | 2011-12-16 | 2011-12-20 | 1 |  | 2011-12-16 | 2011-12-20 | 2012-01-09 |  |  |  |  | 2012-01-18 | 2012-01-23 | 2012-01-26 | 2012-02-01 | 2012-01-23 | 2012-02-20 | 2012-02-20 | [8 empty] | 2012-03-02 | 2012-03-14 | 2012-03-09 | 2012-04-01 | 2012-03-30 | 2012-06-28 | 2012-06-29 | ok. 16/04 CD resubmitted. | VNZ | 2012-03-02 | 2011-09-14 | 2011-09-14 | 2011-12-19 | 2011-12-19 | 2011-12-20 | 2012-01-09 | 2012-01-31 | 2012-02-07 |  | 2012-03-16 | [6 empty] | 2012-01-18 | FALSE |  | 2429000 | 5714400 | Rakaia Hatfield Overdale Road, Rakaia, Canterbury |  | Discretionary Activity due to the height of the existing mast - 08/04/2011 | CELLSITE | [15 empty] | 2012-03-15 | 2012-03-16
South Island | MBN | 992 | MBN-051-012 | Rabbit Island | MBN-051-012-A | Rabbit Island VF Colo | Tasman District | 7 | TIER_2 | ACTIVE | COLO | DU | COLO | grey | STACK_A | COLO | 26 | 28 | 1 | -41.2841 | 173.1941 |  | 2010-10-02 | 2010-06-09 |  | Microwave | MBN-052-015-D | FALSE | TRUE |  |  | FALSE |  | 2011-03-09 | 2011-03-09 | 2011-03-18 | 2011-03-18 | 2011-04-27 | 2011-04-27 | 1 | 2011-04-27 | 2011-04-27 | 2011-07-19 | 2011-07-07 | 2011-08-26 | 2011-08-30 |  |  | 2011-09-15 | DISCRETIONARY_FULL | 2011-05-04 | 2011-05-26 | 2011-06-09 | 2011-05-25 | 1 | 2011-05-25 | 2011-05-25 |  |  | 2011-11-18 | 2011-11-22 | 1 |  | 2011-11-18 | 2011-11-22 | 2011-12-08 |  |  |  |  | 2011-12-01 | 2011-12-07 | 2012-03-13 | 2012-03-13 | 2011-12-11 | 2012-03-06 | 2012-03-07 | [8 empty] | 2012-03-07 | 2012-03-15 | 2012-03-15 | 2012-04-13 | 2012-04-13 | 2013-09-17 | 2013-10-10 |  | VNZ | 2012-03-06 | 2011-11-28 | 2011-11-28 | 2011-12-06 | 2011-12-07 | 2011-12-08 | 2011-12-08 | 2012-02-22 | 2012-03-04 | 2012-03-12 | 2012-03-29 | [5 empty] | BUILD | 2011-12-11 | FALSE |  | 2526250 | 5991389 | Forestry Rd Rabbit Island |  | our antenna will be at a permitted height but the base of the pole is already too large, hence consent is required. We will need to paint all additional equipment. - 14/03/2011 | CELLSITE | [15 empty] | 2012-03-25 | 2012-03-29
South Island | MBN | 1005 | MBN-052-001 | Tahunanui | MBN-052-001-D | Mainfreight | Nelson | 7 | TIER_2 | ACTIVE | GF | DU | T2 25 UF | grey | STACK_A | STANDALONE | 24.5 | 25 | 1 | -41.2912 | 173.2419 |  | 2010-10-02 | 2010-06-09 |  | Microwave | MBN-052-007-B | FALSE | TRUE | 2010-06-15 | 2010-06-15 | FALSE |  | 2011-06-10 | 2011-06-08 | 2011-06-15 | 2011-06-14 | 2011-07-06 | 2011-07-07 | 2 | 2011-07-06 | 2011-10-17 | 2011-07-29 | 2011-08-01 | 2011-11-18 | 2011-11-16 | 2 | 2011-11-18 | 2011-12-05 | DISCRETIONARY_RESTRICT | 2011-07-13 | 2011-07-08 | 2011-08-19 | 2011-07-14 | 1 |  | 2011-07-14 |  |  | 2011-11-18 | 2011-11-17 | 1 |  | 2011-11-18 | 2011-11-17 | 2011-11-24 |  |  |  |  | 2011-11-22 | 2011-11-22 | 2012-01-15 | 2011-11-25 | 2011-12-11 | 2012-02-07 | 2012-02-02 | [8 empty] | 2012-03-09 | 2012-03-15 | 2012-03-15 | 2012-04-14 | 2012-04-03 | 2013-08-16 | 2013-08-15 |  |  | 2012-03-08 | 2011-11-28 | 2011-11-28 | 2011-12-06 | 2011-12-07 | 2011-12-24 | 2011-11-24 | 2012-03-12 | 2012-03-13 | 2012-03-12 | 2012-03-21 | [5 empty] | BUILD | 2011-12-12 | FALSE |  | 2530250 | 5990589 | 47 Parkers Road Annesbrook, Nelson |  |  | CELLSITE | [15 empty] | 2012-03-20 | 2012-03-21
South Island | MBN | 1010 | MBN-052-006 | Stoke | MBN-052-006-D | Stoke Night'n'Day Foodstore | Nelson | 7 | TIER_2 | ACTIVE | RSR | DU | P4H |  | STACK_A | COSITE | 17.5 | 18 | 1 | -41.3122 | 173.2345 |  | 2010-10-02 | 2010-06-09 |  | Microwave | MBN-052-015-D | FALSE | TRUE | 2010-06-15 | 2010-06-15 | FALSE |  | 2011-06-08 | 2011-06-08 | 2011-06-15 | 2011-06-17 | 2011-07-29 | 2011-07-29 | 1 | 2011-07-29 | 2011-07-29 | 2011-08-05 | 2011-08-04 | 2011-08-19 | 2011-08-12 | 1 |  | 2011-08-23 | DISCRETIONARY_FULL | 2011-08-05 | 2011-08-02 | 2011-09-13 | 2011-08-18 | 1 |  | 2011-08-18 |  |  | 2011-11-18 | 2011-11-22 | 1 |  | 2011-11-18 | 2011-11-22 | 2012-02-02 |  |  |  |  | 2012-01-15 | 2012-01-18 | 2012-02-22 | 2012-02-22 | 2012-01-30 | 2012-02-09 | 2012-02-02 | [8 empty] | 2012-03-09 | 2012-03-15 | 2012-03-15 | 2012-03-27 | 2012-03-27 | 2013-06-17 | 2013-06-11 | 28/2/12: Rain delayed pole works. Transfield to send un-QA'd Volume 4 as soon as it's available please. |  | 2012-03-09 | 2011-11-28 | 2011-11-28 | 2011-12-06 | 2012-02-02 | 2011-12-18 | 2012-02-02 | 2012-02-13 | 2012-02-14 | 2012-03-12 | 2012-03-27 | [5 empty] | BUILD | 2012-02-08 | FALSE |  | 2529621 | 5988262 | 504 Main Rd Stoke cnr Putaitai St Stoke, Nelson |  | Noise from cabinets cant comply along the road boundary - 14/07/2011 | CELLSITE | [15 empty] | 2012-03-20 | 2012-03-27
South Island | MBN | 1011 | MBN-052-007 | Nelson Airport | MBN-052-007-B | Contour Roofing | Nelson | 7 | TIER_2 | ACTIVE | GF | DU | T2 25 UF |  | STACK_A | STANDALONE | 24.5 | 25 | 1 | -41.3006 | 173.2294 |  | 2010-10-02 | 2010-06-09 |  | Microwave | MBN-051-003-C | FALSE | TRUE | 2010-06-15 | 2010-06-15 | FALSE |  | 2011-04-15 | 2011-04-13 | 2011-04-19 | 2011-04-19 | 2011-05-30 | 2011-06-01 | 1 | 2011-05-30 | 2011-06-01 | 2011-06-30 | 2011-06-10 | 2011-07-28 | 2011-06-17 | 1 |  | 2011-09-29 | DISCRETIONARY_RESTRICT | 2011-06-07 | 2011-06-03 | 2011-07-18 | 2011-06-10 | 1 |  | 2011-06-10 |  |  | 2011-11-15 | 2011-11-11 | 1 |  | 2011-11-15 | 2011-11-11 | 2011-11-17 |  |  |  |  | 2011-11-28 | 2011-11-09 | 2012-02-17 | 2012-02-17 | 2011-12-08 | 2012-02-07 | 2012-02-02 | [8 empty] | 2012-03-07 | 2012-03-15 | 2012-03-15 | 2012-04-14 | 2012-04-03 | 2013-09-17 | 2013-08-19 |  |  | 2012-03-07 | 2011-11-28 | 2011-11-28 | 2011-12-06 | 2011-12-06 | 2011-11-17 | 2011-11-17 | 2012-02-02 | 2012-01-16 | 2012-03-12 | 2012-03-21 | [5 empty] | BUILD | 2011-12-08 | FALSE |  | 2529200 | 5989555 | Contour Roofing & Windows 41 Venice Place Tahunanui |  | complies with height limit but base diamter of the mast will exceed by 0.067m - 15/04/2011 | CELLSITE | [15 empty] | 2012-03-20 | 2012-03-21
South Island | OTG | 1246 | OTG-071-024 | Andersons Bay | OTG-071-024-F | Independent GF | Dunedin | 4 | TIER_2 | ACTIVE | GF | DU | P1 | green | INLINE | STANDALONE | 12 | 12 | 1 | -45.8945 | 170.5275 | 2010-05-27 |  | 2010-04-28 | 2010-04-28 | Microwave | OTG-071-010-A | FALSE | FALSE | 2009-12-17 | 2009-12-17 | FALSE |  | 2011-07-01 | 2011-07-01 | 2011-07-12 | 2011-07-11 | 2011-07-29 | 2011-07-28 | 3 | 2011-07-29 | 2011-12-22 |  | 2011-07-12 | 2011-08-22 | 2011-08-22 | 1 |  | 2011-09-13 | PERMITTED | 2011-08-30 | 2011-08-01 | 2011-09-27 | 2011-08-30 | 1 |  | 2011-08-30 |  |  | 2011-10-19 | 2011-11-01 | 2 |  | 2011-10-19 | 2012-01-20 | 2011-11-10 |  |  | 2011-10-13 |  | 2011-11-08 | 2011-11-08 | 2012-03-16 | 2012-03-14 | 2012-02-27 | 2012-02-08 | 2012-03-10 | [8 empty] | 2012-03-13 | 2012-03-15 | 2012-03-15 | 2012-02-01 | 2012-04-03 | 2012-07-02 | 2012-07-31 | Plants to be completed |  | 2012-03-09 | 2011-08-31 | 2011-08-31 | 2011-11-05 | 2011-11-05 | 2011-11-10 | 2011-11-10 | 2012-02-08 | 2012-03-08 |  | 2012-03-21 | [6 empty] | 2012-02-24 | TRUE |  | 2317975 | 5476344 | Cnr Somerville St & Silverton St Andersons Bay Dunedin |  | NES cabinets CoC and Council Plan Mast CoC - 11/07/2011 | CELLSITE | [15 empty] | 2012-03-21 | 2012-03-21
South Island | OTG | 1266 | OTG-071-045 | Maori Hill | OTG-071-045-B | Highgate & Drivers Rd RSR | Dunedin | 4 | TIER_2 | ACTIVE | RSR | DU | P4B |  | INLINE | COSITE | 12 | 12 |  | -45.8584 | 170.5006 |  |  |  |  | Microwave | OTG-071-015-A | FALSE | FALSE |  |  | FALSE |  | 2011-07-21 | 2011-07-21 | 2011-07-28 | 2011-07-28 | 2011-08-16 | 2011-08-11 | 2 | 2011-08-16 | 2014-11-18 |  | 2011-09-02 | 2011-11-01 | 2011-09-07 | 1 |  | 2011-09-07 | PERMITTED | 2011-09-08 | 2011-09-08 | 2011-10-17 | 2011-10-19 | 1 |  | 2011-10-19 |  |  | 2011-10-30 | 2011-11-11 | 1 |  | 2011-11-10 | 2011-11-11 | 2011-11-16 |  |  |  |  | 2012-01-16 | 2012-01-16 | 2012-03-09 | 2012-03-14 | 2012-02-29 | 2012-03-10 | 2012-03-12 | [8 empty] | 2012-03-10 | 2012-03-15 | 2012-03-15 | 2012-03-19 | 2012-04-03 | 2013-07-24 | 2013-07-30 |  |  | 2012-03-08 | 2011-09-16 | 2011-09-16 | 2011-12-05 | 2011-12-05 | 2011-11-29 | 2011-11-16 | 2012-03-05 | 2012-03-12 |  | 2012-03-21 | [5 empty] | BUILD | 2012-02-28 | FALSE |  | 2315767 | 5480295 | Junction of Highgate and Drivers Road Adjacent to DCC reservoir |  |  | CELLSITE |  |  | 2015-04-02 | [12 empty] | 2012-03-23 | 2012-03-21 | 2011-07-28
South Island | MBN | 990 | MBN-051-009 | Brightwater | MBN-051-009-D | Vineyard Hill | Tasman District | 7 | TIER_2 | ACTIVE | GF | DU | T2 20 RF | grey | STACK_A | STANDALONE | 18 | 20 | 1 | -41.3853 | 173.1027 |  |  |  |  | Microwave | MBN-052-015-D | FALSE | FALSE |  |  | FALSE |  | 2011-05-13 | 2011-05-11 | 2011-05-20 | 2011-05-16 | 2011-06-02 | 2011-05-27 | 1 | 2011-06-02 | 2011-05-27 |  | 2011-06-14 | 2011-07-25 | 2011-06-23 | 1 |  | 2011-07-08 | PERMITTED | 2011-06-10 | 2011-05-31 | 2011-07-13 | 2011-06-08 | 1 |  | 2011-06-08 |  |  | 2012-02-01 | 2012-02-02 | 1 |  | 2012-02-01 | 2012-02-02 | 2012-01-20 |  |  |  |  | 2012-02-13 | 2012-02-15 | 2012-03-19 | 2012-03-19 | 2012-03-12 | 2012-03-22 | 2012-04-03 | [8 empty] | 2012-03-24 | 2012-04-11 | 2012-04-15 | 2012-04-02 | 2012-04-02 | 2013-08-10 | 2013-08-08 |  |  | 2012-03-23 | 2012-01-06 | 2012-01-06 | 2012-01-12 | 2012-02-02 | 2012-01-15 | 2012-01-20 | 2012-03-24 | 2012-03-16 | 2012-04-03 | 2012-04-02 | [5 empty] | BUILD | 2012-03-09 | FALSE |  | 2518575 | 5980160 | 100 Lord Rutherford Road South Brightwater Nelson |  |  | CELLSITE | [15 empty] | 2012-03-24 | 2012-04-02
South Island | MBN | 1007 | MBN-052-003 | Nelson Central (Main HUB) | MBN-052-003-B | Clock Tower | Nelson | 7 | TIER_2 | ACTIVE | BO | DF | RT | grey | STACK_A | COSITE | 31.5 | 35.5 | 2 | -41.2709 | 173.2837 |  | 2010-10-02 | 2010-06-09 |  | Fibre Optic | WLG-047-071-A | FALSE | TRUE | 2010-06-15 | 2010-06-15 | FALSE |  | 2011-03-10 | 2011-03-10 | 2011-03-19 | 2011-03-19 | 2011-07-06 | 2011-07-07 | 4 | 2012-10-12 | 2014-12-08 | 2011-10-07 | 2011-10-10 | 2011-11-11 | 2011-11-11 | 2 | 2012-11-23 | 2012-11-21 | PERMITTED | 2011-11-08 | 2011-10-31 | 2011-12-20 | 2011-11-15 | 1 | 2012-11-16 | 2012-11-13 |  |  | 2012-02-01 | 2012-02-09 | 1 |  | 2012-11-14 | 2012-02-09 | 2012-02-17 |  |  |  |  | 2012-02-13 | 2012-02-15 | 2012-03-28 | 2012-03-28 | 2012-03-12 | 2012-03-29 | 2012-04-10 | [8 empty] | 2012-03-31 | 2012-04-11 | 2012-04-15 | 2012-03-27 | 2012-04-23 | 2013-09-17 | 2013-09-27 |  |  | 2012-03-30 | 2012-02-03 | 2012-02-03 | 2012-02-22 | 2012-02-29 | 2012-02-17 | 2012-02-17 | 2012-03-28 |  | 2012-04-10 | 2012-04-10 | [5 empty] | BUILD | 2012-03-12 | FALSE |  | 2533759 | 5992831 | 110 Trafalgar Street, Nelson |  |  | CELLSITE |  |  | 2015-04-07 | [12 empty] | 2012-04-05 | 2012-04-10
South Island | MBN | 1013 | MBN-052-009 | Broads | MBN-052-009-B | Franklyn Village | Nelson | 7 | TIER_2 | ACTIVE | RT | DF | RT | grey | STACK_A | COSITE | 18.8 | 18.5 | 3 | -41.286 | 173.2742 |  | 2010-10-02 | 2010-06-09 |  | Leased Line | MBN-052-003-B | FALSE | TRUE | 2010-06-15 | 2010-06-15 | FALSE |  | 2011-03-25 | 2011-03-21 | 2011-03-29 | 2011-03-29 | 2011-05-04 | 2011-05-04 | 1 | 2011-05-04 | 2011-05-04 |  | 2011-05-23 | 2011-06-30 | 2011-06-16 | 1 |  | 2011-07-08 | PERMITTED | 2011-05-12 | 2011-05-11 | 2011-08-18 | 2011-06-01 | 1 |  | 2011-06-01 |  |  | 2012-02-01 | 2012-02-08 | 1 |  | 2012-02-01 | 2012-02-08 | 2012-02-22 |  |  |  |  | 2012-03-08 | 2012-03-08 | 2012-03-19 | 2012-03-19 | 2012-03-15 | 2012-03-23 | 2012-04-03 | [8 empty] | 2012-03-27 | 2012-04-11 | 2012-04-15 | 2012-03-01 | 2012-04-17 | 2013-09-17 | 2013-10-01 | 9/5/13: • Owner wants panel moved. Discussed with you on 8/5. We have done site visit and identified wall of stairwell as ideal location. • GHD have provided quote for design (attached) $2300 -$2680. • You have suggested lowering antenna in it’s current location and using same mount. We had considered this not acceptable as it would be right in front of residential windows, but on reflection, given the nature of the residences in this building, the owner may be agreeable to this. This would be the cheapest option. • Jason B or John W will negotiate with the owner once a cost for the relocation has been established. • My suggestion is that both options be put to the landowner. |  | 2012-03-24 | 2012-01-06 | 2012-01-06 | 2012-01-12 | 2012-01-17 | 2012-02-15 | 2012-02-22 | 2012-03-16 | 2012-03-16 | 2012-04-03 | 2012-04-02 | [5 empty] | BUILD | 2012-03-14 | FALSE |  | 2532955 | 5991163 | Franklyn Village 47 Franklyn Street Nelson South |  | antenna will be 2.6m high and bottom of antenna wil be equal with the roof height - 24/03/2011 | CELLSITE |  |  | 2015-04-07 | [12 empty] | 2012-03-27 | 2012-03-30
South Island | MBN | 1006 | MBN-052-002 | Port Nelson | MBN-052-002-B | Port Shed 2 NW Cnr - Telecom Co-Site | Nelson | 7 | TIER_2 | ACTIVE | GF | DU | T2 25 UF | grey | STACK_A | COSITE | 24.45 | 25 |  | -41.2621 | 173.27 |  | 2010-10-02 | 2010-06-09 |  | Microwave | MBN-052-003-B | FALSE | TRUE | 2010-06-15 | 2010-06-15 | FALSE | 2011-03-04 |  | 2011-03-22 | 2011-03-29 | 2011-03-29 | 2011-05-06 | 2011-06-21 | 3 | 2011-07-15 | 2014-11-19 | 2011-11-09 | 2011-11-08 | 2011-12-21 | 2012-01-19 |  | 2011-12-21 | 2012-01-25 | DISCRETIONARY_RESTRICT | 2011-07-22 | 2011-07-29 | 2011-07-28 | 2011-07-28 | 1 |  | 2011-07-28 |  |  | 2012-03-08 | 2012-03-14 | 1 |  | 2012-03-08 | 2012-03-14 | 2012-02-02 |  |  |  |  | 2012-03-16 | 2012-03-13 | 2012-04-04 | 2012-04-04 | 2012-03-30 | 2012-04-04 | 2012-04-10 | [8 empty] | 2012-04-10 | 2012-04-13 | 2012-04-15 | 2012-03-27 | 2012-04-30 | 2013-06-17 | 2013-06-07 |  |  | 2012-04-04 | 2012-01-16 | 2012-02-15 | 2012-02-21 | 2012-03-05 | 2012-01-13 | 2012-02-02 | 2012-04-02 |  | 2012-04-10 | 2012-04-16 | [5 empty] | BUILD | 2012-03-30 | FALSE |  | 2532613 | 5993817 | Port Nelson, Shed 2, Brunt Quay, Nelson |  | No shrouding, no painting. Should be straight forward. - 24/03/2011 | CELLSITE |  |  | 2015-04-07 | [12 empty] | 2012-04-09 | 2012-04-16
South Island | MBN | 1014 | MBN-052-010 | Grampians | MBN-052-010-A | Kordia Grampians | Nelson | 7 | TIER_2 | ACTIVE | COLO | DU | COLO |  | STACK_A | COLO |  |  | 1 | -41.298 | 173.2791 |  | 2010-10-02 | 2010-06-09 |  | Microwave | MBN-052-003-B | FALSE | TRUE | 2010-06-15 | 2010-06-15 | FALSE | 2011-03-11 | 2011-03-11 | 2011-03-10 | 2011-03-24 | 2011-03-24 | 2012-03-17 | 2011-11-25 | 1 | 2012-03-17 | 2011-11-25 |  | 2011-05-19 | 2011-12-16 | 2011-10-28 |  | 2011-12-16 | 2011-10-28 | DISCRETIONARY_FULL | 2012-03-17 | 2012-04-24 | 2012-03-17 | 2012-04-24 | 1 | 2011-12-13 | 2011-12-13 | 2012-03-06 | 2011-12-13 |  | 2013-06-17 |  |  |  |  | 2012-03-13 |  |  |  |  | 2012-02-07 | 2012-01-30 | 2012-02-14 | 2012-03-05 | 2012-02-15 | 2012-03-25 | 2012-04-10 | [8 empty] | 2012-04-10 | 2012-04-14 | 2012-04-15 | 2012-03-27 | 2012-04-24 | 2013-07-25 | 2013-06-28 | Telecom have Designated Authority on this site. Cost Benefit Analysis completed. | KDA | 2012-03-27 | 2012-01-06 | 2012-01-06 | 2012-02-29 | 2012-02-15 |  | 2012-03-13 | 2012-02-21 | 2012-03-05 | 2012-04-10 | 2012-04-11 | [5 empty] | BUILD | 2012-02-14 | FALSE |  | 2533363 | 5989830 | Grampians Rd Nelson South |  | Co-lo on existing Kordia tower so no problems perceived by Council Planner. No shrouding or painting nesessary and no affected parties. - 14/03/2011 | CELLSITE | [15 empty] | 2012-04-10 | 2012-04-11 | 2011-03-24
South Island | OTG | 1228 | OTG-071-006 | Musselburgh | OTG-071-006-J | Orari Street | Dunedin | 4 | TIER_2 | ACTIVE | GF | DU | T2 25 UF Plus |  | INLINE | STANDALONE | 21.5 | 21.5 |  | -45.8897 | 170.5081 | 2010-05-27 |  | 2010-04-28 | 2010-04-28 | Microwave | OTG-071-010-A | FALSE | FALSE | 2009-12-17 | 2009-12-17 | FALSE |  | 2011-07-01 | 2011-07-01 | 2011-07-05 | 2011-07-05 | 2011-07-13 | 2011-07-16 | 2 | 2011-07-13 | 2012-02-24 |  | 2011-07-18 | 2011-11-08 | 2011-11-25 | 1 |  | 2011-12-01 | PERMITTED | 2011-07-20 | 2011-07-20 | 2011-08-30 | 2011-08-25 | 1 |  | 2011-08-25 |  |  | 2012-03-12 | 2012-03-16 | 1 |  |  | 2012-03-16 | 2012-02-01 |  |  |  |  | 2012-03-09 | 2012-03-13 | 2012-04-20 | 2012-04-13 | 2012-04-02 | 2012-04-11 | 2012-04-11 | [8 empty] | 2012-04-11 | 2012-04-14 | 2012-04-13 | 2012-05-07 | 2012-05-11 | 2013-08-09 | 2013-07-30 | On air. Some works like bollards to be completed. |  | 2012-04-12 | 2011-12-03 | 2011-12-03 | 2012-02-09 | 2012-02-09 | 2012-01-29 | 2012-02-01 | 2012-04-05 | 2012-04-04 |  | 2012-04-30 | [5 empty] | BUILD | 2012-04-03 | FALSE |  | 2316450 | 5476836 | 16 Orari Street Musselburgh Dunedin |  | Good site - 11/07/2011 | CELLSITE |  |  | 2015-04-02 | [12 empty] | 2012-04-25 | 2012-04-30
South Island | STH | 1311 | STH-075-007 | The Bluff | STH-075-007-F | Bluff Ports GF | Invercargill City | 5 | TIER_2 | ACTIVE | GF | DU | SP |  | INLINE | COSITE |  | 35 |  | -46.5898 | 168.3258 | 2010-05-27 | 2010-05-27 | 2010-06-04 | 2010-06-04 | Microwave | STH-075-002-C | FALSE | FALSE | 2010-03-05 | 2010-03-05 | FALSE |  | 2011-09-14 | 2011-09-14 | 2011-09-16 | 2011-09-16 | 2011-10-12 | 2011-10-14 | 4 | 2011-10-12 | 2011-11-29 |  | 2011-11-16 | 2011-11-25 | 2011-12-02 | 3 | 2011-11-25 | 2011-12-02 | PERMITTED | 2011-11-01 | 2011-11-03 | 2011-11-29 | 2011-11-17 | 3 |  | 2011-11-24 |  |  | 2012-01-30 | 2012-02-01 | 1 |  | 2012-01-30 | 2012-02-01 | 2012-02-15 |  |  |  |  | 2012-02-20 | 2012-02-20 | 2012-04-05 | 2012-04-04 | 2012-03-26 | 2012-04-03 | 2012-03-31 | [8 empty] | 2012-03-31 | 2012-04-14 | 2012-04-12 | 2012-05-06 | 2012-05-04 | 2013-04-30 | 2013-04-22 | DoV is with legal review. 16/04 PAD due. |  | 2012-04-03 | 2011-12-03 | 2011-12-03 | 2012-02-08 | 2012-02-08 | 2012-02-17 | 2012-02-15 | 2012-03-30 | 2012-03-30 |  | 2012-04-24 | [6 empty] | 2012-03-28 | FALSE |  | 2151664 | 5391824 | Island Harbour Off Shannon Street Bluff Southland |  |  | CELLSITE | [15 empty] | 2012-04-24 | 2012-04-24
South Island | MBN | 984 | MBN-051-003 | Richmond Hill | MBN-051-003-C | Gum Rd | Tasman District | 7 | TIER_2 | ACTIVE | GF | DU | P3 | green | STACK_A | COSITE | 13 | 15 | 1 | -41.3545 | 173.1992 |  | 2010-10-02 | 2010-06-09 |  | Microwave | MBN-052-015-D | FALSE | TRUE | 2010-06-15 | 2010-06-15 | FALSE |  | 2011-04-01 | 2011-03-30 | 2011-04-05 | 2011-04-05 | 2011-05-13 | 2011-05-16 | 2 | 2011-05-13 | 2011-09-29 |  | 2011-06-14 | 2011-11-16 | 2011-11-11 | 2 |  | 2011-11-14 | PERMITTED | 2011-05-30 | 2011-05-26 | 2012-02-29 | 2012-03-12 | 1 | 2012-02-29 | 2012-03-12 |  |  | 2012-01-25 | 2012-01-26 | 1 |  | 2012-01-25 | 2012-01-26 | 2012-01-24 |  |  |  |  | 2012-03-08 | 2012-03-08 | 2012-04-01 | 2012-04-03 | 2012-03-30 | 2012-04-05 | 2012-04-07 | [8 empty] | 2012-04-07 | 2012-04-16 | 2012-04-15 | 2012-04-24 | 2012-05-02 | 2013-07-17 | 2013-07-03 | 11/10/11: Pole type changed to Tier 1 Type 3 15m with Tier 2 rural headframe. Pole to be modified to suit this headframe (cut down in size and new top flange). |  | 2012-04-05 | 2011-11-25 | 2011-11-25 | 2011-12-14 | 2011-12-16 | 2012-01-15 | 2012-01-24 | 2012-03-30 |  | 2012-04-10 | 2012-04-18 | [5 empty] | BUILD | 2012-03-30 | FALSE |  | 2526653 | 5983567 | Gum Road Richmond |  |  | CELLSITE | [15 empty] | 2012-04-09 | 2012-04-18
South Island | MBN | 991 | MBN-051-010 | Richmond Central | MBN-051-010-I | Petrie Car Park Garden | Tasman District | 7 | TIER_2 | ACTIVE | GF | DU | P2 |  | STACK_A | STANDALONE | 19.5 | 20 | 1 | -41.3369 | 173.1835 |  | 2010-10-02 | 2010-06-09 |  | Microwave | MBN-051-003-C | FALSE | TRUE | 2010-06-15 | 2010-06-15 | FALSE |  | 2011-08-15 | 2011-08-15 | 2011-08-16 | 2011-08-16 | 2011-09-02 | 2011-08-26 | 1 | 2011-09-02 | 2011-08-26 | 2011-09-30 | 2011-10-14 | 2011-11-16 | 2011-11-11 | 1 |  | 2011-11-14 | PERMITTED | 2011-09-09 | 2011-09-02 | 2011-10-21 | 2011-09-21 | 1 | 2011-10-21 | 2011-09-21 |  |  | 2012-01-23 | 2012-01-19 | 1 |  | 2011-12-15 | 2012-01-19 | 2012-02-02 |  |  |  |  | 2012-03-06 | 2012-03-07 | 2012-03-23 | 2012-03-23 | 2012-03-19 | 2012-04-05 | 2012-04-10 | [8 empty] | 2012-04-10 | 2012-04-19 | 2012-04-18 | 2012-04-24 | 2012-04-27 | 2013-09-17 | 2013-08-07 |  |  | 2012-04-05 | 2012-01-06 | 2012-01-06 | 2012-01-12 | 2012-03-05 | 2012-01-19 | 2012-02-02 | 2012-03-27 |  | 2012-04-10 | 2012-04-13 | [5 empty] | BUILD | 2012-03-20 | FALSE |  | 2525344 | 5985525 | Petrie Car Park 302 Queen Street Richmond, NELSON |  | first consent lodged and withdrawn. Amended location wihtin car park, now in garden. - 08/09/2011 | CELLSITE | [15 empty] | 2012-04-09 | 2012-04-13 | 2011-08-16
South Island | OTG | 1268 | OTG-071-047 | North Dunedin | OTG-071-047-A | North Dunedin | Dunedin | 4 | TIER_2 | ACTIVE | RSR | DU | P4F |  | INLINE | STANDALONE |  | 13.4 | 1 | -45.863 | 170.5132 |  |  |  |  | Microwave | OTG-071-015-A | FALSE | FALSE |  |  | FALSE |  | 2011-06-10 | 2011-06-10 | 2011-06-15 | 2011-06-15 | 2011-07-13 | 2011-07-16 | 3 | 2011-07-13 | 2015-02-17 |  | 2011-08-10 | 2011-08-29 | 2011-08-26 | 1 |  | 2011-08-26 | NES | 2011-08-10 | 2011-08-10 | 2011-09-23 | 2011-10-04 | 1 |  | 2011-10-04 |  |  | 2012-03-22 | 2011-11-11 | 2 |  | 2012-03-22 | 2012-03-23 | 2011-11-14 |  |  | 2012-04-01 |  | 2012-03-23 | 2012-04-02 | 2012-04-28 | 2012-04-27 | 2012-04-23 | 2012-04-27 | 2012-04-27 | [8 empty] | 2012-05-04 | 2012-05-11 | 2012-05-14 | 2012-03-06 | 2012-05-31 | 2012-08-29 | 2012-10-09 | Pole shifted to be more inline with cabinets. BER testing to be done on battery power. 07/05 Integrated and waiting for Vol 4. 18/05/12 - PAD submitted and PAC scheduled for 01/06/12 (Ron B) |  | 2012-05-03 | 2011-09-14 | 2011-09-14 | 2011-12-07 | 2011-12-16 | 2011-11-29 | 2011-11-14 | 2012-04-27 | 2012-04-27 | 2012-04-27 | 2012-05-18 | [6 empty] | 2012-04-26 | TRUE |  | 2316764 | 5479812 | Cumberland St Oppsosite North Ground |  | Lodged before s.176 issued by Transit NZ - 11/08/2011 | CELLSITE |  |  | 2015-04-02 | [12 empty] | 2012-05-18 | 2012-05-18
South Island | MBN | 1016 | MBN-052-012 | Nelson East | MBN-052-012-D | Alton St RSR | Nelson | 7 | TIER_2 | ACTIVE | RSR | DU | P4E |  | INLINE | STANDALONE | 18 | 18 | 3 | -41.2755 | 173.2896 |  |  |  |  | Microwave | MBN-052-010-A | FALSE | TRUE |  |  | FALSE |  | 2011-09-07 | 2011-09-07 | 2011-09-09 | 2011-09-09 | 2011-09-28 | 2011-09-27 | 2 | 2011-09-28 | 2014-11-24 | 2012-02-13 | 2012-02-10 | 2012-02-20 | 2012-02-17 |  | 2012-02-20 | 2012-02-22 | PERMITTED | 2012-02-14 | 2012-02-17 | 2012-03-27 | 2012-03-09 | 1 | 2012-03-09 | 2012-03-09 |  |  | 2012-04-18 | 2012-04-19 | 1 |  | 2012-04-18 | 2012-04-19 | [5 empty] | 2012-05-07 | 2012-05-09 | 2012-05-23 | 2012-05-23 | 2012-05-21 | 2012-05-29 | 2012-05-29 | [8 empty] | 2012-05-29 | 2012-06-07 | 2012-06-13 | 2012-06-18 | 2012-06-20 | 2013-09-17 | 2013-09-09 |  |  | 2012-05-29 |  |  |  |  | 2012-05-23 |  | 2012-05-28 | 2012-05-23 |  | 2012-06-07 | 2012-02-17 | HIGH |  |  |  | BUILD | 2012-05-23 | FALSE |  | 2534249 | 5992318 | Alton St Nelson East |  |  | CELLSITE |  |  | 2015-04-07 | [12 empty] | 2012-06-01 | 2012-06-07 | 2011-09-09
South Island | CAN | 644 | CAN-059-007 | Kaiapoi | CAN-059-007-A | Kaiapoi VNZ CoLo RAA | Waimakariri | 8 | TIER_3 | ACTIVE | COLO | DU | NOPOLE |  | INLINE | COLO |  |  | 1 | -43.3918 | 172.6567 |  | 2011-11-07 |  |  | Fibre Optic | CHC-060-063-B | FALSE | FALSE |  |  | FALSE |  |  | 2011-11-01 |  | 2011-11-01 |  | 2011-08-12 | 2 |  | 2012-01-17 |  | 2011-11-28 |  | 2012-04-12 |  |  | 2012-04-12 |  |  | 2011-08-16 |  | 2011-09-16 | 1 |  |  |  |  | 2012-04-20 | 2012-04-23 | 1 |  | 2012-04-20 | 2012-04-23 | 2012-05-08 |  |  |  |  | 2012-05-11 | 2012-05-09 | 2012-05-29 | 2012-05-19 | 2012-05-10 | 2012-05-24 | 2012-06-02 | [8 empty] | 2012-06-02 | 2012-06-15 | 2012-06-13 | 2012-06-29 | 2012-06-28 | 2013-06-28 | 2013-06-21 |  | VNZ | 2012-06-01 | 2012-02-17 | 2012-02-17 | 2012-05-08 | 2012-05-10 | 2012-05-27 | 2012-05-08 | 2012-05-25 | 2012-06-15 |  | 2012-06-02 |  |  | CHRISTCHURCH_OUTER | 2012-05-31 | 2012-05-31 | BUILD | 2012-05-11 | TRUE |  | 2482199 | 5757240 | 116 Courtenay Drive Paul Edward John & Shona Mary Ayres Trustpower Ltd (03) 327 7176 Paul Mobile 027 540 6724 Email s.ayres@slingshot.co.nz |  |  | CELLSITE |  |  | 2015-04-21 | [12 empty] | 2012-06-12 | 2012-06-18
South Island | CAN | 660 | CAN-062-006 | Burnham Military | CAN-062-006-A | Burnham VF Co-Lo RAA | Selwyn District | 8 | TIER_3 | ACTIVE | COLO | DU | COLO |  | INLINE | COLO |  |  | 1 | -43.613 | 172.3234 |  | 2011-12-07 |  |  | Fibre Optic | CHC-060-063-B | FALSE | FALSE |  |  | FALSE |  |  | 2011-11-01 |  | 2011-11-01 |  | 2011-08-12 | 3 |  | 2012-01-17 |  | 2011-12-08 |  | 2012-05-04 |  |  | 2012-05-02 |  |  | 2011-08-23 |  | 2011-09-23 | 1 |  |  |  |  | 2012-04-20 | 2012-04-24 | 2 |  | 2012-04-20 | 2012-04-24 | 2012-05-18 |  |  |  |  | 2012-05-17 | 2012-05-18 | 2012-05-29 | 2012-05-25 | 2012-05-18 | 2012-06-04 | 2012-05-30 | [8 empty] | 2012-06-13 | 2012-06-15 | 2012-06-20 | 2012-07-18 | 2012-07-18 | 2013-09-10 | 2013-08-27 | 01/05 VF require outages only on Sundays. Fibre run required. Transfield to do both trenching and laying (Chorus). 29/05 Waiting for fibre - Chorus must make this happen this Sunday the Vol4 target 08/06. Waiting for permission to build - NT to push VF. 06/07 PAD submitted | VNZ | 2012-06-07 | 2012-02-17 | 2012-02-17 | 2012-05-08 | 2012-05-16 | 2012-05-16 | 2012-05-18 | 2012-05-31 | 2012-06-22 |  | 2012-06-06 |  |  | CHRISTCHURCH_OUTER | 2012-06-05 | 2012-05-31 | BUILD | 2012-05-17 | TRUE |  | 2455393 | 5732493 | Main South Rd Burnham Chch The Old Sawmill Peter Ford Home (03) 347 6685 Peter Mobile 021 138 2341 |  |  | CELLSITE |  |  | 2015-10-15 | [12 empty] | 2012-06-18 | 2012-07-06
South Island | OTG | 1227 | OTG-071-005 | Mosgiel Hill | OTG-071-005-C | Saddle Hill Rd RSR | Dunedin | 4 | TIER_2 | ACTIVE | GF | DU | P1 |  | INLINE | STANDALONE | 12 | 12 | 1 | -45.9067 | 170.3527 | 2010-05-27 |  | 2010-04-28 | 2010-04-28 | Microwave | OTG-071-004-D | FALSE | FALSE | 2009-12-17 | 2009-12-17 | FALSE |  |  | 2011-10-25 | 2011-10-28 | 2011-10-28 | 2011-12-20 | 2011-12-09 | 3 | 2011-12-20 | 2012-02-03 | 2011-10-20 | 2011-10-20 | 2012-01-20 | 2012-02-23 |  | 2012-02-28 | 2012-03-05 | PERMITTED | 2012-01-19 | 2012-01-19 | 2012-02-29 | 2012-02-29 | 2 |  | 2012-02-29 |  |  | 2012-04-27 | 2012-04-30 | 1 |  | 2012-04-27 | 2012-04-30 | 2012-05-25 |  |  |  |  | 2012-05-08 | 2012-05-09 | 2012-05-31 | 2012-05-31 | 2012-05-28 | 2012-06-01 | 2012-06-08 | [8 empty] | 2012-06-09 | 2012-06-15 | 2012-06-15 | 2012-06-18 | 2012-06-28 | 2012-09-26 | 2012-10-29 | 16/04 SPM to chase Chris on slope stability risk. 01/05 Skycomms looking for drilling company with required equipment to bore 600mm hole through rock. |  | 2012-06-04 | 2012-02-17 | 2012-02-28 | 2012-05-25 | 2012-05-29 | 2012-05-25 | 2012-05-25 | 2012-05-30 | 2012-06-11 |  | 2012-06-18 | 2012-01-19 | MEDIUM |  |  |  |  | 2012-05-28 | FALSE |  | 2304455 | 5474581 | Opposite Vodafone Site Saddle Hill Rd Mosgiel Dunedin |  | NES/DCC CoC in Visual Protection Area - 20/01/2012 | CELLSITE | [15 empty] | 2012-06-18 | 2012-06-18
South Island | CAN | 645 | CAN-059-008 | Woodend | CAN-059-008-A | Tuahiwi VF Co-Lo RAA | Waimakariri | 8 | TIER_3 | ACTIVE | COLO | DU | COLO |  | INLINE | COLO |  |  | 1 | -43.3297 | 172.6576 |  | 2012-01-07 |  |  | Fibre Optic | CHC-060-114-A | FALSE | FALSE |  |  | FALSE |  |  | 2011-11-01 |  | 2011-11-01 |  | 2011-08-16 | 2 |  | 2012-01-17 |  | 2011-11-15 |  | 2012-02-09 |  |  | 2012-02-28 |  |  | 2011-08-14 |  | 2011-09-14 | 1 |  |  |  |  | 2012-04-20 | 2012-04-20 | 2 |  | 2012-04-20 | 2012-05-03 | 2012-05-23 |  |  |  |  | 2012-05-21 | 2012-05-21 | 2012-06-01 | 2012-06-02 | 2012-05-30 | 2012-06-21 | 2012-06-08 | [8 empty] | 2012-06-20 | 2012-06-25 | 2012-06-25 | 2012-08-20 | 2012-08-20 | 2013-05-29 | 2013-05-01 | Power installed PAC due on the 2nd August | VNZ | 2012-06-27 | 2012-02-17 | 2012-02-17 | 2012-05-08 | 2012-05-17 | 2012-05-23 | 2012-05-23 | 2012-07-17 | 2012-07-27 | 2012-06-20 | 2012-06-21 |  |  | CHRISTCHURCH_OUTER | 2012-06-25 | 2012-06-19 | BUILD | 2012-05-28 | TRUE |  | 2482240 | 5764137 | 70 Te Pouapatuki Rd Woodend Prattley Farm Margaret Prattley (03) 312 7277 Mob: 027 27752 |  |  | CELLSITE |  |  | 2015-04-21 | [12 empty] | 2012-07-18 | 2012-08-08
South Island | OTG | 1229 | OTG-071-007 | St Kilda | OTG-071-007-D | Forbury Park Rooftop | Dunedin | 4 | TIER_2 | ACTIVE | RT | DF | RT |  | INLINE | COSITE | 18 | 18 |  | -45.908 | 170.4988 | 2010-05-27 |  | 2010-04-28 | 2010-04-28 | Microwave | OTG-071-010-A | FALSE | FALSE | 2009-12-17 | 2009-12-17 | FALSE |  | 2011-11-23 | 2011-11-23 | 2011-11-29 | 2011-11-29 | 2011-12-20 | 2012-01-16 | 2 | 2012-02-17 | 2013-08-22 | 2012-02-24 | 2011-12-16 | 2012-04-02 | 2012-04-12 | 1 | 2012-04-02 | 2012-04-12 | DISCRETIONARY_FULL | 2012-01-30 | 2012-02-03 | 2012-03-09 | 2012-03-06 | 1 |  | 2012-03-06 |  |  | 2012-04-20 | 2012-05-04 | 1 |  | 2012-03-30 | 2012-05-04 | 2012-06-01 |  |  |  |  | 2012-04-10 | 2012-04-15 | 2012-05-30 | 2012-06-08 | 2012-05-15 | 2012-06-06 | 2012-06-15 | [8 empty] | 2012-06-18 | 2012-06-25 | 2012-06-25 | 2012-06-21 | 2012-07-25 | 2013-05-12 | 2013-05-06 | Peter working with Alex on earthing solution. 16/04 Solution must match PD. 23/04 Peter M still waiting for CD - may not meet SOA date. 01/05 manufacture of steel work may delay progress. Vol4 would be needed by 08/06 to be drivetested in time. 07/05 construction starts this wek. Peter M trying to get better price for Monkey Toe |  | 2012-06-07 | 2012-02-17 | 2012-02-17 | 2012-05-08 | 2012-04-03 | 2012-05-25 | 2012-06-01 | 2012-05-18 | 2012-06-12 |  | 2012-07-13 | 2012-02-03 | LOW |  |  |  | BUILD | 2012-05-15 | FALSE |  | 2315791 | 5474777 | Fourbury Park Raceway Victoria Road Dunedin |  |  | CELLSITE |  |  | 2015-04-02 | [12 empty] | 2012-07-13 | 2012-07-13
South Island | CAN | 656 | CAN-062-002 | Sheffield | CAN-062-002-A | Shefield VF Co-Lo RAA | Selwyn District | 8 | TIER_3 | ACTIVE | COLO | DU | COLO |  | INLINE | COLO |  |  | 1 | -43.4046 | 171.9769 |  | 2011-12-07 |  |  | Microwave | CAN-062-014-A | FALSE | FALSE |  |  | FALSE | 2011-12-15 |  | 2011-11-01 |  | 2011-11-01 |  | 2011-08-26 | 2 |  | 2012-01-17 |  | 2011-11-25 |  | 2012-02-09 |  |  | 2012-02-28 |  |  | 2011-09-06 |  | 2011-10-06 | 1 |  |  |  |  | 2012-04-27 | 2012-05-01 | 2 |  | 2012-04-27 | 2012-05-18 | 2012-05-07 |  |  |  |  | 2012-05-18 | 2012-05-18 | 2012-05-29 | 2012-05-24 | 2012-05-18 | 2012-06-01 | 2012-06-05 |  |  |  | 2012-01-25 |  |  |  |  | 2012-06-25 | 2012-06-27 | 2012-06-26 | 2012-07-17 | 2012-07-17 | 2013-06-28 | 2013-07-03 | 06/07 - PAD submitted site on air snags on going | VNZ | 2012-06-19 | 2012-02-17 | 2012-02-17 | 2012-05-08 | 2012-05-14 | 2012-04-27 | 2012-05-07 | 2012-06-15 | 2012-06-22 | 2012-06-22 | 2012-08-17 |  |  | CHRISTCHURCH_OUTER |  |  | BUILD | 2012-05-18 | TRUE |  | 2427140 | 5755361 | Malvern Hills Rd Tom & Judy Redfern (03) 318 3786 Judy Mobile 921 318 373 |  |  | CELLSITE | [15 empty] | 2012-07-06 | 2012-07-06
South Island | CAN | 657 | CAN-062-003 | Darfield | CAN-062-003-A | Darfield VF Co-Lo RAA | Selwyn District | 8 | TIER_3 | ACTIVE | COLO | DU | COLO |  | INLINE | COLO |  | 25 | 1 | -43.4922 | 172.1195 |  | 2011-12-07 |  |  | Microwave | CAN-062-014-A | FALSE | FALSE |  |  | FALSE | 2011-12-13 |  | 2011-11-01 |  | 2011-11-01 |  | 2011-08-16 | 2 |  | 2012-01-17 |  | 2011-10-07 |  | 2011-10-07 |  |  | 2011-11-10 |  |  | 2011-08-29 |  | 2011-09-29 | 1 |  |  |  |  | 2012-04-23 | 2012-04-23 | 2 |  | 2012-04-20 | 2012-04-24 | 2012-05-08 |  |  |  |  | 2012-05-14 | 2012-05-09 | 2012-05-29 | 2012-05-20 | 2012-05-13 | 2012-06-03 | 2012-05-25 |  |  |  | 2012-01-25 |  |  |  |  | 2012-06-26 | 2012-06-27 | 2012-06-27 | 2012-07-20 | 2012-07-20 | 2013-08-23 | 2013-08-16 | site on air Snags on going on this site | VNZ | 2012-06-20 | 2012-02-17 | 2012-02-17 | 2012-05-08 | 2012-05-14 | 2012-05-08 | 2012-05-08 | 2012-05-29 | 2012-06-13 | 2012-06-23 | 2012-08-20 |  |  | CHRISTCHURCH_OUTER |  |  | BUILD | 2012-05-14 | TRUE |  | 2438792 | 5745763 | 10-26 Mathias St Drafield Frews Transport Merv Frew Home (03) 318 8516 Office (03) 366 5544 Mob: 021 763 260 |  |  | CELLSITE | [15 empty] | 2012-07-04 | 2012-07-09
South Island | CAN | 659 | CAN-062-005 | Norwood | CAN-062-005-A | Norwood RAA | Selwyn District | 8 | TIER_3 | ACTIVE | COLO | DU | COLO |  | INLINE | COLO |  |  | 1 | -43.6426 | 172.2404 |  | 2011-12-07 |  |  | Microwave | CAN-062-006-A | FALSE | FALSE |  |  | FALSE | 2011-12-14 |  | 2011-11-01 |  | 2011-11-01 |  | 2011-08-12 | 4 |  | 2012-05-24 |  | 2011-12-14 |  | 2012-04-12 |  |  | 2012-04-12 | PERMITTED | 2012-03-26 | 2012-03-26 |  | 2012-04-24 | 2 |  | 2012-04-24 |  |  | 2012-04-30 | 2012-04-27 | 4 |  | 2012-04-30 | 2013-04-17 | 2012-05-17 |  |  |  |  | 2012-05-31 | 2012-05-31 | 2012-06-21 | 2012-06-21 | 2012-06-13 | 2012-06-22 | 2012-06-22 | [8 empty] | 2012-06-27 | 2012-06-27 | 2012-06-28 | 2012-07-22 | 2012-07-23 | 2013-06-14 | 2013-05-31 | Change out Omnis for panel antennas for less than $7K. 03/04 2degrees will pay for antenna + install. New feeders to be paid for as variation. Vol 4 target 18/06 depending on fibre from burnham military. 21/05 Change Omni's outside of timeline? John C NT to follow up. | VNZ | 2012-06-26 | 2012-02-17 | 2012-02-17 | 2012-05-08 | 2012-05-14 | 2012-05-08 | 2012-05-17 | 2012-06-29 | 2012-06-22 | 2012-06-18 | 2012-06-18 | 2012-03-26 | LOW | CHRISTCHURCH_OUTER |  |  | BUILD | 2012-06-15 | TRUE |  | 2448725 | 5729150 | Cnr Coaltrack & main South Rd RD5 Burnham Chch Andy & Mandy Roberts (03) 325 4925 Andy Moble 027 6688098 andy.amanda@netspeed.net.nz |  |  | CELLSITE | [15 empty] | 2012-07-06 | 2012-07-10
South Island | CAN | 661 | CAN-062-007 | Aylesbury | CAN-062-007-A | Aylesbury VF Co-Lo RAA | Selwyn District | 8 | TIER_3 | ACTIVE | COLO | DU | COLO |  | INLINE | COLO |  |  | 1 | -43.5322 | 172.269 |  | 2011-12-07 |  |  | Fibre Optic | CHC-060-063-B | FALSE | FALSE |  |  | FALSE |  |  | 2011-11-01 |  | 2011-11-01 |  | 2011-08-16 | 2 | 2011-11-30 | 2012-01-17 |  | 2011-11-15 |  | 2011-11-15 |  |  | 2011-11-22 |  |  | 2011-08-23 | 2011-09-23 | 2011-09-23 | 1 |  |  |  |  | 2012-04-27 | 2012-05-02 | 2 |  | 2012-04-27 | 2012-05-17 | 2012-05-28 |  |  |  |  | 2012-05-21 | 2012-05-21 | 2012-05-29 | 2012-05-28 | 2012-05-29 | 2012-06-05 | 2012-06-05 | [8 empty] | 2012-06-14 | 2012-06-27 | 2012-06-26 | 2012-07-13 | 2012-07-13 | 2013-08-09 | 2013-08-07 | Vol 4 target 08/06 Fibre 30/05 | VNZ | 2012-06-16 | 2012-02-17 | 2012-02-17 | 2012-05-08 | 2012-05-14 | 2012-05-23 | 2012-05-28 | 2012-06-06 | 2012-06-08 | 2012-06-13 | 2012-06-08 |  |  | CHRISTCHURCH_OUTER | 2012-05-31 | 2012-06-01 | BUILD | 2012-05-22 | TRUE |  | 2450921 | 5741432 | 954 Aylesbury Rd RD1 Aylesbury Walker Farm Fern Grove Trust (Mark) 694 Waterholes Rd RD8 Chch (03) 344 5524 Mob: 021 226 6300 mark@ruralpm.co.nz |  |  | CELLSITE | [15 empty] | 2012-07-02 | 2012-07-09
South Island | CAN | 638 | CAN-059-001 | Oxford | CAN-059-001-A | Oxford VF CoLo | Waimakariri | 8 | TIER_3 | ACTIVE | COLO | DU | COLO |  | INLINE | COLO |  |  | 1 | -43.2732 | 172.1766 |  | 2011-12-02 |  |  | Microwave | CAN-062-002-A | FALSE | FALSE |  |  | FALSE |  | 2011-09-29 | 2011-09-29 | 2011-09-29 | 2011-09-29 | 2012-02-23 | 2011-08-10 | 2 | 2012-03-28 | 2012-01-17 | 2012-04-13 | 2012-05-03 | 2012-05-27 | 2012-05-22 |  |  | 2012-07-11 |  |  | 2011-08-14 |  | 2011-09-14 | 1 |  |  |  |  | 2012-04-27 | 2012-04-27 | 2 |  | 2012-04-27 | 2013-04-17 | 2012-05-07 |  |  |  |  | 2012-06-01 | 2012-05-31 | 2012-06-29 | 2012-06-28 | 2012-06-25 | 2012-07-02 | 2012-07-02 | [8 empty] | 2012-07-17 | 2012-07-20 | 2012-07-24 | 2012-08-31 | 2012-09-04 | 2013-05-17 | 2013-05-24 |  | VNZ | 2012-07-13 | 2012-03-15 | 2012-03-15 | 2012-05-08 | 2012-05-14 | 2012-05-08 | 2012-05-07 | 2012-07-19 | 2012-08-20 | 2012-06-29 | 2012-08-17 |  |  | CHRISTCHURCH_OUTER |  |  | BUILD | 2012-06-27 | TRUE |  | 2443175 | 5770141 | Scurr Hilltop Bay Road or Sales Road, Oxford John Skurr 03 3124215 jskurr@pggwrightson.co.nz |  |  | CELLSITE | [15 empty] | 2012-07-18 | 2012-08-27 | 2012-02-13
South Island | MBN | 1012 | MBN-052-008 | Toi Toi | MBN-052-008-F | Gibair Hill | Nelson | 7 | TIER_2 | ACTIVE | GF | DU | P1 |  | STACK_A | STANDALONE | 10 | 10 | 2 | -41.3 | 173.2545 |  | 2010-10-02 | 2010-06-09 |  | Microwave | MBN-052-010-A | FALSE | FALSE | 2010-06-15 | 2010-06-15 | FALSE |  | 2011-08-05 | 2011-08-03 | 2011-08-10 | 2011-08-08 | 2011-08-29 | 2011-08-26 | 2 | 2012-02-28 | 2012-02-24 | 2012-02-03 | 2011-12-22 | 2012-03-09 | 2012-03-15 | 1 | 2012-03-09 | 2012-03-15 | DISCRETIONARY_FULL | 2011-09-05 | 2011-08-31 | 2011-10-17 | 2011-09-20 | 1 | 2011-10-17 | 2011-09-20 |  |  | 2012-09-28 | 2012-10-02 | 1 |  | 2012-09-28 | 2012-10-02 |  |  |  | 2012-06-01 |  | 2012-09-17 | 2012-08-27 | 2012-10-17 | 2012-10-16 | 2012-10-04 | 2012-10-07 | 2012-10-07 | [8 empty] | 2012-10-08 | 2012-10-24 | 2012-10-25 | 2012-10-31 | 2012-10-31 | 2013-09-17 | 2013-10-01 | 9/5/13: • Access track in two places to be completed. - Part of track “below the house” was damaged during construction and is to be repaired. This is approx. 110m of metalled track. - Part of track adjacent to site needs to be upgraded (approx 50m). This was not completed prior to construction due to time limitations (remembering that large amounts of rain delayed the building of the track, so time was of the essence). |  | 2012-10-07 | 2012-06-28 | 2012-06-28 |  |  |  |  | 2012-10-11 |  | 2012-10-10 | 2012-10-17 | [5 empty] | BUILD | 2012-09-28 | TRUE |  | 2531303 | 5989607 | 94a Beatson Road Wakatu Nelson |  |  | CELLSITE | [15 empty] | 2012-10-19 | 2012-10-23
South Island | CAN | 625 | CAN-058-001 | Hanmer Springs | CAN-058-001-A | VF Colo Hanmer | Hurunui District | 8 | TIER_3 | ACTIVE | COLO | DU | COLO |  | INLINE | COLO |  |  | 1 | -42.5151 | 172.8187 |  |  |  | 2012-08-31 | Fibre Optic | CHC-060-114-A | FALSE | FALSE |  |  | FALSE |  | 2012-02-22 | 2012-02-22 | 2012-02-29 | 2012-03-01 | 2012-04-04 | 2012-04-04 | 2 | 2012-04-04 | 2012-06-05 | 2012-05-25 | 2012-05-21 | 2012-08-21 | 2012-08-21 | 2 |  | 2012-09-28 | PERMITTED | 2012-06-08 | 2012-06-11 | 2012-07-13 | 2012-06-18 | 2 |  |  |  |  | 2012-08-23 | 2012-09-10 | 2 |  |  | 2012-09-19 | 2012-09-21 |  |  |  |  | 2012-09-28 | 2012-09-28 | 2012-10-12 | 2012-10-03 | 2012-09-29 | 2012-11-07 | 2012-11-07 | [8 empty] | 2012-11-07 | 2012-11-13 | 2012-11-12 | 2012-11-19 | 2012-11-19 | 2013-05-17 | 2013-05-06 | VF Colo – 3-4m extension. Power source and track are via easement with VF and TC. Colo submitted 23/04. Fibre ordered. RF to do license. 23/7 GHD doing site visit. Jaco to check fibre route. Await CD's. SPM requested Arrow power audit 20/7. Power audit complete sent to George | VNZ | 2012-11-07 | 2012-07-16 | 2012-07-16 | 2012-09-10 | 2012-09-19 | 2012-09-17 | 2012-09-21 | 2012-10-16 | 2012-10-16 | 2012-11-08 | 2012-11-08 | 2012-02-08 | LOW | KAIKOURA | 2012-10-29 | 2012-10-29 | BUILD | 2012-09-29 | TRUE |  | 2495104 | 5854667 | Hanmer Springs |  | Permitted if under 30m. - 02/03/2012 | CELLSITE | [15 empty] | 2012-11-16 | 2012-11-13
South Island | CAN | 626 | CAN-058-002 | Culverden | CAN-058-002-C | Culverden VF Cosite | Hurunui District | 8 | TIER_3 | ACTIVE | GF | DU | T2 20 RH |  | INLINE | COSITE |  |  | 1 | -42.7228 | 172.8502 |  | 2012-01-16 |  | 2012-08-31 | Fibre Optic | CHC-060-114-A | FALSE | FALSE |  |  | FALSE |  | 2012-02-21 | 2012-02-21 | 2012-03-21 | 2012-03-21 | 2012-05-18 | 2012-05-21 | 2 | 2012-05-18 | 2012-06-05 | 2012-06-29 | 2012-07-02 | 2012-09-21 | 2012-09-21 |  |  | 2012-09-21 | PERMITTED | 2012-07-02 | 2012-07-03 | 2012-08-02 | 2012-07-18 | 2 |  | 2012-07-30 |  |  | 2012-09-06 | 2012-09-12 | 1 |  |  | 2012-09-12 | 2012-09-19 |  |  |  |  | 2012-09-17 | 2012-09-19 | 2012-11-09 | 2012-11-07 | 2012-10-31 | 2012-11-11 | 2012-11-09 | [8 empty] | 2012-11-12 | 2012-11-13 | 2012-11-13 | 2012-11-20 | 2012-11-19 | 2013-07-01 | 2013-06-28 | 26/03 Now proceeding with GF due to risks/costs with VF colos. SA to talk to LL re track with rev1. 03/04 SA to find out history of track costs and TC easement. 23/04 Power might include 3 transformer upgrades. 29/05 SA to chase LL response re lease. 14/6 - submitted co-siting to Vf & Telecom. 16/7 Vic to chase sol. this wk. Chk maintenance fee if applicable. Tx using fibre solution. Budget approved. Order Fibre. 23/7 Tx - check fibre route. Solic not responded, SA to call other LL to progress. |  | 2012-11-11 | 2012-07-18 | 2012-07-18 | 2012-09-28 | 2012-09-19 | 2012-09-17 | 2012-09-19 | 2012-11-09 | 2012-11-08 | 2012-11-12 | 2012-11-12 | 2012-02-08 | LOW | KAIKOURA | 2012-11-06 | 2012-11-05 | BUILD | 2012-10-31 | TRUE |  | 2497738 | 5831602 | Mousepoint Culverden |  | permitted if under 30m in height - 26/03/2012 | CELLSITE | [15 empty] | 2012-11-15 | 2012-11-15
South Island | CAN | 640 | CAN-059-003 | Ohoka | CAN-059-003-A | Mandeville RBI | Waimakariri | 8 | TIER_3 | ACTIVE | RBI | DU | RBILATTICE |  | STACK_A | COLO | 40 | 40 | 1 | -43.3691 | 172.5578 | [6 empty] | FALSE | FALSE |  |  | FALSE |  |  | 2012-06-20 | 2012-06-01 | 2012-06-01 | 2012-06-01 | 2012-07-03 | 1 | 2012-06-01 | 2012-07-03 |  | 2012-06-01 |  | 2012-06-01 |  |  | 2012-06-01 | FULL_NOTIFIED | 2012-06-01 | 2012-09-13 | 2012-06-01 | 2012-09-13 | 1 | 2012-06-01 | 2012-06-01 |  |  | 2012-08-22 | 2012-07-03 | 1 |  |  | 2012-07-03 | [5 empty] | 2012-09-21 | 2012-09-21 | 2012-09-30 | 2012-09-26 | 2012-09-26 | 2012-10-12 | 2012-10-12 | [8 empty] | 2012-10-30 | 2012-11-13 | 2012-11-01 | 2012-11-13 | 2012-11-09 | 2013-06-21 | 2013-05-31 | cabinets to be installed on area 2 | VNZ | 2012-10-23 |  |  | 2012-09-21 | 2012-09-21 |  |  | 2012-10-05 | 2012-10-05 | 2012-10-15 | 2012-11-01 | 2012-09-13 | LOW | RBI |  |  | BUILD | 2012-09-30 | TRUE |  | 2474169 | 5759723 | 236 Bradleys Road Ohoka Canterbury |  |  | CELLSITE | [15 empty] | 2012-11-05 | 2012-11-01 | 2012-06-01
South Island | MBN | 1026 | MBN-053-004 | Blenheim Central | MBN-053-004-A | Cavalier House | Marlborough District | 7 | TIER_3 | ACTIVE | RT | DF | RT |  | STACK_A | COSITE |  |  | 1 | -41.5113 | 173.9572 |  | 2012-01-11 |  |  | Fibre Optic | WLG-047-071-A | FALSE | FALSE |  |  | FALSE |  | 2012-03-22 | 2012-03-22 | 2012-03-29 | 2012-03-30 | 2012-07-06 | 2012-07-05 | 1 | 2012-07-06 | 2012-07-05 | 2012-06-22 | 2012-06-07 | 2012-07-26 | 2012-07-20 |  | 2012-10-05 | 2012-11-06 | DISCRETIONARY_RESTRICT | 2012-07-12 | 2012-07-06 | 2012-08-23 | 2012-08-10 | 1 | 2012-08-23 | 2012-08-10 |  |  | 2012-10-17 | 2012-10-17 | 1 |  | 2012-10-17 | 2012-10-17 | 2012-10-09 |  |  |  |  | 2012-09-10 | 2012-09-10 | 2012-10-12 | 2012-10-10 | 2012-10-11 | 2012-10-20 | 2012-10-19 | [8 empty] | 2012-10-19 | 2012-11-13 | 2012-10-31 | 2012-11-13 | 2012-11-13 | 2013-06-17 | 2013-06-06 |  |  | 2012-10-19 | 2012-09-03 |  | 2012-09-16 | 2012-10-01 | 2012-09-10 | 2012-10-09 | 2012-10-15 | 2012-09-24 | 2012-10-23 | 2012-10-30 | 2012-04-02 | LOW | BLENHEIM | 2012-10-15 | 2012-10-16 | BUILD | 2012-10-15 | FALSE |  | 2589893 | 5965743 | 1-17 Market Street Blenheim |  | CBD Roftop - 02/04/2012 | CELLSITE |  |  | 2015-04-07 | [12 empty] | 2012-10-30 | 2012-10-30 | 2012-03-30
South Island | CAN | 627 | CAN-058-003 | Waipara | CAN-058-003-A | Waipara VF Colo | Hurunui District | 8 | TIER_3 | ACTIVE | COLO | DU | COLO |  | STACK_A | COLO |  |  | 1 | -42.9988 | 172.7259 |  | 2012-02-01 |  | 2012-08-31 | Microwave | CAN-058-011-A | FALSE | FALSE |  |  | FALSE |  | 2012-02-22 | 2012-02-22 | 2012-02-29 | 2012-03-01 | 2012-04-10 | 2012-04-12 | 4 | 2012-04-10 | 2012-06-26 | 2012-07-13 | 2012-06-20 | 2012-08-15 | 2012-08-15 |  |  | 2012-09-28 | DISCRETIONARY_RESTRICT | 2012-07-18 | 2012-06-25 | 2012-07-23 | 2012-07-17 | 4 |  | 2012-07-17 |  |  | 2012-08-22 | 2012-09-06 | 1 |  |  | 2012-09-06 | 2012-10-02 |  |  |  |  | 2012-10-05 | 2012-10-05 | 2012-10-26 | 2012-10-26 | 2012-10-05 | 2012-11-14 | 2012-11-14 | [8 empty] | 2012-11-15 | 2012-11-23 | 2012-11-22 | 2012-12-04 | 2012-11-29 | 2013-07-18 | 2013-07-03 | VF Colo – on existing monopole below VF. 06/03 Lease extension required (3yrs left). All same landowner so no backup option. 26/03 Access and power to be sorted by SPM and SA. Colo app submitted 19/04. 5/6 VF want design change, colo App refused. 18/6 New Colo app submitted 14/6, approved 20/6. Telecom co-siting issued 9/7. Budget approved. 23/7 GHD - doing site visit pre-CDs. 4 week delay due to Lambing Season no access from 29/08 | VNZ | 2012-11-14 | 2012-07-18 | 2012-07-18 | 2012-09-13 | 2012-10-01 | 2012-09-14 | 2012-10-02 | 2012-11-08 | 2012-11-08 | 2012-11-12 | 2012-11-16 | 2012-02-08 | LOW | KAIKOURA |  |  | BUILD | 2012-10-06 | TRUE |  | 2487658 | 5800919 | Waipara off Weka Pass Road Canterbury |  | Consent required due to being on a ridgeline and within 1km of SH7A. - 02/03/2012 | CELLSITE | [15 empty] | 2012-11-21 | 2012-11-20
South Island | CAN | 633 | CAN-058-011 | Amberley | CAN-058-011-A | Markham Street TC Colo | Hurunui District | 8 | TIER_3 | ACTIVE | COLO | DU | COLO |  | INLINE | COLO |  |  | 1 | -43.1527 | 172.7278 |  |  |  | 2012-08-31 | Fibre Optic | CHC-060-114-A | FALSE | FALSE |  |  | FALSE |  | 2012-02-22 | 2012-02-22 | 2012-02-29 | 2012-03-02 | 2012-05-11 | 2012-05-04 | 2 | 2012-05-23 | 2012-05-24 | 2012-07-23 | 2012-07-18 | 2012-07-27 | 2012-07-25 |  | 2012-08-15 |  | DISCRETIONARY_FULL | 2012-07-19 | 2012-07-20 | 2012-08-20 | 2012-08-15 | 2 |  |  |  |  | 2012-10-02 | 2012-10-03 | 1 |  | 2012-10-02 | 2012-10-03 | 2012-10-19 |  |  | 2012-09-13 |  | 2012-10-25 | 2012-10-25 | 2012-11-12 | 2012-11-12 | 2012-11-06 | 2012-11-15 | 2012-11-15 | [8 empty] | 2012-11-15 | 2012-11-23 | 2012-11-23 | 2012-12-04 | 2012-11-29 | 2013-05-24 | 2013-05-14 | Telecom Colo (lattice) – 3m extension required. 07/05 Fibre quote received. Colo app submitted 10/05. 18/6 Liz to draft RMA. 18/7: Colo approved, lease terms agreed. 23/7 Tx will include fibre. | TNZ | 2012-11-15 | 2012-07-18 | 2012-07-18 | 2012-10-22 | 2012-11-06 | 2012-10-19 | 2012-10-19 | 2012-11-09 | 2012-11-09 | 2012-11-14 | 2012-11-16 | 2012-02-08 | LOW | KAIKOURA | 2012-11-09 | 2012-11-09 | BUILD | 2012-11-12 | TRUE | 2012-09-13 | 2487867 | 5783815 | Off Markham Street Amberley |  | On a designated site. Consent required as extending a lattice tower, for which permitted height is 10m (note existing structure already exceeds this) - 02/03/2012 | CELLSITE | [15 empty] | 2012-11-21 | 2012-11-21
South Island | CAN | 680 | CAN-063-006 | Ealing | CAN-063-006-A | Rangitata GF (east of VF) | Ashburton District | 4 | TIER_3 | ACTIVE | GF | DU | SP |  | STACK_A | COSITE | 35 | 35 | 1 | -44.0503 | 171.4147 |  | 2012-01-10 |  | 2012-09-04 | Fibre Optic | CAN-063-004-A | FALSE | FALSE |  |  | FALSE |  | 2012-02-23 | 2012-02-23 | 2012-02-29 | 2012-03-05 | 2012-04-05 | 2012-04-13 | 2 | 2012-04-05 | 2012-05-10 | 2012-05-07 | 2012-05-18 | 2012-05-31 | 2012-06-13 | 1 |  | 2012-06-13 | DISCRETIONARY_FULL | 2012-05-16 | 2012-05-17 | 2012-06-22 | 2012-06-22 | 2 |  |  | 2012-08-17 |  | 2012-10-02 | 2012-10-02 | 1 |  | 2012-10-02 | 2012-10-02 | 2012-08-30 |  |  |  |  | 2012-08-27 | 2012-08-24 | 2012-10-26 | 2012-10-31 | 2012-09-18 | 2012-11-05 | 2012-11-01 | 2012-11-09 | 2012-11-12 | [6 empty] | 2012-11-14 | 2012-11-23 | 2012-11-21 | 2012-12-06 | 2012-11-30 | 2013-09-20 | 2013-09-23 | GF to east of VF - just other-side of farm gate, power and fibre dependent. 35m monopole to clear tree. Could look at position closer to road if landowner requires, but will need to look at tree height. Cosite issued to VF re power. 2/7 Tree pruning condition highlighted to LL, await response. 16/7 Pole ready and awaiting delivery. 23/7 Geotech this wk - 26/7. Build start 8/8. 30/7 Geotech this wk. LL to be informed of power route. 6/08 Co-ordination require for power & fibre install. CONSTRUCTION START DELAYED due to ground conditions. 27/8 Const. to start. |  | 2012-11-07 | 2012-06-29 | 2012-06-28 | 2012-09-03 | 2012-09-04 | 2012-08-30 | 2012-08-30 | 2012-11-01 | 2012-11-01 | 2012-11-13 | 2012-11-15 | 2012-02-08 | LOW | TIMARU_ASHBURTON |  |  | BUILD | 2012-09-19 | FALSE |  | 2382975 | 5682925 | East of VF Ealing Coldstream Rd Canterbury |  | Exceeds 25m permitted height. - 02/03/2012 | CELLSITE | [15 empty] | 2012-11-22 | 2012-11-20 | 2012-03-05
South Island | OTG | 1216 | OTG-070-009 | Arrowtown | OTG-070-009-A | Glencoe Station TCNZ Cosite | Queenstown | 8 | TIER_3 | ACTIVE | GF | DU | P2 |  | INLINE | COSITE |  | 8 |  | -44.9485 | 168.8527 |  |  |  |  | Microwave | OTG-070-001-A | FALSE | FALSE |  |  | FALSE |  | 2011-05-05 | 2011-05-05 | 2011-05-20 | 2011-05-24 | 2011-07-01 | 2011-07-01 | 6 | 2011-08-24 | 2013-10-03 | 2012-06-18 | 2012-06-22 | 2012-03-21 | 2012-03-19 | 4 |  | 2012-03-19 | DISCRETIONARY_FULL | 2012-02-29 | 2012-02-15 | 2012-04-04 | 2012-04-26 | 2 | [5 empty] | 2012-12-06 | 1 |  |  | 2012-12-06 | 2012-11-05 |  |  |  |  | 2012-09-26 | 2012-09-27 | 2012-11-15 | 2012-11-15 | 2012-11-05 | 2012-11-19 | 2012-11-15 | [8 empty] | 2012-11-21 | 2012-11-30 | 2012-11-29 | 2012-12-10 | 2012-12-10 | 2013-06-21 | 2013-06-07 | 03/10 Peninsula hill dish to be shown on asbuilts. 30/01 Fishnet want to colocate. 03/04 Peter proposed site move closer and down towards TC pole. Chris Adams to visit with Peter M to review concept. 16/04 HW to cxonfirm if skycomms will build. Need revised PD asap. Build and geotech not to commence until details confirmed with Council. 01/05 Delta independent fuse only. Topo survey required to peg ground. Peter to arrange access for geotech. Construction could be achieved using helicopters and concrete pump, therefore no access track required. Peter to find out pole weight and costs. Build not likely to commence until Sept. 23/7DOV signed & S127 approved. Finalise CD's. |  | 2012-11-19 | 2012-06-15 | 2012-05-06 | 2012-10-12 | 2012-11-05 | 2012-10-19 | 2012-11-05 | 2012-11-09 | 2012-11-06 | 2012-11-23 | 2012-11-23 |  |  | TIER_1_INFILL |  |  | BUILD | 2012-11-05 | TRUE |  | 2182814 | 5576160 | Glencoe Station Off Glencoe Road Arrowtown |  |  | CELLSITE | [15 empty] | 2012-11-27 | 2012-11-28 | 2011-05-27
South Island | CAN | 662 | CAN-062-008 | Rolleston | CAN-062-008-C | 846 Jones Road | Selwyn District | 8 | TIER_3 | ACTIVE | GF | DF | SP |  | INLINE | STANDALONE | 35 | 35 | 2 | -43.5878 | 172.3769 |  |  |  |  | Fibre Optic | CHC-060-114-A | FALSE | FALSE |  |  | FALSE |  | 2012-02-29 | 2012-02-29 | 2012-03-13 | 2012-03-14 | 2012-05-25 | 2012-05-24 | 1 | 2012-05-25 | 2012-05-24 | 2012-06-14 | 2012-06-12 | 2012-06-29 | 2012-06-25 | 1 |  | 2012-06-25 | FULL_NOTIFIED | 2012-06-13 | 2012-06-13 | 2012-07-11 | 2012-07-13 | 1 |  |  |  |  | 2012-09-28 | 2012-09-28 | 2 |  | 2012-09-28 | 2012-10-03 | 2012-10-05 |  |  | 2012-09-13 |  | 2012-10-09 | 2012-10-09 | 2012-12-07 | 2012-12-06 | 2012-10-31 | 2012-11-23 | 2012-11-23 | [8 empty] | 2012-12-10 | 2012-12-01 | 2012-12-13 | 2012-12-28 | 2012-12-18 | 2013-10-14 | 2013-12-20 | 5/6 All go. 26/6 Council adv - non notified basis. |  | 2012-12-04 | 2012-08-07 | 2012-08-07 | 2012-10-26 | 2012-10-09 | 2012-10-22 | 2012-10-05 | 2012-12-05 | 2012-12-11 | 2012-11-26 | 2012-12-13 |  | LOW | CHRISTCHURCH_OUTER | 2012-11-10 | 2012-11-09 | BUILD | 2012-10-30 | TRUE | 2012-09-13 | 2459694 | 5735329 | 846 Jones Rd Rolleston |  | Council normally fully notify ten m height increases (35m pole) in consultation wiht council, due to the location, we have discussed that limited ntoification b more appropriate. RMG requested photomontage and are now able to argue no affected parties. Council could have a different view though and may identify some. In particular one to the south. We think worth lodging and getting council to make the call. - 05/06/2012 | CELLSITE |  |  | 2015-10-15 | [12 empty] | 2012-12-12 | 2012-12-12
South Island | CAN | 689 | CAN-064-007 | Timaru | CAN-064-007-D | Timaru - George Street | Timaru | 4 | TIER_3 | ACTIVE | RT | DF | RT |  | INLINE | COSITE | 40 | 40 | 1 | -44.3973 | 171.2546 | 2010-05-27 | 2012-01-09 | 2010-06-24 | 2010-10-20 | Fibre Optic | CAN-064-016-A | FALSE | FALSE | 2010-05-27 | 2010-05-27 | FALSE |  | 2012-03-21 | 2012-03-21 | 2012-03-28 | 2012-03-28 | 2012-06-08 | 2012-06-13 | 2 | 2012-06-13 | 2012-07-17 | 2012-07-27 | 2012-07-09 | 2012-08-03 | 2012-08-03 | 2 |  | 2012-09-13 | CONTROLLED | 2012-07-23 | 2012-07-23 | 2012-08-25 | 2012-08-20 | 2 |  |  |  |  | 2012-11-23 | 2012-11-26 | 1 |  | 2012-11-23 | 2012-11-26 | 2012-10-29 |  |  |  |  | 2012-10-23 | 2012-10-23 | 2012-11-26 | 2012-11-27 | 2012-10-28 | 2012-11-21 | 2012-11-24 |  |  |  | 2012-06-18 |  |  |  |  | 2012-11-27 | 2012-12-05 | 2012-12-06 | 2012-12-12 | 2012-12-11 | 2013-10-18 | 2013-12-03 | Farmside Colo (stub on commercial building) Small chimney on roof may impact RF. Woollcombe House not preferred. Fibre, check + Chorus asap. 28/05 SA to confirm LL is ok with mobile generator in carpark in emergencies. Peter to check calcs of structural reinforcing from TC. 5/6 Draft RMA. Telecom co-siting sent 21/6. Wo2 delayed until lease terms agreed. 16/7 Revised PD required. 23/7 Draft Wo2. Terms agreed & LL. 20/8 Kate to chase Council. 03/09 Jaco to investigate spare ATN. 10/09 No letter drop reqd. | TNZ | 2012-11-22 | 2012-08-28 | 2012-08-28 | 2012-10-10 | 2012-10-16 | 2012-10-30 | 2012-10-29 | 2012-11-15 | 2012-11-19 | 2012-11-27 | 2012-11-28 | 2012-02-14 | LOW | TIMARU | 2012-11-19 | 2012-11-19 | BUILD | 2012-10-25 | FALSE |  | 2370950 | 5644122 | 24-30 George Street Timaru |  | Telecommunications mast specified as controlled activities within Commercial 1 zone, i.e. no permitted activity status possible in this zone. - 26/03/2012 | CELLSITE | [15 empty] | 2012-12-03 | 2012-11-29 | 2012-03-28
South Island | CAN | 621 | CAN-054-001 | Kaikoura North | CAN-054-001-B | KWR Greenfield | Kaikoura District | 8 | TIER_3 | ACTIVE | GF | DU | T2 20 UF |  | INLINE | STANDALONE | 20 | 20 | 1 | -42.3921 | 173.6802 |  | 2012-06-04 |  | 2012-08-31 | Microwave | CAN-054-002-E | FALSE | FALSE |  |  | FALSE |  | 2012-04-24 | 2012-04-24 | 2012-05-04 | 2012-05-03 | 2012-05-28 | 2012-06-06 | 3 | 2012-05-28 | 2013-08-22 | 2012-07-24 | 2012-07-23 | 2012-09-21 | 2012-09-18 | 2 |  | 2012-09-18 | PERMITTED | 2012-07-27 | 2012-07-27 | 2012-08-27 | 2012-08-21 | 2 |  |  |  |  | 2012-10-04 | 2012-10-12 | 1 |  | 2012-10-16 | 2012-10-12 | 2012-11-01 |  |  | 2012-09-14 |  | 2012-10-17 | 2012-10-15 | 2012-11-23 | 2012-11-23 | 2012-11-20 | 2012-11-26 | 2012-11-26 | [8 empty] | 2012-12-01 | 2012-12-12 | 2012-12-06 | 2012-12-26 | 2012-12-14 | 2013-08-15 | 2013-08-12 | HAIL site. 5/6 Look at contamination early PRE WO2. 11/06 Vic - obtain affected party consent. SA to progress LL consent -18/6 Ongoing. GHD to look at foundation design re. contamination thereafter. Draft WO2. 09/07 Show fibre against this site. 23/7 Vic to chase affected party signoff. GHD to send contamination analysis quote. TX to look at fibre route. RMA to include geotechnical component if poss. Waiting for feed back from contamination report. |  | 2012-11-23 | 2012-08-27 |  | 2012-11-20 | 2012-11-13 | 2012-10-17 | 2012-11-01 | 2012-11-21 | 2012-11-27 | 2012-11-28 | 2012-11-28 |  |  | KAIKOURA |  |  | BUILD | 2012-11-20 | TRUE | 2012-09-14 | 2566005 | 5868128 | Edmund Avenue Off Beach Road Kaikoura |  |  | CELLSITE | [15 empty] | 2012-12-07 | 2012-12-07 | 2012-05-03
South Island | CAN | 622 | CAN-054-002 | Kaikoura | CAN-054-002-E | Peninsula hill GF | Kaikoura District | 8 | TIER_3 | ACTIVE | GF | DU | T2 20 RH |  | INLINE | COSITE | 20 | 20 | 2 | -42.4183 | 173.6923 |  | 2012-07-06 |  | 2012-08-31 | Fibre Optic | CHC-060-114-A | FALSE | FALSE |  |  | FALSE |  | 2012-04-24 | 2012-03-13 | 2012-05-01 | 2012-04-10 | 2012-06-07 | 2012-06-06 | 2 | 2012-06-07 | 2012-08-14 | 2012-07-19 | 2012-07-19 | 2012-08-17 | 2012-07-25 |  | 2012-08-29 |  | DISCRETIONARY_RESTRICT | 2012-07-27 | 2012-07-26 | 2012-08-29 | 2012-08-28 | 2 |  |  | 2012-09-28 |  | 2012-10-04 | 2012-10-16 | 1 |  | 2012-10-16 | 2012-10-16 | 2012-11-01 |  |  | 2012-09-14 |  | 2012-10-17 | 2012-10-15 | 2012-11-26 | 2012-11-26 | 2012-11-20 | 2012-11-26 | 2012-11-26 | [8 empty] | 2012-12-01 | 2012-12-12 | 2012-12-06 | 2012-12-26 | 2012-12-14 | 2013-06-26 | 2013-06-26 | GHD to design for new location further up hill. 21/05 TC lease area is designated. 18/6 Colo app submitted 13/6, designated authority requested. Telecom Colo approved 19/7. Tx - MW solution. Team Talk co-siting app sent 1/8 - Team talk approval recived |  | 2012-11-23 | 2012-09-29 | 2012-09-29 | 2012-10-15 | 2012-11-13 | 2012-11-01 | 2012-11-01 | 2012-11-20 |  | 2012-11-28 | 2012-11-28 | 2012-06-05 | LOW | KAIKOURA | 2012-11-20 | 2012-11-26 | BUILD | 2012-11-20 | TRUE | 2012-09-14 | 2566983 | 5865212 | off Maui Street, Peninsula, Kaikoura |  | In a significant landscape area and exceeds height of 12m within that landscape. - 05/06/2012 | CELLSITE | [15 empty] | 2012-12-07 | 2012-12-07 | 2012-04-10
South Island | CAN | 687 | CAN-064-005 | Washdyke | CAN-064-005-D | Washdyke John Jones | Timaru | 4 | TIER_3 | ACTIVE | GF | DU | SP |  | STACK_A | STANDALONE | 35 | 35 | 1 | -44.3537 | 171.244 | 2010-05-27 | 2011-12-21 | 2010-06-24 | 2012-11-11 | Microwave | CAN-064-007-D | FALSE | FALSE | 2010-05-27 | 2010-05-27 | FALSE | 2012-05-03 | 2012-04-18 | 2012-04-18 | 2012-05-09 | 2012-05-09 | 2012-05-31 | 2012-05-30 | 2 | 2012-05-31 | 2012-09-12 | 2012-07-27 | 2012-07-27 | 2012-08-30 | 2012-08-21 | 1 |  | 2012-08-21 | PERMITTED | 2012-07-27 | 2012-07-11 | 2012-09-10 | 2012-09-11 | 1 |  |  |  |  | 2012-11-02 | 2012-10-30 | 1 |  | 2012-11-02 | 2012-10-30 | 2012-10-23 |  |  | 2012-09-13 |  | 2012-10-11 | 2012-10-11 | 2012-11-16 | 2012-12-03 | 2012-11-14 | 2012-11-22 | 2012-11-26 | [8 empty] | 2012-11-27 | 2012-12-12 | 2012-12-04 | 2012-12-26 | 2012-12-17 | 2013-07-16 | 2013-07-10 | Off Elginshire Rd. 5/6 High fibre costs here. LL response re soil disposal may be required. 18/6 RMA is drafted. Martin to chase LL re terms agreed ongoing. 2/7 SA to progress lease changes with LL. Also push for geotech letter & RMA lodge. 09/07 Vic to follow up response. Early Geotech required. 16/7 In & indemnity clause being discussed. GHD to quote for contamination check. 23/7 Draft Wo2 SA to finalise terms this wk. Submit RMA this week. 30/7 Hail site will need contamination chk. 27/8 PD to show landscaping. 03/09 Needs new PD for planting. |  | 2012-11-26 | 2012-08-28 | 2012-08-28 | 2012-10-31 | 2012-10-11 | 2012-10-25 | 2012-10-23 | 2012-11-15 | 2012-11-19 | 2012-12-03 | 2012-12-03 | 2012-05-01 | LOW | TIMARU |  |  | BUILD | 2012-11-13 | TRUE | 2012-09-13 | 2370007 | 5648952 | Elginshire St Washdyke Timaru |  |  | CELLSITE | [15 empty] | 2012-12-10 | 2012-12-07 | 2012-05-09
South Island | CAN | 688 | CAN-064-006 | Oceanview | CAN-064-006-B | RSR Bridge Road | Timaru | 4 | TIER_3 | ACTIVE | RSR | DU | P4F |  | INLINE | STANDALONE | 15 | 15 | 2 | -44.3711 | 171.2432 | 2010-05-27 | 2012-01-09 | 2010-06-24 | 2012-10-15 | Fibre Optic, Fibre Optic | CAN-064-016-A | FALSE | FALSE | 2010-05-27 | 2010-05-27 | FALSE |  | 2012-03-21 | 2012-03-21 | 2012-04-16 | 2012-04-12 | 2012-05-22 | 2012-05-23 | 2 | 2012-05-22 | 2012-07-31 | 2012-06-12 | 2012-06-05 | 2012-06-12 | 2012-06-14 |  |  | 2012-06-15 | NON_COMPLYING_FULL | 2012-06-22 | 2012-06-24 | 2012-07-25 | 2012-07-18 | 1 |  |  |  |  | 2012-10-03 | 2012-10-05 | 1 |  | 2012-10-03 | 2012-10-05 | 2012-10-04 |  |  | 2012-09-07 |  | 2012-10-04 | 2012-10-04 | 2012-11-09 | 2012-11-08 | 2012-10-19 | 2012-11-27 | 2012-11-27 |  |  |  | 2012-04-05 |  |  |  |  | 2012-12-05 | 2012-12-12 | 2012-12-06 | 2012-12-26 | 2012-12-21 | 2013-07-10 | 2013-07-05 | Can link through to Washdyke if necessary. Telco Notice expires 12/06. Liz to speak to council re discretionary application. 11/06 Roading approval received. Trees - Calder Stewart happy, detail s entered in site base. 09/07 Await RMA approval, sensitive. 16/7 Don't proceed with fibre at present. 23/7 Draft Wo2 this week but boundary to be checked first. GHD to check boundary survey & trees shown in wrong location on PDs. 30/7 Fibre to site. 27/8 Try to pull forward. 03/09 Letter this week. |  | 2012-12-03 | 2012-08-28 | 2012-08-28 | 2012-10-11 | 2012-10-10 | 2012-09-28 | 2012-10-04 | 2012-12-06 | 2012-12-06 | 2012-12-03 | 2012-12-03 | 2012-05-01 | LOW | TIMARU | 2012-11-30 | 2012-12-05 | BUILD | 2012-10-19 | TRUE | 2012-09-07 | 2369978 | 5647018 | Off Bridge Rd Timaru |  | Zoning of adjacent land covers this half of road reserve. Telecommunications not listed within zone and therefore defaults to non-complying - 26/06/2012 | CELLSITE | [7 empty] | 2012-10-04 | [7 empty] | 2012-12-12 | 2012-12-12 | 2012-04-12
South Island | WST | 1719 | WST-056-004 | Greymouth Exchange Tx only | WST-056-004-A | Greymouth Exchange Tx only | Grey District | 4 | TIER_3 | ACTIVE | COLO | TX |  |  |  | COLO |  |  |  | -42.449 | 171.2108 | [6 empty] | FALSE | FALSE |  |  | FALSE |  | 2012-08-03 | 2012-08-03 | 2012-08-17 | 2012-08-23 | 2012-08-17 | 2012-09-06 | 1 | 2012-08-23 | 2012-09-06 | 2012-08-17 | 2012-08-23 | 2012-08-17 | 2012-08-23 |  |  | 2013-03-25 | PERMITTED | 2012-09-30 | 2012-09-14 | 2012-09-30 | 2012-09-14 | 1 |  | 2012-09-03 | [13 empty] | 2012-10-26 | 2012-10-26 | 2012-10-26 | 2012-10-26 | 2012-10-26 | 2012-11-09 | 2012-11-16 | [8 empty] | 2012-11-16 | 2012-12-12 | 2012-11-23 | 2012-12-12 | 2012-12-07 | 2013-07-26 | 2013-07-17 | 30/07 Re-submit cost request to Telecom, quote and footprint received. 10/09 CAB dispatched this wk. | TNZ | 2012-11-09 | [6 empty] | 2012-10-10 | 2012-10-26 |  |  |  |  | TRANSMISSION_ONLY | 2012-10-10 | 2012-11-15 | BUILD | 2012-10-10 | FALSE |  | 2362829 | 5860452 | Guiness Street, Greymouth |  | internal work in Chorus exchange - 14/09/2012 | TXSITE | [15 empty] | 2012-11-09 | 2012-10-31
South Island | CAN | 642 | CAN-059-005 | Rangiora | CAN-059-005-B | Luisetti Seeds | Waimakariri | 8 | TIER_3 | ACTIVE | GF | DU | P2 |  | STACK_A | STANDALONE | 25 | 25 | 1 | -43.3004 | 172.5972 |  |  |  |  | Microwave | CAN-059-006-D | FALSE | FALSE |  |  | FALSE | 2012-03-14 | 2012-02-16 | 2012-02-16 | 2012-03-23 | 2012-03-21 | 2012-06-01 | 2012-05-08 | 2 | 2012-06-01 | 2012-05-30 | 2012-07-13 | 2012-07-13 | 2012-08-01 | 2012-08-06 | 2 |  | 2012-08-06 | LIMITED_NOTIFIED | 2012-07-06 | 2012-07-06 | 2012-08-10 | 2012-07-30 | 2 |  |  |  |  | 2012-10-03 | 2012-10-12 | 1 |  | 2012-10-03 | 2012-10-12 | 2012-10-05 |  |  | 2012-09-13 |  | 2012-10-09 | 2012-10-09 | 2012-11-20 | 2012-11-13 | 2012-10-30 | 2012-11-14 | 2012-11-13 | [8 empty] | 2012-11-20 | 2012-12-14 | 2012-12-04 | 2012-12-14 | 2012-12-18 | 2013-07-30 | 2013-07-17 | RMA recived wk WO2 issued the week of 15th August |  | 2012-11-14 | 2012-08-07 | 2012-08-07 | 2012-11-16 | 2012-10-09 | 2012-10-22 | 2012-10-05 | 2012-11-09 | 2012-11-13 | 2012-11-30 | 2012-11-26 |  | LOW | CHRISTCHURCH_OUTER |  |  | BUILD | 2012-10-29 | TRUE | 2012-09-13 | 2477326 | 5767373 | 2 Edward St Rangiora |  | Discretionary activity, potential for limited notification, however location is ideal and council planner agreed therefore, lodge and wait for council to make decision on affected parties. - 05/06/2012 | CELLSITE |  |  | 2015-04-21 | [12 empty] | 2012-12-12 | 2012-12-12
South Island | CAN | 643 | CAN-059-006 | Southbrook | CAN-059-006-D | Cant Engineering | Waimakariri | 8 | TIER_3 | ACTIVE | GF | DU | T2 25 UF |  | INLINE |  |  | 28 | 1 | -43.3262 | 172.6009 |  |  |  |  | Microwave | CAN-059-008-A | FALSE | FALSE |  |  | FALSE |  |  | 2012-05-02 | 2012-05-21 | 2012-05-21 | 2012-05-30 | 2012-06-26 | 1 | 2012-05-30 | 2012-06-26 | 2012-07-13 | 2012-07-13 | 2012-07-20 | 2012-07-20 | 1 |  | 2012-07-20 | LIMITED_NOTIFIED | 2012-07-06 | 2012-07-06 | 2012-08-10 | 2012-07-30 | 1 |  |  |  |  | 2012-09-28 | 2012-10-08 | 2 | 1 | 2012-09-28 | 2013-09-17 | 2012-10-05 |  |  | 2012-09-12 |  | 2012-10-04 | 2012-10-04 | 2012-11-15 | 2012-11-12 | 2012-10-31 | 2012-11-14 | 2012-11-14 | [8 empty] | 2012-11-15 | 2012-12-14 | 2012-11-26 | 2012-12-14 | 2012-12-18 | 2013-09-20 | 2013-09-30 | Site is critical for Woodend link. RMA Recived all go to go |  | 2012-11-14 | 2012-08-07 | 2012-08-07 | 2012-10-15 | 2012-11-01 | 2012-10-15 | 2012-10-05 | 2012-11-12 | 2012-11-09 | 2012-11-30 | 2012-11-21 |  | MEDIUM | CHRISTCHURCH_OUTER |  |  | BUILD | 2012-10-27 | TRUE | 2012-09-12 | 2477639 | 5764508 | 17 Railway Road Rangiora |  | Located well within an industrial area. Given that it is overheight, limited notification is a possibility, but other than the Transpower lattice tower option this is an ideal location if consent is required. recommended that we lodge and ask Council to make the call on affected parties. Note that the location has moved within this site. - 05/06/2012 | CELLSITE |  |  | 2015-04-21 | [12 empty] | 2012-12-14 | 2012-12-14
South Island | CAN | 684 | CAN-064-002 | Pleasant Point | CAN-064-002-D | Water tanks GF | Timaru | 4 | TIER_3 | ACTIVE | GF | DU | T2 20 RH |  | STACK_A | COSITE | 20 | 20 | 1 | -44.187 | 171.1297 |  | 2012-01-23 |  | 2012-09-03 | Microwave | CAN-064-005-D | FALSE | FALSE |  |  | FALSE | 2012-03-21 | 2012-02-23 | 2012-02-23 | 2012-03-01 | 2012-03-05 | 2012-04-05 | 2012-04-13 | 2 | 2012-04-05 | 2012-05-02 | 2012-05-01 | 2012-05-02 | 2012-06-29 | 2012-07-09 | 1 | 2012-07-20 | 2012-08-06 | CONTROLLED | 2012-05-09 | 2012-05-07 | 2012-06-13 | 2012-05-28 | 2 |  |  | 2012-08-17 |  | 2012-07-27 | 2012-08-28 | 1 |  | 2012-07-27 | 2012-08-28 | 2012-08-16 |  |  |  |  | 2012-08-20 | 2012-08-20 | 2012-09-28 | 2012-09-27 | 2012-09-07 | 2012-11-25 | 2012-11-26 | [8 empty] | 2012-11-27 | 2012-12-14 | 2012-12-03 | 2012-12-14 | 2012-12-12 | 2013-07-12 | 2013-07-10 | LL ok to relocate water pipes. Trees to be trimmed belong to neighbour. 14/05 Lease is signed in Auck. Cosite sent. 11/06 Geotech OK. Martin achieved favourable agreement with LL re trees. Downer to address power - cost required. New party to sign LL agreemt. 16/7 SPM to arrange power audit. 23/7 24/7 Geotech due. Downer doing power audit. 8/8 Build start date. SA to chase tree sign off. 30/7 VF power not feasible. Final LL signature required on Lease. 6/8 Transformer does not need to be upgraded. |  | 2012-11-26 | 2012-06-22 | 2012-06-28 | 2012-09-04 | 2012-09-04 | 2012-08-18 | 2012-08-16 | 2012-09-28 | 2012-09-27 | 2012-11-28 | 2012-11-28 | 2012-02-14 | LOW | TIMARU_ASHBURTON |  |  | BUILD | 2012-09-12 | FALSE |  | 2360481 | 5667270 | Off Spur Hutt Road Nr Pleasant Point Canterbury |  | Telecommunications mast specified as controlled activities within Rural 1 zone, i.e. no permitted activity status possible in this zone. - 26/03/2012 | CELLSITE | [15 empty] | 2012-12-03 | 2012-12-04 | 2012-03-05
South Island | CAN | 686 | CAN-064-004 | Temuka | CAN-064-004-A | Hally Tce Kiwirail GF | Timaru | 4 | TIER_3 | ACTIVE | GF | DU | T2 25 UF |  | INLINE | STANDALONE | 25 | 25 | 1 | -44.2427 | 171.2794 |  | 2011-12-14 |  | 2012-10-05 | Microwave | CAN-064-002-D | FALSE | FALSE |  |  | FALSE | 2012-04-05 | 2012-02-23 | 2012-02-23 | 2012-02-29 | 2012-03-06 | 2012-04-04 | 2012-04-04 | 2 | 2012-04-04 | 2012-04-05 | 2012-06-26 | 2012-06-26 | 2012-07-27 | 2012-07-24 |  |  | 2012-07-24 | CONTROLLED | 2012-06-15 | 2012-06-13 | 2012-07-13 | 2012-07-10 | 2 |  |  |  |  | 2012-10-02 | 2012-10-02 | 1 |  | 2012-10-02 | 2012-10-02 | 2012-09-17 |  |  | 2012-08-28 |  | 2012-09-25 | 2012-09-19 | 2012-10-24 | 2012-10-26 | 2012-10-17 | 2012-11-24 | 2012-11-27 | [8 empty] | 2012-12-03 | 2012-12-14 | 2012-12-05 | 2012-12-28 | 2012-12-18 | 2013-07-10 | 2013-06-26 | Storage depot next to Midland Contracting (Hally Terrace). Height – 25m. 29/05 Jaco to get fibre quote as backup to pleasant point link. Trees @ Pleasant Point priority for this site. Jetvac also required. 16/7 GPR report this week overdue. 23/7 Vic - chase Joelyn for signed agreement. SPM to sort out geotech consent. GPR report now due this week. No set-off point shown on PD's, to be shown on CD's. 30/7 Rob submitted Bore consent as part of a group. New GPR required - GHD. 6/08 Contamination check to be carried out - done.. |  | 2012-12-03 | 2012-07-18 | 2012-07-18 | 2012-09-18 | 2012-09-19 | 2012-09-18 | 2012-09-17 | 2012-10-18 | 2012-10-31 | 2012-12-03 | 2012-12-03 | 2012-03-02 | MEDIUM | TIMARU |  |  | BUILD | 2012-10-05 | TRUE | 2012-08-28 | 2372575 | 5661337 | Opposite 37 Hally Terrace Temuka |  | Activity specified as controlled in Recreation 2 Zone - 02/03/2012 | CELLSITE | [15 empty] | 2012-12-07 | 2012-12-07 | 2012-03-06
South Island | CAN | 690 | CAN-064-008 | Fairview | CAN-064-008-C | Fairview GF | Timaru | 4 | TIER_3 | ACTIVE | GF | DU | T2 25 RH |  | INLINE | STANDALONE | 25 | 25 | 1 | -44.4256 | 171.244 | 2010-05-27 | 2011-12-21 | 2010-06-24 | 2012-08-31 | Microwave | CAN-064-007-D | FALSE | FALSE | 2010-05-27 | 2010-05-27 | FALSE | 2012-03-21 | 2012-03-21 | 2012-03-20 | 2012-03-29 | 2012-03-29 | 2012-05-18 | 2012-05-21 | 2 | 2012-05-18 | 2012-05-31 | 2012-06-05 | 2012-06-01 | 2012-09-05 | 2012-09-06 | 1 |  | 2012-09-06 | CONTROLLED | 2012-06-06 | 2012-06-06 | 2012-07-12 | 2012-06-22 | 2 |  |  | 2012-09-03 |  | 2012-09-06 | 2012-09-24 | 1 |  |  | 2012-09-24 | 2012-09-04 |  |  |  |  | 2012-09-06 | 2012-09-06 | 2012-11-02 | 2012-11-05 | 2012-09-28 | 2012-11-01 | 2012-11-01 |  |  |  | 2012-06-18 |  |  |  |  | 2012-11-09 | 2012-12-14 | 2012-12-06 | 2012-12-14 | 2012-12-18 | 2013-09-27 | 2013-09-20 | Colo doesn't work due to interference, now GF at 25m. 5/6 LL lease in legal review. Telecom & Vf co-siting sent 12/6. 18/6 Legal docs with LL legal awaiting Telecom response. 26/SPM chasing Telecom re interference. 2/7 Chase Telecom co-siting response again. 09/07 Lse execution on hold, LL wants confirmation that no interference to Telecom. 23/7 SPM to talk to Jason re Telecom co-siting response. 30/7 Jason chasing T/C co-site response. 27/8 Requires 2 x killer filters - ordered. 10/09 Jaco to investigate fibre connection. |  | 2012-11-09 | 2012-07-18 | 2012-07-18 | 2012-09-12 | 2012-09-17 | 2012-09-04 | 2012-09-04 | 2012-11-01 | 2012-11-01 | 2012-11-10 | 2012-11-12 | 2012-02-14 | LOW | TIMARU |  |  | BUILD | 2012-09-27 | FALSE |  | 2370169 | 5640969 | Farm to east of Timaru Pareora Highway Timaru |  | Telecommunications mast specified as controlled activities within Rural 1 zone, i.e. no permitted activity status possible in this zone. - 26/03/2012 | CELLSITE | [15 empty] | 2012-12-13 | 2012-12-14 | 2012-03-29
South Island | WST | 1717 | WST-056-002 | Greymouth | WST-056-002-B | Greymouth Plumbers | Grey District | 4 | TIER_3 | ACTIVE | GF | DU | P2 |  | INLINE | STANDALONE |  |  |  | -42.45 | 171.2033 | [6 empty] | FALSE | FALSE |  |  | FALSE |  | 2012-03-08 | 2012-03-07 | 2012-03-15 | 2012-03-14 | 2012-05-11 | 2012-05-10 | 3 | 2012-05-11 | 2012-10-05 |  | 2012-04-02 | 2012-07-04 | 2012-06-27 | 1 |  | 2012-06-27 | PERMITTED | 2012-07-04 | 2012-07-04 | 2012-07-30 | 2012-07-12 | 2 |  | 2012-07-12 |  |  | 2012-10-23 | 2012-10-19 | 1 |  | 2012-10-23 | 2012-10-19 |  |  |  | 2012-09-14 |  | 2012-10-24 | 2012-10-24 | 2012-11-30 | 2012-12-14 | 2012-11-30 | 2012-12-05 | 2012-12-15 |  | 2012-12-15 | [6 empty] | 2012-12-15 | 2012-12-19 | 2012-12-19 | 2013-01-02 | 2012-12-21 | 2013-06-11 | 2013-05-31 | Requires extra battery cabinet. Better for fibre access. 23/7 Require contamination check. 17/9 Ask Golders for contamination report. 19/12/12 Drive Testing today |  | 2012-11-30 | 2012-08-28 | 2012-08-28 | 2012-11-14 | 2012-11-12 | 2012-11-14 |  | 2012-11-28 | 2012-12-13 | 2012-12-17 | 2012-12-17 | 2012-04-08 | MEDIUM | GREYMOUTH_WESTPORT | 2012-11-30 | 2012-12-15 | BUILD | 2012-11-26 | TRUE | 2012-09-14 | 2362215 | 5860324 | Plumbers Boundary St |  | commercial area, some random houses entwined in land use matrix... quite an open area with limited visual protection from surrounding landuse 20m mast probably ok - 30/01/2012 | CELLSITE | [15 empty] | 2012-12-14 | 2012-12-18
South Island | WST | 1710 | WST-055-001 | Westport Central | WST-055-001-A | Kiwirail GF | Buller District | 4 | TIER_3 | ACTIVE | GF | DU | T2 25 UF |  | INLINE | STANDALONE | 25 | 25 |  | -41.7568 | 171.5979 | [6 empty] | FALSE | FALSE |  |  | FALSE |  | 2012-03-08 | 2012-03-08 | 2012-03-15 | 2012-03-14 | 2012-05-13 | 2012-05-16 | 2 | 2012-05-13 | 2012-06-12 |  | 2012-03-05 | 2012-09-05 | 2012-09-04 | 2 |  | 2012-09-04 | PERMITTED | 2012-08-21 | 2012-08-17 | 2012-09-21 | 2012-09-07 | 2 |  | 2012-09-07 |  |  | 2012-11-05 | 2012-11-19 | 1 |  | 2012-11-05 | 2012-11-19 | 2012-11-11 |  |  | 2012-09-14 |  | 2012-10-29 | 2012-11-01 | 2012-12-11 | 2012-12-14 | 2012-12-06 | 2012-12-10 | 2012-12-14 |  | 2012-12-14 | [6 empty] | 2012-12-14 | 2012-12-20 | 2012-12-20 | 2013-01-02 | 2012-12-20 | 2013-09-13 | 2013-09-10 | May have contamination. Requires extra battery cabinet. 01/05 requires. Early geotech after PD. 21/05 Buller Power Board request 6m distance from lines. . 29/05 RC required for geotech drill. TP to find out recommended supplier for soil analysis & report. Council have no record of land contamination at the site. Lease agreed await decision on commencement and agreed payment start with KR, need lease prior to RC lodge. 16/7 SA check termination clause with KWR. 6/08 Awaiting 176 form from Kiwi Rail. 3/09 Draft Letter. 19/12/12 Drive Testing tomorrow 20/12 |  | 2012-12-13 | 2012-09-11 | 2012-09-11 | 2012-10-12 |  | 2012-11-08 | 2012-11-11 | 2012-12-07 | 2012-12-11 | 2012-12-18 | 2012-12-17 | 2012-01-23 | MEDIUM | GREYMOUTH_WESTPORT | 2012-12-06 | 2012-12-06 | BUILD | 2012-12-06 | TRUE | 2012-09-14 | 2393387 | 5937937 | KiwiRail Adderly Street Westport |  | Kiwi Rail corridor site - adjacent to Commerical - probably a contaminated site - maximum height 25m - probably ok if located near the train station -other option further South are too close to residential - Holcium cemet works rooftop would be a better option and obtain more height (approx. 30m) - 30/01/2012 site will probably not interfere with the street view of the mainstreet at 25m - 30/01/2012 | CELLSITE | [15 empty] | 2012-12-14 | 2012-12-18
South Island | MBN | 1019 | MBN-052-015 | Saxton Field (TX HUB) | MBN-052-015-D | A-37 Packham Cres | Nelson | 7 | TIER_2 | ACTIVE | GF | DU | T2 25 RF |  | STACK_A | COSITE | 24 | 25 | 2 | -41.3204 | 173.2164 |  |  |  |  | Fibre Optic | MBN-052-003-B | FALSE | FALSE |  |  | FALSE |  | 2011-08-22 | 2011-08-22 | 2011-08-29 | 2011-08-23 | 2011-09-09 | 2011-09-12 | 1 | 2011-09-09 | 2011-09-12 | 2011-10-10 | 2011-09-21 | 2011-10-25 | 2011-09-23 | 1 |  | 2011-09-23 | DISCRETIONARY_RESTRICT | 2011-09-19 | 2011-09-19 | 2011-11-01 | 2011-10-03 | 1 |  | 2011-10-03 |  |  | 2011-11-18 | 2011-11-25 | 1 |  | 2011-11-18 | 2011-11-25 | 2011-11-30 |  |  |  |  | 2011-11-30 | 2011-11-30 | 2012-03-16 | 2012-02-27 | 2011-12-08 | 2011-12-14 | 2011-12-21 | [8 empty] | 2011-12-21 | 2012-12-21 | 2011-12-21 | 2012-03-15 | 2012-03-19 | 2013-09-17 | 2013-12-20 | TX equipt due in country Jan 2012 - use temp uW radios. FX Netwrks brownout starts 11 Dec. |  | 2011-12-14 | 2011-11-28 | 2011-11-28 | 2011-12-06 | 2011-12-07 | 2011-11-30 | 2011-11-30 | 2011-12-16 | 2011-12-12 | 2012-01-31 | 2011-12-23 | [5 empty] | BUILD | 2011-12-08 | FALSE |  | 2528102 | 5987348 | 37 Packham Crescent Stoke, NELSON |  |  | CELLSITE | [15 empty] | 2012-02-28 | 2012-03-05 | 2011-08-23
South Island | CAN | 691 | CAN-064-009 | Highfield | CAN-064-009-C | RSR Park GF | Timaru | 4 | TIER_3 | ACTIVE | RSR | DU | P4H |  | INLINE | STANDALONE | 17.5 | 18 | 1 | -44.3906 | 171.2267 | 2010-05-27 | 2012-01-11 | 2010-06-24 | 2012-10-15 | Fibre Optic | CAN-064-016-A | FALSE | FALSE | 2010-05-27 | 2010-05-27 | FALSE |  | 2012-03-21 | 2012-03-20 | 2012-03-29 | 2012-03-30 | 2012-05-15 | 2012-05-16 | 1 | 2012-05-15 | 2012-05-16 | 2012-06-08 | 2012-06-05 | 2012-06-11 | 2012-06-11 | 1 |  | 2012-06-13 | CONTROLLED | 2012-06-08 | 2012-06-05 | 2012-07-05 | 2012-06-22 | 1 |  |  | 2012-08-22 |  |  | 2012-10-03 | 1 |  | 2012-10-03 | 2012-10-03 | 2012-09-26 |  |  | 2012-08-28 |  | 2012-10-04 | 2012-09-25 | 2012-10-29 | 2012-10-29 | 2012-10-15 | 2012-11-03 | 2012-11-05 | [8 empty] | 2012-11-12 | 2013-01-15 | 2013-01-14 | 2013-01-17 | 2013-01-17 | 2013-07-10 | 2013-06-27 | 19/12/12 Power still required |  | 2012-11-08 | 2012-08-06 | 2012-08-06 | 2012-09-18 | 2012-09-18 | 2012-09-26 | 2012-09-26 | 2012-12-17 | 2012-12-19 | 2012-11-12 | 2012-11-13 | 2012-02-14 | MEDIUM | TIMARU | 2012-11-02 | 2012-11-02 | BUILD | 2012-10-15 | TRUE | 2012-08-28 | 2368715 | 5644827 | RSR outside West End Park Wai-iti Road |  | Telecommunications mast specified as controlled activities within Recreation 2 zone, i.e. no permitted activity status possible in this zone. Council won't allow LP swap outs and RF needs additional height in this location anyway. - 26/03/2012 | CELLSITE | [15 empty] | 2012-12-18 | 2012-12-21 | 2012-03-30
South Island | CAN | 692 | CAN-064-010 | Waimataitai | CAN-064-010-E | Maori Park RSR | Timaru | 4 | TIER_3 | ACTIVE | RSR | DU | P4F |  | INLINE | STANDALONE | 15 | 15 | 1 | -44.3852 | 171.2424 |  | 2012-01-10 |  | 2012-11-23 | Fibre Optic | CAN-064-016-A | FALSE | FALSE |  |  | FALSE |  | 2012-04-18 | 2012-04-18 | 2012-05-01 | 2012-04-26 | 2012-05-23 | 2012-05-24 | 2 | 2012-05-23 | 2012-09-04 | 2012-06-16 | 2012-06-05 | 2012-06-11 | 2012-06-14 | 1 |  | 2012-06-15 | CONTROLLED | 2012-07-12 | 2012-07-10 | 2012-09-12 | 2012-09-07 | 2 |  |  |  |  | 2012-11-12 | 2012-11-12 | 1 |  | 2012-11-12 | 2012-11-12 | 2012-11-01 |  |  | 2012-09-13 |  | 2012-11-02 | 2012-11-01 | 2012-12-07 | 2012-12-12 | 2012-11-19 | 2012-12-05 | 2012-12-07 | [8 empty] | 2012-12-12 | 2013-01-15 | 2012-12-17 | 2013-01-15 | 2012-12-20 | 2013-09-02 | 2013-09-16 | 15m pole might be sensitive. Vic to contact PUB as backup. 07/05 Pub would mean fibre for TX. Submit this RC last. 5/6 GPR to be done, chase!. Telco Act Notice expires 15/6. Reasonable fibre quote received in old location. Chase. 23/7 GHD to check boundary. SA & TP to talk to council re pavement layout. Jaco - fibre chase quote. Await full GPR report. 13/8 Fibre to be ordered. Update PD. |  | 2012-12-12 | 2012-09-04 | 2012-09-04 | 2012-11-16 | 2012-11-14 | 2012-11-01 | 2012-11-01 | 2012-12-04 | 2012-12-07 | 2012-12-07 | 2012-12-14 | 2012-05-01 | HIGH | TIMARU | 2012-11-23 | 2012-12-03 | BUILD | 2012-11-17 | TRUE | 2012-09-13 | 2369951 | 5645446 | Cnr of Benvenue Ave & Te Weka St Maori Hill Timaru |  | Telecommunications listed as controlled in this zone - 01/05/2012 | CELLSITE | [15 empty] | 2012-12-18 | 2012-12-14 | 2012-04-26
South Island | CAN | 667 | CAN-062-013 | Prebbleton | CAN-062-013-A | Prebbleton Shops | Selwyn District | 8 | TIER_3 | ACTIVE | GF | DU | P2 |  | INLINE | STANDALONE | 20 | 20 | 1 | -43.5805 | 172.5134 |  | 2012-01-23 |  |  | Fibre Optic | CHC-060-114-A | FALSE | FALSE |  |  | FALSE |  | 2012-02-14 | 2012-02-14 | 2012-02-22 | 2012-02-22 | 2012-06-01 | 2012-06-06 | 3 | 2012-06-01 | 2012-08-17 | 2012-08-17 | 2012-08-16 | 2012-09-14 | 2012-09-14 | 2 |  | 2012-09-14 | PERMITTED | 2012-08-24 | 2012-08-09 | 2012-09-10 | 2012-08-23 | 3 |  |  |  |  | 2012-10-25 | 2012-12-13 | 1 |  | 2012-10-25 | 2012-12-13 | 2012-11-14 |  |  | 2012-09-27 |  | 2012-11-20 | 2012-11-20 | 2012-12-14 | 2012-12-19 | 2012-12-10 | 2013-01-11 | 2013-01-11 | [8 empty] | 2013-01-22 | 2013-01-25 | 2013-01-24 | 2013-02-22 | 2013-02-25 | 2013-10-04 | 2013-10-21 | Option 1 at boundary edge or option 2 within carpark area. 05/03 Slimeline pole can be used. LOS done. 16/04 B/U is 18m RSR. 23/04 Photomontages to be reviewed. TP to prepare CoC with Vic. 29/05 Pile size depends on Geotech. PDs to be corrected and issued asap. approx 20cubic meters of soil to be moved. TP to check conditions. 26/6 Legal review. Martin to chase up 03/07. 02/07 RMA drafted. |  | 2013-01-14 | 2012-09-04 | 2012-09-04 | 2012-11-21 | 2012-11-26 | 2012-11-15 | 2012-11-14 | 2013-01-11 | 2013-01-11 | 2013-01-24 | 2013-01-23 |  |  | CHRISTCHURCH_OUTER | 2012-12-06 | 2013-01-09 | BUILD | 2012-12-08 | TRUE | 2012-09-27 | 2470710 | 5736215 | Prebbleton Shops Springs Rd |  | at 20m it complies - 05/06/2012 | CELLSITE |  |  | 2015-10-15 | [12 empty] | 2013-02-08 | 2013-02-15
South Island | CAN | 693 | CAN-064-011 | Glenwood | CAN-064-011-D | Aorangi Park RSR | Timaru | 4 | TIER_3 | ACTIVE | RSR | DU | P4H |  | INLINE | STANDALONE | 18 | 18 | 1 | -44.3836 | 171.2102 | 2010-05-27 | 2012-01-10 | 2010-06-24 | 2012-10-24 | Fibre Optic | CAN-064-016-A | FALSE | FALSE | 2010-05-27 | 2010-05-27 | FALSE |  | 2012-03-21 | 2012-03-21 | 2012-03-28 | 2012-03-28 | 2012-05-31 | 2012-05-31 | 1 | 2012-05-31 | 2012-05-31 | 2012-06-22 | 2012-06-05 | 2012-06-22 | 2012-06-14 | 1 |  | 2012-06-15 | CONTROLLED | 2012-06-08 | 2012-06-11 | 2012-07-12 | 2012-07-05 | 1 |  |  | 2012-08-24 |  | 2012-10-02 | 2012-10-03 | 1 |  | 2012-10-02 | 2012-10-03 | 2012-10-03 |  |  | 2012-08-28 |  | 2012-09-25 | 2012-09-25 | 2012-10-23 | 2012-10-24 | 2012-10-17 | 2013-01-11 | 2013-01-11 | [8 empty] | 2013-01-15 | 2013-01-25 | 2013-01-21 | 2013-02-22 | 2013-02-25 | 2013-06-21 | 2013-06-19 | LPR off Morgan Road, adjacent to Aorangi Park. RF want floodlights height ideally. Space available, resi close by. 21/05 revisit complete. Keep TX below RF at this stage. 11/06 TX will be with fibre solution. Telco notice expired. GPR 11/7, Francis to chase. 09/07 Jetvac may be required. 23/7 SPM to check GPR. Await full report. Letter drop to do. |  | 2013-01-15 | 2012-07-23 | 2012-07-23 | 2012-09-18 | 2012-09-18 | 2012-09-18 | 2012-10-03 | 2012-12-07 | 2012-12-19 | 2013-01-18 | 2013-01-17 | 2012-02-14 | MEDIUM | TIMARU | 2013-01-10 | 2013-01-10 | BUILD | 2012-10-17 | TRUE | 2012-08-28 | 2367382 | 5645569 | Adjacent to Aorangi Park Off Morgans Road Timaru |  | Telecommunications mast specified as controlled activities within Recreation 2 zone, i.e. no permitted activity status possible in this zone. Council won't agree to LP swap out in order to be permitted under NES - 26/03/2012 | CELLSITE | [15 empty] | 2013-02-08 | 2013-02-11 | 2012-03-28
South Island | MBN | 1021 | MBN-052-017 | Nelson Haven | MBN-052-017-B | 305 Akersten St | Nelson | 7 | TIER_3 | ACTIVE | GF | DU | P4H |  | STACK_A | STANDALONE | 14.7 | 16.3 | 1 | -41.2542 | 173.2841 |  |  |  |  | Microwave | MBN-052-003-B | FALSE | FALSE |  |  | FALSE |  | 2012-06-18 | 2012-06-18 | 2012-06-25 | 2012-06-22 | 2012-08-03 | 2012-08-06 | 1 | 2012-08-03 | 2012-08-06 | 2012-08-17 | 2012-08-17 | 2012-09-21 | 2012-09-19 | 1 | 2012-09-21 | 2012-09-19 | PERMITTED | 2012-08-03 | 2012-08-07 | 2012-09-14 | 2012-09-10 | 1 | 2012-09-14 | 2012-09-14 |  |  | 2012-11-14 | 2012-11-13 | 1 |  | 2012-11-14 | 2012-11-13 |  |  |  | 2012-10-02 |  | 2012-10-31 | 2012-10-30 | 2012-12-03 | 2012-12-03 | 2012-12-04 | 2012-12-06 | 2012-12-06 | [8 empty] | 2012-12-17 | 2013-01-25 | 2013-01-24 | 2013-01-15 | 2012-12-20 | 2013-09-10 | 2013-10-18 | 21/12/12 - PAC signed by 2 D although site is not on air - 2 Degrees have left the COW running over the Xmas / NY break and site to be placed on air in Jan 2013 |  | 2012-12-07 |  |  |  |  | 2012-11-16 |  | 2012-12-06 |  | 2012-12-17 | 2012-12-18 | 2012-06-21 | MEDIUM | NELSON_OUTER |  |  | BUILD | 2012-12-04 | TRUE | 2012-10-02 | 2533795 | 5994684 | 305 Akersten St Nelson Haven |  |  | CELLSITE | [15 empty] | 2012-12-19 | 2012-12-19 | 2012-06-22
South Island | CAN | 696 | CAN-064-014 | Watlington | CAN-064-014-A | Quarry Rd RSR | Timaru | 4 | TIER_3 | ACTIVE | RSR | DU | P4J |  | INLINE | STANDALONE | 12.5 | 12.5 | 1 | -44.4029 | 171.2301 |  | 2013-06-29 |  | 2012-08-31 | Microwave | CAN-064-007-D | FALSE | FALSE |  |  | FALSE | 2012-06-18 | 2012-03-21 | 2012-03-20 | 2012-03-28 | 2012-03-29 | 2012-05-15 | 2012-05-21 | 2 | 2012-05-15 | 2012-06-15 | 2012-06-12 | 2012-06-05 | 2012-06-12 | 2012-06-14 | 1 |  | 2012-06-15 | CONTROLLED | 2012-06-08 | 2012-06-11 | 2012-07-12 | 2012-07-05 | 2 |  |  | 2012-08-22 |  | 2012-09-28 | 2012-09-26 | 1 |  | 2012-09-28 | 2012-09-26 | 2012-09-17 |  |  | 2012-08-20 |  | 2012-09-25 | 2012-09-25 | 2013-01-16 | 2013-01-18 | 2012-12-12 | 2013-01-17 | 2013-01-18 |  |  |  | 2012-06-18 |  |  |  |  | 2013-01-23 | 2013-01-29 | 2013-01-29 | 2013-02-12 | 2013-02-11 | 2013-06-11 | 2013-06-06 | Quarry Rd RSR not LPR. Transformer adjacent. School close by off Quarry Rd. 14/05 boundary survey completed, revised results received 11/6. 29/05 Telco Notice due 12/06. 18/6 Rev 2 issued - new boundary shown. GPR results due by 11/7. 09/07 Letter drops required 20 wking days pre-const. Jetvac may be required. 23/7 No GPR yet, chase full report. 6/08 Downer to slit trench. Determine if Alpine Energy will allow cables to be moved. |  | 2013-01-20 | 2012-07-23 | 2012-07-23 | 2012-09-18 | 2012-09-21 | 2012-09-18 | 2012-09-17 | 2013-01-16 | 2013-01-18 | 2013-01-22 | 2013-01-22 | 2012-02-14 | MEDIUM | TIMARU |  |  | BUILD | 2012-12-10 | TRUE | 2012-08-20 | 2369011 | 5643464 | Quarry Road Timaru |  | Telecommunications mast specified as controlled activities within Residential 1 zone, i.e. no permitted activity status possible in this zone. TDC won't agree to LP swap out in order for permitted activity under NES - 26/03/2012 | CELLSITE | [15 empty] | 2013-01-23 | 2013-01-29 | 2012-03-29
South Island | CAN | 666 | CAN-062-012 | Dunsandel | CAN-062-012-A | Synlait | Selwyn District | 8 | TIER_3 | ACTIVE | RT | DF | RT |  | INLINE | STANDALONE | 37 | 37 | 1 | -43.6911 | 172.1198 |  | 2011-12-21 |  |  | Fibre Optic | CHC-060-114-A | FALSE | FALSE |  |  | FALSE |  | 2012-02-14 | 2012-02-14 | 2012-02-22 | 2012-02-22 | 2012-05-26 | 2012-05-31 | 2 | 2012-05-26 | 2012-06-27 | 2012-08-10 | 2012-08-16 | 2012-09-14 | 2012-09-13 | 1 |  | 2012-09-13 | DISCRETIONARY_FULL | 2012-09-10 | 2012-09-10 | 2012-10-15 | 2012-10-04 | 2 |  |  |  |  | 2012-10-25 | 2012-12-20 | 1 |  | 2012-10-25 | 2012-12-20 | 2012-11-09 |  |  |  |  | 2012-12-03 | 2012-12-03 | 2012-12-21 | 2012-12-21 | 2012-12-07 | 2012-12-20 | 2012-12-18 |  |  |  | 2012-06-13 |  |  |  |  | 2013-01-18 | 2013-01-30 | 2013-01-25 | 2013-02-12 | 2013-02-18 | 2013-09-13 | 2013-08-27 | PDs overdue. Rails/brackets fixing to building to be confirmed. Is it possible to weld? SA to find out 29/05 PDs said to have been issued but not showing in sitebase and team doesn't have copies. - NT to follow up. 26/6 Martin to adv Lease negotiations update nxt wk. |  | 2013-01-15 | 2012-09-04 | 2012-09-04 | 2012-11-09 | 2012-11-20 | 2012-11-09 | 2012-11-09 | 2012-12-12 | 2012-12-10 | 2013-01-24 | 2013-01-23 |  | LOW | CHRISTCHURCH_OUTER | 2012-12-06 | 2012-12-20 | BUILD | 2012-12-07 | TRUE |  | 2439054 | 5723662 | Frasers Rd |  | ideal location as absorbed by the scale of the synlait building. Consent still required but can argue no affected parties. - 05/06/2012 | CELLSITE | [15 empty] | 2013-01-31 | 2013-02-04
South Island | CAN | 658 | CAN-062-004 | Leeston | CAN-062-004-C | Ellesmere Transport | Selwyn District | 8 | TIER_3 | ACTIVE | GF | DU | SP |  | INLINE | STANDALONE |  | 30 | 1 | -43.7639 | 172.3011 |  |  |  |  | Microwave | CAN-062-012-A | FALSE | FALSE |  |  | FALSE | 2012-03-13 | 2012-02-29 | 2012-02-29 | 2012-03-06 | 2012-03-08 | 2012-05-24 | 2012-05-25 | 1 | 2012-05-24 | 2012-05-25 | 2012-06-08 | 2012-06-07 | 2012-06-15 | 2012-06-15 | 1 |  | 2012-06-15 | LIMITED_NOTIFIED | 2012-06-07 | 2012-06-08 | 2012-07-15 | 2012-07-09 | 1 |  |  |  |  | 2012-10-25 | 2012-11-09 | 1 |  | 2012-10-25 | 2012-11-09 | 2012-11-22 |  |  | 2012-09-27 |  | 2012-11-13 | 2012-11-12 | 2012-12-12 | 2012-12-19 | 2012-12-08 | 2013-01-07 | 2012-12-21 | [8 empty] | 2013-01-21 | 2013-02-07 | 2013-02-07 | 2013-02-22 | 2013-02-25 | 2013-09-13 | 2013-09-10 | This site will have a exploreatary contamination test done to establish the levels of contamination Based on this a MOP will be established to deal with the next step if any This site is reliant on the Synlait 012 site to go to WO2 |  | 2013-01-16 | 2012-09-04 | 2012-09-04 | 2012-11-15 | 2012-11-26 | 2012-11-14 | 2012-11-22 | 2012-12-13 | 2012-12-28 | 2013-01-25 | 2013-01-28 |  | LOW | CHRISTCHURCH_OUTER |  |  | BUILD | 2012-12-06 | TRUE | 2012-09-27 | 2453733 | 5715716 | Ellesmere Transport 12 Station Rd Leeston |  | ideal industrial location at industrial/rural interface, however due to height increase (5m above/30m tower) limited notification potential. No other location in leeston other than this particular industrial area is however appropriate for a 30m tower. - 05/06/2012. Also note contaminated site. - 08/06/2012 | CELLSITE | [15 empty] | 2013-01-08 | 2013-02-12
South Island | CAN | 719 | CAN-068-004 | Oamaru Outer | CAN-068-004-A | VF colo | Waitaki District | 4 | TIER_3 | ACTIVE | COLO | DU | COLO |  | INLINE | COLO | 20 | 20 |  | -45.1166 | 170.9683 |  |  |  |  | Fibre Optic | CAN-064-016-A | FALSE | FALSE |  |  | FALSE |  | 2012-03-22 | 2012-03-22 | 2012-05-01 | 2012-05-01 | 2012-06-01 | 2012-06-12 | 3 | 2012-06-11 | 2015-08-06 |  | 2012-04-18 | 2012-08-30 | 2012-08-10 | 1 |  | 2012-09-28 | PERMITTED | 2012-06-08 | 2012-06-13 | 2012-07-13 | 2012-06-25 | 1 |  |  |  |  | 2012-10-01 | 2012-10-02 | 4 |  | 2012-10-01 | 2015-10-05 | 2012-10-18 |  |  |  |  | 2012-11-06 | 2012-11-06 | 2013-01-25 | 2013-01-25 | 2012-11-21 | 2013-01-24 | 2013-01-27 | [8 empty] | 2013-02-01 | 2013-02-12 | 2013-02-13 | 2013-02-18 | 2013-02-18 | 2013-08-23 | 2013-08-12 | Permitted <25m. Passed structural check. 14/05 Send rev0 to VF to get a response on space availability. 21/05 Antenna VF Future requirements. 11 Jun - colo and cosite apps lodged. 02/07 Vf colo required for Lease. VF colo approved, site may be moved into build for year now. 16/7 Wo2 to be issued this week. 13/8 Awaiting signed paperwork from Vf. 10/09 Can be operational without central. Requirement to paint pole caused Downer a significant delay. | VNZ | 2013-01-25 | 2012-08-28 | 2012-08-28 | 2012-10-10 | 2012-10-11 | 2012-10-10 | 2012-10-18 | 2012-12-10 | 2012-12-20 | 2013-01-29 | 2013-02-01 |  |  | OAMARU | 2012-11-21 | 2012-11-21 | BUILD | 2012-11-21 | FALSE |  | 2350087 | 5563707 | Off Bushy Beach Road Oamaru |  | permitted if < 30m - 17/05/2012 | CELLSITE |  |  | 2015-10-20 | [12 empty] | 2013-01-31 | 2013-02-04
South Island | CAN | 724 | CAN-068-009 | Oamaru Central | CAN-068-009-A | RSR Dee/Thames | Waitaki District | 4 | TIER_3 | ACTIVE | RSR | DU | P4E |  | INLINE | STANDALONE | 15 | 15 |  | -45.0945 | 170.9724 | [6 empty] | FALSE | FALSE |  |  | FALSE |  | 2012-03-22 | 2012-03-22 | 2012-03-27 | 2012-03-27 | 2012-06-28 | 2012-08-03 | 5 | 2012-07-31 | 2015-05-08 | 2012-09-07 | 2012-04-02 | 2012-09-17 | 2012-09-14 | 1 |  | 2012-09-14 | DISCRETIONARY_FULL | 2012-09-11 | 2015-06-12 | 2012-10-26 | 2015-06-12 | 5 |  |  |  |  | 2012-11-28 | 2012-11-30 | 1 |  | 2012-11-28 | 2012-11-30 | 2012-12-01 |  |  | 2012-11-06 |  | 2013-01-07 | 2013-01-08 | 2013-01-18 | 2013-01-18 | 2013-01-18 | 2013-01-22 | 2013-01-22 | [8 empty] | 2013-01-31 | 2013-02-13 | 2013-02-12 | 2013-02-21 | 2013-02-21 | 2013-10-04 | 2013-12-18 | Telco Act plus agreement with NZTA. Underground services to be meticulously investigated, pole may need to move slightly away from kerb. Extra GPR for opposite side of the road + boundary survey. Jetvac also required before PD - SPM. Do not lodge until we have Lease. GPR carried out 9 Jul. 16/7 Jetvac required. 16/7 RF will only agree to this site if alternatives not possible. 23/7 Check shroud size & cross arms for PD mast now 15.5m. 13/8 Drawings with NZTA could take 5wks for agreement 176 requested. 17/9 Still need 176 to complete RMA. |  | 2013-01-31 | 2012-08-28 | 2012-08-28 | 2012-10-10 | 2012-11-28 | 2012-10-10 | 2012-12-01 | 2013-01-25 |  | 2013-01-28 | 2013-02-08 | 2012-04-08 | MEDIUM | OAMARU | 2012-12-18 | 2013-01-29 | BUILD | 2013-01-18 | TRUE | 2012-11-05 | 2350351 | 5566168 | Corner of Thames St and Dee St |  |  | CELLSITE |  |  | 2015-10-20 |  |  |  |  | 2012-11-08 | [7 empty] | 2013-02-08 | 2013-02-07
South Island | CAN | 685 | CAN-064-003 | Geraldine | CAN-064-003-B | Geraldine Colo | Timaru | 4 | TIER_3 | ACTIVE | COLO | DF | COLO |  | INLINE | COLO |  | 40 | 2 | -44.0901 | 171.2724 |  | 2012-01-10 |  | 2012-08-31 | Microwave | CAN-063-006-A | FALSE | FALSE |  |  | FALSE |  | 2012-04-18 | 2012-04-18 | 2012-04-28 | 2012-05-01 | 2012-05-30 | 2012-05-31 | 2 | 2012-05-30 | 2012-07-13 | 2012-08-30 | 2012-09-03 | 2012-11-02 | 2012-10-30 |  |  | 2012-11-13 | CONTROLLED | 2012-07-27 | 2012-07-31 | 2012-08-30 | 2012-08-27 | 2 |  |  |  |  | 2012-11-27 | 2012-12-07 | 1 |  | 2012-11-27 | 2012-12-07 | 2013-01-16 |  |  |  |  | 2012-12-12 | 2012-12-19 | 2013-01-23 | 2013-01-27 | 2012-12-20 | 2013-01-31 | 2013-02-02 | [8 empty] | 2013-02-02 | 2013-02-14 | 2013-02-14 | 2013-03-07 | 2013-03-07 | 2013-08-13 | 2013-08-16 | 16/04 5m extension required. Good linking option for TX. 01/05 Requires LOS. TP to discuss this option with Council. SA to check power source. Tenure to be sorted asap. Link to PleasantPoint and Ealing not Cavendish. Colo Application submitted 8/6. High fibre pricing recieved. 2/7 SA to chase affected party signoff for RMA. Colo decision due next week. 09/07 Colo appln appvd on basis of move cabinets. LL sold site to Clearspan. Vic to speak w LL. 16/7 Rev2 to be sent 16/7 - Vic. Draft RMA & lodge this week-ongoing. 23/7 SPM to check tower - manufacturer. Affected party consent - Vic to talk to John W APA will hold up RMA. 13/8 Monitor progress of Vf documentation. 20/8 Spk to Liz with regards to Vf Documentation. Chk for Vf Colo apprvd. | VNZ | 2013-01-31 | 2012-09-04 | 2012-09-04 | 2012-11-19 | 2012-11-26 | 2012-12-14 | 2013-01-16 | 2013-01-31 | 2013-02-07 | 2013-02-10 | 2013-02-12 | 2012-05-01 | LOW | TIMARU_ASHBURTON |  |  | BUILD | 2012-12-12 | FALSE |  | 2371665 | 5678282 | Off Orari Back Road Geraldine |  | Telecommunications listed as controlled in this zone, even though a colo - 01/05/2012 | CELLSITE | [15 empty] | 2013-02-08 | 2013-02-12 | 2012-05-01
0 | CHC | 726 | CHC-060-001 | South City | CHC-060-001-G | South City | Christchurch City |  | TIER_1_ALL | ACTIVE | RT | B | NOPOLE | grey |  |  | 11.7 | 11.7 |  | -43.5369 | 172.6339 |  |  |  |  | Microwave, Microwave | CHC-060-012-A, CHC-060-012-A | [5 empty] | 2008-12-17, 2008-12-17 | [5 empty] | 2007-08-17 | 5 | 2007-10-29 | 2011-05-12 |  |  | 2007-10-05 | 2007-10-05 | 4 | 2007-10-05 | 2007-10-05 | [6 empty] | 2008-08-28 | 2008-08-20 |  | 2008-01-21 |  | 2008-03-01 | 3 | 4 | 2008-04-28 | 2008-04-28 | [6 empty] | 2008-05-20 | 2008-05-30 | 2008-05-30 |  | 2008-06-24 | 2008-07-11 | [8 empty] | 2008-12-24 | 2008-12-31 | 2008-12-24 | [6 empty] | 2008-12-17 | [17 empty] | FALSE |  | 2480424 | 5741106 | Vino Fino 188 Durham Street North Christchurch |  |  | CELLSITE |  |  | 2015-10-21 | [5 empty] | 2008-04-16 | [8 empty] | 2007-07-24
0 | CHC | 727 | CHC-060-002 |  | CHC-060-002-C | City West | Christchurch City |  | TIER_1_ALL | ACTIVE | RT | B | NOPOLE | grey |  | COSITE | 21.8 | 21.8 |  | -43.5339 | 172.6351 |  |  |  |  | Microwave, Microwave | CHC-060-065-G, CHC-060-065-G | [5 empty] | 2009-03-18, 2009-03-18 | [5 empty] | 2008-04-18 | 3 | 2008-11-19 | 2009-06-18 |  |  | 2009-02-05 | 2009-02-09 | 2 | 2009-02-05 | 2009-02-09 | [6 empty] | 2008-12-12 | 2008-12-12 |  | 2008-04-28 |  | 2008-06-28 | 3 | 3 | 2009-01-27 | 2009-06-19 | [5 empty] | 2009-02-23 | 2009-03-05 | 2009-03-31 | 2009-03-31 |  | 2009-05-29 | 2009-05-22 | [8 empty] | 2009-05-27 | 2009-05-29 | [5 empty] | Site was off air after earthquakes, but recommissioned in August 2013 Site decommissioned 07 Dec 2014, with equipment/site reloccated to CHC-060-150 |  | 2009-05-29 | [15 empty] | BUILD |  | FALSE |  | 2480515 | 5741443 | Council owned carpark 29-33 Lichfield St Christchurch |  |  | CELLSITE |  |  |  |  | 2014-12-07 |  |  | 2009-03-02 | 2009-02-10 | [8 empty] | 2008-03-04
0 | CHC | 728 | CHC-060-003 |  |  |  | Christchurch City |  | TIER_1_ALL
0 | CHC | 729 | CHC-060-004 |  | CHC-060-004-C | Moorhouse | Christchurch City |  | TIER_1_ALL | ACTIVE | GF | A | P3 | grey |  |  | 25 | 25 |  | -43.5407 | 172.6496 |  |  |  |  | Fibre Optic, Fibre Optic | CHC-060-013-A, CHC-060-013-A | [5 empty] | 2008-12-19, 2008-12-19 | [5 empty] | 2007-09-12 | 9 | 2007-10-29 | 2013-06-28 |  |  | 2008-06-30 | 2008-06-30 | 4 | 2008-06-30 | 2008-06-30 | [6 empty] | 2008-03-20 | 2008-03-20 |  | 2008-03-31 |  | 2008-05-19 | 6 |  | 2008-07-18 | 2011-10-18 | [6 empty] | 2008-08-08 | 2008-10-30 | 2008-10-30 |  | 2008-11-14 | 2008-11-14 | [8 empty] | 2008-12-11 | 2008-12-29 | 2008-12-11 | [6 empty] | 2008-12-15 | [17 empty] | FALSE |  | 2481695 | 5740694 | Hire Quip 488 Moorhouse Ave Christchurch |  |  | CELLSITE |  |  | 2015-10-29 | [5 empty] | 2008-08-01 | [8 empty] | 2007-08-14
0 | CHC | 730 | CHC-060-005 |  | CHC-060-005-D | Fitzgerald | Christchurch City |  | TIER_1_ALL | ACTIVE | GF | A | P2 | grey |  |  | 20 | 20 |  | -43.5343 | 172.6513 |  |  |  |  | Microwave, Microwave | CHC-060-097-A, CHC-060-097-A | [5 empty] | 2007-10-15, 2007-10-15 |  |  |  |  | 2007-09-05 | 2007-09-05 | 7 | 2007-10-29 | 2015-09-03 |  |  | 2008-08-29 | 2008-08-29 | 5 | 2008-08-29 | 2008-08-29 |  | 2008-08-08 |  |  |  |  | 2008-09-05 | 2008-09-05 |  | 2008-03-31 |  | 2008-08-26 | 1 | 5 | 2008-08-26 | 2008-08-26 | 2008-11-26 | [5 empty] | 2008-10-13 | 2008-12-12 | 2008-12-15 |  | 2008-12-24 | 2008-12-22 | [8 empty] | 2008-12-22 | 2008-12-31 | 2008-12-22 | [6 empty] | 2008-12-23 | [5 empty] | 2008-11-26 | [11 empty] | FALSE |  | 2481828 | 5741398 | Idiens Ltd 7 Livingstone Street Christchurch |  |  | CELLSITE |  |  | 2015-10-21 | [5 empty] | 2008-09-10 | [8 empty] | 2007-07-24
0 | CHC | 731 | CHC-060-006 |  |  |  | Christchurch City |  | TIER_1_ALL
0 | CHC | 732 | CHC-060-007 |  |  |  | Christchurch City |  | TIER_1_ALL
0 | CHC | 733 | CHC-060-008 |  | CHC-060-008-H | Salisbury | Christchurch City |  | TIER_1_ALL | ACTIVE | GF | A | P2 | grey |  |  | 20 | 20 |  | -43.5236 | 172.6406 |  |  |  |  | Microwave | CHC-060-005-D | [5 empty] | 2009-03-11 | [5 empty] | 2008-11-21 | 1 | 2008-11-24 | 2008-11-21 |  |  | 2008-12-24 | 2008-12-23 | 1 | 2008-12-24 | 2008-12-24 |  | 2008-11-28 |  |  |  |  | 2009-01-16 | 2009-01-16 | 2009-03-15 | 2008-12-12 |  | 2009-03-03 | 1 | 1 | 2009-03-05 | 2009-03-03 | 2009-02-05 |  |  |  |  | 2009-03-09 | 2009-03-10 | 2009-04-03 | 2009-04-03 |  | 2009-04-17 | 2009-04-17 | [8 empty] | 2009-04-27 | 2009-04-26 | 2009-04-27 |  |  |  |  | Site Build: Leave dish in current position. |  | 2009-04-26 |  |  |  |  | 2009-03-09 | 2009-02-05 | [11 empty] | FALSE |  | 2480955 | 5742591 | 195 Salisbury St, Christchurch |  |  | CELLSITE |  |  | 2015-10-21 |  |  |  |  | 2009-03-05 | 2009-03-06 | [8 empty] | 2008-11-03
0 | CHC | 734 | CHC-060-009 |  |  |  | Christchurch City | 8 | TIER_1_ALL | [22 empty] | FALSE | [60 empty] | Option A. A 25 Meter pole on the Orian Substation Near to Telecom. Option B. A 25 Meter Pole on the existing site property near to road on Montreal St. Option C. A 25 Meter Pole within Search Ring. Option D. A Collocation on the Telecom Tower with Antennas above Telecom.
0 | CHC | 735 | CHC-060-010 | Riccarton | CHC-060-010-A | Riccarton | Christchurch City |  | TIER_1_ALL | ACTIVE | RT | B6 | NOPOLE | grey |  |  | 19.2 | 19.2 |  | -43.5305 | 172.5992 |  |  |  |  | Microwave, Microwave | CHC-060-094-B, CHC-060-094-B | [5 empty] | 2009-03-17, 2009-03-17 | [5 empty] | 2007-10-10 | 5 | 2007-10-30 | 2014-11-11 |  |  | 2008-06-30 | 2008-06-26 | 4 | 2008-06-30 | 2008-06-26 | [6 empty] | 2008-03-20 | 2008-03-20 |  | 2008-03-12 |  | 2008-06-30 | 3 |  | 2008-06-30 | [8 empty] | 2008-08-15 |  |  | 2008-08-29 | 2008-08-28 | [8 empty] | 2008-12-16 | 2009-02-27 | 2008-12-16 |  |  |  |  | Note, BBU 3806 swapped out for 3900 on 17/10/12. |  | 2009-02-27 | [17 empty] | FALSE |  | 2477616 | 5741805 | State Insurance Building 88 Division Street Christchurch |  |  | CELLSITE |  |  | 2014-09-19 | [5 empty] | 2008-07-01 | [8 empty] | 2007-08-14
0 | CHC | 736 | CHC-060-011 | Tower Junction | CHC-060-011-K | Tower Junction | Christchurch City |  | TIER_1_ALL | ACTIVE | GF | A6 | P2 | grey |  |  | 20 | 20 |  | -43.5412 | 172.6048 |  |  |  |  | Microwave | CHC-060-062-D | [5 empty] | 2009-01-23 | [5 empty] | 2008-09-12 | 3 | 2008-09-25 | 2015-09-04 |  |  | 2008-09-24 | 2008-09-25 | 1 | 2008-09-24 | 2008-09-25 |  | 2008-09-16 |  |  |  |  | 2008-10-03 | 2008-10-03 |  | 2008-09-22 |  | 2008-10-17 | 3 |  | 2008-10-17 | 2015-02-05 | 2008-12-17 | [6 empty] | 2008-12-24 |  |  | 2009-01-23 | 2009-01-16 | [8 empty] | 2009-03-18 | 2009-03-13 | 2009-03-18 | [6 empty] | 2009-03-13 | [5 empty] | 2008-12-17 | [11 empty] | FALSE |  | 2478071 | 5740622 | Allstor Self Storage 9 Longley Place Addington Christchurch |  |  | CELLSITE |  |  | 2014-09-19 | [5 empty] | 2008-11-14 | [8 empty] | 2008-08-25
0 | CHC | 737 | CHC-060-012 | Sydenham West | CHC-060-012-A | Sydenham West | Christchurch City |  | TIER_1_ALL | ACTIVE | GF | A | P2 | grey |  |  | 20 | 20 |  | -43.5432 | 172.6298 |  |  |  |  | Microwave | CHC-060-004-C | [11 empty] | 2007-09-28 | 5 | 2007-10-30 | 2015-09-04 |  |  | 2008-05-31 | 2008-05-30 | 4 | 2008-05-31 | 2008-05-30 | [6 empty] | 2008-03-17 | 2008-03-17 |  | 2008-03-12 |  | 2008-03-19 | 2 | 4 | 2008-08-13 | 2008-08-13 | [6 empty] | 2008-08-04 | 2008-09-30 | 2008-09-30 |  | 2008-10-10 | 2008-10-17 | [8 empty] | 2008-12-15 | 2008-12-12 | 2008-12-15 | [6 empty] | 2008-12-12 | [17 empty] | FALSE |  | 2480093 | 5740407 | 122 Antigua Street Christchurch |  |  | CELLSITE |  |  | 2015-10-29 | [5 empty] | 2008-08-01 | [8 empty] | 2007-09-07
0 | CHC | 738 | CHC-060-013 |  | CHC-060-013-A | Eastgate | Christchurch City |  | TIER_1_ALL | ACTIVE | GF | A | P2 | grey |  |  | 20 | 20 |  | -43.5329 | 172.673 |  |  |  |  | Microwave, Microwave | CHC-060-097-A, CHC-060-097-A | FALSE | FALSE |  |  | FALSE | 2008-12-19, 2008-12-19 |  |  |  |  | 2007-09-28 | 2007-09-28 | 5 | 2011-10-25 | 2015-09-03 |  |  | 2008-05-31 | 2008-05-09 | 3 | 2008-05-31 | 2008-05-09 | PERMITTED |  | 2008-08-28 |  | 2008-09-18 | 4 |  | 2008-09-18 |  | 2008-02-01 |  | 2008-03-19 | 5 |  | 2008-08-08 | 2011-10-27 | [6 empty] | 2008-10-22 | 2008-12-17 | 2008-12-16 |  | 2008-12-24 | 2008-12-24 | [8 empty] | 2008-12-24 | 2008-12-31 | 2008-12-24 |  |  |  |  | 12/12 Works complete just waiting for fibre and barrel lock. |  | 2008-12-31 | [17 empty] | FALSE |  | 2483583 | 5741568 | Car Park 9 Buckleys Rd Christchurch |  | CoC application - - 01/11/2011 | CELLSITE |  |  | 2015-10-15 | [5 empty] | 2008-10-20 | [8 empty] | 2007-09-07
0 | CHC | 739 | CHC-060-014 |  | CHC-060-014-F | Bush Inn | Christchurch City |  | TIER_1_ALL | ACTIVE | GF | A6 | P2 | green |  |  | 20 | 20 |  | -43.5309 | 172.5761 |  |  |  |  | Microwave | CHC-060-011-K | [5 empty] | 2009-05-20 | [5 empty] | 2008-08-21 | 2 | 2008-08-21 | 2008-09-18 |  |  | 2009-06-08 | 2009-06-11 | 2 | 2009-06-08 | 2009-06-11 |  | 2008-09-19 |  | 2008-09-26 |  |  | 2008-09-26 | 2008-09-26 |  | 2008-09-22 |  | 2008-10-31 | 1 | 2 | 2008-10-31 | 2008-10-31 | 2009-02-12 |  |  |  |  | 2009-06-08 | 2009-06-11 | 2009-06-29 | 2009-06-29 |  | 2009-06-30 | 2009-06-30 | [8 empty] | 2009-06-30 | 2009-07-03 | 2009-06-30 | [6 empty] | 2009-07-03 |  |  |  |  | 2009-03-09 | 2009-02-12 | [11 empty] | FALSE |  | 2475750 | 5741750 | Bush Inn Shopping Centre, 20 Waimairi Rd, Christchurch |  |  | CELLSITE |  |  | 2014-09-19 |  |  |  |  | 2009-06-11 | 2009-06-11 | [8 empty] | 2008-07-30
0 | CHC | 740 | CHC-060-015 |  | CHC-060-015-A | Hillsborough | Christchurch City |  | TIER_1_ALL | ACTIVE | GF | A | P2 | grey |  |  | 20 | 20 |  | -43.5587 | 172.6775 |  |  |  |  | Microwave, Microwave | CHC-060-097-A, CHC-060-097-A | [5 empty] | 2008-04-23, 2008-04-23 | [5 empty] | 2007-09-05 | 3 | 2007-10-30 | 2008-03-11 |  |  | 2007-11-14 | 2007-11-14 | 3 | 2007-11-14 | 2007-11-14 | [6 empty] | 2008-02-22 | 2008-02-22 |  | 2008-01-21 |  | 2008-02-26 | 1 | 3 | 2008-02-26 | 2008-02-26 | [6 empty] | 2008-04-28 | 2008-04-04 | 2008-05-20 |  | 2008-05-04 | 2008-05-22 | [8 empty] | 2008-12-23 | 2008-12-31 | 2008-12-23 | [6 empty] | 2008-12-31 | [17 empty] | FALSE |  | 2483958 | 5738701 | Woolshed, 53 Currie Rd, Hillsborough, Christchurch |  |  | CELLSITE | [8 empty] | 2008-02-29 | [8 empty] | 2007-08-14
0 | CHC | 741 | CHC-060-016 |  | CHC-060-016-A | Bromley South | Christchurch City |  | TIER_1_ALL | ACTIVE | GF | A | P2 | grey |  |  | 20 | 20 |  | -43.5389 | 172.6964 |  |  |  |  | Microwave, Microwave | CHC-060-045-A, CHC-060-045-A | [5 empty] | 2007-10-15, 2007-10-15 | [5 empty] | 2007-09-07 | 4 | 2007-10-30 | 2008-03-11 |  |  | 2007-12-19 | 2007-12-19 | 4 | 2007-12-19 | 2007-12-19 | [6 empty] | 2008-04-30 | 2008-04-30 |  | 2008-01-21 |  | 2008-02-26 | 1 | 4 | 2008-02-26 | 2008-02-26 | [6 empty] | 2008-05-30 | 2008-06-23 | 2008-06-30 |  | 2008-07-07 | 2008-07-11 | [8 empty] | 2008-12-19 | 2009-02-27 | 2008-12-19 | [6 empty] | 2009-02-27 | [17 empty] | FALSE |  | 2485470 | 5740910 | Bromley Self Storage 17 Tanya Street Bromley Christchurch |  |  | CELLSITE |  |  | 2015-10-15 | [5 empty] | 2008-05-01 | [8 empty] | 2007-08-14
0 | CHC | 742 | CHC-060-017 |  | CHC-060-017-H | Upper Riccarton | Christchurch City |  | TIER_1_ALL | ACTIVE | GF | A6 | P2 | grey |  |  | 20 | 20 |  | -43.5391 | 172.5674 |  |  |  |  | Microwave, Microwave | CHC-060-018-F, CHC-060-018-F | [5 empty] | 2009-03-17, 2008-04-18 | [5 empty] | 2008-01-22 | 2 | 2008-01-22 | 2008-03-11 |  |  | 2008-08-31 | 2008-09-26 | 2 | 2008-08-31 | 2008-09-26 | [6 empty] | 2008-02-22 | 2008-02-22 |  | 2008-02-18 |  | 2008-03-19 | 2 | 2 | 2008-08-15 | 2008-08-15 | 2009-01-12 | [5 empty] | 2008-08-08 | 2009-01-16 | 2009-01-16 |  | 2009-01-30 | 2009-02-02 | [8 empty] | 2009-03-31 | 2009-03-31 | 2009-03-31 | [6 empty] | 2009-03-31 | [5 empty] | 2009-01-12 | [11 empty] | FALSE |  | 2475050 | 5740835 | 444 Blenheim Rd Christchurch |  |  | CELLSITE |  |  | 2014-09-19 | [5 empty] | 2008-09-30 | [8 empty] | 2007-11-12
0 | CHC | 743 | CHC-060-018 |  | CHC-060-018-F | Sockburn | Christchurch City |  | TIER_1_ALL | ACTIVE | GF | A | P2 | grey |  |  | 20 | 20 |  | -43.5409 | 172.5541 |  |  |  |  | Microwave, Microwave | CHC-060-094-B, CHC-060-094-B | [5 empty] | 2009-03-17, 2009-03-06 | [5 empty] | 2007-11-16 | 4 | 2008-01-22 | 2015-09-03 |  |  | 2008-04-03 | 2008-04-03 | 3 | 2008-04-03 | 2008-04-03 | [6 empty] | 2008-02-18 | 2008-02-18 |  | 2008-03-03 |  | 2008-04-30 | 1 | 3 | 2008-04-30 | 2008-04-30 | [6 empty] | 2008-05-30 | 2008-06-27 | 2008-06-30 |  | 2008-07-04 | 2008-07-04 | [8 empty] | 2009-03-30 | 2009-03-31 | 2009-03-30 | [6 empty] | 2009-03-31 | [17 empty] | FALSE |  | 2473972 | 5740631 | Blairs 3 Alloy Street Christchurch |  |  | CELLSITE |  |  | 2015-11-05 | [5 empty] | 2008-05-01 | [8 empty] | 2007-10-19
0 | CHC | 744 | CHC-060-019 |  | CHC-060-019-B | Hornby | Christchurch City |  | TIER_1_ALL | ACTIVE | GF | A | P2 | grey |  |  | 20 | 20 |  | -43.5415 | 172.5309 |  |  |  |  | Microwave, Microwave | CHC-060-085-C, CHC-060-085-C | [5 empty] | 2009-03-17, 2008-04-22 | [5 empty] | 2008-01-29 | 3 | 2007-10-30 | 2015-09-03 |  |  | 2008-10-31 | 2008-10-24 | 2 | 2009-05-01 | 2009-03-24 | [6 empty] | 2008-09-24 | 2008-09-24 |  | 2008-03-31 |  | 2008-06-03 | 2 | 2 | 2008-09-01 | 2008-09-01 | 2009-01-15 | [5 empty] | 2008-11-18 | 2009-01-22 | 2009-01-23 |  | 2009-02-04 | 2009-02-02 | [8 empty] | 2009-04-09 | 2009-04-10 | 2009-04-09 | [6 empty] | 2009-04-10 | [5 empty] | 2009-01-15 | [11 empty] | FALSE |  | 2472097 | 5740559 | Toll site Canterbury St Christchurch |  |  | CELLSITE |  |  | 2015-11-05 | [5 empty] | 2008-11-14 | [8 empty] | 2007-11-12
0 | CHC | 745 | CHC-060-020 |  | CHC-060-020-A | University | Christchurch City |  | TIER_1_ALL | ACTIVE | RT | B6 | NOPOLE | grey |  |  | 29.5 | 29.5 |  | -43.5218 | 172.5826 |  |  |  |  | Microwave, Microwave | CHC-060-094-B, CHC-060-094-B | [5 empty] | 2009-03-18, 2009-03-18 | [5 empty] | 2007-11-06 | 6 | 2008-09-17 | 2013-10-10 |  |  | 2009-02-16 | 2009-02-11 | 4 | 2009-05-30 | 2009-05-22 |  | 2008-10-23 |  |  |  |  | 2008-11-27 | 2008-11-27 |  | 2008-12-18 |  | 2009-02-19 | 1 | 4 | 2009-02-19 | 2009-02-19 | [5 empty] | 2009-03-13 | 2009-03-13 | 2009-04-09 | 2009-04-09 |  | 2009-05-25 | 2009-05-25 | [8 empty] | 2009-05-27 | 2009-05-30 | 2009-05-27 |  |  |  |  | NOTE - BBU 3806 SWAPPED OUT FOR NEW 3900 UNIT ON 17/10/2012. |  | 2009-05-30 | [17 empty] | FALSE |  | 2476270 | 5742760 | Rutherford Building, Canterbury University Christchurch 8020 |  |  | CELLSITE |  |  | 2014-09-19 |  |  |  |  | 2009-03-06 | 2009-03-06 | [8 empty] | 2007-08-29
0 | CHC | 746 | CHC-060-021 |  | CHC-060-021-A | Wainoni | Christchurch City |  | TIER_1_ALL | ACTIVE | GF | A | P2 | grey |  |  | 20 | 20 |  | -43.5159 | 172.6925 | [6 empty] | FALSE | FALSE |  |  | FALSE | [6 empty] | 2007-11-20 | 2 | 2007-11-20 | 2008-01-22 |  |  | 2008-11-26 | 2008-11-25 | 2 | 2008-11-26 | 2008-11-25 | [6 empty] | 2008-08-26 | 2008-10-29 |  | 2008-06-03 |  | 2008-08-26 | 1 | 2 | 2008-08-26 | 2008-08-26 | 2009-01-16 | [5 empty] | 2008-12-22 | 2009-02-04 | 2009-02-04 |  | 2009-02-13 | 2009-02-13 | [8 empty] | 2009-02-27 | 2009-02-27 | 2009-02-27 | [6 empty] | 2009-02-27 |  |  |  |  | 2009-01-12 | 2009-01-16 | [11 empty] | FALSE |  | 2485147 | 5743454 | 52 Shortland St Avondale Christchurch |  |  | CELLSITE | [8 empty] | 2008-12-11 | [8 empty] | 2007-10-12
0 | CHC | 747 | CHC-060-022 |  | CHC-060-022-H | Elmwood | Christchurch City |  | TIER_1_ALL | ACTIVE | GF | A6 | P4E | grey |  |  | 15 | 15 |  | -43.5094 | 172.6063 |  |  |  |  | Leased Line | CHC-060-063-B | [11 empty] | 2008-10-08 | 2 | 2008-10-14 | 2008-10-14 |  |  | 2008-11-06 | 2008-11-06 | 2 | 2009-03-24 | 2009-03-24 |  | 2008-10-08 |  | 2009-02-11 |  |  | 2009-02-11 | 2009-02-11 |  | 2008-11-20 |  | 2009-01-30 | 1 | 2 | 2009-01-30 | 2009-01-30 | 2009-04-03 |  |  |  |  | 2009-04-21 | 2009-04-21 | 2009-04-30 | 2009-04-27 |  | 2009-06-02 | 2009-06-02 | [8 empty] | 2009-06-05 | 2009-06-05 | 2009-06-05 | [6 empty] | 2009-06-05 |  |  |  |  | 2009-04-06 | 2009-04-03 | [11 empty] | FALSE |  | 2478179 | 5744156 | 1 Normans Rd, Bryndwr, Christchurch |  |  | CELLSITE |  |  | 2014-09-19 |  |  |  |  | 2009-04-21 | 2009-04-21 | [8 empty] | 2008-09-15
0 | CHC | 748 | CHC-060-023 |  | CHC-060-023-A | Papanui | Christchurch City |  | TIER_1_ALL | ACTIVE | RT | B6 | NOPOLE | grey |  |  | 22.4 | 22.4 |  | -43.4962 | 172.6073 | [6 empty] | FALSE | FALSE |  |  | FALSE | [5 empty] | 2007-09-28 | 2007-09-28 | 9 | 2011-11-30 | 2011-09-30 |  |  | 2008-04-30 | 2008-04-30 | 6 | 2011-12-23 |  | DISCRETIONARY_FULL | 2008-10-18 | 2011-09-27 | 2008-11-22 | 2011-10-17 | 9 | 2011-11-03 | 2011-10-07 |  | 2008-01-21 | 2008-08-26 | 2008-08-26 | 3 | 6 | 2011-09-30 | 2008-08-08 | [6 empty] | 2008-08-11 | 2008-09-12 | 2008-09-12 |  | 2008-09-15 | 2008-10-06 | [8 empty] | 2008-12-17 | 2008-12-30 | 2008-12-17 |  |  |  |  | Fendalton far end. Manufacture std bracket. Cosite response received. 05/12 Letter with Rev9 was sent on 09/11. NOTE - BBU 3806 SWAPPED OUT FOR NEW 3900 UNIT 17/10/2012. |  | 2008-12-16 | [17 empty] | FALSE |  | 2478249 | 5745623 | Work & Income Building 7 Winston Ave Papanui Christchurch |  |  | CELLSITE |  |  | 2014-09-19 | [5 empty] | 2008-08-11 | [8 empty] | 2007-09-07
0 | CHC | 749 | CHC-060-024 |  | CHC-060-024-D | Merivale | Christchurch City |  | TIER_1_ALL | ACTIVE | COLO | A6 | COLO | grey |  | COLO | 17 | 17 |  | -43.512 | 172.6237 |  |  |  |  | Microwave | CHC-060-009-A | [5 empty] | 2009-05-20 | [5 empty] | 2008-11-27 | 4 | 2009-01-20 | 2009-05-21 |  |  | 2009-05-27 | 2009-05-26 | 3 | 2009-09-29 | 2009-08-18 |  | 2009-01-19 |  |  |  |  | 2009-02-04 | 2009-02-04 |  | 2009-01-23 |  | 2009-01-23 | 3 |  | 2009-03-06 | 2009-03-25 | [5 empty] | 2009-04-03 | 2009-04-03 | 2009-06-10 | 2009-06-12 |  | 2009-06-23 | 2009-06-23 | [8 empty] | 2009-06-25 | 2009-06-29 | 2009-06-25 |  |  |  |  | As Builts needs to be sent to TNZL. | TNZ | 2009-06-30 | [17 empty] | FALSE |  | 2479584 | 5743867 | 25 St Albans St, Merivale, Christchurch |  |  | CELLSITE |  |  | 2014-09-19 |  |  |  |  | 2009-04-14 | 2009-04-03 | [8 empty] | 2008-10-07
0 | CHC | 750 | CHC-060-025 |  | CHC-060-025-F | Shirley | Christchurch City |  | TIER_1_ALL | ACTIVE | RSR | A | P4D | green |  |  | 14 | 14 |  | -43.5085 | 172.6517 |  |  |  |  | Microwave, Leased Line, Microwave | CHC-060-097-A, CHC-060-063-B, CHC-060-097-A | [5 empty] | 2009-10-12, 2009-10-12 | [5 empty] | 2008-12-12 | 4 | 2009-01-30 | 2009-10-29 |  |  | 2009-02-12 | 2009-02-10 | 3 | 2009-02-12 | 2009-02-12 |  |  |  | 2009-02-09 |  |  | 2009-01-16 | 2009-01-16 | 2009-02-27 | 2009-02-19 |  | 2009-03-05 | 1 | 3 | 2009-03-13 | 2009-03-05 | 2009-04-23 |  |  |  |  | 2009-04-16 | 2009-04-16 | 2009-04-28 | 2009-04-28 |  | 2009-05-08 | 2009-05-08 | [8 empty] | 2009-05-16 | 2009-05-18 | 2009-05-16 |  |  |  |  | COMPLETE: Handover to Operations Team |  | 2009-05-18 |  |  |  |  | 2009-04-23 | 2009-04-23 | [11 empty] | FALSE |  | 2481850 | 5744273 | RSR - Outside 204 Hills Road (Shirley Shopping Centre) Shirley Christchurch |  |  | CELLSITE |  |  | 2015-10-15 |  |  |  |  | 2009-04-16 | 2009-04-16 | [8 empty] | 2008-12-03
0 | CHC | 751 | CHC-060-026 |  | CHC-060-026-F | New Brighton | Christchurch City |  | TIER_1_ALL | ACTIVE | GF | A | P2 | green |  |  | 20 | 20 |  | -43.5067 | 172.7275 | [17 empty] | 2008-03-04 | 4 | 2008-10-01 | 2008-10-01 |  |  | 2008-05-31 | 2008-05-19 | 4 | 2008-05-31 | 2008-05-19 | [6 empty] | 2008-10-15 | 2008-10-15 |  | 2008-03-31 |  | 2008-06-03 | 3 | 4 | 2008-11-07 | 2008-11-07 | 2009-01-19 | [5 empty] | 2008-11-21 | 2009-01-29 | 2009-01-23 |  | 2009-02-09 | 2009-02-12 | [8 empty] | 2009-02-27 |  | 2009-02-27 | [6 empty] | 2009-02-27 |  |  |  |  | 2009-01-19 | 2009-01-19 | [11 empty] | FALSE |  | 2487974 | 5744491 | 104 Brighton Mall Off Hawke Street New Brighton Christchurch |  |  | CELLSITE | [8 empty] | 2008-11-12 | [8 empty] | 2008-01-25
0 | CHC | 752 | CHC-060-027 |  | CHC-060-027-E | Ferrymead | Christchurch City |  | TIER_1_ALL | ACTIVE | GF | A | P2 | green |  |  | 20 | 20 |  | -43.5571 | 172.6972 |  |  |  |  | Microwave | CHC-060-045-A | [5 empty] | 2009-02-16 | [5 empty] | 2008-10-08 | 3 | 2008-12-19 | 2008-12-19 |  |  | 2008-10-24 | 2008-10-17 | 3 | 2009-01-14 | 2009-01-14 |  | 2008-10-08 |  |  |  |  | 2008-11-21 | 2009-01-12 |  | 2008-11-12 |  | 2008-11-28 | 2 | 3 | 2008-12-24 | 2008-12-24 | 2009-01-23 | [5 empty] | 2009-01-07 | 2009-01-31 | 2009-01-31 |  | 2009-02-20 | 2009-02-12 | [8 empty] | 2009-02-27 |  | 2009-02-27 | [11 empty] | 2009-02-02 | 2009-01-23 | [11 empty] | FALSE |  | 2485545 | 5738887 | 950 Ferry Road Christchurch |  |  | CELLSITE | [8 empty] | 2008-12-11 | [8 empty] | 2008-09-30
0 | CHC | 753 | CHC-060-028 |  | CHC-060-028-B | Styx | Christchurch City |  | TIER_1_ALL | ACTIVE | GF | A | P3 | green |  |  | 25 | 25 |  | -43.4671 | 172.6123 |  |  |  |  | Microwave, Microwave | CHC-060-084-D, CHC-060-084-D | [5 empty] | 2009-04-07, 2009-04-07 | [5 empty] | 2008-10-13 | 1 | 2008-10-13 | 2008-10-13 |  |  | 2008-12-16 | 2008-11-21 | 1 | 2008-12-16 | 2008-11-21 |  | 2008-10-15 |  |  |  |  | 2008-11-25 | 2008-10-31 |  | 2008-11-20 |  | 2008-12-05 | 1 | 1 | 2008-12-05 | 2008-12-05 | 2009-03-05 |  |  |  |  | 2009-03-13 | 2009-03-09 | 2009-03-30 | 2009-03-30 |  | 2009-04-27 | 2009-04-08 | [8 empty] | 2009-04-21 | 2009-04-30 | 2009-04-21 | [6 empty] | 2009-04-27 |  |  |  |  | 2009-03-06 | 2009-03-05 | [11 empty] | FALSE |  | 2478637 | 5748857 | Christchurch City Council Eco Depot, 76 Styx Mill Rd, Christchurch |  |  | CELLSITE |  |  | 2015-10-12 |  |  |  |  | 2009-03-09 | 2009-03-09 | [8 empty] | 2008-10-06
0 | CHC | 754 | CHC-060-029 |  | CHC-060-029-A | Belfast | Christchurch City |  | TIER_1_ALL | ACTIVE | GF | A | P2 | grey |  |  | 20 | 20 |  | -43.4456 | 172.6379 |  |  |  |  | Microwave, Microwave | CHC-060-096-G, CHC-060-096-G | [5 empty] | 2009-03-31, 2009-03-31 | [5 empty] | 2007-12-13 | 1 | 2007-12-13 | 2007-12-13 |  |  | 2008-01-24 | 2008-01-24 | 1 | 2008-01-24 | 2008-01-24 | [6 empty] | 2008-02-28 | 2008-02-28 |  | 2008-02-22 |  | 2008-04-17 | 3 | 1 | 2008-04-17 | 2009-08-13 | [6 empty] | 2008-05-19 | 2008-05-30 | 2008-05-30 |  | 2008-06-27 | 2008-06-30 | [8 empty] | 2009-03-30 | 2009-03-27 | 2009-03-30 | [6 empty] | 2009-03-27 | [17 empty] | FALSE |  | 2480702 | 5751257 | 50 Factory Rd Belfast Christchurch |  |  | CELLSITE | [8 empty] | 2008-04-18 | [8 empty] | 2007-11-12
0 | CHC | 755 | CHC-060-030 |  | CHC-060-030-D | Bishopdale | Christchurch City |  | TIER_1_ALL | ACTIVE | GF | A | P2 | green |  |  | 20 | 20 |  | -43.4905 | 172.5863 |  |  |  |  | Microwave, Microwave | CHC-060-033-D, CHC-060-033-D | [5 empty] | 2008-05-06, 2008-05-06 | [5 empty] | 2008-04-08 | 2 | 2008-08-08 | 2008-10-17 |  |  | 2008-11-14 | 2008-11-13 | 2 | 2008-11-14 | 2008-11-13 | [6 empty] | 2008-06-16 | 2008-06-16 |  | 2008-04-29 |  | 2008-08-21 | 2 | 2 | 2008-10-15 | 2008-10-15 | [6 empty] | 2008-12-01 | 2008-12-23 | 2008-12-19 |  | 2009-01-06 | 2008-12-23 | [8 empty] | 2008-12-24 | 2008-12-31 | 2008-12-24 | [6 empty] | 2008-12-31 | [17 empty] | FALSE |  | 2476550 | 5746245 | Bishopdale Mall Off Farrington Avenue Christchurch |  |  | CELLSITE |  |  | 2015-10-12 | [5 empty] | 2008-11-28 | [8 empty] | 2008-01-29
0 | CHC | 756 | CHC-060-031 |  | CHC-060-031-F | Burnside | Christchurch City |  | TIER_1_ALL | ACTIVE | RSR | A6 | P4E | green |  |  | 18 | 18 |  | -43.5003 | 172.5601 |  |  |  |  | Microwave, Microwave | CHC-060-023-A, CHC-060-023-A | [5 empty] | 2008-04-18, 2008-04-18 | [5 empty] | 2008-02-09 | 1 | 2008-01-15 | 2008-02-09 |  |  | 2008-02-25 | 2008-02-25 | 1 | 2008-02-25 | 2008-02-25 | [6 empty] | 2008-04-30 | 2008-04-30 |  | 2008-04-29 |  | 2008-05-12 | 1 | 1 | 2008-05-12 | 2008-05-12 | [6 empty] | 2008-07-25 | 2008-08-29 | 2008-08-29 |  | 2008-09-12 | 2008-09-24 | [8 empty] | 2008-12-18 | 2008-12-11 | 2008-12-18 | [6 empty] | 2008-11-27 | [17 empty] | FALSE |  | 2474435 | 5745146 | Opposite 37 Roydvale Avenue Russley Christchurch |  |  | CELLSITE |  |  | 2014-09-19 | [5 empty] | 2008-07-21 | [8 empty] | 2008-01-15
0 | CHC | 757 | CHC-060-032 |  | CHC-060-032-G | Broomfield | Christchurch City |  | TIER_1_ALL | ACTIVE | RSR | A | P4E | green |  |  | 18 | 18 |  | -43.5216 | 172.5378 |  |  |  |  | Microwave, Microwave | CHC-060-094-B, CHC-060-094-B | [5 empty] | 2009-03-18, 2009-03-18 | [5 empty] | 2008-04-21 | 1 | 2008-04-21 | 2008-04-21 |  |  | 2008-03-26 | 2008-03-26 | 1 | 2008-03-26 | 2008-03-26 | [6 empty] | 2008-05-27 | 2008-05-27 |  | 2008-04-29 |  | 2008-05-20 | 2 | 1 | 2008-09-01 | 2008-09-01 | [6 empty] | 2008-09-01 | 2008-09-28 | 2008-09-26 |  | 2008-10-23 | 2008-10-24 | [8 empty] | 2008-12-10 | 2008-12-31 | 2008-12-10 | [6 empty] | 2008-12-31 | [17 empty] | FALSE |  | 2472645 | 5742764 | Opposite 2 Steadman Rd Christchurch |  |  | CELLSITE |  |  | 2015-11-05 | [5 empty] | 2008-09-01 | [8 empty] | 2008-03-12
0 | CHC | 758 | CHC-060-033 |  | CHC-060-033-D | Wairakei | Christchurch City |  | TIER_1_ALL | ACTIVE | GF | A | P2 | grey |  |  | 18.8 | 18.8 |  | -43.4898 | 172.5669 |  |  |  |  | Microwave, Microwave | CHC-060-023-A, CHC-060-023-A | [5 empty] | 2008-05-06, 2008-05-06 | [5 empty] | 2007-08-21 | 3 | 2007-10-30 | 2008-03-13 |  |  | 2007-11-28 | 2007-11-28 | 3 | 2007-11-28 | 2007-11-28 | [6 empty] | 2008-04-30 | 2008-04-30 |  | 2008-04-04 |  | 2008-04-30 | 1 | 3 | 2008-04-30 | 2008-04-30 | [6 empty] | 2008-06-03 | 2008-07-31 | 2008-07-31 |  | 2008-08-14 | 2008-08-28 | [8 empty] | 2008-12-18 | 2008-12-11 | 2008-12-18 | [6 empty] | 2008-11-27 | [17 empty] | FALSE |  | 2474979 | 5746309 | Pacific Wide 525 Wairakei Road Christchurch |  |  | CELLSITE |  |  | 2015-10-12 | [5 empty] | 2008-05-01 | [8 empty] | 2007-07-24
0 | CHC | 759 | CHC-060-034 |  | CHC-060-034-C | Mairehau | Christchurch City |  | TIER_1_ALL | ACTIVE | RSR | A | P2 | green |  |  | 20 | 20 |  | -43.4901 | 172.6548 |  |  |  |  | Microwave, Microwave | CHC-060-097-A, CHC-060-097-A | [5 empty] | 2009-04-24, 2009-04-24 | [5 empty] | 2008-12-12 | 1 | 2008-12-11 | 2008-12-12 |  |  | 2009-02-18 | 2009-02-18 | 1 | 2009-02-18 | 2009-02-18 |  | 2009-01-31 |  | 2009-01-29 |  |  | 2009-01-29 | 2009-01-29 | 2009-03-17 | 2009-03-09 |  | 2009-03-16 | 2 | 1 | 2009-03-20 | 2009-04-15 | 2009-03-09 |  |  |  |  | 2009-04-03 | 2009-04-03 | 2009-04-28 | 2009-04-17 |  | 2009-05-12 | 2009-05-12 | [8 empty] | 2009-05-29 | 2009-05-29 | 2009-05-29 | [6 empty] | 2009-05-29 |  |  |  |  | 2009-03-09 | 2009-03-09 | [11 empty] | FALSE |  | 2482086 | 5746316 | Queen Elizabeth II Drive & Innes Rd Intersection Christchurch |  |  | CELLSITE |  |  | 2015-10-15 |  |  |  |  | 2009-03-23 | 2009-03-23 | [8 empty] | 2008-12-04
0 | CHC | 760 | CHC-060-035 |  | CHC-060-035-C | Hillmorton | Christchurch City |  | TIER_1_ALL | ACTIVE | GF | A6 | P2 | grey |  |  | 18 | 18 |  | -43.5504 | 172.5964 |  |  |  |  | Microwave, Microwave | CHC-060-094-B, CHC-060-094-B | [5 empty] | 2009-03-23, 2009-03-23 | [5 empty] | 2008-01-24 | 5 | 2008-01-24 | 2008-04-09 |  |  | 2008-10-20 | 2008-10-20 | 5 | 2008-10-20 | 2008-10-20 |  | 2008-07-07 |  | 2008-09-05 |  |  | 2008-09-05 | 2008-09-05 |  | 2008-03-31 |  | 2008-06-04 | 2 | 5 | 2008-08-15 | 2008-08-15 | 2009-02-20 | [5 empty] | 2008-12-05 | 2009-02-28 | 2009-02-26 |  | 2009-03-27 | 2009-03-06 | [8 empty] | 2009-03-31 | 2009-03-31 | 2009-03-31 | [6 empty] | 2009-03-31 |  |  |  |  | 2009-03-24 | 2009-02-20 | [11 empty] | FALSE |  | 2477395 | 5739593 | 23 Sylvan Street Hoon Hay Christchurch |  |  | CELLSITE |  |  | 2014-09-19 | [5 empty] | 2008-11-18 | [8 empty] | 2007-12-11
0 | CHC | 761 | CHC-060-036 |  | CHC-060-036-A | Beckenham | Christchurch City |  | TIER_1_ALL | ACTIVE | GF | A | P2 | green |  |  | 20 | 20 |  | -43.5577 | 172.6373 |  |  |  |  | Microwave, Microwave | CHC-060-094-B, CHC-060-094-B | [5 empty] | 2009-05-21, 2009-05-21 | [5 empty] | 2008-07-01 | 2 | 2007-07-01 | 2009-05-13 |  |  | 2008-10-31 | 2008-10-09 | 2 | 2009-04-06 | 2008-10-09 | [6 empty] | 2008-09-12 | 2008-09-12 | 2009-04-02 | 2009-01-21 |  | 2009-04-15 | 2 | 2 | 2009-05-05 | 2009-05-25 | 2009-02-09 |  |  |  |  | 2009-06-22 | 2009-06-22 | 2009-07-10 | 2009-07-10 |  | 2009-07-27 | 2009-07-27 | [8 empty] | 2009-07-31 | 2009-08-01 | 2009-07-31 |  |  |  |  | Site to be audited by Sean (On Going). |  | 2009-08-01 |  |  |  |  | 2009-02-09 | 2009-02-09 | [11 empty] | FALSE |  | 2480705 | 5738794 | Tandoori Palace, 134 Colombo St, Christchurch |  |  | CELLSITE |  |  | 2015-10-29 |  |  |  |  | 2009-06-15 | 2009-06-15 | [8 empty] | 2007-10-31
0 | CHC | 762 | CHC-060-037 |  | CHC-060-037-B | Huntsbury | Christchurch City |  | TIER_1_ALL | ACTIVE | RSR | A | P4E | green |  |  | 18 | 18 |  | -43.57 | 172.6444 |  |  |  |  | Microwave, Microwave | CHC-060-097-A, CHC-060-097-A | [5 empty] | 2008-04-22, 2008-04-22 | [5 empty] | 2008-03-28 | 3 | 2008-03-26 | 2008-04-23 |  |  | 2008-02-25 | 2008-02-25 | 3 | 2008-02-25 | 2008-02-25 | [6 empty] | 2008-05-19 | 2008-05-19 |  | 2008-03-31 |  | 2008-05-19 | 2 | 3 | 2008-09-02 | 2008-09-02 | [6 empty] | 2008-09-09 | 2008-09-30 | 2008-09-30 |  | 2008-10-21 | 2008-10-21 | [8 empty] | 2008-12-23 | 2008-12-31 | 2008-12-23 |  |  |  |  | 2degrees will need to sign off the pad for the cabinet |  | 2008-12-23 | [17 empty] | FALSE |  | 2481289 | 5737430 | Opposite 60 Centaurus Road Cashmere Christchurch |  |  | CELLSITE | [8 empty] | 2008-09-03 | [8 empty] | 2008-01-15
0 | CHC | 763 | CHC-060-038 |  | CHC-060-038-A | Templeton | Christchurch City |  | TIER_1_ALL | ACTIVE | GF | A | P2 | grey |  |  | 20 | 20 |  | -43.5522 | 172.4799 |  |  |  |  | Microwave, Microwave | CHC-060-085-C, CHC-060-085-C | [5 empty] | 2009-03-18, 2009-03-18 | [5 empty] | 2007-11-19 | 4 | 2008-04-08 | 2008-04-08 |  |  | 2008-08-31 | 2008-08-20 | 4 | 2008-08-31 | 2008-08-20 | [6 empty] | 2008-03-17 | 2008-03-17 |  | 2008-04-29 |  | 2008-07-29 | 1 | 4 | 2008-07-29 | 2008-07-29 | 2009-01-12 | [5 empty] | 2008-09-05 | 2009-01-19 | 2009-01-19 |  | 2009-02-13 | 2009-02-02 | [8 empty] | 2009-04-09 | 2009-04-10 | 2009-04-09 | [6 empty] | 2009-04-10 | [5 empty] | 2009-01-12 | [11 empty] | FALSE |  | 2467985 | 5739337 | 762 Main South Road Christchurch |  |  | CELLSITE | [8 empty] | 2008-09-03 | [8 empty] | 2007-10-19
0 | CHC | 764 | CHC-060-039 |  | CHC-060-039-F | Sumner | Christchurch City |  | TIER_1_ALL | ACTIVE | GF | A | P4D | grey |  |  | 10.8 | 10.8 |  | -43.5763 | 172.7662 |  |  |  |  | Leased Line | CHC-060-063-B | [11 empty] | 2008-02-22 | 5 | 2008-02-22 | 2009-11-25 |  |  | 2008-05-31 | 2008-05-30 | 4 | 2008-05-31 | 2008-05-30 | [6 empty] | 2008-06-30 | 2008-06-30 |  | 2008-04-29 |  | 2008-07-01 | 1 | 3 | 2008-07-01 | 2008-07-01 | [6 empty] | 2008-08-11 | 2008-09-19 | 2008-09-19 |  | 2008-09-30 | 2008-09-29 | [8 empty] | 2009-01-29 | 2009-01-30 | 2009-01-29 | [6 empty] | 2009-01-30 | [17 empty] | FALSE |  | 2491126 | 5736771 | 18 Heberden Ave Sumner Christchurch |  |  | CELLSITE | [8 empty] | 2008-07-21 | [8 empty] | 2008-01-24
0 | CHC | 765 | CHC-060-040 |  | CHC-060-040-E | Christchurch Airport | Christchurch City |  | TIER_1_ALL | ACTIVE | GF | A | P2 | grey |  |  | 20 | 20 |  | -43.4861 | 172.5518 |  |  |  |  | Microwave, Microwave | CHC-060-023-A, CHC-060-023-A | [5 empty] | 2008-07-16, 2008-07-16 | [5 empty] | 2008-04-04 | 4 | 2008-11-18 | 2008-11-12 |  |  | 2008-05-31 | 2008-05-30 | 4 | 2008-05-31 | 2008-05-30 | [6 empty] | 2008-09-11 | 2008-09-11 |  | 2008-03-31 |  | 2008-08-08 | 2 | 3 | 2008-11-12 | 2008-11-12 | [6 empty] | 2008-10-17 | 2008-12-12 | 2008-12-10 |  | 2008-12-31 | 2008-12-17 | [8 empty] | 2008-12-18 | 2009-02-27 | 2008-12-18 |  |  |  |  | COMPLETE: Handover to Operations Team |  | 2009-02-27 | [17 empty] | FALSE |  | 2473759 | 5746715 | 791 Wairakei Rd Christchurch |  |  | CELLSITE |  |  | 2015-10-12 | [5 empty] | 2008-09-16 | [8 empty] | 2008-02-27
0 | CHC | 766 | CHC-060-041 |  | CHC-060-041-A | Harewood | Christchurch City |  | TIER_1_ALL | ACTIVE | GF | A | OTHERS | grey |  |  | 35 | 35 |  | -43.4638 | 172.5793 |  |  |  |  | Microwave, Microwave | CHC-060-097-A, CHC-060-097-A | [5 empty] | 2009-04-29, 2009-04-29 | [5 empty] | 2008-01-17 | 5 | 2008-12-18 | 2008-12-18 |  |  | 2009-03-25 | 2009-03-25 | 5 | 2009-04-23 | 2009-04-21 |  |  |  | 2008-09-29 |  |  | 2009-01-12 | 2009-01-12 |  | 2008-03-12 |  | 2008-12-19 | 1 | 5 | 2008-12-19 | 2008-12-19 | 2009-04-24 |  |  |  |  | 2009-04-30 | 2009-04-30 | 2009-05-28 | 2009-05-28 |  | 2009-06-12 | 2009-06-04 | [8 empty] | 2009-06-12 | 2009-06-16 | 2009-06-12 |  |  |  |  | . |  | 2009-06-16 |  |  |  |  | 2009-04-27 | 2009-04-24 | [11 empty] | FALSE |  | 2475970 | 5749203 | Greywacke Rd Christchurch |  |  | CELLSITE |  |  | 2015-10-12 |  |  |  |  | 2009-04-27 | 2009-04-22 | [8 empty] | 2007-10-31
0 | CHC | 767 | CHC-060-042 |  | CHC-060-042-D | Bridgend | Christchurch City |  | TIER_1_ALL | ACTIVE | GF | A | P2 | grey |  |  | 20 | 20 |  | -43.421 | 172.6523 |  |  |  |  | Microwave, Microwave | CHC-060-096-G, CHC-060-096-G | [5 empty] | 2008-09-19, 2008-09-19 | [5 empty] | 2008-05-15 | 2 | 2008-09-11 | 2008-09-11 |  |  | 2008-08-18 | 2008-08-18 | 2 | 2008-08-18 | 2008-08-18 | [6 empty] | 2008-09-09 | 2008-09-09 |  | 2008-06-03 |  | 2008-09-11 | 1 | 2 | 2008-09-11 | 2008-09-11 | 2009-01-15 | [5 empty] | 2008-10-17 | 2009-01-22 | 2009-01-23 |  | 2009-02-04 | 2009-02-02 | [8 empty] | 2009-03-30 | 2009-03-27 | 2009-03-30 |  |  |  |  | As Builts: None |  | 2009-03-27 | [5 empty] | 2009-01-15 | [11 empty] | FALSE |  | 2481853 | 5753987 | Safestore Container Park Main North Road Bridgend Christchurch |  |  | CELLSITE | [8 empty] | 2008-09-16 | [8 empty] | 2008-04-28
0 | CHC | 768 | CHC-060-043 | Hagley | CHC-060-043-G | Hagley | Christchurch City |  | TIER_1_ALL | ACTIVE | RSR | A6 | P4E | green |  |  | 18 | 18 |  | -43.5351 | 172.6263 |  |  |  |  | Microwave | CHC-060-001-G | [5 empty] | 2009-06-17 |  |  |  |  | 2009-04-30 | 2009-04-16 | 5 | 2009-04-30 | 2014-11-11 |  |  | 2009-05-29 | 2009-05-29 | 3 | 2009-05-29 | 2009-05-29 |  | 2009-04-15 |  | 2009-05-10 |  |  | 2009-06-12 | 2009-06-12 | 2009-04-30 | 2009-05-04 |  | 2009-06-10 | 3 |  | 2009-06-09 | 2015-02-05 | 2009-06-23 |  |  |  |  | 2009-06-15 |  | 2009-06-29 |  |  | 2009-06-30 | 2009-06-30 | [8 empty] | 2009-06-30 | 2009-06-30 | 2009-06-30 | [6 empty] | 2009-06-30 |  |  |  |  | 2009-06-23 | 2009-06-23 | [11 empty] | FALSE |  | 2479806 | 5741307 | RSR Cnr Tuam and Hagley Ave Christchurch |  |  | CELLSITE |  |  | 2014-09-19 |  |  |  |  | 2009-06-15 | 2009-06-15 | [8 empty] | 2009-04-02
0 | CHC | 769 | CHC-060-044 |  |  |  | Christchurch City |  | TIER_1_ALL
0 | CHC | 770 | CHC-060-045 |  | CHC-060-045-A | Bromley | Christchurch City |  | TIER_1_ALL | ACTIVE | GF | A | LATTICE | grey |  |  | 35 | 35 |  | -43.5306 | 172.6978 | [17 empty] | 2008-03-12 | 6 | 2009-01-23 | 2009-01-23 |  |  | 2008-10-30 | 2008-10-17 | 5 | 2008-10-30 | 2008-10-17 | DISCRETIONARY_FULL | 2008-12-15 | 2011-09-05 | 2009-05-22 | 2011-12-19 | 5 | 2009-05-25 | 2009-05-25 |  | 2008-08-27 |  | 2008-11-21 | 7 |  | 2009-01-16 | 2011-10-18 | 2009-01-30 |  |  |  |  | 2009-06-08 | 2009-06-08 | 2009-07-10 | 2009-07-10 |  | 2009-07-28 | 2009-07-15 | [8 empty] | 2009-07-31 | 2009-07-31 | 2009-07-31 | [6 empty] | 2009-07-31 | [5 empty] | 2009-01-30 | [11 empty] | FALSE |  | 2485581 | 5741823 | 77 Ruru Road Bromley Christchurch |  | Approved on the 19.12.11 by Jo Mcafee of CCC: Reference number: rma92018726 - 11/01/2012 | CELLSITE | [7 empty] | 2009-06-08 | 2009-06-02 | [8 empty] | 2007-10-19
0 | CHC | 771 | CHC-060-046 |  |  |  | Christchurch City |  | TIER_1_ALL
0 | CHC | 772 | CHC-060-047 |  | CHC-060-047-E | Hornby South | Christchurch City |  | TIER_1_ALL | ACTIVE | GF | A | P3 | green |  |  | 25 | 25 |  | -43.5606 | 172.5216 |  |  |  |  | Microwave, Microwave | CHC-060-094-B, CHC-060-094-B | [5 empty] | 2009-03-17, 2009-03-17 | [5 empty] | 2008-08-27 | 3 | 2008-10-06 | 2015-09-03 |  |  | 2008-09-15 | 2008-09-26 | 2 | 2008-09-15 | 2008-09-26 |  | 2008-10-24 |  |  |  |  | 2008-10-23 | 2008-10-23 |  | 2008-08-29 |  | 2008-11-28 | 3 | 2 | 2009-01-20 | 2009-06-18 | 2009-03-05 |  |  |  |  | 2009-03-10 | 2009-03-10 | 2009-04-09 | 2009-04-08 |  | 2009-04-15 | 2009-04-15 | [8 empty] | 2009-05-13 | 2009-05-15 | 2009-05-13 | [6 empty] | 2009-05-15 |  |  |  |  | 2009-03-06 | 2009-03-05 | [11 empty] | FALSE |  | 2471358 | 5738427 | 76 Colombia Ave Hornby Christchurch |  |  | CELLSITE |  |  | 2015-11-05 |  |  |  |  | 2009-03-06 | 2008-12-11 | [8 empty] | 2008-07-22
0 | CHC | 773 | CHC-060-048 | Lyttelton Repair | CHC-060-048-A | Lyttelton | Christchurch City | 11 | TIER_1_ALL | ACTIVE | GF | A | OTHERS | grey |  |  | 30 | 30 |  | -43.6095 | 172.7214 |  |  |  |  | Microwave, Microwave | CHC-060-096-G, CHC-060-096-G | FALSE | FALSE |  |  | FALSE | 2009-04-21, 2009-04-21 | [5 empty] | 2008-04-21 | 2 | 2008-04-21 | 2008-04-29 |  |  | 2008-11-11 | 2008-11-03 | 2 | 2008-11-11 | 2008-11-03 | [6 empty] | 2008-10-29 | 2008-10-29 |  | 2008-09-16 |  | 2008-11-28 | 3 |  | 2008-11-28 | 2012-09-25 | 2009-02-20 | [5 empty] | 2009-03-24 | 2009-04-24 | 2009-04-24 |  | 2009-05-08 | 2009-05-08 | [8 empty] | 2009-06-16 | 2009-06-30 | 2009-06-16 |  |  |  |  | Damaged in Earthquakes. 17/10 Lyttelton Port will now keep the Quay so the existing site can stay with repairs to cabinet and pole. 07/11 Monitor fortnightly. Pole may need to move out of the way of other construction work. 16/04 How much is the ground moving? |  | 2009-06-30 |  |  |  |  | 2009-03-03 | 2009-02-20 | [6 empty] | TIER_1_INFILL |  |  |  |  | FALSE |  | 2487520 | 5733070 | Lyttelton Port Company, Lyttelton, Christchurch |  |  | CELLSITE | [7 empty] | 2009-03-20 | 2009-03-20 | [8 empty] | 2007-11-26
0 | CHC | 774 | CHC-060-049 | Hoon Hay | CHC-060-049-D | Hoon Hay | Christchurch City |  | TIER_1_ALL | ACTIVE | RSR | A | P4E | green |  |  | 18 | 18 |  | -43.5679 | 172.6153 |  |  |  |  | Microwave, Microwave, Leased Line | CHC-060-096-G, CHC-060-096-G, CHC-060-063-B | [5 empty] | 2008-09-05, 2008-09-05 | [5 empty] | 2008-02-20 | 4 | 2008-02-12 | 2014-11-11 |  |  | 2008-02-25 | 2008-02-25 | 3 | 2008-02-25 | 2008-02-25 | [6 empty] | 2008-09-23 | 2008-09-23 |  | 2008-04-29 |  | 2008-05-14 | 4 |  | 2008-06-16 | 2015-02-05 | [7 empty] | 2008-09-30 |  |  | 2008-10-21 | 2008-10-21 | [8 empty] | 2009-01-30 | 2009-03-31 | 2009-01-30 |  |  |  |  | Site Build & Site Design: Next survey to be done Feb 2010. |  | 2009-03-31 | [17 empty] | FALSE |  | 2478930 | 5737651 | Opposite 4 Lyttelton St Hoon Hay Christchurch |  |  | CELLSITE | [8 empty] | 2008-07-21 | [8 empty] | 2008-01-15
0 | CHC | 775 | CHC-060-050 |  | CHC-060-050-F | St Martins | Christchurch City |  | TIER_1_ALL | ACTIVE | GF | A | P4E | green |  |  | 18 | 18 |  | -43.5585 | 172.6545 |  |  |  |  | Microwave | CHC-060-064-J | [5 empty] | 2009-05-21 | [5 empty] | 2009-03-30 | 2 | 2009-03-27 | 2009-04-01 |  |  | 2009-04-30 | 2009-04-30 | 2 | 2009-04-30 | 2009-04-30 |  |  |  | 2009-04-15 |  |  | 2009-04-15 | 2009-04-07 | 2009-05-06 | 2009-04-29 |  | 2009-05-12 | 1 | 2 | 2009-05-11 | 2009-05-12 | 2009-06-11 |  |  |  |  | 2009-06-15 | 2009-06-15 | 2009-06-26 | 2009-06-26 |  | 2009-06-30 | 2009-06-29 | [8 empty] | 2009-06-30 | 2009-06-30 | 2009-06-30 | [6 empty] | 2009-06-30 |  |  |  |  | 2009-06-10 | 2009-06-11 | [11 empty] | FALSE |  | 2482099 | 5738719 | 90 Wilsons Road South St Martins Christchurch |  |  | CELLSITE |  |  | 2015-10-29 |  |  |  |  | 2009-05-20 | 2009-05-20 | [8 empty] | 2009-03-10
0 | CHC | 776 | CHC-060-051 |  | CHC-060-051-F | Waimairi | Christchurch City |  | TIER_1_ALL | ACTIVE | RSR | A6 | P4E | green |  |  | 18 | 18 |  | -43.5167 | 172.572 |  |  |  |  | Microwave | CHC-060-070-G | [5 empty] | 2009-05-20 |  |  |  |  | 2009-04-30 | 2009-04-29 | 4 | 2009-04-30 | 2009-06-24 |  |  | 2009-05-29 | 2009-05-29 | 2 | 2009-05-29 | 2009-05-29 |  | 2009-05-12 |  | 2009-05-15 |  |  | 2009-05-29 | 2009-05-29 | 2009-05-11 | 2009-05-27 |  | 2009-06-10 | 1 | 3 | 2009-06-09 | 2009-06-10 | 2009-06-23 |  |  |  |  | 2009-06-19 | 2009-06-19 | 2009-07-02 | 2009-07-02 |  | 2009-07-08 | 2009-07-08 | [8 empty] | 2009-07-14 | 2009-07-10 | 2009-07-14 | [6 empty] | 2009-07-10 |  |  |  |  | 2009-06-23 | 2009-06-23 | [11 empty] | FALSE |  | 2475404 | 5743323 | RSR Outside 203 Waimairi Road Christchurch |  |  | CELLSITE |  |  | 2014-09-19 |  |  |  |  | 2009-06-19 | 2009-06-19 | [8 empty] | 2009-05-15
0 | CHC | 777 | CHC-060-052 |  | CHC-060-052-D | Avonside West | Christchurch City |  | TIER_1_ALL | ACTIVE | GF | D | P2 | grey |  |  | 15 | 15 |  | -43.5256 | 172.6464 |  |  |  |  | Microwave | CHC-060-003-F | [5 empty] | 2009-02-13 | [5 empty] | 2008-10-21 | 4 | 2009-04-06 | 2009-04-02 |  |  | 2009-01-05 | 2009-01-13 | 1 | 2009-04-06 | 2009-04-08 |  | 2008-10-23 |  | 2008-11-27 |  |  | 2009-04-06 | 2008-11-27 | 2009-10-06 | 2008-12-12 |  | 2009-02-17 | 3 |  | 2009-10-16 | 2009-04-02 | 2009-04-23 | [5 empty] | 2009-03-20 | 2009-04-30 | 2009-04-29 |  | 2009-06-05 | 2009-06-05 | [8 empty] | 2009-06-29 | 2009-06-22 | 2009-06-29 |  |  |  |  | Site Build: Some paintwork to be done. |  | 2009-06-29 |  |  |  |  | 2009-04-23 | 2009-04-23 | [11 empty] | FALSE |  | 2481429 | 5742369 | 17 Nova Plc Christchurch |  |  | CELLSITE |  |  | 2015-10-21 |  |  |  |  | 2009-03-20 | 2009-03-20 | [8 empty] | 2008-09-30
0 | CHC | 778 | CHC-060-053 |  | CHC-060-053-E | Charleston | Christchurch City |  | TIER_1_ALL | ACTIVE | RSR | A | P4E | green |  |  | 18 | 18 |  | -43.5425 | 172.6648 |  |  |  |  | Microwave, Microwave | CHC-060-013-A, CHC-060-013-A | [5 empty] | 2008-04-24, 2008-04-24 | [5 empty] | 2008-03-25 | 3 | 2008-03-25 | 2008-08-20 |  |  | 2008-03-26 | 2008-03-26 | 3 | 2008-03-26 | 2008-03-26 | [6 empty] | 2008-05-05 | 2008-05-05 |  | 2008-04-29 |  | 2008-06-10 | 2 | 3 | 2008-08-22 | 2008-08-22 | [6 empty] | 2008-09-02 | 2008-10-21 | 2008-10-22 |  | 2008-10-29 | 2008-10-30 | [8 empty] | 2008-12-20 | 2009-02-27 | 2008-12-20 | [6 empty] | 2009-02-27 | [17 empty] | FALSE |  | 2482920 | 5740490 | Isabella Place and Ferry Road Junction Charleston Christchurch |  |  | CELLSITE |  |  | 2015-10-29 | [5 empty] | 2008-08-29 | [8 empty] | 2008-03-04
0 | CHC | 779 | CHC-060-054 |  | CHC-060-054-H | Heathcote | Christchurch City |  | TIER_1_ALL | ACTIVE | GF | A | P2 | grey |  |  | 20 | 20 |  | -43.5691 | 172.6885 |  |  |  |  | Microwave, Microwave | CHC-060-015-A, CHC-060-015-A | [5 empty] | 2008-04-24, 2008-04-24 | [5 empty] | 2008-03-28 | 2 | 2008-03-20 | 2008-03-28 |  |  | 2008-04-03 | 2008-04-03 | 2 | 2008-04-03 | 2008-04-03 | [6 empty] | 2008-05-21 | 2008-05-21 |  | 2008-04-04 |  | 2008-06-03 | 2 | 2 | 2008-08-11 | 2008-08-11 | [6 empty] | 2008-08-08 | 2008-09-24 | 2008-09-24 |  | 2008-10-10 | 2008-10-07 | [8 empty] | 2008-12-22 | 2008-12-11 | 2008-12-22 | [6 empty] | 2008-11-27 | [17 empty] | FALSE |  | 2484851 | 5737552 | 10 Chapmans Road Woolston Christchurch |  |  | CELLSITE | [8 empty] | 2008-08-01 | [8 empty] | 2008-02-25
0 | CHC | 780 | CHC-060-055 | Bexley | CHC-060-055-G | Bexley/New Repair | Christchurch City | 11 | TIER_1_ALL | ACTIVE | RSR | A | [7 empty] | -43.5242 | 172.728 |  | 2012-01-31 |  |  |  |  | FALSE | FALSE |  |  | FALSE |  | 2012-08-08 | 2012-08-08 | 2012-08-30 | 2012-08-30 |  | 2012-09-06 | 1 | 2012-09-13 | 2012-09-06 |  | 2012-10-18 | 2012-10-08 | 2012-10-18 |  |  |  | PERMITTED |  | 2012-11-12 | 2012-10-08 | 2012-11-12 | 1 | [15 empty] | 2012-11-10 | 2012-11-10 | 2012-12-10 | 2012-12-10 | [13 empty] | 2012-12-13 |  |  |  |  | 19/03 Joh to provide quote to SHIM pole and re-do foundation for cabinets. 01/05 PS1 won't be necessary. 07/05 Service life of 50 years is not required. Simple SHIM of pole and SKIM under cabinet is required. 23/7 Chris Adams is looking at reports and to make a recommendation this week. 30/7 Chris Adams to inspect next week on his trip to CHC. 6/8 Chris Adams to inspect and define solution this week. 13/8 Chris Adams has drawn a solution, change of pole position and new pole. 10/09 Alex Jorowski inspected. Providing design input into repair design. 17/9 Waiting on construction drawings. 24/10 CAR required from Transfield. | [12 empty] | 2012-09-17 | LOW | TIER_1_INFILL |  |  |  |  | FALSE |  | 2488024 | 5742545 | South New Brighton, 114 Bridge Street, Outside bridge Street Reserve, Christchurch |  |  | CELLSITE
0 | CHC | 781 | CHC-060-056 |  | CHC-060-056-D | Southshore | Christchurch City |  | TIER_1_ALL | ACTIVE | COLO | A | NOPOLE | grey |  | COSITE | 18 | 18 |  | -43.5374 | 172.7376 |  |  |  |  | Microwave | CHC-060-045-A | [5 empty] | 2009-08-06 | [5 empty] | 2007-05-01 | 1 | 2007-05-01 | 2007-05-01 |  |  | 2009-06-19 | 2009-06-15 |  | 2009-06-19 | 2009-06-15 |  | 2009-05-15 |  | 2009-06-26 |  |  | 2009-06-30 | 2009-06-29 | 2009-04-13 | 2007-05-01 |  | 2009-06-29 | 1 | 1 | 2009-06-29 | 2009-06-29 | 2009-10-05 |  |  |  |  | 2009-08-12 | 2009-08-12 | 2009-10-16 | 2009-10-13 |  | 2009-10-23 | 2009-10-21 | [8 empty] | 2009-11-06 | 2009-11-04 | 2009-11-06 | [6 empty] | 2009-11-04 |  |  |  |  | 2009-09-18 | 2009-10-05 | [11 empty] | FALSE |  | 2488804 | 5741085 | Off Ebbtide St Southshore Christchurch |  |  | CELLSITE | [7 empty] | 2009-08-04 | 2009-08-04 | [8 empty] | 2007-04-01
0 | CHC | 782 | CHC-060-057 |  |  |  | Christchurch City | 8 | TIER_1_ALL | [22 empty] | FALSE
0 | CHC | 783 | CHC-060-058 |  | CHC-060-058-A | Sydenham | Christchurch City |  | TIER_1_ALL | ACTIVE | GF | A | P2 | grey |  |  | 20 | 20 |  | -43.5441 | 172.6424 |  |  |  |  | Microwave, Microwave | CHC-060-004-C, CHC-060-004-C | [5 empty] | 2008-05-20, 2008-05-20 | [5 empty] | 2007-09-26 | 6 | 2007-10-30 | 2008-04-17 |  |  | 2008-04-30 | 2008-05-05 | 6 | 2008-04-30 | 2008-05-05 | [6 empty] | 2008-08-25 | 2008-08-25 |  | 2008-02-26 |  | 2008-05-27 | 2 | 6 | 2008-08-29 | 2008-08-29 | [6 empty] | 2008-10-13 | 2008-12-12 | 2008-12-08 |  | 2008-12-26 | 2008-12-12 | [8 empty] | 2008-12-19 | 2008-12-31 | 2008-12-19 | [6 empty] | 2008-12-31 | [17 empty] | FALSE |  | 2481114 | 5740306 | 61 Gasson Street Sydenham Christchurch |  |  | CELLSITE |  |  | 2015-10-29 | [5 empty] | 2008-09-10 | [8 empty] | 2007-09-07
0 | CHC | 784 | CHC-060-059 |  | CHC-060-059-H | City South | Christchurch City |  | TIER_1_ALL | ACTIVE | GF | A | P4E | green |  |  | 18 | 18 |  | -43.5371 | 172.6414 |  |  |  |  | Microwave | CHC-060-062-D | [5 empty] | 2009-02-03 | [5 empty] | 2008-11-21 | 2 | 2009-02-06 | 2009-02-05 |  |  | 2008-12-15 | 2008-12-12 | 2 | 2008-12-15 | 2008-12-17 |  | 2008-11-24 |  |  |  |  | 2009-01-22 | 2009-01-22 |  | 2008-12-18 |  | 2009-01-30 | 1 | 1 | 2009-01-30 | 2009-01-30 | 2009-04-09 |  |  |  |  | 2009-04-03 | 2009-04-03 | 2009-04-23 | 2009-04-22 |  | 2009-05-08 | 2009-05-06 | [8 empty] | 2009-05-11 | 2009-05-15 | 2009-05-11 | [6 empty] | 2009-05-15 |  |  |  |  | 2009-04-08 | 2009-04-09 | [11 empty] | FALSE |  | 2481026 | 5741084 | 246 St Asaph Street Christchurch |  |  | CELLSITE |  |  | 2015-10-21 |  |  |  |  | 2009-03-16 | 2009-03-26 | [8 empty] | 2008-10-28
0 | CHC | 785 | CHC-060-060 |  | CHC-060-060-C | Avonside | Christchurch City |  | TIER_1_ALL | ACTIVE | GF | A | P2 | grey |  |  | 15 | 15 |  | -43.5216 | 172.6558 |  |  |  |  | Microwave, Microwave | CHC-060-097-A, CHC-060-097-A | [5 empty] | 2009-03-10, 2009-03-10 | [5 empty] | 2008-02-09 | 2 | 2008-03-06 | 2008-03-27 |  |  | 2008-07-31 | 2008-07-25 | 2 | 2008-07-31 | 2008-07-25 | [6 empty] | 2008-11-14 | 2008-11-14 |  | 2008-04-29 |  | 2008-10-08 | 3 | 2 | 2009-01-15 | 2009-01-15 | 2008-12-22 |  |  |  |  | 2009-03-18 | 2009-03-13 | 2009-03-31 | 2009-03-31 |  | 2009-04-09 | 2009-04-08 | [8 empty] | 2009-04-24 | 2009-04-23 | 2009-04-24 | [6 empty] | 2009-04-24 |  |  |  |  | 2009-03-23 | 2008-12-22 | [11 empty] | FALSE |  | 2482188 | 5742812 | 265 Stanmore Rd (Also 18 Pavitt St) Avonside Christchurch |  |  | CELLSITE |  |  | 2015-10-15 |  |  |  |  | 2009-03-13 | 2009-03-06 | [8 empty] | 2008-01-10
0 | CHC | 786 | CHC-060-061 |  | CHC-060-061-M | Hagley East | Christchurch City |  | TIER_1_ALL | ACTIVE | RSR | A6 | P4D | green |  |  | 14 | 14 |  | -43.5324 | 172.6307 |  |  |  |  | Leased Line | CHC-060-063-B | [10 empty] | 2009-01-30 | 2009-01-30 | 1 | 2009-01-30 | 2009-01-30 |  |  | 2009-02-25 | 2009-02-10 |  | 2009-02-25 | 2009-02-12 |  | 2009-02-27 |  | 2009-02-04 |  |  | 2009-02-04 | 2009-02-04 |  | 2009-02-19 |  | 2009-03-12 | 2 | 1 | 2009-03-13 | 2009-04-14 | 2009-04-23 |  |  |  |  | 2009-04-16 | 2009-04-16 | 2009-05-05 | 2009-05-05 |  | 2009-05-12 | 2009-05-13 | [8 empty] | 2009-05-20 | 2009-05-23 | 2009-05-20 | [6 empty] | 2009-05-23 |  |  |  |  | 2009-04-23 | 2009-04-23 | [11 empty] | FALSE |  | 2480159 | 5741601 | Opposite 275 Montreal Street Christchurch CBD |  |  | CELLSITE |  |  | 2014-09-19 |  |  |  |  | 2009-04-16 | 2009-04-16 | [8 empty] | 2009-01-15
0 | CHC | 787 | CHC-060-062 |  | CHC-060-062-D | Sydenham North | Christchurch City |  | TIER_1_ALL | ACTIVE | GF | A | P2 | grey |  |  | 20 | 20 |  | -43.5411 | 172.6372 |  |  |  |  | Microwave, Microwave | CHC-060-004-C, CHC-060-004-C | [5 empty] | 2009-01-23, 2008-05-06 | [5 empty] | 2008-04-09 | 1 | 2008-04-10 | 2008-04-09 |  |  | 2008-11-11 | 2008-11-03 | 1 | 2008-11-11 | 2008-11-03 | [6 empty] | 2008-05-19 | 2008-05-19 |  | 2008-04-29 |  | 2008-08-25 | 1 | 1 | 2008-08-25 | 2008-08-25 | 2009-01-19 | [5 empty] | 2008-12-15 | 2009-01-30 | 2009-01-30 |  | 2009-03-11 | 2009-03-13 | [8 empty] | 2009-03-18 | 2009-03-13 | 2009-03-18 |  |  |  |  | None |  | 2009-03-13 |  |  |  |  | 2009-01-19 | 2009-01-19 | [11 empty] | FALSE |  | 2480692 | 5740639 | Near Rail Area off Caryle Street/Colombo Christchurch |  |  | CELLSITE |  |  | 2015-10-29 | [5 empty] | 2008-12-11 | [8 empty] | 2008-02-12
0 | CHC | 788 | CHC-060-063 |  |  |  | Christchurch City |  | TIER_1_ALL
0 | CHC | 789 | CHC-060-064 |  | CHC-060-064-J | Waltham | Christchurch City |  | TIER_1_ALL | ACTIVE | GF | A | P2 | grey |  |  | 20 | 20 |  | -43.549 | 172.6597 |  |  |  |  | Microwave, Microwave | CHC-060-004-C, CHC-060-004-C | [5 empty] | 2008-07-28, 2008-07-28 | [5 empty] | 2008-08-22 | 3 | 2008-08-22 | 2014-11-11 |  |  | 2008-09-29 | 2008-09-26 | 2 | 2008-09-29 | 2008-09-26 |  | 2008-09-01 |  |  |  |  | 2008-09-26 | 2008-09-26 |  | 2008-09-16 |  | 2008-10-08 | 3 |  | 2008-10-08 | 2015-02-05 | [7 empty] | 2008-12-18 |  |  | 2008-12-24 | 2008-12-24 | [8 empty] | 2008-12-24 | 2008-12-31 | 2008-12-24 | [6 empty] | 2008-12-24 | [17 empty] | FALSE |  | 2482515 | 5739777 | 501 Brougham St, Christchurch |  |  | CELLSITE |  |  | 2015-10-29 | [5 empty] | 2008-10-20 | [8 empty] | 2008-07-22
0 | CHC | 790 | CHC-060-065 |  |  |  | Christchurch City |  | TIER_1_ALL
0 | CHC | 791 | CHC-060-066 |  | CHC-060-066-E | Bryndwr | Christchurch City |  | TIER_1_ALL | ACTIVE | RSR | D6 | P4E | green |  |  | 15 | 15 |  | -43.5109 | 172.5826 |  |  |  |  | Microwave, Microwave | CHC-060-023-A, CHC-060-023-A | [5 empty] | 2008-11-21, 2008-11-21 | [5 empty] | 2008-11-14 | 6 |  | 2009-05-21 |  |  | 2009-05-21 | 2009-05-06 | 2 | 2009-06-05 | 2009-06-05 |  | 2009-04-15 |  | 2009-04-27 |  |  | 2009-05-21 | 2009-05-15 | 2009-04-13 | 2009-01-07 |  | 2009-05-21 | 1 | 1 | 2009-05-29 | 2009-05-21 | 2009-07-14 |  |  |  |  | 2009-06-15 | 2009-06-15 | 2009-07-20 | 2009-07-20 |  | 2009-07-24 | 2009-07-24 | [8 empty] | 2009-07-31 | 2009-07-31 | 2009-07-31 | [6 empty] | 2009-07-31 |  |  |  |  | 2009-07-14 | 2009-07-14 | [11 empty] | FALSE |  | 2476257 | 5743972 | Near Jellie Park 295 Ilam Road Christchurch |  |  | CELLSITE |  |  | 2014-09-19 |  |  |  |  | 2009-06-15 | 2009-06-15 | [8 empty] | 2008-10-10
0 | CHC | 792 | CHC-060-067 |  | CHC-060-067-F | Spencerville | Christchurch City |  | TIER_1_ALL | ACTIVE | GF | A | P3 | green |  |  | 25 | 25 |  | -43.4199 | 172.6859 |  |  |  |  | Microwave, Microwave | CHC-060-096-G, CHC-060-096-G | [5 empty] | 2008-11-17, 2008-11-17 | [5 empty] | 2008-11-21 | 2 | 2008-11-25 | 2009-03-09 |  |  | 2009-03-31 | 2009-03-31 | 1 | 2009-05-30 | 2009-05-22 |  | 2008-11-28 |  | 2009-03-23 |  |  | 2009-03-23 | 2009-03-17 |  | 2009-01-07 |  | 2009-01-23 | 1 | 1 | 2009-01-23 | 2009-01-23 | 2009-01-30 |  |  |  |  | 2009-04-09 | 2009-04-21 | 2009-06-12 | 2009-06-11 |  | 2009-06-19 | 2009-06-19 | [8 empty] | 2009-09-02 | 2009-08-24 | 2009-09-02 | [6 empty] | 2009-08-24 |  |  |  |  | 2009-04-20 | 2009-01-30 | [11 empty] | FALSE |  | 2484575 | 5754122 | Near Telecom Pole, 287 Spencerville Road Off Earlham St, Christchurch |  |  | CELLSITE | [7 empty] | 2009-04-22 | 2009-04-21 | [8 empty] | 2008-11-11
0 | CHC | 793 | CHC-060-068 |  | CHC-060-068-E | North Beach | Christchurch City |  | TIER_1_ALL | ACTIVE | GF | A | P4E | green |  |  | 18 | 18 |  | -43.4865 | 172.717 | [16 empty] | 2009-04-30 | 2009-04-23 | 2 | 2009-04-30 | 2009-05-21 |  |  | 2009-06-10 | 2009-06-11 | 2 | 2009-06-10 | 2009-06-11 |  | 2009-05-10 |  | 2009-05-11 |  |  | 2009-05-20 | 2009-05-15 | 2009-04-30 | 2009-05-15 |  | 2009-05-21 | 1 | 1 | 2009-05-20 | 2009-05-21 | 2009-06-18 |  |  |  |  | 2009-06-15 | 2009-06-17 | 2009-06-26 | 2009-06-26 |  | 2009-06-29 | 2009-06-29 | [8 empty] | 2009-06-30 | 2009-06-30 | 2009-06-30 | [6 empty] | 2009-06-30 |  |  |  |  | 2009-06-18 | 2009-06-18 | [11 empty] | FALSE |  | 2487123 | 5746738 | Waimairi Beach Golf Club 460 Bower Avenue Parklands Christchurch |  |  | CELLSITE | [7 empty] | 2009-06-15 | 2009-06-10 | [8 empty] | 2009-04-09
0 | CHC | 794 | CHC-060-069 |  | CHC-060-069-B | Dallington | Christchurch City |  | TIER_1_ALL | ACTIVE | RSR | A | P4E | green |  |  | 18 | 18 |  | -43.5065 | 172.6695 |  |  |  |  | Microwave, Microwave | CHC-060-045-A, CHC-060-045-A | [5 empty] | 2008-04-24, 2008-04-24 | [5 empty] | 2007-11-20 | 6 | 2008-02-20 | 2009-06-17 |  |  | 2008-12-03 | 2008-11-28 | 4 | 2008-12-03 | 2008-12-04 | [6 empty] | 2008-08-28 | 2008-08-26 |  | 2008-03-31 |  | 2008-09-02 | 2 | 3 | 2008-10-08 | 2008-10-08 | 2009-01-20 | [5 empty] | 2009-02-11 | 2009-02-18 | 2009-02-19 |  | 2009-02-27 | 2009-02-27 | [8 empty] | 2009-03-20 |  | 2009-03-20 |  |  |  |  | COMPLETE: Handover to Operations Team. RET to be checked. | [7 empty] | 2009-01-20 | [11 empty] | FALSE |  | 2483285 | 5744491 | Opposite 71 New Brighton Road Shirley Christchurch |  |  | CELLSITE |  |  | 2015-10-15 | [5 empty] | 2008-12-11 | [8 empty] | 2008-01-23
0 | CHC | 795 | CHC-060-070 |  | CHC-060-070-G | Hyde Park | Christchurch City |  | TIER_1_ALL | ACTIVE | GF | A | P2 | grey |  |  | 20 | 20 |  | -43.51 | 172.5499 |  |  |  |  | Microwave, Microwave | CHC-060-094-B, CHC-060-094-B | [5 empty] | 2009-03-17, 2009-03-17 | [5 empty] | 2008-09-19 | 2 | 2008-09-19 | 2008-09-23 |  |  | 2008-12-18 | 2008-12-01 | 2 | 2008-12-18 | 2008-12-04 |  | 2008-11-14 |  |  |  |  | 2008-11-14 | 2008-11-14 |  | 2008-09-22 |  | 2008-10-31 | 1 | 2 | 2008-10-31 | 2008-10-31 | 2009-01-19 | [5 empty] | 2009-01-08 | 2009-01-29 | 2009-01-29 |  | 2009-02-13 | 2009-02-09 | [8 empty] | 2009-03-31 | 2009-03-31 | 2009-03-31 | [6 empty] | 2009-03-31 |  |  |  |  | 2009-01-19 | 2009-01-19 | [11 empty] | FALSE |  | 2473612 | 5744062 | 144 Hawthornden Road Avonhead Christchurch |  |  | CELLSITE |  |  | 2015-11-05 | [5 empty] | 2008-12-11 | [8 empty] | 2008-08-25
0 | CHC | 796 | CHC-060-071 |  | CHC-060-071-E | Westlake | Christchurch City |  | TIER_1_ALL | ACTIVE | RSR | A | P4E | green |  |  | 18 | 18 |  | -43.5666 | 172.5476 |  |  |  |  | Microwave, Microwave | CHC-060-096-G, CHC-060-096-G | [5 empty] | 2008-12-17, 2008-12-17 | [5 empty] | 2008-09-17 | 2 | 2008-11-05 | 2008-09-29 |  |  | 2008-12-03 | 2008-11-28 | 2 | 2008-12-03 | 2008-12-04 |  | 2008-09-25 |  | 2008-10-17 |  |  | 2008-10-17 | 2008-10-17 |  | 2008-11-25 |  | 2009-01-30 | 1 | 2 | 2009-01-30 | 2009-01-30 | 2009-01-20 | [5 empty] | 2009-02-13 | 2009-02-27 | 2009-02-27 |  | 2009-03-10 | 2009-03-10 | [8 empty] | 2009-04-16 | 2009-04-15 | 2009-04-16 |  |  |  |  | COMPLETE: Handover to Operations Team |  | 2009-04-15 | [5 empty] | 2009-01-20 | [11 empty] | FALSE |  | 2473466 | 5737775 | Opposite Karting Club Carrs Road Westlake Christchurch |  |  | CELLSITE |  |  | 2015-11-05 | [5 empty] | 2009-02-09 | [8 empty] | 2008-09-01
0 | CHC | 797 | CHC-060-072 |  | CHC-060-072-E | Burwood | Christchurch City |  | TIER_1_ALL | ACTIVE | RSR | A | P4E | green |  |  | 15 | 15 |  | -43.4825 | 172.681 |  |  |  |  | Microwave, Microwave | CHC-060-074-A, CHC-060-074-A | [5 empty] | 2008-05-06, 2008-05-06 | [5 empty] | 2008-05-23 | 1 | 2008-06-30 | 2008-05-23 |  |  | 2008-09-26 | 2008-09-26 | 1 | 2008-09-26 | 2008-09-26 |  |  |  | 2008-06-30 |  |  | 2008-06-30 | 2008-06-30 |  | 2008-06-05 |  | 2008-09-04 | 2 | 1 | 2008-12-15 | 2008-12-15 | 2009-01-20 | [5 empty] | 2008-12-05 | 2009-02-27 | 2009-02-27 |  | 2009-03-13 | 2009-03-13 | [8 empty] | 2009-03-20 | 2009-03-20 | 2009-03-20 | [6 empty] | 2009-03-20 | [5 empty] | 2009-01-20 | [11 empty] | FALSE |  | 2484202 | 5747167 | 283 Burwood Road Cnr of Mairehau Rd and Burwood Rd, Burwood, Christchurch |  |  | CELLSITE | [8 empty] | 2008-10-20 | [8 empty] | 2008-03-18
0 | CHC | 798 | CHC-060-073 |  | CHC-060-073-E | Northcote East | Christchurch City |  | TIER_1_ALL | ACTIVE | RSR | A | P4E | green |  |  | 18 | 18 |  | -43.4857 | 172.6267 |  |  |  |  | Microwave | CHC-060-094-B | [5 empty] | 2009-05-27 |  |  |  |  | 2009-01-30 | 2009-01-30 | 1 | 2009-01-30 | 2009-01-30 |  |  | 2009-02-25 | 2009-02-10 |  | 2009-02-12 | 2009-02-12 |  | 2009-02-12 |  | 2009-03-03 |  |  | 2009-03-03 | 2009-02-27 | 2009-03-02 | 2009-03-09 |  | 2009-03-19 | 3 | 1 | 2009-03-20 | 2009-04-20 | 2009-04-28 |  |  |  |  | 2009-04-28 | 2009-04-28 | 2009-04-30 | 2009-04-30 |  | 2009-05-28 | 2009-05-28 | [8 empty] | 2009-06-05 | 2009-06-05 | 2009-06-05 | [6 empty] | 2009-06-05 |  |  |  |  | 2009-04-27 | 2009-04-28 | [11 empty] | FALSE |  | 2479817 | 5746791 | Opposite QEII Drive & Grimseys Road intersection Christchurch |  |  | CELLSITE |  |  | 2015-10-15 |  |  |  |  | 2009-04-28 | 2009-04-28 | [8 empty] | 2009-01-15
0 | CHC | 799 | CHC-060-074 |  | CHC-060-074-A | Parklands | Christchurch City |  | TIER_1_ALL | ACTIVE | GF | A | P2 | green |  |  | 20 | 20 |  | -43.4811 | 172.7054 |  |  |  |  | Microwave, Microwave | CHC-060-097-A, CHC-060-097-A | [5 empty] | 2008-08-18, 2008-09-18 | [5 empty] | 2008-01-31 | 3 |  | 2008-04-30 |  |  | 2008-07-31 | 2008-06-30 | 3 | 2008-07-31 | 2008-06-30 | [6 empty] | 2008-05-26 | 2008-05-26 |  | 2008-02-26 |  | 2008-05-16 | 2 | 3 | 2008-05-16 | 2008-08-01 | 2008-12-18 | [5 empty] | 2008-11-24 | 2009-01-23 | 2009-01-16 |  | 2009-02-06 | 2009-01-23 | [8 empty] | 2009-02-05 | 2009-02-18 | 2009-02-05 |  |  |  |  | COMPLETE: Handover to Operations Team. |  | 2009-02-18 | [5 empty] | 2008-12-18 | [11 empty] | FALSE |  | 2486180 | 5747330 | 60 Queenspark Drive Christchurch |  |  | CELLSITE | [8 empty] | 2008-09-15 | [8 empty] | 2008-01-14
0 | CHC | 800 | CHC-060-075 |  | CHC-060-075-C | Sparks | Christchurch City |  | TIER_1_ALL | ACTIVE | GF | A | P3 | grey |  |  | 30 | 30 |  | -43.5783 | 172.5823 |  |  |  |  | Microwave, Microwave | CHC-060-094-B, CHC-060-094-B | [5 empty] | 2009-03-18, 2009-03-18 | [5 empty] | 2008-09-12 | 3 | 2009-02-20 | 2009-02-17 |  |  | 2008-12-01 | 2008-12-01 | 1 | 2009-04-30 | 2009-03-23 | [6 empty] | 2008-10-31 | 2008-10-31 |  | 2008-11-20 |  | 2008-12-05 | 3 | 1 | 2009-02-17 | 2009-03-02 | 2009-03-05 |  |  |  |  | 2009-03-18 | 2009-03-13 | 2009-05-18 | 2009-05-18 |  | 2009-05-25 | 2009-05-25 | [8 empty] | 2009-05-30 | 2009-05-30 | 2009-05-30 | [6 empty] | 2009-05-30 |  |  |  |  | 2009-03-06 | 2009-03-05 | [11 empty] | FALSE |  | 2476276 | 5736488 | 381 - 391 Sparks Rd Halswell Christchurch |  |  | CELLSITE | [7 empty] | 2009-03-06 | 2009-03-06 | [8 empty] | 2008-08-25
0 | CHC | 801 | CHC-060-076 |  | CHC-060-076-A | The Causeway | Christchurch City |  | TIER_1_ALL | ACTIVE | RSR | A | P4E | green |  |  | 15 | 15 |  | -43.556 | 172.7221 |  |  |  |  | Leased Line | CHC-060-063-B | [11 empty] | 2007-12-20 | 5 | 2008-12-20 | 2008-09-17 |  |  | 2008-02-25 | 2008-09-12 | 4 | 2008-02-25 | 2008-09-12 | [6 empty] | 2008-09-26 | 2008-09-26 |  | 2008-04-29 |  | 2008-05-14 | 3 | 5 | 2008-10-08 | 2008-10-08 | [6 empty] | 2008-10-23 | 2008-11-28 | 2008-11-30 |  | 2008-12-12 | 2008-12-19 | [8 empty] | 2008-12-20 | 2009-02-27 | 2008-12-20 | [6 empty] | 2009-02-27 | [17 empty] | FALSE |  | 2487556 | 5739016 | Causeway Main Rd Redcliffs Christchurch |  |  | CELLSITE | [8 empty] | 2008-10-13 | [8 empty] | 2007-11-21
0 | CHC | 802 | CHC-060-077 |  | CHC-060-077-D | Mt Pleasant | Christchurch City |  | TIER_1_ALL | ACTIVE | GF | A | P4E | green |  |  | 12 | 12 |  | -43.5631 | 172.7164 |  |  |  |  | Leased Line | CHC-060-063-B | [11 empty] | 2008-03-04 | 9 | 2009-02-06 | 2010-03-03 |  |  | 2009-03-27 | 2009-03-02 | 8 | 2009-03-22 | 2009-03-27 |  | 2009-01-22 |  | 2009-02-04 |  |  | 2009-03-13 | 2009-02-04 |  | 2009-01-21 |  | 2009-03-30 | 2 | 8 | 2009-03-27 | 2009-04-20 | 2009-04-28 |  |  |  |  | 2009-04-20 | 2009-04-20 | 2009-04-30 | 2009-04-30 |  | 2009-05-21 | 2009-05-21 | [8 empty] | 2009-05-21 | 2009-05-24 | 2009-05-21 | [6 empty] | 2009-05-24 |  |  |  |  | 2009-04-27 | 2009-04-28 | [11 empty] | FALSE |  | 2487101 | 5738225 | Corner Billys track Major Hornbrook Road Christchurch |  |  | CELLSITE | [7 empty] | 2009-04-20 | 2009-04-22 | [8 empty] | 2008-02-11
0 | CHC | 803 | CHC-060-078 |  | CHC-060-078-E | Cranford | Christchurch City |  | TIER_1_ALL | ACTIVE | RSR | A | P4E | green |  |  | 18 | 18 |  | -43.4979 | 172.6283 |  |  |  |  | Microwave | CHC-060-097-A | [5 empty] | 2009-02-17 | [5 empty] | 2008-12-12 | 2 | 2009-01-07 | 2009-01-07 |  |  | 2009-02-13 | 2009-02-10 | 1 | 2009-02-12 | 2009-02-12 |  | 2009-01-12 |  |  |  |  | 2009-01-29 | 2009-01-29 | 2009-03-02 | 2009-03-09 |  | 2009-03-16 | 3 | 2 | 2009-03-14 | 2009-04-20 | 2009-04-16 |  |  |  |  | 2009-04-20 | 2009-04-20 | 2009-04-30 | 2009-04-30 |  | 2009-05-18 | 2009-05-18 | [8 empty] | 2009-05-26 | 2009-05-27 | 2009-05-26 |  |  |  |  | COMPLETE: Handover to Operations Team |  | 2009-05-27 |  |  |  |  | 2009-04-16 | 2009-04-16 | [11 empty] | FALSE |  | 2479949 | 5745433 | 319 Cranford Street, Christchurch On RSR adjoining the above property. |  |  | CELLSITE |  |  | 2015-10-15 |  |  |  |  | 2009-04-20 | 2009-04-20 | [8 empty] | 2008-12-04
0 | CHC | 804 | CHC-060-079 |  | CHC-060-079-B | Avondale CHC | Christchurch City | 8 | TIER_1_ALL | ACTIVE | RSR | A | P4D | green |  |  | 15 | 15 |  | -43.5012 | 172.691 |  |  |  |  | Leased Line | CHC-060-063-B | FALSE | FALSE |  |  | FALSE | [6 empty] | 2008-02-20 | 4 | 2008-03-26 | 2010-01-26 |  |  | 2008-02-25 | 2008-02-25 | 1 | 2008-02-25 | 2008-02-25 | [6 empty] | 2008-05-19 | 2008-05-19 |  | 2008-03-31 |  | 2008-04-25 | 2 | 1 | 2008-09-04 | 2008-09-04 | [6 empty] | 2008-09-16 | 2008-09-30 | 2008-09-30 |  | 2008-10-21 | 2008-10-20 | [8 empty] | 2008-12-24 | 2009-02-27 | 2008-12-24 |  |  |  |  | Damaged in earthquakes. Site to be replaced. 19/03 SHIM completed. |  | 2009-02-27 | [17 empty] | FALSE |  | 2485019 | 5745089 | Opposite 345 New Brighton Road Burwood Christchurch |  |  | CELLSITE | [8 empty] | 2008-09-10 | [8 empty] | 2008-01-15
0 | CHC | 805 | CHC-060-080 | New Brighton | CHC-060-080-B | QEII | Christchurch City | 11 | TIER_1_ALL | ACTIVE | GF | A | P2 | green |  |  | 15 | 15 |  | -43.495 | 172.7101 |  |  |  |  | Microwave, Microwave | CHC-060-087-A, CHC-060-087-A | FALSE | FALSE |  |  | FALSE | 2007-10-16, 2007-10-16 | [5 empty] | 2008-02-15 | 3 |  |  |  |  | 2008-07-31 | 2008-08-06 | 3 | 2008-07-31 | 2008-08-06 | PERMITTED | [5 empty] | 2008-10-23 | 2008-10-23 |  | 2008-04-29 |  | 2009-01-13 | 3 |  |  | 2013-12-12 | 2009-01-05 | [5 empty] | 2008-11-17 |  | 2009-01-15 | [11 empty] | 2009-02-05 |  | 2013-01-18 |  |  |  |  | 05/12 Alternative design to be quoted. 21/05 CPT ground investigations. 29/05 NT to follow up with Bruce to ensure drawings are underway. 13/8 New pile foundation under existing damaged Plinth. |  | 2009-02-10 | [5 empty] | 2009-01-05 | [6 empty] | TIER_1_INFILL |  |  | BUILD |  | FALSE |  | 2486567 | 5745789 | QE II Shop Parade 227 Travis Road New Brighton Christchurch |  | No planning required, EQ damage remedial work - 16/07/2012 | CELLSITE | [8 empty] | 2008-11-14 | [8 empty] | 2007-11-14
0 | CHC | 806 | CHC-060-081 | Cashmere | CHC-060-081-F | Cashmere | Christchurch City |  | TIER_1_ALL | ACTIVE | GF | A | P2 | green |  |  | 20 | 20 |  | -43.5752 | 172.6055 |  |  |  |  | Microwave | CHC-060-096-G | [5 empty] | 2008-10-15 | [5 empty] | 2008-10-09 | 4 | 2008-11-25 | 2014-11-11 |  |  | 2008-09-30 | 2008-09-26 | 3 | 2008-09-30 | 2008-09-26 | [6 empty] | 2008-12-18 | 2008-12-18 |  | 2008-10-21 |  | 2008-11-28 | 3 |  | 2008-11-28 | 2015-02-05 | 2009-02-05 | [6 empty] | 2009-02-27 |  |  | 2009-03-14 | 2009-02-20 | [8 empty] | 2009-03-30 | 2009-03-30 | 2009-03-30 |  |  |  |  | Site Build: verge needs to be fixed. RET functional. |  | 2009-03-30 | [5 empty] | 2009-02-05 | [11 empty] | FALSE |  | 2478146 | 5736838 | 239 Cashmere Rd, Westmorland, Christchurch |  |  | CELLSITE | [8 empty] | 2009-02-06 | [8 empty] | 2008-09-15
0 | CHC | 807 | CHC-060-082 |  | CHC-060-082-K | Richmond | Christchurch City |  | TIER_1_ALL | ACTIVE | RSR | D | P4E | green |  | STANDALONE | 14 |  |  | -43.5249 | 172.6727 | [17 empty] | 2009-06-13 | 2 | 2009-06-13 | 2009-06-23 |  |  | 2009-07-23 | 2009-07-23 | 2 | 2009-07-23 | 2009-07-23 |  |  |  | 2009-06-30 |  |  | 2009-06-30 | 2009-06-29 |  | 2009-07-03 |  | 2009-07-03 | 1 | 2 | 2009-07-03 | 2009-07-03 | 2009-08-27 |  |  |  |  | 2009-08-18 | 2009-08-18 | 2009-08-27 | 2009-08-27 |  | 2009-09-11 | 2009-09-11 | [8 empty] | 2009-09-17 | 2009-09-18 | 2009-09-17 | [6 empty] | 2009-09-11 |  |  |  |  | 2009-08-27 | 2009-08-27 | [11 empty] | FALSE |  | 2483555 | 5742450 | RSR Beside BP Garage 706 Gloucester Street (corner of Woodham Road) Avonside Christchurch |  |  | CELLSITE |  |  | 2015-10-15 |  |  |  |  | 2009-08-18 | 2009-08-18 | [8 empty] | 2009-06-05
0 | CHC | 808 | CHC-060-083 |  | CHC-060-083-F | Halswell | Christchurch City |  | TIER_1_ALL | ACTIVE | RSR | A | P4E | grey |  |  | 18 | 18 |  | -43.5624 | 172.5795 |  |  |  |  | Microwave, Microwave | CHC-060-094-B, CHC-060-094-B | [5 empty] | 2009-05-18, 2009-05-18 | [5 empty] | 2009-03-09 | 7 | 2009-03-06 | 2013-09-16 |  |  | 2009-04-21 | 2009-04-22 | 1 | 2009-04-21 | 2009-04-22 |  | 2009-03-08 |  | 2009-04-06 |  |  | 2009-04-06 | 2009-03-20 | 2009-03-13 | 2009-03-16 |  | 2009-03-18 | 3 | 4 | 2009-03-20 | 2009-04-20 | 2009-04-08 |  |  |  |  | 2009-04-20 | 2009-04-22 | 2009-04-30 | 2009-04-30 |  | 2009-05-27 | 2009-05-27 | [8 empty] | 2009-06-02 | 2009-05-30 | 2009-06-02 |  |  |  |  | As Builts: Needs to go to Transit Site Build: Reinstatement required |  | 2009-06-03 |  |  |  |  | 2009-05-15 | 2009-04-08 | [11 empty] | FALSE |  | 2476040 | 5738248 | RSR NZTA SH73 Halswell Road Christchurch |  |  | CELLSITE |  |  | 2015-11-05 |  |  |  |  | 2009-04-20 | 2009-04-20 | [8 empty] | 2009-03-09
0 | CHC | 809 | CHC-060-084 |  | CHC-060-084-D | Clearwater | Christchurch City |  | TIER_1_ALL | ACTIVE | GF | A | P2 | green |  |  | 20 | 20 |  | -43.4523 | 172.6103 |  |  |  |  | Microwave, Microwave | CHC-060-097-A, CHC-060-097-A | [5 empty] | 2008-06-27, 2008-06-27 | [5 empty] | 2008-08-11 | 2 | 2008-11-25 | 2008-11-25 |  |  | 2008-10-31 | 2008-10-09 | 2 | 2008-10-31 | 2008-10-09 |  | 2008-08-22 |  | 2008-09-26 |  |  | 2008-12-18 | 2008-12-18 |  | 2008-08-29 |  | 2008-09-19 | 2 | 2 | 2008-11-26 | 2008-11-26 | 2009-01-16 | [5 empty] | 2009-01-14 | 2009-02-20 | 2009-02-20 |  | 2009-03-06 | 2009-03-06 | [8 empty] | 2009-03-10 | 2009-03-16 | 2009-03-10 | [6 empty] | 2009-03-16 |  |  |  |  | 2009-01-12 | 2009-01-16 | [11 empty] | FALSE |  | 2478467 | 5750497 | 172 Johns Road Christchurch |  |  | CELLSITE |  |  | 2015-10-19 | [5 empty] | 2008-12-19 | [8 empty] | 2008-06-30
0 | CHC | 810 | CHC-060-085 |  | CHC-060-085-C | Islington | Christchurch City |  | TIER_1_ALL | ACTIVE | COLO | A | COLO | grey |  | COSITE | 20 | 20 |  | -43.5388 | 172.5112 |  |  |  |  | Microwave, Microwave | CHC-060-094-B, CHC-060-094-B | [5 empty] | 2008-04-18, 2009-03-17 | [5 empty] | 2008-02-16 | 5 | 2008-09-29 | 2008-09-29 |  |  | 2009-01-01 | 2008-12-22 | 5 | 2009-01-05 | 2009-01-01 |  | 2008-11-25 |  | 2008-11-25 |  |  | 2008-11-25 | 2008-11-25 |  | 2008-04-29 |  | 2008-11-13 | 2 | 5 | 2008-11-13 | 2009-09-17 | [6 empty] | 2009-02-16 | 2009-03-09 | 2009-02-27 |  | 2009-04-03 | 2009-04-03 | [8 empty] | 2009-04-06 | 2009-04-10 | 2009-04-06 | [6 empty] | 2009-04-10 | [17 empty] | FALSE |  | 2470504 | 5740843 | Ohau Drive Off Moffet Street Hei Hei Christchurch |  |  | CELLSITE |  |  | 2015-11-05 | [5 empty] | 2009-02-09 | [8 empty] | 2008-01-10
0 | CHC | 811 | CHC-060-086 | Casebrook | CHC-060-086-C | Casebrook - Relocate | Christchurch City |  | TIER_1_ALL | ACTIVE | GF | A | P2 | Grey | INLINE |  | 20 | 20 |  | -43.4775 | 172.5905 | [12 empty] | 2014-08-25 | 2014-08-25 | 2014-08-28 | 2014-08-28 | 2014-09-12 | 2014-09-08 | 1 | 2014-09-19 | 2014-09-08 | 2014-09-19 |  | 2014-09-26 |  |  | 2014-09-26 |  | PERMITTED | 2014-09-22 |  | 2014-10-17 |  |  | 2014-10-17 |  |  |  |  | 2014-09-29 | 1 |  |  | 2014-09-29 | [5 empty] | 2014-11-18 | 2014-11-18 | 2014-11-18 | 2014-11-18 | [13 empty] | 2014-11-18 |  |  |  |  | RElocate site to alternative position next to Bowling Greens. Site Acq to complete discussion with RM Design/Papanui Club re costs to relocate. Siote relocated, using existing mast and cabinets from Candidate A to this location | [17 empty] | BUILD |  | FALSE |  | 2476879 | 5747690 | 310 Sawyers Arms Rd Papanui |  |  | CELLSITE |  |  | 2015-10-12 | [14 empty] | 2014-08-28
0 | CHC | 812 | CHC-060-087 |  | CHC-060-087-A | Bexley North | Christchurch City | 8 | TIER_1_ALL | ACTIVE | GF | A | P2 | grey |  |  | 20 | 20 |  | -43.5031 | 172.7112 |  |  |  |  | Microwave | CHC-060-097-A | FALSE | FALSE |  |  | FALSE | [6 empty] | 2008-01-23 | 1 | 2008-01-23 | 2008-01-23 |  |  | 2008-04-03 | 2008-04-03 | 1 | 2008-04-03 | 2008-04-03 | [6 empty] | 2008-02-22 | 2008-02-22 |  | 2008-03-12 |  | 2008-04-30 | 1 | 1 | 2008-04-30 | 2008-04-30 | [6 empty] | 2008-05-30 | 2008-08-08 | 2008-08-08 |  | 2008-08-22 | 2008-09-01 | [8 empty] | 2009-01-09 | 2009-03-31 | 2009-01-09 |  |  |  |  | 23/01 Transfield to straighten pole on bolts to improve public appearance for interim. CRs required to pan and tilt all links. To make location safe for repair and rebuild: 30/01 NT & Dawie idea to plate bolt walls together. John to provide price. 13/02 building being sold soon. New owner willing to complete repair works internally but cost to 2d needs to be compared to Transfield's quote first. 03/04 Constructor quote received. SA to ask LL to resight. |  | 2009-03-31 | [17 empty] | FALSE |  | 2486653 | 5744882 | 12 C Bower Avenue New Brighton Christchurch |  |  | CELLSITE | [8 empty] | 2008-07-21 | [8 empty] | 2007-10-12
0 | CHC | 813 | CHC-060-088 | Addington | CHC-060-088-L | Addington | Christchurch City |  | TIER_1_ALL | ACTIVE | RSR | A6 | P4E | green |  |  | 18 | 18 |  | -43.5477 | 172.6217 |  |  |  |  | Microwave, Microwave | CHC-060-004-C, CHC-060-004-C | [5 empty] | 2009-05-05, 2009-05-05 |  |  |  |  | 2009-01-30 | 2009-01-30 | 4 | 2009-03-20 | 2014-11-11 |  |  | 2009-02-25 | 2009-02-10 |  | 2009-04-09 | 2009-04-08 |  | 2009-02-03 |  | 2009-02-27 |  |  | 2009-04-15 | 2009-04-15 |  | 2009-03-30 |  | 2009-03-30 | 4 |  | 2009-03-27 | 2015-02-05 | 2009-04-16 |  |  |  |  | 2009-05-04 |  | 2009-05-29 |  |  | 2009-06-09 | 2009-06-08 | [8 empty] | 2009-06-12 | 2009-06-12 | 2009-06-12 |  |  |  |  | COMPLETE: Handover to Operations Team. RET to be fixed. |  | 2009-06-12 |  |  |  |  | 2009-04-16 | 2009-04-16 | [11 empty] | FALSE |  | 2479441 | 5739905 | Corner of Brougham and Selwyn Streets Addington Christchurch |  |  | CELLSITE |  |  | 2014-09-19 |  |  |  |  | 2009-04-15 | 2009-04-22 | [8 empty] | 2009-01-15
0 | CHC | 814 | CHC-060-089 |  | CHC-060-089-A | Woolston | Christchurch City |  | TIER_1_ALL | ACTIVE | GF | A | P2 | grey |  |  | 20 | 20 |  | -43.5491 | 172.6808 |  |  |  |  | Microwave, Microwave | CHC-060-016-A, CHC-060-016-A | [5 empty] | 2008-12-16, 2008-12-18 | [5 empty] | 2007-09-26 | 3 | 2008-10-30 | 2008-01-17 |  |  | 2008-10-31 | 2008-10-01 | 3 | 2008-10-31 | 2008-10-01 |  |  |  | 2008-10-28 |  |  | 2008-10-28 | 2008-10-28 |  | 2008-09-22 |  | 2008-12-24 | 1 | 3 | 2008-12-24 | 2008-12-24 | 2009-01-23 | [5 empty] | 2009-02-19 | 2009-03-13 | 2009-03-12 |  | 2009-03-23 | 2009-03-20 | [8 empty] | 2009-03-31 | 2009-03-31 | 2009-03-31 | [6 empty] | 2009-03-31 |  |  |  |  | 2009-01-19 | 2009-01-23 | [11 empty] | FALSE |  | 2484214 | 5739762 | 580 Ferry Rd, Woolston, Christchurch |  |  | CELLSITE | [8 empty] | 2008-12-24 | [8 empty] | 2007-09-07
0 | CHC | 815 | CHC-060-090 |  | CHC-060-090-D | Yaldhurst | Christchurch City |  | TIER_1_ALL | ACTIVE | GF | A | P2 | grey |  |  | 20 | 20 |  | -43.5118 | 172.5039 |  |  |  |  | Microwave, Microwave | CHC-060-085-C, CHC-060-085-C | [5 empty] | 2009-03-26, 2009-03-26 | [5 empty] | 2007-11-30 | 2 | 2008-01-17 | 2008-01-17 |  |  | 2008-03-12 | 2008-03-12 | 2 | 2008-03-12 | 2008-03-12 | [6 empty] | 2008-02-22 | 2008-02-22 |  | 2008-02-12 |  | 2008-05-13 | 2 | 2 | 2008-07-04 | 2008-07-04 | [6 empty] | 2008-06-03 | 2008-06-30 | 2008-06-30 |  | 2008-07-14 | 2008-07-25 | [8 empty] | 2009-04-09 | 2009-04-10 | 2009-04-09 | [6 empty] | 2009-04-10 | [17 empty] | FALSE |  | 2469900 | 5743838 | 33 School Road Christchurch |  |  | CELLSITE | [8 empty] | 2008-05-14 | [8 empty] | 2007-10-29
0 | CHC | 816 | CHC-060-091 |  | CHC-060-091-D | Somerfield | Christchurch City |  | TIER_1_ALL | ACTIVE | RSR | A | P4E | green |  |  | 18 | 18 |  | -43.5598 | 172.6195 |  |  |  |  | Microwave | CHC-060-035-C | [5 empty] | 2009-02-10 | [5 empty] | 2008-04-03 | 5 | 2008-04-03 | 2009-06-02 |  |  | 2008-02-25 | 2008-02-25 | 1 | 2008-02-25 | 2008-02-25 | [6 empty] | 2008-05-26 | 2009-06-12 |  | 2008-04-29 |  | 2008-05-27 | 3 | 5 | 2008-09-19 | 2009-06-02 | [6 empty] | 2008-09-24 | 2008-10-31 | 2008-10-31 |  | 2009-01-23 | 2009-01-16 | [8 empty] | 2009-01-29 | 2009-01-30 | 2009-01-29 | [6 empty] | 2009-01-30 | [17 empty] | FALSE |  | 2479269 | 5738558 | Opposite 75 Frankleigh St, Sydenham, Christchurch |  |  | CELLSITE |  |  | 2015-10-29 | [5 empty] | 2008-09-23 | [8 empty] | 2008-02-07
0 | CHC | 817 | CHC-060-092 |  | CHC-060-092-G | Northcote West | Christchurch City |  | TIER_1_ALL | ACTIVE | RSR | A | P4E | Green |  | STANDALONE | 18 | 18 | 1 | -43.4843 | 172.607 | 2009-10-12 | 2009-10-12 | 2010-02-12 | 2010-02-12 | Microwave | CHC-060-086-A | TRUE | TRUE | 2009-10-12 | 2009-10-12 | TRUE | 2010-01-25 | [5 empty] | 2010-02-08 | 2 | 2010-05-27 | 2010-06-30 |  |  | 2010-07-26 | 2010-07-27 |  | 2010-07-26 | 2010-08-05 | PERMITTED | 2010-05-03 |  | 2010-05-19 |  |  | 2010-05-24 | 2010-05-19 |  |  |  | 2010-06-30 | 1 | 1 | 2010-06-30 | 2010-06-30 | 2010-07-26 |  |  |  |  | 2010-08-16 | 2010-08-16 | 2010-08-23 | 2010-08-23 |  | 2010-08-26 | 2010-08-31 | [8 empty] | 2010-08-31 | 2010-08-31 | 2010-08-31 |  |  |  |  | Construction timeframe will require higher mpA concrete to be used. PM to discuss with design. |  | 2010-08-31 |  |  |  |  | 2010-07-26 | 2010-07-26 | [11 empty] | FALSE |  | 2478217 | 5746938 | Opposite 156 Vagues Rd, Christchurch |  |  | CELLSITE |  |  | 2015-10-12 |  |  |  |  | 2010-08-16 | 2010-08-16 | [8 empty] | 2010-01-25
0 | CHC | 818 | CHC-060-093 |  | CHC-060-093-E | Sydenham South | Christchurch City |  | TIER_1_ALL | ACTIVE | RSR | A | P4E | grey |  |  | 18 | 18 |  | -43.5506 | 172.6344 |  |  |  |  | Microwave, Microwave | CHC-060-064-J, CHC-060-064-J | [5 empty] | 2009-04-29, 2009-04-30 | 2009-01-27 |  |  |  | 2009-02-06 | 2009-02-05 | 1 | 2009-02-06 | 2009-02-05 |  |  | 2009-02-28 | 2009-03-03 | 1 | 2009-03-06 | 2009-03-03 |  | 2009-02-06 |  | 2009-02-20 |  |  | 2009-02-19 | 2009-02-19 |  | 2009-02-05 |  | 2009-03-09 | 2 | 1 | 2009-03-06 | 2009-04-14 | 2009-04-09 |  |  |  |  | 2009-04-14 | 2009-04-14 | 2009-04-30 | 2009-04-30 |  | 2009-05-25 | 2009-05-25 | [8 empty] | 2009-06-19 | 2009-06-19 | 2009-06-19 |  |  |  |  | As Builts: None. |  | 2009-06-19 |  |  |  |  | 2009-04-08 | 2009-04-09 | [11 empty] | FALSE |  | 2480469 | 5739587 | Opposite 240 Milton Street Christchurch |  |  | CELLSITE |  |  | 2015-10-29 |  |  |  |  | 2009-04-14 | 2009-04-14 | [8 empty] | 2009-01-28
0 | CHC | 819 | CHC-060-094 |  | CHC-060-094-B | Middleton | Christchurch City |  | TIER_1_ALL | ACTIVE | GF | A6 | LATTICE | grey |  |  | 35 | 35 |  | -43.5405 | 172.5799 | [17 empty] | 2008-05-08 | 6 | 2008-12-05 | 2015-09-03 |  |  | 2009-05-01 | 2009-05-04 | 4 | 2009-01-16 | 2009-01-16 | DISCRETIONARY_FULL |  | 2011-09-05 | 2008-11-12 | 2012-01-11 | 4 | 2008-11-12 | 2008-11-12 |  | 2008-09-08 |  | 2008-11-17 | 8 |  | 2008-12-24 | 2011-10-18 | 2009-01-30 | [5 empty] | 2009-01-20 | 2009-03-20 | 2009-03-20 |  | 2009-04-22 | 2009-04-22 | [8 empty] | 2009-04-28 | 2009-04-30 | 2009-04-28 | [6 empty] | 2009-04-30 |  |  |  |  | 2009-01-06 | 2009-01-30 | [11 empty] | FALSE |  | 2476058 | 5740683 | Toll - Middleton, 7 Matipo St, (Also known as 258 Annex Rd) Middleton, Christchurch |  | Approved by council on the 11.01.2012 by Jo Mcafee, consent number 92018735 with rev 6 plans - 13/02/2012 | CELLSITE |  |  | 2014-09-19 |  |  |  |  | 2009-01-06 | 2009-01-16 | [8 empty] | 2007-12-24
0 | CHC | 820 | CHC-060-095 |  | CHC-060-095-B | St Albans | Christchurch City | 8 | TIER_1_ALL | ACTIVE | RSR | A | P4E | green |  |  | 18 | 18 |  | -43.5081 | 172.6375 |  |  |  |  | Microwave, Microwave | CHC-060-097-A, CHC-060-097-A | FALSE | FALSE |  |  | FALSE | 2009-05-07, 2009-05-07 | [5 empty] | 2008-11-14 | 3 | 2011-12-16 | 2011-11-30 |  |  | 2009-02-25 | 2009-02-10 | 1 | 2009-02-12 | 2009-02-12 | [6 empty] | 2009-05-07 | 2009-05-07 |  | 2008-12-18 |  | 2009-01-30 | 3 | 2 | 2011-01-15 | 2009-05-12 | 2009-04-28 |  |  |  |  | 2009-04-24 | 2009-04-24 | 2009-05-23 | 2009-05-23 |  | 2009-05-28 | 2009-05-28 | [8 empty] | 2009-05-30 | 2009-06-05 | 2009-05-30 |  |  |  |  | HG. As-builts - ongoing. 29/05 ODU needs to be replaced. |  | 2009-06-05 |  |  |  |  | 2009-04-27 | 2009-04-28 | [11 empty] | FALSE |  | 2480699 | 5744310 | 117 Cranford Street Carpark St Albans Christchurch |  |  | CELLSITE |  |  | 2015-10-15 |  |  |  |  | 2009-04-24 | 2009-04-24 | [8 empty] | 2008-10-10
0 | CHC | 821 | CHC-060-096 |  | CHC-060-096-G | Sugarloaf | Christchurch City |  | TIER_1_ALL | ACTIVE | COLO | TX | COLO |  |  | COSITE | 0 | 0 |  | -43.6031 | 172.6489 |  |  |  |  | Microwave | CHC-060-063-B | [11 empty] | 2007-05-01 | 1 | 2007-05-01 | 2007-05-01 |  |  | 2009-01-13 | 2009-01-13 |  | 2009-01-20 | 2009-01-20 |  |  |  | 2008-12-25 |  |  | 2008-12-25 | 2008-12-25 |  | 2007-05-01 |  | 2007-05-01 | 1 | 1 | 2007-05-01 | 2007-05-01 | [6 empty] | 2009-01-09 | 2009-02-09 | 2009-01-29 |  | 2009-03-31 | 2009-03-30 | [8 empty] | 2009-03-31 | 2009-03-31 | 2009-03-31 | [6 empty] | 2009-03-31 | [17 empty] | FALSE |  | 2481668 | 5733757 | Kordia - Sugarloaf Off Summit Road Christchurch |  |  | TXSITE | [8 empty] | 2009-01-08 | [8 empty] | 2007-04-01
0 | CHC | 822 | CHC-060-097 |  |  |  | Christchurch City |  | TIER_1_ALL
0 | CHC | 823 | CHC-060-098 |  | CHC-060-098-D | Marshland | Christchurch City |  | TIER_1_ALL | ACTIVE | GF | A | OTHERS | green |  |  | 28 | 28 |  | -43.4589 | 172.6588 |  |  |  |  | Microwave, Microwave | CHC-060-096-G, CHC-060-096-G | [5 empty] | 2009-05-18, 2009-05-21 | [5 empty] | 2008-11-21 | 4 | 2009-02-20 | 2009-04-01 |  |  | 2009-03-20 | 2009-03-16 | 3 | 2009-03-20 | 2009-03-16 |  | 2008-12-03 |  | 2009-03-16 |  |  | 2009-03-16 | 2009-03-17 | 2009-03-02 | 2008-12-12 |  | 2009-04-01 | 1 | 4 | 2009-04-03 | 2009-04-01 | 2009-05-13 |  |  |  |  | 2009-05-01 | 2009-05-01 | 2009-06-03 | 2009-06-03 |  | 2009-06-11 | 2009-06-12 | [8 empty] | 2009-06-26 | 2009-06-30 | 2009-06-26 | [6 empty] | 2009-06-30 |  |  |  |  | 2009-05-12 | 2009-05-13 | [11 empty] | FALSE |  | 2482402 | 5749779 | 570 Marshlands Rd, Christchurch |  |  | CELLSITE | [7 empty] | 2009-04-14 | 2009-04-22 | [8 empty] | 2008-10-28
0 | CHC | 824 | CHC-060-099 | Akaroa Harbour |  |  | Christchurch City |  | TIER_9 | [22 empty] | FALSE
0 | CHC | 825 | CHC-060-100 | Akaroa | CHC-060-100-A | Akaroa Hilltop | Christchurch City | 21 | TIER_4 | ACTIVE | GF | DF | SP |  | STACK_A | COSITE |  |  | 1 | -43.7374 | 172.876 |  | 2012-01-30 |  |  | Microwave | CHC-060-116-A | FALSE | FALSE | 2014-11-04 |  | TRUE | 2012-05-28 | 2012-02-29 | 2012-02-29 | 2015-05-06 | 2015-05-06 | 2015-08-21 | 2015-08-18 | 3 |  | 2015-12-04 | 2015-09-11 | 2015-09-07 | 2016-03-11 |  |  |  |  | DISCRETIONARY_FULL | 2016-02-12 | 2016-01-21 | 2016-03-18 |  | 3 | 2016-04-29 |  | 2015-09-16 | 2015-09-17 | 2105-12-18 | 2015-09-30 | 4 |  |  | 2016-01-28 | [5 empty] | 2016-05-02 |  | 2016-05-27 |  |  | 2016-06-17 |  | 2015-12-18 | [8 empty] | 2016-07-15 | [5 empty] | GF option. Dave to ID two alternate sites in Akaroa. 14/05 LA supports this location off the ridge. Site visit/ CV planned for Mon28th. SA to arrange access with keys for both gates at top and bottom. 29/05 NT to send sketch to team. Excavation depth to be decided. 26/6 NT to follow up. 02/07 Jason to chase up Telecom. Martin to contact landowner to est. lease plan. 8 Oct 2014 - visit arragned (16 Oct) to confirm RF requirements thereafter existing PD to be amended/issued. 28 Oct - Visit arranged to confirm feasibility of construction prior to continuing, Tx investigation DMR options - Build is feasible continue with tweaks to PD - await team comments on PD, overlay topo information. Rob to meet council next week. 11 Dec Council visit to site required, accurate assessment of tower hieght/summit height required - scheduled 7 Jan. Council want slimmer pole. Site needs to be approved for inclusion in build program via RF review before we continue. Council want a guyed mast, confirmation of mast hieght required. RC drone appears to be teh best option to determine mast hieght and position. 10 July - PD produced in house, priority work delays Akaroa PD. 14 Aug - PD to be issued. Site is # 105 - not in 2015 build list. 15 Oct, site back into build, Consent requires neighbours approval, neighbour has requested the Spark SFA document which is being produced by Spark. Availability of this document (and its acceptance) may cause a delay to the site. | TNZ | 2015-12-02 | [8 empty] | 2016-06-29 |  |  | HIGH | CHRISTCHURCH_OUTER |  |  | BUILD |  | FALSE |  | 2500026 | 5718892 | spot height 700 |  | outstanding landscape and prominent ridgeline location means that public notification risk - consistent with other applications is highly likely. all ridgeline options in BP has this treatment. This is the preferred landscape, planning and rf option wihtin this context as it is further away from roads and is within the context of the telecom designation. - 05/06/2012 | CELLSITE | WIPACTIVE |  |  | ROAMING |  |  | 2016-02-10 | 2016-03-18 | [5 empty] | 2016-04-15 |  | 2015-12-05 |  | 2015-05-06
0 | CHC | 826 | CHC-060-101 | CHC Airport Inbuilding |  |  | Christchurch City |  | TIER_1_ALL
0 | CHC | 827 | CHC-060-102 | Airport Terminals | CHC-060-102-A | Airport Tower | Christchurch City | 8 | TIER_1_INFILL | ACTIVE | BO | DU5 | BO | grey | INLINE | STANDALONE | 32 | 77.7 | 1 | -43.4885 | 172.5404 |  |  |  |  | Microwave | CHC-060-094-B | FALSE | FALSE |  |  | FALSE | 2010-06-10 | 2011-05-27 | 2011-05-27 | 2011-05-27 | 2011-05-27 | 2011-06-06 | 2010-07-06 | 1 | 2011-06-06 | 2010-07-06 |  |  | 2011-11-18 | 2012-02-01 |  | 2011-11-18 | 2012-02-01 | PERMITTED | 2011-09-16 | 2011-09-16 | 2011-10-19 | 2011-09-29 | 1 |  | 2011-10-07 | [14 empty] | 2012-01-10 |  | 2012-01-27 |  | 2012-01-27 | 2012-01-27 | [9 empty] | 2012-02-21 | 2012-02-08 | 2012-02-21 | 2012-08-09 | 2013-08-23 | 2012-11-09 | 12.06.2014 : "D" configuration build. (APM, Battery, & 2 x RFC) using version "B" cabinets. Thus making it a "DU" Site. (As per Ron Bush/blr) | [17 empty] | BUILD |  | FALSE |  | 2472832 | 5746449 | 32 Durey Road, Christchurch International Airport |  | Need Requiring Authority Approval from CIAL as the site is designated for Airport Purposes - 27/05/2011 | CELLSITE |  |  | 2014-09-19
0 | CHC | 828 | CHC-060-103 | Marleys Hill |  |  | Christchurch City |  | TIER_9 | [22 empty] | FALSE | [60 empty] | Site is to allow LAC exclusion. Single sector away from city itself. VF has two sectors however main emphasis is on containment and roaming cost from sector two.
0 | CHC | 829 | CHC-060-104 | Fendalton | CHC-060-104-B | Fendalton RSR | Christchurch City | 8 | CSP2013 | ACTIVE | RSR | DU5 | P4L |  | INLINE |  | 18.9 | 20 |  | -43.5201 | 172.6065 | [6 empty] | FALSE | FALSE |  |  | FALSE |  |  | 2013-08-02 |  | 2013-08-02 | 2013-09-09 | 2013-05-30 | 6 | 2013-09-09 | 2014-08-21 | 2013-10-18 | 2013-09-19 | 2013-09-23 | 2013-09-23 |  | 2013-11-12 | 2013-11-20 | PERMITTED | 2013-09-20 | 2013-09-20 | 2013-10-14 | 2013-10-14 | 4 | 2013-11-12 | 2013-12-02 |  |  |  | 2013-09-12 | 2 |  | 2013-09-17 | 2013-11-08 |  | 2013-09-13 | 2013-09-13 | 2013-10-14 |  | 2013-11-13 | 2013-11-12 | 2013-12-13 | 2013-12-13 | 2013-12-06 | 2013-12-06 | 2013-12-13 | 2013-11-22 | 2013-12-06 |  |  | 2013-12-06 |  | 2013-11-08 | 2013-11-22 |  | 2013-12-13 | 2013-12-19 | [15 empty] | 2013-12-10 | 2013-12-18 | 2013-09-04 | MEDIUM | CHRISTCHURCH_OUTER | 2013-10-31 | 2013-12-06 | BUILD | 2013-11-13 | TRUE | 2013-10-14 | 2478199 | 5742969 | Corner Fendalton Rd & Clifford Ave Fendalton Christchurch |  |  | CELLSITE |  |  | 2014-09-19 |  |  |  |  | 2013-11-13 | [9 empty] | 2013-08-02
0 | CHC | 830 | CHC-060-105 | Bryndwr North | CHC-060-105-B | LBJ Pub | Christchurch City | 8 | TIER_1_INFILL | ACTIVE | GF | Ab | P2 |  |  | STANDALONE |  | 20 |  | -43.4991 | 172.5862 |  |  |  |  | Microwave | CHC-060-023-A | FALSE | FALSE |  |  | FALSE |  | 2011-07-13 | 2011-07-13 | 2011-07-15 | 2011-07-15 | 2011-08-26 | 2011-08-29 | 1 | 2011-08-26 | 2011-08-29 |  | 2011-10-25 | 2012-01-27 | 2012-03-21 | 1 | 2012-01-27 | 2012-08-30 | PERMITTED | 2011-10-10 | 2011-10-10 | 2011-11-15 | 2011-11-01 | 1 |  | 2011-11-01 |  |  | 2012-02-13 | 2012-02-24 | 1 |  | 2012-02-13 | 2012-02-24 | 2012-03-22 |  |  |  |  | 2012-03-02 | 2012-03-06 | 2012-04-30 | 2012-04-30 | 2012-04-24 | 2012-05-02 | 2012-04-28 | [8 empty] | 2012-05-12 | 2012-05-07 | 2012-05-15 | 2012-05-02 | 2012-05-31 | 2012-08-29 | 2012-08-31 | 14/05 PAD in a week. 17/05 - Pad submitted. Accept or reject by 31/05. 29/05 Waiting for Design and Access feedback on PAD. 02/07 Faults to be resolved. 3 outstanding issues. |  | 2012-05-05 | 2011-10-12 | 2011-10-12 | 2012-01-23 | 2012-02-01 | 2012-03-09 | 2012-03-22 | 2012-05-02 | 2012-04-27 |  | 2012-05-17 | [6 empty] | 2012-04-24 | FALSE |  | 2476543 | 5745287 | 290 Wairakei Road |  |  | CELLSITE |  |  | 2015-10-12 | [12 empty] | 2012-05-19 | 2012-05-17 | 2011-07-15
0 | CHC | 831 | CHC-060-106 | Russley East | CHC-060-106-D | Racecourse Rd GF | Christchurch City | 8 | TIER_1_INFILL | ACTIVE | GF | Ab | P2 |  | INLINE | STANDALONE |  | 20 | 1 | -43.5265 | 172.5531 | [6 empty] | FALSE | FALSE |  |  | FALSE |  | 2011-08-31 | 2011-08-31 | 2011-09-05 | 2011-09-05 | 2011-10-04 | 2011-10-07 | 1 | 2011-10-04 | 2011-10-07 | 2011-10-31 | 2011-12-20 | 2011-10-31 | 2011-11-25 |  | 2011-10-31 | 2011-11-25 | CONTROLLED | 2011-10-18 | 2011-10-18 | 2011-11-18 | 2011-11-04 | 1 |  | 2011-11-04 |  |  | 2012-07-02 | 2012-07-02 | 1 |  | 2012-06-28 | 2012-07-02 | 2012-07-26 |  |  |  |  | 2012-07-12 | 2012-07-12 | 2012-08-20 | 2012-08-06 | 2012-08-06 | 2012-08-22 | 2012-08-09 | [8 empty] | 2012-08-10 | 2012-09-15 | 2012-08-16 | 2012-08-21 | 2012-08-30 | 2013-10-04 | 2013-09-25 | 23/04 Katrien antennas - pole to be adjusted. High voltage line is in the way of pile cap. Build in parrallel with Oaklands. 21/05 CD rev1 due 15/06. 5/6 JB to get letters ready by 8th. |  | 2012-08-23 | 2012-06-18 | 2012-06-18 | 2012-06-18 | 2012-07-02 | 2012-07-25 | 2012-07-26 | 2012-08-20 | 2012-08-06 |  | 2012-07-31 | [5 empty] | BUILD | 2012-08-16 | FALSE |  | 2473883 | 5742226 | Racecourse Rd Riccarton |  |  | CELLSITE |  |  | 2015-11-05 | [12 empty] | 2012-08-31 | 2012-08-21 | 2011-09-05
0 | CHC | 832 | CHC-060-107 | Redwood East | CHC-060-107-B | Grimseys Rd LPR | Christchurch City | 8 | TIER_6 | ACTIVE | RSR | D |  |  |  | STANDALONE |  | 14 |  | -43.4751 | 172.6296 | [6 empty] | FALSE | FALSE |  |  | FALSE |  | 2011-08-31 | 2011-08-31 | 2011-09-12 | 2011-09-15 | 2011-10-19 | 2011-11-30 | 1 | 2011-10-19 | 2011-11-30 | 2011-10-25 | 2011-11-09 | 2012-03-30 | 2012-04-10 |  | 2012-03-30 | 2012-04-10 | NES | 2011-10-21 | 2011-11-29 | 2012-01-17 | 2012-01-20 | 1 |  | 2012-02-08 | [35 empty] | Build site last due to probable reaction of local residents. 03/10 Cabinet location moved up the street to avoid visual impact on adjacent resident. RF happy for 550 feeder cables to be used provided its a straight run or very tight join. 19/03 HARDMATCHED | [12 empty] | 2012-02-09 | EXTREMEHIGH | TIER_1_INFILL |  |  | HARDMATCH |  | FALSE |  | 2480043 | 5747966 | SW Cnr Grimseys and Prestions Rd |  |  | CELLSITE | WIPHOLDING
0 | CHC | 833 | CHC-060-108 | Oaklands | CHC-060-108-E | Nicholls rd Cnr RSR | Christchurch City | 8 | TIER_1_INFILL | ACTIVE | GF | DU | P2 |  | INLINE | STANDALONE | 19.5 | 20 | 1 | -43.5793 | 172.5666 | [6 empty] | FALSE | FALSE |  |  | FALSE |  | 2011-07-20 | 2011-07-20 | 2011-08-16 | 2011-07-22 | 2011-09-27 | 2011-09-30 | 4 | 2011-11-09 | 2015-04-28 | 2011-11-25 | 2011-11-25 | 2011-11-25 | 2011-11-07 |  | 2011-11-25 | 2011-12-02 | CONTROLLED | 2011-12-20 | 2012-01-09 | 2012-02-13 | 2012-02-23 | 3 |  | 2012-02-23 |  |  | 2012-07-02 | 2012-07-02 | 1 |  | 2012-06-28 | 2012-07-02 | 2012-08-01 |  |  |  |  | 2012-07-12 | 2012-07-12 | 2012-08-18 | 2012-08-18 | 2012-08-15 | 2012-08-18 | 2012-08-24 | [8 empty] | 2012-09-06 | 2012-09-15 | 2012-09-11 | 2012-08-18 | 2012-09-21 | 2013-06-14 | 2013-05-31 | 23/04 HW arranging contract, geotech and Jetvac. 21/05 Geotech shows ground is soft. CD rev1 due 15/06. 5/6 JB to provide letters for drop by 8th. |  | 2012-08-27 | 2012-06-08 | 2012-06-08 | 2012-06-18 | 2012-07-02 | 2012-07-24 | 2012-08-01 | 2012-08-15 | 2012-08-16 |  | 2012-07-31 | [5 empty] | BUILD | 2012-08-14 | FALSE |  | 2475004 | 5736367 | Cnr Halswell rd and Nicholls rd |  |  | CELLSITE |  |  | 2015-11-05 | [12 empty] | 2012-09-10 | 2012-09-10 | 2011-07-22
0 | CHC | 834 | CHC-060-109 | Christchurch Office | CHC-060-109-A | CHC Office - Nga Mahi Rd | Christchurch City |  | 2014 | ACTIVE |  | TX | [75 empty] | 2014-04-14 | [22 empty] | BUILD | [5 empty] | Unit 8/19 Nga Mahi Rd, Sockburn, Christchurch |  |  | TXSITE
0 | CHC | 835 | CHC-060-110 | 123 Blenheim Rd | CHC-060-110-A | 2 Degrees CH office WAN | Christchurch City |  | TIER_6 | ACTIVE | RT | TX | RT |  |  | STANDALONE |  |  |  | -43.5378 | 172.6 | [93 empty] | 2477683 | 5740998 | 123 Blenhiem Rd Christchurch
0 | CHC | 836 | CHC-060-111 | RBI - Kainga |  |  | Christchurch City |  | RBI | [22 empty] | FALSE
0 | CHC | 837 | CHC-060-112 | RBI - Yaldhurst |  |  | Christchurch City |  | RBI | [22 empty] | FALSE
0 | CHC | 838 | CHC-060-113 | Akaroa |  |  | Christchurch City | 8 | TIER_9 | [22 empty] | FALSE
0 | CHC | 839 | CHC-060-114 | Revera DC |  |  | Christchurch City | 8 | TIER_6 | [22 empty] | FALSE
0 | CHC | 840 | CHC-060-115 | VFNZ CPT | CHC-060-115-A | TX HUB | Christchurch City | 8 | TIER_6 | ACTIVE | COLO | TX | [15 empty] | FALSE | FALSE |  |  | FALSE | [55 empty] | 2008-03-01 |  | 2008-03-01 |  |  | SOA and PAC dates entered to reflect status | [19 empty] | FALSE |  |  |  | 45 Sir William Pickering Drive, CHC |  |  | TXSITE
0 | CHC | 841 | CHC-060-116 | Little River Telecom | CHC-060-116-A | Little River | Christchurch City | 21 | TIER_4 | ACTIVE | RT | X | RT |  |  | COLO |  |  |  | -43.7704 | 172.7915 |  |  |  |  | Fibre Optic | CAN-062-011-C | FALSE | FALSE |  |  | FALSE |  | 2015-04-23 | 2015-04-30 | 2015-09-25 | 2015-09-29 | 2016-02-19 | 2015-10-20 | 1 |  | 2015-10-20 | 2016-02-26 | 2016-01-18 | 2016-03-18 | 2016-01-25 |  |  |  | DISCRETIONARY_FULL | 2015-10-23 | 2015-11-17 | 2015-11-20 | 2015-12-17 | 1 | 2015-11-27 | 2015-12-17 | 2016-03-03 |  | 2016-03-25 | [10 empty] | 2016-06-09 |  | 2016-06-23 |  |  | 2016-07-08 |  | 2016-01-15 | [8 empty] | 2016-06-24 | [5 empty] | Tx Link for Akaroa site. Fibre feasibility to be confirmed. SOA date aligned with Akaroa site | TNZ | [9 empty] | 2016-07-22 |  | 2015-06-08 | LOW | TRANSMISSION_ONLY | 2016-01-15 |  | BUILD |  | TRUE |  | 2493227 | 5715206 | Main Akaroa to CHC Rd |  |  | TXSITE | WIPACTIVE |  |  | ROAMING |  |  |  | 2016-04-08 | [5 empty] | 2016-05-05 |  |  |  | 2015-09-29
0 | CHC | 842 | CHC-060-117 | Carlton Corner | CHC-060-117-B | Carlton Corner | Christchurch City | 11 | TIER_3 | ACTIVE | RSR | DU5 | P4L |  |  | STANDALONE |  |  |  | -43.5207 | 172.6269 |  | 2013-06-26 |  |  |  |  | FALSE | FALSE |  |  | FALSE |  |  | 2013-02-01 |  | 2013-02-01 |  | 2013-02-13 | 2 | 2013-02-13 | 2014-07-22 |  | 2013-03-04 | 2013-03-11 | 2013-03-11 |  | 2013-03-12 |  | PERMITTED |  | 2013-02-12 | 2013-03-06 | 2013-02-25 | 1 | 2013-03-15 | 2013-02-25 |  | 2013-03-01 |  | 2013-03-28 | 1 |  | 2013-03-26 | 2013-03-28 | 2013-05-20 |  |  | 2013-03-15 |  | 2013-05-20 | 2013-05-10 | 2013-06-21 | 2013-06-21 | 2013-06-21 | 2013-06-28 | 2013-06-27 |  | 2013-06-21 | [7 empty] | 2013-07-14 | 2013-07-12 | 2013-07-17 | 2013-07-23 | 2013-10-28 | 2013-12-06 |  |  | 2013-06-28 | 2013-04-22 | 2013-04-22 | 2013-04-29 | 2013-04-29 |  | 2013-05-20 | 2013-06-28 |  | 2013-07-01 | 2013-07-01 | 2013-02-01 | MEDIUM | TIER_1_INFILL | 2013-05-31 | 2013-06-21 | BUILD | 2013-06-21 | TRUE | 2013-03-15 | 2479848 | 5742907 | Adjacent to 1 Papanui Rd, Bealey Ave, Christchurch |  |  | CELLSITE |  |  | 2014-09-19 |  |  |  |  | 2013-04-01 | 2013-04-18 | [6 empty] | 2013-07-08
0 | CHC | 843 | CHC-060-118 | Southern Cross | CHC-060-118-B | Southern Cross | Christchurch City | 11 | TIER_3 | ACTIVE | RSR | DU | P4L |  | INLINE | STANDALONE | 20 | 20.06 | 1 | -43.5201 | 172.6358 |  | 2012-03-27 |  |  | Fibre Optic | CHC-060-131-A | FALSE | FALSE |  |  | FALSE |  | 2012-08-09 | 2012-08-09 | 2012-08-27 | 2012-08-27 |  | 2012-09-24 | 4 | 2012-09-13 | 2015-04-28 | 2012-09-20 | 2012-08-29 | 2012-10-10 | 2012-10-05 | 1 |  | 2013-03-21 | PERMITTED | 2012-10-10 | 2012-10-05 | 2012-11-07 | 2012-11-07 | 3 | 2013-01-29 | 2013-01-29 |  | 2012-11-15 | 2013-01-25 | 2013-01-25 | 1 |  |  | 2013-01-25 |  |  |  | 2013-01-29 |  | 2013-03-25 | 2013-03-25 | 2013-05-13 | 2013-05-13 | 2013-04-26 | 2013-05-14 | 2013-05-17 | [8 empty] | 2013-05-27 | 2013-06-14 | 2013-06-14 | 2013-06-21 | 2013-06-21 | 2013-09-19 | 2013-12-06 | 27/8 Wo1 issued for new candidate. Positive feedback. Straight Telco Notice. 03/09 Redlines to bo back. Reduce montage and plumes. 15/10 Hardmatch only. |  | 2013-05-27 | 2013-04-03 |  | 2013-04-09 | 2013-04-01 |  |  |  | 2013-05-01 | 2013-05-27 | 2013-06-11 | 2012-09-17 | MEDIUM | TIER_1_INFILL | 2013-05-10 | 2013-05-10 | BUILD | 2013-04-26 | TRUE |  | 2480569 | 5742973 | outside 14 Caledonian Rd Christchurch |  |  | CELLSITE |  |  | 2015-10-21 | [12 empty] | 2013-05-31 | 2013-06-10
0 | CHC | 844 | CHC-060-119 | CHCH Tunnel | CHC-060-119-A | Tunnel rebuild | Christchurch City | 11 | TIER_3 | ACTIVE | RT | D |  |  |  | STANDALONE |  |  |  | -43.5866 | 172.7068 |  | 2012-03-27 |  |  |  |  | FALSE | FALSE |  |  | FALSE |  | 2011-11-04 | 2011-11-04 | 2011-11-16 | 2011-11-21 | 2011-12-16 | 2012-01-16 | 4 | 2012-06-13 | 2012-08-07 | 2012-01-30 | 2012-01-30 | 2012-05-09 | 2012-05-11 |  | 2012-05-09 | 2012-05-16 | DISCRETIONARY_FULL | 2012-07-03 | 2012-02-07 | 2012-08-27 | 2012-08-27 | 4 |  |  |  |  | 2012-09-02 | 2012-10-26 | 1 |  | 2012-09-02 | 2012-10-26 | [5 empty] | 2012-10-23 | 2012-10-23 | 2012-11-08 | 2012-11-08 |  | 2012-11-08 | 2012-11-08 | 2012-11-14 | 2012-11-14 | [7 empty] | 2012-11-14 | 2012-11-14 | 2012-11-21 | 2012-11-21 |  | 2013-02-21 | Statement of works to be issued instead of WO2 on 3rd April. Transfield to complete TI and CRs etc. Transfield need CD to provide quote for PO before works start. MW mounts need to be fabricated. Most other equipment is already available. Waiting for PDs to resubmitt RC. 29/05 PD to be completed inhouse? TP to find out if s176 is required for resubmission. 23/7 Cabinets to be changed to original size. RMA lodged. Fibre is available on site and is most likely Tx option. 30/7 Plans lodged with Heritage Soc. Expected feedback this week. Once planners approve to go to Opus for final approval. Raise PO for Tunnel. 6/8 Lease area amendment final change to come through. Transfield are pricing for the work to be completed. 13/8 Waiting on pricing to come back from Transfield. Some amendments to planning document required. A co-site appln form to be completed. 27/8 RMA supplied. Wo2 to go out, today. Telco co-lo to be processed. Pete awaiting email from NZTA. 03/09 Equipment arrived, waiting on const. drwgs for final pricing. 10/09 Fibre to be ordered. Leonard to get price from Enable. 17/9 Waiting on construction drawings. 24/10 Construction drawing | [10 empty] | 2012-11-09 | 2012-11-09 | 2012-05-02 | LOW | TIER_1_INFILL |  |  | BUILD |  | TRUE |  | 2486334 | 5735610 | chch end of lyttelton tunnel |  | Briefly taken over by Kasuni after Sean left. Over to Rob Monro now. - 02/05/2012 | CELLSITE
0 | CHC | 845 | CHC-060-120 | Aranui | CHC-060-120-A | Aranui | Christchurch City | 11 | TIER_3 | ACTIVE | RSR | DU | P4L |  | INLINE |  |  | 20 | 1 | -43.5139 | 172.7101 |  | 2012-05-07 |  |  |  |  | FALSE | FALSE |  |  | FALSE |  | 2012-05-15 | 2012-05-15 | 2012-07-11 | 2012-07-11 | 2012-07-18 | 2012-08-14 | 2 | 2012-08-10 | 2012-10-26 | 2012-08-22 | 2012-08-29 | 2012-09-17 | 2012-09-21 | 1 | 2012-10-31 | 2013-03-28 | PERMITTED | 2012-09-18 | 2012-10-05 | 2012-10-31 | 2012-10-31 | 2 |  |  |  |  | 2013-01-03 | 2012-11-16 | 1 |  |  | 2012-11-16 | 2013-03-15 |  |  | 2012-11-06 |  | 2013-01-31 | 2013-01-29 | 2013-02-19 | 2013-02-09 | 2013-02-22 | 2013-03-01 | 2013-03-07 | 2013-02-25 | 2013-03-21 | [6 empty] | 2013-03-11 | 2013-03-22 | 2013-03-22 | 2013-03-29 | 2013-03-28 | 2013-10-14 | 2013-12-12 | 23/04 Site to replace Bexley North damaged in earthquakes. 29/05 Design resource to be decided. 23/7 MW required, 300mm dish/es. Minimum height 19m - Fahad. Possibly put 1 300 MW in shroud. 30/7 Waiting on plans to be released. On track. 10/09 BOQ to be defined for Tx to enable WO2 to be raised. 17/9 Telco Notice lodged. 24/10 Head frame to be changed to 600. |  | 2013-03-05 | [5 empty] | 2013-03-15 | 2013-03-06 | 2013-03-11 | 2013-03-14 | 2013-03-18 | 2012-09-03 | MEDIUM | TIER_1_INFILL |  |  | BUILD | 2013-02-15 | TRUE | 2012-11-02 | 2486574 | 5743688 | Adjacent to 478 Pages Road, Aranui, Christchurch |  |  | CELLSITE | [15 empty] | 2013-03-15 | 2013-03-15
0 | CHC | 846 | CHC-060-121 | Madras St | CHC-060-121-D | C1 Candidate | Christchurch City | 11 | TIER_3 | ACTIVE | RT | DF | RT |  |  | STANDALONE |  |  | 1 | -43.53 | 172.6391 |  | 2012-03-27 |  |  | Fibre Optic | CHC-060-131-A | FALSE | FALSE |  |  | FALSE |  | 2012-08-23 | 2012-08-23 | 2012-08-29 | 2012-08-29 | 2012-10-03 | 2012-10-11 | 2 | 2012-10-03 | 2012-11-30 | 2012-10-19 | 2012-10-19 | 2013-02-12 | 2013-02-26 |  |  | 2013-02-26 | DISCRETIONARY_FULL | 2012-11-14 | 2012-12-05 | 2013-02-14 | 2013-01-09 | 2 |  | 2013-01-30 | 2012-11-23 | 2013-01-10 | 2013-01-10 | 2013-01-24 | 1 |  | 2013-01-30 | 2013-01-24 | 2013-03-13 |  |  |  |  | 2013-03-12 | 2013-03-12 | 2013-03-29 | 2013-04-05 | 2013-04-12 | 2013-04-24 | 2013-04-19 | 2013-03-20 | 2013-05-03 | [6 empty] | 2013-05-10 | 2013-05-15 | 2013-05-15 | 2013-06-20 | 2013-05-31 | 2013-09-20 | 2013-09-23 | 13/8 9:30 Wed site visit. Press building possible back up. 17/9 Waiting for first draft of PD. SF to follow up with Ritchie. 8/10 Decision made to proceed with RF site by itself so as not to delay by increasing the build/planning by incorporating proposed mini hub. Transmission to be done as a secondary project. 15/10 Hardmatch only. |  | 2013-05-06 | 2013-03-14 | 2013-03-14 | 2013-03-18 | 2013-03-18 | 2013-03-13 | 2013-03-13 |  |  | 2013-05-08 | 2013-05-08 | 2012-09-17 | LOW | TIER_1_INFILL | 2013-04-24 | 2013-05-03 | BUILD | 2013-03-27 | FALSE |  | 2480841 | 5741881 | Pacific Tower 166 Glouster Street Christchurch |  |  | CELLSITE |  |  | 2015-10-21 | [12 empty] | 2013-05-17 | 2013-05-22
0 | CHC | 847 | CHC-060-122 | Lyttelton Re_build |  |  | Christchurch City | 11 | TIER_3 | [22 empty] | FALSE | [60 empty] | Lyttelton Re_build site.
0 | CHC | 848 | CHC-060-123 | Avondale |  |  | Christchurch City | 11 | TIER_3 | [22 empty] | FALSE | [60 empty] | Avondale Re-build site | [14 empty] | TIER_1_INFILL
0 | CHC | 849 | CHC-060-124 | CHCH Casino |  |  | Christchurch City | 11 | COW | [22 empty] | FALSE | [60 empty] | Kilmore St Replacement. | [14 empty] | TIER_1_INFILL
0 | CHC | 850 | CHC-060-125 | Wigram Skies | CHC-060-125-A | Active Candidate for Forecasting | Christchurch City | 23 | TIER_5 | ACTIVE | GF | DU | [15 empty] | FALSE | FALSE |  |  | FALSE |  | 2016-03-31 | [54 empty] | 2013-04-14 |  |  |  | RF Engineer - Patrick Urlich | [17 empty] | BUILD |  | FALSE | [7 empty] | WIPACTIVE |  |  | CAPACITY
0 | CHC | 851 | CHC-060-126 | Park Tce | CHC-060-126-B | George Hotel | Christchurch City | 11 | TIER_3 | ACTIVE | RT | DF5 | RT |  |  | STANDALONE |  |  | 1 | -43.526 | 172.6288 |  |  |  |  | Fibre Optic | CHC-060-131-A | FALSE | FALSE |  |  | FALSE |  | 2012-07-04 | 2012-07-04 | 2012-07-20 | 2012-07-16 |  | 2012-09-14 | 1 | 2012-09-14 | 2012-09-14 | 2012-08-20 | 2012-08-14 | 2012-11-19 | 2012-11-20 | 1 |  | 2012-11-20 | PERMITTED | 2012-11-21 | 2012-11-21 | 2012-12-17 | 2012-12-14 | 1 |  |  |  |  | 2013-02-10 | 2013-02-13 | 2 |  | 2013-02-12 | 2013-02-28 |  |  |  | 2013-01-25 |  | 2013-03-18 | 2013-03-18 | 2013-04-23 | 2013-04-22 | 2013-03-25 | 2013-04-19 | 2013-04-22 | [8 empty] | 2013-05-08 | 2013-05-15 | 2013-05-15 | 2013-05-31 | 2013-05-31 | 2013-08-29 | 2013-09-12 | 23/7 Awaiting Plans from Council to complete drawings. 13/8 George revisited for more detailed plans. 27/8 Redlines to be processed. 10/09 Planning drawings getting redlined at the moment. 17/9 PD released, being redlined. 01/10 Owners have seen & apprvd the initial PD's. |  | 2013-05-07 | [6 empty] | 2013-04-24 | 2013-04-29 | 2013-05-13 | 2013-05-13 | 2012-10-01 | MEDIUM | TIER_1_INFILL | 2013-04-17 | 2013-04-17 | BUILD | 2013-03-25 | TRUE | 2013-01-25 | 2480002 | 5742320 | 50 Park Terrace, The George Hotel Christchurch |  |  | CELLSITE |  |  | 2014-09-19 | [12 empty] | 2013-05-17 | 2013-05-17
0 | CHC | 852 | CHC-060-127 | Hornby West | CHC-060-127-B | Hornby 3 | Christchurch City | 11 | TIER_3 | ACTIVE | RSR | DU | [6 empty] | 1 | -43.5489 | 172.51 |  | 2012-06-19 |  |  |  |  | FALSE | FALSE |  |  | FALSE |  | 2012-07-05 | 2012-07-05 | 2012-07-27 | 2012-07-27 | 2012-08-09 | 2012-08-20 | 3 | 2012-08-20 | 2012-11-02 | 2012-09-10 | 2012-10-10 | 2013-02-08 | 2013-02-12 |  |  |  | CONTROLLED | 2013-01-15 | 2013-01-23 | 2013-02-20 | 2013-02-07 | 3 |  | 2013-02-08 | [35 empty] | 23/7 Waiting on Rf spec to generate Wo1. 10/09 Lease due today, SF to contact Pete Rogan to confirm. 01/10 Awaiting for Council, permits issue, Telco notice an option. 8/10 Lease sitting with council over permit and rental agreement. 15/10 Hardmatch only. 24/10 Lease delayed due to negotiations with council & 2D. | [12 empty] | 2012-07-03 | LOW | TIER_1_INFILL |  |  | HARDMATCH |  | TRUE |  | 2470415 | 5739726 |  |  |  | CELLSITE | WIPHOLDING
0 | CHC | 853 | CHC-060-128 | Diamond Harbour | CHC-060-128-B | Diamond Harbour | Christchurch City | 11 | TIER_3 | ACTIVE | GF | Ab | P3 |  |  | STANDALONE |  | 25 | 2 | -43.6405 | 172.7207 |  | 2012-08-07 |  |  | Fibre Optic | CHC-060-131-A | FALSE | FALSE |  |  | FALSE |  | 2012-08-14 | 2012-08-14 | 2012-08-30 | 2012-09-19 | 2012-11-19 | 2012-11-20 | 4 | 2012-11-19 | 2013-03-12 | 2012-11-22 | 2012-11-15 | 2013-02-08 | 2013-02-08 | 3 |  | 2013-02-08 | DISCRETIONARY_FULL | 2012-12-19 | 2013-02-04 | 2013-02-20 | 2013-03-27 | 3 |  | 2013-03-27 |  | 2013-01-15 | 2013-02-27 | 2013-01-24 | 3 |  | 2013-03-07 | 2013-04-26 | [5 empty] | 2013-04-29 | 2013-04-29 | 2013-05-30 | 2013-05-31 | 2013-05-31 | 2013-06-05 | 2013-06-05 | 2013-05-17 | 2013-06-06 | [6 empty] | 2013-06-05 | 2013-06-25 | 2013-06-24 | 2013-06-27 | 2013-06-25 | 2013-09-27 | 2013-09-23 | 24/10 Site survey underway to finalise drawings. |  | 2013-06-05 |  |  | 2013-04-22 | 2013-05-01 | 2013-05-28 |  | 2013-06-03 | 2013-05-31 | 2013-05-23 | 2013-06-13 | 2012-11-21 | MEDIUM | TIER_1_INFILL | 2013-05-10 | 2013-06-05 | BUILD | 2013-05-30 | FALSE |  | 2487473 | 5729618 | Diamond Harbour, Herbert Peak Road, Diamond Harbour, Canterbury |  | Remote from residential but in Outstanding Natural Landscape. Less exposed than 'upper' option. - 06/09/2012 - 04/02/2013 | CELLSITE | [15 empty] | 2013-06-12 | 2013-06-12
0 | CHC | 854 | CHC-060-129 | Marshlands Rd | CHC-060-129-A | Burwood 3 | Christchurch City | 21 | 2015P | ACTIVE | RSR | DU | [6 empty] | 1 | -43.4997 | 172.6621 | [6 empty] | FALSE | FALSE |  |  | FALSE |  | 2012-07-05 | 2012-07-05 | 2012-07-27 | 2012-07-27 | 2012-08-09 | 2012-08-20 | 2 | 2012-08-20 | 2012-11-02 | 2012-10-08 | 2012-10-08 | 2013-02-08 | 2013-02-12 |  |  |  | CONTROLLED | 2012-12-20 | 2013-01-25 | 2013-02-20 | 2013-02-20 | 2 |  | 2013-02-20 | 2015-11-06 |  | 2015-12-18 | [10 empty] | 2016-02-15 |  | 2016-03-18 |  |  | 2016-03-31 | [10 empty] | 2016-04-14 | [5 empty] | 23/7 Waiting on Rf spec to generate Wo1. 03/09 Still negotiating with council on permit. Back-up Telco notice option plan to be built/prepared. 10/09 Lease due today, SF to contact Pete Rogan to confirm. 24/10 Lease delayed due to council negotiation. 16 Mar - Resources to continue restricted due to roaming commitment. Dates pushed out until budget to build is available |  | 2015-09-15 | [8 empty] | 2016-04-06 |  |  | MEDIUM | TIER_1_INFILL | 2016-01-29 |  | HARDMATCH | 2016-01-29 | TRUE | 2016-01-15 | 2482687 | 5745255 |  |  |  | CELLSITE | WIPHOLDING |  |  | CAPACITY |  |  |  | 2015-12-18 | [5 empty] | 2016-01-29 |  | 2015-09-01
0 | CHC | 855 | CHC-060-130 | Halswell West | CHC-060-130-A | Quaifes Road | Christchurch City | 11 | TIER_3 | ACTIVE | RSR | DU |  |  |  |  | 20 |  | 1 | -43.5815 | 172.5453 |  | 2012-06-20 |  |  |  |  | FALSE | FALSE |  |  | FALSE |  | 2012-07-05 | 2012-07-05 | 2012-07-20 | 2012-07-19 |  | 2012-08-14 | 3 | 2012-08-10 | 2012-11-02 | 2012-06-26 | 2012-07-03 | 2012-10-22 | 2012-10-04 | 2 |  |  | PERMITTED | 2012-09-21 | 2012-09-21 | 2012-10-19 | 2012-10-09 | 2 | [37 empty] | 23/7 LOS OK for MW. Waiting for drawings to be released. 30/7 Waiting on Orion plans. 27/8 New drawings @ 18m needed to amend Telco notice. 15/10 Hardmatch only. | [12 empty] | 2012-08-01 | LOW | TIER_1_INFILL |  |  | HARDMATCH |  | TRUE |  | 2473288 | 5736113 |  |  |  | CELLSITE | WIPHOLDING
0 | CHC | 856 | CHC-060-131 | Riccarton - FTTS | CHC-060-131-A | Enable co-lo | Christchurch City |  | TIER_6 | ACTIVE | COLO | TX |  |  |  | COLO |  |  |  | -43.5431 | 172.6067 | [66 empty] | 2013-06-01 |  | 2013-06-01 |  |  | SOA and PAC dates entered to reflect status | [19 empty] | FALSE |  | 2478226 | 5740407 | 40 Whiteleigh Ave |  |  | TXSITE
0 | CHC | 857 | CHC-060-132 | Central - FTTS | CHC-060-132-A | Enable co-lo | Christchurch City |  | TIER_6 | ACTIVE | COLO | TX |  |  |  | COLO |  |  |  | -43.5432 | 172.6323 | [66 empty] | 2013-06-01 |  | 2013-06-01 |  |  | SOA and PAC dates entered to reflect status | [19 empty] | FALSE |  | 2480297 | 5740404 | 2 Wordsworth Street |  |  | TXSITE
0 | CHC | 858 | CHC-060-133 | C1 Building |  |  | Christchurch City | 11 | TIER_3 | [22 empty] | FALSE | [75 empty] | TIER_1_INFILL
0 | CHC | 859 | CHC-060-134 | Norwood Repeater |  |  | Christchurch City | 11 | TIER_6 | [22 empty] | FALSE | [60 empty] | rooftop of Harvey Norman shop 1 donor yagi plus 2 indoor panel antennas installed with a 3dB splitter
0 | CHC | 860 | CHC-060-135 | Stanmore/Worcester_rd | CHC-060-135-A | Worcester Rd | Christchurch City |  | TIER_6 | ACTIVE | [100 empty] | HARDMATCH
0 | CHC | 861 | CHC-060-136 | Riccarton West | CHC-060-136-A | Riccarton Rd | Christchurch City | 6 | 2014 | ACTIVE | RSR | DU5 | P4L | Grey | STACK_A |  | 20 | 20 |  | -43.5308 | 172.5872 | [6 empty] | FALSE | FALSE |  |  | FALSE |  | 2014-04-03 | 2014-04-03 | 2014-04-07 | 2014-04-07 | 2014-05-15 | 2014-05-07 | 3 | 2014-05-15 | 2014-08-26 | 2014-06-16 | 2014-06-04 | 2014-06-16 | 2014-06-11 |  | 2014-06-16 | 2014-06-19 | PERMITTED | 2014-05-15 | 2014-09-04 | 2014-06-16 | 2014-09-17 | 3 | 2014-06-16 | 2014-06-09 | 2014-05-15 | 2014-05-08 | 2014-07-04 | 2014-07-01 | 3 |  | 2014-07-08 | 2014-09-11 | [5 empty] | 2014-09-29 | 2014-09-29 | 2014-10-17 | 2014-10-17 | 2014-10-13 | 2014-10-22 | 2014-10-22 | 2014-10-30 | 2014-11-04 | [7 empty] | 2014-11-25 | 2014-11-25 |  |  |  |  | Fibre delivery delayed by Enable due to Road Crossings and finding their network Site on air 25 Nov | [10 empty] | 2014-11-11 | 2014-11-17 | 2014-06-11 | LOW |  | 2014-10-22 | 2014-10-24 | BUILD | 2014-10-13 | FALSE |  | 2476644 | 5741765 | Cnr Riccarton and Euston Street |  |  | CELLSITE |  |  | 2014-11-25
0 | CHC | 862 | CHC-060-137 | South Wigram | CHC-060-137-A | South Wigram | Christchurch City |  | TIER_6 | ACTIVE | [100 empty] | HARDMATCH
0 | CHC | 863 | CHC-060-138 | St Albans Cannon St |  |  | Christchurch City |  | TIER_6 | [83 empty] | CSP U900 infill coverage site
0 | CHC | 864 | CHC-060-139 | Northwood | CHC-060-139-A | Northwood | Christchurch City |  | TIER_6 | ACTIVE | [100 empty] | HARDMATCH
0 | CHC | 865 | CHC-060-140 | Bryndwr | CHC-060-140-A | Glandovey Rds | Christchurch City |  | TIER_6 | ACTIVE | [100 empty] | HARDMATCH
0 | CHC | 866 | CHC-060-141 | The Palms Mall CHCH | CHC-060-141-A | The Palms | Christchurch City |  | TIER_6 | ACTIVE | [100 empty] | HARDMATCH
0 | CHC | 867 | CHC-060-142 | Waltham Rd | CHC-060-142-A | Waltham Rd | Christchurch City |  | TIER_6 | ACTIVE | [100 empty] | HARDMATCH
0 | CHC | 868 | CHC-060-144 | Cellutronics 012 Issacs Constr |  |  | Christchurch City |  | TIER_6 | [83 empty] | Customers Name: Isaac Construction, Jim Shankie Location/address: Street number, Street Name. Suburb, Town/City: Isaac Construction, McArthurs Road, Harewood, Christchurch, 8543. Contact: Jim Shankie - 0274437108 / 033599145 Donor site: CHC-060-041, S3
0 | CHC | 869 | CHC-060-145 | Isaacs Repeater | CHC-060-145-A | Isaacs Repeater | Christchurch City |  | TIER_6 | ACTIVE | BO | 900_2100_MINI_RPTR | [7 empty] | -43.4684 | 172.5135 | [93 empty] | 2470649 | 5748663 | McLeans Island Road CHC
0 | CHC | 870 | CHC-060-146 | Addington Central | CHC-060-146-A | Addington Central GF | Christchurch City | 6 | 2014 | ACTIVE | RSR | DU5 | P4L | Grey | STACK_A |  | 20 | 20 |  | -43.5466 | 172.6103 |  |  |  |  | Fibre Optic | CHC-060-131-A | FALSE | FALSE |  |  | FALSE |  | 2014-04-03 | 2014-04-03 | 2014-04-07 | 2014-04-07 | 2014-05-15 | 2014-05-07 | 1 | 2014-05-15 | 2014-05-07 | 2014-06-16 | 2014-06-18 | 2014-06-16 | 2014-06-18 |  | 2014-06-16 | 2014-06-18 | PERMITTED | 2014-05-15 | 2014-05-01 | 2014-06-16 | 2014-05-29 | 1 | 2014-06-16 | 2014-05-29 | 2014-05-15 | 2014-05-08 | 2014-07-04 | 2014-07-01 | 1 |  | 2014-07-08 | 2014-07-01 | [5 empty] | 2014-09-01 | 2014-09-01 | 2014-09-29 | 2014-09-29 | 2014-09-25 | 2014-10-03 | 2014-10-09 | 2014-10-31 | 2014-10-30 | [7 empty] | 2014-11-11 | 2014-11-13 |  |  |  |  | Boundary Surveys requested Updated from Transfield Plan 18/8 Pole modified to fit site by transfield. Pole up 26/9 - weather permitting 9/10 - power on, cabs in , TI completed, waiting for fibre | [10 empty] | 2014-11-04 | 2014-10-30 | 2014-05-29 | LOW |  | 2014-10-07 | 2014-10-24 | BUILD | 2014-09-25 | FALSE |  | 2478516 | 5740025 | Barrington Street Addington |  |  | CELLSITE |  |  | 2014-11-13
0 | CHC | 871 | CHC-060-147 | Papanui CO Enable | CHC-060-147-A | Papanui Enable TX co-lo | Christchurch City |  | TIER_6 | ACTIVE | COLO | TX | COLO |  |  | COLO | [100 empty] | 13 Bishopdale Court Bishopdale Christchurch 8053 |  |  | TXSITE | WIPACTIVE
0 | CHC | 872 | CHC-060-148 | Riccarton East |  |  | Christchurch City |  | TIER_9
0 | CHC | 873 | CHC-060-149 | Riccarton South |  |  | Christchurch City |  | TIER_9
0 | CHC | 874 | CHC-060-150 | Christchurch Exchange | CHC-060-150-A | Chorus Exchange | Christchurch City | 6 | 2014 | ACTIVE | RT | B | RT | Grey | INLINE | COSITE |  |  |  | -43.5316 | 172.6355 | [6 empty] | FALSE | FALSE |  |  | FALSE |  |  | 2014-11-24 |  | 2014-11-20 |  | 2014-09-18 | 5 |  | 2014-12-04 | 2014-11-21 | 2014-12-01 | 2014-12-19 |  |  | 2014-12-19 |  | DISCRETIONARY_FULL | 2014-11-17 |  | 2014-12-05 |  |  | 2014-12-05 |  | 2014-11-21 | 2014-11-21 | 2014-11-26 | 2014-12-17 | 1 |  | 2014-11-28 | 2014-12-17 | [5 empty] | 2014-11-24 | 2014-11-24 | 2014-12-05 | 2014-12-07 | 2014-12-07 | 2014-12-07 | 2014-12-07 | 2014-12-04 | 2014-12-05 | [7 empty] | 2014-12-07 | 2014-12-07 |  |  |  |  | 29/9 - Drawings and colo application sent to Rob to lodge with Spark. Spark still have not defined if their existing antennas will shift, so lodged our application to force the issue forward. May need to revise plans on feedback. | [10 empty] | 2014-12-07 | 2014-12-07 |  |  |  | 2014-12-04 | 2014-12-05 | BUILD | 2014-12-07 | FALSE |  | 2480550 | 5741700 | 91 Hereford Street Christchurch |  |  | CELLSITE |  |  | 2015-10-21 |  |  |  |  | 2014-11-24 | 2014-11-24 | [8 empty] | 2014-08-13
0 | CHC | 875 | CHC-060-151 | Riccarton Mall Microcell |  |  | Christchurch City | 21 | TIER_9 | [22 empty] | FALSE | [60 empty] | 2 Microcells preferably loacated in the main predestrain area outside K-Mart
0 | CHC | 876 | CHC-060-152 | Hornby Mall Microcell | CHC-060-152-A | Hornby Mall Microcell | Christchurch City | 21 | 2015 | ACTIVE | RT | MC | NOPOLE | [6 empty] | -43.5427 | 172.5236 | [6 empty] | FALSE | FALSE |  |  | FALSE |  | 2014-12-09 | 2014-12-11 | 2015-01-22 | 2015-01-22 | 2015-01-30 | 2014-10-14 | 3 | 2015-01-30 | 2015-02-19 | 2015-03-06 | 2015-03-06 | 2015-03-27 | 2015-03-20 |  | 2015-04-03 | 2015-03-20 | PERMITTED | [7 empty] | 2015-02-20 | 2015-02-20 | 2015-03-16 | 2015-03-16 | 1 |  | 2015-03-16 | 2015-03-16 | [5 empty] | 2015-03-05 | 2015-03-04 | 2015-03-20 |  | 2015-03-11 | 2015-03-26 | 2015-03-27 | [9 empty] | 2015-04-01 | 2015-04-03 |  |  |  |  | Photo montage done, presented and seems OK. PD's underway. Jaco placed order for fibre. Rob to conclude deal. (14 Oct) PD 1 to be issued. 12 Nov - Mtg with Mall, chosen MC locations not suitable, MC to be hidden with seperated antenna, Mall very helpful and will suggest some mounting options, SOA in year doubtful. Management could not fond a location for our MC, re-caravan site. 11 dec site re-visited, new acceptable location found, design input required. 20 Feb - Roofer and electrician engaged, await lease confirmation to continue. TSL to oversee TI in conjunction wth electrician. Enable very slow, GaryLee Electrical engaged to priovide fibre quote. Permission from Mall to instll pre-lease has been obtained. Enable can deliver fibre week ending 27 March. Unable to process a CR in time for a 27 Mar integartion. | [10 empty] | 2015-04-01 |  |  |  |  | 2015-03-26 | 2015-03-27 | BUILD | 2015-03-12 | FALSE |  | 2471506 | 5740416 | 416 Main South Rd, Hornby, Christchurch, New Zealand |  |  | CELLSITE |  |  |  | SMALL CELLS | [13 empty] | 2015-01-22
0 | CHC | 877 | CHC-060-153 | Linwood | CHC-060-153-A | RSR | Christchurch City | 21 | 2015P | ACTIVE | RSR | DU5 |  |  | INLINE | STANDALONE | 20 | 20 |  | -43.5311 | 172.6572 | [6 empty] | FALSE | FALSE |  |  | FALSE |  | 2015-06-15 | 2015-06-15 | 2015-06-15 | 2015-06-18 | 2015-09-18 |  |  |  |  | 2015-10-16 |  | 2015-10-23 |  |  | 2015-10-23 |  |  | 2015-09-22 |  | 2015-10-20 |  |  | 2015-10-23 |  | 2015-10-19 |  | 2015-11-27 | [10 empty] | 2016-01-11 |  | 2016-02-05 |  |  | 2016-02-12 | [10 empty] | 2016-02-29 | [5 empty] | Council approve of identified RSR location - in house drawing, caravan measure up week ending 12 Jun to be arranged. Dates pushed out pending budget to build |  | 2015-12-10 | [8 empty] | 2016-02-19 | [6 empty] | ONHOLD | 2016-01-25 | FALSE |  | 2482302 | 5741754 | South east corner of Stanmore Road and Worcester Street Christchurch |  |  | CELLSITE | WIPACTIVE |  |  | CAPACITY |  |  |  | 2015-11-20 | [5 empty] | 2015-12-18 |  | 2015-12-17 |  | 2015-06-18
0 | CHC | 878 | CHC-060-154 | McLeans Island | CHC-060-154-A | McLeans Island | Christchurch City | 21 | TIER_9 | ACTIVE |  |  | COLO |  |  | COLO | 45 | 40 |  | -43.4641 | 172.4695 | [6 empty] | FALSE | FALSE |  |  | FALSE |  | 2015-10-16 | [59 empty] | VNZ | [16 empty] | BUILD |  | FALSE |  | 2467084 | 5749121 | McLeans Island Golf Course McLeans Island Road Chc | [6 empty] | ROAMING
0 | CHC | 879 | CHC-060-155 | 2D CHC Office | CHC-060-155-A | Christchurch Office | Christchurch City |  | 2015P | ACTIVE | IB | LS | NOPOLE |  |  | STANDALONE |  | 16 |  | -43.542 | 172.6137 | [66 empty] | 2015-11-17 | [22 empty] | BUILD |  |  |  | 2478794 | 5740537 | Lvl 4, 351 Lincoln Rd, Addington, Christchurch |  |  | CELLSITE |  |  |  | SMALL CELLS
0 | CHC | 880 | CHC-060-156 | Hornby North |  |  | Christchurch City |  | TIER_9
0 | CHC | 881 | CHC-060-157 | Wigram West |  |  | Christchurch City |  | TIER_9
0 | CHC | 882 | CHC-060-158 | Wigram East |  |  | Christchurch City |  | TIER_9
0 | COB | 883 | COB-100-001 | COB1 | COB-100-001-A | Hagley Oval - Event | Cellsite On Blocks |  | COW | ACTIVE | GF | X | [7 empty] | -43.534 | 172.6202 |  |  |  |  | Fibre Optic | CHC-060-132-A | [87 empty] | 2479311 | 5741427 |  |  |  | CELLSITE
0 | COB | 884 | COB-100-002 | COB |  |  | Cellsite On Blocks |  | COW
0 | COW | 885 | COW-000-001 | Daisy | COW-000-001-N | Wanaka COW - Event | Cellsite On Wheels | 9 | COW | ACTIVE | BO | DU | [7 empty] | -44.6948 | 169.1392 | [6 empty] | FALSE | FALSE |  |  | FALSE | [60 empty] | Temp for holiday season. | [17 empty] | BUILD |  | FALSE |  | 2204075 | 5605410 | Chorus Exchange Wanaka |  |  | CELLSITE |  |  |  | ROAMING
0 | COW | 886 | COW-000-002 | Blossom | COW-000-002-L | Waverley - Roaming COW | Cellsite On Wheels | 9 | COW | ACTIVE | BO | DU |  |  |  | COSITE | 10 | 12 |  | -39.7543 | 174.6523 | [6 empty] | FALSE | FALSE |  |  | FALSE |  | 2015-07-10 | 2015-07-10 | [7 empty] | 2015-07-17 | 2015-07-23 | 2015-07-24 | 2015-07-23 |  | 2015-07-24 | 2015-07-23 | PERMITTED | 2015-07-21 |  | 2015-07-21 |  |  | 2015-07-21 | 2015-07-21 | 2015-07-17 | 2015-07-17 | 2015-07-17 |  |  |  | 2015-07-17 | [6 empty] | 2015-08-17 |  | 2015-08-20 |  |  | 2015-08-20 |  | 2015-08-19 |  | 2015-07-29 | 2015-08-07 | 2015-08-10 | 2015-08-10 | 2015-08-07 | 2015-08-03 |  | 2015-08-26 | 2015-11-27 |  |  |  |  | 7 July: Site Acquisition complete 14 July: Co-site applications submitted (VF & Spark) 28 July: RFS 14 Aug 29 July: PO raised for power supply to be installed 29 July: Spark co-site approval received | [10 empty] | 2015-08-21 |  |  |  |  | 2015-08-19 |  |  | 2015-08-17 | FALSE |  | 2651588 | 6159929 | 1685-1703 State Highway 3 Patea-Nukumaru, Waverley |  |  | CELLSITE | [9 empty] | 2015-06-26 | 2015-06-26 | 2015-07-17 | 2015-07-17 |  |  |  |  | 2015-07-20
0 | COW | 887 | COW-000-003 | Mavis | COW-000-003-E | Cromwell Roaming COW | Cellsite On Wheels | 9 | COW | ACTIVE | BO | X |  |  | B2B | COSITE | 13.2 | 13.2 |  | -45.0598 | 169.2055 | [6 empty] | FALSE | FALSE |  |  | FALSE | [55 empty] | 2012-03-01 | [22 empty] | BUILD |  |  |  | 2211191 | 5565148 | Cornish Point Rd Cromwell |  |  | CELLSITE
0 | COW | 888 | COW-000-004 | Milo | COW-000-004-Y | Big Gay Out - Event | Cellsite On Wheels | 9 | TIER_6 | ACTIVE | [17 empty] | FALSE | FALSE |  |  | FALSE | [54 empty] | 2016-02-12 | [25 empty] | FALSE |  |  |  | Coyle Park, Pt Chev
0 | COW | 889 | COW-000-005 | Lucy |  |  | Cellsite On Wheels | 9 | COW | [22 empty] | FALSE
0 | COW | 890 | COW-000-006 | Hetty | COW-000-006-A | Renwick Exchange | Cellsite On Wheels | 9 | COW | ACTIVE | BO | X |  |  |  | COLO | 12 | 12 |  | -41.5072 | 173.8275 | [6 empty] | FALSE | FALSE |  |  | FALSE |  | 2011-11-10 | 2011-11-10 |  |  |  | 2011-11-23 | 1 | 2011-11-28 | 2011-11-23 |  | 2012-01-20 |  |  |  |  | 2012-01-31 | PERMITTED |  | 2012-03-05 | 2012-03-31 | 2012-03-14 | 1 |  | 2012-03-14 | [29 empty] | 2012-03-09 | 2012-03-09 |  |  |  |  | Good for Tx - Yes Good for RF - NO Good for Access - Yes TX - Telecom HSNS | TNZ | [12 empty] | MEDIUM | [5 empty] | FALSE |  | 2579070 | 5966304 | 60 High Street Renwick |  |  | CELLSITE
0 | COW | 891 | COW-000-007 | Angus | COW-000-007-H | Ngarauwahia VF CO Site - Roaming | Cellsite On Wheels | 9 | COW | ACTIVE | BO | X |  |  |  | COSITE | 12.5 |  |  | -37.6617 | 175.1395 | [6 empty] | FALSE | FALSE |  |  | FALSE | [6 empty] | 2015-04-09 | 1 |  | 2015-04-09 | [44 empty] | 2015-07-27 | 2015-07-27 |  |  |  |  | Water Reservoir, VF site, Brownlee ave, Ngaruawahia | [17 empty] | BUILD |  | FALSE |  | 2698982 | 6391206 | Water Reservoir VF Site |  |  | CELLSITE
0 | COW | 892 | COW-000-008 | Molly |  |  | Cellsite On Wheels | 9 | COW | [22 empty] | FALSE
0 | COW | 893 | COW-000-009 | Petal | COW-000-009-M | Dargaville - Roaming | Cellsite On Wheels | 9 | COW | ACTIVE | BO | DU |  |  | INLINE |  | 10 | 12 |  | -35.942 | 173.8671 | [6 empty] | FALSE | FALSE |  |  | FALSE | [10 empty] | 2015-05-15 | 2015-05-13 | 2015-05-29 |  |  | 2015-06-19 |  | PERMITTED | 2015-06-05 |  | 2015-06-08 |  |  | 2015-06-08 | 2015-06-08 | [17 empty] | 2015-08-11 | 2015-08-20 |  | 2015-08-27 |  | 2015-07-03 |  | 2015-08-16 |  | 2015-08-12 |  |  | 2015-08-21 | 2015-09-07 |  |  |  |  | 21 July: Awaiting fibre delivery 11 Aug: Fibre delivered | [15 empty] | 2015-08-27 |  |  | 2015-08-25 | FALSE |  | 2588849 | 6584043 | 30 Normanby Road, Dargaville |  |  | CELLSITE | [9 empty] | 2015-05-14 | 2015-05-14 | 2015-06-22 | 2015-06-22 |  |  |  |  | 2015-05-17
0 | COW | 894 | COW-000-010 | Tulip | COW-000-010-H | Winton - Roaming COW | Cellsite On Wheels | 9 | COW | ACTIVE | BO |  |  |  | B2B | COSITE | 10 | 12 |  | -46.1176 | 168.392 | [6 empty] | FALSE | FALSE |  |  | FALSE |  | 2015-06-23 | 2015-06-23 |  |  | 2015-06-26 |  |  | 2015-06-26 |  | 2015-06-30 | 2015-07-02 | 2015-08-14 |  |  | 2015-08-14 |  | PERMITTED | 2015-07-09 |  | 2015-07-14 |  |  | 2015-07-15 | 2015-07-14 | 2015-07-22 |  | 2015-07-22 | [15 empty] | 2015-08-27 |  | 2015-09-03 |  | 2015-08-11 |  | 2015-08-21 |  |  |  |  | 2015-08-31 | 2015-10-02 |  |  |  |  | 24 June: Site visit (Phil & Andrew) 2 July: LO agreement in principle (overseas to 22 July). 8 July: Fibre feasibility ordered 13 July: Fibre ordered (SNAP termination) 13 July: Co-site applications lodged for VF/Spark/Woosh 22 July: RFS set date 15 July: Requested Steve Esther to look at power pole connection 15 July: Planner approves proposal (via e-mail) 17 July: Sent licence to LO to sign | [15 empty] | 2015-09-02 |  |  | 2015-08-25 | FALSE |  | 2153791 | 5444512 | off Sinclair Rd, Winton |  |  | CELLSITE |  |  |  | ROAMING | [5 empty] | 2015-07-13 |  | 2015-07-23 | [5 empty] | 2015-06-26
0 | COW | 895 | COW-000-011 | Bobby | COW-000-011-C | Queenstown Central | Cellsite On Wheels |  | COW | ACTIVE | BO | X | NOPOLE |  |  | STANDALONE |  |  |  | -45.0317 | 168.6581 | [17 empty] | 2013-05-27 | 2 |  | 2013-08-21 |  |  |  | 2013-07-31 |  |  | 2013-07-31 | PERMITTED |  | 2013-07-11 |  | 2013-08-31 | 1 | [32 empty] | 2013-09-09 | [17 empty] | 2013-07-11 | MEDIUM | [7 empty] | 2167968 | 5566140 | Man St Car Park 22 Man Street Queenstown |  |  | CELLSITE |  |  | 2015-05-26
0 | COW | 896 | COW-000-012 | Bruce | COW-000-012-A | Stratford - Roaming | Cellsite On Wheels | 21 | COW | ACTIVE | BO | X | SP | [6 empty] | -39.3386 | 174.2834 | [6 empty] | FALSE | FALSE |  |  | FALSE | [54 empty] | 2016-01-07 | 2016-01-07 |  |  |  |  | 9/11/15 - 1/3/16 Site on Air 7 January | [19 empty] | FALSE |  | 2620672 | 6206595 | 38 Miranda Street Stratford |  |  | CELLSITE |  |  |  | ROAMING
0 | COW | 897 | COW-000-013 | Tululah |  |  | Cellsite On Wheels |  | TIER_6
0 | COW | 898 | COW-000-014 | Sally |  |  | Cellsite On Wheels |  | TIER_6
0 | COW | 899 | COW-000-015 | Victoria St COW |  |  | Cellsite On Wheels | 11 | TIER_6 | [22 empty] | FALSE
0 | COW | 900 | COW-000-016 | Christchurch - Showgrounds |  |  | Cellsite On Wheels |  | COW
0 | COW | 901 | COW-000-017 | Christchurch - Racecourse |  |  | Cellsite On Wheels |  | COW
0 | GSB | 902 | GSB-028-001 |  |  |  | Gisborne |  | TIER_9
0 | GSB | 903 | GSB-028-002 |  |  |  | Gisborne |  | TIER_9
0 | GSB | 904 | GSB-028-003 | Awapuni | GSB-028-003-A | Awapuni, VF Colo (Awapuni) | Gisborne | 7 | TIER_3 | ACTIVE | COLO | DU | COLO |  | STACK_A | COLO |  |  | 1 | -38.6661 | 178.0064 |  | 2012-01-24 |  | 2011-06-01 | Leased Line | HKB-031-001-A | TRUE | TRUE | 2011-06-01 |  | TRUE |  | 2011-07-22 | 2011-07-21 | 2011-07-22 | 2011-07-22 | 2011-07-29 | 2011-07-29 | 2 | 2011-07-29 | 2011-08-04 | 2011-08-12 | 2011-08-11 | 2012-04-12 | 2012-04-12 |  | 2012-04-12 | 2012-04-12 | PERMITTED | 2011-08-10 | 2011-08-16 | 2011-09-23 | 2011-09-21 | 2 | 2011-09-23 | 2011-09-21 |  |  | 2012-04-18 | 2012-04-19 | 2 |  | 2012-04-18 | 2012-05-08 | 2012-05-21 |  |  |  |  | 2012-05-10 | 2012-05-09 | 2012-05-18 | 2012-05-21 | 2012-05-20 | 2012-05-23 | 2012-05-24 | [8 empty] | 2012-06-10 | 2012-06-15 | 2012-06-15 | 2012-06-29 | 2012-06-29 | 2013-05-06 | 2013-05-02 | 29/09/11 - Jason to check with Mike Goss on when to sign sub-lease 29/09/11 - Sub-lease with VF required. Documents to be requested 06/10/11 - Colo documents ordered 28/10/11 - 2D not chasing colo docs this stage until final decision on build or not 24/11/11 - VF has requested 2D to get additional term on lease. VF then do their document changes, then sublease document to be done with 2D | VNZ | 2012-06-01 | 2012-05-12 | 2012-05-12 | 2012-04-20 | 2012-05-21 | 2012-04-30 | 2012-05-21 | 2012-05-25 | 2012-05-23 | 2012-06-08 | 2012-06-08 |  |  | GISBORNE | 2012-05-22 | 2012-05-24 | BUILD | 2012-05-15 | FALSE |  | 2945543 | 6269802 | 210 Stanley Rd, Gisborne |  |  | CELLSITE |  |  | 2015-04-07 | [12 empty] | 2012-06-08 | 2012-06-15 | 2011-07-22
0 | GSB | 905 | GSB-028-004 | Gisborne Central | GSB-028-004-A | River Oak Mews | Gisborne | 7 | TIER_3 | ACTIVE | RT | DF | RT |  | STACK_A | COSITE |  |  | 1 | -38.6645 | 178.0251 |  | 2012-01-24 |  | 2010-02-26 | Leased Line | HKB-031-001-A | FALSE | FALSE |  |  | FALSE |  | 2012-02-23 | 2012-02-22 | 2012-02-29 | 2012-03-01 | 2012-04-05 | 2012-04-17 | 3 | 2012-04-05 | 2014-12-08 | 2012-05-16 | 2012-04-27 | 2012-05-23 | 2012-05-14 | 1 | 2012-05-23 | 2012-05-14 | DISCRETIONARY_RESTRICT | 2012-04-23 | 2012-04-23 | 2012-06-01 | 2012-05-17 | 1 | 2012-06-01 | 2012-05-17 |  |  | 2012-07-30 | 2012-07-31 | 1 |  | 2012-07-27 | 2012-07-31 | [5 empty] | 2012-07-02 | 2012-07-02 | 2012-07-31 | 2012-07-27 | 2012-06-29 | 2012-07-27 | 2012-07-27 | [8 empty] | 2012-07-27 | 2012-08-16 | 2012-08-09 | 2012-08-15 | 2012-08-15 | 2013-09-17 | 2013-08-12 |  | VNZ | 2012-07-27 | 2012-06-15 |  |  |  | 2012-06-25 |  | 2012-07-31 | 2012-07-27 | 2012-08-01 | 2012-08-02 | 2012-02-27 | LOW | GISBORNE | 2012-07-27 | 2012-07-27 | BUILD | 2012-07-17 | FALSE |  | 2947175 | 6269897 | 74 Grey St. Gisborne CBD |  |  | CELLSITE |  |  | 2015-04-07 | [12 empty] | 2012-07-30 | 2012-08-01 | 2012-03-01
0 | GSB | 906 | GSB-028-005 |  |  |  | Gisborne |  | TIER_9
0 | GSB | 907 | GSB-028-006 |  |  |  | Gisborne |  | TIER_9
0 | GSB | 908 | GSB-028-007 |  |  |  | Gisborne |  | TIER_9
0 | GSB | 909 | GSB-028-008 |  |  |  | Gisborne |  | TIER_9
0 | GSB | 910 | GSB-028-009 |  |  |  | Gisborne |  | TIER_9
0 | GSB | 911 | GSB-028-010 | Gisborne West |  |  | Gisborne | 7 | TIER_9 | [22 empty] | FALSE
0 | GSB | 912 | GSB-028-011 |  |  |  | Gisborne |  | TIER_9
0 | GSB | 913 | GSB-028-012 | Riverdale | GSB-028-012-B | GF House of Breakthrough | Gisborne | 7 | TIER_3 | ACTIVE | GF | DU | SP |  | STACK_A | COSITE | 23.5 | 23.5 | 1 | -38.6394 | 178.003 |  | 2012-01-24 |  | 2010-02-26 | Leased Line | HKB-031-001-A | FALSE | FALSE |  |  | FALSE |  | 2012-02-23 | 2012-02-22 | 2012-03-08 | 2012-03-12 | 2012-05-07 | 2012-05-08 | 1 | 2012-05-07 | 2012-05-08 | 2012-06-05 | 2012-05-31 | 2012-08-03 | 2012-08-02 | 1 | 2012-08-30 | 2012-08-27 | PERMITTED | 2012-05-11 | 2012-05-14 | 2012-06-22 | 2012-06-07 | 1 | 2012-06-22 | 2012-06-07 |  |  | 2012-08-15 | 2012-08-14 | 2 |  | 2012-08-15 | 2013-05-06 | 2012-08-29 |  |  | 2012-07-31 |  | 2012-08-14 | 2012-08-14 | 2012-10-12 | 2012-10-12 | 2012-08-29 | 2012-09-11 | 2012-09-07 | [8 empty] | 2012-09-10 | 2012-09-24 | 2012-09-14 | 2012-10-06 | 2012-09-28 | 2013-06-17 | 2013-06-06 |  |  | 2012-09-11 |  |  |  |  | 2012-08-29 | 2012-08-29 | 2012-08-21 | 2012-08-21 | 2012-09-12 | 2012-09-13 | 2012-05-14 | MEDIUM | GISBORNE | 2012-08-31 | 2012-08-31 | BUILD | 2012-08-30 | TRUE |  | 2945407 | 6272783 | House of Breakthrough Church Corner Ormond & Lytton Roads Gisborne |  |  | CELLSITE |  |  | 2015-04-07 | [12 empty] | 2012-09-20 | 2012-09-17 | 2012-03-12
0 | GSB | 914 | GSB-028-013 | Elgin | GSB-028-013-B | GF 681 Childers Road | Gisborne | 7 | TIER_3 | ACTIVE | GF | DU | SP |  | STACK_A | STANDALONE |  | 23.5 | 1 | -38.6569 | 177.9969 |  | 2012-01-24 |  | 2010-02-26 | Leased Line | HKB-031-001-A | FALSE | FALSE |  |  | FALSE |  | 2012-02-23 | 2012-02-22 | 2012-03-08 | 2012-03-19 | 2012-04-26 | 2012-05-01 | 3 | 2012-04-26 | 2012-07-27 | 2012-05-29 | 2012-05-28 | 2012-06-29 | 2012-06-27 |  | 2012-06-29 | 2012-06-27 | DISCRETIONARY_RESTRICT | 2012-05-04 | 2012-05-04 | 2012-06-15 | 2012-06-14 | 1 | 2012-06-15 | 2012-06-14 |  |  | 2012-07-25 | 2012-07-27 | 2 |  | 2012-07-25 | 2013-05-06 | 2012-08-29 |  |  | 2012-07-11 |  | 2012-08-02 | 2012-08-02 | 2012-09-05 | 2012-09-05 | 2012-08-28 | 2012-09-10 | 2012-09-07 | [8 empty] | 2012-09-10 | 2012-09-24 | 2012-09-14 | 2012-10-06 | 2012-09-28 | 2013-09-17 | 2013-08-12 |  |  | 2012-09-10 |  |  |  |  | 2012-08-29 | 2012-08-29 | 2012-08-21 | 2012-08-21 | 2012-09-12 | 2012-09-13 | 2012-02-27 | HIGH | GISBORNE | 2012-08-31 | 2012-08-30 | BUILD | 2012-08-28 | TRUE |  | 2944774 | 6270867 | 681 Childers Road Elgin |  | cabinets within yard requirement to Elgin Lane RSR (residential zone). - 27/02/2012 | CELLSITE |  |  | 2015-04-07 | [12 empty] | 2012-09-19 | 2012-09-17 | 2012-03-19
0 | GSB | 915 | GSB-028-014 | Mangapapa East | GSB-028-014-B | Mangapapa East, Ormond Road BP petrol pump | Gisborne | 24 | 2015P | ACTIVE | GF | DU5 | P4L |  | INLINE | STANDALONE |  |  |  | -38.6507 | 178.0203 |  | 2010-02-26 |  | 2010-02-26 | Leased Line | HKB-030-001-A | FALSE | FALSE |  |  | FALSE |  | 2015-04-01 | 2015-04-01 | 2015-08-28 | 2015-09-09 | 2015-09-25 |  | 1 |  |  | 2015-07-28 | 2015-07-28 | 2015-10-30 |  |  |  |  | PERMITTED | 2015-09-28 |  | 2015-10-30 |  | 1 |  |  | 2015-10-16 |  | 2015-11-13 |  | 1 | [8 empty] | 2016-01-18 |  | 2016-02-29 |  |  | 2016-03-11 | [10 empty] | 2016-04-15 | [5 empty] | 9/7 AS -Moved to next year build | [10 empty] | 2016-03-31 | [6 empty] | ONHOLD |  | FALSE |  | 2946843 | 6271445 | BP Petrol pump, Ormons Road, Gisborne |  |  | CELLSITE | WIPACTIVE |  |  | CAPACITY |  |  |  | 2015-11-02 | [5 empty] | 2015-12-04 |  |  |  | 2015-09-09
0 | GSB | 916 | GSB-028-015 | Outer Kaiti | GSB-028-015-C | GF at Jackson St Shopping Centre | Gisborne | 7 | TIER_3 | ACTIVE | GF | DU | SP |  | STACK_A | STANDALONE | 18 | 18 |  | -38.6752 | 178.0459 |  | 2012-01-24 |  | 2010-02-26 | Leased Line | HKB-031-001-A | FALSE | FALSE |  |  | FALSE |  | 2012-02-23 | 2012-02-23 | 2012-03-08 | 2012-03-12 | 2012-04-26 | 2012-04-26 | 1 | 2012-04-26 | 2012-04-26 | 2012-05-24 | 2012-05-15 | 2012-06-29 | 2012-06-14 | 1 | 2012-06-29 | 2012-06-14 | PERMITTED | 2012-05-04 | 2012-05-04 | 2012-06-15 | 2012-06-06 | 1 | 2012-06-15 | 2012-06-06 |  |  | 2012-09-28 | 2012-09-26 | 1 |  | 2012-09-28 | 2012-09-26 | 2012-10-01 |  |  | 2012-08-15 |  | 2012-09-17 | 2012-09-17 | 2012-10-02 | 2012-10-02 | 2012-10-01 | 2012-10-04 | 2012-10-03 | [8 empty] | 2012-10-03 | 2012-10-26 | 2012-10-19 | 2012-10-13 | 2012-10-13 | 2013-05-17 | 2013-05-07 |  |  | 2012-10-04 |  |  | 2012-09-21 | 2012-10-01 | 2012-09-21 | 2012-10-01 | 2012-10-02 | 2012-10-01 | 2012-10-04 | 2012-10-04 | 2012-02-27 | HIGH | GISBORNE | 2012-10-02 | 2012-10-02 | BUILD | 2012-10-02 | TRUE |  | 2948914 | 6268608 | Jackson St Shopping Centre 498-508 Wainui Rd Outer Kaiti |  |  | CELLSITE |  |  | 2015-04-07 | [12 empty] | 2012-10-08 | 2012-10-05 | 2012-03-12
0 | GSB | 917 | GSB-028-016 | Wainui | GSB-028-016-A | Wainui, VF Colo (Wainui) | Gisborne | 7 | TIER_3 | ACTIVE | COLO | DU | COLO |  | STACK_A | COLO |  |  | 1 | -38.6782 | 178.0699 |  | 2012-01-24 |  | 2011-06-01 | Microwave | GSB-028-003-A | TRUE | TRUE | 2011-06-01 |  | TRUE |  | 2011-07-22 | 2011-07-21 | 2011-07-22 | 2011-07-22 | 2011-08-08 | 2011-08-04 | 1 | 2011-08-08 | 2011-08-04 | 2011-10-07 | 2011-10-06 | 2012-05-04 | 2012-04-23 |  | 2012-05-31 | 2012-07-11 | DISCRETIONARY_RESTRICT | 2011-08-10 | 2011-08-16 | 2011-09-09 | 2011-09-14 | 1 | 2011-09-09 | 2011-09-14 |  |  | 2012-04-18 | 2012-04-19 | 2 |  | 2012-04-18 | 2012-05-16 | 2012-05-25 |  |  |  |  | 2012-05-21 | 2012-05-08 | 2012-05-27 | 2012-05-27 | 2012-05-27 | 2012-06-01 | 2012-06-10 | [8 empty] | 2012-06-11 | 2012-06-15 | 2012-06-15 | 2012-06-29 | 2012-06-29 | 2013-06-10 | 2013-05-24 | 25/08/11 - Sublease VF/2D to sign 29/09/11 - Jason to check with Mike Goss on when to sign sub-lease 29/09/11 - Sub-lease with VF required. Documents to be requested 06/10/11 - Colo documents ordered 28/10/11 - 2D not chasing colo docs this stage until final decision on build or not 24/11/11 - Owner has sub-leae doc from VF. wanting $2k extra rent (not agreeable with VF!!). Then docs with 2D 9/5/13: • Tx rearrangement requested by Clif. Refer Clif for details. • Redlined PD at Tx rearrangement required. Refer Clif for details. Redine PD at T:\2degrees\Site Folders\Gisborne (GSB)\GSB-028 Gisborne\016 Wainui\Active Candidate-A VF Co-lo\Site Design\Planning\Rev 2\History. • VF approval for new location received. Docs in site folder. • RFQ sent to Graham Parker, waiting for response. | VNZ | 2012-06-02 | 2012-05-12 | 2012-05-12 | 2012-04-20 | 2012-05-21 | 2012-05-24 | 2012-05-25 | 2012-05-25 | 2012-05-28 | 2012-06-08 | 2012-06-08 |  |  | GISBORNE |  |  | BUILD | 2012-05-25 | FALSE |  | 2950986 | 6268158 | Wheatstone Rd, Wainui, Gisborne |  | Urban Ridgeline and Protected Coastal Area - 16/08/2011 | CELLSITE |  |  | 2015-04-07 | [12 empty] | 2012-06-11 | 2012-06-15 | 2011-07-22
0 | GSB | 918 | GSB-028-017 | Lytton West |  |  | Gisborne |  | TIER_9 | [22 empty] | FALSE
0 | GSB | 919 | GSB-028-018 | Gisborne West | GSB-028-018-A | Gisborne West | Gisborne | 4 | TIER_3 | ACTIVE | COLO | DU | COLO |  | STACK_A | COLO |  |  | 1 | -38.5961 | 177.9885 |  | 2012-01-25 |  | 2011-06-01 | Microwave | GSB-028-003-A | TRUE | TRUE | 2011-06-01 |  | TRUE |  | 2011-08-12 | 2011-08-12 | 2011-08-15 | 2011-08-15 | 2011-08-02 | 2011-07-29 | 3 | 2011-08-16 | 2011-08-25 | 2011-09-02 | 2011-08-25 | 2011-12-16 | 2011-11-22 |  | 2011-12-21 | 2012-02-28 | PERMITTED | 2011-08-12 | 2011-08-16 | 2011-09-23 | 2011-09-21 | 2 | 2011-09-27 | 2011-09-21 |  |  | 2012-04-19 | 2012-04-20 | 2 | 3 | 2012-04-19 | 2013-09-25 | 2012-05-18 |  |  |  |  | 2012-05-21 | 2012-05-19 | 2012-05-28 | 2012-05-27 | 2012-05-27 | 2012-06-07 | 2012-06-07 | [8 empty] | 2012-06-09 | 2012-06-15 | 2012-06-15 | 2012-06-29 | 2012-06-29 | 2013-09-17 | 2013-10-14 | 25/08/11 - Deed of Variation to be done 1/9/11 - VF Preliminary approval has been received 29/09/11 - Jason to check with Mike Goss on when to sign sub-lease 29/09/11 - Sub-lease with VF required. Documents to be requested 06/10/11 - Colo documents with 2D for signing 24/11/11 - Sub-lease signed by 2D, but not sending back to VF until build confirmed (rent starts when sent to VF) | VNZ | 2012-06-08 | 2012-06-28 | 2012-06-28 | 2012-04-20 | 2012-05-18 | 2012-04-30 | 2012-05-18 | 2012-05-25 | 2012-05-25 | 2012-06-08 | 2012-06-08 |  |  | GISBORNE |  |  | BUILD | 2012-05-26 | FALSE |  | 2944417 | 6277655 | Waimata Valley Road Waipura Gisborne |  |  | CELLSITE | [15 empty] | 2012-06-14 | 2012-06-19
0 | GSB | 920 | GSB-028-019 | Tutara | GSB-028-019-A | Kordia Colo | Gisborne | 24 | TIER_4 | ACTIVE | COLO | DF | LATTICE |  | STACK_A | COLO |  | 16.5 |  | -37.8059 | 178.3588 |  | 2015-03-04 |  | 2015-04-15 | Leased Line | AKL-007-112-A | FALSE | FALSE |  |  | FALSE |  | 2014-11-25 | 2014-11-25 | 2015-03-27 | 2015-03-27 | 2015-04-17 | 2015-03-31 | 1 | 2015-04-08 | 2015-03-31 | 2015-05-07 | 2015-05-07 | 2015-05-15 | 2015-05-07 |  | 2015-08-04 | 2015-08-04 | DISCRETIONARY_FULL | 2015-05-31 | 2015-04-20 | 2015-06-30 | 2015-04-20 | 1 |  | 2015-04-20 | 2015-04-17 | 2015-03-27 | 2015-05-31 | 2015-04-10 | 1 |  | 2015-04-10 | 2015-04-10 | [5 empty] | 2015-08-28 | 2015-08-27 | 2015-09-30 | 2015-09-17 | 2015-08-06 | 2015-10-09 | 2015-10-05 | 2015-08-03 | 2015-07-28 | 2015-07-28 | 2015-07-28 | 2015-07-28 | 2015-07-28 | 2015-07-28 | 2015-07-28 |  | 2015-10-29 | 2015-10-29 |  |  |  |  | PB - colo request submitted 27 Nov (PDI claimed). PB 6 Jan - await Kordia response to proposal, site is subject to RF review/confirmation 05/03 AS - Spoken to Kordia on progress. Kordia still waiting for power company to provide quote on power upgrade required to meet 2degrees single phase 63amps power requirement. 12/03: Ed will check feasilibility from Tikitiki Chorus exchange as plan B for Kordia co-lo Tutara if Kordia fails to provide backhaul leased line. 12/03 AS - Spoken to Kordia on what power rating is currently available w/o upgrade from power company just to cater initial build current load. 20/03 AS: Quote from Kordia received..20amps power sufficient Tim confirmed it. Proceed with lease, RMA, PDI & CDI 16/04: PD & CDs issued 16/04: Waiting for quote on formal letter from Kordia - It is with John Watson to proceed 6/08 AS: delaying due to bad weather | KDA | [9 empty] | 2015-10-26 | 2015-10-28 |  |  |  | 2015-07-28 | 2015-07-28 | BUILD | 2015-08-06 | FALSE |  | 2981819 | 6363378 | SH35, Te Aroroa Road, Gisborne |  |  | CELLSITE |  |  |  | ROAMING |  |  | 2015-04-24 | 2015-04-23 | 2015-04-23 |  |  |  |  | 2015-05-14 | 2015-05-13 |  |  | 2015-03-27
0 | GSB | 921 | GSB-028-020 | Hicks Bay | GSB-028-020-A | GF | Gisborne | 24 | TIER_4 | ACTIVE | GF | DF | T2 25 RH |  | STACK_A | STANDALONE |  |  |  | -37.5992 | 178.3088 |  | 2015-03-04 |  | 2015-04-15 | Microwave | GSB-028-019-A | FALSE | FALSE |  |  | FALSE |  | 2015-04-03 | 2015-04-01 | 2015-04-30 | 2015-04-15 | 2015-05-31 | 2015-05-27 | 2 |  | 2015-07-21 | 2015-07-28 | 2015-07-28 | 2015-08-07 | 2015-08-05 |  |  | 2015-08-04 | DISCRETIONARY_RESTRICT | 2015-06-19 | 2015-06-09 | 2015-08-14 | 2015-08-13 | 1 |  | 2015-09-10 | 2015-05-15 | 2015-05-14 | 2015-07-31 | 2015-07-31 | 2 |  |  | 2015-09-03 | [5 empty] | 2015-09-15 | 2015-09-21 | 2015-10-16 | 2015-10-06 |  | 2015-10-30 | 2015-11-03 | 2015-09-04 |  | 2015-09-04 | [6 empty] | 2015-11-13 | 2015-11-10 |  |  |  |  | 05/03 AS - Site brief issued to WH to come up with potential candidates to plan site caravan 12/03 AS: TX far end will be Te Araroa Chorus exchange 18/03 AS Preference 1 Site#2; - Private broadband, Preference 2 Site#1; - Vodafone 16/04 AS PDI issed | [10 empty] | 2015-11-06 | 2015-11-10 |  | LOW |  |  |  | BUILD |  | FALSE |  | 2978770 | 6386541 | 5138 Te Aroroa Road, Hicks Bay, Gisborne |  |  | CELLSITE |  |  |  | ROAMING |  | 2015-07-09 | 2015-06-02 | 2015-07-17 | 2015-07-27 |  |  |  |  | 2015-09-04 | 2015-09-03 |  |  | 2015-04-15
0 | GSB | 922 | GSB-028-021 | Te Karaka | GSB-028-021-A | Spark Co-site | Gisborne | 24 | TIER_4 | ACTIVE | GF | DF | T2 20 RH |  | STACK_A | STANDALONE |  |  |  | -38.4616 | 177.8917 |  | 2015-03-04 |  | 2015-04-15 | Fibre Optic | HKB-030-001-A | FALSE | FALSE |  |  | FALSE |  | 2015-04-03 | 2015-04-01 | 2015-04-17 | 2015-04-15 | 2015-05-18 | 2015-05-26 | 1 |  | 2015-05-26 |  | 2015-05-06 | 2015-08-28 | 2015-09-10 |  | 2015-08-28 | 2015-08-11 | DISCRETIONARY_RESTRICT | 2015-05-29 | 2015-05-28 | 2015-06-26 | 2015-07-08 | 1 |  | 2015-08-11 | 2015-05-15 | 2015-05-14 | 2015-07-31 | 2015-07-30 | 1 |  |  | 2015-07-30 | [5 empty] | 2015-09-15 | 2015-10-06 | 2015-11-11 | 2015-11-17 |  | 2015-11-13 | 2015-11-17 | 2015-09-04 |  | 2015-07-28 | 2015-07-28 | [5 empty] | 2015-11-24 | 2015-11-24 |  |  |  |  | active candidate for forecasting 12/03 AS: Ed to come back with TX feasilibility from Chorus. If it fails need to come back with back up. 16/04 AS: PDI issued 14/05 AS: PD Rev1 issued, CDI issued further | [10 empty] | 2015-11-24 | 2015-11-17 |  |  |  | 2015-09-04 |  | BUILD |  | FALSE |  | 2936802 | 6293020 | 16 Mangaoe Road, Te Karaka, Gisborne |  |  | CELLSITE |  |  |  | ROAMING |  | 2015-06-02 | 2015-05-04 | 2015-07-17 | 2015-07-21 |  |  |  |  | 2015-09-08 | 2015-09-08 |  |  | 2015-04-15
0 | GSB | 923 | GSB-028-022 | Tolaga Bay | GSB-028-022-B | Kordia colo | Gisborne | 24 | TIER_4 | ACTIVE | COLO | DF | COLO |  | STACK_A | COLO |  |  |  | -38.3956 | 178.324 |  | 2015-03-10 |  | 2015-03-31 | Microwave | GSB-028-024-A | FALSE | FALSE |  |  | FALSE |  | 2015-04-03 | 2015-04-01 | 2015-08-07 | 2015-08-05 | 2015-08-14 | 2015-08-06 | 1 |  | 2015-08-06 | 2015-08-07 | 2015-08-05 | 2015-08-31 | 2015-08-06 |  |  | 2015-08-06 |  | 2015-08-31 | 2015-08-06 | 2015-09-30 | 2015-08-06 | 1 |  | 2015-08-06 | 2015-08-14 | 2015-08-05 | 2015-08-25 | 2015-08-20 | 1 |  |  | 2015-08-20 | [5 empty] | 2015-10-02 | 2015-09-21 | 2015-10-16 | 2015-11-03 |  | 2015-10-30 | 2015-11-03 | [9 empty] | 2015-12-10 | 2015-12-06 |  |  |  |  | 7/05 AS: Spark co-lo and Kordia co-lo needs submission | KDA | [9 empty] | 2015-12-04 | 2015-12-04 | [5 empty] | BUILD |  | FALSE |  | 2974912 | 6298202 | 128 Wharf Road, Tolaga |  |  | CELLSITE |  |  |  | ROAMING |  |  | 2015-07-31 | 2015-09-04 | 2015-08-04 |  |  |  |  | 2015-10-02 | 2015-08-24 |  |  | 2015-08-05
0 | GSB | 924 | GSB-028-023 | Hicks Bay TX only |  |  | Gisborne | 24 | TIER_9 | [22 empty] | FALSE
0 | GSB | 925 | GSB-028-024 | Tolaga Bay TX only | GSB-028-024-A | Mangatarata Kordia | Gisborne | 24 | TIER_4 | ACTIVE | COLO | TX | NOPOLE |  | STACK_A | COLO |  |  |  | -38.0976 | 178.0981 |  | 2015-04-15 |  | 2015-03-31 | Leased Line | AKL-007-112-A | FALSE | FALSE |  |  | FALSE |  | 2015-08-06 | 2015-08-06 | 2015-08-05 | 2015-08-05 | 2015-08-07 | 2015-08-06 | 1 |  | 2015-08-06 | 2015-08-06 | 2015-08-06 | 2015-08-06 | 2015-08-06 |  | 2015-08-06 | 2015-08-11 | PERMITTED |  | 2015-08-06 |  | 2015-08-06 | 1 |  | 2015-08-06 | 2015-08-05 | 2015-08-05 | 2015-08-06 | 2015-08-20 | 1 |  |  | 2015-08-20 | [5 empty] | 2015-10-16 | 2015-11-20 | 2015-10-23 | 2015-11-20 |  | 2015-11-13 | 2015-11-20 | 2015-10-16 |  | 2015-10-09 | [6 empty] | 2015-12-10 | 2015-12-06 | [5 empty] | KDA | [9 empty] | 2015-12-04 | 2015-12-04 |  |  |  | 2015-08-06 | 2015-08-06 | BUILD |  | FALSE |  | 2957075 | 6332371 | Pirauau hill, Mata road, Tokumaru bay |  |  | TXSITE |  |  |  | ROAMING |  |  | 2015-07-31 | 2015-08-04 | 2015-08-04 |  |  |  |  | 2015-08-28 | 2015-08-24 |  |  | 2015-08-05
0 | HKB | 926 | HKB-029-001 |  |  |  | Wairoa |  | TIER_9
0 | HKB | 927 | HKB-029-002 | Wairoa | HKB-029-002-B | GF-VF Cosite | Wairoa | 7 | TIER_3 | ACTIVE | GF | DU | T2 15 RFH |  | STACK_A | COSITE |  | 15 |  | -39.045 | 177.3714 |  |  |  |  | Leased Line | HKB-031-001-A | FALSE | FALSE |  |  | FALSE |  | 2012-02-23 | 2012-02-22 | 2012-03-08 | 2012-03-19 | 2012-05-08 | 2012-05-08 | 1 | 2012-05-08 | 2012-05-08 | 2012-08-31 | 2012-09-05 | 2012-09-14 | 2012-09-13 | 1 | 2012-09-14 | 2012-09-13 | DISCRETIONARY_RESTRICT | 2012-05-25 | 2012-05-28 | 2012-07-20 | 2012-07-06 | 1 | 2012-07-20 | 2012-07-06 |  |  | 2012-09-28 | 2012-10-02 | 1 |  | 2012-09-28 | 2012-10-02 | 2012-10-01 |  |  |  |  | 2012-09-19 | 2012-09-20 | 2012-10-17 | 2012-10-17 | 2012-10-09 | 2012-10-19 | 2012-10-18 | [8 empty] | 2012-10-19 | 2012-11-02 | 2012-11-02 | 2012-10-27 | 2012-10-26 | 2013-06-17 | 2013-05-31 |  |  | 2012-10-19 |  |  | 2012-08-20 | 2012-10-01 | 2012-08-21 | 2012-10-01 | 2012-10-17 | 2012-10-16 | 2012-10-24 | 2012-10-25 | 2012-02-27 | LOW | GISBORNE | 2012-10-12 | 2012-10-12 | BUILD | 2012-10-15 | FALSE |  | 2888296 | 6230670 | Part Section 5 & Section 6 Block VIII Waihua Survey District |  | 15m - 27/02/2012 Iwi site of significance - approval received 28 May - 29/05/2012 | CELLSITE | [15 empty] | 2012-10-24 | 2012-10-24 | 2012-03-19
0 | HKB | 928 | HKB-029-003 |  |  |  | Wairoa |  | TIER_9
0 | HKB | 929 | HKB-029-004 | Wairoa Town |  |  | Wairoa |  | TIER_9 | [83 empty] | RRU likely as lattice tower with plenty of room on Chorus / Spark Exchange tower. 3 Antennas initially with future L700 allowed for where possible
0 | HKB | 930 | HKB-029-005 | Nuhaka | HKB-029-005-B | Greenfield | Wairoa | 24 | TIER_5 | ACTIVE | GF | DF | SP |  | STACK_A | COSITE | 16 | 17.5 |  | -38.9537 | 177.7784 | [6 empty] | FALSE | FALSE |  |  | FALSE |  | 2015-09-11 | 2015-12-21 | 2015-12-21 | 2015-12-21 | 2016-02-05 | 2016-01-26 | 1 |  | 2016-01-26 | 2016-02-19 | 2016-02-05 | 2016-03-11 | [5 empty] | 2016-02-19 |  | 2016-03-18 |  |  |  |  | 2016-03-18 |  | 2016-04-29 | [10 empty] | 2016-06-10 |  | 2016-07-15 |  |  | 2016-07-29 | [10 empty] | 2016-08-15 | [16 empty] | 2016-08-05 | [6 empty] | BUILD |  | FALSE |  | 2924030 | 6238999 | MORERE HILL, SH2 WAIROA |  |  | CELLSITE |  |  |  | ROAMING |  |  |  | 2016-04-25 | [5 empty] | 2016-05-31 |  |  |  | 2015-12-21
0 | HKB | 931 | HKB-029-006 | Whakapunake Kordia | HKB-029-006-A | Whakapunake Kordia | Wairoa | 24 | TIER_5 | ACTIVE | COLO | TX | COLO |  | STACK_A | COLO | [11 empty] | FALSE | FALSE |  |  | FALSE |  |  | 2015-12-07 | 2016-02-12 | 2016-02-10 | 2016-03-11 |  |  |  |  | 2016-02-26 |  | 2016-02-12 | [5 empty] | 2016-03-04 |  | 2016-03-18 |  |  |  |  | 2016-03-11 |  | 2016-03-30 | [10 empty] | 2016-05-30 |  | 2016-06-30 |  |  | 2016-07-15 | [10 empty] | 2016-08-19 | [6 empty] | KDA | [9 empty] | 2016-07-29 | [6 empty] | BUILD |  | FALSE | [6 empty] | TXSITE |  |  |  | ROAMING |  |  |  | 2016-04-15 | [5 empty] | 2016-05-20 |  |  |  | 2016-02-10
0 | HKB | 932 | HKB-030-001 | Hastings Central (Main HUB) | HKB-030-001-A | Hastings Central Westpac Bank - MAIN HUB | Hastings | 1 | TIER_2 | ACTIVE | RT | DF | RT | grey | STACK_A | COSITE | 22.7 | 23.2 | 1 | -39.6415 | 176.843 |  | 2010-09-02 |  | 2010-02-12 | Fibre Optic | WLG-047-071-A | FALSE | TRUE |  |  | FALSE |  | 2011-03-25 | 2011-03-17 | 2011-04-01 | 2011-03-22 | 2011-05-02 | 2011-05-04 | 3 | 2011-05-02 | 2014-12-08 | 2011-05-20 | 2011-05-18 | 2011-06-15 | 2011-06-10 | 1 | 2011-06-30 | 2011-07-06 | PERMITTED | 2011-06-03 | 2011-06-08 | 2011-07-18 | 2011-07-14 | 2 | 2011-07-22 | 2011-07-14 |  |  | 2011-08-26 | 2011-08-26 | 1 |  | 2011-08-26 | 2011-08-26 | 2011-11-14 |  |  |  |  | 2011-08-08 | 2011-08-08 | 2011-10-21 | 2011-11-14 | 2011-10-09 | 2011-10-14 | 2011-10-14 | [8 empty] | 2011-10-27 | 2011-11-14 | 2011-11-08 | 2011-11-21 | 2011-11-15 | 2013-04-12 | 2013-04-19 | Genny on wheel's ordered in VO72, ETA required & Ops to arrange storage. Note to Huawei re noise level for a/c unit. Site snag free, Alan to resend the FAN but can't be signed until Genny delivered. 3/4/13 - FAC sign off completed - waiting for mobile genny 19/04/13 - FAC signed |  | 2011-10-19 | 2011-08-29 | 2011-08-29 | 2011-09-30 | 2011-11-14 | 2011-09-09 | 2011-11-14 | 2011-10-13 | 2011-10-13 |  | 2011-11-01 | [6 empty] | 2011-10-09 | FALSE |  | 2839757 | 6166612 | Westpac Bank |  | Photomontage sent to Council and initial feedback positive. Note - antenna locations have been changed since montage sent. - 24/03/2011 s92 request re air conditioning noise specifications recieved from council on 17 June 11. Information sent and emailed by AT and has been accepted. - 22/07/2011 | CELLSITE |  |  | 2015-04-22 | [12 empty] | 2011-11-14 | 2011-11-14
0 | HKB | 933 | HKB-030-002 | Stortford Lodge | HKB-030-002-E | 129 Maraekakaho Rd | Hastings | 1 | TIER_2 | ACTIVE | GF | DU | T2 25 UF | grey | STACK_A | STANDALONE | 24.5 | 25 | 1 | -39.6311 | 176.8284 |  | 2010-09-02 |  | 2010-02-12 | Microwave | HKB-030-001-A | FALSE | TRUE |  |  | FALSE | 2011-03-09 | 2011-02-23 | 2011-02-24 | 2011-03-02 | 2011-03-01 | 2011-03-23 | 2011-03-29 | 1 | 2011-03-23 | 2011-03-29 | 2011-05-06 | 2011-05-06 | 2011-06-30 | 2011-07-01 | 1 | 2011-06-30 | 2011-07-01 | PERMITTED | 2011-05-09 | 2011-05-09 | 2011-06-06 | 2011-05-25 | 1 | 2011-06-13 | 2011-06-02 |  |  | 2011-08-29 | 2011-09-08 | 1 |  | 2011-08-29 | 2011-09-08 | 2011-11-15 |  |  |  |  | 2011-09-05 | 2011-09-05 | 2011-09-21 | 2011-09-21 | 2011-09-23 | 2011-10-13 | 2011-10-13 | [8 empty] | 2011-10-27 | 2011-11-14 | 2011-11-08 | 2011-11-21 | 2011-11-15 | 2012-02-13 | 2012-07-31 |  |  | 2011-10-19 | 2011-08-29 | 2011-08-29 | 2011-10-03 | 2011-11-15 | 2011-08-29 | 2011-11-15 | 2011-10-06 | 2011-10-06 |  | 2011-10-27 | [6 empty] | 2011-09-27 | FALSE |  | 2838550 | 6167822 | Corner Maraekakaho Rd & Southampton Rd |  | RMA20110129 - 02/06/2011 | CELLSITE |  |  | 2015-04-22 | [12 empty] | 2011-11-07 | 2011-11-07
0 | HKB | 934 | HKB-030-003 |  |  |  | Hastings |  | TIER_9
0 | HKB | 935 | HKB-030-004 | Parkvale | HKB-030-004-D | LPR - Collinge Rd | Hastings | 1 | TIER_2 | ACTIVE | RSR | DU | P4F | green | INLINE | STANDALONE | 15 | 15.5 | 2 | -39.6378 | 176.8657 |  | 2010-09-02 |  | 2010-02-12 | Microwave | HKB-030-006-E | FALSE | TRUE |  |  | FALSE |  | 2011-05-25 | 2011-04-20 | 2011-05-02 | 2011-05-02 | 2011-05-25 | 2011-05-31 | 3 | 2011-05-25 | 2014-11-26 | 2011-08-08 | 2011-08-10 | 2011-08-29 | 2011-08-22 |  | 2011-09-05 | 2011-09-02 | CONTROLLED | 2011-08-19 | 2011-08-25 | 2011-09-19 | 2011-09-16 | 2 | 2011-09-23 | 2011-09-16 |  |  | 2011-11-30 | 2011-12-22 | 1 |  | 2011-11-30 | 2011-12-22 | 2011-12-15 |  |  |  |  | 2011-12-12 | 2011-12-12 | 2011-12-20 | 2011-12-20 | 2012-01-13 | 2012-01-26 | 2012-01-25 | [8 empty] | 2012-01-26 | 2012-02-10 | 2012-02-15 | 2012-02-17 | 2012-02-27 | 2012-05-28 | 2012-08-23 |  |  | 2012-01-26 | 2011-12-15 | 2011-12-15 | 2011-12-15 | 2011-12-15 | 2011-12-15 | 2011-12-15 | 2012-01-23 | 2012-01-23 |  | 2012-02-13 | [6 empty] | 2012-01-14 | FALSE |  | 2841718 | 6166934 | 602 Collinge Rd, opposite Collinge Place, Hastings |  |  | CELLSITE |  |  | 2015-04-22 | [12 empty] | 2012-02-13 | 2012-02-13
0 | HKB | 936 | HKB-030-005 |  |  |  | Hastings |  | TIER_9
0 | HKB | 937 | HKB-030-006 | Mahora | HKB-030-006-E | Williams Street Industrial | Hastings | 1 | TIER_2 | ACTIVE | GF | DU | T2 25 UF | grey | STACK_A | STANDALONE | 24.5 | 25 | 1 | -39.6279 | 176.8538 |  | 2010-09-02 |  |  | Microwave | HKB-030-002-E | FALSE | TRUE |  |  | FALSE | 2011-04-07 | 2011-04-21 | 2011-04-20 | 2011-05-02 | 2011-05-02 | 2011-05-26 | 2011-05-31 | 1 | 2011-05-26 | 2011-05-31 | 2011-07-01 | 2011-06-29 | 2011-07-15 | 2011-07-06 | 1 | 2011-07-22 | 2011-07-06 | PERMITTED | 2011-06-10 | 2011-06-13 | 2011-07-11 | 2011-07-12 | 1 | 2011-07-14 | 2011-07-12 |  |  | 2011-08-26 | 2011-12-22 | 1 |  | 2011-09-16 | 2011-12-22 | 2011-11-15 |  |  |  |  | 2011-10-13 | 2011-10-13 | 2011-11-25 | 2011-11-28 | 2011-11-16 | 2011-11-25 | 2011-11-28 | [8 empty] | 2011-11-29 | 2011-12-14 | 2011-12-07 | 2011-12-05 | 2011-12-16 | 2012-03-15 | 2012-07-31 |  |  | 2011-11-29 | 2011-11-15 | 2011-11-15 | 2011-10-04 | 2011-11-15 | 2011-11-10 | 2011-11-15 | 2011-11-28 | 2011-11-28 |  | 2011-11-30 | [6 empty] | 2011-11-16 | FALSE |  | 2840750 | 6168075 | 500 Williams Street Mahora, Hastings |  |  | CELLSITE |  |  | 2015-04-22 | [12 empty] | 2011-12-06 | 2011-12-06
0 | HKB | 938 | HKB-030-007 |  |  |  | Hastings |  | TIER_9
0 | HKB | 939 | HKB-030-008 |  |  |  | Hastings |  | TIER_9
0 | HKB | 940 | HKB-030-009 | Havelock North | HKB-030-009-D | Cooper Street | Hastings | 1 | TIER_2 | ACTIVE | GF | DU | T2 25 UF | grey | STACK_A | STANDALONE | 24.5 | 25 | 1 | -39.6672 | 176.8772 |  | 2010-09-02 |  | 2010-02-12 | Fibre Optic | HKB-030-001-A | FALSE | TRUE |  |  | FALSE |  | 2011-02-23 | 2011-02-24 | 2011-03-02 | 2011-03-01 | 2011-03-31 | 2011-03-31 | 1 | 2011-03-31 | 2011-03-31 | 2011-05-06 | 2011-05-06 | 2011-07-15 | 2011-07-14 | 1 | 2011-07-15 | 2011-07-14 | PERMITTED | 2011-05-09 | 2011-05-09 | 2011-06-06 | 2011-05-25 | 1 | 2011-06-13 | 2011-06-02 |  |  | 2011-08-26 | 2011-08-15 | 1 |  | 2011-08-15 | 2011-08-15 | 2011-11-14 |  |  |  |  | 2011-08-16 | 2011-08-17 | 2011-09-21 | 2011-09-21 | 2011-09-23 | 2011-10-03 | 2011-10-03 | [8 empty] | 2011-10-27 | 2011-11-14 | 2011-11-08 | 2011-11-21 | 2011-11-15 | 2012-02-13 | 2012-07-31 | HARD MATCHED Equipment delivery date TBC Confirm fibre delivery once we know cbinet delivery date. |  | 2011-10-19 | 2011-08-29 | 2011-08-29 | 2011-10-04 | 2011-11-14 | 2011-08-29 | 2011-11-14 | 2011-09-30 | 2011-09-30 |  | 2011-10-27 | [6 empty] | 2011-09-26 | FALSE |  | 2842562 | 6163635 | 9 Cooper Street Havelock North Hastings |  | 25m mono is permitted - 24/03/2011 RMA20110128 - 02/06/2011 | CELLSITE |  |  | 2015-04-22 | [12 empty] | 2011-11-11 | 2011-11-14
0 | HKB | 941 | HKB-030-010 |  |  |  | Hastings |  | TIER_9
0 | HKB | 942 | HKB-030-011 |  |  |  | Hastings |  | TIER_9
0 | HKB | 943 | HKB-030-012 |  |  |  | Hastings |  | TIER_9
0 | HKB | 944 | HKB-030-013 |  |  |  | Hastings |  | TIER_9
0 | HKB | 945 | HKB-030-014 |  |  |  | Hastings |  | TIER_9
0 | HKB | 946 | HKB-030-015 | Mt Threave | HKB-030-015-A | Mt Threave - Shureview | Hastings | 24 | TIER_5 | ACTIVE | COLO | DF | LATTICE |  | STACK_A | COLO |  |  | 1 | -39.7515 | 176.7834 |  |  |  |  | Microwave | HKB-030-022-B | FALSE | FALSE |  |  | FALSE |  | 2015-12-04 | 2015-12-07 | 2015-12-21 | 2015-12-21 | 2016-02-12 | 2016-01-22 | 1 |  | 2016-01-22 | 2016-02-05 | 2016-01-26 | 2016-03-18 |  |  |  |  | PERMITTED | 2016-03-01 |  | 2016-03-30 |  |  |  |  | 2016-03-04 |  | 2016-03-30 | [10 empty] | 2016-05-20 |  | 2016-06-10 |  |  | 2016-06-24 | [10 empty] | 2016-07-15 |  | 2012-12-06 |  |  |  |  | VNZ | [9 empty] | 2016-07-01 |  |  |  | NAPIER_DANNEVIRKE |  |  | BUILD |  | FALSE |  | 2834128 | 6154628 |  |  |  | CELLSITE | WIPACTIVE |  |  | ROAMING |  |  |  | 2016-04-08 | [5 empty] | 2016-05-13 |  |  |  | 2015-12-21
0 | HKB | 947 | HKB-030-016 |  |  |  | Hastings |  | TIER_9
0 | HKB | 948 | HKB-030-017 |  |  |  | Hastings |  | TIER_9
0 | HKB | 949 | HKB-030-018 | Hastings South | HKB-030-018-A | Hastings South, VF Colo (Hastings South) | Hastings | 1 | TIER_2 | ACTIVE | COLO | DU | COLO | grey | STACK_A | COLO | 25 | 25.75 | 1 | -39.6562 | 176.8532 |  | 2010-09-02 |  |  | Microwave | HKB-030-001-A | FALSE | TRUE |  |  | FALSE | 2011-03-08 | 2011-02-25 | 2011-02-25 | 2011-03-04 | 2011-03-01 | 2011-03-18 | 2011-03-16 | 3 | 2011-05-23 | 2011-05-23 | 2011-06-17 | 2011-06-10 | 2011-07-29 | 2011-07-27 | 1 | 2011-09-01 | 2011-08-04 | DISCRETIONARY_RESTRICT | 2011-06-03 | 2011-06-08 | 2011-07-08 | 2011-06-29 | 3 | 2011-08-15 | 2011-07-06 |  |  | 2011-08-26 | 2011-09-07 | 2 |  | 2011-08-30 | 2011-09-15 | 2011-11-14 |  |  |  |  | 2011-09-21 | 2011-09-21 | 2011-09-29 | 2011-09-29 | 2011-10-05 | 2011-10-20 | 2011-10-27 | [8 empty] | 2011-10-27 | 2011-11-14 | 2011-11-08 | 2011-11-21 | 2011-11-15 | 2012-02-13 | 2012-08-31 | VF Prelim approval received VF DOV & sublease signed by LO Note: Dish location on CD's and lighting spike Waiting on VF docs and power share Huawei to do VF power capacity check & project plan | VNZ | 2011-10-27 | 2011-08-29 | 2011-08-29 | 2011-09-29 | 2011-11-14 | 2011-11-14 | 2011-11-14 | 2011-10-14 | 2011-10-14 |  | 2011-10-31 | [6 empty] | 2011-10-05 | FALSE |  | 2840557 | 6164946 | 314 Norton Rd, Carnavan, Hastings |  | Pre-Lodgement meeting held on 16/3/11. Positive initial feedback. - 24/03/2011 Granted 29.6.11 by Planner Sean Crocker - 1.7.11 - 01/07/2011 RC Approved - 29/06/2011 - 04/07/2011 | CELLSITE |  |  | 2015-04-22 | [12 empty] | 2011-11-14 | 2011-11-14
0 | HKB | 950 | HKB-030-019 | Bridge Pa | HKB-030-019-A | Hastings Aerodrome | Hastings | 1 | TIER_2 | ACTIVE | GF | DU | T2 25 UF | grey | STACK_A | STANDALONE | 24.5 | 25 | 1 | -39.6516 | 176.7659 |  | 2010-09-02 |  | 2010-02-12 | Fibre Optic | HKB-030-001-A | FALSE | TRUE |  |  | FALSE |  | 2011-03-25 | 2011-03-17 | 2011-04-01 | 2011-03-22 | 2011-04-04 | 2011-04-07 | 1 | 2011-04-04 | 2011-04-07 | 2011-05-20 | 2011-05-11 | 2011-06-24 | 2011-06-23 | 1 | 2011-06-30 | 2011-07-06 | PERMITTED | 2011-05-23 | 2011-05-19 | 2011-06-23 | 2011-06-01 | 1 | 2011-06-30 | 2011-06-15 |  |  | 2011-09-01 | 2011-09-22 | 1 |  | 2011-09-08 | 2011-09-22 | 2011-11-15 |  |  |  |  | 2011-09-22 | 2011-09-22 | 2011-10-07 | 2011-10-07 | 2011-10-09 | 2011-10-12 | 2011-10-12 | [8 empty] | 2011-10-27 | 2011-11-14 | 2011-11-08 | 2011-11-21 | 2011-11-15 | 2012-02-13 | 2012-08-31 |  |  | 2011-10-27 | 2011-08-29 | 2011-08-29 | 2011-09-30 | 2011-11-15 | 2011-09-19 | 2011-11-15 | 2011-10-10 | 2011-10-10 |  | 2011-10-31 | [6 empty] | 2011-10-09 | FALSE |  | 2833092 | 6165766 | 1591 Marakakaho Rd, Napier |  | 25m mono permitted. Possible issues w/ wastewater disposal field - site aq currently confirming w LO. Height restrictions for aerodrome apply, however proposed location is ok. - 24/03/2011 | CELLSITE | [15 empty] | 2011-11-09 | 2011-11-09
0 | HKB | 951 | HKB-030-020 | Omahu | HKB-030-020-B | Omahu, GF on Korokipo Road | Hastings | 1 | TIER_2 | ACTIVE | GF | DU | T2 25 UF | grey | STACK_A | STANDALONE | 23.5 | 25 | 1 | -39.5812 | 176.7639 |  | 2010-09-02 |  | 2010-02-12 | Microwave | HKB-030-022-B | FALSE | TRUE |  |  | FALSE | 2011-06-28 | 2011-04-21 | 2011-04-20 | 2011-05-02 | 2011-05-02 | 2011-05-26 | 2011-05-31 | 1 | 2011-05-26 | 2011-05-31 | 2011-06-10 | 2011-06-13 | 2011-06-24 | 2011-06-23 | 1 | 2011-06-30 | 2011-07-06 | PERMITTED | 2011-06-10 | 2011-06-13 | 2011-07-11 | 2011-06-28 | 1 | 2011-07-14 | 2011-07-12 |  |  | 2011-09-05 | 2011-09-22 | 1 |  | 2011-09-05 | 2011-09-22 | 2011-09-30 |  |  |  |  | 2011-09-21 | 2011-09-21 | 2011-10-12 | 2011-10-12 | 2011-10-13 | 2011-10-18 | 2011-10-18 | [8 empty] | 2011-10-19 | 2011-11-14 | 2011-11-08 | 2011-11-21 | 2011-11-15 | 2013-04-05 | 2013-04-09 | Site snag free, FAN in signoff process 2/04/2013 - FAC ready but missing folder 9/4/13 - FACed |  | 2011-10-19 | 2011-08-29 | 2011-08-29 | 2011-09-30 | 2011-11-14 | 2011-09-19 | 2011-09-30 | 2011-10-18 | 2011-10-18 |  | 2011-10-27 | [6 empty] | 2011-10-13 | FALSE |  | 2833254 | 6173592 | Korokipo Rd |  | 25m mono is permitted - 24/03/2011 Granted on 28th June by Roger Widdin - 12/07/2011 | CELLSITE |  |  | 2015-04-22 | [12 empty] | 2011-11-14 | 2011-11-14
0 | HKB | 952 | HKB-030-021 | Flaxmere East | HKB-030-021-B | Flaxmere Village Shopping Centre - GF | Hastings | 1 | TIER_2 | ACTIVE | GF | DU | P3 | grey | STACK_A | STANDALONE | 24.5 | 25 | 1 | -39.6251 | 176.7868 |  | 2010-09-02 |  | 2010-02-12 | Microwave | HKB-030-022-B | FALSE | TRUE |  |  | FALSE | 2011-06-28 | 2011-04-21 | 2011-04-20 | 2011-05-02 | 2011-05-02 | 2011-05-25 | 2011-05-27 | 1 | 2011-05-25 | 2011-05-27 | 2011-06-24 | 2011-06-17 | 2011-07-15 | 2011-07-06 | 1 | 2011-07-15 | 2011-07-06 | PERMITTED | 2011-06-24 | 2011-06-24 | 2011-07-25 | 2011-07-11 | 1 | 2011-08-01 | 2011-07-11 |  |  | 2011-09-16 | 2011-12-22 | 1 |  | 2011-11-21 | 2011-12-22 | 2011-11-29 |  |  |  |  | 2011-11-11 | 2011-11-11 | 2011-11-29 | 2011-11-29 | 2011-11-29 | 2011-12-02 | 2011-12-01 | [8 empty] | 2011-12-07 | 2011-12-22 | 2011-12-07 | 2011-12-22 | 2011-12-16 | 2013-05-16 | 2013-05-17 | 5 snags remaining, 4 actioned with Huawei technical team for resolution. Othr snag is for compound fill, they have left it as-is with no weed mat or stone. As the area is generally stony they've tried to leave it as such which is not acceptable. Happy to agree to a small VO for concrete fill to compound as good way to settle this snag? 09/04/13 - No FAN yest. FAC reforecasted 01/05/13 - No FAN yet. FAC reforecasted 26/04/13 - FAN in sign off 17/05/13 - FAC signed |  | 2011-12-03 | 2011-11-15 | 2011-11-15 | 2011-10-07 | 2011-11-29 | 2011-11-18 | 2011-11-29 | 2011-12-01 | 2011-12-01 |  | 2011-12-07 | [5 empty] | BUILD | 2011-11-28 | FALSE |  | 2835015 | 6168635 | 12 Swansea Rd, Flaxmere |  | Permitted 25m mono - but semi-sensitive area next to council park / skate park. - 24/03/2011 | CELLSITE |  |  | 2015-04-22 | [12 empty] | 2011-12-09 | 2011-12-09
0 | HKB | 953 | HKB-030-022 | Woolwich (TX HUB) | HKB-030-022-B | Woolwich - TX HUB | Hastings | 1 | TIER_2 | ACTIVE | GF | DU | T2 25 RF | grey | STACK_A | STANDALONE | 24 | 26.1 | 1 | -39.6146 | 176.797 |  | 2010-09-02 |  | 2010-02-12 | Fibre Optic | HKB-030-001-A | FALSE | TRUE |  |  | FALSE |  | 2011-06-01 | 2011-06-01 | 2011-06-08 | 2011-06-02 | 2011-06-20 | 2011-06-16 | 2 | 2011-06-20 | 2011-08-10 | 2011-06-24 | 2011-06-27 | 2011-07-08 | 2011-07-06 | 1 | 2011-07-08 | 2011-07-06 | DISCRETIONARY_RESTRICT | 2011-06-27 | 2011-09-13 | 2011-08-05 | 2011-10-05 | 2 | 2011-08-05 | 2011-08-05 |  |  | 2011-09-01 | 2011-09-08 | 2 |  | 2011-09-02 | 2011-09-23 | 2011-10-10 |  |  |  |  | 2011-09-05 | 2011-09-05 | 2011-10-10 | 2011-10-10 | 2011-10-07 | 2011-10-17 | 2011-10-17 | [8 empty] | 2011-10-19 | 2011-11-14 | 2011-11-08 | 2011-11-21 | 2011-11-15 | 2013-05-17 | 2013-05-02 | 12 snags outstanding, 11 been addressed and with Nester, Ryan and Peter to close. Alarms have been addressed and with Huawei/2degrees to close. 09/04/13 - FAC reforecasted - No FAN as snags still to clear 23/04/13 - FAN in sign off 02/05/13 - FAC signed |  | 2011-10-19 | 2011-08-29 | 2011-08-29 | 2011-09-30 | 2011-10-10 | 2011-09-12 | 2011-10-10 | 2011-10-18 | 2011-10-19 |  | 2011-10-27 | [6 empty] | 2011-10-07 | FALSE |  | 2835934 | 6169764 | 5 Hazelwood Street Hastings |  | Approved on the 4 August 2011, Council reference: RMA20110199 Section 127: Approved on 5 October 2011, Council Reference RMA20110302 - 06/10/2011 | CELLSITE |  |  | 2015-04-22 | [12 empty] | 2011-11-10 | 2011-11-10 | 2011-06-02
0 | HKB | 954 | HKB-030-023 | Pakipaki | HKB-030-023-C | 91 Longlands Rd East | Hastings | 1 | TIER_2 | ACTIVE | GF | DU | P3 | grey | STACK_A | STANDALONE | 24.5 | 25 | 1 | -39.6745 | 176.8252 |  | 2010-09-02 |  | 2010-02-12 | Microwave | HKB-030-018-A | FALSE | TRUE |  |  | FALSE | 2011-03-08 | 2011-02-23 | 2011-02-24 | 2011-03-02 | 2011-03-01 | 2011-03-16 | 2011-03-16 | 2 | 2011-04-01 | 2011-04-11 | 2011-04-21 | 2011-04-21 | 2011-06-24 | 2011-06-23 | 2 | 2011-06-30 | 2011-07-06 | PERMITTED | 2011-04-26 | 2011-04-26 | 2011-05-26 | 2011-05-06 | 2 | 2011-06-08 | 2011-06-15 |  |  | 2011-08-10 | 2011-09-08 | 1 |  | 2011-08-10 | 2011-09-08 | 2011-11-15 |  |  |  |  | 2011-08-15 | 2011-08-17 | 2011-09-21 | 2011-09-21 | 2011-10-03 | 2011-10-07 | 2011-10-07 | [8 empty] | 2011-10-27 | 2011-11-14 | 2011-11-08 | 2011-11-21 | 2011-11-15 | 2012-02-13 | 2012-08-31 | HARD MATCHED Power quote received (Dylan) Cabinet delivery date TBC |  | 2011-10-20 | 2011-08-29 | 2011-08-29 | 2011-09-30 | 2011-11-15 | 2011-09-15 | 2011-11-15 | 2011-09-30 | 2011-09-30 |  | 2011-10-27 | [6 empty] | 2011-10-03 | FALSE |  | 2838074 | 6163011 | 91 Longlands Rd East, Hastings |  | Permitted 25m mono. Need to know earthworks details for power. - 24/03/2011 | CELLSITE | [15 empty] | 2011-10-07 | 2011-11-07
0 | HKB | 955 | HKB-030-024 | Akina | HKB-030-024-A | Tollemache GF | Hastings | 1 | TIER_2 | ACTIVE | GF | DU | T2 25 RF | grey | STACK_A | STANDALONE | 24 | 25 | 1 | -39.6533 | 176.8241 |  | 2010-09-02 |  | 2010-02-12 | Microwave | HKB-030-001-A | FALSE | TRUE |  |  | FALSE | 2011-07-15 | 2011-06-30 | 2011-06-30 | 2011-07-08 | 2011-07-06 | 2011-07-29 | 2011-07-29 | 1 | 2011-07-29 | 2011-07-29 | 2011-08-15 | 2011-08-03 | 2011-09-05 | 2011-08-25 | 1 | 2011-09-12 | 2011-10-05 | PERMITTED | 2011-08-05 | 2011-08-09 | 2011-09-09 | 2011-08-30 | 1 | 2011-09-12 | 2011-08-30 |  |  | 2011-11-30 | 2012-08-29 | 1 |  | 2011-11-30 | 2012-08-29 | 2011-12-15 |  |  |  |  | 2011-12-08 | 2011-12-10 | 2012-01-17 | 2012-01-20 | 2012-01-19 | 2012-01-27 | 2012-01-31 | [8 empty] | 2012-02-03 | 2012-02-10 | 2012-02-15 | 2012-02-20 | 2012-02-28 | 2012-05-28 | 2012-08-31 |  |  | 2012-02-01 | 2011-12-15 | 2011-12-15 | 2011-12-15 | 2011-12-15 | 2011-12-21 | 2011-12-15 | 2012-01-24 | 2012-01-24 |  | 2012-02-28 | [6 empty] | 2012-01-20 | FALSE |  | 2838075 | 6165371 | Akina - Springwood Orchard 67 Tollemache Rd Akina, Hastings |  | 25m mono should be permitted - provided not in flood plain / next to res. - 24/03/2011 | CELLSITE |  |  | 2015-04-22 | [12 empty] | 2012-02-14 | 2012-02-14
0 | HKB | 956 | HKB-030-025 | Craggy Range | HKB-030-025-A | Craggy Range GF | Hastings | 1 | TIER_2 | ACTIVE | GF | DU | SP | green | INLINE | COSITE | 7.5 | 8 | 1 | -39.6804 | 176.9398 |  | 2010-09-02 |  | 2010-02-12 | Microwave | HKB-030-001-A | FALSE | TRUE |  |  | FALSE | 2011-03-17 | 2011-03-17 | 2011-03-17 | 2011-03-24 | 2011-03-22 | 2011-04-15 | 2011-04-15 | 1 | 2011-04-15 | 2011-04-15 | 2011-05-13 | 2011-05-10 | 2011-06-20 | 2011-06-17 | 1 | 2011-06-30 | 2011-07-06 | PERMITTED | 2011-05-16 | 2011-05-19 | 2011-06-16 | 2011-06-14 | 1 | 2011-07-08 | 2011-07-12 |  |  | 2011-08-31 | 2011-09-23 | 1 |  | 2011-09-08 | 2011-09-23 | 2011-11-14 |  |  |  |  | 2011-09-21 | 2011-09-21 | 2011-10-28 | 2011-10-28 | 2011-10-25 | 2011-10-29 | 2011-10-29 | [8 empty] | 2011-10-31 | 2011-11-14 | 2011-11-08 | 2011-11-21 | 2011-11-15 | 2012-02-13 | 2012-11-02 | HARD MATCHED Huawei advised to work closely with LO for access arrangements during build. VF used helicopter for concrete and pole lift. Power quote received but working with VF to swap them to 3-phase and share existing 4 core cable. Waiting power quote from Infratel/Huawei, then TBC if use VF or LPA connection. Hand auger geotech TBC Monday 22nd |  | 2011-10-29 | 2011-08-29 | 2011-08-29 | 2011-10-07 | 2011-11-14 | 2011-10-26 | 2011-11-14 | 2011-10-27 | 2011-10-27 |  | 2011-11-01 | [6 empty] | 2011-10-27 | FALSE |  | 2847866 | 6161933 | 877 Tuki Tuki Rd |  | Significant Landscape Character Area. Sensitive design required - due to view corridor from Te Mata Peak. VF used 6m wooden pole with painted antennas. 2degrees to use metal pole, but paint forest green to blend in with adjacent trees. - 24/03/2011 | CELLSITE | [15 empty] | 2011-11-14 | 2011-11-14
0 | HKB | 957 | HKB-030-026 | Clive | HKB-030-026-A | Whakatu, VF Colo (Clive) | Hastings | 1 | TIER_2 | ACTIVE | COLO | DU | COLO | grey | STACK_A | COLO | 25 | 26 |  | -39.6006 | 176.9127 |  | 2010-09-02 |  | 2010-02-12 | Microwave | HKB-030-025-A | FALSE | TRUE |  |  | FALSE | 2011-03-07 | 2011-03-16 | 2011-03-16 | 2011-03-23 | 2011-03-25 | 2011-04-18 | 2011-04-18 | 1 | 2011-04-18 | 2011-04-18 | 2011-08-26 | 2011-08-30 | 2011-09-26 | 2011-08-31 |  | 2011-09-30 | 2011-09-26 | PERMITTED | 2011-04-26 | 2011-04-26 | 2011-05-27 | 2011-05-06 | 1 | 2011-06-09 | 2011-06-15 |  |  | 2011-11-30 | 2011-11-30 | 1 |  | 2011-11-30 | 2011-11-30 | 2012-03-02 |  |  |  |  | 2012-02-21 | 2012-02-16 | 2012-02-29 | 2012-02-17 | 2012-02-22 | 2012-03-06 | 2012-03-09 | [8 empty] | 2012-03-09 | 2012-03-15 | 2012-03-15 | 2012-03-09 | 2012-03-23 | 2012-06-21 | 2012-07-31 |  | VNZ | 2012-03-06 | 2012-01-13 | 2012-01-13 | 2012-01-13 | 2012-03-02 | 2012-01-13 | 2012-03-02 | 2012-03-05 | 2012-03-06 |  | 2012-03-15 | [6 empty] | 2012-02-29 | FALSE |  | 2845934 | 6170883 | 30 Richmond Rd Clive, Hastings |  | Ringframe co-lo at same height as VF (25m) will be permitted - 24/03/2011 | CELLSITE | [15 empty] | 2012-03-15 | 2012-03-15
0 | HKB | 958 | HKB-030-027 | Flaxmere West | HKB-030-027-A | Bacchus Ventures | Hastings | 24 | 2015P | ACTIVE | GF | DF5 | T2 25 UF |  | STACK_A | STANDALONE |  |  |  | -39.6075 | 176.7752 |  | 2015-02-23 |  | 2015-06-11 | Fibre Optic | HKB-030-022-B | FALSE | FALSE |  |  | FALSE |  | 2015-05-27 | 2015-05-21 | 2015-06-12 | 2015-06-12 | 2015-07-17 | 2015-06-17 | 1 |  | 2015-06-17 | 2015-07-28 | 2015-07-23 | 2015-08-14 | 2015-07-23 |  | 2015-07-28 | 2015-08-04 | PERMITTED | 2015-07-24 | 2015-06-29 | 2015-08-31 | 2015-07-23 | 1 |  | 2015-08-06 | 2015-10-23 |  | 2015-11-27 | [10 empty] | 2016-01-18 |  | 2016-02-29 |  |  | 2016-03-11 | [10 empty] | 2016-04-29 | [5 empty] | 09/7 AS- moved to next year build | [10 empty] | 2016-03-31 | [6 empty] | ONHOLD |  | FALSE |  | 2834101 | 6170625 | 1500 Omahu Road, Hastings |  |  | CELLSITE | WIPACTIVE |  |  | CAPACITY |  |  |  | 2015-11-02 | [5 empty] | 2015-12-04 |  |  |  | 2015-06-12
0 | HKB | 959 | HKB-030-028 | Eskdale | HKB-030-028-A | VF colo | Hastings | 24 | TIER_5 | ACTIVE | COLO | DF | COLO |  | STACK_A | COLO |  |  |  | -39.3901 | 176.8093 | [6 empty] | FALSE | FALSE |  |  | FALSE |  | 2015-09-11 | 2015-09-10 | 2015-10-01 | 2015-10-01 | 2015-10-23 | 2015-12-11 | 1 |  | 2015-12-11 | 2015-12-18 |  | 2016-03-15 | [5 empty] | 2016-03-11 |  | 2016-04-08 |  |  |  |  | 2016-03-04 |  | 2016-04-08 | [10 empty] | 2016-05-20 |  | 2016-06-10 |  |  | 2016-06-24 | [10 empty] | 2016-07-22 | [6 empty] | VNZ | [9 empty] | 2016-07-08 | [6 empty] | BUILD |  | FALSE |  | 2838056 | 6194624 | Off SH5 Eskdale |  |  | CELLSITE |  |  |  | ROAMING |  |  |  | 2016-04-15 | [5 empty] | 2016-05-13 |  |  |  | 2015-10-01
0 | HKB | 960 | HKB-031-001 | Napier Hub (Main HUB) | HKB-031-001-A | Dunvegan House - MAIN HUB | Napier | 1 | TIER_2 | ACTIVE | RT | DU | RT | grey | STACK_A | COSITE | 24 | 24.5 | 1 | -39.4922 | 176.9179 |  | 2010-09-02 |  | 2010-02-12 | Fibre Optic | WLG-047-071-A | FALSE | TRUE |  |  | FALSE |  | 2011-02-24 | 2011-02-24 | 2011-03-03 | 2011-03-01 | 2011-05-02 | 2011-05-04 | 1 | 2011-05-02 | 2011-05-04 | 2011-05-13 | 2011-05-11 | 2011-06-09 | 2011-06-09 | 1 | 2011-06-30 | 2011-07-06 | DISCRETIONARY_RESTRICT | 2011-05-13 | 2011-05-19 | 2011-06-24 | 2011-06-09 | 1 | 2011-07-01 | 2011-06-15 |  |  | 2011-08-24 | 2012-01-04 | 1 |  | 2011-08-24 | 2012-01-04 | 2011-11-14 |  |  |  |  | 2011-09-18 | 2011-09-18 | 2011-10-21 | 2011-11-14 | 2011-10-03 | 2011-10-21 | 2011-11-14 | [8 empty] | 2011-10-29 | 2011-11-14 | 2011-11-14 | 2011-11-21 | 2011-11-25 | 2013-05-17 | 2013-05-13 | 8 snags remaining, alarm has been addressed, design and some Tx test cases outstanding 09/04/13 - FAC reforecasted - No FAN received 01/05/13 - No FAN yet. FAC reforecasted 13/05/13 - FAC signed |  | 2011-10-28 | 2011-08-29 | 2011-08-29 | 2011-09-30 | 2011-11-14 | 2011-09-09 | 2011-11-14 | 2011-10-18 | 2011-10-19 |  | 2011-11-01 | [5 empty] | BUILD | 2011-10-03 | FALSE |  | 2846910 | 6182895 | Dunvegan House, 215 Hastings Street, Napier |  |  | CELLSITE |  |  | 2015-05-26 | [12 empty] | 2011-11-15 | 2011-11-15
0 | HKB | 961 | HKB-031-002 | Hospital Hill |  |  | Napier |  | TIER_9 | [22 empty] | FALSE | [60 empty] | Height dependant on TP input. Preferred option is Hospital rooftop. Recommend G1800 only due to the ground height of the site and to avoid pollution of network. Backup Hinepare Accommodation or GF to rear of hospital building.
0 | HKB | 962 | HKB-031-003 | Mclean Park | HKB-031-003-B | KiwiRail Land | Napier | 1 | TIER_2 | ACTIVE | GF | DU | P2 | grey | STACK_A | STANDALONE | 23 | 24 | 1 | -39.4979 | 176.9159 |  | 2010-09-02 |  | 2010-02-12 | Microwave | HKB-031-001-A | FALSE | TRUE |  |  | FALSE | 2011-07-15 | 2011-07-14 | 2011-07-14 | 2011-07-18 | 2011-07-20 | 2011-08-05 | 2011-08-08 | 2 | 2011-08-05 | 2014-12-04 | 2011-09-15 | 2011-10-06 | 2011-11-21 | 2011-10-21 |  | 2011-11-30 | 2011-10-21 | DISCRETIONARY_RESTRICT | 2011-08-31 | 2011-09-16 | 2011-09-30 | 2011-09-29 | 1 | 2011-10-07 | 2011-10-06 |  |  |  | 2012-02-14 | 1 |  |  | 2012-02-14 | 2012-02-28 |  |  |  |  | 2012-01-31 | 2012-01-31 | 2012-02-17 | 2012-02-24 | 2012-02-18 | 2012-02-27 | 2012-02-28 | [8 empty] | 2012-02-28 | 2012-03-15 | 2012-03-15 | 2012-03-09 | 2012-03-14 | 2012-06-07 | 2012-10-18 |  |  | 2012-02-27 | 2012-02-28 | 2012-02-28 | 2012-02-28 | 2012-02-28 | 2012-02-28 | 2012-02-28 | 2012-02-20 | 2012-02-27 |  | 2012-03-06 | [6 empty] | 2012-02-18 | FALSE |  | 2846709 | 6182265 | 11 Sale Street Napier |  | Approved by council on the 29.9.11, council reference number RM110136 - 04/10/2011 | CELLSITE |  |  | 2015-05-26 | [12 empty] | 2012-03-02 | 2012-03-02
0 | HKB | 963 | HKB-031-004 | Onekawa | HKB-031-004-A | Onekawa West, VF Colo (Expressway) | Napier | 1 | TIER_2 | ACTIVE | COLO | DU | COLO | grey | STACK_A | COLO | 22 | 25 | 1 | -39.5079 | 176.877 |  | 2010-09-02 |  | 2010-02-12 | Microwave | HKB-031-015-B | FALSE | TRUE |  |  | FALSE | 2011-07-15 | 2011-02-24 | 2011-02-25 | 2011-03-10 | 2011-03-07 | 2011-04-01 | 2011-04-04 | 2 | 2011-05-30 | 2011-05-27 | 2011-07-20 | 2011-06-27 | 2011-08-11 | 2011-08-08 |  | 2011-09-01 | 2011-09-01 | PERMITTED | 2011-05-31 | 2011-04-08 | 2011-06-30 | 2011-06-21 | 2 | 2011-07-07 | 2011-07-12 |  |  |  | 2012-02-24 | 1 |  |  | 2012-02-24 | 2012-03-02 |  |  |  |  | 2012-02-15 | 2012-02-19 | 2012-02-24 | 2012-03-02 | 2012-02-24 | 2012-03-02 | 2012-03-09 | [8 empty] | 2012-03-09 | 2012-03-15 | 2012-03-15 | 2012-03-09 | 2012-03-23 | 2012-06-21 | 2012-08-31 | Prelim approval received and LO consent received. 2nd Trustee signed DOV and sublease, ready for posting/collection. Will get own power supply. | VNZ | 2012-03-02 | 2012-01-24 | 2012-03-02 | 2012-01-31 | 2012-03-02 | 2012-02-09 | 2012-03-02 | 2012-02-27 | 2012-03-01 |  | 2012-03-15 | [6 empty] | 2012-02-24 | FALSE |  | 2843318 | 6181304 | 31 Edmundson Street, Napier |  |  | CELLSITE |  |  | 2015-05-26 | [12 empty] | 2012-03-15 | 2012-03-15
0 | HKB | 964 | HKB-031-005 | Marewa | HKB-031-005-C | Marewa LPR | Napier | 1 | TIER_2 | ACTIVE | RSR | DU | P4F | grey | INLINE | STANDALONE | 13.2 | 13.7 | 1 | -39.5037 | 176.8968 |  | 2010-09-02 |  |  |  |  | FALSE | TRUE |  |  | FALSE |  | 2011-06-01 | 2011-06-01 | 2011-06-08 | 2011-06-07 | 2011-06-20 | 2011-06-21 | 2 | 2011-06-20 | 2014-12-05 | 2011-08-31 | 2011-08-31 | 2011-09-30 | 2011-10-06 |  | 2011-09-30 | 2011-10-06 | NES | 2011-08-19 | 2011-08-25 | 2011-09-19 | 2011-09-08 | 1 | 2011-09-23 | 2011-10-10 |  |  | 2011-12-05 | 2011-12-05 | 1 |  | 2011-12-05 | 2011-12-05 | 2012-01-13 |  |  |  |  | 2011-12-12 | 2011-12-14 | 2011-12-20 | 2011-12-20 | 2012-01-12 | 2012-02-03 | 2012-02-03 | [8 empty] | 2012-02-07 | 2012-02-10 | 2012-02-15 | 2012-02-20 | 2012-02-27 | 2012-05-28 | 2012-08-31 | Signed by 2degrees, with Council. |  | 2012-02-07 | 2012-01-13 | 2012-01-13 | 2012-01-13 | 2012-01-13 | 2012-01-13 | 2012-01-13 | 2012-02-03 | 2012-02-03 |  | 2012-02-15 | [6 empty] | 2012-01-13 | FALSE |  | 2845036 | 6181699 | Corner Kennedy & Riverbend Roads Marewa Napier |  |  | CELLSITE |  |  | 2015-05-26 | [12 empty] | 2012-02-14 | 2012-02-15
0 | HKB | 965 | HKB-031-006 | Maraenui | HKB-031-006-A | Maraenui, Service Lane, 34 Bledisloe Road Shopping Centre | Napier | 1 | TIER_2 | ACTIVE | GF | DU | P2 | grey | INLINE | STANDALONE | 19 | 20 | 1 | -39.5152 | 176.905 |  | 2010-09-02 |  | 2010-02-12 | Microwave | HKB-031-012-A | FALSE | TRUE |  |  | FALSE | 2011-03-08 | 2011-04-21 | 2011-04-21 | 2011-05-02 | 2011-05-02 | 2011-05-26 | 2011-05-27 | 1 | 2011-05-26 | 2011-05-27 | 2011-06-17 | 2011-06-17 | 2011-06-24 | 2011-06-23 | 1 | 2011-06-30 | 2011-07-06 | PERMITTED | 2011-06-20 | 2011-06-20 | 2011-07-20 | 2011-07-07 | 1 | 2011-07-27 | 2011-07-12 |  |  | 2011-08-31 | 2011-12-22 | 1 |  | 2011-09-02 | 2011-12-22 | 2011-11-15 |  |  |  |  | 2011-09-28 | 2011-09-28 | 2011-10-31 | 2011-11-02 | 2011-11-02 | 2011-11-12 | 2011-11-12 | [8 empty] | 2011-11-21 | 2011-12-14 | 2011-12-08 | 2011-12-10 | 2011-12-16 | 2012-03-15 | 2012-08-31 | HARD MATCHED GPR required to locate services & strong design anti-vandol cage required. Cabinet delivery dates TBC |  | 2011-11-19 | 2011-08-29 | 2011-08-29 | 2011-08-31 | 2011-11-15 | 2011-09-12 | 2011-11-15 | 2011-11-11 | 2011-11-12 |  | 2011-11-21 | [6 empty] | 2011-11-02 | FALSE |  | 2845690 | 6180386 | 34 Service Lane, off Bledisloe Rd, Napier |  |  | CELLSITE |  |  | 2015-05-26 | [12 empty] | 2011-12-02 | 2011-12-05
0 | HKB | 966 | HKB-031-007 | Tamatea |  |  | Napier |  | TIER_9 | [22 empty] | FALSE | [60 empty] | VF Colo at Sports park is preferred with GF in same location as backup. Nominal position is actually northwest of that shown in the map at Clyde Jeffery Dr.
0 | HKB | 967 | HKB-031-008 | Pirimai |  |  | Napier |  | TIER_9 | [22 empty] | FALSE | [60 empty] | Coverage Objective: Residential areas of Pirimai and into Marewa. 12m minimum required. Concerns: Proximity to school.
0 | HKB | 968 | HKB-031-009 |  |  |  | Napier |  | TIER_9
0 | HKB | 969 | HKB-031-010 | Greenmeadows | HKB-031-010-A | Greenmeadows, VF Colo (Greenmeadows) | Napier | 1 | TIER_2 | ACTIVE | COLO | DU | COLO | grey | STACK_A | COLO | 23.7 | 24.2 | 1 | -39.5257 | 176.8635 |  | 2010-09-02 |  | 2010-02-12 | Microwave | HKB-031-014-A | FALSE | TRUE |  |  | FALSE | 2011-07-26 | 2011-02-24 | 2011-02-25 | 2011-03-03 | 2011-03-01 | 2011-03-17 | 2011-03-16 | 1 | 2011-03-17 | 2011-03-16 | 2011-06-30 | 2011-06-17 | 2011-08-15 | 2011-07-27 | 1 | 2011-09-01 | 2011-08-04 | PERMITTED | 2011-03-24 | 2011-03-16 | 2011-05-06 | 2011-03-30 | 1 |  | 2011-04-11 |  |  | 2011-08-19 | 2011-09-08 | 2 |  | 2011-08-30 | 2012-10-16 | 2011-11-15 |  |  |  |  | 2011-10-01 | 2011-10-01 | 2011-11-12 | 2011-11-14 | 2011-11-09 | 2011-11-13 | 2011-11-14 | [8 empty] | 2011-11-29 | 2011-12-14 | 2011-12-08 | 2011-12-05 | 2011-12-16 | 2012-03-15 | 2012-10-30 | VF application prelim approval received Signed DOV and sublease with 2degrees. Waiting on VF for power share. May require Fibre if Tamatea does not come through in time. Cabinet delivery date TBC | VNZ | 2011-11-29 | 2011-08-29 | 2011-08-29 | 2011-09-30 | 2011-11-15 | 2011-09-12 | 2011-11-15 | 2011-11-11 | 2011-11-14 |  | 2011-12-01 | [6 empty] | 2011-11-09 | FALSE |  | 2842066 | 6179379 | 14 Gloucester Street, Greenmeadows, Napier |  |  | CELLSITE |  |  | 2015-05-26 | [12 empty] | 2011-12-06 | 2011-12-06
0 | HKB | 970 | HKB-031-011 | Taradale | HKB-031-011-A | Taradale, GF at Service Lane at 304 Gloucester Street Shops | Napier | 1 | TIER_2 | ACTIVE | GF | DU | P2 | grey | STACK_A | STANDALONE | 19.5 | 20 | 3 | -39.5368 | 176.8485 |  | 2010-09-02 |  | 2010-02-12 | Fibre Optic | HKB-031-001-A | FALSE | TRUE |  |  | FALSE |  | 2011-04-21 | 2011-04-21 | 2011-05-02 | 2011-05-02 | 2011-05-26 | 2011-05-27 | 1 | 2011-05-26 | 2011-05-27 | 2011-06-10 | 2011-06-02 | 2011-06-30 | 2011-07-01 | 1 | 2011-07-15 | 2011-07-13 | PERMITTED | 2011-06-10 | 2011-06-13 | 2011-07-11 | 2011-06-30 | 1 | 2011-07-18 | 2011-07-06 |  |  | 2011-08-26 | 2011-08-26 | 1 |  | 2011-08-26 | 2011-08-26 | 2011-11-15 |  |  |  |  | 2011-10-18 | 2011-10-19 | 2011-11-12 | 2011-11-15 | 2011-11-11 | 2011-11-17 | 2011-11-18 | [8 empty] | 2011-12-15 | 2011-12-22 | 2011-12-16 | 2012-01-23 | 2012-01-20 | 2012-04-19 | 2012-07-05 | SOA |  | 2011-12-16 | 2011-08-29 | 2011-08-29 | 2011-08-31 | 2011-11-15 | 2011-09-14 | 2011-11-15 | 2011-11-11 | 2011-11-11 |  | 2011-12-16 | [6 empty] | 2011-11-10 | FALSE |  | 2840730 | 6178200 | 304 Gloucester Street, Taradale |  | Granted on 30.6.2011 by Tania Diack Napier City Council Resource Consents Planner - 04/07/2011 | CELLSITE |  |  | 2015-05-26 | [12 empty] | 2011-12-23 | 2011-12-23
0 | HKB | 971 | HKB-031-012 | Taradale South | HKB-031-012-A | VF Colo (Taradale) | Napier | 1 | TIER_2 | ACTIVE | COLO | DU | COLO | grey | STACK_A | COLO | 21.2 | 24 | 1 | -39.5418 | 176.8253 |  | 2010-09-02 |  | 2010-02-12 | Microwave | HKB-030-022-B | FALSE | TRUE |  |  | FALSE | 2011-07-15 | 2011-02-24 | 2011-02-25 | 2011-03-10 | 2011-03-09 | 2011-04-18 | 2011-04-16 | 2 | 2011-05-25 | 2011-05-25 | 2011-06-30 | 2011-06-20 | 2011-07-06 | 2011-07-13 |  | 2011-07-29 | 2011-07-27 | DISCRETIONARY_RESTRICT | 2011-06-03 | 2011-06-08 | 2011-07-08 | 2011-07-06 | 2 | 2011-07-15 | 2011-07-12 |  |  | 2011-09-29 | 2011-09-29 | 1 |  | 2011-09-29 | 2011-09-29 | 2011-11-15 |  |  |  |  | 2011-11-07 | 2011-11-07 | 2011-12-02 | 2011-12-02 | 2011-11-11 | 2011-12-03 | 2011-12-03 | [8 empty] | 2011-12-16 | 2011-12-14 | 2011-12-08 | 2012-01-23 | 2012-01-20 | 2013-05-17 | 2013-04-30 | Our breaker in the VF switch board to be reaplced for 6A breaker (not a snag as agreed after site installed)No snags remaining, Alan to issue FAN. 2/4/13 - FAC ready - waiting on VO for breaker swapouts 30/04/13 - FAC signed | VNZ | 2011-12-16 | 2011-11-15 | 2011-11-15 | 2011-11-15 | 2011-11-15 | 2011-11-15 | 2011-11-15 | 2011-11-11 | 2011-11-12 |  | 2012-01-09 | [6 empty] | 2011-11-11 | FALSE |  | 2838708 | 6177729 | 160 Springfield Rd Taradale |  |  | CELLSITE |  |  | 2015-05-26 | [12 empty] | 2011-12-23 | 2011-12-23
0 | HKB | 972 | HKB-031-013 | Bayview | HKB-031-013-A | Bayview VF Co-lo | Napier | 1 | TIER_2 | ACTIVE | COLO | DU | COLO | grey | STACK_A | COLO | 25 | 26 | 1 | -39.4296 | 176.869 |  |  |  |  | Microwave | HKB-031-015-B | FALSE | TRUE |  |  | FALSE | 2011-07-15 | 2011-03-16 | 2011-02-25 | 2011-03-23 | 2011-03-01 | 2011-04-06 | 2011-03-29 | 1 | 2011-04-06 | 2011-03-29 | 2011-07-29 | 2011-07-25 | 2011-08-15 | 2011-08-29 | 1 | 2011-08-31 | 2011-09-15 | DISCRETIONARY_RESTRICT | 2011-06-20 | 2011-06-21 | 2011-08-02 | 2011-07-19 | 1 | 2011-08-09 | 2011-07-19 |  |  | 2012-03-09 | 2012-03-01 | 2 |  | 2012-03-09 | 2012-03-01 | 2012-03-02 |  |  |  |  | 2012-02-27 | 2012-02-16 | 2012-03-02 | 2012-03-02 | 2012-02-20 | 2012-03-06 | 2012-03-09 | [8 empty] | 2012-03-09 | 2012-03-15 | 2012-03-15 | 2012-03-09 | 2012-03-23 | 2012-06-21 | 2012-08-31 | Prelim approval received - DOV and Sublease received from VF & in legal review, then to Clearspan. No power sharing allowed, AP to follow up. | VNZ | 2012-03-07 | 2012-02-02 | 2012-03-09 | 2012-03-02 | 2012-03-02 | 2012-03-02 | 2012-03-02 | 2012-03-05 | 2012-03-06 |  | 2012-03-15 | [6 empty] | 2012-03-05 | FALSE |  | 2843003 | 6190013 | 66 Buchanan Street, Napier |  |  | CELLSITE | [15 empty] | 2012-03-15 | 2012-03-15
0 | HKB | 973 | HKB-031-014 | Tamatea | HKB-031-014-A | Park Island Colo | Napier | 1 | TIER_2 | ACTIVE | COLO | DU | COLO | grey | STACK_A | COLO | 28.8 | 29.3 | 1 | -39.5093 | 176.855 |  | 2010-09-02 |  |  | Microwave | HKB-031-004-B | FALSE | TRUE |  |  | FALSE | 2011-03-07 | 2011-04-05 | 2011-02-25 | 2011-04-12 | 2011-03-01 | 2011-03-31 | 2011-03-31 | 2 | 2011-08-05 | 2011-08-16 | 2011-08-19 | 2011-08-19 | 2011-09-30 | 2011-09-21 |  | 2011-09-30 | 2011-10-10 | DISCRETIONARY_RESTRICT | 2011-04-19 | 2011-04-22 | 2011-05-30 | 2011-05-19 | 1 | 2011-10-07 | 2011-09-26 |  |  |  | 2012-02-07 | 2 |  |  | 2012-02-27 | 2012-02-28 |  |  |  |  | 2012-02-20 | 2012-02-22 | 2012-02-24 | 2012-03-02 | 2012-02-28 | 2012-02-07 | 2012-03-09 | [8 empty] | 2012-03-13 | 2012-03-15 | 2012-03-15 | 2012-03-18 | 2012-03-28 | 2012-06-26 | 2012-11-02 |  | VNZ | 2012-03-07 | 2012-02-28 | 2012-02-28 | 2012-02-28 | 2012-02-28 | 2012-02-28 | 2012-02-28 | 2012-03-15 | 2012-03-15 |  | 2012-03-22 | [6 empty] | 2012-02-27 | FALSE |  | 2841420 | 6181230 | Clyde Jeffery Drive Napier |  |  | CELLSITE |  |  | 2015-05-26 | [12 empty] | 2012-03-20 | 2012-03-22
0 | HKB | 974 | HKB-031-015 | Pandora (TX HUB) | HKB-031-015-B | Pandora - TX HUB | Napier | 1 | TIER_2 | ACTIVE | GF | DU | T2 25 UF | grey | STACK_A | STANDALONE | 24 | 25 | 1 | -39.4916 | 176.8856 |  | 2010-09-02 |  |  | Fibre Optic | HKB-031-001-A | FALSE | TRUE |  |  | FALSE |  | 2011-06-30 | 2011-06-30 | 2011-07-08 | 2011-07-06 | 2011-08-01 | 2011-07-29 | 2 | 2011-08-01 | 2011-10-11 | 2011-08-29 | 2011-08-29 | 2011-09-19 | 2011-08-31 | 1 | 2011-09-26 | 2011-08-31 | PERMITTED | 2011-08-29 | 2011-08-25 | 2011-09-29 | 2011-09-08 | 1 | 2011-10-03 | 2011-10-04 |  |  |  | 2012-02-28 | 1 |  |  | 2012-02-28 | 2012-02-28 |  |  |  |  | 2012-01-16 | 2012-01-09 | 2012-02-09 | 2012-02-08 | 2012-02-08 | 2012-02-15 | 2012-02-24 | [8 empty] | 2012-02-17 | 2012-03-15 | 2012-02-27 | 2012-02-21 | 2012-03-14 | 2013-05-17 | 2013-05-01 | Peter to check saggy door (not yet arranged) before FAC signed but FAN signoff can progress in the meantime, Alan will issue FAN. 09/04/13 - FAC reforecasted - Folder missing - to be found then Sean to final QA check 1/5/13 - FAC signed |  | 2012-02-17 | 2012-02-28 | 2012-02-28 | 2012-02-28 | 2012-02-28 | 2011-12-08 | 2012-02-28 | 2012-02-08 | 2012-02-09 |  | 2012-03-02 | [5 empty] | BUILD | 2012-02-07 | FALSE |  | 2844135 | 6183077 | Pandora Hub 11 Severn Street Pandora, Napier |  |  | CELLSITE |  |  | 2015-05-26 | [12 empty] | 2012-02-29 | 2012-03-02
0 | HKB | 975 | HKB-031-016 | Awatoto | HKB-031-016-D | Awatoto | Napier | 1 | TIER_2 | ACTIVE | GF | DU | T2 25 UF | grey | STACK_A | STANDALONE | 24.5 | 25 | 1 | -39.5454 | 176.9196 |  | 2010-09-02 |  |  | Microwave | HKB-031-012-A | FALSE | TRUE |  |  | FALSE | 2011-04-21 | 2011-05-30 | 2011-04-21 | 2011-05-02 | 2011-05-02 | 2011-05-26 | 2011-05-27 | 1 | 2011-05-26 | 2011-05-27 | 2011-06-17 | 2011-06-02 | 2011-06-20 | 2011-06-17 | 1 | 2011-06-30 | 2011-07-06 | PERMITTED | 2011-06-15 | 2011-06-16 | 2011-07-15 | 2011-07-12 | 1 | 2011-07-22 | 2011-07-12 |  |  | 2011-09-09 | 2011-09-22 | 1 |  | 2011-09-09 | 2011-09-22 | 2011-08-29 |  |  |  |  | 2011-10-08 | 2011-10-12 | 2011-11-03 | 2011-11-02 | 2011-11-03 | 2011-11-12 | 2011-11-13 | [8 empty] | 2011-11-14 | 2011-11-28 | 2011-12-08 | 2011-12-05 | 2011-12-16 | 2012-03-15 | 2012-07-31 | HARD MATCHED Cabinet dates TBC |  | 2011-11-14 | 2011-08-29 | 2011-08-29 | 2011-08-31 | 2011-11-15 | 2011-08-29 | 2011-08-29 | 2011-11-11 | 2011-11-11 |  | 2011-11-21 | [6 empty] | 2011-11-04 | FALSE |  | 2846790 | 6176982 | 44 Briasco st Awatoto |  |  | CELLSITE |  |  | 2015-05-26 | [12 empty] | 2011-12-02 | 2011-12-05
0 | HKB | 976 | HKB-031-017 | Napier Port | HKB-031-017-B | Napier Port, Floodlight swapout | Napier | 1 | TIER_2 | ACTIVE | GF | DU | SP | grey | INLINE | STANDALONE | 34.8 | 37.1 | 1 | -39.4789 | 176.9208 |  | 2010-09-02 |  |  | Fibre Optic | HKB-031-001-A | FALSE | TRUE |  |  | FALSE |  | 2011-06-01 | 2011-06-01 | 2011-06-08 | 2011-06-08 | 2011-07-07 | 2011-07-08 | 2 | 2011-08-05 | 2011-08-04 | 2011-08-08 | 2011-08-03 | 2011-08-31 | 2011-08-22 |  | 2011-09-07 | 2011-09-09 | DISCRETIONARY_FULL | 2011-08-05 | 2011-08-09 | 2011-09-09 | 2011-08-29 | 2 | 2011-09-12 | 2011-08-29 |  |  | 2011-12-13 | 2012-01-04 | 1 |  | 2011-12-13 | 2012-01-04 | 2012-02-28 |  |  |  |  | 2011-12-05 | 2011-12-05 | 2012-03-05 | 2012-03-06 | 2012-02-27 | 2012-03-07 | 2012-03-09 | [8 empty] | 2012-03-12 | 2012-03-30 | 2012-03-15 | 2012-03-21 | 2012-03-28 | 2012-06-26 | 2012-07-05 |  |  | 2012-03-07 | 2012-02-28 | 2012-03-02 | 2012-02-28 | 2012-02-28 | 2012-02-28 | 2012-02-28 | 2012-03-05 | 2012-03-15 |  | 2012-03-23 | [6 empty] | 2012-02-27 | FALSE |  | 2847222 | 6184349 | Napier Port, Bradkwater Rd, Napier |  |  | CELLSITE |  |  | 2015-05-26 | [12 empty] | 2012-03-21 | 2012-03-22
0 | HKB | 977 | HKB-031-018 | Napier Airport | HKB-031-018-A | VF Cosite - GF | Napier | 1 | TIER_2 | ACTIVE | GF | DU | P3 | grey | STACK_A | COSITE | 24.5 | 25 | 1 | -39.4731 | 176.8731 |  |  |  |  | Microwave | HKB-031-015-B | FALSE | TRUE |  |  | FALSE | 2011-04-15 | 2011-03-17 | 2011-03-18 | 2011-03-23 | 2011-03-25 | 2011-04-19 | 2011-04-16 | 1 | 2011-04-19 | 2011-04-16 | 2011-06-14 | 2011-05-11 | 2011-09-19 | 2011-07-27 | 1 | 2011-09-26 | 2011-11-30 | DISCRETIONARY_FULL | 2011-08-01 | 2011-08-01 | 2011-10-28 | 2011-08-29 | 1 | 2011-11-04 | 2011-08-29 |  |  | 2011-11-30 | 2011-12-22 | 1 |  | 2011-11-30 | 2011-12-22 | 2012-01-13 |  |  |  |  | 2011-11-28 | 2011-11-28 | 2012-01-20 | 2012-01-14 | 2012-01-18 | 2012-02-18 | 2012-02-15 | [8 empty] | 2012-02-14 | 2012-03-15 | 2012-02-27 | 2012-02-29 | 2012-03-14 | 2012-05-29 | 2012-08-31 | Affected party letter sent 25/5, Matt met LO wife and does not sound likley they will sign off affected party consent. Agreed we now need to submit consent without affected party apprvoal from house. Lease with Airport (actually the councils) for signing, executed by 2degrees. Matt to follow up Friday. |  | 2012-02-20 | 2011-11-15 | 2011-11-15 | 2011-11-30 | 2012-01-13 | 2011-11-21 | 2012-01-13 | 2012-01-26 | 2012-01-31 |  | 2012-03-02 | [6 empty] | 2012-01-18 | FALSE |  | 2843147 | 6185182 | Watchman Rd |  |  | CELLSITE |  |  | 2015-05-26 | [12 empty] | 2012-02-28 | 2012-03-02
0 | HKB | 978 | HKB-031-019 | Napier Exchange Co-Lo | HKB-031-019-A | Exchange Co-Lo | Napier |  | TIER_6 | ACTIVE | COLO | TX | [104 empty] | 35 Browning St, Napier |  |  | TXSITE | WIPACTIVE
0 | HKB | 979 | HKB-032-001 | Ashcott | HKB-032-001-A | Ashcott - Kordia | Central Hawke's Bay District | 24 | TIER_4 | ACTIVE | COLO | DF | LATTICE |  | STACK_A | COLO |  |  |  | -39.9478 | 176.3431 |  | 2015-03-05 |  | 2015-04-15 | Leased Line | AKL-007-112-A | FALSE | FALSE |  |  | FALSE |  | 2012-03-15 | 2015-03-12 | 2015-03-31 | 2015-03-27 | 2015-04-17 | 2015-03-31 | 1 | 2015-04-08 | 2015-03-31 | 2015-04-20 | 2015-04-20 | 2015-05-22 | 2015-04-21 |  | 2015-04-21 | 2015-04-21 | DISCRETIONARY_RESTRICT | 2015-05-31 | 2015-04-20 | 2015-06-30 | 2015-04-20 | 1 |  | 2015-04-20 | 2015-04-17 | 2015-03-27 | 2015-05-18 | 2015-04-10 | 1 |  | 2015-04-10 | 2015-04-10 | [5 empty] | 2015-07-27 | 2015-07-28 | 2015-08-10 | 2015-08-06 | 2015-08-06 | 2015-08-21 | 2015-08-17 | 2015-08-21 | 2015-08-13 | 2015-07-28 | 2015-07-28 | 2015-07-28 | 2015-07-28 | 2015-07-28 | 2015-07-28 |  | 2015-09-21 | 2015-09-21 |  | 2015-10-22 |  |  | Colocation application submitted 17 Feb 11/03 AS: Kordia has come back with quote on installation, need to liase with internal team on further steps. Kordia backhaul available.. Need to issue formal planning & construction drawing. 16/04 Build instruction issued - PO6 has to be raised waiting for quote on formal letter from Kordia | KDA | [9 empty] | 2015-09-09 | 2015-09-09 |  |  | NAPIER_DANNEVIRKE | 2015-08-18 | 2015-08-13 | BUILD | 2015-08-06 | FALSE |  | 2795603 | 6134362 | Tukituki Road SH50 |  |  | CELLSITE |  |  |  | ROAMING |  |  | 2015-03-26 | 2015-04-10 | 2015-04-10 |  |  |  |  | 2015-05-14 | 2015-05-13 |  |  | 2015-03-27
0 | HKB | 980 | HKB-032-002 | Waipukurau | HKB-032-002-A | Waipukurau VNZ Co-Lo | Central Hawke's Bay District | 21 | 2015P | ACTIVE | COLO | DU | COLO |  | STACK_A | COLO |  |  | 1 | -39.9934 | 176.5949 |  |  |  |  | Leased Line | HKB-030-001-A | FALSE | FALSE |  |  | FALSE |  | 2012-03-06 | 2012-03-06 | 2012-03-02 | 2012-03-02 |  | 2011-08-11 | 2 |  | 2014-05-16 | 2014-09-19 | 2014-11-24 | 2014-09-19 | 2015-02-27 |  | 2014-09-19 | 2015-02-27 | PERMITTED | 2012-05-07 | 2011-09-13 | 2012-06-07 | 2011-09-30 | 1 | 2012-06-11 | 2011-09-30 | 2014-05-15 | 2014-05-15 | 2014-08-07 | 2014-08-25 | 4 |  | 2014-08-15 | 2014-10-13 | [5 empty] | 2014-11-26 | 2014-12-01 | 2015-01-31 | 2015-02-01 | 2014-12-01 | 2015-02-16 | 2015-02-17 | 2015-02-23 | 2015-02-27 | [7 empty] | 2015-04-17 | 2015-04-17 |  |  |  |  | 07.08.14 : Have VNZ Prelim approval. Await Clearspan sub leas / DoV DOCS. Have RMA. Await CD's. With Clearspan sublease we can submit Project Plan (Takes 10days to approve) Fibre has been requested. Steel work completed by Ken of Amediate Engineering. To build with K225 antenna (In stock) then swap out with required antenna when arrive. Stef to take BR and contractors to site Monday 18 Aug. BR to follow up with Rob M : RM to ask Gemma of VNZ for the sublease doc. It needs to be signed by VNZ, 2D and Clearspan. 30 Oct Build tender issued to TSL - easement for power causing build start delays. 4 Nov TSL to install ringframe, antennas, cabinets while 2D work on easement. 11 Nov - SOA this year at risk due to power delivery and VF proj plan approval. Spark Co-site approval submitted. 10 Dec Additional support arms not avialble to complete ring frame installation. Power connection is on the critical path. 16 Dec Support arms arrived today minus one mounting plate. 29 Jan - yet more incorrect steel work delivered, ring frame is up, 2 antenna mount poles to be installed prior to antenna . Inability of PM to get CR approval delays integration. Fibre issue discovered during pre-integration. Integration failed first attempt, SIM issues prevented call testing. 19 Mar - site integarted, Vol4 due on Mon 23rd. 10 Apr- VF PIM issues to be rectified prior to going to air | VNZ | [9 empty] | 2015-03-23 | 2015-03-27 |  |  | NAPIER_DANNEVIRKE | 2015-02-23 |  | BUILD | 2014-11-14 | FALSE |  | 2816900 | 6128463 | 130, Mangatarata Road, Waipukurau |  |  | CELLSITE |  |  |  | CAPACITY
0 | HKB | 981 | HKB-032-003 | Otane |  |  | Central Hawke's Bay District | 6 | TIER_3 | [22 empty] | FALSE | [60 empty] | Primary Coverage Objective: ROAMING MITIGATION SH2 coverage COLO at Vodafone Backup: Greenfield nearby but additional height and distance is critical for co-site isolation | [14 empty] | NAPIER_DANNEVIRKE
South Island | MBN | 985 | MBN-051-004 | Motueka Township | MBN-051-004-A | Motueka Township RBI Colo | Tasman District | 7 | TIER_3 | ACTIVE | RBI | DU | COLO |  | STACK_A | COLO |  |  | 1 | -41.1138 | 173.0133 |  | 2012-01-26 |  |  | Leased Line | MBN-052-003-B | FALSE | FALSE |  |  | FALSE |  | 2012-03-28 | 2012-03-27 | 2012-04-04 | 2012-04-13 | 2012-07-05 | 2012-07-06 | 2 | 2012-07-05 | 2012-10-16 | 2012-09-12 | 2012-08-31 | 2012-10-19 | 2012-10-14 |  | 2013-05-24 |  | DISCRETIONARY_FULL | 2012-08-07 | 2012-07-30 | 2012-09-18 | 2012-09-07 | 1 | 2012-12-07 | 2012-12-07 | 2012-10-25 |  | 2012-11-16 | 2012-11-27 | 1 |  | 2012-11-16 | 2012-11-27 |  |  |  | 2012-10-25 |  | 2012-11-30 | 2012-12-04 | 2013-01-25 | 2013-01-25 | 2012-12-03 | 2013-02-07 | 2013-02-01 | [8 empty] | 2013-02-01 | 2013-02-15 | 2013-02-15 | 2013-03-04 | 2013-02-27 | 2013-08-30 | 2013-10-10 |  | TNZ | 2013-02-01 | [6 empty] | 2013-01-23 | 2013-01-25 | 2013-02-07 | 2013-02-11 | 2012-04-02 | LOW | RBI | 2013-01-18 | 2013-01-18 | BUILD | 2012-12-07 | TRUE | 2012-10-18 | 2511106 | 6010313 | 7 Hickmott Place Motueka |  |  | CELLSITE |  |  | 2015-10-27 | [12 empty] | 2013-02-07 | 2013-02-08 | 2012-04-13
South Island | MBN | 996 | MBN-051-016 | Mt Campbell | MBN-051-016-A | Mt Campbell | Tasman District | 7 | TIER_3 | ACTIVE | COLO | DU | COLO |  | STACK_A | COLO |  | 63 | 1 | -41.1238 | 172.8527 |  | 2012-01-26 |  |  | Microwave | MBN-051-004-A | FALSE | FALSE |  |  | FALSE |  | 2012-03-28 | 2012-03-27 | 2012-04-18 | 2012-04-20 | 2012-07-26 | 2012-07-31 | 4 | 2012-07-26 | 2015-06-23 | 2012-09-11 | 2012-09-28 | 2012-09-28 | 2012-09-28 | 1 | 2012-09-28 | 2012-10-01 | DISCRETIONARY_RESTRICT | 2012-07-31 | 2015-07-14 | 2012-09-12 | 2015-08-12 | 4 | 2012-09-12 | 2012-08-30 |  |  | 2012-11-21 | 2012-11-21 | 4 |  | 2012-11-21 | 2015-10-14 | 2012-12-03 |  |  |  |  | 2013-01-07 | 2013-01-07 | 2013-02-13 | 2013-02-22 | 2013-01-10 | 2013-02-07 | 2013-02-01 | [8 empty] | 2013-02-02 | 2013-02-15 | 2013-02-15 | 2013-03-05 | 2013-03-05 | 2013-09-10 | 2013-12-12 |  | TNZ | 2013-01-30 |  |  | 2012-12-03 |  | 2012-12-03 | 2012-12-03 | 2013-01-22 | 2013-01-25 | 2013-02-07 | 2013-02-11 | 2012-04-02 | LOW | NELSON_OUTER |  |  | BUILD | 2013-01-08 | FALSE |  | 2497618 | 6009199 | Mt Campbell Road, Brooklyn Motueka 7198 |  |  | CELLSITE | [15 empty] | 2013-02-12 | 2013-02-20 | 2012-04-20
South Island | WST | 1720 | WST-057-001 | Hokitika | WST-057-001-C | Lodge Co-site | Westland District | 4 | TIER_3 | ACTIVE | GF | DU | SP |  | INLINE | COSITE | 35 | 35 | 1 | -42.71 | 170.9796 |  |  |  |  | Fibre Optic | WST-056-004-A | FALSE | FALSE |  |  | FALSE |  | 2012-03-06 | 2012-03-06 | 2012-06-29 | 2012-06-29 | 2012-07-12 | 2012-08-06 | 2 | 2012-08-10 | 2012-12-14 | 2012-08-17 | 2012-08-16 | 2012-09-14 | 2012-09-10 | 1 |  | 2013-03-25 | DISCRETIONARY_FULL | 2012-09-17 | 2012-09-03 | 2012-10-15 | 2012-10-18 | 1 |  |  |  |  | 2012-11-30 | 2013-01-15 | 1 |  | 2013-01-14 | 2013-01-15 |  |  |  | 2012-09-14 |  | 2013-02-06 | 2013-02-04 | 2013-02-22 | 2013-03-01 | 2013-03-01 | 2013-02-28 | 2013-03-11 | [8 empty] | 2013-03-11 | 2013-03-22 | 2013-03-18 | 2013-04-02 | 2013-03-28 | 2013-07-11 | 2013-06-28 | Back up option if VF colo fails (due to close proximity to Telecom Tower). we may be able to get good height and improve on VF coverage. Council appear relaxed about taller structure. Requires extra battery cabinet. 13/8 May be able to bring Wo2 forward. 03/09 Re-submitt co-site appln. Original GHD drawing set had fundamental set out dimension errors which proved site unbuildable, new PD and thereafter CD were required causing significant delay. |  | 2013-03-01 | 2012-09-04 | 2012-09-04 | 2012-11-05 |  | 2012-11-05 |  | 2013-02-26 | 2013-03-04 | 2013-03-14 | 2013-03-14 | 2012-09-03 | LOW | GREYMOUTH_WESTPORT | 2013-02-26 | 2013-03-05 | BUILD | 2013-02-25 | TRUE | 2012-09-14 | 2344510 | 5831035 | Seaview Lodge Seaview Hill Road Hokitika |  | Discretionary if > 25m - 17/05/2012 | CELLSITE | [15 empty] | 2013-03-15 | 2013-03-15
South Island | WST | 1718 | WST-056-003 | Karoro | WST-056-003-C | Karoro KiwiRail | Grey District | 4 | TIER_3 | ACTIVE | GF | DU | T2 20 UF LTD |  | INLINE | STANDALONE | 20 | 22.7 |  | -42.4688 | 171.1899 |  |  |  |  | Fibre Optic | CHC-060-114-A | FALSE | FALSE |  |  | FALSE |  | 2012-05-22 | 2012-05-22 | 2012-05-30 | 2012-05-30 | 2012-06-20 | 2012-06-27 | 1 | 2012-06-28 | 2012-06-27 |  | 2012-06-15 | 2012-12-12 | 2012-12-11 | 1 | 2012-12-12 | 2012-12-11 | PERMITTED | 2012-10-19 | 2012-10-17 | 2012-11-19 | 2012-11-02 | 1 |  |  | 2103-01-15 |  | 2013-01-24 | 2013-01-16 | 2 |  |  | 2013-02-07 |  |  |  | 2012-12-05 |  | 2013-01-21 | 2013-01-21 | 2013-02-15 | 2013-03-15 | 2013-03-15 | 2013-03-13 | 2013-03-15 | [9 empty] | 2013-04-05 | 2013-04-04 | 2013-04-16 | 2013-04-16 | 2013-09-02 | 2013-08-27 | TP to find out permitted height and if soil is likely to be contaminated. 5/6 Fibre request is in. PD rejected for a 2nd time not having all requested changes included. Await advice on commencement date and rent payment start for lease, need lease prior to RC lodge. 3/12 Lease signed 30 Nov. |  | 2013-02-19 | [6 empty] | 2013-03-15 |  | 2013-03-25 | 2013-04-02 | 2012-08-01 | MEDIUM | GREYMOUTH_WESTPORT | 2013-02-15 | 2013-03-22 | BUILD | 2013-02-18 | TRUE | 2012-12-15 | 2361157 | 5858214 | Tasman Street, Greymouth |  |  | CELLSITE | [15 empty] | 2013-03-22 | 2013-04-04
South Island | OTG | 1218 | OTG-070-011 | Wanaka | OTG-070-011-A | Wanaka VF colo | Queenstown | 4 | TIER_3 | ACTIVE | COLO | DU | COLO |  | INLINE | COLO |  |  |  | -44.73 | 169.116 |  |  |  |  | Fibre Optic | OTG-070-001-A | FALSE | FALSE |  |  | FALSE |  | 2012-04-12 | 2012-04-12 | 2012-05-01 | 2012-05-01 | 2012-06-08 | 2012-06-11 | 2 | 2012-06-11 | 2012-06-25 | 2012-07-20 | 2012-07-26 | 2012-11-09 | 2012-11-14 |  |  | 2012-12-21 | DISCRETIONARY_RESTRICT | 2012-08-15 | 2012-08-09 | 2012-11-22 | 2012-11-08 | 2 | 2012-09-14 |  | 2013-01-15 |  | 2013-01-15 | 2013-01-16 | 1 |  |  | 2013-01-16 | 2013-02-15 | 2013-01-15 |  |  |  | 2013-02-11 | 2013-02-16 | 2013-02-25 | 2013-03-07 | 2013-02-19 | 2013-02-27 | 2013-03-08 | [8 empty] | 2013-03-08 | 2013-04-11 | 2013-04-11 | 2013-04-20 | 2013-04-12 | 2013-09-13 | 2013-09-10 | Controlled if < 15m. Requires extra battery cabinet. Local planner prefers colo. 29/05 SA - continuing negotiations. 02/07 On hold as Vf do not know if they can sub-let. Jason will assist with land acquisition from Telecom. 16/7 Vf now off-hold. LL consent required to continue, response expected this wk. 13/8 Still waiting for Vf docs. 20/8 Legal review taking a long time. 3/9 Next council meeting 2nd Oct. 17/9 Additional form for LL to sign. Chorus need to swap PSU for fibre modem to a DC-DC type before site can go live | VNZ | 2013-03-08 | 2012-12-20 | 2012-12-20 | 2013-02-15 | 2013-02-15 | 2013-02-15 | 2013-02-15 | 2013-02-27 | 2013-03-07 | 2013-03-13 | 2013-03-18 |  | LOW | OTAGO | 2013-02-20 | 2013-02-27 | BUILD | 2013-02-19 | FALSE |  | 2202425 | 5601423 | Off Cardrona Valley Road |  | Controlled if >15m - 17/05/2012 | CELLSITE | [15 empty] | 2013-03-15 | 2013-03-19
South Island | OTG | 1222 | OTG-070-015 | Queenstown Exchange | OTG-070-015-A | Chorus - TX Only site | Queenstown | 4 | TIER_3 | ACTIVE | COLO | TX |  |  |  | COLO |  |  |  | -45.0319 | 168.6628 | [6 empty] | FALSE | FALSE |  |  | FALSE |  | 2012-12-13 | 2012-12-13 | 2012-12-13 | 2012-12-13 | 2012-12-13 | 2013-01-23 | 1 | 2012-12-13 | 2013-01-23 | 2012-12-13 | 2012-12-13 |  | 2013-01-25 |  |  | 2013-01-25 | PERMITTED | 2013-02-08 | 2013-01-25 | 2013-02-08 | 2013-01-25 | 1 |  |  |  |  | 2013-02-08 | 2013-02-11 | 1 |  | 2013-02-08 | 2013-02-11 | [5 empty] | 2013-01-25 | 2013-01-25 | 2013-02-22 | 2013-03-22 | 2013-01-25 | 2013-04-23 | 2013-04-24 | [9 empty] | 2013-04-30 | 2013-04-30 | 2013-05-15 | 2013-05-15 | 2013-09-06 | 2013-09-06 | No caravan, WO1, PD or CD required colocation inside Telecom exchange for a CX-600 rack only |  | 2013-04-16 |  |  | 2013-03-04 | 2013-03-04 |  |  | 2013-04-15 | 2013-04-15 |  |  |  |  | TRANSMISSION_ONLY |  |  | BUILD | 2013-01-25 | FALSE |  | 2168336 | 5566137 | 11A Camp Street Queenstown Queenstown Lakes |  |  | TXSITE | [15 empty] | 2013-04-25 | 2013-05-06 | 2012-12-13
South Island | MBN | 1034 | MBN-053-012 | Wither Hills | MBN-053-012-D | GF Near Kordia Site | Marlborough District | 6 | 2014 | ACTIVE | GF | DU | SP | Grey | STACK_A | COSITE | 10.6 | 12.55 |  | -41.5458 | 173.9846 |  | 2012-01-11 |  |  | Microwave | MBN-053-004-A | FALSE | FALSE |  |  | FALSE |  | 2012-03-22 | 2012-03-21 | 2012-04-02 | 2012-04-02 | 2012-06-13 | 2012-06-14 | 3 | 2012-06-13 | 2014-04-17 | 2013-01-18 | 2013-01-18 | 2014-05-20 | 2014-05-20 |  | 2014-06-25 | 2014-06-20 | PERMITTED | 2012-06-20 | 2012-06-15 | 2012-08-01 | 2012-07-13 | 1 | 2012-08-01 | 2012-07-13 | 2014-02-26 | 2014-02-26 | 2014-06-15 | 2014-04-17 | 1 |  | 2014-06-15 | 2014-04-17 | [5 empty] | 2014-07-15 | 2014-06-23 | 2014-08-15 | 2014-08-01 | 2014-07-15 | 2014-08-25 | 2014-08-07 |  | 2014-08-07 | [7 empty] | 2014-08-30 | 2014-08-29 |  |  |  |  | 9/5/13: • Council have requested 2 degrees sign lease first. Lease is with 2 degrees for signing, but is subject to Site Acqu review. • COW is in service. Progressing Lease execution with Council. CDI issued 06.08.14 Site Integrated 08.08.14 Co site for VNZ and TNZ in the file. Kordia ? BR asked SS | [10 empty] | 2014-08-30 | 2014-08-06 | 2012-04-02 | LOW | BLENHEIM |  |  | BUILD | 2014-08-20 | FALSE |  | 2592135 | 5961878 | Cob Cottage Road Wither Hills Blenheim |  | Withier Hills - 02/04/2012 | CELLSITE |  |  | 2015-04-07 | [14 empty] | 2012-04-02
South Island | OTG | 1199 | OTG-069-003 | Clyde | OTG-069-003-A | Clyde Greenfield | Central Otago | 21 | TIER_4 | ACTIVE | GF | DU |  |  | INLINE | COSITE | 15 | 15 |  | -45.1865 | 169.3004 | [6 empty] | FALSE | FALSE |  |  | FALSE |  | 2012-04-12 | 2012-04-12 | 2012-05-03 | 2012-05-03 | 2012-06-01 | 2012-06-06 | 2 | 2012-06-01 | 2015-05-26 | 2012-07-05 | 2012-07-02 | 2012-08-17 | 2012-08-17 | 1 |  | 2012-08-20 | PERMITTED | 2012-08-15 | 2012-07-13 | 2012-09-12 | 2012-08-03 | 1 |  | 2012-08-03 | 2014-11-07 | 2014-11-07 | 2015-04-28 | 2015-02-23 | 2 |  |  | 2015-07-15 | 2015-06-10 |  |  |  |  | 2015-05-19 | 2015-05-18 | 2015-06-26 | 2015-07-01 | 2015-06-08 | 2015-07-10 | 2015-07-13 | 2015-07-02 | [7 empty] | 2015-07-13 | 2015-07-24 | 2015-07-30 |  | 2015-08-13 |  |  | Could be an expensive build. Most of the track is public, last section is Telecoms. Requires extra battery cabinet. 16/7 Lease sent to LL Fri 13th - SA. 23/7 Should be ready by 15 Aug. 13/8 Needs LL to re-sign. (8 Oct 2014) - RF to review PD, may need antenna type amendment and azimuth tweaks. PM to re-visit power connection cost. Tx to re visit fibre connection. FO looks good, Trans upgrade $6k. CDI issued. 12 Nov - Tx re-checking FO cost. Site subject to RF redesign. 29 Jan - site confirmwed dates changed to align with expected Huawei equipment delivery | VNZ | 2015-07-10 |  |  | 2015-05-08 | 2015-05-27 | 2015-05-29 | 2015-06-10 | 2015-06-26 | 2015-07-01 | 2015-07-20 | 2015-07-15 | 2012-06-20 | LOW | OTAGO | 2015-05-15 |  | BUILD | 2015-06-15 | FALSE |  | 2219287 | 5551422 | Hawksburn Road Clyde |  | Slippage rules don't apply - 17/05/2012 | CELLSITE |  |  |  | ROAMING |  | 2015-03-13 | 2015-02-04 | 2015-03-30 | 2015-03-27 |  |  |  |  | 2015-05-13 | 2015-05-13 | 2015-07-16 | 2015-07-23 | 2012-05-03
South Island | STH | 1297 | STH-073-020 | Te Anau | STH-073-020-A | Te Anau Town | Southland District | 21 | TIER_4 | ACTIVE | GF | DU | P2 |  | INLINE | STANDALONE |  |  |  | -45.4119 | 167.7302 | [6 empty] | FALSE | FALSE |  |  | FALSE |  | 2012-04-13 | 2012-03-29 | 2012-04-05 | 2012-04-05 | 2012-05-22 | 2012-05-21 | 1 | 2012-05-22 | 2012-05-21 |  | 2012-04-02 | 2012-06-20 | 2012-06-11 | 1 |  | 2012-06-11 | PERMITTED | 2012-06-13 | 2012-06-15 | 2012-07-13 | 2012-07-11 | 1 |  | 2012-07-11 | 2014-11-07 | 2014-11-07 | 2015-01-30 | 2015-01-21 | 1 |  |  | 2015-01-21 |  |  |  | 2015-03-31 |  | 2015-05-11 | 2015-05-11 | 2015-06-15 | 2015-06-19 | 2015-06-10 | 2015-06-17 | 2015-07-03 | 2015-07-01 | [7 empty] | 2015-07-08 | 2015-07-24 | 2015-07-30 |  | 2015-08-17 |  |  | Requires extra battery cabinet. 29/05 PD rev2 to include planting for RC. 02/07 T.P. to work with Council regarding neighbours. 8 Oct 2014 - RF to confirm this is the best location if VF colo becomes an option - site visit required, planned for week ending 24 Oct. This is not prefered location (Now Woosh) but is hard matched await direction - CDI issued for this site. Tx rechecking FO cost. Site subject to RF review and confirmation - construction dates could slip. 26 Jan - site back in build list. Date align with Huawei equipment delivery. 16 July - 12 days added to Vol 4 date due to late fibre from Chorus |  | 2015-07-08 |  |  | 2015-05-22 | 2015-06-02 | 2015-05-22 |  | 2015-06-12 | 2015-06-19 | 2015-07-22 | 2015-07-09 | 2012-04-08 | MEDIUM | SOUTHLAND | 2015-06-10 |  | BUILD | 2015-06-10 | TRUE | 2015-03-31 | 2097691 | 5519702 | 4 Snodgrass Road Te Anau |  |  | CELLSITE |  |  |  | ROAMING |  | 2015-03-13 | 2015-02-04 | 2015-04-02 | 2015-04-02 | [5 empty] | 2015-05-07 | 2015-07-24 |  | 2012-04-05
South Island | OTG | 1273 | OTG-072-003 | Milton | OTG-072-003-B | Milton GF | Clutha | 21 | TIER_4 | ACTIVE | GF | DU |  |  | INLINE | COSITE |  |  |  | -46.0623 | 170.0053 |  |  |  |  | Microwave | OTG-071-001-C | FALSE | FALSE |  |  | FALSE |  | 2012-03-21 | 2012-03-22 | 2012-03-27 | 2012-03-27 | 2012-05-14 | 2012-05-16 | 1 | 2012-05-14 | 2012-05-16 | 2012-05-30 | 2012-06-15 | 2012-07-23 | 2012-07-19 | 1 |  |  | PERMITTED | 2012-06-15 | 2012-06-15 | 2012-07-13 | 2012-06-20 | 1 |  | 2012-06-20 | 2015-02-06 | 2015-02-05 | 2015-03-20 | 2015-03-24 | 1 |  |  | 2015-03-24 | 2015-06-24 |  |  |  |  | 2015-05-20 | 2015-05-20 | 2015-07-01 | 2015-07-01 | 2015-06-24 | 2015-07-10 | 2015-07-16 | 2015-06-26 | [7 empty] | 2015-07-21 | 2015-07-31 | 2015-08-06 |  | 2015-09-24 |  |  | Flat ground unlikley to need any in ground retaining structure. Access OK and may be farmer owned. Plenty of room for lease area to cater for cheapest foundation option. Cosite applications completed 12 Jun. 16/7 Owner does not own below the surface (mineral coy have rights). 26 Jan - Rf to review and CDI to be issued. Review complete - antenna changes will trigger minor lease/consent amendment. Dates accomodate Huawei equipment delivery date.16 Jul - 13 days added to Vol4 date from civil complete to late Chorus fibre delivery (Phil) + 5 days added for LO preventing build start. |  | 2015-07-20 |  |  |  |  | 2015-06-24 | 2015-06-24 | 2015-07-01 | 2015-07-01 | 2015-07-25 | 2015-07-23 | 2012-04-08 | LOW | OTAGO |  |  | BUILD | 2015-06-24 | FALSE |  | 2278135 | 5456377 | Off McNeil Road Milton |  |  | CELLSITE |  |  |  | ROAMING |  | 2015-03-13 | 2015-02-04 | 2015-04-02 | 2015-04-02 | [5 empty] | 2015-05-13 | 2015-09-04 | 2015-09-07 | 2012-03-27
South Island | CAN | 665 | CAN-062-011 | Lincoln University | CAN-062-011-C | Burns Building | Selwyn District | 21 | TIER_4 | ACTIVE | RT | DF |  |  |  | COSITE |  |  |  | -43.6432 | 172.4698 |  |  |  |  | Fibre Optic |  | FALSE | FALSE |  |  | FALSE |  | 2012-03-30 | 2012-03-27 | 2012-04-05 | 2012-03-29 | 2012-10-10 | 2013-01-21 | 4 | 2015-01-16 | 2015-02-13 | 2014-10-30 | 2014-10-30 | 2015-05-30 | 2015-06-22 |  |  |  | PERMITTED | 2015-01-30 | 2015-01-30 | 2015-03-06 | 2015-01-30 | 3 | 2015-03-06 | 2015-01-30 | 2014-12-01 | 2014-11-21 | 2015-03-27 | 2015-04-30 | 1 |  |  | 2015-04-30 | 2015-06-30 |  |  | 2015-05-01 |  | 2015-06-24 | 2015-06-24 | 2015-07-03 | 2015-07-07 | 2015-07-02 | 2015-07-08 | 2015-07-21 | 2015-07-13 | [7 empty] | 2015-07-24 | 2015-08-07 | 2015-08-06 |  | 2015-09-30 |  |  | SA slowly working with Lincoln Uni on their timescale. 12/05 Lincoln Uni have restarted communication and have noted that construction will be limited to semester breaks. 03/04 antenna and dishes limited to 2m above point of attachment. 07/05 Sketches required for correct location. RF to find out building height. 14/005 Building might be condemned. 8 Oct 2014 - Visit organised for RF to confirm antenna azimuths - Bldg has not been condemned Site visit 16th Oct SA inform that changes to existing design will cause delay and as such the antenn locations on PD will remain - access to upper antenna via abseil 4 Nov- Aquire lease as per PD and see if we can optimise design for CD. 11 Nov, lease executed may be quicker than planned. RF to reassess plume from S2, prefered location is still on bldg parapet. Plumes are Ok, continue and try to relocate antenna if no delay to project - CDI Issued. New plumes are not good on roof, University are happy to relocate the antenna to Bldg parapet, new PD will be reqd but push on with CD. 26 Jan - Uni advise buildibg to be demolished within 5 years, looking for alternative solutions but pushing on with this design |  | 2015-07-24 |  |  | 2015-05-29 | 2015-06-02 | 2015-06-05 | 2015-06-30 | 2015-06-29 | 2015-07-07 | 2015-07-27 | 2015-08-03 | 2013-03-14 | LOW | CHRISTCHURCH_OUTER | 2015-06-12 |  | BUILD | 2015-07-03 | TRUE | 2015-05-01 | 2467230 | 5729224 | Springs Road, Burns Building, Lincoln University |  |  | CELLSITE |  |  |  | ROAMING |  |  | 2015-03-19 | 2015-04-30 | 2015-05-01 |  |  |  |  | 2015-05-29 | 2015-06-09 | 2015-09-04 | 2015-09-10 | 2012-04-05
South Island | MBN | 1003 | MBN-051-023 | Takaka RBI | MBN-051-023-A | Takaka RBI | Tasman District | 21 | TIER_4 | ACTIVE | RBI | DF | COLO |  | STACK_A | COLO | 25 | 25 |  | -40.8269 | 172.787 | [6 empty] | FALSE | FALSE |  |  | FALSE |  | 2015-04-14 | 2015-04-14 | 2015-05-21 | 2015-05-22 | 2015-05-22 | 2015-05-21 | 1 | 2015-05-21 | 2015-05-21 | 2015-06-26 | 2015-06-23 | 2015-07-17 | 2015-06-23 |  | 2015-07-10 | 2015-07-10 | PERMITTED | 2015-05-22 | 2015-05-29 | 2015-06-05 | 2015-06-25 | 1 | 2015-06-05 | 2015-06-25 | 2015-05-21 | 2015-05-21 | 2015-05-26 | 2015-06-12 | 2 |  | 2015-05-15 | 2015-06-15 | 2015-07-22 |  |  |  |  | 2015-07-21 | 2015-07-20 | 2015-07-23 | 2015-07-22 | 2015-07-21 | 2015-07-28 | 2015-07-28 | 2015-07-22 | 2015-07-22 | 2015-07-10 | 2015-07-22 | 2015-07-10 | 2015-07-10 | 2015-07-03 | 2015-07-23 | 2015-07-30 | 2015-08-13 | 2015-08-13 |  | 2015-08-28 |  |  | Tx Site to serve Collingwood Kordia colo site 19 June: RFS 22 July 26 June: POR approved 27 June: Project Plan sent to VF 10 July: VF final approval received 17 July: Fibre delivered 28 July: Integrated successfully 30 July: Vol4 received with ATN errors 31 July: Correct Vol4 errors 4 Aug: Waiting on power connection then SOA 10 Aug: Power installed & site powered up 12 Aug: SOA 13 Aug: Waiting for PAD documents. Note: Need to design, manufacture (ex China) & install stand-off bracket for sector 3. Currently 315deg but needs to be 330deg. | VNZ | 2015-07-31 | 2015-07-22 | 2015-07-22 | 2015-07-15 | 2015-07-15 | 2015-07-22 | 2015-07-22 | 2015-07-31 | 2015-08-10 | 2015-08-12 | 2015-08-12 |  |  |  | 2015-07-22 | 2015-07-17 | BUILD | 2015-07-20 | FALSE |  | 2492016 | 6042152 | 259 Takaka- Collingwood Highway |  |  | CELLSITE |  |  |  | ROAMING |  |  | 2015-06-12 | 2015-05-20 | 2015-05-21 | 2015-05-18 | 2015-05-18 | 2015-06-03 | 2015-06-03 | 2015-06-30 | 2015-06-29 | 2015-09-08 | 2015-08-18 | 2015-05-21
South Island | OTG | 1270 | OTG-071-049 | Waikouaiti | OTG-071-049-B | Waikouaiti GF | Dunedin | 21 | TIER_4 | ACTIVE | GF | DU | T2 15 RFH |  | INLINE | COSITE |  | 16 |  | -45.5749 | 170.6661 |  |  |  |  | Microwave | OTG-071-015-A | FALSE | FALSE |  |  | FALSE | 2012-03-15 | 2012-03-21 | 2012-03-22 | 2012-04-05 | 2012-03-27 | 2012-05-14 | 2012-05-10 | 2 | 2012-05-14 | 2015-05-27 | 2012-04-27 | 2012-04-16 | 2012-07-12 | 2012-07-13 |  |  |  | DISCRETIONARY_RESTRICT | 2012-06-08 | 2012-06-07 | 2012-07-13 | 2012-07-12 | 1 |  | 2015-08-17 | 2015-02-03 | 2015-02-03 | 2015-03-25 | 2015-03-18 | 1 |  |  | 2015-03-18 | 2015-05-20 |  |  |  |  | 2015-05-19 | 2015-05-19 | 2015-07-01 | 2015-07-07 | 2015-07-01 | 2015-07-27 | 2015-07-27 | 2015-06-09 | [7 empty] | 2015-08-07 | 2015-08-14 | 2015-08-13 |  | 2015-09-21 |  |  | Flat ground not likely to require any retaining structure, room for pad or pile which ever is cheaper. 14/05 Rob to draft RC. Cosite application lodged 12 Jun for TC and VF. 26 Jan - Rf to review and CDI to be issued. Review complete dates aligned with expected Hauwei equipment delivery. 30 Jul - 20 days added to Vol4 date from civil complete to late Chorus fibre delivery (Phil) |  | 2015-07-15 |  |  | 2015-05-20 | 2015-05-20 | 2015-05-20 | 2015-05-20 | 2015-07-06 | 2015-07-07 | 2015-07-27 | 2015-08-07 | 2015-08-21 | LOW | OTAGO | 2015-06-05 |  | BUILD | 2015-06-26 | FALSE |  | 2327738 | 5512166 | Off Quarry Road Waikouaiti |  |  | CELLSITE |  |  |  | ROAMING |  | 2015-03-13 | 2015-02-04 | 2015-04-02 | 2015-04-02 |  |  |  |  | 2015-05-13 | 2015-05-13 | 2015-09-04 | 2015-09-08 | 2012-03-27
South Island | CAN | 669 | CAN-062-015 | RBI - West Melton Central | CAN-062-015-A | RBI | Selwyn District | 21 | TIER_4 | ACTIVE | RBI | DF | RBI Pole |  | STACK_A | COLO | 25 | 25 |  | -43.514 | 172.3751 |  |  |  |  | Fibre Optic |  | FALSE | FALSE |  |  | FALSE |  | 2015-03-27 | 2015-03-30 | 2015-04-14 | 2015-04-15 | 2015-05-01 | 2015-04-15 | 1 | 2015-04-15 | 2015-04-15 | 2015-06-26 | 2015-06-24 | 2015-06-26 | 2015-06-24 |  | 2015-07-03 | 2015-06-24 | PERMITTED | 2015-05-08 | 2015-04-15 | 2015-06-05 | 2015-04-15 | 1 | 2015-06-12 | 2015-04-15 | 2015-05-29 | 2015-04-17 | 2015-05-29 | 2015-04-22 | 2 |  |  | 2015-06-25 |  |  |  | 2015-06-19 |  | 2015-07-27 | 2015-07-27 | 2015-08-02 | 2015-07-27 | 2015-07-30 | 2015-08-05 | 2015-08-05 | 2015-08-11 | [7 empty] | 2015-08-04 | 2015-08-26 | 2015-08-28 |  | 2015-09-17 |  |  | RBI site surrounded by trees, search should be made for an alternative site but planning in the area is an issue. RBI site to be used, SDP recieved 27 Mar, application to be lodged. Equipment ordered for Gore can be used | VNZ | 2015-08-06 |  |  | 2015-07-10 | 2015-07-14 |  |  | 2015-08-13 |  | 2015-08-15 | 2015-08-05 | 2015-02-20 | LOW |  |  |  | BUILD | 2015-07-31 | TRUE | 2015-06-19 | 2459486 | 5743530 | 198 Halkett Road West Melton |  | Permitted if no height increase to RBI tower - 20/02/2015 | CELLSITE |  |  |  | ROAMING |  |  | 2015-06-04 | 2015-05-22 | 2015-05-11 |  |  |  |  | 2015-06-22 | 2015-06-12 | 2015-08-31 |  | 2015-04-15
South Island | WST | 1716 | WST-056-001 | Greymouth Outer | WST-056-001-C | Sewell Peak VF colo | Grey District | 21 | TIER_4 | ACTIVE | COLO | DU | COLO |  | INLINE | COLO |  | 10 |  | -42.408 | 171.3425 |  |  |  |  | Microwave | WST-056-002-B | FALSE | FALSE |  |  | FALSE |  | 2015-03-11 | 2015-03-11 | 2015-04-01 | 2015-03-30 | 2015-04-29 | 2012-05-29 | 4 | 2015-03-30 | 2015-04-28 | 2015-05-29 | 2015-05-14 | 2015-08-07 | 2015-08-04 |  | 2015-08-14 | 2015-08-10 | PERMITTED | 2015-05-08 | 2012-12-07 | 2015-06-05 | 2012-12-20 | 3 |  | 2015-08-24 | 2015-06-12 | 2015-05-15 | 2015-07-10 | 2015-06-19 | 1 |  |  | 2015-06-19 | 2015-08-27 |  |  |  |  | 2015-08-24 | 2015-08-27 | 2015-09-08 | 2015-09-09 | 2015-09-03 | 2015-09-04 | 2015-09-29 | 2015-09-23 | [7 empty] | 2015-10-09 | 2015-10-26 | 2015-10-16 |  |  |  |  | Agreement with VF + DOC. structural ok. no power or access contribution. Requires extra battery cabinet. 21/05 new structural assessment. SA to find out applicable fees from DOC. 29/05 Jason asking VF for fee to be reduced. Telecom to be contacted regarding generator sharing, site may switch to Telecom colo. 02/07 SA chasing doc. 13/8 Pole up option to be re-visited. 27/8 Structural analysis for pole up passed. 03/09 New drwg & Colo appln required. 3/12 Vf colo, could lodge? 10/12 Lease complete with doc but not with Vf. 12 Mar - No new Vf equipment, looks good to resurrect the original proposal RF do not need 6 antennas. 30 Mar existing PD is OK to use with minor amendment. 30 Apr colo application submitted | VNZ | 2015-09-30 | 2015-08-10 | 2015-08-10 | 2015-08-10 | 2015-08-10 | 2015-08-14 | 2015-08-27 | 2015-09-12 | 2015-09-29 | 2015-10-02 | 2015-10-09 | 2012-04-08 | LOW | GREYMOUTH_WESTPORT |  |  | BUILD | 2015-09-09 | FALSE |  | 2373571 | 5865230 | Sewell Peak Greymouth |  |  | CELLSITE |  |  |  | ROAMING |  |  | 2015-05-27 | 2015-07-24 | 2015-05-12 |  |  |  |  | 2015-07-24 | 2015-07-27 | 2015-11-04 |  | 2015-03-30
South Island | OTG | 1200 | OTG-069-004 | Springvale | OTG-069-004-A | Springvale VF colo | Central Otago | 21 | TIER_4 | ACTIVE | COLO | DU | COLO |  | INLINE | COLO |  |  |  | -45.2316 | 169.4154 | [6 empty] | FALSE | FALSE | 2014-12-16 |  | TRUE |  | 2012-04-13 | 2012-04-12 | 2012-05-01 | 2012-04-26 | 2012-05-28 | 2012-05-29 | 4 | 2015-03-27 | 2015-04-29 | 2015-06-22 | 2015-06-25 | 2015-08-07 | 2015-08-06 |  | 2015-08-07 |  | PERMITTED | 2012-08-30 | 2015-05-15 | 2012-09-27 | 2015-05-15 | 4 |  | 2012-08-06 | 2015-05-15 | 2015-05-15 | 2015-07-17 | 2015-07-21 | 2 |  |  | 2015-08-04 | 2015-09-09 |  |  | 2015-07-31 |  | 2015-08-31 | 2015-09-08 | 2015-10-09 | 2015-10-12 | 2015-09-22 | 2015-10-07 | 2015-10-14 | 2015-09-09 | [7 empty] | 2015-10-15 | 2015-10-30 | 2015-10-26 |  |  |  |  | Permitted if <20m. Flat ground easy access, VF lease expires May 2015. 23/05 Awaiting structural reassessment. Requires extra battery cabinet. 28/05 Colo app submitted. Lightening rod exceeds permitted height. 02/07 Need DoV for Vf for our Lease. 23/7 New Wo2 required for additional PSU. 6/08 Confirm approach with LL. 30 Apr 2015 colo application submitted DMR to Clyde. 12 May Preliminary acceptance received. Lease delayed due to VF releasing terms. Vol4 date pushed out as lease delay prevented submission of Project Plan | VNZ | 2015-10-18 |  |  | 2015-08-19 | 2015-08-19 | 2015-09-09 | 2015-09-09 | 2015-09-18 | 2015-09-21 | 2015-10-21 | 2015-10-23 | 2012-06-21 | MEDIUM | OTAGO |  |  | BUILD | 2015-09-14 | TRUE | 2015-07-20 | 2228531 | 5546812 | Off Ferris Road Alexdendra |  | Permitted if <20m - 17/05/2012 | CELLSITE |  |  |  | ROAMING |  |  | 2015-05-18 | 2015-06-12 | 2015-06-12 |  |  |  |  | 2015-07-10 | 2015-07-03 | 2015-10-26 |  | 2012-04-26
South Island | CAN | 700 | CAN-065-001 | Fairlie | CAN-065-001-B | Fairlie Hilltop GF | Mackenzie District | 21 | TIER_4 | ACTIVE | GF | DU | T2 20 RH |  | INLINE | STANDALONE | 20 | 20 | 2 | -44.0472 | 170.8741 |  | 2012-01-23 |  |  |  |  | FALSE | FALSE |  |  | FALSE |  | 2012-02-23 | 2012-02-23 | 2012-03-29 | 2012-03-27 | 2012-05-15 | 2012-05-16 | 2 | 2012-05-15 | 2015-05-22 | 2015-07-03 | 2015-07-13 | 2015-07-31 | 2015-07-29 | 1 | 2015-08-14 | 2015-08-11 | PERMITTED | 2015-05-25 | 2015-05-26 | 2015-07-24 | 2015-07-24 | 2 | 2015-06-19 | 2015-08-17 | 2015-05-22 | 2015-05-22 | 2015-07-24 | 2015-08-06 | 1 |  |  | 2015-08-06 | 2015-10-23 |  |  |  |  | 2015-10-12 | 2015-10-12 | 2015-11-03 | 2015-11-03 | 2015-10-21 | 2015-11-13 | 2015-11-03 | 2015-08-28 | [7 empty] | 2015-11-09 | 2015-11-15 | 2015-11-12 |  |  |  |  | Existing poles were gained with affected party approval. Power – transformer adjacent to TC and access is via TC easement. 26/03 Now proceeding with GF due to colo costs/risks. 14/05 no LOS achieved waiting for Chorus pricing for fibre. 21/05 Site at risk due to budget + LOS + access costs. 29/05 SA to add condition to lease for easement over neighbours land. Co-siting apps sent to Vf & Telecom 15/6, including easement request to Telecom. Budget cut, site now hard-match only. 16/7 SA to chase response to terms from Akld. 23/7 SA to check & Akd if site proceeding. 13/8 Vic to update situation. Unknown why VF colo dropped - GF will be opursued as we already have a PD which will save at least 4 weeks in the program. Boundary survey required due to easements. 4 Jun - terms agreed removed complications with Clearspan delaying lease. Access for geotech delays CD |  | 2015-11-10 |  |  | 2015-09-29 | 2015-09-29 | 2015-10-22 | 2015-10-23 | 2015-11-03 | 2015-10-28 | 2015-11-11 | 2015-11-09 | 2012-02-08 | LOW | TIMARU_ASHBURTON |  |  | BUILD | 2015-10-26 | FALSE |  | 2339656 | 5682312 | Off Mt Michael Road Fairlie |  | Permitted height 20m - 02/03/2012 | CELLSITE |  |  |  | ROAMING |  | 2015-05-05 | 2015-05-08 | 2015-07-10 | 2015-06-25 |  |  |  |  | 2015-09-04 | 2015-09-03 | 2015-11-20 |  | 2012-03-27
South Island | CAN | 705 | CAN-065-006 | Fairlie Exchange | CAN-065-006-A | Telecom Exchange Fairlie | Mackenzie District | 21 | TIER_4 | ACTIVE | COLO | TX | COLO |  |  | COLO | [11 empty] | FALSE | FALSE |  |  | FALSE |  | 2015-02-19 | 2015-02-19 | 2015-06-05 | 2015-06-04 | 2015-06-26 | 2015-06-22 | 1 |  | 2015-06-22 | 2015-07-10 | 2015-07-01 | 2015-07-31 | 2015-07-01 |  | 2015-08-14 |  | PERMITTED | 2015-06-30 | 2015-06-30 | 2015-07-28 | 2015-07-22 | 1 | 2015-07-28 | 2015-08-17 | 2015-07-24 | 2015-07-20 | 2015-09-03 | 2015-09-07 | 1 |  |  | 2015-09-07 | [5 empty] | 2015-10-12 | 2015-11-03 | 2015-10-25 | 2015-11-03 | 2015-11-03 | 2015-10-28 | 2015-11-03 | 2015-08-28 | [8 empty] | 2015-11-15 | 2015-11-12 |  |  |  |  | Ownership of mast to be confirmed, Spark and VF dishes are on the mast. Opus undertaking structural assessment 20 May. Site build will be concurrent with Fairlie site | [8 empty] | 2015-10-25 | 2015-11-04 | 2015-11-06 | 2015-11-12 | 2015-07-22 | LOW | TRANSMISSION_ONLY | 2015-08-07 |  | BUILD | 2015-10-25 | FALSE |  |  |  | Fairlie |  |  | TXSITE |  |  |  | ROAMING |  |  | 2015-05-08 | 2015-08-27 | 2015-08-27 |  |  |  |  | 2015-09-04 | 2015-09-04 |  |  | 2015-06-04
South Island | CAN | 715 | CAN-066-007 | St Andrews RBI | CAN-066-007-A | St Andrews RBI | Waimate District | 21 | TIER_4 | ACTIVE | RBI | DF |  |  |  | COLO | 25 | 25 |  | -44.5006 | 171.165 | [6 empty] | FALSE | FALSE |  |  | FALSE |  | 2015-07-12 | 2015-07-12 | 2015-07-30 | 2015-07-24 | 2015-07-31 | 2015-08-18 | 1 |  | 2015-08-18 | 2015-08-21 | 2015-08-05 | 2015-09-07 | 2015-08-27 |  | 2015-09-08 |  | PERMITTED | 2015-08-07 | 2015-08-19 | 2015-08-18 | 2015-08-19 | 1 | 2015-08-21 | 2015-08-13 | 2015-07-27 | 2015-07-27 | 2015-08-27 | 2015-08-27 | 1 |  |  | 2015-08-27 | [5 empty] | 2015-11-09 | 2015-11-04 | 2015-11-13 | 2015-11-04 |  | 2015-11-13 | 2015-11-11 | 2015-09-18 |  | 2015-09-04 | [5 empty] | 2015-11-17 | 2015-11-24 | 2015-11-24 |  |  |  |  | 5 Aug: fibre ordered 12 Aug: RFS 21 Sept 12 Aug: VF prelim approval received 13 Aug: 866 antennas quote due from George 13 Aug: RMA letter approved from Council | VNZ | 2015-11-12 | [6 empty] | 2015-11-14 | 2015-11-14 | 2015-11-18 | 2015-11-17 | 2015-08-19 | LOW |  | 2015-09-21 |  | BUILD |  | FALSE |  | 2364064 | 5632503 | O'Briens Road, St Andrews |  |  | CELLSITE |  |  |  | ROAMING |  |  | 2015-07-31 | 2015-08-12 | 2015-08-12 | 2015-07-20 | 2015-07-21 | 2015-07-31 | 2015-08-05 | 2015-09-11 | 2015-09-15 | 2015-11-27 | 2015-11-20 | 2015-07-24
South Island | CAN | 650 | CAN-059-013 | Waikuku Beach RBI | CAN-059-013-A | Waikuku Beach RBI | Waimakariri | 21 | TIER_4 | ACTIVE | RBI | DF |  |  |  | COLO | 28 | 28 |  | -43.2804 | 172.6971 | [6 empty] | FALSE | FALSE |  |  | FALSE |  | 2015-07-12 | 2015-07-12 | 2015-08-03 | 2015-08-07 | 2015-08-07 | 2015-08-18 | 1 | 2015-08-11 | 2015-08-18 | 2015-08-14 | 2015-07-31 | 2015-09-21 | 2015-08-27 |  | 2015-09-21 |  | PERMITTED | 2015-08-13 | 2015-08-19 | 2015-08-20 | 2015-08-19 | 1 | 2015-08-20 | 2015-08-19 | 2015-08-21 | 2015-07-28 | 2015-08-26 | 2015-08-11 | 1 |  | 2015-08-13 | 2015-08-11 | [5 empty] | 2015-10-28 | 2015-10-28 | 2015-11-06 | 2015-11-03 | 2015-11-03 | 2015-11-21 | 2015-11-20 | 2015-09-22 |  | 2015-09-11 |  | 2015-09-25 | 2015-11-03 | 2015-09-11 | 2015-11-03 |  | 2015-12-06 | 2015-12-06 |  |  |  |  | 4 Aug: fibre ordered. RFS 28 Aug 10 Aug: TI issued to Huawei 12 Aug: RMA Letter sent to Planner (permitted activity) 13 Aug: Waiting on Spark approval to move antennas 14 Aug: George getting quote for 866 antennas from maser | VNZ | 2015-11-26 | [6 empty] | 2015-11-04 | 2015-11-16 | 2015-12-04 | 2015-12-03 | 2015-08-19 | LOW |  | 2015-08-28 |  | BUILD | 2015-11-03 | FALSE |  | 2485426 | 5769619 | End of Leggitts Road, Waikuku |  |  | CELLSITE |  |  |  | ROAMING |  |  | 2015-10-12 | 2015-08-12 | 2015-08-10 | 2015-07-20 | 2015-07-20 | 2015-07-31 | 2015-08-04 | 2015-09-11 | 2015-09-15 | 2015-12-02 |  | 2015-07-23
South Island | CAN | 663 | CAN-062-009 | Tai Tapu | CAN-062-009-A | Taitapu VF Co-Lo | Selwyn District | 21 | TIER_4 | ACTIVE | COLO | DU | COLO |  | INLINE | COLO |  |  | 1 | -43.6759 | 172.5575 |  |  |  |  | Microwave | CAN-062-011-C | FALSE | FALSE |  |  | FALSE |  | 2012-05-22 | 2012-05-22 | 2012-05-28 | 2012-05-28 |  | 2011-08-16 | 3 | 2012-06-01 | 2015-07-17 | 2015-05-07 | 2015-05-15 | 2015-08-14 | 2015-08-18 | 2 | 2015-08-14 | 2015-08-18 | DISCRETIONARY_FULL |  | 2011-09-01 |  | 2012-01-18 | 2 |  | 2012-01-18 | 2015-05-08 | 2015-04-21 | 2015-08-21 | 2015-08-20 | 2 |  |  | 2015-09-09 | [5 empty] | 2015-11-02 | 2015-11-04 | 2015-11-19 | 2015-11-20 | 2015-11-04 | 2015-11-20 | 2015-11-26 | 2015-09-25 | [7 empty] | 2015-12-01 | 2015-12-09 | 2015-12-09 |  |  |  |  | RC already exists for 18m colo. 01/05 Both LL + VF are inagreement at last. 07/05 Caravan required. NT to talk to Liz S re colo payments. 21/05 PD to go to Rev3. 13 Mar - structural assessment requested - pass. 15 Mar colo application. 24 Apr - prelim notice received. Lease negotiations underway.12 Jun Lease delayed as no sub lease info received yet. VF have rejected colo application, PD modification required | VNZ | 2015-11-26 | 2012-09-04 | 2012-09-04 |  |  |  |  | 2015-11-17 | 2015-11-24 | 2015-12-04 | 2015-12-09 |  |  | CHRISTCHURCH_OUTER |  |  | BUILD | 2015-11-10 | FALSE |  | 2474330 | 5725631 | Christchurch - Akaroa Road Tai Tapu | 7/8/15 lambing season - LO says at least 24 hours notice required for contractors. Says the road will need to be re-shingled if any equipment of a reasonable size is going on the track - apparently this is a deal he has with VF. If its really wet he reckons its doubtful you would get up the track. Don't cause any damage. LO can be very particular so common sense is needed when dealing with him - 07/08/2015 | Outstanding Landscape - 24/01/2012 | CELLSITE |  |  |  | ROAMING |  |  | 2015-05-08 | 2015-05-15 | 2015-05-11 |  |  |  |  | 2015-09-25 | 2015-10-01 | 2015-12-03 |  | 2012-05-28
South Island | STH | 1301 | STH-074-001 | Gore | STH-074-001-B | Gore GF | Gore District | 21 | TIER_4 | ACTIVE | GF | DF |  |  | STACK_A | COSITE |  | 20 |  | -46.1022 | 168.9888 | [6 empty] | FALSE | FALSE |  |  | FALSE |  | 2015-04-09 | 2015-04-08 | 2015-04-17 | 2015-04-17 | 2015-06-15 | 2015-06-15 | 1 |  | 2015-06-15 | 2015-06-19 | 2015-05-01 | 2015-08-07 | 2015-08-06 |  | 2015-08-14 |  | PERMITTED | 2015-06-19 | 2015-06-17 | 2015-07-17 | 2015-07-15 | 1 | 2015-07-24 | 2015-08-17 | 2015-06-26 | 2015-06-25 | 2015-09-04 | 2015-09-21 | 1 |  |  | 2015-09-21 | [5 empty] | 2015-10-22 | 2015-10-23 | 2015-11-30 | 2015-12-01 | 2015-11-03 | 2015-12-02 | 2015-12-01 | 2015-10-16 | [7 empty] | 2015-12-03 | 2015-12-13 | 2015-12-10 |  |  |  |  | VF site no longer the best option - no future capacity available and no LOS to Gore Exchange. Clearspan issues could delay lease. 7 Aug Geotech delays CD |  | 2015-11-09 | [6 empty] | 2015-11-06 | 2015-12-03 | 2015-12-11 | 2015-12-10 | 2012-04-08 | MEDIUM | SOUTHLAND |  |  | BUILD | 2015-11-05 | FALSE |  | 2199772 | 5448628 | Millane Road Gore |  |  | CELLSITE |  |  |  | ROAMING |  | 2015-09-03 | 2015-06-04 | 2015-07-03 | 2015-06-25 |  |  |  |  | 2015-09-18 | 2015-09-21 | 2015-12-11 |  | 2015-04-17
South Island | STH | 1302 | STH-074-002 | Gore Exchange Tx only | STH-074-002-A | Gore Exchange TX only | Gore District | 21 | TIER_4 | ACTIVE | RT | TX | COLO |  |  | COLO |  |  |  | -46.1017 | 168.9437 | [6 empty] | FALSE | FALSE |  |  | FALSE |  | 2015-04-09 | 2015-04-09 | 2015-06-15 | 2015-06-22 | 2015-06-26 | 2015-09-15 | 1 |  | 2015-09-15 | 2015-07-10 | 2015-09-03 | 2015-07-31 | 2015-09-21 |  | 2015-07-31 | 2012-08-26 | PERMITTED | 2015-06-30 | 2015-05-22 | 2015-07-29 | 2015-05-22 | 1 | 2015-07-31 | 2015-05-22 | 2015-08-13 | 2015-08-13 | 2015-09-04 | 2015-10-05 | 2 |  |  | 2015-11-03 | [5 empty] | 2015-10-19 | 2015-11-03 | 2015-11-16 | 2015-11-10 | 2015-11-03 | 2015-12-10 | 2015-12-07 | 2015-10-23 | [8 empty] | 2015-12-13 | 2015-12-10 |  |  |  |  | Ed to check process with Chorus, confirm no resource consent issue for new dish. Include mount design detail in Wo2. 08/10 Drawing required for Resource Consent. 19 Mar - site bought back into project due to loss of Edendale Fronterra. Requires assessment of structure by GHD and rigger. Site must be on air prior to Gore site 20 Nov. No TI issued, work priced as part of Gore site build | [8 empty] | 2015-10-30 |  | 2015-12-11 | 2015-12-10 | 2015-05-22 | LOW | TRANSMISSION_ONLY | 2015-09-18 |  | BUILD | 2015-10-30 | FALSE |  | 2196284 | 5448503 | Corner of SH1 and Civic Ave Gore |  |  | TXSITE |  |  |  | ROAMING |  |  | 2015-05-18 | 2015-09-16 | 2015-08-28 |  |  |  |  | 2015-10-02 | 2015-10-15 |  |  | 2015-06-22
South Island | STH | 1303 | STH-074-003 | Mataura | STH-074-003-B | Mataura VF Colo | Gore District | 21 | TIER_4 | ACTIVE | COLO | DF | COLO |  | INLINE | COLO |  |  |  | -46.2284 | 168.8767 | [6 empty] | FALSE | FALSE |  |  | FALSE |  | 2014-11-20 | 2014-11-21 | 2014-11-27 | 2014-11-21 | 2015-04-03 | 2015-04-16 | 1 |  | 2015-04-16 | 2015-07-03 | 2015-07-13 | 2015-08-14 | 2015-08-26 |  | 2015-08-14 | 2015-08-26 | PERMITTED | 2015-04-17 | 2015-04-21 | 2015-05-15 | 2015-05-15 | 1 | 2015-05-15 | 2015-05-15 | 2015-05-22 | 2015-05-15 | 2015-06-26 | 2015-07-17 | 2 |  | 2015-06-26 | 2015-08-31 | 2015-10-12 |  |  |  |  | 2015-10-01 | 2015-09-10 | 2015-11-06 | 2015-11-05 | 2015-10-16 | 2015-11-27 | 2015-12-03 | 2015-10-16 | [8 empty] | 2015-12-13 | 2015-12-10 |  |  |  |  | VF colo likely possible but Woosh is prefered location. TP status awaiting Council response 8 Oct 2014 - RF need to visit site, VF colo may be better than Woosh colo. Data pack to be requested after visit on 23 Oct. VF colo preferd Phil to order data pack- Ordered. 11 Nov SDP Rx'd RF and Tx input underway for structraul assessment. Assessment passed, may move to PDI without site visit - PDI issued. 6 Jan, Tx options under review, site is subject to Rf review and confirmation. 16 March - PD and strructural assessmnet to be reviewed - new Tx plan in place. 9 Apr - Site solution locked in, Site will need Gore and Gore Exchange for Tx. 21 Apr colo application submitted. Prelim approval 4 May. 4 Jun Lease delayed waiting for VF terms. 27 July - Lease docs from VF are incorrect and have been sent back - this delays lease executed |  | 2015-12-03 |  |  | 2015-10-12 | 2015-10-12 | 2015-10-12 | 2015-10-12 | 2015-10-20 | 2015-10-16 | 2015-12-11 | 2015-12-10 | 2012-04-08 | LOW | SOUTHLAND |  |  | BUILD | 2015-10-15 | FALSE |  | 2191812 | 5434199 | Perkins Road Matuara |  |  | CELLSITE |  |  |  | ROAMING |  |  | 2015-05-18 | 2015-06-26 | 2015-06-25 |  |  |  |  | 2015-09-03 | 2015-09-08 | 2015-11-19 |  | 2014-11-21
South Island | CAN | 706 | CAN-065-007 | Twizel | CAN-065-007-A | VF Colocation | Mackenzie District | 21 | TIER_4 | ACTIVE | COLO | DU | COLO |  | INLINE | COLO |  |  |  | -44.4039 | 170.0332 | [6 empty] | FALSE | FALSE |  |  | FALSE |  | 2014-12-05 | 2014-12-02 | 2015-02-13 | 2015-02-05 | 2015-03-20 | 2015-03-20 | 2 | 2015-03-20 | 2015-10-06 | 2015-05-22 | 2015-05-21 | 2015-07-31 | 2015-08-06 |  | 2015-08-07 |  | DISCRETIONARY_RESTRICT | 2015-03-27 | 2015-03-27 | 2015-04-30 | 2015-04-24 | 1 | 2015-04-30 | 2015-04-24 | 2015-05-08 | 2015-05-15 | 2015-09-03 | 2015-09-07 | 3 |  |  | 2015-11-18 | [5 empty] | 2015-11-23 | 2015-11-25 | 2015-11-29 | 2015-12-01 | 2015-11-25 | 2015-12-04 | 2015-12-10 | 2015-10-16 | [7 empty] | 2015-12-10 | 2015-12-17 | 2015-12-15 |  |  |  |  | Dates assume VF colo is suitable in terms of lease tenure and structural capacity. Site visit required for RF. 11 Nov - VF colo looks good we have SDP. Structural assessmnet passed. DMR route TBC could be Twizel or Omarama exchange Nominals raised for exchanges. Caravan complete 2 Dec site looks good for colo. PDI will be issued when site has been reviewed/confirmed by RF. 4 Jun - VF release of terms delaying lease. This delays date when project plan can be submitted so PO6 date delayed Site will be at risk of weather if constructed in Winter. VF approach will negate the need to install ring frame. Pricing visit and PO6 at risk due to winter site access. We will need to build quicker than contractual dates to complete in year - easy build no headframe required. Site will need to be built faster than contract specifies to be on air in 2015, dates reflect an accelerated build | VNZ | 2015-11-02 |  |  | 2015-11-20 | 2015-11-20 |  |  | 2015-11-30 | 2015-12-03 | 2015-12-14 | 2015-12-15 | 2015-02-20 | LOW |  |  |  | BUILD | 2015-11-25 | FALSE |  | 2273716 | 5640641 | Buscott Station Omarama |  | over 900m in elevation and in ONL - 27/03/2015 | CELLSITE |  |  |  | ROAMING |  |  | 2015-05-12 | 2015-08-14 | 2015-08-14 |  |  |  |  | 2015-10-23 | 2015-10-29 | 2015-12-18 |  | 2015-02-05
South Island | MBN | 1030 | MBN-053-008 | Chorus PN-Picton Exchange CoLo | MBN-053-008-A | Picton Chorus Exchange | Marlborough District | 21 | TIER_4 | ACTIVE | COLO | TX | COLO |  |  | COLO |  |  |  | -41.2909 | 174.0076 | [6 empty] | FALSE | FALSE |  |  | FALSE |  | 2015-02-06 | 2015-03-06 | 2015-03-20 | 2015-03-17 | 2015-04-28 | 2015-04-29 | 1 |  | 2015-04-29 | 2015-05-22 | 2015-06-03 | 2015-05-29 | 2015-06-03 |  | 2015-06-05 | 2015-07-27 | PERMITTED | 2015-05-01 | 2015-05-01 | 2015-05-29 | 2015-05-20 | 1 | 2015-05-29 | 2015-05-20 | 2015-05-04 | 2015-05-06 | 2015-05-22 | 2015-05-29 | 1 |  |  | 2015-05-29 | [5 empty] | 2015-10-27 | 2015-12-07 | 2015-11-11 | 2015-12-07 |  | 2015-11-11 | 2015-12-07 | 2015-06-19 | [8 empty] | 2015-12-17 | 2015-12-17 |  |  |  |  | Awaiting dish position conformation from Chorus. Date changed to align with Mt Freeth build dates. 6 March - Chorus requested a full drawing. Ownership of pole in compound unknown we will have to press on with building mounted pole. Downer will install on variation to the Mt Freeth construction | [8 empty] | 2015-11-11 |  | 2015-11-15 | 2015-12-17 | 2015-02-20 | LOW |  | 2015-06-08 |  | BUILD |  | FALSE |  | 2594378 | 5990170 | Chorus PN-Picton Exchange 14 Waikawa Rd, Picton 7220 |  |  | TXSITE |  |  |  | ROAMING |  |  | 2015-02-09 | 2015-06-05 | 2015-06-05 | [5 empty] | 2015-11-10 |  |  | 2015-03-17
South Island | CAN | 708 | CAN-065-009 | Twizel Site Chorus Tx only col | CAN-065-009-A | Omarama Exchange | Mackenzie District | 21 | TIER_4 | ACTIVE | COLO | TX |  |  |  | COLO | [11 empty] | FALSE | FALSE |  |  | FALSE |  | 2014-12-05 | 2014-12-02 | 2015-06-05 | 2015-06-04 | 2015-07-17 | 2015-07-20 | 1 |  | 2015-07-20 | 2015-07-24 | 2015-07-16 | 2015-08-07 | 2015-07-16 |  | 2015-08-07 |  | DISCRETIONARY_FULL | 2015-07-21 | 2015-07-27 | 2015-08-18 | 2015-08-21 | 1 | 2015-08-25 | 2015-08-21 | 2015-07-21 | 2015-07-20 | 2015-09-03 | 2015-09-14 | 1 |  |  | 2015-09-14 | [5 empty] | 2015-11-16 | 2015-12-07 | 2015-11-20 | 2015-12-07 | 2015-11-20 | 2015-12-04 | 2015-12-07 | 2015-10-09 | [8 empty] | 2015-12-20 | 2015-12-15 |  |  |  |  | Site has monople available for dish but appears there is no fibre, Tx investigating - Fibre confirmed, this site will be best option for Tx to Twizel hilltop. SOA aligned with Twizel site. 20 May Opus carrying out structural assessment. Site will be built along with main Twizel site | [8 empty] | 2015-11-20 |  | 2015-12-09 | 2015-12-15 | 2015-08-21 | LOW |  |  |  | HARDMATCH | 2015-11-20 | FALSE | [6 empty] | TXSITE |  |  |  | ROAMING |  |  | 2015-05-08 | 2015-08-26 | 2015-08-27 |  |  |  |  | 2015-10-23 | 2015-11-13 | 2015-12-10 |  | 2015-06-04
South Island | MBN | 1029 | MBN-053-007 | Mt Freeth | MBN-053-007-B | Mt Freeth GF Co-site | Marlborough District | 21 | TIER_4 | ACTIVE | GF | DU | T2 15 RFH |  | STACK_A | COSITE | 11.7 | 13.7 |  | -41.2963 | 173.9767 |  |  |  |  | Microwave | MBN-053-013-A | FALSE | FALSE |  |  | FALSE |  | 2012-03-22 | 2012-03-21 | 2012-04-02 | 2012-04-02 | 2012-07-04 | 2012-07-10 | 2 | 2012-07-04 | 2013-04-10 | 2012-08-09 | 2012-08-07 | 2012-12-07 | 2012-12-04 | 1 | 2012-12-07 | 2012-12-04 | PERMITTED | 2012-07-18 | 2012-07-17 | 2012-08-29 | 2012-08-10 | 1 | 2012-08-29 | 2012-08-14 | 2014-11-07 | 2014-11-07 | 2015-02-13 | 2015-02-19 | 1 |  |  | 2015-02-19 | 2015-09-03 |  |  |  |  | 2015-11-06 | 2015-11-03 | 2015-11-30 | 2015-12-07 | 2015-10-27 | 2015-12-03 | 2015-12-07 | 2015-07-07 | [8 empty] | 2015-12-20 | 2015-12-17 |  |  |  |  | Minor tweaks to existing PD may be required - antenna types and azimuths, RF to review. Site to be constructed to accept a taller head frame in future if required. Tx only site will be required at Picton Exchange. Mt Freeth site ready to move to CD when confidence around Tx is known. CDI issued. DMR link to exchange currently critical path. Site need to be confirmed as included in the build program via RF review prior to moving to construction. Date amended to align with expecte Huawei equipment delivery. Construction delayed due to condition of access track |  | 2015-11-16 |  |  | 2015-05-28 | 2015-05-14 | 2015-05-28 | 2015-09-03 | 2015-11-12 |  | 2015-12-17 | 2015-12-17 | 2012-04-02 | LOW | BLENHEIM |  |  | BUILD | 2015-11-10 | FALSE |  | 2591781 | 5989597 | Mt Freeth Scotland Street Picton |  | As long as under height - close to identified ridgeline - 02/04/2012 | CELLSITE |  |  |  | ROAMING |  | 2015-03-13 | 2015-02-09 | 2015-03-30 | 2015-03-30 | [5 empty] | 2015-05-13 | 2015-12-01 |  | 2012-04-02
South Island | OTG | 1207 | OTG-069-011 | Ranfurly | OTG-069-011-B | Kordia colo | Central Otago | 21 | TIER_4 | ACTIVE | COLO | DF | COLO |  |  | COLO | 25 |  |  | -44.9575 | 170.065 | [6 empty] | FALSE | FALSE |  |  | FALSE |  | 2015-03-25 | 2015-03-25 | 2015-04-06 | 2015-04-06 | 2015-05-08 | 2015-05-19 | 1 |  | 2015-05-19 | 2015-06-05 | 2015-05-28 | 2015-06-19 | 2015-05-28 |  | 2015-06-19 | 2015-06-24 | OPW | 2015-05-08 | 2015-05-19 | 2015-06-05 | 2015-05-19 | 1 | 2015-06-05 | 2015-08-17 | 2015-07-17 | 2015-07-30 | 2015-07-24 | 2015-07-30 | 1 |  |  | 2015-07-30 | [5 empty] | 2015-11-23 | 2015-11-03 | 2015-11-28 | 2015-11-03 | 2015-11-03 | 2015-11-26 | 2015-12-10 | 2015-09-11 | [7 empty] | 2015-12-10 | 2015-12-21 | 2015-12-21 |  |  |  |  | Korida colo, plenty of space on mast and in building. Likley DMR link to Clyde via 1.8m dishes if Clyde can support one. 7 Apr - colo application lodged. 18 May - still await Korida response. Price received and accepted, Kordia cannot build until mid Aug. 4 Jun - continue to hard match and ensure all arrangement made but build will likely be delayed until 2016. Date pushed out accordingly |  | 2015-12-02 | [6 empty] | 2015-11-29 | 2015-11-19 | 2015-12-18 | 2015-12-21 | 2015-05-19 | LOW |  |  |  | BUILD | 2015-11-27 | FALSE |  | 2278424 | 5579254 | Little Mount Ida |  | Kordia responsibility - 19/05/2015 | CELLSITE |  |  |  | ROAMING |  |  | 2015-08-03 | 2015-07-23 | 2015-07-23 |  |  |  |  | 2015-08-14 | 2015-08-03 | 2015-12-18 |  | 2015-04-06
South Island | MBN | 988 | MBN-051-007 | Collingwood | MBN-051-007-A | Kordia Colo | Tasman District | 21 | TIER_4 | ACTIVE | COLO | DF | COLO |  | STACK_A | COLO |  |  |  | -40.639 | 172.6407 |  | 2012-01-26 |  |  |  |  | FALSE | FALSE |  |  | FALSE |  | 2012-03-28 | 2012-03-28 | 2015-03-13 | 2015-03-12 | 2015-06-19 | 2015-05-19 | 1 |  | 2015-05-19 | 2015-06-19 | 2015-06-16 | 2015-07-24 | 2015-07-23 |  | 2015-07-24 |  | OPW | 2015-05-08 | 2015-05-19 | 2015-06-05 | 2015-05-19 | 1 | 2015-06-05 | 2015-05-19 | 2015-07-17 | 2015-07-30 | 2015-07-31 | 2015-07-30 | 1 |  |  | 2015-07-30 | [5 empty] | 2015-11-02 | 2015-11-02 | 2015-11-16 | 2015-11-03 | 2015-11-03 | 2015-12-11 |  | 2015-09-25 | [8 empty] | 2015-12-22 | 2015-12-21 |  |  |  |  | 12 Mar Colo application sent to Kordia. 1 May await reply....Kordia chased many times new due date for proposal 15 May - now passed. 1 Jun - still await Kordia response 15 Jun - cost received negotiations on going, high confidence in site going to build. 10 July Cost will have to be accepted to build site, construction time frame TBC by Kordia. 14 Aug, Kordia request design change - investigations underway likely minimum impact | KDA | 2015-11-22 | [6 empty] | 2015-11-16 |  | 2015-12-17 | 2015-12-21 | 2012-04-02 | LOW | NELSON_OUTER |  |  | BUILD | 2015-11-13 | FALSE |  | 2479595 | 6062980 | Mt Burnett, Collingwood |  | Kordia take care of RMA - 02/04/2012 | CELLSITE |  |  |  | ROAMING |  |  | 2015-05-18 | 2015-07-23 | 2015-07-23 |  |  |  |  | 2015-08-03 | 2015-08-03 | 2015-11-30 |  | 2015-03-12
South Island | CAN | 711 | CAN-066-003 | Waimate | CAN-066-003-C | Mt Studholme GF | Waimate District | 21 | TIER_4 | ACTIVE | GF | DU |  |  |  | COSITE |  |  |  | -44.6569 | 170.9242 |  |  |  |  | Microwave | CAN-068-004-A | FALSE | FALSE |  |  | FALSE |  | 2014-12-03 | 2014-12-03 | 2015-03-06 | 2015-02-25 | 2015-04-03 | 2015-04-15 | 1 |  | 2015-04-15 | 2015-05-15 | 2015-05-15 | 2015-09-25 | 2015-10-02 |  | 2015-10-02 |  | DISCRETIONARY_RESTRICT | 2015-04-14 | 2015-04-23 | 2015-05-29 | 2015-05-05 | 1 | 2015-06-05 | 2015-05-13 | 2015-06-12 | 2015-06-12 | 2015-09-25 | 2015-09-30 | 3 |  |  | 2016-01-27 | [5 empty] | 2015-11-09 | 2015-11-09 | 2015-12-04 |  | 2015-11-20 | 2015-12-11 |  | 2015-10-19 | [8 empty] | 2015-12-23 | 2015-12-23 |  |  |  |  | VF colo failed strutural review. This GF site is dependent on RF review and confirmation of site requirement. Dates are provisional. Land has been transfered to DOC - this could be problematic, VF structural failed assessment, 2Degrees will need its own tower. ON AIR WILL BE DELAYED IF BIG HILL NOT ACCELERATED. Tx solution changed to allow Waimate to be built without Big Hill. 4 Jun Lease delayed as DOC requested additional information. 14 July - lack of access for geotech drill delays CD. 9 Oct - site will need to be built in less than contracted amount of time. Pile cost check delaying issue of PO6 |  | 2015-11-24 | [6 empty] | 2015-12-04 |  | 2015-12-15 | 2015-12-23 |  | LOW |  |  |  | BUILD | 2015-11-20 | FALSE |  | 2345349 | 5614687 | Mt Studholme Studholme Road Waimate | Department of Conservation (DoC) site - access through Chorus title. 10 year non notified license obtained from DoC. - 02/10/2015 | Discretionary as over 900m and > 7m in height - 20/02/2015 | CELLSITE |  |  |  | ROAMING |  | 2015-07-08 | 2015-08-03 | 2015-07-24 | 2015-06-25 |  |  |  |  | 2015-10-23 | 2015-10-27 | 2015-12-13 |  | 2015-02-25
South Island | CAN | 707 | CAN-065-008 | Tekapo | CAN-065-008-A | VF Co-site Mt John | Mackenzie District | 21 | TIER_4 | ACTIVE | GF | DF | SP |  | INLINE | COSITE |  |  |  | -43.9855 | 170.4648 |  |  |  |  | Fibre Optic |  | FALSE | FALSE |  |  | FALSE |  | 2014-11-07 | 2014-11-06 | 2014-11-21 | 2014-11-20 | 2015-05-01 | 2015-04-30 | 7 |  | 2015-09-16 | 2015-03-27 | 2015-03-13 | 2015-10-23 | 2015-10-29 |  | 2015-10-23 |  | DISCRETIONARY_RESTRICT | 2015-05-06 | 2015-05-15 | 2015-08-28 | 2015-08-25 | 6 | 2015-08-31 | 2015-08-25 | 2015-06-26 | 2015-06-25 | 2015-09-24 | 2015-09-24 | 1 |  |  | 2015-09-24 | [5 empty] | 2015-11-16 |  | 2015-12-11 |  |  | 2016-01-15 |  | 2015-10-30 | [8 empty] | 2016-01-14 | [5 empty] | Site search confirmed site Ok for RF and Tx - caraven to be arranged, a fair amount of structural design work required for antenna mounts. Site visit with GHD TBC for PDs. Tx working on FO solution. Caravan with GHD structural spt - 6 Nov. 11 Nov caravan complete, some complications with VF and cafe lease areas, under review prior to PDI. PDI issued Rev ) PD requires amendment, Plumes and public areas need careful consideration. 6 Mar - drg to be revised with taller antenna pole 9 Feb - Site visit required to determine RF exposure with proposed antennas hieghts- 20 Feb visit carried out, PD to be tweaked to raise 1 antenna. 4 Jun lease execution delayed university now questioning design which could be problematic. 6 July - new design now being questioned by university! 14 July - Design agreed, VF approval to use ducting still outstanding - confirmed. Oct - Fibre issue still delays lease, site may be excluded from program, price available, site will need to be built faster than contract dates to be on air in 2015. 15 Oct Site not confirmed for build |  | 2015-10-15 | [8 empty] | 2016-01-08 |  | 2015-05-15 | LOW |  |  |  | ONHOLD | 2015-10-28 | FALSE |  | 2306660 | 5688243 | Mt John Observatory Tekapo |  |  | CELLSITE | WIPACTIVE |  |  | ROAMING |  |  |  | 2015-09-07 | 2015-09-14 |  |  |  |  | 2015-10-23 |  | 2015-10-22 |  | 2014-11-20
South Island | MBN | 998 | MBN-051-018 | Motueka South | MBN-051-018-A | TBC - New Site | Tasman District | 21 | TIER_9 | ACTIVE | [17 empty] | FALSE | FALSE |  |  | FALSE |  | 2015-07-24 |  | 2015-07-31 |  | 2015-08-28 |  |  |  |  | 2015-09-18 |  | 2015-10-30 |  |  | 2015-11-06 |  |  | 2015-09-04 |  | 2015-10-02 |  |  |  |  | 2015-09-21 |  | 2015-10-30 | [10 empty] | 2015-12-01 |  | 2016-01-01 |  |  | 2016-01-27 | [10 empty] | 2016-01-22 | [5 empty] | Resources to start limited by roaming commitment |  | 2016-01-28 | [8 empty] | 2016-02-01 |  |  |  |  | 2015-12-11 |  | HARDMATCH | 2016-01-01 | FALSE | [6 empty] | CELLSITE | WIPACTIVE |  |  | CAPACITY | [11 empty] | 2016-02-04
South Island | MBN | 1040 | MBN-053-018 | Seddon Exchange colo | MBN-053-018-A | Chorus Exchange | Marlborough District | 21 | TIER_4 | ACTIVE | COLO | TX |  |  |  | COLO | [9 empty] | Fibre Optic | WLG-047-071-A | FALSE | FALSE |  |  | FALSE |  | 2015-03-04 | 2015-03-04 | 2015-06-22 | 2015-06-24 | 2015-08-21 | 2015-08-14 | 1 |  | 2015-08-14 | 2015-08-28 | 2015-08-24 | 2015-08-31 | 2015-08-24 |  | 2015-09-04 |  | PERMITTED | 2015-08-26 | 2015-08-19 | 2015-09-23 | 2015-09-10 | 1 | 2015-09-25 | 2015-09-15 | 2015-08-24 | 2015-08-24 | 2015-09-11 | [10 empty] | 2015-12-14 |  | 2015-12-18 |  |  | 2016-01-08 |  | 2015-11-06 | [8 empty] | 2016-01-29 | [5 empty] | Tx site for Seddon, we may move to an RSR solution. RSR solution expensive to build even though rent free. Exchange mounted antenna option to be pursued. Current timeframes meet the VF colo option if lease can be agreed. If we move to GF site timeline for exchange work will be extended | [10 empty] | 2016-01-22 |  | 2015-08-19 | LOW | TRANSMISSION_ONLY | 2015-10-16 |  | HARDMATCH |  | FALSE |  |  |  | Richmond St Seddon |  |  | TXSITE | WIPACTIVE |  |  | ROAMING |  |  |  | 2015-10-30 | [5 empty] | 2015-11-27 |  |  |  | 2015-06-24
South Island | MBN | 1039 | MBN-053-017 | Seddon | MBN-053-017-B | VF Colo | Marlborough District | 21 | TIER_4 | ACTIVE | COLO | DF |  |  |  | COLO |  |  |  | -41.6895 | 174.0497 | [6 empty] | FALSE | FALSE |  |  | FALSE |  | 2015-04-10 | 2015-03-04 | 2015-04-17 | 2015-04-02 | 2015-05-15 | 2015-05-04 | 1 |  | 2015-05-04 | 2015-07-29 | 2015-07-28 | 2015-11-27 |  |  | 2015-11-27 |  | PERMITTED | 2015-05-08 | 2015-05-08 | 2015-06-05 | 2015-05-27 | 1 | 2015-06-12 | 2015-06-08 | 2015-07-17 | 2015-07-15 | 2015-08-19 | 2015-08-13 | 1 |  |  | 2015-08-13 | [5 empty] | 2015-11-30 |  | 2015-12-18 |  |  | 2016-01-22 |  | 2015-10-14 | [8 empty] | 2016-02-03 | [5 empty] | searches to be completed 5 March - VF colocation to be pursued. A new nominal for Tx linking to Seddon Chorus exchange will be required. VF SDP requested. 18 MAr - Structural assessment requested. 2 Apr - assessment passed PDI issued. & May colo application lodged. Site dropped from program, lease executed target date pushed out as far as possible without colocation process breach. we need to decide if we hardmatch or drop site completely by end of Nov Dates amended to reflect that | VNZ | 2015-11-21 | [8 empty] | 2016-01-28 |  | 2015-02-20 | LOW |  |  |  | ONHOLD | 2015-11-30 | FALSE |  | 2597374 | 5945862 | Off Marama Road |  | if under 25m - 20/02/2015 | CELLSITE | WIPACTIVE |  |  | ROAMING |  |  |  | 2015-07-17 | [5 empty] | 2015-10-30 |  | 2015-11-29 |  | 2015-04-02
South Island | CAN | 671 | CAN-062-017 | Rolleston South | CAN-062-017-B | Orion - Burnham School Rd | Selwyn District | 21 | 2015P | ACTIVE | RSR | DU | P4L |  | INLINE |  | 16 | 16 | 1 | -43.6076 | 172.3574 |  | 2014-07-08 |  |  |  |  | FALSE | FALSE |  |  | FALSE |  | 2012-07-05 | 2012-07-05 | 2012-07-11 | 2012-07-10 | 2015-09-30 | 2012-09-18 | 2 |  | 2015-06-05 | 2012-08-10 | 2012-07-09 | 2012-10-12 | 2012-10-17 |  | 2015-10-29 |  | DISCRETIONARY_FULL | 2015-06-08 | 2012-10-17 | 2015-07-06 | 2012-11-06 | 1 | 2015-10-30 |  | 2015-04-17 | 2015-04-15 | 2015-11-12 |  | 1 | [8 empty] | 2016-01-11 |  | 2016-02-12 |  |  | 2016-02-26 |  | 2016-02-19 | [8 empty] | 2016-02-11 | [5 empty] | 02/07 Support from council. 23/7 Feedback from Council is 16m max height. Rf to confirm if acceptable. L.O.S. OK to Rolleston. 30/7 Waiting for plans from Ritchie. 16M height restriction. 03/09 SF to chas Ritchie for drawings for Orion Site. 10/9 Ritchie to generate Orion drawings. 17/9 Lodge for RMA. 15/10 Hardmatch only. 16 Mar - Resource to continue limited by roaming commitments 22 May - Cabs need to move, new PD new Telco act notice required. Connectics lighting assessment required. 27 July - GPR results show pole needs to be moved and PD amended to avoid underground cables | [10 empty] | 2016-03-04 |  | 2012-09-04 | MEDIUM | TIER_1_INFILL |  |  | ONHOLD | 2016-01-18 | TRUE | 2015-12-11 | 2458131 | 5733116 | Cnr Burnham School Road and Dunns crossing Road Rolleston |  | 15m permitted - 26/06/2012 | CELLSITE | WIPACTIVE |  |  | CAPACITY | [9 empty] | 2015-12-11 |  | 2015-09-01
South Island | WST | 1713 | WST-055-004 | Westport Outer | WST-055-004-A | Kordia colo | Buller District | 21 | TIER_4 | ACTIVE | COLO | DF |  |  | INLINE | COLO | 20 | 45 | 1 | -41.7788 | 171.7406 |  | 2015-02-26 |  |  |  |  | FALSE | FALSE |  |  | FALSE |  | 2012-03-08 | 2012-03-08 | 2015-03-17 | 2015-03-16 | 2015-06-22 | 2015-07-30 | 1 |  | 2015-07-30 | 2015-05-29 | 2015-05-28 | 2015-06-05 | 2015-05-28 |  | 2015-08-28 |  | PERMITTED | 2015-05-22 | 2015-08-13 | 2015-05-29 | 2015-08-13 | 1 | 2015-05-29 | 2015-08-13 | 2015-07-17 | 2015-07-30 | 2015-08-28 | 2015-07-30 | 1 |  |  | 2015-07-30 | [5 empty] | 2015-12-14 |  | 2016-01-29 |  |  | 2016-02-12 |  | 2015-10-16 | [8 empty] | 2016-02-25 | [5 empty] | SPM to request Kordia prices. - under action. No dates in sitebase because Kordia plod through these milestones on their timeline. SPM to put together a brief to loose this nominal due to coverage gained in Westport town. 21/05 Comments sent to Kordia on colo price/proposal. SITE on HOLD 12 Mar- Kordia colo app submitted 4 Jun - kordia proposal accepted issues with filtering to be resolved. Kordia working with 3rd party to change STL link frequency. Build dates will be dependant on Kordia. Delays in Kordia resolving the STL ink issues. Oct - solution for STL links available. Site has been removed from build program, dates pushed out and set as hardmatch only | KDA | 2015-08-24 | [8 empty] | 2016-02-19 |  | 2012-01-23 | LOW | GREYMOUTH_WESTPORT |  |  | ONHOLD |  | FALSE |  | 2405288 | 5935677 | Mt Rochfort Westport |  | Colocation on existing Kordia designated hilltop base station - good option - 30/01/2012 | CELLSITE | WIPACTIVE |  |  | ROAMING |  |  |  | 2015-07-31 | [5 empty] | 2015-11-27 |  | 2015-08-31 |  | 2015-03-16
South Island | WST | 1715 | WST-055-006 | Reefton Tx Exchange colo | WST-055-006-A | Chorus Exchange | Buller District | 21 | TIER_4 | ACTIVE | COLO | TX |  |  |  | COLO | [11 empty] | FALSE | FALSE |  |  | FALSE |  | 2015-03-10 | 2015-03-10 | 2015-03-23 | 2015-03-23 | 2015-04-17 | 2015-04-16 | 1 |  | 2015-04-16 | 2015-10-30 |  | 2015-11-20 |  |  | 2015-11-20 |  | PERMITTED | 2015-04-24 | 2015-04-23 | 2015-05-22 | 2015-05-11 | 1 | 2015-05-29 | 2015-05-11 | 2015-11-20 |  | 2015-12-11 | [10 empty] | 2016-02-02 |  | 2016-02-26 |  |  | 2016-02-26 |  | 2016-01-15 | [8 empty] | 2016-03-04 | [5 empty] | Tx site for Reefton. Must be ready before Reefton hill site - 25 Oct. May not produce CD dependant on approach for sites to build in 2016. If Reefton site comes into 2015 site list the exchange site can be installed to compliment the main site | [10 empty] | 2016-02-26 |  | 2015-04-24 | LOW | TRANSMISSION_ONLY | 2016-01-15 |  | ONHOLD |  | FALSE |  |  |  | Cnr Bridge Street and Shiel Street Reefton |  |  | TXSITE | WIPACTIVE |  |  | ROAMING |  |  | 2015-05-08 | 2015-12-11 | [5 empty] | 2016-01-15 |  |  |  | 2015-03-23
South Island | OTG | 1204 | OTG-069-008 | Tarras | OTG-069-008-B | VF Colo | Central Otago | 21 | TIER_4 | ACTIVE | COLO |  |  |  |  | COLO |  |  |  | -44.7693 | 169.3807 | [6 empty] | FALSE | FALSE |  |  | FALSE |  | 2015-04-17 | 2015-03-25 | 2015-05-29 | 2015-05-19 | 2015-06-24 | 2015-06-19 | 1 |  | 2015-06-19 | 2015-10-30 |  | 2015-11-27 |  |  | 2015-11-30 |  | PERMITTED | 2015-10-30 |  | 2015-11-27 |  |  | 2015-11-30 |  | 2015-10-27 |  | 2015-11-27 | [10 empty] | 2016-01-11 |  | 2016-02-05 |  |  | 2016-02-12 |  | 2016-01-22 | [8 empty] | 2016-03-08 | [5 empty] | Vf colo is active but may fail, GF options sketched but will be awkward. 28 April Kordia own the IP on the tower and will have to undertake structural assessment - in progress 4 Jun - May delay colocation application and all dates thereafter as acceptance will time expire after 120 days. Site in jeopardy WRT structural assessment - design input required. Rethink required on site design, dates pushed to accommodate 14 Aug - New design referred back to Kordia for assessment. Site will not be delivered in 2015 - #106 Oct - Solution agreed with VF, mast to be detailed and assessed by GHD, new PD in play |  | 2016-01-02 | [8 empty] | 2016-02-29 | [6 empty] | ONHOLD |  | FALSE |  | 2223560 | 5598016 | Tarras hill off Jolly Road SH 8A |  | up to 20m - 22/02/2015. - 22/02/2015 | CELLSITE | WIPACTIVE |  |  | ROAMING |  |  |  | 2015-11-27 | [5 empty] | 2015-12-18 |  | 2016-01-08 |  | 2015-05-19
South Island | OTG | 1272 | OTG-072-002 | Balclutha | OTG-072-002-G | Chorus Colo | Clutha | 21 | TIER_4 | ACTIVE | COLO | DF |  |  |  | COLO |  | 30 |  | -46.2389 | 169.7392 | [6 empty] | FALSE | FALSE |  |  | FALSE |  | 2015-04-03 | 2015-04-09 | 2015-07-24 | 2015-07-23 | 2015-08-21 | 2015-08-18 | 1 |  | 2015-08-18 | 2015-08-19 | 2015-09-07 | 2015-09-11 |  |  | 2015-09-18 |  | PERMITTED | 2015-08-25 | 2015-08-19 | 2015-09-22 | 2015-08-28 | 1 | 2015-09-25 | 2015-08-28 | 2015-09-04 | 2015-09-01 | 2015-11-20 |  | 1 | [8 empty] | 2016-01-18 |  | 2016-02-12 |  |  | 2016-02-26 |  | 2015-11-27 | [8 empty] | 2016-03-10 | [5 empty] | Tower in exchange grounds belongs to Chorus making this candidate active over a GF. GHD need top assess tower for structural capacity. 4 Jun Continue to hard match Chorus colo still possible to construct in year #90 on the build list - to be SOA in 2015. Oct - site removed from build list, hardmatch only, dates pushed out. Need to hang in with Chorus application as long as we can before it is cancelled |  | 2015-12-12 | [8 empty] | 2016-03-03 |  | 2015-08-10 | LOW | OTAGO |  |  | ONHOLD |  | TRUE | 2015-12-11 | 2258332 | 5435991 | James St Balclutha |  |  | CELLSITE | WIPACTIVE |  |  | ROAMING |  |  |  | 2015-11-20 | [5 empty] | 2015-12-18 |  | 2015-12-20 |  | 2015-07-23
South Island | STH | 1320 | STH-075-016 | RBI - Lorneville | STH-075-016-A | Lorneville RBI | Invercargill City | 25 | TIER_5 | ACTIVE | RBI | DF | COLO |  | STACK_A | COLO | 28 | 30 |  | -46.3464 | 168.3425 |  |  |  |  | Fibre Optic | OTG-070-015-A | FALSE | FALSE |  |  | FALSE |  | 2015-10-15 | 2015-10-15 | 2015-10-16 | 2015-10-16 | 2015-10-19 | 2015-11-02 | 1 | 2015-10-20 | 2015-11-02 | 2016-01-18 | 2015-11-24 | 2016-01-20 | 2015-11-26 |  | 2016-02-05 | 2016-02-04 | PERMITTED | 2015-12-04 | 2015-12-04 | 2015-12-11 | 2015-12-09 | 1 | 2015-12-15 | 2015-12-09 | 2015-11-19 | 2015-11-19 | 2015-11-20 | 2015-12-08 | 1 |  | 2015-11-20 | 2015-12-08 | [5 empty] | 2016-02-22 |  | 2016-02-26 |  |  | 2016-02-26 |  | 2016-02-26 |  | 2016-02-17 |  | 2016-02-10 |  | 2016-01-21 | 2016-01-25 |  | 2016-03-11 | [5 empty] | 19 Oct: Awaiting RF design & co-lo/site forms to be completed 20 Oct: Fibre ordered. RFS 19 Jan 22 Oct: Draft planning letter & lodge co-lo application 5 Dec: VF pre approval granted 7 Dec: ATN ordered. Antenna quote ordered 21 Jan: Waiting on VF approval & HW antenna ETA. 26 Jan: Project Plan submitted to VF. 29 Jan: Build approval received 10 Feb: CX Config raised for 17th Feb | VNZ | [9 empty] | 2016-03-04 |  |  |  |  | 2016-02-23 |  | BUILD | 2016-02-19 | FALSE |  | 2151413 | 5418905 | 49 Wallacetown-Lorneville Highway |  | Letter to confirm compliance sent to Council - 25/01/2016 | CELLSITE |  |  |  | ROAMING |  |  | 2016-02-10 | 2015-11-10 | 2015-11-13 | 2015-10-19 | 2015-10-19 | 2015-10-30 | 2015-10-20 | 2016-01-29 | 2016-02-02 |  |  | 2015-10-15
South Island | CAN | 637 | CAN-058-015 | RBI - Leithfield | CAN-058-015-A | Leithfield RBI | Hurunui District | 25 | TIER_5 | ACTIVE | RBI | DF | RBI Pole |  | STACK_A | COLO | 28 | 30 |  | -43.1971 | 172.735 |  |  |  |  | Fibre Optic | CHC-060-131-A | FALSE | FALSE |  |  | FALSE |  | 2015-09-30 | 2015-09-30 | 2015-10-23 | 2015-10-23 | 2015-10-23 | 2015-11-02 | 1 | 2015-11-02 | 2015-11-02 | 2015-11-30 | 2015-11-24 | 2015-12-03 | 2015-11-26 |  | 2016-02-12 |  | PERMITTED | 2015-11-30 | 2015-11-27 | 2015-12-02 | 2015-11-30 | 1 | 2015-12-04 | 2015-11-30 | 2015-11-16 | 2015-11-16 | 2015-12-04 | 2015-12-07 | 1 |  | 2015-12-04 | 2015-12-07 | [5 empty] | 2016-02-22 |  | 2016-02-26 |  |  | 2016-02-26 |  | 2016-03-04 |  | 2016-02-10 |  | 2016-02-10 |  | 2016-02-03 | 2016-01-26 |  | 2016-03-15 | [5 empty] | 2 Oct - Data pack requested 16 Oct: Fibre ready to order. 19 Oct: Waiting for RF solution. Fibre ordered (100mb/s 30mb/s bandwidth) 20 Oct: ATN BOQ underway. 11 Nov: ATN ordered 16 Dec: Cabinet ordered 1 Dec: RFS date 16 Feb 12 Jan: Waiting on Huawei antennas 27 Jan: Project Plan sent to VF. 3 Jan: Waiting on VF build approval 10 Feb: CX Config raised for 24th Feb | VNZ | [9 empty] | 2016-03-04 |  |  |  |  | 2016-02-23 |  | BUILD | 2016-02-19 | FALSE |  | 2488469 | 5778887 | 64 Terrace Road Leithfield |  | Letter to confirm sent to Council - 25/01/2016 | CELLSITE |  |  |  | ROAMING |  |  | 2016-02-10 | 2015-11-20 | 2015-11-19 | 2015-10-09 | 2015-10-09 | 2015-10-19 | 2015-10-19 | 2015-12-22 | 2015-12-22 |  |  | 2015-10-16
South Island | CAN | 652 | CAN-059-015 | RBI - Swannanoa | CAN-059-015-A | Swannanoa RBI | Waimakariri | 25 | TIER_5 | ACTIVE | RBI | DF | RBI Pole |  | STACK_A | COLO | 28 | 30 |  | -43.3711 | 172.4461 |  |  |  |  | Fibre Optic | CHC-060-131-A | FALSE | FALSE |  |  | FALSE |  | 2015-09-30 | 2015-09-30 | 2015-10-19 | 2015-10-20 | 2015-10-23 | 2015-11-02 | 1 | 2015-11-02 | 2015-11-02 | 2016-01-29 |  | 2016-02-19 |  |  | 2016-02-24 |  | PERMITTED | 2016-01-22 | 2016-01-21 | 2016-01-27 | 2016-01-21 | 1 | 2016-01-29 | 2016-01-21 | 2015-11-17 | 2015-11-19 | 2016-02-12 |  |  |  | 2016-02-16 | [6 empty] | 2016-03-07 |  | 2016-03-11 |  |  | 2016-03-11 |  | 2016-03-11 |  | 2016-02-17 |  | 2016-02-17 |  | 2016-02-23 | 2016-01-25 |  | 2016-03-25 | [5 empty] | 2 Oct - Data pack requested 16 Oct: Fibre pre-qual ordered. 28 Oct: Co-lo & co-site lodged 29 Oct: CD1 Requested 7 Nov: ATN & antennas ordered. Waiting on VF approval. 16 Dec: Updated RF design with new mounts as per VF instructions 12 Jan: Waiting for ETA on antennas 3 Feb: PO6 Issued. Waiting on VF pre-approval & antenna quote. | VNZ | [9 empty] | 2016-03-18 |  |  |  |  | 2016-03-08 |  | BUILD | 2016-03-07 | FALSE |  | 2465120 | 5759439 | Corner of Browns Road & North Eyre Road |  | Letter to confirm compliance sent to Council - 25/01/2016 | CELLSITE |  |  |  | ROAMING |  |  | 2016-02-10 | 2015-11-20 | 2015-11-20 | 2015-10-09 | 2015-10-09 | 2015-11-13 | 2015-11-13 | 2015-12-18 | 2015-12-23 |  |  | 2015-10-16
South Island | STH | 1299 | STH-073-022 | Riverton | STH-073-022-A | Vodafone Co-Lo | Southland District | 21 | TIER_4 | ACTIVE | COLO | DF | COLO |  | STACK_A | COLO | 13.1 | 15 |  | -46.3764 | 168.0182 |  |  |  |  | Fibre Optic | OTG-070-015-A | FALSE | FALSE |  |  | FALSE |  | 2015-04-09 | 2015-04-09 | 2015-05-22 | 2015-05-19 | 2015-07-10 | 2015-06-22 | 3 |  | 2015-07-20 | 2015-08-18 | 2015-08-10 | 2015-10-02 | 2015-09-21 |  | 2015-10-09 | 2015-09-21 | PERMITTED | 2015-07-24 | 2015-07-21 | 2015-08-21 | 2015-08-18 | 3 | 2015-08-25 | 2015-08-25 | 2015-09-04 | 2015-09-02 | 2015-10-06 | 2015-10-12 | 1 |  |  | 2015-10-12 | [5 empty] | 2016-02-05 | 2016-02-02 | 2016-02-20 |  |  | 2016-03-05 |  | 2015-12-02 | [8 empty] | 2016-03-30 | [5 empty] | DMR link to Invercargill has risk with multipath over the water, Riverton will be a fibre connection. | VNZ | [9 empty] | 2016-03-19 |  | 2015-08-25 | LOW |  |  |  | BUILD |  | FALSE |  | 2126692 | 5414105 | Off Lex Street Riverton Southland |  |  | CELLSITE | WIPACTIVE |  |  | ROAMING |  |  | 2016-01-14 | 2015-10-02 | 2015-10-02 |  |  |  |  | 2016-01-15 | 2015-12-22 |  |  | 2015-05-19
South Island | CAN | 651 | CAN-059-014 | RBI - Cust | CAN-059-014-A | Cust RBI | Waimakariri | 25 | TIER_5 | ACTIVE | RBI | DF | RBI Pole |  | STACK_A | COLO | 23 | 25 |  | -43.2749 | 172.3456 |  |  |  |  | Fibre Optic | CHC-060-131-A | FALSE | FALSE |  |  | FALSE |  | 2015-09-30 | 2015-09-30 | 2015-10-16 | 2015-10-16 | 2015-10-19 | 2015-11-02 | 1 | 2015-10-29 | 2015-11-02 | 2015-11-27 | 2015-12-02 | 2015-11-30 | 2015-12-02 |  | 2016-02-12 |  | PERMITTED | 2015-11-30 | 2015-12-02 | 2015-12-03 | 2015-12-03 | 1 | 2015-12-03 | 2015-12-03 | 2015-11-16 | 2015-11-18 | 2015-11-19 | 2015-12-08 | 2 |  | 2015-12-08 | 2016-01-15 | [5 empty] | 2016-03-14 |  | 2016-03-18 |  |  | 2016-03-18 |  | 2016-02-24 |  | 2016-02-24 |  | 2016-03-09 |  | 2016-03-09 | 2016-01-25 |  | 2016-03-31 | [5 empty] | 2 Oct - Data pack requested 16 Oct: Fibre pre-qual ordered. 28 Oct: Co-lo & co-site lodged with VF & Spark 29 Oct: CD1 ordered & Fibre ordered 8 Dec: VF pre approval received. ATN & antennas ordered. 22 Dec: VF PO sent through to order antennas 12 Jan: Waiting on VF & Huawei antenna ETA 26 Jan: Project Plan sent to VF. 3 Feb: PO6 Issued. Waiting on VF final approval & antenna quote. Answering VF query about antenna bracket 10 Feb: CX Config raised for 24th Feb | VNZ | [9 empty] | 2016-03-25 |  |  |  |  | 2016-03-01 |  | BUILD | 2016-03-14 | FALSE |  | 2456892 | 5770069 | 289 Summerhill Road Cust |  | Letter to confirm sent to Council - 25/01/2016 | CELLSITE |  |  |  | ROAMING |  |  | 2016-02-10 | 2015-11-20 | 2015-12-11 | 2015-10-08 | 2015-10-09 | 2015-11-04 | 2015-10-30 | 2016-01-28 | 2016-02-02 |  |  | 2015-10-16
South Island | WST | 1714 | WST-055-005 | Reefton | WST-055-005-C | Reefton Green Field | Buller District | 21 | TIER_4 | ACTIVE | GF |  |  |  | STACK_A | COSITE | 25 | 25 | [9 empty] | FALSE | FALSE |  |  | FALSE |  | 2015-03-10 | 2015-03-10 | 2015-05-21 | 2015-05-21 | 2015-10-09 | 2015-07-29 | 1 |  | 2015-07-29 | 2015-10-23 |  | 2015-11-20 |  |  | 2015-11-27 |  | PERMITTED | 2015-10-13 |  | 2015-11-10 |  |  | 2015-11-12 |  | 2015-10-23 |  | 2015-12-04 | [10 empty] | 2016-02-01 |  | 2016-02-26 |  |  | 2016-03-15 | [10 empty] | 2016-04-04 | [5 empty] | Colo candidate looks like acquisition will be timely and costly on rent. GF option may be more cost effective. Jun 22- GF option to be pursued. Site not in 2015 build list but progressing to hard match. 11 Aug LO ants to move site, there will be a PD re-issue delay site is not scheduled in year #107. Scrub clearing to be arranged, local contractor identified, RF required on site at time of clearing to confirm new mast location | [10 empty] | 2016-03-25 |  | 2015-08-10 | LOW |  |  |  | ONHOLD | 2016-02-01 | FALSE |  |  |  | Victoria Forest Park Off Soldiers Big River Road |  |  | CELLSITE | WIPACTIVE |  |  | ROAMING |  |  |  | 2015-12-07 | [5 empty] | 2016-01-15 |  |  |  | 2015-05-21
South Island | CAN | 673 | CAN-062-019 | RBI - Glentunnel | CAN-062-019-A | Glentunnel RBI | Selwyn District | 25 | TIER_5 | ACTIVE | RBI | DF | RBILATTICE |  | STACK_A | COLO | 28 | 30 |  | -43.4779 | 171.9214 |  |  |  |  | Fibre Optic | CHC-060-131-A | FALSE | FALSE |  |  | FALSE |  | 2015-10-15 | 2015-10-15 | 2015-10-16 | 2015-10-16 | 2015-10-19 | 2015-11-02 | 1 | 2015-10-23 | 2015-11-02 | 2016-02-04 |  | 2016-02-25 |  |  | 2016-02-29 |  | PERMITTED | 2015-12-16 |  | 2016-02-05 |  |  | 2016-01-22 |  | 2015-11-24 | 2015-11-13 | 2016-02-05 |  |  |  | 2016-02-08 | [6 empty] | 2016-04-04 |  | 2016-04-08 |  |  | 2016-04-08 |  | 2016-03-30 |  | 2016-03-23 |  | 2016-03-30 |  | 2016-03-30 | 2016-01-25 |  | 2016-04-21 | [5 empty] | 2 Oct - Data pack requested 16 Oct: Fibre pre-qual ordered. 28 Oct: Co-lo & Co-site applications lodged 29 Oct: CD1 ordered 5 Nov: RF Re-design solution 16 Dec: New RF design required as cannot go on lower level 12 Jan: Waiting for VF approval & quote for antennas. 3 Feb: PO6 Issued. Waiting on VF pre-approval & VF antenna quote. | VNZ | [9 empty] | 2016-04-15 |  |  |  |  | 2016-04-05 |  | BUILD | 2016-04-04 | FALSE |  | 2422748 | 5747166 | White Cliffs Road Glentunnel |  |  | CELLSITE |  |  |  | ROAMING |  |  | 2016-02-10 | 2015-11-20 | 2015-12-10 | 2015-10-13 | 2015-10-13 | 2015-10-07 | 2015-10-27 | 2016-01-22 | 2015-12-22 |  |  | 2015-10-15
South Island | MBN | 1037 | MBN-053-015 | Springlands | MBN-053-015-B | Supermarket RSR | Marlborough District | 21 | 2015P | ACTIVE | RSR | DU5 |  |  | STACK_A | STANDALONE |  |  |  | -41.5092 | 173.9356 |  |  |  |  | Leased Line | WLG-047-071-A | FALSE | FALSE |  |  | FALSE |  | 2015-06-09 | 2015-06-09 | 2015-06-12 | 2015-06-16 | 2015-09-30 | 2015-10-13 | 1 |  | 2015-10-13 | 2015-10-30 | 2015-11-11 | 2015-11-06 | 2015-11-11 |  | 2015-11-06 |  | PERMITTED | 2015-10-02 |  | 2015-10-30 |  |  | 2015-11-06 |  | 2015-11-09 |  | 2015-12-18 |  | 1 | [8 empty] | 2016-02-22 |  | 2016-03-18 |  |  | 2016-04-08 | [10 empty] | 2016-04-22 | [5 empty] | New site - all previous candidates failed. GHD need to attend site. RSR site in play, dates pushed out pending budget to build. Pole change to minimise deflection delays PD |  | 2016-01-12 | [8 empty] | 2016-04-15 |  | 2015-08-10 | MEDIUM |  |  |  | BUILD |  | FALSE |  | 2588086 | 5965991 | Opposite 128 Middle Renwick Road |  |  | CELLSITE |  |  |  | CAPACITY |  |  |  | 2016-01-11 | [5 empty] | 2016-02-05 |  | 2016-01-21 |  | 2015-06-16
South Island | STH | 1287 | STH-073-010 | Winton | STH-073-010-C | Green Field | Southland District | 21 | TIER_4 | ACTIVE | GF | DF | T2 25 RH |  | STACK_A | COSITE | 25 | 25 |  | -46.1176 | 168.3918 |  |  |  |  | Fibre Optic | OTG-070-015-A | FALSE | FALSE | 2015-07-01 |  | FALSE |  | 2015-06-23 | 2015-06-23 | 2015-07-07 | 2015-07-07 | 2015-09-09 | 2015-09-14 | 1 |  | 2015-09-14 | 2015-09-11 | 2015-08-04 | 2015-10-09 | 2015-09-04 |  | 2015-10-16 |  | PERMITTED | 2015-09-29 | 2015-09-29 | 2015-10-30 | 2015-10-28 | 1 | 2015-10-30 | 2015-10-28 | 2015-09-10 | 2015-09-16 | 2016-01-22 | 2016-01-28 | 1 |  |  | 2016-01-28 | [5 empty] | 2016-02-29 |  | 2016-03-31 |  |  | 2016-04-15 | [10 empty] | 2016-05-16 | [5 empty] | 7 Sept - PD delay has shifted SOA into Feb 2016 | [10 empty] | 2016-04-29 |  | 2015-09-29 | LOW | SOUTHLAND |  |  | BUILD |  | FALSE |  | 2153773 | 5444512 | Off Sinclair Road Winton |  |  | CELLSITE | WIPACTIVE |  |  | ROAMING |  | 2016-02-05 | 2015-12-15 | 2015-10-22 | 2015-11-04 |  |  |  |  | 2016-02-26 |  |  |  | 2015-07-07
South Island | OTG | 1221 | OTG-070-014 | Queenstown Central | OTG-070-014-C | Church Street | Queenstown | 21 | TIER_4 | ACTIVE | RT | DU5 | RT |  | INLINE | STANDALONE | 14.6 | 11.9 | 1 | -45.0327 | 168.6613 |  |  |  |  | Fibre Optic | OTG-070-015-A | FALSE | FALSE |  |  | FALSE |  | 2012-12-01 | 2012-12-01 | 2013-02-06 | 2013-02-06 | 2013-02-05 | 2013-02-05 | 5 | 2013-02-05 | 2015-10-08 |  | 2013-03-20 | 2013-05-11 | 2013-06-21 | 4 |  | 2013-06-21 | DISCRETIONARY_FULL | 2015-09-21 | 2015-09-21 | 2015-10-20 | 2015-11-05 | 5 | 2015-10-27 | 2015-11-06 | 2015-09-16 | 2015-09-16 | 2016-02-19 | [10 empty] | 2016-03-31 |  | 2016-04-30 |  |  | 2016-05-13 | [10 empty] | 2016-05-30 | [5 empty] | 15 Oct, pre tender visit to site has been made with PD, once CD is complete pricing can be requested | [10 empty] | 2016-05-27 |  | 2015-09-22 | LOW | TIER_1_INFILL |  |  | BUILD |  | FALSE |  | 2168225 | 5566036 | 11 - 17 Church Street Queenstown |  |  | CELLSITE | WIPACTIVE |  |  | ROAMING |  |  | 2016-01-14 | 2015-10-21 | 2015-11-04 | 2015-09-18 |  |  |  | 2016-03-19 |  |  |  | 2013-01-14
South Island | CAN | 713 | CAN-066-005 | Kurow | CAN-066-005-C | Spark Colo | Waimate District | 21 | TIER_4 | ACTIVE | COLO | DF | COLO |  | STACK_A | COLO |  |  |  | -44.7503 | 170.5617 |  |  |  |  | Microwave | CAN-068-003-B | FALSE | FALSE |  |  | FALSE |  | 2015-03-25 | 2015-03-25 | 2015-07-17 | 2015-07-23 | 2015-08-21 | 2015-08-21 | 1 |  | 2015-08-21 | 2016-02-12 |  | 2016-02-29 |  |  |  |  | PERMITTED | 2015-08-28 | 2015-08-25 | 2015-09-25 | 2015-09-11 | 1 | 2015-09-30 | 2015-10-19 | 2015-10-02 | 2015-10-02 | 2016-01-27 | 2016-01-20 | 1 |  |  | 2016-01-20 | [5 empty] | 2016-05-06 |  | 2016-06-03 |  |  | 2016-06-17 |  | 2015-11-24 | [8 empty] | 2016-07-15 | [5 empty] | Issues with Ownership of tower, Transpower do not know who owns the tower....It is nor Spark or VF, Chorus and Kordia are checking their records.. Chorus think the mast may be theirs.... JUn - I tis a Chorus tower, Chorus request colo application to determine if they have the drawings. 14 Aug Colo application underway, site is outside 2015 build list (#97). 9 Oct Power delivery is complicated, drg under amendment, power from transformer, SA confirm easement not required |  | 2016-01-02 | [8 empty] | 2016-06-30 |  | 2015-08-25 | LOW |  |  |  | BUILD |  | FALSE |  | 2316920 | 5603530 | Off Mchenrys Road Kurow |  |  | CELLSITE | WIPACTIVE |  |  | ROAMING |  |  |  | 2016-03-11 | [5 empty] | 2016-04-29 |  | 2016-01-10 |  | 2015-07-23
South Island | STH | 1300 | STH-073-023 | Woodlands | STH-073-023-A | Woosh Colo | Southland District | 21 | TIER_5 | ACTIVE | COLO | DF | COLO |  |  | COLO | 45 | 50 |  | -46.3668 | 168.5312 |  |  |  |  | Fibre Optic | OTG-070-015-A | FALSE | FALSE |  |  | FALSE |  | 2015-11-30 | 2015-12-07 | 2015-12-23 | 2015-12-23 | 2016-02-19 | 2016-01-22 | 2 |  | 2016-02-10 | 2016-02-26 |  | 2016-03-31 | [5 empty] | 2016-03-25 |  | 2016-04-29 |  |  |  |  | 2016-04-08 |  | 2016-04-29 | [10 empty] | 2016-06-03 |  | 2016-06-17 |  |  | 2016-06-30 | [10 empty] | 2016-07-31 | [5 empty] | 2 Oct Structural assessment underway, if result is positive caravan date could be claimed | [10 empty] | 2016-07-15 | [6 empty] | BUILD |  | FALSE |  | 2166035 | 5417450 |  |  |  | CELLSITE |  |  |  | ROAMING |  |  |  | 2016-05-06 | [5 empty] | 2016-05-31 |  |  |  | 2015-12-23
South Island | CAN | 718 | CAN-068-003 | Big Hill | CAN-068-003-B | VF colo | Waitaki District | 21 | TIER_4 | ACTIVE | COLO | DF | NOPOLE |  | STACK_A | COLO |  |  |  | -44.9823 | 170.9272 |  |  |  |  | Microwave | CAN-068-004-A | FALSE | FALSE |  |  | FALSE |  | 2015-04-24 | 2015-03-25 | 2015-05-18 | 2015-05-19 | 2015-07-09 | 2015-07-09 | 2 |  | 2015-12-17 | 2016-02-05 |  | 2016-03-18 |  |  |  |  | PERMITTED | 2015-07-24 | 2015-07-22 | 2015-08-21 | 2015-08-12 | 1 | 2015-08-28 | 2015-08-13 | 2016-03-23 |  | 2016-04-29 | [10 empty] | 2016-06-03 |  | 2016-06-30 |  |  | 2016-07-04 |  | 2016-01-14 | [8 empty] | 2016-08-12 | [5 empty] | VF colo looks good. Hopefully extend existing lattice structure. DMR links possible to Waimate and Kurow and thereafter to Oamaru outer for fibre connection. Kordia have to undertake structural assessment and provide PS1. Kordia structural assessment underway 18 May. Big Hill is required for Tx for Waimate and Kurow. Big Hill will link to Oamaru. 4 Jun will push on but may not submit colocation application as it will time expire before site is ready to build. 10 Jul - colo application submitted. VF now have future equipment, structurals referred back to kordia. Site in jeopardy for delivery in year, 20 Aug - site dropped from top 90. 14 Sept- VF future requirements delaying design agreement. 9 Oct - Solution agreed with VF, mast will need to be detailed and assessed by GHD, new PD underway |  | 2016-01-02 | [8 empty] | 2016-07-15 |  | 2015-02-22 | LOW |  |  |  | BUILD |  | FALSE |  | 2346490 | 5578544 | Big Hill Quarry Off SH 83 |  | up to 25m - 22/02/2015 | CELLSITE | WIPACTIVE |  |  | ROAMING |  |  |  | 2016-04-15 | [5 empty] | 2016-05-20 |  | 2016-01-10 |  | 2015-05-19
South Island | STH | 1304 | STH-074-004 | Hedgehope | STH-074-004-A | Chorus co-lo | Gore District | 21 | TIER_5 | ACTIVE | COLO | DF | COLO |  | STACK_A | COLO | [9 empty] | Fibre Optic | STH-074-002-A | FALSE | FALSE |  |  | FALSE |  | 2016-02-05 | 2016-02-03 | 2016-02-19 |  | 2016-03-30 |  |  |  |  | 2016-03-18 |  | 2016-05-13 | [5 empty] | 2016-05-06 |  | 2016-05-31 |  |  |  |  | 2016-04-15 |  | 2016-05-13 | [10 empty] | 2016-06-24 |  | 2016-07-15 |  |  | 2016-07-31 | [10 empty] | 2016-08-30 | [6 empty] | TNZ | [9 empty] | 2016-08-12 | [6 empty] | BUILD |  | FALSE |  |  |  | Access off 1197 Waimea Highway at Otamita |  |  | CELLSITE |  |  |  | ROAMING |  |  |  | 2016-05-13 | [5 empty] | 2016-06-10
South Island | MBN | 997 | MBN-051-017 | Kaiteriteri | MBN-051-017-F | GF - TNZ Co-site | Tasman District | 21 | TIER_5 | ACTIVE | GF | DF | SP |  | STACK_A | COSITE |  | 25 |  | -41.0445 | 173.0122 |  |  |  |  | Microwave | MBN-051-004-A | FALSE | FALSE |  |  | FALSE |  | 2015-12-04 | 2015-12-08 | 2015-12-23 | 2015-12-23 | 2016-02-12 | 2016-01-21 | 2 |  | 2016-01-21 | 2016-02-12 |  | 2016-04-29 |  |  |  |  | DISCRETIONARY_FULL | 2016-04-01 |  | 2016-04-29 |  |  |  |  | 2016-04-08 |  | 2016-05-20 | [10 empty] | 2016-06-01 |  | 2016-07-15 |  |  | 2016-07-29 | [10 empty] | 2016-08-31 | [16 empty] | 2016-08-12 |  | 2012-04-02 | HIGH | NELSON_OUTER |  |  | BUILD |  | TRUE |  | 2511008 | 6018018 |  |  | VA Required Consent triggered by height, Rec Zone height and Cultural Significance - 02/04/2012 | CELLSITE |  |  |  | ROAMING |  |  |  | 2016-04-28 | [5 empty] | 2016-05-27 |  |  |  | 2015-12-23
South Island | CAN | 699 | CAN-064-017 | Clandeboye | CAN-064-017-A | Community hall | Timaru | 21 | TIER_5 | ACTIVE | GF | DF | SP |  |  | STANDALONE | 34 | 35 |  | -44.211 | 171.3798 | [6 empty] | FALSE | FALSE |  |  | FALSE |  | 2016-02-05 | 2016-02-02 | 2016-02-19 |  | 2016-03-30 |  |  |  |  | 2016-03-04 |  | 2016-04-29 | [5 empty] | 2016-04-01 |  | 2016-04-29 |  |  |  |  | 2016-05-06 |  | 2016-05-31 | [10 empty] | 2016-07-01 |  | 2016-07-31 |  |  | 2016-08-12 | [10 empty] | 2016-09-09 | [16 empty] | 2016-08-26 | [6 empty] | BUILD |  | FALSE |  | 2380520 | 5665020 | 1066 Milford Clandeboye Road |  |  | CELLSITE |  |  |  | ROAMING |  |  |  | 2016-06-01 | [5 empty] | 2016-06-30
South Island | STH | 1278 | STH-073-001 | Fonterra Edendale | STH-073-001-B | Scenic Reserve Road | Southland District | 21 | TIER_5 | ACTIVE | GF | DF | SP |  | STACK_A | STANDALONE |  |  |  | -46.3079 | 168.7847 |  |  |  |  | Microwave | STH-074-002-A | FALSE | FALSE |  |  | FALSE |  | 2016-02-05 | 2016-02-04 | 2016-02-19 |  | 2016-03-30 |  |  |  |  | 2016-03-04 |  | 2016-04-29 |  |  |  |  | DISCRETIONARY_FULL | 2016-04-08 |  | 2016-04-29 |  |  |  |  | 2016-04-15 |  | 2016-05-30 | [10 empty] | 2016-07-08 |  | 2016-08-12 |  |  | 2016-08-26 | [10 empty] | 2016-09-30 | [5 empty] | new candidate for forecasting as Fonterra candidate is not possible. SMT to meet with Fonterra | [10 empty] | 2016-09-16 |  | 2015-02-20 | LOW |  |  |  | BUILD |  | TRUE |  | 2185181 | 5425016 | 25 Scenic Reserve Road |  | Discretionary if over 20m - 20/02/2015 | CELLSITE | WIPACTIVE |  |  | ROAMING |  |  |  | 2016-05-27 | [5 empty] | 2016-06-30
South Island | MBN | 1027 | MBN-053-005 | Kaituna | MBN-053-005-A | Kaituna VNZ CoLo | Marlborough District | 21 | TIER_4 | ACTIVE | COLO | DF | COLO |  | STACK_A | COLO | 23 | 20 | 1 | -41.4347 | 173.8149 |  |  |  |  | Microwave | MBN-053-004-A | FALSE | FALSE |  |  | FALSE |  | 2015-03-06 | 2015-03-04 | 2015-03-31 | 2015-03-30 | 2015-04-30 | 2015-04-28 | 2 |  | 2015-04-28 | 2015-10-30 |  | 2015-12-11 |  |  | 2015-12-11 |  | PERMITTED | 2015-05-07 | 2015-04-30 | 2015-06-04 | 2015-05-20 | 2 | 2015-06-05 | 2015-05-26 | 2015-06-05 | 2015-05-15 | 2015-08-07 | 2015-07-21 | 1 |  |  | 2015-07-21 | [21 empty] | 2017-01-13 | [5 empty] | SDP requested, PD in existance. New structurals and 4 port antenna change required. GF would be very trick to build. 12 Mar - Structuiral assessment requested. 27 Mar structural passed - 30 Mar PDI issued. 30 Apr Colo app submitted, 12 May prelim acceptance from VF 4 Jun lease delayed waiting on VF terms. 24 Jun - If VF delay much more build date will slip. Lease in jeopardy, VF negotiating lease extension, Spark negotiating extended tenure for power easement. Site unlikely to be on air in 2015 | VNZ | [11 empty] | 2012-04-02 | LOW | BLENHEIM |  |  | ONHOLD |  | FALSE |  | 2578092 | 5974362 | Storey's Creek Road Okaramio Marlborough |  |  | CELLSITE | WIPACTIVE |  |  | ROAMING |  |  |  | 2015-11-13 | [9 empty] | 2015-03-30
South Island | CAN | 623 | CAN-054-003 | Kaikoura Telecom Exchange |  |  | Kaikoura District |  | TIER_9 | [83 empty] | Transmission site only
0 | MNW | 1041 | MNW-036-001 |  |  |  | Ruapehu District |  | TIER_9
0 | MNW | 1042 | MNW-036-002 | Taumarunui | MNW-036-002-A | Taumarunui | Ruapehu District | 24 | TIER_4 | ACTIVE | GF | DU | T2 20 UF | Grey | STACK_A | STANDALONE | 19.5 | 20 |  | -38.8837 | 175.2621 |  | 2015-04-15 |  | 2015-04-15 | Fibre Optic | WKT-016-023-B | FALSE | FALSE |  |  | FALSE |  | 2015-03-06 | 2015-03-06 | 2015-03-06 | 2015-03-06 | 2015-03-06 | 2015-03-06 | 1 | 2015-03-06 | 2015-03-06 | 2012-09-01 | 2015-03-06 | 2012-09-01 | 2012-09-03 | 1 | 2012-09-06 | 2012-09-03 | PERMITTED | 2012-07-20 | 2012-07-20 | 2012-08-24 | 2012-08-20 | 1 | 2012-08-28 | 2012-08-23 | 2015-02-03 | 2015-02-03 | 2015-03-25 | 2015-03-27 | 1 |  | 2015-03-27 | 2015-03-27 | [5 empty] | 2015-06-15 | 2015-06-16 | 2015-08-18 | 2015-08-18 | 2015-08-04 | 2015-08-18 | 2015-08-18 | 2015-08-07 | 2015-08-12 | 2015-07-28 | 2015-07-28 | 2015-07-28 | 2015-07-28 | 2015-07-28 | 2015-07-28 |  | 2015-09-08 | 2015-09-08 |  |  |  |  | 23 Jan - RF to review and CDI to be issued 06/03 AS - CD approved to issue Rev1 16/04 AS: Build instruction issued Waiting on quote from Huawei | [10 empty] | 2015-09-04 | 2015-09-02 | 2012-07-04 | LOW | NATIONAL_PARK | 2015-08-07 | 2015-08-04 | BUILD | 2015-08-04 | FALSE |  | 2706312 | 6255365 | Taumarunui 36 Miriama Street |  |  | CELLSITE |  |  |  | ROAMING |  | 2015-03-13 | 2015-03-17 | 2015-05-21 | 2015-04-07 |  |  |  |  | 2015-06-12 | 2015-06-12 |  |  | 2015-03-06
0 | MNW | 1043 | MNW-036-003 | Taumarunui South | MNW-036-003-B | GF VF co-site | Ruapehu District | 24 | TIER_4 | ACTIVE | GF | DF | T2 25 RH |  | STACK_A | COSITE |  |  |  | -38.8981 | 175.3598 |  | 2015-03-11 |  | 2015-06-18 | Fibre Optic | WKT-016-023-B | FALSE | FALSE |  |  | FALSE |  | 2015-04-27 | 2015-04-30 | 2015-06-12 | 2015-06-12 | 2015-06-16 | 2015-06-11 | 1 |  | 2015-06-11 | 2015-07-28 | 2015-07-28 | 2015-08-07 | 2015-08-11 |  | 2015-08-11 | 2015-08-11 | DISCRETIONARY_RESTRICT | 2015-06-30 | 2015-06-19 | 2015-08-14 | 2015-08-11 | 1 |  | 2015-08-06 | 2015-07-01 | 2015-06-29 | 2015-08-28 | 2015-08-26 | 1 |  |  | 2015-08-26 | [5 empty] | 2017-01-31 |  | 2017-02-28 |  |  | 2017-03-17 |  | 2015-10-16 |  | 2015-07-28 | 2015-07-28 | [5 empty] | 2017-04-14 | [5 empty] | 1/05 AS GF co-site | [10 empty] | 2017-03-31 |  |  |  |  | 2015-10-16 |  | ONHOLD |  | FALSE |  | 2714738 | 6253550 | Burnand Road Tamunurui | Template lease docs and plans with LO. - 16/06/2015 |  | CELLSITE |  |  |  | ROAMING |  | 2015-07-16 |  | 2015-08-14 | 2015-08-07 |  |  |  |  | 2017-01-13 |  |  |  | 2015-05-27
0 | MNW | 1044 | MNW-036-004 | Ruapehu |  |  | Ruapehu District | 24 | TIER_9 | [22 empty] | FALSE | [60 empty] | • 2 panel antennas per sector (Azimuths 050, 170, 290) Likely antennas will be 2 x Kathrein 80010456 and 1 x Kathrein 742 266, the second set of antennas are likely to be 2.6m x 200mm x 380mm 51Kg each • 4 RRU (Remote Radio Units) per sector mounted within a 5m cable length of the antenna (the closer the better) 610 x 380 x 200mm 22Kg. • Fibre and DC power cable to each RRU.
0 | MNW | 1045 | MNW-036-005 | Whakapapa Ski Field |  |  | Ruapehu District |  | TIER_9 | [22 empty] | FALSE
0 | MNW | 1046 | MNW-036-006 | Turoa Ski Field |  |  | Ruapehu District |  | TIER_9 | [22 empty] | FALSE
0 | MNW | 1047 | MNW-036-007 | Ohakune | MNW-036-007-A | Ohakune VNZ Co-Lo | Ruapehu District | 24 | TIER_4 | ACTIVE | COLO | DF | COLO |  | STACK_A | COLO | 30 | 34 |  | -39.4329 | 175.3995 |  | 2015-01-01 |  | 2015-04-15 | Fibre Optic | MNW-040-003-B | FALSE | FALSE |  |  | FALSE |  | 2012-04-04 | 2012-03-21 | 2012-04-10 | 2012-03-26 | 2015-01-30 | 2012-05-07 | 3 | 2015-03-19 | 2015-02-05 | 2015-06-24 | 2015-06-24 | 2015-09-04 | 2015-09-02 |  | 2015-09-04 | 2015-09-02 | DISCRETIONARY_FULL | 2015-03-27 | 2015-03-23 | 2015-04-24 | 2015-04-15 | 3 | 2015-05-01 | 2015-04-15 | 2015-03-27 | 2015-03-19 | 2015-04-24 | 2015-05-12 | 1 |  | 2015-07-14 | 2015-05-12 | [5 empty] | 2015-09-18 | 2015-10-06 | 2015-10-30 | 2015-11-03 |  | 2015-10-30 | 2015-11-03 | 2015-09-04 |  | 2015-07-28 | 2015-07-28 | [5 empty] | 2015-11-29 | 2015-11-24 |  |  |  |  | 10/03 - VF co-lo approval awaited 19/03 AS: VF preliminary approval received, Acceptance sent back to Jordan, Planner instructed to file resource sonsent, CDI issued to GHD. Jordan asked to initiate lease/paper work and complete acqusition. 16/04 AS: Liz working on sub-lease with VF, CD due 24/04 | VNZ | [9 empty] | 2015-11-23 | 2015-11-24 |  | LOW | NATIONAL_PARK | 2015-09-04 |  | BUILD |  | FALSE |  | 2716564 | 6194092 | Ratamaire Rd, Ohakune |  |  | CELLSITE |  |  |  | ROAMING |  |  | 2015-03-19 | 2015-05-06 | 2015-05-06 |  |  |  |  | 2015-09-11 | 2015-09-02 |  |  | 2012-03-26
0 | MNW | 1048 | MNW-036-008 |  |  |  | Ruapehu District |  | TIER_9
0 | MNW | 1049 | MNW-036-009 | Waiouru | MNW-036-009-A | Waiouru VNZ Co-Lo | Ruapehu District | 24 | TIER_4 | ACTIVE | COLO | DF | NOPOLE |  | STACK_A | COLO |  | 30 |  | -39.4985 | 175.6525 |  | 2015-06-09 |  | 2015-04-15 | Fibre Optic | MNW-040-003-B | FALSE | FALSE |  |  | FALSE |  | 2012-04-04 | 2012-03-21 | 2012-04-10 | 2012-03-27 | 2015-03-13 | 2012-05-16 | 3 | 2015-03-19 | 2015-03-16 | 2015-09-18 |  | 2015-09-25 |  |  | 2015-09-30 |  | DISCRETIONARY_FULL | 2015-04-30 | 2015-04-21 | 2015-05-31 | 2015-05-15 | 3 |  | 2015-08-06 | 2015-04-30 | 2015-04-13 | 2015-05-31 | 2015-05-20 | 1 |  |  | 2015-05-20 | [5 empty] | 2017-01-27 |  | 2017-02-28 |  |  | 2017-03-17 |  | 2015-10-09 |  | 2015-10-02 | [6 empty] | 2017-04-14 | [5 empty] | 09/03 AS: PD Rev 3 requested, on receipt need to submit VF co-lo application 19/03 AS: VF co-lo submitted over to Jordan 13/04 AS: VF Co-lo CDI issued 16/04 AS: PD & CD issued 16/04AS: Liz is working on sub-lease with VF | VNZ | [9 empty] | 2017-03-31 |  |  | LOW | NATIONAL_PARK | 2015-10-09 |  | ONHOLD |  | FALSE |  | 2738116 | 6186212 | North Island, State Highway 1, Waiouru |  |  | CELLSITE | WIPACTIVE |  |  | ROAMING |  |  |  | 2015-05-06 | 2015-05-06 |  |  |  |  | 2017-01-13 |  |  |  | 2012-03-27
0 | MNW | 1050 | MNW-036-010 |  |  |  | Ruapehu District |  | TIER_9
0 | MNW | 1051 | MNW-036-011 |  |  |  | Ruapehu District |  | TIER_9
0 | MNW | 1052 | MNW-036-012 | Ruapehu TX only |  |  | Ruapehu District | 24 | TIER_9 | [22 empty] | FALSE
0 | MNW | 1053 | MNW-037-001 | Wanganui CBD (Main HUB) | MNW-037-001-A | 76 Guyton Street | Wanganui | 6 | TIER_2 | ACTIVE | RT | DF | RT |  | STACK_A |  |  |  | 1 | -39.9313 | 175.0496 |  | 2010-10-02 |  | 2010-02-12 | Fibre Optic | WLG-047-071-A | TRUE | TRUE |  |  | FALSE | 2011-03-22 | 2011-04-07 | 2011-04-07 | 2011-04-18 | 2011-04-26 | 2011-05-13 | 2011-05-18 | 2 | 2011-05-13 | 2014-12-08 | 2011-06-04 | 2011-06-10 | 2011-07-04 | 2011-06-17 | 1 | 2011-07-09 | 2011-07-04 | DISCRETIONARY_FULL | 2011-05-16 | 2011-05-19 | 2011-06-23 | 2011-06-03 | 1 | 2011-07-11 | 2011-06-03 |  |  | 2011-08-29 | 2011-09-08 | 1 |  | 2011-08-29 | 2011-09-08 | 2011-09-26 |  |  |  |  | 2011-09-20 | 2011-09-20 | 2011-11-18 | 2011-11-18 | 2011-09-29 | 2011-10-19 | 2011-10-19 | [8 empty] | 2011-10-26 | 2011-11-08 | 2011-11-11 | 2011-10-21 | 2011-12-01 | 2013-09-25 | 2013-12-16 | Contact Brendan & Sue Brosnahan (Chaineys Buildings Ltd) 0274420061. burrentals@hotmail.com. 76 Guyton Ave, Wanganui. |  | 2011-10-21 | 2011-07-27 | 2011-07-27 | 2011-09-26 | 2011-10-17 | 2011-09-26 | 2011-09-26 | 2011-10-05 | 2011-10-06 |  | 2011-11-11 | [5 empty] | BUILD | 2011-09-28 | FALSE |  | 2685171 | 6139563 | 76 Guyton Street Wanganui |  | Not in heritage overlay - should be good - 01/04/2011 | CELLSITE | [15 empty] | 2011-11-25 | 2011-11-25 | 2011-04-26
0 | MNW | 1054 | MNW-037-002 | Wanganui North | MNW-037-002-D | Somme Pde LPR | Wanganui | 6 | TIER_2 | ACTIVE | RSR | DU | P4F | green | INLINE | STANDALONE | 15 | 15.5 | 1 | -39.9205 | 175.0499 |  | 2010-10-02 |  | 2010-02-12 | Microwave | MNW-037-001-A | TRUE | TRUE |  |  | FALSE | 2011-04-19 | 2011-04-29 | 2011-05-04 | 2011-05-04 | 2011-05-10 | 2011-05-30 | 2011-06-02 | 2 | 2011-05-31 | 2014-11-24 | 2011-07-05 | 2011-06-14 | 2011-09-05 | 2011-09-02 | 1 | 2011-09-09 | 2011-09-02 | CONTROLLED | 2011-06-07 | 2011-06-03 | 2011-07-09 | 2011-06-22 | 1 | 2011-07-14 | 2011-06-22 |  |  | 2011-08-29 | 2011-09-13 | 1 |  | 2011-08-29 | 2011-09-13 | 2011-09-09 |  |  |  |  | 2011-11-01 | 2011-11-02 | 2011-11-18 | 2011-11-18 | 2011-11-04 | 2011-11-05 | 2011-11-05 | [8 empty] | 2011-11-17 | 2011-11-10 | 2011-11-11 | 2011-11-19 | 2011-12-01 | 2013-09-16 | 2013-09-19 |  |  | 2011-11-16 | 2011-08-23 | 2011-08-23 | 2011-10-24 | 2011-10-17 | 2011-09-09 | 2011-09-09 | 2011-11-04 | 2011-11-04 |  | 2011-11-29 | [5 empty] | BUILD | 2011-11-04 | FALSE |  | 2685221 | 6140755 | Somme Parade Wanganui |  | LPR exceeding NES for height and underlying permitted activity so is controlled. - 06/05/2011 | CELLSITE |  |  | 2015-05-26 | [12 empty] | 2011-11-30 | 2011-11-29 | 2011-05-10
0 | MNW | 1055 | MNW-037-003 | Otamatea | MNW-037-003-D | 173 Great North Rd LPR | Wanganui | 6 | TIER_2 | ACTIVE | RSR | DU | P4F | green | INLINE | STANDALONE | 13.3 | 13.8 | 1 | -39.9068 | 175.0213 |  | 2010-10-02 |  | 2010-02-12 | Microwave | MNW-037-007-A | TRUE | TRUE |  |  | FALSE | 2011-05-03 | 2011-06-21 | 2011-05-05 | 2011-05-27 | 2011-05-10 | 2011-05-27 | 2011-06-02 | 1 | 2011-05-31 | 2011-06-02 | 2011-07-12 | 2011-08-02 | 2011-08-11 | 2011-08-05 | 1 | 2011-08-16 | 2011-08-09 | NES | 2011-06-03 | 2011-06-03 | 2011-07-03 | 2011-06-23 | 1 | 2011-08-16 | 2011-06-23 |  |  | 2011-10-21 | 2011-12-08 | 1 |  | 2011-10-21 | 2011-12-08 | 2011-11-04 |  |  |  |  | 2011-11-07 | 2011-11-03 | 2011-11-22 | 2011-11-22 | 2011-11-11 | 2011-11-23 | 2011-11-20 | [8 empty] | 2011-11-22 | 2011-11-30 | 2011-12-01 | 2011-12-27 | 2011-12-13 | 2012-03-12 | 2012-06-29 |  |  | 2011-11-22 |  | 2011-08-30 | 2011-11-18 | 2011-11-18 | 2011-11-04 | 2011-11-04 | 2011-11-14 | 2011-11-14 |  | 2011-11-28 | [6 empty] | 2011-11-11 | FALSE |  | 2682808 | 6142333 | 173 Great North Road |  |  | CELLSITE | [15 empty] | 2011-12-02 | 2011-12-02 | 2011-05-10
0 | MNW | 1056 | MNW-037-004 | Castlecliff | MNW-037-004-B | Kirk Street WDC land | Wanganui | 6 | TIER_2 | ACTIVE | GF | DU | T2 20 UF | jumbo grey | STACK_A | STANDALONE | 19.4 | 20 | 1 | -39.9442 | 174.9909 |  | 2010-10-02 |  | 2010-02-12 | Microwave | MNW-037-006-A | FALSE | FALSE |  |  | FALSE | 2011-03-25 | 2011-04-14 | 2011-04-14 | 2011-04-19 | 2011-04-26 | 2011-05-13 | 2011-05-17 | 1 | 2011-05-13 | 2011-05-17 | 2011-06-25 | 2011-06-17 | 2011-09-07 | 2011-09-02 | 1 | 2011-09-10 | 2011-09-02 | PERMITTED | 2011-05-20 | 2011-05-19 | 2011-06-24 | 2011-06-07 | 1 | 2011-07-11 | 2011-06-07 |  |  | 2011-07-08 | 2011-08-01 | 1 |  | 2011-07-15 | 2011-08-01 | 2011-09-27 |  |  |  |  | 2011-09-12 | 2011-09-12 | 2011-10-31 | 2011-10-31 | 2011-10-10 | 2011-10-19 | 2011-10-19 | [8 empty] | 2011-10-26 | 2011-11-10 | 2011-11-11 | 2011-10-21 | 2011-12-01 | 2012-02-29 | 2012-10-05 |  |  | 2011-10-20 | 2011-07-27 | 2011-07-27 | 2011-10-14 | 2011-10-17 | 2011-09-27 | 2011-09-27 | 2011-10-07 | 2011-10-06 |  | 2011-11-11 | [6 empty] | 2011-10-05 | FALSE |  | 2680123 | 6138240 | 1 Morrison Street, Castlecliff, Wanganui |  |  | CELLSITE |  |  | 2015-05-26 | [12 empty] | 2011-11-24 | 2011-11-23 | 2011-04-26
0 | MNW | 1057 | MNW-037-006 | Wanganui Airport | MNW-037-006-A | Wanganui Airport, VF Colo (Wanganui Airport) | Wanganui | 6 | TIER_2 | ACTIVE | COLO | DU | COLO | grey | STACK_A | COLO | 27 | 30 | 1 | -39.9553 | 175.0552 |  | 2010-10-02 |  | 2010-02-12 | Microwave | MNW-037-001-A | TRUE | TRUE | 2011-03-02 |  | FALSE |  | 2011-03-17 | 2011-03-17 | 2011-03-22 | 2011-03-22 | 2011-04-08 | 2011-04-26 | 1 | 2011-04-19 | 2011-04-26 | 2011-05-18 | 2011-08-02 | 2011-08-06 | 2011-08-29 | 1 | 2011-08-09 | 2011-09-15 | DISCRETIONARY_FULL | 2011-05-02 | 2011-05-02 | 2011-06-16 | 2011-05-19 | 1 | 2011-06-21 | 2011-05-19 |  |  | 2011-08-29 | 2011-09-06 | 1 |  | 2011-08-29 | 2011-09-06 | 2011-10-10 |  |  |  |  | 2011-09-29 | 2011-10-03 | 2011-10-31 | 2011-10-31 | 2011-10-06 | 2011-10-17 | 2011-10-19 | [8 empty] | 2011-10-26 | 2011-11-10 | 2011-11-11 | 2011-10-21 | 2011-12-01 | 2012-02-29 | 2012-06-29 |  | VNZ | 2011-10-21 | 2011-07-27 | 2011-07-27 | 2011-10-06 | 2011-10-17 | 2011-10-14 | 2011-10-10 | 2011-10-14 | 2011-10-14 |  | 2011-11-11 | [6 empty] | 2011-10-06 | FALSE |  | 2685582 | 6136891 | State Highway 3, Main Road South, Putiki |  |  | CELLSITE | [15 empty] | 2011-11-23 | 2011-11-23 | 2011-03-22
0 | MNW | 1058 | MNW-037-007 | Bastia Hill | MNW-037-007-A | Bastia Hill, Bastia Hill | Wanganui | 6 | TIER_2 | ACTIVE | BO | DF | NOPOLE | grey | INLINE | COSITE | 31.3 | 50 | 1 | -39.9269 | 175.0694 |  | 2010-10-02 |  | 2010-02-12 | Microwave | MNW-037-001-A | TRUE | TRUE | 2011-03-02 |  | FALSE | 2011-03-22 | 2011-04-07 | 2011-04-07 | 2011-04-27 | 2011-04-27 | 2011-05-16 | 2011-05-31 | 2 | 2011-05-17 | 2014-11-24 | 2011-06-13 | 2011-06-10 | 2011-07-13 | 2011-08-10 | 1 | 2011-07-18 | 2011-08-10 | DISCRETIONARY_FULL | 2011-05-21 | 2011-06-03 | 2011-07-02 | 2011-06-22 | 1 | 2011-07-18 | 2011-06-22 |  |  | 2011-09-28 | 2011-11-07 | 1 |  | 2011-09-28 | 2011-11-07 | 2011-10-27 |  |  |  |  | 2011-10-18 | 2011-10-15 | 2011-11-18 | 2011-11-18 | 2011-10-21 | 2011-11-18 | 2011-11-18 | [8 empty] | 2011-10-26 | 2011-11-10 | 2011-11-11 | 2011-11-19 | 2011-12-07 | 2013-08-30 | 2013-08-27 | Contact Srien Fonseca (WDC) 06 3490001 Moved out due to RF review possibly try to get TX off |  | 2011-10-26 | 2011-08-23 | 2011-08-23 | 2011-10-21 | 2011-10-21 | 2011-10-18 | 2011-10-27 | 2011-11-02 | 2011-10-25 |  | 2011-11-11 | [5 empty] | BUILD | 2011-10-27 | FALSE |  | 2686875 | 6140007 | Bastia Hill Water Tower, 13 Bastia Ave, Wanganui |  | Heritage rules tripped as site is a historic water tower. NZHPT approval will be sought for this design. - 01/04/2011 | CELLSITE |  |  | 2015-05-26 | [12 empty] | 2011-11-25 | 2011-11-24 | 2011-04-27
0 | MNW | 1059 | MNW-037-008 |  |  |  | Wanganui |  | TIER_9
0 | MNW | 1060 | MNW-037-009 | Blueskin | MNW-037-009-A | Blueskin, VF Colo (Wanganui West) | Wanganui | 6 | TIER_2 | ACTIVE | COLO | DU | COLO | grey | STACK_A | COLO | 26.6 | 29.5 | 1 | -39.8896 | 175.014 |  | 2010-10-02 |  | 2010-12-02 | Microwave | MNW-037-007-A | TRUE | TRUE | 2011-02-24 |  | FALSE | 2011-03-22 | 2011-03-17 | 2011-03-17 | 2011-03-22 | 2011-03-22 | 2011-04-18 | 2011-04-16 | 2 | 2011-04-22 | 2011-05-04 | 2011-05-18 | 2011-07-28 | 2011-06-17 | 2011-08-04 | 2 | 2011-06-19 | 2011-08-29 | DISCRETIONARY_FULL | 2011-05-02 | 2011-05-02 | 2011-06-16 | 2011-05-19 | 1 | 2011-06-21 | 2011-05-19 |  |  | 2011-08-29 | 2011-09-13 | 1 |  | 2011-08-29 | 2011-09-13 | 2011-10-18 |  |  |  |  | 2011-09-29 | 2011-09-29 | 2011-11-18 | 2011-11-18 | 2011-10-08 | 2011-11-08 | 2011-10-24 | [8 empty] | 2011-10-26 | 2011-11-29 | 2011-12-01 | 2011-11-19 | 2011-12-08 | 2012-03-07 | 2012-06-29 |  | VNZ | 2011-10-26 | 2011-07-27 | 2011-07-27 | 2011-10-17 | 2011-10-18 | 2011-10-13 | 2011-10-18 | 2011-11-04 | 2011-10-17 |  | 2011-11-11 | [6 empty] | 2011-10-06 | FALSE |  | 2682233 | 6144258 | Blueskin Rd, Westmere, Wanganui |  | Ring headframe VF @ 25m - 22/03/2011 | CELLSITE | [15 empty] | 2011-11-25 | 2011-11-25 | 2011-03-22
0 | MNW | 1061 | MNW-037-010 | Tawhero | MNW-037-010-D | Victoria Park GF | Wanganui | 6 | TIER_2 | ACTIVE | GF | DU | T2 20 UF | flax green | STACK_A | STANDALONE | 23.3 | 23.85 | 1 | -39.9255 | 175.0331 |  | 2010-10-02 |  | 2010-02-12 | Microwave | MNW-037-001-A | TRUE | TRUE |  |  | FALSE | 2011-05-03 | 2011-05-05 | 2011-05-05 | 2011-05-10 | 2011-05-10 | 2011-05-27 | 2011-06-01 | 1 | 2011-05-30 | 2011-06-01 | 2011-06-26 | 2011-06-13 | 2011-07-26 | 2011-07-01 | 1 | 2011-07-31 | 2011-07-01 | DISCRETIONARY_FULL | 2011-06-14 | 2011-06-15 | 2011-07-18 | 2011-06-29 | 1 | 2011-08-01 | 2011-06-29 |  |  | 2011-09-16 | 2011-09-19 | 1 |  | 2011-09-16 | 2011-09-19 | 2011-11-15 |  |  |  |  | 2011-10-12 | 2011-10-12 | 2011-11-25 | 2011-11-24 | 2011-10-29 | 2011-11-23 | 2011-11-23 | [8 empty] | 2011-11-28 | 2011-11-28 | 2011-12-01 | 2011-11-19 | 2011-12-13 | 2013-05-05 | 2013-05-02 |  |  | 2011-11-25 | 2011-08-23 | 2011-08-23 | 2011-11-09 | 2011-11-09 | 2011-11-15 | 2011-11-15 | 2011-11-16 | 2011-11-08 |  | 2011-11-28 | [5 empty] | BUILD | 2011-11-14 | FALSE |  | 2683770 | 6140233 | Victoria Park |  | Mast does not comply with structure height condition for open space zone - 06/05/2011 | CELLSITE |  |  | 2015-05-26 | [12 empty] | 2011-12-02 | 2011-12-02 | 2011-05-10
0 | MNW | 1062 | MNW-037-011 | Aramoho | MNW-037-011-B | GF at Roberts Ave | Wanganui | 6 | TIER_2 | ACTIVE | GF | DU | T2 15 UF | grey | STACK_A | COSITE | 18.3 | 18.8 | 2 | -39.8911 | 175.0657 |  | 2010-10-02 |  | 2010-02-12 | Microwave | MNW-037-001-A | FALSE | FALSE |  |  | FALSE | 2011-03-22 | 2011-04-07 | 2011-04-07 | 2011-04-19 | 2011-04-27 | 2011-05-13 | 2011-05-23 | 1 | 2011-05-13 | 2011-05-23 | 2011-05-29 | 2011-05-09 | 2011-06-28 | 2011-07-01 | 1 | 2011-07-03 | 2011-07-01 | PERMITTED | 2011-05-18 | 2011-06-03 | 2011-06-21 | 2011-06-23 | 1 | 2011-06-06 | 2011-06-23 |  |  | 2011-09-16 | 2011-09-13 | 1 |  | 2011-09-16 | 2011-09-13 | 2011-11-15 |  |  |  |  | 2011-10-17 | 2011-10-15 | 2011-11-30 | 2011-11-28 | 2011-11-16 | 2011-11-23 | 2011-11-23 | [8 empty] | 2011-11-29 | 2011-11-29 | 2011-12-01 | 2011-11-19 | 2011-12-01 | 2012-02-29 | 2012-06-29 |  |  | 2011-11-27 | 2011-08-22 | 2011-08-23 | 2011-11-09 | 2011-11-15 | 2011-11-15 | 2011-11-15 | 2011-11-18 | 2011-11-18 |  | 2011-11-29 | [6 empty] | 2011-11-15 | FALSE |  | 2686648 | 6143995 | 180 Roberts Ave, Wanganui |  | Nearby BCL designation, site will be heavily co-sited. - 01/04/2011 | CELLSITE | [15 empty] | 2011-12-02 | 2011-12-02 | 2011-04-27
0 | MNW | 1063 | MNW-037-012 | Gonville | MNW-037-012-B | 289 Head Rd | Wanganui | 6 | TIER_2 | ACTIVE | GF | DU | T2 20 UF | grey | STACK_A | STANDALONE | 19.5 | 20 | 2 | -39.9492 | 175.0203 |  |  |  |  | Microwave | MNW-037-006-A | TRUE | TRUE |  |  | FALSE | 2011-03-31 | 2011-04-07 | 2011-04-07 | 2011-04-19 | 2011-04-26 | 2011-05-13 | 2011-05-12 | 1 | 2011-05-13 | 2011-05-12 | 2011-06-15 | 2011-05-31 | 2011-07-05 | 2011-05-31 |  | 2011-07-10 | 2011-07-08 | PERMITTED | 2011-05-13 | 2011-05-19 | 2011-06-24 | 2011-06-07 | 1 | 2011-06-13 | 2011-06-07 |  |  | 2011-09-17 | 2011-09-20 | 1 |  | 2011-09-17 | 2011-09-20 | 2011-09-27 |  |  |  |  | 2011-09-08 | 2011-09-08 | 2011-11-18 | 2011-11-18 | 2011-10-10 | 2011-10-26 | 2011-10-20 | [8 empty] | 2011-10-26 | 2011-11-10 | 2011-11-11 | 2011-10-21 | 2011-12-01 | 2012-02-29 | 2012-06-29 |  |  | 2011-10-26 | 2011-07-27 | 2011-07-27 | 2011-10-12 | 2011-10-18 | 2011-09-27 | 2011-09-27 | 2011-10-17 | 2011-10-16 |  | 2011-11-11 | [6 empty] | 2011-10-17 | FALSE |  | 2682619 | 6137638 | 289 Heads Rd, Wanganui |  | Discretion restricted to height, needs to be well justified. - 01/04/2011 | CELLSITE |  |  | 2015-05-26 | [12 empty] | 2011-11-23 | 2011-11-23 | 2011-04-26
0 | MNW | 1064 | MNW-038-001 | Whangaehu | MNW-038-001-A | Whangaehu VNZ Co-Lo | Rangitikei District | 24 | TIER_4 | ACTIVE | COLO | DF | NOPOLE |  | STACK_A | COLO |  |  | 1 | -40.0278 | 175.1887 |  | 2015-03-11 |  | 2015-08-12 | Fibre Optic | MNW-040-003-B | FALSE | FALSE |  |  | FALSE |  | 2015-04-30 | 2015-04-30 | 2015-05-22 | 2015-05-27 | 2015-06-30 | 2015-06-23 | 1 |  | 2015-06-23 | 2015-07-17 | 2015-07-28 | 2015-09-11 | 2015-09-10 |  | 2015-09-18 |  | PERMITTED | 2015-08-21 | 2015-08-18 | 2015-09-25 | 2015-09-03 | 1 |  | 2015-09-10 | 2015-09-17 | 2015-09-10 | 2015-12-18 | 2015-11-27 | 1 |  |  | 2015-11-27 | [5 empty] | 2016-03-18 |  | 2016-04-01 |  |  | 2016-04-15 | [10 empty] | 2016-05-06 | [5 empty] | 11/03 AS : VF site data pack requested. 20/03 AS datapack received, RF has proposed solution need to run structural assessment | VNZ | [9 empty] | 2016-04-29 |  | 2012-04-16 | LOW | FIELDING |  |  | BUILD |  | FALSE |  | 2696788 | 6128567 | Ratana Rd, Whangaehu |  |  | CELLSITE | WIPACTIVE |  |  | ROAMING |  |  | 2016-02-10 | 2016-01-15 | 2016-01-12 |  |  |  |  | 2016-03-11 |  |  |  | 2015-05-27
0 | MNW | 1065 | MNW-038-002 | Marton | MNW-038-002-A | unknown | Rangitikei District | 24 | TIER_9 | ACTIVE |  | DF |  |  | STACK_A |  |  |  |  | -40.1107 | 175.3593 | [6 empty] | FALSE | FALSE |  |  | FALSE |  | 2015-10-26 | [76 empty] | BUILD |  | FALSE |  | 2711097 | 6118989 |  |  |  | CELLSITE |  |  |  | ROAMING
0 | MNW | 1066 | MNW-038-003 |  |  |  | Rangitikei District |  | TIER_9
0 | MNW | 1067 | MNW-038-004 |  |  |  | Rangitikei District |  | TIER_9
0 | MNW | 1068 | MNW-038-005 |  |  |  | Rangitikei District |  | TIER_9
0 | MNW | 1069 | MNW-038-006 | Taihape | MNW-038-006-B | Benson Property | Rangitikei District | 24 | TIER_4 | ACTIVE | GF | DU | T2 20 RF |  | STACK_A | COSITE | 19 | 20 | 1 | -39.6879 | 175.8013 |  | 2015-04-15 |  | 2015-04-15 | Microwave | MNW-038-009-A | FALSE | FALSE |  |  | FALSE |  | 2012-03-23 | 2012-03-21 | 2012-03-30 | 2012-03-26 | 2012-04-12 | 2012-05-24 | 2 | 2012-04-12 | 2012-10-18 | 2012-10-05 | 2012-10-11 | 2012-10-15 | 2012-10-17 | 1 | 2012-10-22 | 2012-10-17 | PERMITTED | 2012-06-20 | 2012-07-18 | 2012-08-17 | 2012-08-13 | 1 | 2012-08-24 | 2012-08-16 | 2014-11-07 | 2014-11-07 | 2015-02-06 | 2015-02-12 | 1 |  | 2015-03-17 | 2015-02-12 | [5 empty] | 2015-06-15 | 2015-06-16 | 2015-07-31 | 2015-07-28 | 2015-07-30 | 2015-08-14 | 2015-07-30 | 2015-07-28 | 2015-07-28 | 2015-07-28 | 2015-07-28 | 2015-07-28 | 2015-07-28 | 2015-07-30 | 2015-07-30 |  | 2015-08-30 | 2015-08-31 |  |  |  |  | 8 Oct 2014 - RF to check PD for any minor mods. If any major issues with VF co-site RF would like to consider Spark co-site. VF colo hard matched - OK with RF to continue move to CD - CDI issued 5 Jan - CD (and lease) has conflict with location that was used to obtain consent. Site is subject to RF review and confirmation. 29 Jan - Site confiormed construction dates amended to suit equipment delivery 13/08 AS: delay by a week due to power 16/04 AS: Waiting on co-lo approval from Chorus for Taihape Exchange co-lo Jordan is chasing it | [10 empty] | 2015-08-27 | 2015-08-24 | 2012-05-21 | LOW | NATIONAL_PARK | 2015-08-13 | 2015-08-13 | BUILD | 2015-07-30 | FALSE |  | 2750241 | 6164807 | Off Lookout Road Dixon Way Taihape |  |  | CELLSITE |  |  |  | ROAMING |  | 2015-03-13 | 2015-02-09 | 2015-04-23 | 2015-04-23 |  |  |  |  | 2015-05-26 | 2015-05-26 |  |  | 2012-03-26
0 | MNW | 1070 | MNW-038-007 | Woodhill |  |  | Rangitikei District |  | TIER_1_ALL
0 | MNW | 1071 | MNW-038-008 | RBI - Marton Central | MNW-038-008-A | RBI Marton | Rangitikei District | 6 | TIER_2 | ACTIVE | RBI | DU | RBI Pole |  | STACK_A | COLO |  |  | 1 | -40.0796 | 175.4003 |  | 2011-12-13 |  |  | Leased Line | MNW-040-003-B | FALSE | FALSE |  |  | FALSE |  | 2012-04-26 | 2012-04-26 | 2012-04-26 | 2012-04-26 | 2012-04-26 | 2012-04-30 | 1 | 2012-04-26 | 2012-04-30 |  | 2012-05-15 |  | 2012-05-15 |  |  | 2012-05-15 |  |  | 2012-09-25 |  | 2012-09-25 | 1 |  | 2012-09-25 |  |  |  | 2012-04-30 | 1 |  |  | 2012-04-30 | [6 empty] | 2012-08-10 | 2012-08-10 | 2012-08-07 | 2012-09-07 | 2012-09-21 | 2012-09-20 | [8 empty] | 2012-09-24 | 2012-10-06 | 2012-10-05 | 2012-10-06 | 2012-10-05 | 2013-04-25 | 2013-04-26 |  | VNZ | 2012-09-22 | [6 empty] | 2012-09-14 | 2012-09-18 |  | 2012-09-26 |  |  | RBI | 2012-08-10 | 2012-09-20 | BUILD | 2012-08-10 | FALSE |  | 2714682 | 6122344 | Marton Central, Purakau Street, Marton |  |  | CELLSITE | [15 empty] | 2012-09-28 | 2012-09-28 | 2012-04-26
0 | MNW | 1072 | MNW-038-009 | Taihape Exchange | MNW-038-009-A | Taihape Exchange | Rangitikei District | 24 | TIER_4 | ACTIVE | RT | TX | RT |  | STACK_A | COSITE |  |  |  | -39.6783 | 175.8003 |  | 2015-04-15 |  | 2015-04-15 | Fibre Optic | MNW-040-003-B | TRUE | FALSE |  |  | FALSE |  | 2012-03-23 | 2012-03-21 | 2012-04-05 | 2012-03-26 | 2012-04-12 | 2012-05-16 | 2 | 2012-07-13 | 2012-07-12 | 2012-08-10 | 2012-07-24 | 2012-09-07 | 2015-04-22 |  | 2015-02-20 | 2015-06-03 | PERMITTED | 2012-08-15 | 2012-07-17 | 2012-08-16 | 2012-07-30 | 2 | 2012-08-23 | 2012-07-30 | 2014-11-26 | 2014-11-25 | 2015-01-14 | 2015-01-15 | 1 |  | 2015-04-23 | 2015-01-15 | [5 empty] | 2015-06-19 | 2015-06-16 | 2015-07-31 | 2015-07-29 | 2015-08-04 | 2015-08-04 | 2015-08-04 | 2015-08-04 | 2015-08-04 | 2015-08-04 | 2015-08-04 | 2015-08-04 | 2015-08-04 | 2015-08-04 | 2015-08-04 |  | 2015-08-30 | 2015-08-31 |  |  |  |  | 16/05/12 - Amendments received 15/5. 16/5 All good, and request for formal issue made 01/06/12 - Chorus colo lodged in OOT by Brett. Telecom have requested dish is 2m above roof for H+S 21/06/12 - James to advise on 2m above roofline irt planning issues - OK 27/06/12 - Confirm if TC have given approval. Look at Consent app moving forward. 24/07/12 - Telecom colo approved, rev 2 drawings issued, consent lodged 27/07/12 - Company decision to place site in hardmatch only 08/08/12 - WO2 forcasted 05/10/12 - Site taken out from Build Programme 15 Oct 2014 - Cliff to check status of application WRT restarting. Colo application re-submitted. Site requires review and confirmation of the Taihap site before wecontinue with the build of this Tx only site. Dates changed to aligne with equipment delivery for Taihape cell site | [10 empty] | 2015-08-21 | 2015-08-31 |  |  | TRANSMISSION_ONLY | 2015-06-19 | 2015-08-04 | BUILD | 2015-08-03 | FALSE |  | 2750192 | 6165874 | 23 Kuku Street Taihape |  |  | TXSITE |  |  |  | ROAMING |  |  | 2015-02-09 | 2015-04-23 | 2015-04-23 |  |  |  |  | 2015-05-26 | 2015-05-26 |  |  | 2012-03-26
0 | MNW | 1073 | MNW-039-002 | Feilding | MNW-039-002-A | Feilding VF Colo | Manawatu District | 6 | TIER_3 | ACTIVE | COLO | DU | COLO |  | INLINE | COLO |  |  | 2 | -40.2109 | 175.5541 |  | 2012-02-25 |  |  | Leased Line | MNW-040-003-B | FALSE | FALSE |  |  | FALSE |  |  | 2011-11-01 |  | 2011-11-01 |  | 2011-08-12 | 1 |  | 2011-08-12 |  | 2011-11-18 |  | 2012-03-22 |  |  | 2012-03-22 |  |  | 2011-08-15 |  | 2011-09-15 | 1 |  | 2011-09-15 |  |  | 2012-04-19 | 2012-04-20 | 1 |  |  | 2012-04-20 | 2012-05-16 |  |  |  |  | 2012-05-14 | 2012-05-09 | 2012-05-26 | 2012-05-31 | 2012-05-16 | 2012-05-26 | 2012-05-29 | [8 empty] | 2012-06-12 | 2012-06-04 | 2012-06-12 | 2012-06-29 | 2012-06-28 | 2013-04-26 | 2013-05-01 |  | VNZ | 2012-06-09 | 2012-06-28 | 2012-06-28 | 2012-05-20 | 2012-05-16 | 2012-05-16 | 2012-05-16 | 2012-05-30 | 2012-06-05 | 2012-05-28 | 2012-05-28 |  |  | FIELDING | 2012-06-08 | 2012-06-08 | BUILD | 2012-05-16 | FALSE |  | 2727368 | 6107403 | Halcombe Road, Feilding |  |  | CELLSITE |  |  | 2015-04-02 | [12 empty] | 2012-05-29 | 2012-06-15
0 | MNW | 1074 | MNW-039-003 | Awahuri | MNW-039-003-A | Awahuri VF Co-Lo | Manawatu District | 6 | TIER_3 | ACTIVE | COLO | DU | COLO |  | INLINE | COLO |  |  | 1 | -40.2455 | 175.493 |  | 2011-12-19 |  |  | Microwave | MNW-040-001-B | FALSE | FALSE |  |  | FALSE |  |  | 2011-11-01 |  | 2011-11-01 |  | 2011-08-12 | 1 |  | 2011-08-12 |  | 2012-03-22 |  | 2012-03-22 |  |  | 2012-03-22 |  |  | 2011-08-15 |  | 2011-09-15 | 1 |  | 2011-09-15 |  |  | 2012-04-19 | 2012-04-20 | 1 |  | 2012-04-19 | 2012-04-20 | 2012-05-07 |  |  |  |  | 2012-05-07 | 2012-05-07 | 2012-05-24 | 2012-05-25 | 2012-05-16 | 2012-05-25 | 2012-05-25 | [8 empty] | 2012-05-28 | 2012-06-04 | 2012-06-01 | 2012-06-18 | 2012-06-15 | 2013-05-15 | 2013-05-13 |  | VNZ | 2012-05-25 |  |  | 2012-05-15 | 2012-05-15 | 2012-05-30 | 2012-05-07 | 2012-05-24 | 2012-05-30 | 2012-05-28 | 2012-05-30 |  |  | FIELDING |  |  | BUILD | 2012-05-16 | FALSE |  | 2722069 | 6103714 | Penny Rd Awahuri |  |  | CELLSITE | [15 empty] | 2012-05-29 | 2012-06-08
0 | MNW | 1075 | MNW-039-004 | Himatangi | MNW-039-004-A | Himatangi - VF Colo | Manawatu District | 6 | TIER_3 | ACTIVE | COLO | DU | COLO |  | STACK_A | COLO |  |  | 1 | -40.3443 | 175.3332 |  | 2011-12-19 |  |  | Microwave | MNW-042-001-B | FALSE | FALSE |  |  | FALSE |  | 2012-03-06 | 2012-03-06 | 2012-04-26 | 2012-04-26 | 2012-06-29 | 2012-07-05 | 1 | 2012-10-19 | 2012-07-05 | 2012-10-19 | 2012-10-16 | 2012-10-19 | 2012-10-16 |  | 2012-10-19 | 2012-10-16 | NON_COMPLYING_LIMITED | 2012-07-11 | 2012-07-12 | 2012-09-07 | 2012-09-04 | 1 | 2012-09-07 | 2012-09-04 |  |  | 2012-09-11 | 2012-09-24 | 1 |  | 2012-11-26 | 2012-09-24 | 2012-10-19 |  |  |  |  | 2012-10-30 | 2012-10-30 | 2012-11-09 | 2012-11-05 | 2012-10-30 | 2012-12-15 | 2012-11-19 | [8 empty] | 2012-12-15 | 2013-01-14 | 2012-12-18 | 2013-01-31 | 2012-12-21 | 2013-06-21 | 2013-04-26 | 19/12/12 - Drive team advise SOA to Ron B | VNZ | 2012-12-15 | 2012-09-03 | 2012-09-03 | 2012-09-26 | 2012-10-19 | 2012-09-26 | 2012-10-19 | 2012-11-20 | 2012-11-20 | 2012-12-10 | 2012-12-10 | 2012-04-16 | LOW | FIELDING |  |  | BUILD | 2012-10-30 | FALSE |  | 2708183 | 6093127 | SH1 Omanuka Road Himatangi |  |  | CELLSITE | [15 empty] | 2012-12-20 | 2012-12-20
0 | MNW | 1076 | MNW-039-005 | Bulls | MNW-039-005-A | Bulls - VF Colo | Manawatu District | 6 | TIER_3 | ACTIVE | COLO | DU | COLO |  | STACK_A | COLO |  |  | 2 | -40.1903 | 175.3921 |  | 2012-01-25 |  |  | Microwave | MNW-039-003-A | FALSE | FALSE |  |  | FALSE |  | 2012-03-06 | 2012-03-06 | 2012-04-26 | 2012-04-26 | 2012-06-29 | 2012-07-06 | 1 | 2012-06-29 | 2012-07-06 | 2012-06-13 | 2012-06-27 | 2012-11-16 | 2012-10-16 |  | 2012-11-16 | 2012-10-16 | DISCRETIONARY_RESTRICT | 2012-07-11 | 2012-07-11 | 2012-09-07 | 2012-09-07 | 1 | 2012-09-07 | 2012-09-07 |  |  | 2012-09-11 | 2012-09-10 | 1 |  | 2012-09-11 | 2012-09-10 | 2012-10-01 |  |  |  |  | 2012-12-03 | 2012-12-03 | 2012-12-04 | 2012-12-05 | 2012-11-30 | 2012-12-15 | 2012-12-15 | [8 empty] | 2012-12-15 | 2013-01-14 | 2012-12-18 | 2013-01-23 | 2013-01-23 | 2013-09-16 | 2013-08-12 | 19/12/12 - Drive team advise SOA to Ron B | VNZ | 2012-12-15 | 2012-09-03 | 2012-09-03 | 2012-09-22 | 2012-10-01 | 2012-09-29 | 2012-10-01 | 2013-01-17 | 2013-01-17 | 2012-12-15 | 2012-12-15 | 2012-04-16 | LOW | FIELDING |  |  | BUILD | 2012-12-03 | FALSE |  | 2713648 | 6110081 | Wightman Road, 3402 SH1 Ohakea BULLS |  |  | CELLSITE | [15 empty] | 2012-12-20 | 2012-12-20
0 | MNW | 1077 | MNW-039-006 |  |  |  | Manawatu District |  | TIER_9
0 | MNW | 1078 | MNW-039-007 |  |  |  | Manawatu District |  | TIER_9
0 | MNW | 1079 | MNW-039-008 | Feilding Central | MNW-039-008-B | Steam Rail | Manawatu District | 24 | 2015P | ACTIVE | GF | DU5 | T2 20 UF |  | STACK_A | STANDALONE | 21 | 23 |  | -40.2265 | 175.5705 |  | 2015-04-23 |  | 2015-04-23 | Leased Line | MNW-040-003-B | FALSE | FALSE |  |  | FALSE |  | 2014-08-28 | 2014-08-28 | 2014-09-16 | 2014-09-17 | 2014-11-13 | 2014-11-14 | 2 | 2014-11-13 | 2015-03-18 | 2014-10-02 | 2014-10-02 | 2015-02-04 | 2015-01-12 | 1 | 2015-02-23 | 2015-03-11 | DISCRETIONARY_RESTRICT | 2014-11-27 | 2014-11-26 | 2015-02-04 | 2014-12-12 | 1 | 2015-01-27 | 2014-12-15 | 2015-03-10 | 2015-03-10 | 2015-04-30 | 2015-05-04 | 1 |  | 2015-05-06 | 2015-05-04 |  |  |  | 2015-06-19 |  | 2015-07-01 | 2015-06-22 | 2015-08-07 | 2015-08-12 | 2015-07-30 | 2015-08-06 | 2015-08-13 | 2015-08-18 | 2015-08-25 | 2015-07-28 | 2015-07-28 | 2015-07-28 | 2015-07-28 | 2015-07-28 | 2015-07-28 |  | 2015-10-08 | 2015-10-07 |  |  |  |  | 09/03 AS: Gone back to RF for justification on change of Antenna type, soil contamination report and contamination investigation report. 10/03 AS: Work order 2 issued CDI 13/08 AS: Delay by a week due to power | [10 empty] | 2015-09-24 | 2015-09-17 |  | LOW |  | 2015-07-28 | 2015-07-28 | BUILD | 2015-07-30 | TRUE | 2015-04-30 | 2728718 | 6105631 | 28 Gladstone Street Feilding | Committee meetings for approval opf plans/leases every third Saturday of each month - 10/10/2014 - 27/02/2015 |  | CELLSITE |  |  | 2015-10-07 | CAPACITY |  | 2015-03-19 | 2015-05-19 | 2015-05-06 | 2015-05-06 |  |  |  |  | 2015-06-12 | 2015-06-12 |  |  | 2014-09-17
0 | MNW | 1080 | MNW-039-009 | RBI Himatangi Beach | MNW-039-009-A | Himitangi Beach RBI | Manawatu District | 25 | TIER_5 | ACTIVE | RBI | DF | RBI Pole |  | STACK_A | COLO | 36 | 40 |  | -40.3682 | 175.2495 | [6 empty] | FALSE | FALSE |  |  | FALSE |  | 2015-09-11 | 2015-09-09 | 2015-10-19 | 2015-10-21 | 2015-10-20 | 2015-11-02 | 1 | 2015-11-02 | 2015-11-02 | 2015-12-02 | 2015-12-02 | 2015-12-03 | 2015-12-02 |  | 2016-02-05 |  | PERMITTED | 2015-12-03 | 2015-12-08 | 2015-12-04 | 2015-12-18 | 1 | 2015-12-07 | 2015-12-08 | 2015-11-17 | 2015-11-17 | 2015-11-19 | 2015-12-07 | 1 |  | 2015-11-20 | 2015-12-07 | [5 empty] | 2016-03-14 |  | 2016-03-18 |  |  | 2016-03-18 |  | 2016-03-04 |  | 2016-03-09 |  | 2016-03-01 |  | 2016-03-02 |  |  | 2016-03-31 | [5 empty] | 16 Oct: Pre-qual & CD1 ordered 19 Oct: Planning letter complete 6 Dec: VF pre approval obtained 7 Dec: ATN & antennas ordered 16 Dec: Cabinet PO requested 22 Dec: VF PO sent through to order antennas 12 Jan: Waiting on Huawei antenna ETA 21 Jan: Contractor Tender visit 3 Feb: Finalising Contractor quotes. Waiting on VF final approval & antenna quote. | VNZ | [9 empty] | 2016-03-25 |  |  |  |  | 2016-03-15 |  | BUILD | 2016-03-14 | FALSE |  | 2701007 | 6090651 | Himatangi Beach Road |  | Letter to confirm compliance sent to Council - 25/01/2016 | CELLSITE |  |  |  | ROAMING |  |  | 2016-02-10 | 2015-11-20 | 2015-12-10 | 2015-10-15 | 2015-10-16 | 2015-11-11 | 2015-11-11 | 2015-12-23 |  |  |  | 2015-10-29
0 | MNW | 1081 | MNW-039-010 | Bunnythorpe |  |  | Manawatu District |  | TIER_9 | [22 empty] | FALSE
0 | MNW | 1082 | MNW-040-001 | Milson | MNW-040-001-B | VF Colo Milson | Palmerston North City | 6 | TIER_2 | ACTIVE | COLO | DU | COLO | grey | STACK_A | COLO | 31 | 45.1 | 1 | -40.3354 | 175.6152 |  | 2010-09-02 |  | 2010-02-12 | Microwave | MNW-040-003-B | TRUE | FALSE | 2011-02-02 |  | FALSE | 2011-03-01 | 2011-03-17 | 2011-03-03 | 2011-03-22 | 2011-03-08 | 2011-04-08 | 2011-03-30 | 1 | 2011-03-22 | 2011-03-30 | 2011-05-18 | 2011-05-17 | 2011-06-18 | 2011-06-10 |  | 2011-06-12 | 2011-07-27 | DISCRETIONARY_RESTRICT | 2011-04-15 | 2011-04-04 | 2011-05-27 | 2011-05-06 | 1 | 2011-06-18 | 2011-05-06 |  |  | 2011-06-24 | 2011-07-19 | 1 |  | 2011-07-01 | 2011-07-19 | 2011-09-12 |  |  |  |  | 2011-09-20 | 2011-09-01 | 2011-09-27 | 2011-09-15 | 2011-09-05 | 2011-09-21 | 2011-09-25 | [8 empty] | 2011-10-06 | 2011-09-28 | 2011-10-12 | 2011-09-30 | 2011-11-15 | 2013-09-15 | 2013-11-14 |  | VNZ | 2011-09-22 | 2011-07-27 | 2011-07-27 | 2011-09-11 | 2011-09-18 | 2011-09-26 | 2011-09-12 | 2011-10-20 |  |  | 2011-10-10 | [5 empty] | BUILD | 2011-09-05 | FALSE |  | 2732162 | 6093439 | Milson Line |  | Discretionary Activity due to height of exisitng VF lattice. No issues anticipated with this one - existing VF site is large. - 04/03/2011 | CELLSITE |  |  | 2015-04-07 | [12 empty] | 2011-11-05 | 2011-11-10 | 2011-03-08
0 | MNW | 1083 | MNW-040-002 | Kelvin Grove | MNW-040-002-B | Roslyn, VF Colo (Kelvin Grove) | Palmerston North City | 6 | TIER_2 | ACTIVE | COLO | DU | COLO | grey | STACK_A | COLO | 28 | 28.5 | 1 | -40.3388 | 175.6442 |  | 2010-09-02 |  | 2010-02-12 | Microwave | MNW-040-004-A | FALSE | TRUE | 2011-02-02 |  | FALSE | 2011-02-18 | 2011-02-17 | 2011-02-17 | 2011-02-21 | 2011-02-22 | 2011-03-07 | 2011-03-14 | 1 | 2011-03-07 | 2011-03-14 | 2011-05-22 | 2011-05-17 | 2011-06-18 | 2011-06-10 | 1 | 2011-06-20 | 2011-07-01 | DISCRETIONARY_RESTRICT | 2011-03-30 | 2011-04-04 | 2011-05-25 | 2011-05-06 | 1 | 2011-06-20 | 2011-05-06 | 2011-06-02 |  | 2011-07-04 | 2011-07-19 | 1 |  | 2011-07-08 | 2011-07-19 | 2011-08-22 |  |  |  |  | 2011-08-23 | 2011-08-23 | 2011-09-21 | 2011-09-24 | 2011-09-20 | 2011-09-25 | 2011-09-25 | [8 empty] | 2011-10-07 | 2011-10-24 | 2011-10-26 | 2011-09-30 | 2011-11-15 | 2012-02-13 | 2012-06-29 | Power close at fron section of property. Full headframe replacement | VNZ | 2011-09-26 | 2011-07-27 | 2011-07-27 | 2011-09-11 | 2011-09-18 | 2011-08-22 | 2011-08-22 | 2011-09-23 | 2011-09-24 |  | 2011-10-10 | [6 empty] | 2011-09-19 | FALSE |  | 2734614 | 6092991 | Keith Street Kelvin Grove |  | Total height here is 29m - 9m above permitted baseline. Co-lo is to our advantage but looking to bolster application with external consultant's visual assessment from key locations to avoid identification of affected parties. - 18/02/2011 | CELLSITE |  |  | 2015-04-07 | [12 empty] | 2011-10-25 | 2011-11-10 | 2011-02-22
0 | MNW | 1084 | MNW-040-003 | Palmerston North Cen(Main HUB) | MNW-040-003-B | 65 Rangitikei St | Palmerston North City | 6 | TIER_2 | ACTIVE | RT | DF | RT | grey | INLINE | COSITE |  |  | 1 | -40.3544 | 175.6101 |  |  |  |  | Fibre Optic | WLG-047-071-A | TRUE | TRUE | 2011-02-02 |  | FALSE | 2011-03-22 | 2011-03-17 | 2011-03-03 | 2011-03-08 | 2011-03-08 | 2011-03-25 | 2011-03-30 | 4 | 2011-03-22 | 2014-12-04 | 2011-06-16 | 2011-06-10 | 2011-06-25 | 2011-07-01 |  | 2011-06-27 | 2011-07-01 | DISCRETIONARY_RESTRICT | 2011-05-01 | 2011-04-05 | 2011-05-12 | 2011-05-06 | 2 | 2011-05-26 | 2011-05-06 | 2011-06-02 |  | 2011-07-04 | 2011-07-19 | 1 |  | 2011-07-08 | 2011-07-19 | 2011-09-13 |  |  |  |  | 2011-08-22 | 2011-08-17 | 2011-10-28 | 2011-11-18 | 2011-08-26 | 2011-09-23 | 2011-09-26 | [8 empty] | 2011-09-20 | 2011-09-28 | 2011-10-12 | 2011-09-30 | 2011-11-15 | 2013-09-15 | 2013-12-16 |  |  | 2011-09-18 | 2011-07-27 | 2011-07-27 | 2011-09-02 | 2011-09-02 | 2011-09-08 | 2011-09-13 | 2011-08-31 | 2011-09-19 |  | 2011-10-10 | [5 empty] | BUILD | 2011-08-30 | FALSE |  | 2731668 | 6091339 | 65 Rangitikei St Palmerston North |  | Discretionary Activity due to height of exisitng building. No issues - 04/03/2011 | CELLSITE |  |  | 2015-04-07 | [12 empty] | 2011-10-25 | 2011-11-11 | 2011-03-08
0 | MNW | 1085 | MNW-040-004 | Palmerston North (TX HUB) | MNW-040-004-A | Palmerston North, Ferguson & Ashley St | Palmerston North City | 6 | TIER_2 | ACTIVE | RT | DF | RT | grey | STACK_A | STANDALONE | 25.8 | 26.3 | 1 | -40.3578 | 175.6163 |  | 2010-09-02 |  |  | Fibre Optic | MNW-040-003-B | TRUE | TRUE | 2011-02-02 |  | FALSE | 2011-02-22 | 2011-02-17 | 2011-02-17 | 2011-02-21 | 2011-02-22 | 2011-03-07 | 2011-03-14 | 4 | 2011-03-07 | 2014-12-04 | 2011-06-16 | 2011-07-27 | 2011-06-10 | 2011-07-27 | 2 | 2011-06-15 | 2011-07-27 | DISCRETIONARY_RESTRICT | 2011-03-14 | 2011-03-14 | 2011-05-25 | 2011-05-06 | 2 | 2011-06-18 | 2011-11-04 | 2011-06-01 |  | 2011-09-23 | 2011-12-09 | 1 |  | 2011-09-23 | 2011-12-09 | 2011-09-19 |  |  |  |  | 2011-09-19 | 2011-09-19 | 2011-10-28 | 2011-11-18 | 2011-09-22 | 2011-09-29 | 2011-10-01 | [8 empty] | 2011-10-07 | 2011-10-28 | 2011-10-12 | 2011-11-19 | 2011-11-15 | 2013-09-15 | 2013-12-16 | Landlord John Farqua 06 3584106 or 021 662203/ Access George Allen 0212290462 Structural roof assesment to be done to confirm possition of two sectors. Power at roof. Rev 2 Requested |  | 2011-09-30 | 2011-06-10 | 2011-06-10 | 2011-09-15 | 2011-09-19 | 2011-09-19 | 2011-09-19 | 2011-09-22 | 2011-09-26 |  | 2011-10-10 | [5 empty] | BUILD | 2011-09-22 | FALSE |  | 2732178 | 6090943 | Cnr Ferguson & Ashley St, Palmerston North |  | RC required due to building exceeding zone height for buildings. No issues anticipated. - 18/02/2011 | CELLSITE |  |  | 2015-04-07 | [12 empty] | 2011-10-25 | 2011-11-11 | 2011-02-22
0 | MNW | 1086 | MNW-040-005 | Cloverlea | MNW-040-005-A | Cloverlea, Admiral Plc | Palmerston North City | 6 | TIER_2 | ACTIVE | GF | DU | P2 | grey | STACK_A | COSITE | 21.3 | 21.8 | 1 | -40.3498 | 175.5846 |  | 2010-09-02 |  | 2010-02-12 | Microwave | MNW-040-003-B | TRUE | TRUE | 2011-03-02 |  | FALSE | 2011-03-18 | 2011-03-16 | 2011-03-16 | 2011-03-21 | 2011-03-22 | 2011-04-19 | 2011-04-16 | 1 | 2011-04-21 | 2011-04-16 | 2011-07-07 | 2011-05-27 | 2011-08-06 | 2011-05-27 | 1 | 2011-06-17 | 2011-08-12 | DISCRETIONARY_RESTRICT | 2011-04-25 | 2011-04-28 | 2011-06-10 | 2011-06-01 | 1 | 2011-08-10 | 2011-06-01 | 2011-06-01 |  | 2011-09-14 | 2011-09-13 | 1 |  | 2011-09-14 | 2011-09-13 | 2011-10-17 |  |  |  |  | 2011-09-21 | 2011-09-21 | 2011-11-04 | 2011-11-18 | 2011-10-14 | 2011-11-05 | 2011-11-05 | [8 empty] | 2011-10-28 | 2011-10-28 | 2011-11-01 | 2011-11-19 | 2011-12-01 | 2012-02-29 | 2012-06-29 |  |  | 2011-11-07 | 2011-08-23 | 2011-08-23 | 2011-10-22 | 2011-10-21 | 2011-10-17 | 2011-10-17 | 2011-10-18 | 2011-10-21 |  | 2011-11-24 | [6 empty] | 2011-10-20 | FALSE |  | 2729518 | 6091912 | 9 Admiral Plc, Cloverlea, Palmerston North |  | Consent req for height - VF site adjacent - 12/04/2011 | CELLSITE |  |  | 2015-04-07 | [12 empty] | 2011-11-25 | 2011-11-24 | 2011-03-22
0 | MNW | 1087 | MNW-040-006 | West End | MNW-040-006-B | West End, VF Colo (West End) | Palmerston North City | 6 | TIER_2 | ACTIVE | COLO | DU | COLO | grey | STACK_A | COLO | 22.5 | 23 | 1 | -40.364 | 175.5994 |  | 2010-09-02 |  | 2010-02-12 | Microwave | MNW-040-003-B | TRUE | TRUE | 2011-02-02 |  | FALSE | 2011-02-24 | 2011-02-17 | 2011-02-17 | 2011-02-21 | 2011-02-28 | 2011-03-17 | 2011-03-23 | 1 | 2011-03-07 | 2011-03-23 | 2011-05-18 | 2011-04-12 | 2011-06-18 | 2011-06-10 | 1 | 2011-05-25 | 2011-06-10 | DISCRETIONARY_RESTRICT | 2011-03-30 | 2011-03-28 | 2011-05-15 | 2011-05-13 | 1 | 2011-06-20 | 2011-05-13 | 2011-06-01 | 2011-07-01 | 2011-06-24 | 2011-07-11 | 1 |  | 2011-07-01 | 2011-07-11 | 2011-09-12 |  |  |  |  | 2011-09-12 | 2011-09-12 | 2011-11-04 | 2011-11-18 | 2011-09-29 | 2011-09-28 | 2011-10-09 | [8 empty] | 2011-10-10 | 2011-09-28 | 2011-10-12 | 2011-09-30 | 2011-11-15 | 2012-02-13 | 2012-06-29 |  | VNZ | 2011-09-28 | 2011-07-27 | 2011-07-27 | 2011-09-11 | 2011-09-18 | 2011-09-12 | 2011-09-12 | 2011-09-28 | 2011-09-29 |  | 2011-10-10 | [6 empty] | 2011-09-28 | FALSE |  | 2730725 | 6090302 | 50 West Street |  | Co-lo preferred to another permitted mast so Council backing this consent - not anticipating any issues. Shrouded and colour matched cable tray and antenna extension. - 24/02/2011 | CELLSITE |  |  | 2015-04-07 | [12 empty] | 2011-10-25 | 2011-11-10
0 | MNW | 1088 | MNW-040-007 |  |  |  | Palmerston North City |  | TIER_9
0 | MNW | 1089 | MNW-040-008 | Massey University PN Campus | MNW-040-008-D | Social science tower | Palmerston North City | 24 | TIER_5 | ACTIVE | RT | DF | RT |  | STACK_A | COSITE |  |  |  | -40.385 | 175.6161 | [6 empty] | FALSE | FALSE |  |  | FALSE |  | 2015-11-19 | 2015-12-07 | 2015-12-21 | 2015-12-21 | 2016-01-29 | 2016-01-28 | 1 |  | 2016-01-28 | 2016-03-04 |  | 2016-04-29 |  |  |  |  | DISCRETIONARY_RESTRICT | 2016-03-18 | 2016-02-01 | 2016-04-22 |  | 1 |  |  | 2016-04-01 |  | 2016-04-29 | [10 empty] | 2016-06-03 |  | 2016-06-30 |  |  | 2016-07-15 | [10 empty] | 2016-08-12 | [16 empty] | 2016-07-29 |  | 2016-02-05 | LOW |  |  |  | BUILD |  | FALSE |  | 2732070 | 6087928 |  |  |  | CELLSITE |  |  |  | ROAMING |  |  |  | 2016-05-06 | [5 empty] | 2016-05-31 |  |  |  | 2015-12-21
0 | MNW | 1090 | MNW-040-009 | Linton | MNW-040-009-B | Linton, VF Colo (Linton) | Palmerston North City | 6 | TIER_2 | ACTIVE | COLO | DU | COLO | flax green | STACK_A | COLO | 23.6 | 25 | 1 | -40.4101 | 175.5811 |  | 2010-09-02 |  | 2010-02-12 | Microwave | MNW-042-002-B | TRUE | TRUE | 2011-02-02 |  | FALSE | 2011-04-01 | 2011-02-17 | 2011-02-17 | 2011-02-22 | 2011-02-22 | 2011-03-11 | 2011-03-14 | 1 | 2011-03-07 | 2011-03-14 | 2011-05-20 | 2011-05-17 | 2011-06-10 | 2011-07-08 | 1 | 2011-06-20 | 2011-07-08 | DISCRETIONARY_RESTRICT | 2011-03-18 | 2011-03-14 | 2011-04-29 | 2011-04-19 | 1 | 2011-06-25 | 2011-04-19 | 2011-06-01 |  | 2011-07-04 | 2011-07-19 | 2 | 1 | 2011-07-08 | 2011-07-21 | 2011-08-31 |  |  |  |  | 2011-08-29 | 2011-08-29 | 2011-11-16 | 2011-11-16 | 2011-09-08 | 2011-11-17 | 2011-11-17 | [8 empty] | 2011-12-04 | 2011-12-09 | 2011-12-08 | 2011-12-01 | 2011-12-19 | 2012-03-19 | 2012-06-29 | Transformer on site possible capacity. | VNZ | 2011-12-02 | 2011-07-08 | 2011-07-27 | 2011-09-11 | 2011-10-18 | 2011-09-04 | 2011-08-31 | 2011-10-28 | 2011-10-28 |  | 2011-12-05 | [6 empty] | 2011-09-08 | FALSE |  | 2729026 | 6085233 | On road to Linton camp |  | Rural permitted height is 15m so co-lo requires RC. Significant existing VF mast so not anticipating any issues. Shrouded cable tray and colour matched. - 18/02/2011 | CELLSITE |  |  | 2015-04-07 | [12 empty] | 2011-12-07 | 2011-12-05 | 2011-02-22
0 | MNW | 1091 | MNW-040-010 | Terrace End | MNW-040-010-A | Terrace End VF Colo (Terrace End) | Palmerston North City | 6 | TIER_2 | ACTIVE | COLO | DU | COLO | grey | STACK_A | COLO | 22.5 | 23 | 1 | -40.3465 | 175.6259 |  | 2010-09-02 |  | 2010-02-12 | Microwave | MNW-040-003-B | TRUE | TRUE | 2011-02-02 |  | FALSE |  | 2011-02-17 | 2011-02-17 | 2011-02-22 | 2011-02-22 | 2011-03-11 | 2011-03-14 | 1 | 2011-03-07 | 2011-03-14 | 2011-04-15 | 2011-04-15 | 2011-06-19 | 2011-06-24 | 1 | 2011-06-20 | 2011-07-08 | DISCRETIONARY_RESTRICT | 2011-03-18 | 2011-03-14 | 2011-04-29 | 2011-04-11 | 1 | 2011-06-24 | 2011-04-11 |  |  | 2011-06-24 | 2011-07-11 | 2 | 1 | 2011-07-01 | 2011-07-21 | 2011-09-12 |  |  |  |  | 2011-09-12 | 2011-09-12 | 2011-10-24 | 2011-11-18 | 2011-09-28 | 2011-09-28 | 2011-10-01 | [8 empty] | 2011-10-07 | 2011-09-28 | 2011-10-12 | 2011-09-30 | 2011-11-15 | 2012-02-13 | 2012-06-29 | Compound extention to allow for car park area. Power from road next to VFNZ. Fibre on site be aware | VNZ | 2011-09-28 | 2011-07-27 | 2011-07-27 | 2011-09-11 | 2011-09-18 | 2011-09-12 | 2011-09-12 | 2011-09-27 | 2011-09-29 |  | 2011-10-10 | [6 empty] | 2011-09-27 | FALSE |  | 2733031 | 6092180 | 242 - 250 Ruahine Street, Terrace End, Palmerston North |  | VF site is slimline pole @ 20m. Our colo will add approx 3-4m so discretionary activity by some margin (14m). Will likely seek to use external visual assessment to bolster the application and reduce chances of affected parties being notified. Council land also adjacent. - 18/02/2011 | CELLSITE |  |  | 2015-04-07 | [12 empty] | 2011-10-25 | 2011-11-11 | 2011-02-22
0 | MNW | 1092 | MNW-040-011 | Coronation Park | MNW-040-011-B | Holden Corner Floodlight Replacement | Palmerston North City | 6 | TIER_2 | ACTIVE | GF | DU | P2 | grey | STACK_A | STANDALONE | 19.5 | 20 | 1 | -40.3427 | 175.602 |  | 2010-09-02 |  | 2010-02-12 | Microwave | MNW-040-003-B | TRUE | TRUE | 2011-02-14 |  | FALSE | 2011-02-22 | 2011-03-17 | 2011-02-17 | 2011-02-28 | 2011-02-28 | 2011-03-21 | 2011-03-23 | 1 | 2011-04-07 | 2011-03-23 | 2011-05-12 | 2011-04-12 | 2011-06-12 | 2011-05-17 |  | 2011-05-25 | 2011-05-17 | PERMITTED | 2011-03-30 | 2011-03-28 | 2011-05-05 | 2011-04-19 | 1 | 2011-05-25 | 2011-04-19 | 2011-06-01 | 2011-07-01 | 2011-06-24 | 2011-07-12 | 1 |  | 2011-07-01 | 2011-07-12 | 2011-08-30 |  |  |  |  | 2011-09-04 | 2011-08-10 | 2011-08-15 | 2011-08-15 | 2011-09-03 | 2011-09-19 | 2011-09-19 | [8 empty] | 2011-09-29 | 2011-09-28 | 2011-10-12 | 2011-09-30 | 2011-11-15 | 2012-02-13 | 2012-06-29 |  |  | 2011-09-27 | 2011-07-27 | 2011-07-27 | 2011-09-11 | 2011-09-18 | 2011-08-24 | 2011-08-30 | 2011-09-14 | 2011-09-16 |  | 2011-10-10 | [6 empty] | 2011-09-03 | FALSE |  | 2731018 | 6092663 | Holden Corner 541-543 Cnr Tremaine Ave/Rangitikei Line Coronation Park, Palmerston North |  | Permitted activity proposed here. Replacement of exisiting car yard floodlight. Require painted grey and no climbing pegs - cherry picker access so no issues with this. - 24/02/2011 | CELLSITE |  |  | 2015-04-07 | [12 empty] | 2011-10-25 | 2011-11-10 | 2011-02-24
0 | MNW | 1093 | MNW-040-012 | Hokowhitu | MNW-040-012-E | LPR at Roundabout | Palmerston North City | 6 | TIER_2 | ACTIVE | RSR | DU | P4F |  | STACK_A | STANDALONE |  |  | 2 | -40.3626 | 175.6337 |  | 2010-09-02 |  | 2010-02-12 |  |  | TRUE | TRUE | 2011-03-02 |  | FALSE |  | 2011-05-05 | 2012-04-05 | 2011-05-10 | 2012-04-27 | 2012-05-10 | 2012-07-04 | 2 | 2012-05-14 | 2014-11-24 | 2011-06-26 | 2012-06-15 | 2011-07-26 | 2012-08-02 | 1 | 2011-07-31 | 2012-08-02 | PERMITTED | 2011-07-03 | 2012-07-05 | 2011-08-18 | 2012-11-16 | 1 | 2011-08-23 | 2012-11-16 |  |  | 2012-08-17 | 2012-09-10 | 1 |  | 2012-08-17 | 2012-09-10 | 2012-08-23 |  |  |  |  | 2012-09-10 | 2012-09-07 | 2012-09-24 | 2012-10-24 | 2012-09-18 | 2012-09-20 | 2012-09-20 | [8 empty] | 2012-10-09 | 2012-10-15 | 2012-10-12 | 2012-11-03 | 2012-10-31 | 2013-05-25 | 2013-05-23 |  |  | 2012-10-02 | 2012-06-28 | 2012-06-28 | 2012-08-10 | 2012-08-13 | 2012-08-21 | 2012-08-23 | 2012-09-19 | 2012-09-19 |  | 2012-10-12 | 2012-07-05 | HIGH |  |  |  | BUILD | 2012-09-18 | FALSE |  | 2733643 | 6090374 | Lightpole at corner of Pahiatua St/Albert St southside Hokowhitu Palmerston North |  | NES LPR with cabinets in private property - 05/07/2012 | CELLSITE |  |  | 2015-04-07 | [12 empty] | 2012-09-29 | 2012-10-17 | 2012-04-27
0 | MNW | 1094 | MNW-040-013 | Takaro | MNW-040-013-A | Manawatu Trotting Club VF Colo | Palmerston North City | 6 | TIER_2 | ACTIVE | COLO | DU | COLO | grey | STACK_A | COLO | 28 | 28.5 | 1 | -40.367 | 175.5718 |  | 2010-09-02 |  | 2010-02-12 | Microwave | MNW-040-003-B | TRUE | TRUE | 2011-02-02 |  | FALSE |  | 2011-03-17 | 2011-02-17 | 2011-03-22 | 2011-02-22 | 2011-04-08 | 2011-03-14 | 1 | 2011-04-07 | 2011-03-14 | 2011-06-08 | 2011-05-17 | 2011-07-07 | 2011-06-10 | 1 | 2011-07-12 | 2011-06-10 | DISCRETIONARY_RESTRICT | 2011-04-15 | 2011-03-14 | 2011-05-27 | 2011-04-19 | 1 | 2011-07-15 | 2011-04-19 |  |  | 2011-06-24 | 2011-07-11 | 2 | 1 | 2011-07-01 | 2011-07-21 | 2011-08-18 |  |  |  |  | 2011-08-20 | 2011-08-20 | 2011-11-04 | 2011-11-18 | 2011-08-20 | 2011-09-27 | 2011-10-01 | [8 empty] | 2011-10-05 | 2011-10-25 | 2011-11-01 | 2011-09-30 | 2011-11-15 | 2012-02-13 | 2012-06-29 | Long Power run (180m). Would require a services markout to be recorded on the PD | VNZ | 2011-09-27 | 2011-07-27 | 2011-07-27 | 2011-09-11 | 2011-09-18 | 2011-08-18 | 2011-08-18 | 2011-09-22 | 2011-09-20 |  | 2011-11-14 | [6 empty] | 2011-08-20 | FALSE |  | 2728372 | 6090040 | 401 Poineer Hwy, Takaro, Palmerston North |  | Rural zone so 15m permitted height is exceeded and RC required. Not anticipating any issues due to significant existing VF structure and location away from residences. Cable tray shrouded and colour matched. - 18/02/2011 | CELLSITE |  |  | 2015-04-07 | [12 empty] | 2011-10-25 | 2011-11-11 | 2011-02-22
0 | MNW | 1095 | MNW-040-014 | Palmerston North |  |  | Palmerston North City |  | TIER_9 | [22 empty] | FALSE
0 | MNW | 1096 | MNW-040-015 | Fitzherbert | MNW-040-015-C | Turitea TNZ Colo | Palmerston North City | 6 | TIER_2 | ACTIVE | COLO | DU | LATTICE |  | STACK_A | COLO | 32 | 33.9 | 1 | -40.39 | 175.6384 |  | 2010-09-02 |  | 2010-02-12 | Microwave | MNW-040-004-A | TRUE | TRUE | 2011-02-15 |  | FALSE | 2011-07-08 | 2011-06-15 | 2011-06-15 | 2011-06-16 | 2011-06-16 | 2011-07-23 | 2011-08-05 | 4 | 2011-07-27 | 2014-11-24 | 2012-03-10 | 2012-02-20 | 2012-03-12 | 2012-02-20 |  | 2012-03-22 | 2012-02-20 | DISCRETIONARY_RESTRICT | 2011-09-20 | 2011-09-08 | 2012-03-20 | 2012-03-14 | 2 | 2012-03-20 | 2012-03-14 |  |  | 2012-02-28 | 2012-06-13 | 1 |  | 2012-02-28 | 2012-06-13 | 2012-06-28 |  |  |  |  | 2012-04-10 | 2012-04-10 | 2012-04-30 | 2012-06-28 | 2012-04-30 | 2012-05-07 | 2012-05-25 | [8 empty] | 2012-05-25 | 2012-05-25 | 2012-06-01 | 2012-06-29 | 2012-06-28 | 2013-08-25 | 2013-12-03 |  | TNZ | 2012-05-11 | 2012-01-06 | 2012-01-06 | 2012-01-12 | 2012-02-20 | 2012-04-21 | 2012-06-28 | 2012-04-25 | 2012-04-25 |  | 2012-05-30 | [5 empty] | BUILD | 2012-04-23 | FALSE |  | 2733954 | 6087317 | Turitea TNZ COLO, Pacific Drive, Fitzherbert, Palmerston North |  | Telecom designation number 22, radiocommunication and telecommunications purposes. Telecom didn't agree to do OPW so RC with s176 it is. - 09/09/2011 | CELLSITE |  |  | 2015-04-07 | [12 empty] | 2012-05-21 | 2012-06-11
0 | MNW | 1097 | MNW-040-016 | Palmerston North Air | MNW-040-016-F | 28 Armstrong Street | Palmerston North City | 6 | TIER_2 | ACTIVE | GF | DU | P2 | grey | STACK_A | STANDALONE | 22.7 | 23.2 | 2 | -40.3279 | 175.6331 |  | 2010-09-02 |  | 2010-02-12 | Microwave | MNW-040-003-B | TRUE | TRUE | 2011-02-15 |  | FALSE | 2011-06-03 |  | 2011-06-01 |  | 2011-06-08 | 2011-06-17 | 2011-06-17 | 3 | 2011-06-20 | 2015-01-13 | 2011-06-25 | 2011-06-24 | 2011-07-20 | 2011-07-14 | 1 | 2011-07-30 | 2011-07-14 | DISCRETIONARY_RESTRICT | 2011-06-25 | 2011-06-15 | 2011-07-25 | 2011-07-12 | 1 | 2011-12-17 | 2012-02-20 |  |  | 2011-09-14 | 2011-09-13 | 1 |  | 2011-09-14 | 2011-09-13 | 2011-10-17 |  |  |  |  | 2011-10-17 | 2011-10-12 | 2011-11-30 | 2011-11-24 | 2011-10-31 | 2011-11-05 | 2011-11-06 | [8 empty] | 2011-11-05 | 2011-11-18 | 2011-11-15 | 2011-11-19 | 2011-12-08 | 2012-03-07 | 2012-06-29 |  |  | 2011-11-06 | 2011-08-23 | 2011-06-10 | 2011-10-22 | 2011-10-30 | 2011-10-14 | 2011-10-17 | 2011-11-01 | 2011-11-03 |  | 2011-11-28 | [6 empty] | 2011-10-27 | FALSE |  | 2733709 | 6094228 | 28 Armstrong Street Palmerston North |  |  | CELLSITE |  |  | 2015-04-07 | [12 empty] | 2011-11-28 | 2011-11-28 | 2011-06-01
0 | MNW | 1098 | MNW-040-017 | Ashhurst | MNW-040-017-C | OnTrack Monopole | Palmerston North City | 6 | TIER_2 | ACTIVE | GF | DU | T2 20 UF | green | STACK_A | STANDALONE | 23 | 24.5 | 1 | -40.297 | 175.7512 |  |  |  |  | Microwave | MNW-040-003-B | TRUE | TRUE |  |  | FALSE | 2011-04-01 | 2011-04-07 | 2011-04-07 | 2011-04-22 | 2011-04-26 | 2011-05-13 | 2011-05-31 | 2 | 2011-05-12 | 2014-04-08 | 2011-06-18 | 2011-06-10 | 2011-07-18 | 2011-07-01 |  | 2011-07-13 | 2011-07-01 | DISCRETIONARY_RESTRICT | 2011-05-20 | 2014-05-05 | 2011-06-27 | 2014-05-05 | 2 | 2011-07-18 | 2011-07-08 |  |  | 2011-08-30 | 2011-09-13 | 2 |  | 2011-08-30 | 2011-12-07 | 2011-12-01 |  |  |  |  | 2011-10-25 | 2011-10-21 | 2011-12-20 | 2011-12-07 | 2011-11-07 | 2011-12-09 | 2011-12-12 | [8 empty] | 2011-12-12 | 2011-12-16 | 2011-12-14 | 2011-11-19 | 2012-01-19 | 2013-04-25 | 2013-04-30 |  |  | 2011-12-09 | 2011-08-23 | 2011-08-23 | 2011-10-24 | 2011-10-24 | 2011-12-05 | 2011-12-01 | 2011-12-06 | 2011-12-06 |  | 2011-12-14 | [6 empty] | 2011-11-14 | FALSE |  | 2743844 | 6097348 | Railway Site, Railway corridor, York Street, Ashhurst |  | ood permitted baseline here and co-location, but res in clsoe proximity and potential issues with limited notification. - 01/04/2011 | CELLSITE | [15 empty] | 2011-12-13 | 2011-12-23 | 2011-04-26
0 | MNW | 1099 | MNW-040-018 | Awapuni South | MNW-040-018-D | Dr Ting | Palmerston North City | 6 | TIER_2 | ACTIVE | RSR | DU | P4F | green | INLINE | STANDALONE | 14.3 | 14.3 |  | -40.3734 | 175.5911 |  | 2010-09-02 |  | 2010-02-12 | Microwave | MNW-040-004-A | TRUE | TRUE | 2011-02-02 |  | FALSE | 2011-06-10 |  | 2011-06-15 |  | 2011-06-21 |  | 2011-07-08 | 2 | 2011-07-01 | 2014-11-24 | 2011-09-05 | 2011-09-29 | 2011-10-05 | 2011-09-29 | 1 | 2011-10-05 | 2011-09-29 | NES |  | 2011-07-12 | 2011-08-15 | 2011-08-10 | 1 | 2011-08-15 | 2011-08-10 |  |  | 2011-11-04 | 2011-12-09 | 1 |  | 2011-11-04 | 2011-12-09 | 2011-11-04 |  |  |  |  | 2011-12-02 | 2011-12-01 | 2011-12-23 | 2011-12-23 | 2011-12-09 | 2011-12-14 | 2011-12-14 | [8 empty] | 2011-12-14 | 2011-12-16 | 2011-12-14 | 2012-01-27 | 2012-01-19 | 2013-09-15 | 2013-11-14 |  |  | 2011-12-14 | 2011-11-18 | 2011-12-01 | 2011-11-30 | 2011-12-05 | 2011-11-11 | 2011-11-04 | 2011-12-13 | 2011-12-13 |  | 2011-12-14 | [5 empty] | BUILD | 2011-12-07 | FALSE |  | 2729991 | 6089283 | College St Awapuni Palmerston North |  |  | CELLSITE |  |  | 2015-04-07 | [12 empty] | 2012-01-15 | 2011-12-23 | 2011-06-21
0 | MNW | 1100 | MNW-040-019 | RBI - Ashurst |  |  | Palmerston North City |  | RBI | [22 empty] | FALSE
0 | MNW | 1101 | MNW-040-020 | Hokowhitu University | MNW-040-020-A | Active Candidate for forecasting | Palmerston North City | 23 | TIER_5 | ACTIVE | [5 empty] | COSITE | [11 empty] | FALSE | FALSE |  |  | FALSE |  | 2016-03-31 | [58 empty] | RF Engineer - Chris Rowley. 10/2/16 - Site search brief issued | [19 empty] | FALSE | [7 empty] | WIPACTIVE |  |  | CAPACITY
0 | MNW | 1102 | MNW-041-001 | NOR |  |  | Tararua District |  | TIER_9 | [22 empty] | FALSE
0 | MNW | 1103 | MNW-041-002 | Dannevirke | MNW-041-002-A | Dannervirke VNZ CoLo | Tararua District | 6 | TIER_3 | ACTIVE | COLO | DU | COLO |  | STACK_A | COLO |  |  | 1 | -40.2012 | 176.0857 |  | 2012-02-02 |  |  | Microwave | MNW-041-003-A | FALSE | FALSE |  |  | FALSE |  | 2012-03-06 | 2012-03-06 | 2012-03-20 | 2012-03-08 | 2012-04-28 | 2012-07-11 | 1 | 2012-05-01 | 2012-07-11 | 2012-10-20 | 2012-10-16 | 2012-10-20 | 2012-10-16 |  | 2012-10-20 | 2012-10-16 | PERMITTED | 2012-05-07 | 2012-07-11 | 2012-06-07 | 2012-07-11 | 1 | 2012-06-11 | 2012-07-11 |  |  | 2012-09-11 | 2012-09-12 | 1 |  | 2012-09-11 | 2012-09-12 | 2012-10-19 |  |  |  |  | 2012-10-15 | 2012-10-12 | 2012-11-02 | 2012-10-26 | 2012-10-19 | 2012-11-25 | 2012-11-06 | [8 empty] | 2013-02-27 | 2013-03-15 | 2013-03-08 | 2013-03-15 | 2013-03-15 | 2013-07-13 | 2013-07-03 |  | VNZ | 2013-02-26 |  |  | 2012-09-22 | 2012-10-19 | 2012-09-29 | 2012-10-19 | 2013-02-11 | 2013-02-15 | 2013-03-10 | 2013-03-04 | 2012-07-11 | LOW | NAPIER_DANNEVIRKE |  |  | BUILD | 2012-11-02 | FALSE |  | 2772643 | 6107041 | Rule Road, Dannevirke |  |  | CELLSITE | [15 empty] | 2013-03-01 | 2013-03-01
0 | MNW | 1104 | MNW-041-003 | Wharite | MNW-041-003-A | Wharite - Kordia Colo | Tararua District | 6 | TIER_3 | ACTIVE | COLO | DU | LATTICE |  | STACK_A | COLO |  |  | 2 | -40.2553 | 175.8574 |  | 2011-12-19 |  |  | Microwave | MNW-040-001-B | FALSE | FALSE |  |  | FALSE |  | 2012-03-06 | 2012-03-06 | 2012-04-26 | 2012-04-16 | 2012-11-15 | 2012-11-12 | 1 | 2012-11-15 | 2012-11-12 | 2012-11-15 | 2012-11-23 | 2012-11-18 | 2012-11-23 |  | 2013-04-01 |  | OPW | 2012-11-20 | 2012-11-26 | 2012-11-20 | 2012-11-26 | 1 | 2012-11-25 | 2012-11-26 |  |  | 2013-01-03 | 2013-02-12 | 1 |  |  | 2013-02-12 | [5 empty] | 2013-01-21 | 2013-01-07 | 2013-08-10 | 2013-08-01 | 2013-02-19 | 2013-08-15 | 2013-08-23 | [9 empty] | 2013-08-15 | 2013-09-04 | 2013-09-23 | 2013-09-23 | 2013-08-27 | 2013-12-20 |  | KDA | 2013-07-15 | [8 empty] | 2013-08-15 | 2013-08-23 | 2012-11-26 | LOW | WAIRARAPA |  |  | BUILD | 2013-01-25 | FALSE |  | 2753022 | 6101686 | Wharite |  | Designated Kordia site, their OPW - 26/11/2012 | CELLSITE
0 | MNW | 1105 | MNW-041-004 |  |  |  | Tararua District |  | TIER_9
0 | MNW | 1106 | MNW-041-005 | Pahiatua | MNW-041-005-A | Paihiatua - VF Colo | Tararua District | 6 | TIER_3 | ACTIVE | COLO | DU | COLO |  | STACK_A | COLO |  |  | 1 | -40.4247 | 175.852 |  | 2012-01-25 |  |  | Microwave | MNW-041-003-A | FALSE | FALSE |  |  | FALSE |  | 2012-03-06 | 2012-03-07 | 2012-04-20 | 2012-04-26 | 2012-06-26 | 2012-07-03 | 1 | 2012-06-26 | 2012-07-03 | 2012-06-23 | 2012-07-19 | 2012-10-12 | 2012-10-15 |  | 2012-10-12 | 2012-10-16 | DISCRETIONARY_FULL | 2012-07-11 | 2012-07-11 | 2012-08-11 | 2012-08-16 | 1 | 2012-08-11 | 2013-03-01 |  |  | 2012-08-24 | 2012-09-10 | 2 | 1 | 2013-05-28 | 2013-06-17 | 2012-10-01 |  |  |  |  | 2013-01-25 | 2013-01-29 | 2013-02-15 | 2013-02-15 | 2013-02-15 | 2013-05-28 | 2013-06-13 | [8 empty] | 2013-06-10 | 2013-06-30 | 2013-06-21 | 2013-07-01 | 2013-06-28 | 2013-09-27 | 2013-10-23 |  | VNZ | 2013-03-29 | 2012-09-21 |  | 2012-10-31 | 2012-10-22 | 2012-09-11 | 2012-10-01 | 2013-01-28 | 2013-01-29 | 2013-06-07 | 2013-06-13 | 2012-04-16 | LOW | WAIRARAPA |  |  | BUILD | 2013-02-15 | FALSE |  | 2751950 | 6082900 | Pahiatua PIA West Road Mangatainoka |  |  | CELLSITE | [15 empty] | 2013-06-07 | 2013-06-14
0 | MNW | 1107 | MNW-041-006 |  |  |  | Tararua District |  | TIER_9
0 | MNW | 1108 | MNW-042-001 | Levin | MNW-042-001-B | Levin VF Colo | Horowhenua District | 6 | TIER_2 | ACTIVE | COLO | DU | COLO | grey | STACK_A | COLO | 20 | 23 | 1 | -40.6495 | 175.3474 |  |  |  |  | Microwave | MNW-042-003-A | FALSE | FALSE |  |  | FALSE | 2011-04-01 | 2011-03-31 | 2011-03-30 | 2011-04-18 | 2011-04-26 | 2011-05-13 | 2011-05-24 | 4 | 2011-05-14 | 2012-11-26 | 2011-10-21 | 2011-10-25 | 2011-12-05 | 2011-12-12 |  | 2011-12-05 | 2012-02-20 | NON_COMPLYING_FULL | 2011-05-20 | 2011-05-27 | 2011-06-29 | 2011-06-23 | 1 | 2011-07-11 | 2011-06-23 |  | 2011-07-29 | 2011-07-08 | 2011-07-29 | 2 |  | 2011-07-15 | 2011-10-17 | 2011-11-25 |  |  |  |  | 2012-01-11 | 2012-01-13 | 2012-02-03 | 2012-02-03 | 2012-01-27 | 2012-02-03 | 2012-02-04 | [8 empty] | 2012-02-03 | 2012-02-12 | 2012-02-16 | 2012-02-10 | 2012-02-29 | 2013-05-25 | 2013-05-29 |  | VNZ | 2012-02-03 | 2011-07-27 | 2011-07-27 | 2011-09-26 | 2012-01-27 | 2011-11-25 | 2011-11-25 | 2012-02-01 | 2012-02-01 | 2012-02-12 | 2012-02-20 | [5 empty] | BUILD | 2012-01-30 | FALSE |  | 2708485 | 6059214 | Gladstone Road Levin |  | Tararua Range Outstanding Natural Landscape and breaches permitted height of 3m. - 26/04/2011 | CELLSITE |  |  | 2015-04-02 | [12 empty] | 2012-02-27 | 2012-02-20 | 2011-04-26
0 | MNW | 1109 | MNW-042-002 | Tokomaru | MNW-042-002-B | VFNZ Tokomaru Colo | Horowhenua District | 6 | TIER_2 | ACTIVE | COLO | DU | COLO | grey | STACK_A | COLO | 29 | 30 | 1 | -40.4805 | 175.544 |  |  |  |  | Microwave | MNW-040-004-A | FALSE | FALSE |  |  | FALSE | 2011-07-12 | 2011-03-30 | 2011-03-30 | 2011-04-18 | 2011-04-26 | 2011-05-13 | 2011-05-23 | 1 | 2011-05-15 | 2011-05-23 | 2011-09-29 | 2011-09-22 | 2011-09-29 | 2011-09-22 |  | 2011-09-29 | 2011-10-10 | DISCRETIONARY_FULL | 2011-05-20 | 2011-05-27 | 2011-06-29 | 2011-06-27 | 1 | 2011-12-16 | 2012-02-21 |  |  | 2011-07-08 | 2011-07-29 | 1 |  | 2011-07-15 | 2011-07-29 | 2011-10-03 |  |  |  |  | 2011-11-10 | 2011-11-11 | 2011-11-30 | 2011-11-21 | 2011-11-20 | 2011-12-02 | 2011-12-04 | [8 empty] | 2011-12-04 | 2011-12-09 | 2011-12-08 | 2011-12-01 | 2011-12-19 | 2012-03-19 | 2012-06-29 |  | VNZ | 2011-12-04 | 2011-07-27 | 2011-07-27 | 2011-10-14 | 2011-10-18 | 2011-09-12 | 2011-10-03 | 2011-11-25 | 2011-11-25 |  | 2011-12-06 | [6 empty] | 2011-11-15 | FALSE |  | 2725650 | 6077506 | 113-135 Williams Rd Tokomaru Rural |  | Within Hill Country High Amenity Landscape - PC22 - 26/04/2011 | CELLSITE | [15 empty] | 2011-12-07 | 2011-12-06 | 2011-04-26
0 | MNW | 1110 | MNW-042-003 | Levin Central (Main HUB) | MNW-042-003-A | Levin Central VF Colo | Horowhenua District | 6 | TIER_2 | ACTIVE | COLO | DU | COLO | grey | STACK_A | COLO | 23.5 | 24 | 1 | -40.6211 | 175.2866 |  |  |  |  | Fibre Optic | WLG-047-071-A | FALSE | FALSE |  |  | FALSE | 2011-04-01 | 2011-03-31 | 2011-03-30 | 2011-04-18 | 2011-04-26 | 2011-05-13 | 2011-05-12 | 1 | 2011-05-13 | 2011-05-12 | 2011-06-04 | 2011-07-01 | 2011-07-04 | 2011-07-01 | 1 | 2011-07-09 | 2011-07-01 | DISCRETIONARY_RESTRICT | 2011-05-20 | 2011-05-27 | 2011-06-29 | 2011-06-28 | 1 | 2011-07-04 | 2011-06-28 |  |  | 2011-07-08 | 2011-07-29 | 2 |  | 2011-07-15 | 2011-08-17 | 2011-11-01 |  |  |  |  | 2011-11-09 | 2011-11-09 | 2011-11-30 | 2011-12-04 | 2011-11-20 | 2011-11-30 | 2011-12-04 | [8 empty] | 2011-12-04 | 2011-12-09 | 2011-12-08 | 2011-12-01 | 2011-12-19 | 2012-03-19 | 2012-06-29 |  | VNZ | 2011-12-01 | 2011-07-27 | 2011-07-27 | 2011-11-16 | 2011-11-14 | 2011-10-25 | 2011-11-01 | 2011-11-28 | 2011-11-28 |  | 2011-12-06 | [6 empty] | 2011-11-10 | FALSE |  | 2703430 | 6062498 | 249-255 Oxford Street, Levin |  | Exceeds height control for masts in the COmmercial zone so requires consent. Discretion limited to areas of non-compliance so will need to justify height - 12/04/2011 | CELLSITE |  |  | 2015-04-02 | [12 empty] | 2011-12-07 | 2011-12-06 | 2011-04-26
0 | MNW | 1111 | MNW-042-004 | Pukehou | MNW-042-004-A | Pukehou Telecom Colo | Horowhenua District | 6 | TIER_3 | ACTIVE | COLO | TX | COLO |  | INLINE | COSITE |  |  |  | -40.7424 | 175.1898 | [6 empty] | TRUE | TRUE |  |  | TRUE |  |  | 2013-02-12 |  | 2013-02-12 |  | 2013-02-18 | 1 |  | 2013-02-18 |  | 2013-02-12 |  | 2013-02-13 |  | 2014-04-01 |  |  |  | 2013-02-18 |  | 2013-02-18 | 1 |  | 2013-02-18 | [13 empty] | 2013-02-01 | 2013-02-01 | 2013-02-05 | 2013-02-05 | 2013-02-07 | 2013-02-14 | 2013-02-14 | [10 empty] | 2013-03-07 |  | 2013-09-25 |  | 2013-06-11 | Transmission only site for Manukau Straights |  | 2013-02-15 | [9 empty] | 2013-03-07 |  |  | TRANSMISSION_ONLY |  |  | BUILD | 2013-02-07 | FALSE |  | 2694907 | 6049251 |  |  |  | TXSITE
0 | MNW | 1112 | MNW-042-005 | Manakau Straigh | MNW-042-005-B | Manakau GF | Horowhenua District | 6 | TIER_3 | ACTIVE | GF | DU | T2 15 UF |  | STACK_A | STANDALONE | 22.3 | 23 | 1 | -40.7077 | 175.2173 |  |  |  |  | Microwave | WLG-043-011-A | FALSE | FALSE |  |  | FALSE |  | 2011-10-27 | 2011-10-27 | 2011-11-03 | 2011-11-14 | 2012-02-13 | 2012-02-13 | 1 | 2012-02-13 | 2012-02-13 | 2012-02-14 | 2012-02-02 | 2012-02-28 | 2012-03-09 | 1 | 2012-02-28 | 2012-03-09 | DISCRETIONARY_RESTRICT | 2012-02-25 | 2012-02-14 | 2012-03-21 | 2012-04-13 | 1 | 2012-03-21 | 2012-04-13 |  |  |  | 2012-07-17 | 1 |  |  | 2012-07-17 | 2012-07-12 |  |  |  |  | 2012-06-14 | 2012-06-14 | 2012-07-20 | 2012-07-23 | 2012-07-19 | 2013-02-01 | 2012-07-27 | [8 empty] | 2013-02-20 | 2013-03-08 | 2013-03-07 | 2013-03-09 | 2013-03-08 | 2013-07-05 | 2013-06-11 | This site is dependent on the Pukehou Telecom Repeater |  | 2013-02-19 | 2012-06-05 |  | 2012-06-29 | 2012-07-12 | 2012-06-28 | 2012-07-12 | 2012-07-20 | 2012-07-24 | 2013-03-05 | 2013-02-22 |  |  | FIELDING |  |  | BUILD | 2012-07-18 | FALSE |  | 2697324 | 6053045 | 962 Levin South Rd, Levin |  |  | CELLSITE | [15 empty] | 2013-02-21 | 2013-02-22
0 | MNW | 1113 | MNW-042-006 | Foxton | MNW-042-006-A | Watertower | Horowhenua District | 6 | TIER_2 | ACTIVE | BO | DF | BO | grey | STACK_A | COSITE | 21.2 | 30 | 1 | -40.4781 | 175.2821 |  |  |  |  | Microwave | MNW-042-002-B | FALSE | FALSE |  |  | FALSE | 2011-04-19 | 2011-03-30 | 2011-03-30 | 2011-04-18 | 2011-04-26 | 2011-06-20 | 2011-07-01 | 1 | 2011-06-27 | 2011-07-01 | 2011-10-09 | 2011-10-06 | 2011-10-09 | 2011-10-06 | 1 | 2011-10-15 | 2011-10-06 | DISCRETIONARY_RESTRICT | 2011-06-30 | 2011-07-13 | 2011-09-07 | 2011-09-29 | 1 | 2011-09-07 | 2011-09-29 |  | 2012-02-15 | 2012-03-02 | 2012-02-02 | 1 |  | 2012-03-02 | 2012-02-02 | 2012-02-28 |  |  |  |  | 2011-12-20 | 2011-12-20 | 2012-03-16 | 2012-03-13 | 2012-02-20 | 2012-02-27 | 2012-03-01 | [8 empty] | 2012-03-01 | 2012-02-25 | 2012-03-12 | 2012-02-27 | 2012-03-26 | 2013-05-25 | 2013-05-23 |  |  | 2012-03-01 | 2012-01-06 | 2012-01-06 | 2012-02-07 | 2012-02-10 | 2012-02-21 | 2012-02-28 | 2012-02-23 | 2012-02-28 |  | 2012-03-16 | [5 empty] | BUILD | 2012-02-22 | FALSE |  | 2703461 | 6078383 | Foxton Watertower, Harbour Street, Foxton |  | Exceeds residential height limit of 13.5m. - 26/04/2011 | CELLSITE | [15 empty] | 2012-03-09 | 2012-03-16 | 2011-04-26
0 | MNW | 1114 | MNW-042-007 | Pukehou |  |  | Horowhenua District |  | TIER_3 | [83 empty] | Transmission Hub only
0 | MNW | 1115 | MNW-042-008 | Cellutronics 008 |  |  | Horowhenua District |  | TIER_6 | [83 empty] | Jongeneel transport 104 Hoggs Road, Ohau, Levin. Contact: Sarah (or Renee) 0-6-367 2130 or 027 5147782) (also 027 442 4019) On air 30 May 2013
0 | MNW | 1116 | MNW-042-009 | Levin South | MNW-042-009-A | Levin South - Crightons | Horowhenua District | 24 | 2015P | ACTIVE | GF | DU5 | T2 25 UF |  | STACK_A | STANDALONE | 23 | 25 |  | -40.633 | 175.2715 |  | 2015-04-23 |  | 2015-04-23 | Leased Line | MNW-042-003-A | FALSE | FALSE |  |  | FALSE |  | 2014-08-27 | 2014-08-28 | 2014-09-02 | 2014-09-04 | 2014-09-15 | 2014-10-02 | 1 | 2014-09-30 | 2014-10-02 | 2014-10-02 | 2014-10-02 | 2015-02-04 | 2015-01-12 |  | 2015-02-04 | 2015-01-12 | PERMITTED | 2014-10-17 | 2014-11-21 | 2014-12-19 | 2014-12-04 | 1 | 2014-12-19 | 2014-12-04 | 2014-11-14 | 2014-11-14 | 2015-01-21 | 2015-01-15 | 1 |  | 2015-01-21 | 2015-01-15 |  |  |  | 2015-06-30 |  | 2015-07-01 | 2015-07-03 | 2015-08-10 | 2015-08-10 | 2015-08-04 | 2015-08-12 | 2015-08-13 | 2015-08-07 | 2015-08-25 | 2015-08-04 | 2015-08-04 | 2015-07-28 | 2015-07-28 | 2015-07-28 | 2015-07-28 |  | 2015-09-30 | 2015-09-30 |  |  |  |  | HARD MATCH ONLY 08.08.14 Stefan has done site search. 1 candidate identified. Landlord willing. Stefan to speak to Vaughan to see when we can Caravan Caravan is complete, all agree this is the best site. PDI issued. 13/08 AS Delay by a week due to power 16/04: TX PO raised waiting for Huawei equipment's to turn up. 19/03: need to put tender out Vaughan terms agreed for rental at $7k. Lease progressing well. CD to comence after geotech and contamination report Geotech drill 29th Oct. 4 Nov lease with LO for signature. 6 Jan requires lease completion and approval to build | [10 empty] | 2015-09-14 | 2015-09-11 | 2014-12-08 | LOW |  | 2015-07-28 | 2015-07-28 | BUILD | 2015-08-04 | TRUE | 2015-08-06 | 2702115 | 6061210 | Coventry Street Levin |  |  | CELLSITE |  |  | 2015-09-30 | CAPACITY |  | 2015-03-11 | 2015-05-19 | 2015-05-06 | 2015-05-06 |  |  |  |  | 2015-06-12 | 2015-06-12 |  |  | 2014-09-04
0 | MNW | 1117 | MNW-042-010 | Shannon RBI | MNW-042-010-A | Shannon RBI | Horowhenua District | 24 | TIER_4 | ACTIVE | RBI | DF |  |  |  | COLO |  | 25 |  | -40.5373 | 175.4263 |  | 2015-05-11 |  |  |  |  | FALSE | FALSE |  |  | FALSE |  | 2015-05-21 | 2015-05-21 | 2015-05-21 | 2015-05-21 | 2015-05-29 | 2015-05-21 | 1 | 2015-05-29 | 2015-05-21 | 2015-05-21 | 2015-05-21 | 2015-05-21 | 2015-06-23 |  | 2015-05-21 | 2015-06-23 | PERMITTED | 2015-05-22 | 2015-05-27 | 2015-05-26 | 2015-05-27 | 1 | 2015-06-05 | 2015-06-02 | 2015-05-21 | 2015-05-28 | 2015-06-08 | 2015-07-16 | 1 |  | 2015-06-19 | 2015-07-16 | [5 empty] | 2015-07-20 | 2015-07-20 | 2015-07-23 | 2015-07-23 | 2015-07-20 | 2015-08-05 | 2015-08-05 | 2015-07-23 | 2015-07-22 | 2015-07-10 | 2015-07-22 | 2015-07-10 | 2015-07-08 | 2015-07-24 | 2015-07-22 |  | 2015-08-20 | 2015-08-18 |  | 2015-10-22 |  |  | Rapid Access RBI site. Construction start is blind guess TX ordered 3 June. 3 June: POR issued RFS date 23 July. 19 June: VF approval to build received 23 June: TX CX Config issue so TX delivery failed. Retry 27th July. 31 July: Integration planned 20 July: Equip delivered & build started 23 July: Fibre & power delivered, TX integration failed 24 July TX issue fixed 31 July: Integration re-scheduled 4 Aug: Ret motor issue. Vol4 data incomplete. 10 Aug: Major snag with clock/ATN. With Huawei to fix. | VNZ | [9 empty] | 2015-08-14 | 2015-08-14 |  |  |  | 2015-07-23 | 2015-07-23 | BUILD | 2015-07-20 | FALSE |  | 2715500 | 6071487 | State Highway 57 |  |  | CELLSITE |  |  |  | ROAMING |  |  | 2015-06-12 | 2015-05-20 | 2015-05-20 | 2015-05-18 | 2015-05-18 | 2015-06-03 | 2015-06-03 | 2015-06-03 | 2015-06-12 |  |  | 2015-05-21
0 | NTH | 1118 | NTH-001-001 | Mt Hikurangi |  |  | Far North |  | TIER_9 | [22 empty] | FALSE | [60 empty] | The primary requirement is to mitigate roaming cost. Site therefore needs to provide the same coverage as Vodafone to do this.
0 | NTH | 1119 | NTH-001-002 |  |  |  | Far North |  | TIER_9
0 | NTH | 1120 | NTH-001-003 |  |  |  | Far North |  | TIER_9
0 | NTH | 1121 | NTH-001-004 | Kaikohe | NTH-001-004-F | Kaikohe GF - Co site VNZ | Far North | 23 | TIER_4 | ACTIVE | GF | DU | T2 20 RF |  | STACK_A | COSITE | 20 | 20 |  | -35.373 | 173.8303 |  |  |  |  | Microwave | NTH-001-039-A | FALSE | FALSE |  |  | FALSE |  | 2012-03-13 | 2012-03-13 | 2012-07-13 | 2012-07-13 | 2012-09-14 | 2012-10-02 | 3 | 2012-09-14 | 2013-01-23 | 2012-10-03 | 2012-09-25 | 2012-12-07 | 2012-12-14 |  | 2012-12-07 | 2012-12-14 | DISCRETIONARY_FULL | 2012-11-05 | 2015-03-15 | 2012-12-21 | 2015-04-16 | 1 | 2015-01-30 | 2015-01-30 | 2014-10-21 | 2014-10-21 | 2015-02-06 | 2015-02-12 | 1 |  | 2015-02-06 | 2015-02-12 | 2015-03-18 |  |  |  |  | 2015-04-13 | 2015-04-20 | 2015-06-19 | 2015-06-26 | 2015-06-01 | 2015-06-05 | 2015-06-26 | [9 empty] | 2015-07-30 | 2015-07-28 |  | 2015-08-28 |  | 2015-08-28 | Huawei Build PO 35102 Have VNZ co site approval. RMA CONDITIONS ONEROUS # 3 : Power route - Archaelogical assesment required VERY IMPORTANT - Please read full conditions. # 4 : Earthworks and excavation conditions - VERY IMPORTANT - Please read full conditions # 5 : Vegetation and re establishment 18.12.2014 Steve Esther has requested info from North Power - to get quote and scope in New Year 25/2/15 - RF specs supplied, TX specs issued 3/3/15 S127 for change to pile to be lodged by end of week 13 March 25/3/15 - S127 lodged 16 March - small risk with being referred to Heritage NZ. Build is about to start,8 April 12/05/15 - Power ready to upgrade. Xformer to deliver. Pilecap poured. Rock struck during piling (Variation). Pole up WC 25/5, Integrate maybe wc 8/6 26/05/15 - Ron to lodge CR for integration (When date known) 03/06/15 - Feeder sweeps to be reviewed by RF. Need VF letter for power connection to their transformer 23/06/15 - Integrate 29/6 CR 45055. Drive test resources booked for week 13 July 20/07/15 - Feeders replaced, POwer on , Vol 4 in for review - some faults |  | 2015-06-29 |  |  |  |  | 2015-03-18 | 2015-03-18 | 2015-06-19 |  | 2015-07-07 | 2015-07-06 |  |  | NORTHLAND |  |  | BUILD | 2015-06-01 | FALSE |  | 2586217 | 6647211 | Remuera Settlers Road |  | Sent to FNDC on 6.11.2012 to Pat Killara - 08/11/2012 | CELLSITE |  |  |  | ROAMING |  | 2014-12-18 | 2015-02-03 | 2015-03-13 | 2015-03-13 |  |  |  |  | 2015-03-30 | 2015-03-30 | 2015-07-03 |  | 2012-07-13
0 | NTH | 1122 | NTH-001-005 |  |  |  | Far North |  | TIER_9
0 | NTH | 1123 | NTH-001-006 |  |  |  | Far North |  | TIER_9
0 | NTH | 1124 | NTH-001-007 |  |  |  | Far North |  | TIER_9
0 | NTH | 1125 | NTH-001-008 | Russell | NTH-001-008-D | Russell GF | Far North | 23 | TIER_4 | ACTIVE | GF | DU | T2 15 UF LTD |  | STACK_A | COSITE | 16 | 16 |  | -35.2557 | 174.124 | 2010-02-26 | 2011-12-19 | 2010-02-26 | 2010-02-25 | Fibre Optic | NTH-001-040-A | TRUE | FALSE | 2010-02-12 |  | FALSE |  | 2012-03-13 | 2012-03-13 | 2012-03-21 | 2012-03-22 | 2012-04-12 | 2012-05-23 | 8 | 2012-07-20 | 2015-11-04 | 2012-09-21 | 2012-09-18 | 2012-10-05 | 2012-10-05 |  | 2015-01-30 | 2014-11-18 | DISCRETIONARY_FULL | 2012-09-21 | 2012-09-20 | 2015-06-19 | 2015-06-03 | 3 | 2015-06-12 | 2015-06-03 | 2015-04-10 | 2015-04-07 | 2015-05-26 | 2015-05-12 | 1 |  | 2015-06-30 | 2015-05-12 |  |  |  | 2015-08-21 |  | 2015-10-12 | 2015-10-12 | 2015-11-13 | 2015-11-20 |  |  |  | 2015-11-25 | 2015-11-24 | [7 empty] | 2015-12-17 | 2015-12-16 |  |  |  |  | 01.12.2014 Have JDA / Media Works, Radio Works cosite approval - we need to take their wooden pole down and place their equipment on ours. 4/11/15 - Working with Chorus to try getting fibre delivered earlier. Agreement reached with owners on supplying power to a pillar for their future. Also Manuka fence required 24/11/15 - Maybe issue with interference to Mediaworks STL . needs careful powering up. 30/11/15 - Vol 4 received. FM antenna to be relocated | [10 empty] | 2015-11-26 | 2015-11-26 |  |  | BAY_OF_ISLANDS | 2015-11-25 | 2015-11-24 | BUILD |  | TRUE | 2015-08-21 | 2613088 | 6659900 | Flagstaff Road Russell |  | Designation BC230 - 05/04/2012 | CELLSITE |  |  |  | ROAMING |  | 2015-05-05 | 2015-04-24 | 2015-06-15 | 2015-04-29 | 2015-04-23 | 2015-04-23 | 2015-04-23 |  | 2015-09-18 | 2015-09-21 |  |  | 2012-03-22
0 | NTH | 1126 | NTH-001-009 | Russell East |  |  | Far North |  | TIER_9 | [22 empty] | FALSE | [60 empty] | Russell East. Access via Russell Heights Road. Option A: Co-site on 15m TNZ. Pole TNZ is wood. Suggest a swap out and a 15m spider armed pole so all can get on etc. (Good location - covering Russell, Paroa bay to the east and the Bays out West also Pahia area). Grid: E2614096 N6659012 Option B: GF Pole option within same compound Grid: E2614096 N6659012 SITE NOT REQUIRED IF NTH-001-008 RUSSELL SECURED.
0 | NTH | 1127 | NTH-001-010 |  |  |  | Far North |  | TIER_9
0 | NTH | 1128 | NTH-001-011 |  |  |  | Far North |  | TIER_9
0 | NTH | 1129 | NTH-001-012 |  |  |  | Far North |  | TIER_9
0 | NTH | 1130 | NTH-001-013 |  |  |  | Far North |  | TIER_9
0 | NTH | 1131 | NTH-001-014 |  |  |  | Far North |  | TIER_9
0 | NTH | 1132 | NTH-001-015 |  |  |  | Far North |  | TIER_9
0 | NTH | 1133 | NTH-001-016 |  |  |  | Far North |  | TIER_9
0 | NTH | 1134 | NTH-001-017 |  |  |  | Far North |  | TIER_9
0 | NTH | 1135 | NTH-001-018 |  |  |  | Far North |  | TIER_9
0 | NTH | 1136 | NTH-001-019 |  |  |  | Far North |  | TIER_9
0 | NTH | 1137 | NTH-001-020 | Kerikeri | NTH-001-020-B | Kerikeri GF | Far North | 23 | TIER_4 | ACTIVE | GF | DU | T2 20 RF |  | STACK_A | COSITE | 20 | 20 |  | -35.2199 | 173.885 |  | 2011-12-19 |  |  | Microwave | NTH-001-021-H | FALSE | FALSE |  |  | FALSE |  | 2012-03-13 | 2012-03-13 | 2012-03-23 | 2012-03-22 | 2012-05-25 | 2012-05-31 | 1 | 2012-05-25 | 2012-05-31 | 2012-06-29 | 2012-07-26 | 2012-11-02 | 2012-11-02 |  | 2012-11-02 | 2012-11-02 | PERMITTED | 2012-07-09 | 2012-07-04 | 2012-10-17 | 2012-08-02 | 1 | 2012-08-13 | 2012-08-06 | 2014-10-24 | 2014-10-21 | 2015-01-23 | 2015-01-20 | 1 |  | 2015-01-30 | 2015-01-20 | [5 empty] | 2015-05-18 | 2015-05-18 | 2015-07-22 | 2015-07-22 | 2015-06-10 | 2015-06-30 | 2015-07-09 | [8 empty] | 2015-07-20 | 2015-07-31 | 2015-07-28 |  | 2015-08-28 |  | 2015-08-28 | Huawei Build PO 35468 12/05/15 - 40m track required. Owner OK to leave in. Power SFA requested and letter for Lines Company 26/05/15 - Slab pour Fri. 6 June ready for TI. Weather dealys. Tower up 9 June, TI 10 June 16/06/15 - Power...Letter for Top Energy (done) 07/07/15 - Site Integrated on Generator. Ron sorting power meter issue with AMS/Meridian. 9/7 - go with external meter housing 8/7 Duco to supply final parts for mW mounts, that were missed 14/07/15 - Integrated on generator. Power on 21 July |  | 2015-06-30 | 2015-03-18 | 2015-03-18 |  |  |  |  | 2015-07-08 | 2015-07-08 | 2015-07-24 | 2015-07-22 |  |  | NORTHLAND |  |  | BUILD | 2015-06-08 | FALSE |  | 2591413 | 6664141 | Maungakeretu Road KERIKERI |  | 2130003-RMACOC - 07/08/2012 | CELLSITE |  |  |  | ROAMING |  | 2015-03-13 | 2015-02-03 | 2015-04-07 | 2015-04-07 |  |  |  |  | 2015-05-05 | 2015-05-05 | 2015-08-11 |  | 2012-03-23
0 | NTH | 1138 | NTH-001-021 | Kerikeri Centre | NTH-001-021-H | Kerikeri Center Firestone | Far North | 23 | TIER_4 | ACTIVE | RT | DU | RT |  | INLINE | STANDALONE | 12 | 4.8 |  | -35.2289 | 173.9484 | 2010-02-26 | 2011-12-19 | 2010-02-26 | 2010-02-25 | Fibre Optic | NTH-001-040-A | TRUE | FALSE | 2010-02-11 |  | FALSE |  | 2012-02-22 | 2012-02-22 | 2012-03-19 | 2012-03-08 | 2012-06-05 | 2012-06-13 | 1 | 2012-06-08 | 2012-06-13 | 2012-07-03 | 2012-07-03 | 2012-09-21 | 2012-09-19 | 1 | 2012-09-28 | 2012-09-25 | PERMITTED | 2012-08-08 | 2012-08-08 | 2012-09-05 | 2012-08-20 | 1 | 2012-09-12 | 2012-08-20 | 2014-10-24 | 2014-10-21 | 2015-01-23 | 2015-02-09 | 1 |  | 2015-01-30 | 2015-02-09 | [5 empty] | 2015-05-25 | 2015-05-14 | 2015-07-20 | 2015-07-24 | 2015-06-19 | 2015-06-24 | 2015-07-09 | 2015-06-30 | 2015-07-03 | [6 empty] | 2015-07-15 | 2015-07-29 | 2015-07-28 |  | 2015-08-28 |  | 2015-08-28 | Huawei build - PO 35496 issued 13/5 04/05/15 - Specs in place, Huawei/Skycomms to start construction 13/05/15 - Metalwork underway 26/05/15 - Fibre duct in. Duco to advise steel delivery. Ron to send 12 FSJ4-50 connectors. Power from Transformer 04/06/15 - Starting on site 8 June. Metalwork arrives 6 June 16/06/15 - Fibre duct in, fibre 26/6, power next week. Integrate 29/6 08/07/15 - Site Integrated on Generator. Ron sorting power meter issue with AMS/Meridian. 9/7 - go with external meter housing 14/07/15 - Power on 16/07, Vol 4 to be submitted 20/07/15 - Vol 4 submitted |  | 2015-06-29 | [6 empty] | 2015-06-26 | 2015-07-26 | 2015-07-20 | 2015-07-20 |  |  | NORTHLAND | 2015-06-30 | 2015-07-03 | BUILD | 2015-06-22 | TRUE |  | 2597146 | 6663081 | 4 Hobson Ave Kerikeri |  |  | CELLSITE |  |  |  | ROAMING |  |  | 2015-02-03 | 2015-04-07 | 2015-04-07 | 2015-04-23 | 2015-04-23 | 2015-04-23 | 2015-04-23 | 2015-05-13 | 2015-05-13 | 2015-07-24 |  | 2012-03-19
0 | NTH | 1139 | NTH-001-022 | Kerikeri Inlet | NTH-001-022-E | KeriKeri Inlet | Far North | 23 | TIER_4 | ACTIVE | GF | DF | T2 15 RFH |  | INLINE | STANDALONE | 15 | 15 |  | -35.1921 | 173.9851 | 2010-02-26 | 2011-12-19 | 2010-02-26 | 2010-02-25 | Microwave | NTH-001-020-B | TRUE | FALSE | 2010-02-11 |  | FALSE |  | 2014-12-15 | 2014-12-15 | 2014-12-16 | 2014-12-17 | 2015-02-16 | 2015-01-27 | 1 | 2015-02-23 | 2015-01-27 | 2014-12-16 | 2014-12-16 | 2015-03-30 | 2015-03-13 |  | 2015-04-10 | 2015-04-15 | PERMITTED | 2015-03-30 | 2015-03-27 | 2015-05-01 | 2015-04-08 | 1 | 2015-05-08 | 2015-04-08 |  |  |  |  | 1 | [30 empty] | 02/10/15 - Site to HARDMATCH ONLY - not build 17/2/15 - Noted from James that Power may require Archeological supervision at time of build 29/04/15 - Build instruction issued. RF specs issued - TX specs required (issued 8/5) 25/05/15 - ALL WORKS ON SITE TO STOP. Archaelogical find during geotech, so will need full assessment, possible relocation (or another site) or approval to continue. 03/06/15 - Archaeologist and Iwi to be engaged (Ron) 07/07/15 - Report received. best option is to continue with location, but will require sign-off by Heritage NZ and IWI. Ben assisting with IWI engagement 14/07/15 - Working on keeping site in same location. Iwi meeting next week 4/11/15 - Ron still to find time to complete build process report for HNZ and Ngati Wai | [14 empty] | BAY_OF_ISLANDS |  |  | ONHOLD |  | TRUE |  | 2600532 | 6667119 | 236 Redcliffs Road KeriKeri |  |  | CELLSITE | WIPACTIVE |  |  | ROAMING |  | 2015-05-05 | [11 empty] | 2014-12-17
0 | NTH | 1140 | NTH-001-023 | Haruru | NTH-001-023-C | Haruru GF Co-site | Far North | 23 | TIER_4 | ACTIVE | GF | DF | T2 20 RH |  | STACK_A | COSITE |  |  |  | -35.2886 | 174.052 | 2010-02-26 |  | 2010-02-26 | 2010-02-25 | Fibre Optic | NTH-001-040-A | TRUE | FALSE | 2010-02-11 |  | FALSE |  | 2015-04-30 | 2015-03-18 | 2015-03-27 | 2015-04-07 | 2015-05-13 | 2015-05-07 | 1 | 2015-05-15 | 2015-05-07 | 2015-06-19 | 2015-06-04 | 2015-07-01 | 2015-06-25 |  | 2015-11-06 | 2015-11-04 | DISCRETIONARY_FULL | 2015-07-06 | 2015-07-06 | 2016-04-08 |  | 1 | 2016-04-08 |  | 2015-06-30 | 2015-06-16 | 2015-07-31 | 2015-07-22 | 1 |  | 2015-08-07 | 2015-07-22 | [5 empty] | 2016-07-07 | [15 empty] | 2016-08-29 | [5 empty] | 02/10/15 - Site to HARDMATCH ONLY - Not Build 03/06/12 - Lease terms agreed. lease dates bought forward. Look to issue CDI end June, but geotech will not be able to access till early July 23/06/15 - Lease signed. GHD access 01/02 July. Will need in future to daisy chain locks on gate 09/07/15 - Co-site applications lodged - VF approved 10/8 04/08/15 - S92 from Council - Heritage NZ and Iwi 18/08/15 - Site consultation with Heritage NZ and Iwi 2-3 Sept 09/09/15 - Consultation put on hold until better weather for access | [10 empty] | 2016-08-22 |  | 2015-03-25 | MEDIUM |  |  |  | ONHOLD |  | FALSE |  | 2606490 | 6656334 | 333 Puketona Rd |  |  | CELLSITE | WIPACTIVE |  |  | ROAMING |  |  |  | 2016-05-18 |  | 2015-04-23 | 2015-04-23 |  |  | 2016-06-12 |  |  |  | 2015-04-07
0 | NTH | 1141 | NTH-001-024 | Kawakawa | NTH-001-024-A | Kawakawa Vodafone Co Lo | Far North | 23 | TIER_4 | ACTIVE | COLO | DU | COLO |  | STACK_A | COLO | 20 | 20 |  | -35.3698 | 174.0384 |  | 2011-12-19 |  |  | Microwave | NTH-001-020-B | FALSE | FALSE |  |  | FALSE |  | 2012-03-13 | 2012-03-13 | 2012-03-22 | 2012-03-21 | 2012-04-11 | 2012-05-15 | 3 | 2012-04-11 | 2012-09-10 | 2015-04-20 | 2015-04-22 | 2015-05-08 | 2015-05-22 |  | 2015-05-15 | 2015-05-27 | DISCRETIONARY_FULL | 2015-03-04 | 2015-03-10 | 2015-04-28 | 2015-04-28 | 3 | 2015-04-30 | 2015-04-28 | 2015-04-06 | 2015-02-25 | 2015-04-30 | 2015-04-23 | 1 |  | 2015-05-06 | 2015-04-23 | [5 empty] | 2015-07-23 | 2015-07-03 | 2015-10-02 | 2015-10-02 | [12 empty] | 2015-10-15 | 2015-10-14 |  | 2015-10-30 |  | 2015-10-30 | 18/06/15 - VF approval to build received. Huawei still to provide pricing 09/09/15 - Restart on site next week. Cabinets in, Power ordered, Integrate CR 21-25 Sept 16/09/15 - Earthing and power complete. Ringframe next week if weather OK. 24/09/15 - Ringframe helicoptered in. Power will be connected 8 Oct. VF CR raised 02/10/15 - Integrated. Needing power next week 12/10/15 - Ready to go live Wed night | VNZ | [9 empty] | 2015-10-13 | 2015-10-12 |  |  | NORTHLAND |  |  | BUILD |  | FALSE |  | 2605129 | 6647339 | McIntyre Road |  | pERMITTED TO 20M (tbc) Could be non-complying in coastal landscape as of 5.4.12 - 05/04/2012 Discretionary Activity - exceeds sunlight recession plane, impermeable surface area and height - AT, 4.9.12 - 04/09/2012 | CELLSITE |  |  |  | ROAMING |  |  | 2015-04-24 | 2015-05-08 | 2015-04-29 |  |  |  |  | 2015-07-03 | 2015-06-29 |  |  | 2012-03-22
0 | NTH | 1142 | NTH-001-025 | Kawakawa East | NTH-001-025-A | Kawakawa East VF Co-Lo | Far North | 23 | TIER_4 | ACTIVE | COLO | DU | COLO | Grey | STACK_A | COLO |  |  |  | -35.3518 | 174.0774 |  |  |  |  | Fibre Optic | NTH-001-040-A | FALSE | FALSE |  |  | FALSE |  | 2015-04-06 | 2015-03-17 | 2015-04-15 | 2015-04-13 | 2015-05-21 | 2015-05-19 | 1 | 2015-05-28 | 2015-05-19 | 2015-07-24 | 2015-06-02 | 2015-08-28 | 2015-08-06 |  | 2015-09-11 | 2015-09-08 | DISCRETIONARY_RESTRICT | 2015-06-25 | 2015-05-27 | 2015-07-10 | 2015-06-25 | 1 | 2015-07-10 | 2015-06-25 | 2015-06-22 | 2015-06-16 | 2015-07-24 | 2015-07-14 | 1 |  | 2015-07-31 | 2015-07-14 | [5 empty] | 2015-10-09 | 2015-10-02 | 2015-11-20 | 2015-11-20 |  |  |  | 2015-12-15 | 2015-12-07 | [7 empty] | 2015-12-18 | 2015-12-16 |  |  |  |  | 28/9/15 - Build approval received and forwarded 02/10/15 Build started. 24/11/15 - Still no confirmed date from Chorus for fibre - revised dates to 4 Dec 30/11/15 - RQ if fibre is 14 Dec, and Chorus trying to deliver same day 7/12/15 - Chorus fibre delivered!! | VNZ | [9 empty] | 2015-12-11 | 2015-12-11 | 2015-03-25 | LOW |  | 2015-12-11 | 2015-12-07 | BUILD |  | FALSE |  | 2608708 | 6649292 | VF Colocation Lemon Farm Whangae Road Kawakawa |  |  | CELLSITE |  |  |  | ROAMING |  |  | 2015-08-03 | 2015-07-27 | 2015-08-02 | 2015-04-23 | 2015-04-23 | 2015-06-01 |  | 2015-09-04 | 2015-09-03 |  |  | 2015-04-13
0 | NTH | 1143 | NTH-001-026 | Paihia |  |  | Far North |  | TIER_9 | [22 empty] | FALSE | [60 empty] | Paihia Option A: 12m Rooftop Cosite with Vodafone , Opposite Ferry Building Paihia. Grid: E2610124 N6657123 Option B: Colo on TNZ unfinished 10m pole at Exchange Building in William Street. Grid: E2610004 N6656946 Option C: GF Pole in on of the Industrial yards - several options Grid: E2610144 N6657113
0 | NTH | 1144 | NTH-001-027 | Opua | NTH-001-027-A | Opua - VF Co-lo | Far North | 23 | TIER_4 | ACTIVE | COLO | DU | COLO |  | STACK_A | COLO | 12 |  | 1 | -35.2977 | 174.1251 | 2010-02-26 |  | 2010-02-26 | 2010-02-25 | Fibre Optic | NTH-001-040-A | TRUE | FALSE | 2010-02-11 |  | FALSE |  | 2015-04-06 | 2015-03-17 | 2015-03-27 | 2015-03-26 | 2015-05-15 | 2015-05-21 | 3 | 2015-05-22 | 2015-08-21 | 2015-09-11 | 2015-09-10 | 2016-05-27 |  |  | 2016-05-27 |  | DISCRETIONARY_FULL | 2015-10-13 | 2015-10-02 | 2015-11-27 | 2015-10-30 | 3 | 2015-12-04 | 2015-10-30 | 2016-05-02 |  | 2016-05-27 |  |  |  | 2016-05-27 | [6 empty] | 2016-07-18 | [15 empty] | 2016-09-30 | [5 empty] | 02/10/15 - Site to HARDMATCH ONLY - not build programme 22/05/15 - Colocation application lodged with VF 11/06/15 - VF rejected colocation due to RF concerns on placement of TMA's. Plans marked up for PD revision 23/06/15 - Revised PD's issued - Ron to relodge application - done 26/6 30/06/15 - Pushed out RMA dates due to site risk. Need to work to pull back as we go forward as site critical for Xmas 21/07/15 - Preliminary Approval received. Visual assessment due today 01/09/15 - Terms agreed, subject to VF agreement 22/09/15 - VF agreed on terms. With owners legal review 4/11/15 - some issues with Owner and Top Energy access for power. Go slow for 2 Degrees since not in immediate build programme | VNZ | [9 empty] | 2016-09-16 |  | 2015-03-25 | MEDIUM |  |  |  | ONHOLD |  | TRUE |  | 2613126 | 6655229 | 206 Aucks Rd, Opua |  |  | CELLSITE | WIPACTIVE |  |  | ROAMING |  |  |  | 2016-06-06 |  | 2015-04-23 | 2015-04-23 |  |  | 2016-07-04 |  |  |  | 2015-03-26
0 | NTH | 1145 | NTH-001-030 | Paihia | NTH-001-030-E | Paihia - VNZ CO SITE | Far North | 23 | TIER_4 | ACTIVE | RT | DF | RT |  | INLINE | COSITE |  |  |  | -35.2812 | 174.0914 |  | 2011-12-19 |  |  | Fibre Optic | NTH-001-040-A | FALSE | FALSE |  |  | FALSE |  | 2012-03-14 | 2012-03-14 | 2012-07-04 | 2012-07-04 | 2012-08-27 | 2012-08-29 | 2 | 2012-08-27 | 2015-05-29 |  | 2012-07-04 | 2012-09-21 | 2012-10-04 |  | 2012-09-28 | 2012-10-30 | PERMITTED | 2012-09-12 | 2012-09-12 | 2012-10-18 | 2012-10-04 | 1 | 2012-10-25 | 2012-10-05 | 2015-01-27 | 2015-01-27 | 2015-05-19 | 2015-07-03 | 1 |  | 2015-05-21 | 2015-07-03 |  |  |  | 2015-08-20 |  | 2015-08-28 | 2015-08-25 | 2015-10-23 | 2015-10-23 | 2015-09-21 | 2015-10-23 | 2015-10-23 | 2015-10-16 | 2015-10-19 | [7 empty] | 2015-11-12 | 2015-11-13 |  | 2015-11-27 |  | 2015-11-27 | 18/08/15 - PO 36686 issued to Huawei/Downers. Downers to plan pre-start meeting and advise date/time. Graham dropping off pre-build letters 25/08/15 - Pre-start meeting 28 August. Metalwork underway 24/09/15 - Build underway. Some issues with mounts and getting cables through building. GHD reviewing design on site 24/09/15 CR 47390 raised for integration 12-30 Oct 29/09/15 - Some issues getting cables through building. GHD on site and issues well underway to being sorted 14/10/15 - Power this week, Fibre 19, Integrate with Vol 4 by 22/10 19/10/15 - still chasing property owner fro permission to connect power 4/11/15 - Power on, site integrated, still waiting for Volume 4 | [8 empty] | 2015-09-25 |  | 2015-11-06 | 2015-11-06 |  |  | BAY_OF_ISLANDS | 2015-10-16 | 2015-10-19 | BUILD | 2015-09-21 | TRUE | 2015-08-21 | 2610079 | 6657113 | Same building as Vodafone, Paihia |  | Lodged COC application on the 12.9.2012 with Rev 1 plans. - 12/09/2012 | CELLSITE |  |  |  | ROAMING |  |  | 2015-02-25 | 2015-06-19 | 2015-06-17 | 2015-04-23 | 2015-04-23 | 2015-04-23 | 2015-04-23 | 2015-08-21 | 2015-08-19 |  |  | 2012-07-04
0 | NTH | 1146 | NTH-001-031 |  |  |  | Far North |  | TIER_9
0 | NTH | 1147 | NTH-001-032 | Orongo Bay |  |  | Far North |  | TIER_9 | [22 empty] | FALSE | [60 empty] | Orongo Bay TNZ Monopole. Good location. Access is a problem. Option A: 15m Pole Colocate with TNZ some modification to fit a hoop or spider arm might be required. Grid: as above. Option B: GF option with same compound. Grid: as above
0 | NTH | 1148 | NTH-001-033 |  |  |  | Far North |  | TIER_9
0 | NTH | 1149 | NTH-001-034 | RBI - Houhora Central |  |  | Far North |  | RBI | [22 empty] | FALSE
0 | NTH | 1150 | NTH-001-035 | Kaitaia | NTH-001-035-B | Kaitaia GF | Far North | 23 | TIER_4 | ACTIVE | GF | DU | T2 20 RH |  | INLINE | COSITE | 20 | 20 |  | -35.1083 | 173.2722 |  |  |  |  | Fibre Optic | NTH-001-040-A | FALSE | FALSE |  |  | FALSE |  | 2012-03-13 | 2012-03-13 | 2012-03-23 | 2012-03-21 | 2012-04-11 | 2012-05-23 | 4 |  | 2014-07-18 | 2012-05-31 | 2012-06-29 | 2012-06-29 | 2012-08-03 |  | 2012-07-06 | 2012-10-30 | DISCRETIONARY_RESTRICT | 2012-06-20 | 2012-06-19 | 2012-10-05 | 2012-10-05 | 1 | 2012-10-12 | 2012-10-05 |  | 2014-06-17 | 2014-07-15 | 2014-07-18 | 1 |  | 2014-07-23 | 2014-07-18 | [5 empty] | 2015-05-25 | 2015-05-27 | 2015-07-16 | 2015-07-17 | 2015-07-03 | 2015-06-29 | 2015-07-10 | 2015-07-01 | 2015-06-30 | [6 empty] | 2015-07-01 | 2015-07-24 | 2015-07-20 |  | 2015-08-28 |  | 2015-08-28 | Huawei Build PO35496 issued 13/5 18.12.14 CD Issued. Ready to tender. COW placement upgraded the T/F - SO power is sorted. 22/04/15 - Build cost accepted and Huawei/Skycomms instructed to start build 26/05/15 - Build underway, inspection Thurs (Chris to attend) 16/06/15 - Pole delivery 18/6, fibre next week, 50 ohm earth with just pegs. Integrate 1/7 07/07/15 - Site Integrated on Generator. Ron sorting power meter issue with AMS/Meridian. 9/7 - go with external meter housing 14/07/15 Power going on today. kevin to manage site to air, COW to be removed 24/7 |  | 2015-07-01 | [6 empty] | 2015-06-23 | 2015-07-01 | 2015-07-06 | 2015-07-06 |  |  | NORTHLAND | 2015-07-01 | 2015-06-30 | BUILD | 2015-06-25 | FALSE |  | 2535654 | 6677006 | Korimako Road Kaitia |  | Pat Killalea, Principal Planner Far North District Council t: 021.927.419 - 28/06/2012 | CELLSITE |  |  |  | ROAMING |  | 2015-03-13 | 2015-02-04 | 2015-04-07 | 2015-04-07 | 2015-04-23 | 2015-04-23 | 2015-04-23 | 2015-04-23 | 2015-05-13 | 2015-05-13 | 2015-08-12 |  | 2012-03-23
0 | NTH | 1151 | NTH-001-036 | Whangaroa |  |  | Far North |  | TIER_9 | [22 empty] | FALSE
0 | NTH | 1152 | NTH-001-037 | Coopers Beach | NTH-001-037-A | Coopers Beach VF COLO | Far North | 23 | TIER_4 | ACTIVE | COLO | DU | COLO |  | STACK_A | COLO |  |  |  | -34.9554 | 173.5403 |  |  |  |  | Microwave | NTH-001-042-A | FALSE | FALSE |  |  | FALSE |  | 2015-01-26 | 2014-12-15 | 2015-02-18 | 2015-03-02 | 2015-03-27 | 2015-04-15 | 1 | 2015-03-27 | 2015-04-15 | 2015-07-31 | 2015-07-27 | 2015-08-28 | 2015-08-17 |  | 2015-10-02 | 2015-08-17 | PERMITTED | 2015-04-10 | 2015-04-17 | 2015-05-22 | 2015-05-15 | 1 | 2015-05-29 | 2015-05-15 | 2015-05-18 | 2015-05-15 | 2015-06-19 | 2015-06-22 | 1 |  | 2015-06-19 | 2015-06-22 | [5 empty] | 2015-09-07 | 2015-08-19 | 2015-11-04 | 2015-11-04 | [12 empty] | 2015-12-17 | 2015-12-15 |  |  |  |  | 31/07/15 - PO6 36531 issued. Sky can start metalwork. Clock stopped until access granted 20/10/15 - Site built Vol 4 in, No power and no date for power yet 4/11/15 - Power now scheduled for 19 November!!!. BER test still to come 30/11/15 - Power Transformer upgrade done. Power by 4 Dec hopefully 7/12/15 - Power 8 Dec. 24 Hr BER 9/10 Dec, Vol 4 10/11 Dec SOA next week | VNZ | [9 empty] | 2015-12-11 | 2015-12-08 | [5 empty] | BUILD |  | FALSE |  | 2560242 | 6693800 | VF Colocation Waiaua Road, Hihi Far North District |  |  | CELLSITE |  |  |  | ROAMING |  |  | 2015-04-24 | 2015-07-20 | 2015-06-17 |  |  |  |  | 2015-08-28 | 2015-08-03 |  |  | 2015-03-02
0 | NTH | 1153 | NTH-001-038 | Tutukaka |  |  | Far North |  | TIER_9
0 | NTH | 1154 | NTH-001-039 | Kaikohe TX site | NTH-001-039-A | Kaikohe Exchange | Far North | 23 | TIER_4 | ACTIVE | COLO | TX | COLO |  |  | COLO |  |  |  | -35.407 | 173.7978 |  |  |  |  | Fibre Optic | NTH-001-040-A | FALSE | FALSE |  |  | FALSE |  | 2012-04-16 | 2012-04-16 | 2012-04-30 | 2012-04-30 | 2012-05-25 | 2012-06-07 | 1 | 2012-06-08 | 2012-06-07 | 2015-03-27 | 2015-03-30 | 2015-04-30 | 2015-04-20 |  | 2015-05-08 | 2015-05-05 | DISCRETIONARY_FULL | 2012-07-16 | 2012-07-17 | 2012-08-13 | 2012-08-22 | 1 | 2012-08-20 | 2012-08-24 | 2015-03-11 | 2015-03-11 | 2015-04-17 | 2015-05-04 | 1 |  | 2015-04-17 | 2015-05-04 | [5 empty] | 2015-05-25 | 2015-05-13 | 2015-06-19 | 2015-07-09 | 2015-05-27 | 2015-06-12 | 2015-07-06 | 2015-06-26 | 2015-07-03 | [7 empty] | 2015-07-03 | 2015-07-09 |  |  |  |  | PO35743 issued 20/5/15 13/5/15 - Final approval received (1 day!). Steelwork underway. Quote supplied and approved. Huawei to issue Docs for PO 12/05/15 - Quote with Huawei to process. 26/05/15 - Rack supplied. Visionstream calling for coax (Skcomms will supply). Backhaul due Fri 04/06/15 - Chorus pushed Fibre RFS from 29/5 to 26/6 (without consultation). requested to bring forward asap 15/06/15 - Rack installed, powered up. RTN in cabinet. Issues with MW mount to be resolved 07/07/15 - link in place with Kaikohe site integrated. Skycomms to confer with GHD that alternative mount build is acceptable | TNZ | [9 empty] | 2015-06-26 | 2015-07-06 |  |  | TRANSMISSION_ONLY | 2015-05-29 | 2015-07-03 | BUILD | 2015-06-12 | FALSE |  | 2583224 | 6643473 |  |  | REF: 2130025-RMALUC - 24/08/2012 | TXSITE |  |  |  | ROAMING |  |  | 2014-12-19 | 2015-04-29 | 2015-04-29 | 2015-04-23 | 2015-04-23 | 2015-04-23 | 2015-04-23 |  | 2015-05-20 |  |  | 2012-04-30
0 | NTH | 1155 | NTH-001-040 | KeriKeri TX only site | NTH-001-040-A | Kerikeri Exchange | Far North | 23 | TIER_4 | ACTIVE | COLO | TX | NOPOLE |  |  | COLO | 0 | 0 | [7 empty] | Fibre Optic | NTH-002-011-A | FALSE | FALSE |  |  | FALSE |  | 2015-02-17 | 2012-03-05 | 2015-02-17 | 2015-02-24 | 2015-03-06 | 2015-03-03 | 1 | 2015-03-13 | 2015-03-03 | 2015-03-20 | 2015-02-26 | 2015-03-27 | 2015-02-25 |  | 2015-04-03 | 2015-02-26 | PERMITTED | 2015-03-13 | 2015-03-30 | 2015-03-27 | 2015-03-30 | 1 | 2015-03-27 | 2015-02-26 | 2015-03-13 | 2015-03-03 | 2015-03-06 | 2015-03-13 | 1 |  | 2015-03-13 | 2015-03-13 | [5 empty] | 2015-04-13 | 2015-04-13 | 2015-04-16 | 2015-04-22 | 2015-04-27 | 2015-05-25 | 2015-05-25 | 2015-05-08 | [7 empty] | 2015-05-25 | 2015-06-12 | 2015-06-05 |  | 2015-06-08 | 2015-06-08 | 2015-06-08 | Huawei Build PO 35486 11/3/15 - Equip arrives 02/04. Chorus to install rack, Fibre backhaul RFS 16/04, Huawei to install CX and commission week 20 April 22/04/15 - Build price confirmed to Huawei/Skycomms. Huawei request to shift rack to Chorus and CX to office for pre-confiq 04/04/15 - Rack with Chorus, CX install 1 May. Huawei to issue MOP etc for CR 26/05/15 - Testing completed, L3 all good. Vol 4 to be supplied 03/06/15 - Vol 4 received and in acceptance phase | TNZ | 2015-05-25 | [8 empty] | 2015-05-29 | 2015-05-28 |  |  | TRANSMISSION_ONLY | 2015-04-16 | 2015-04-23 | BUILD | 2015-04-27 | FALSE |  |  |  | Kerikeri Exhange Hobson St Kerikeri |  |  | TXSITE |  |  |  | ROAMING |  |  | 2015-02-03 | 2015-04-07 | 2015-04-07 | 2015-04-23 | 2015-04-23 | 2015-04-23 | 2015-04-23 | 2015-05-04 | 2015-05-04 | 2015-06-08 | 2015-06-08 | 2015-02-24
0 | NTH | 1156 | NTH-001-041 | Kaitaia TX Only | NTH-001-041-A | Kaitaia TX only site | Far North |  | TIER_6 | ACTIVE | RT | TX | RT | [12 empty] | Fibre Optic | AKL-005-078-A | FALSE | FALSE |  |  | FALSE | [55 empty] | 2014-03-28 | [28 empty] | 9 Puckey Avenue, Kaitaia, Northland, New Zealand |  |  | TXSITE
0 | NTH | 1157 | NTH-001-042 | Coopers Beach Exchange | NTH-001-042-A | Coopers Beach Exchange | Far North | 23 | TIER_4 | ACTIVE | COLO | TX | P4B |  |  | COLO | 8.6 | 9.5 | [7 empty] | Fibre Optic | NTH-001-040-A | FALSE | FALSE |  |  | FALSE |  | 2015-01-26 | 2014-12-15 | 2015-02-17 | 2015-02-18 | 2015-03-20 | 2015-03-24 | 2 | 2015-03-27 | 2015-06-16 | 2015-05-22 | 2015-05-18 | 2015-05-29 | 2015-05-18 |  | 2015-06-05 | 2015-05-22 | DISCRETIONARY_FULL | 2015-04-01 | 2015-03-27 | 2015-05-25 | 2015-05-05 | 1 | 2015-05-29 | 2015-05-05 | 2015-05-04 | 2015-05-15 | 2015-06-12 | 2015-06-11 | 1 |  | 2015-06-19 | 2015-06-11 | [5 empty] | 2015-08-24 | 2015-08-25 | 2015-10-09 | 2015-10-09 |  |  |  | 2015-09-30 | 2015-09-16 | [7 empty] | 2015-10-26 | 2015-10-21 |  |  |  |  | 18/05/15 - Preliminary approval received. lease accepted. Jordan lodging for final approval with RMA 28/05/15 - 2D has approved Chorus build and requested for 1/8 start. Fibre 15/8 RFS 16/06/15 - Final TX specs required 23/06/15 - Ron to obtain Packing list so Girma can select items for Chorus/Visionstream to install - done and sent to Huawei 30/7/15 PO 36531 issued to Skycomms for build 04/08/15 - Skycomms to do Chorus project plan 13/08/15 - Project Plan lodged with Chorus. Approved by 17.8. All go for Sky 25/08/15 - Pole received. Need RG8 for Visionstream 16/9/15 - Fibre in, service given. Hole drilled for pole. RG8 delivered. Visionstream to do rack etc. | TNZ | [9 empty] | 2015-10-19 | 2015-10-21 |  |  |  | 2015-09-30 | 2015-09-16 | BUILD |  | FALSE |  |  |  | 18 Wrathall Road Mangonui |  | Minor infringements of building coverage and impermeable area - 24/03/2015 | TXSITE |  |  |  | ROAMING |  |  | 2015-03-13 |  | 2015-06-17 | 2015-04-23 | 2015-04-23 | 2015-04-23 | 2015-04-23 | 2015-07-24 | 2015-08-03 |  |  | 2015-02-18
0 | NTH | 1158 | NTH-001-043 | Cape Karikari | NTH-001-043-B | Karikari VF Colocation | Far North | 23 | TIER_4 | ACTIVE | COLO | DU | COLO |  | STACK_A | COLO |  |  |  | -34.8665 | 173.391 |  |  |  |  | Microwave | NTH-001-037-A | FALSE | FALSE |  |  | FALSE |  | 2015-04-17 | 2015-04-14 | 2015-04-21 | 2015-04-17 | 2015-05-11 | 2015-06-03 | 3 | 2015-05-15 | 2015-09-08 | 2016-03-18 |  | 2016-05-18 |  |  | 2016-05-25 |  | DISCRETIONARY_RESTRICT | 2016-04-19 |  | 2016-06-04 |  |  | 2016-06-11 |  | 2016-04-04 |  | 2016-05-20 |  |  |  | 2016-05-20 | [6 empty] | 2016-08-12 |  | 2016-09-04 | [13 empty] | 2016-10-29 | [5 empty] | 02/10/15 - Site to HARDMATCH ONLY - not in build programme 14/4/15 - Caravanned. VF colo best option, with own greenfield also done. Power to site needs to be investigated as if this needs to come from the Winery transformer, the costs will be high. 11/05/15 - GHD advised structural pass (0.84d deflection) 21/08/15 - Preliminary approval received. Need decision from Business, whether to continue with this site (is it in 2016 build?) 19/06/15 - Not in 2015/2016 programme. Landbank site - so Consent/Lease 29/09/15 - Melissa will do review of Plan Change to see if any impact | VNZ | [9 empty] | 2016-10-22 | [6 empty] | ONHOLD |  | FALSE |  | 2546667 | 6703767 |  |  |  | CELLSITE | WIPACTIVE |  |  | ROAMING | [9 empty] | 2016-06-18 |  |  |  | 2015-04-17
0 | NTH | 1159 | NTH-001-044 | Maungataniwha (Kordia G2) | NTH-001-044-A | Kordia Maungataniwha | Far North | 23 | TIER_4 | ACTIVE | COLO | DF | COLO |  | INLINE | COLO |  |  |  | -35.1674 | 173.5234 |  |  |  |  | Microwave | NTH-001-035-B | FALSE | FALSE |  |  | FALSE |  | 2015-03-06 | 2015-03-03 | 2015-03-13 | 2015-03-03 | 2015-04-24 | 2015-04-07 | 1 | 2015-04-24 | 2015-04-07 | 2015-04-17 | 2015-04-06 | 2015-05-29 | 2015-05-04 |  | 2015-05-29 | 2015-05-20 | PERMITTED | 2015-04-24 | 2015-03-23 | 2015-06-12 | 2015-04-11 | 1 | 2015-06-12 | 2015-04-11 | 2015-06-12 | 2015-04-05 | 2015-05-08 | 2015-05-04 | 1 |  | 2015-05-08 | 2015-05-04 | [5 empty] | 2015-05-29 | 2015-05-27 | 2015-09-18 | 2015-09-24 |  | 2015-09-25 | 2015-10-02 | [9 empty] | 2015-10-22 | 2015-10-20 |  | 2015-11-06 |  | 2015-11-06 | PO 35727 issued to Huawei 20/05/15 20/07/15 - kORDIA REVISED DATES RECEIVED - Delays with metalwork and access 12/08/15 - Kordia plan has TI complete 4/9, Integrated 10/9 01/09/15 - Kordia still have not started on site 14/09/15 - S1+3 antennas in, Cabinets in and cabled. Power to go on, link being installed 24/09/15 - CR for linking to Kaitia done for 28/9-02/10 . Integration CR46524 for 28/9 - 2/10 | KDA | [9 empty] | 2015-10-09 | 2015-10-09 | [5 empty] | BUILD |  | FALSE |  | 2558506 | 6670288 | off Iwitaua Road Maungamuka Northland |  |  | CELLSITE |  |  |  | ROAMING |  |  | 2015-04-24 | 2015-05-04 | 2015-04-29 |  |  |  |  | 2015-05-26 | 2015-05-20 |  |  | 2015-03-03
0 | NTH | 1160 | NTH-001-045 | Ahipara (Kordia G4) | NTH-001-045-A | Kordia Ahipara | Far North | 23 | TIER_4 | ACTIVE | COLO | DF | COLO |  | STACK_A | COLO |  |  |  | -35.1757 | 173.1468 |  |  |  |  | Microwave | NTH-001-035-B | FALSE | FALSE |  |  | FALSE |  | 2015-03-06 | 2015-03-03 | 2015-03-13 | 2015-03-03 | 2015-04-17 | 2015-04-07 | 1 | 2015-04-24 | 2015-04-07 | 2015-04-17 | 2015-04-06 | 2015-05-29 | 2015-05-18 |  | 2015-05-29 | 2015-05-20 | PERMITTED | 2015-04-17 | 2015-03-23 | 2015-06-05 | 2015-04-11 | 1 | 2015-06-12 | 2015-04-11 | 2015-06-12 | 2015-04-05 | 2015-05-08 | 2015-05-04 | 1 |  | 2015-05-08 | 2015-05-04 | [5 empty] | 2015-05-29 | 2015-05-27 | 2015-10-02 | 2015-09-30 |  | 2015-10-09 | [10 empty] | 2015-10-23 | 2015-10-21 |  | 2015-11-06 |  | 2015-11-06 | PO 35695 issued 20/5/15 22/06/15 - Dates from Kordia supplied and updated - will need review to bring in better 20/07/15 - Dates revised by Kordia - delays with metalwork 12/08/15 - Kordia revised dates 15/9 TI Complete, 17/9 Integration, 24/9 Vol 4 01/09/15 - Kordia still not started on site 29/09/15 - Working on site. Build largely completed. Link alignment and site integration 5-10 Oct | KDA | [9 empty] | 2015-10-16 | 2015-10-16 | [5 empty] | BUILD |  | FALSE |  | 2524192 | 6669583 | 16-24 Roma Road Ahipara Northland |  |  | CELLSITE |  |  |  | ROAMING |  |  | 2015-05-01 | 2015-04-13 | 2015-04-07 |  |  |  |  | 2015-05-22 | 2015-05-20 |  |  | 2015-03-03
0 | NTH | 1161 | NTH-001-046 | Pakaraka | NTH-001-046-A | Pakaraka Candidate for Forecasting | Far North | 23 | TIER_9 | ACTIVE | COLO | DF |  |  | STACK_A | COLO | [5 empty] | 2015-09-11 |  | 2015-09-18 |  |  |  | FALSE | FALSE |  | 2015-09-25 | FALSE |  | 2015-11-06 |  | 2015-11-13 |  | 2015-12-18 |  |  | 2015-12-18 |  | 2016-02-19 |  | 2016-04-15 |  |  | 2016-04-15 |  |  | 2016-04-15 |  | 2016-05-20 |  |  | 2016-05-20 | [36 empty] | 02/10/15 - Site removed from Acquisition programme - HOLD ALL WORKS 01/09/15 - Kevin to issue search ring by Wed 2/9 1/09/15 - VF Site Datapack received 19/06/15 - Set up caravan 29/09/15 - Advised to hold on site | [17 empty] | HARDMATCH |  | FALSE | [6 empty] | CELLSITE | WIPACTIVE
0 | NTH | 1162 | NTH-002-001 |  |  |  | Whangarei |  | TIER_9 | [22 empty] | FALSE
0 | NTH | 1163 | NTH-002-002 | Whangarei Central |  |  | Whangarei |  | TIER_9 | [22 empty] | FALSE | [60 empty] | Whangarei Central Whangarei Option A: VNZ 12m Co-site on rooftop Grid: 26299981 6607131 (Not great - prefer the TNZ option located at the TNZ Exchange just North of this location) Option B: TNZ option under NTH 002-017 Whanageria North: Grid: see NTH 002-017 Whanageria North Option C: 15/20m GF Pole option on one of the Industrial addresses - plenty of options. Grid: E2629901 N6607131
0 | NTH | 1164 | NTH-002-003 | Otaika | NTH-002-003-A | VF Co-lo | Whangarei | 3 | TIER_2 | ACTIVE | COLO | DU | COLO | grey | INLINE | COLO | 21 | 23.86 | 1 | -35.7453 | 174.3163 | 2010-02-26 | 2010-02-25 | 2010-02-26 | 2010-02-25 | Microwave | NTH-002-007-A | TRUE | FALSE | 2010-02-10 |  | TRUE | 2010-02-10 | 2011-02-10 | 2011-02-10 | 2011-02-17 | 2011-02-17 | 2011-03-03 | 2011-03-07 | 2 | 2011-03-03 | 2014-11-26 | 2011-04-06 | 2011-04-06 | 2011-06-23 | 2011-06-08 | 1 | 2011-06-23 | 2011-06-06 | DISCRETIONARY_RESTRICT | 2011-03-24 | 2011-03-22 | 2011-05-05 | 2011-04-14 | 1 |  | 2011-04-21 |  |  | 2011-08-30 | 2011-09-06 | 1 |  | 2011-08-30 | 2011-09-06 | 2011-10-04 |  |  |  |  | 2011-09-07 | 2011-09-15 | 2011-09-30 | 2011-10-10 | 2011-10-03 | 2011-10-21 | 2011-10-21 | [8 empty] | 2011-10-21 | 2011-10-30 | 2011-10-27 | 2011-10-25 | 2011-11-15 | 2012-02-13 | 2012-04-05 | Vodafone have a 20.5m Type H pole with estimated 71% spare capacity, VF ref: WID. Ring frame on existing. Telecom have 3phase power plinth in their compound. Site Visit : 26.02.2012. Structural Passed. Good co lo option. Caravan planned 08.02.2011 10.02.11 Caravan completed. WO1 issued. Await plans 01 March 2011 01.03.2011 - Rev 0 plans received, circulation complete will be forwarded to Infratel 02.03.2011. PD's issued, VNZ full application to be submitted. VNZ Application and RMA SUBMITTED. VNZ and RC received. VNZ final approval received. | VNZ | 2011-10-20 | 2011-08-22 | 2011-08-22 | 2011-09-07 | 2011-09-07 | 2011-09-29 | 2011-10-04 | 2011-10-07 | 2011-10-10 |  | 2011-10-21 | [6 empty] | 2011-10-01 | FALSE |  | 2629722 | 6605313 | opp 92 High St, Otaika |  |  | CELLSITE |  |  | 2015-05-26 | [12 empty] | 2011-10-07 | 2011-11-07
0 | NTH | 1165 | NTH-002-004 | Hikurangi | NTH-002-004-A | Hikurangi Greenfield | Whangarei | 23 | TIER_4 | ACTIVE | GF | DF | T2 20 RH |  | STACK_A | COSITE |  |  |  | -35.5985 | 174.2709 |  |  |  |  | Microwave | NTH-002-005-A | FALSE | FALSE |  |  | FALSE |  | 2015-04-13 | 2015-03-18 | 2015-04-20 | 2015-03-26 | 2015-05-29 | 2015-05-15 | 1 | 2015-06-05 | 2015-05-15 | 2015-06-26 | 2015-05-20 | 2015-06-12 | 2015-06-10 |  | 2015-06-19 | 2015-08-05 | DISCRETIONARY_RESTRICT | 2015-07-03 | 2015-07-07 | 2016-04-08 |  | 1 | 2016-04-08 |  | 2015-09-04 | 2015-05-20 | 2015-06-30 | 2015-07-07 | 1 |  | 2015-06-30 | 2015-07-07 | [5 empty] | 2016-07-11 | [15 empty] | 2016-08-27 | [5 empty] | 02/10/15 - Site in BUILD Programme 15/06/15 - Require VF co-site approval for All Site Acq Complete. IWI consultation to be set up (Ron) 09/07/15 - Lodges co-site approval and also Tender Instruction 04/08/15 - S92 from Council - Heritage NZ and Iwi` 05/08/15 - VF Co-site approval received 18/08/15 - Iwi consultation when weather better for access. Puit consent on hold. Not build 2015. Withdraw tender instruction. 22/09/15 - Landscape/visual looks OK. Iwi sign-off will be required for consent 9/2/16 - Iwi consultation on site 22 Feb (planned) | [10 empty] | 2016-08-13 |  | 2015-03-25 | MEDIUM |  |  |  | BUILD |  | FALSE |  | 2625867 | 6621661 | Mountain View Road, Huikurangi |  |  | CELLSITE | WIPACTIVE |  |  | ROAMING |  |  |  | 2016-05-26 | [5 empty] | 2016-06-18 |  |  |  | 2015-03-26
0 | NTH | 1166 | NTH-002-005 | Kamo North (TX HUB) | NTH-002-005-A | Kamo North on TNZ land | Whangarei | 3 | TIER_2 | ACTIVE | GF | DU | T2 20 RH | grey | STACK_A | COSITE | 19.5 | 20 |  | -35.659 | 174.2815 | 2010-02-26 | 2010-02-25 | 2010-02-26 | 2010-02-25 | Microwave | NTH-002-006-E | TRUE | FALSE | 2010-02-11 |  | FALSE | 2011-03-15 | 2011-03-22 | 2011-03-22 | 2011-03-24 | 2011-03-24 | 2011-05-06 | 2011-05-05 | 1 | 2011-05-06 | 2011-05-05 | 2011-08-30 | 2011-08-31 | 2011-11-04 | 2011-10-28 |  | 2011-11-30 |  | OPW | 2011-05-30 | 2011-06-01 | 2011-07-13 | 2011-06-29 | 1 | 2011-07-20 | 2011-06-29 |  |  | 2011-09-12 | 2011-09-26 | 1 |  | 2011-09-12 | 2011-09-26 | 2011-11-10 |  |  |  |  | 2011-10-20 | 2011-10-19 | 2011-11-24 | 2011-11-04 | 2011-11-09 | 2011-11-26 | 2011-11-25 | [8 empty] | 2011-11-25 | 2011-12-05 | 2011-12-07 | 2011-11-24 | 2011-12-20 | 2012-03-19 | 2012-06-15 | Hub site and given dish requirements not suitable unless pole replaced. 23.03.2011 Caravaned. LOS cherry pick complete. Site chosen adjacent to trig beacon on TNZ land. WO 1 issued 24.03.2011 boundary survey complete today, await plans. Have RC. TNZ approved Project Plan. Await sub lease from Jon W. | TNZ | 2011-11-27 | 2011-08-22 | 2011-08-22 | 2011-10-10 | 2011-11-02 | 2011-11-19 | 2011-11-10 | 2011-11-11 | 2011-11-10 | 2011-11-21 | 2011-11-30 | [6 empty] | 2011-11-10 | FALSE |  | 2626730 | 6614935 | 231 Purakiore Rd on TNZ land |  |  | CELLSITE | [15 empty] | 2011-12-07 | 2011-12-07
0 | NTH | 1167 | NTH-002-006 | Kamo (TX HUB) | NTH-002-006-E | Kamo | Whangarei | 3 | TIER_2 | ACTIVE | GF | DU | P1 | grey | STACK_A | COSITE | 14.5 | 15 |  | -35.6831 | 174.2997 | 2010-02-26 | 2010-02-25 | 2010-02-26 | 2010-02-25 | Fibre Optic | NTH-002-011-A | TRUE | FALSE | 2010-02-11 |  | FALSE |  | 2011-02-24 | 2011-02-24 | 2011-03-03 | 2011-03-02 | 2011-05-06 | 2011-05-05 | 1 | 2011-05-06 | 2011-05-05 | 2011-05-16 | 2011-05-06 | 2011-06-24 | 2011-06-24 |  | 2011-09-30 | 2011-09-14 | DISCRETIONARY_RESTRICT | 2011-05-16 | 2011-05-16 | 2011-06-27 | 2011-06-07 | 1 | 2011-06-27 | 2011-06-15 |  |  | 2011-09-07 | 2011-09-13 | 1 |  | 2011-09-07 | 2011-09-13 | 2011-09-13 |  |  |  |  | 2011-09-13 | 2011-09-14 | 2011-10-07 | 2011-09-23 | 2011-09-27 | 2011-10-18 | 2011-10-18 | [8 empty] | 2011-10-21 | 2011-10-30 | 2011-10-27 | 2011-11-04 | 2011-11-15 | 2012-02-13 | 2012-05-29 | 24.03.2011 Site moved from behind Super Liquor to where the Pohutukawa tree was. Now out of the way of teh truck delivery to trade entrance to Super Liquor. Landlord happy. Await drawings. 30.03.2011 Boundary servey complete today. Expect plans tomorrow for first review |  | 2011-10-18 | 2011-08-22 | 2011-08-22 | 2011-08-31 | 2011-08-31 | 2011-09-13 | 2011-09-13 | 2011-10-13 | 2011-10-03 |  | 2011-10-21 | [6 empty] | 2011-10-12 | FALSE |  | 2628332 | 6612237 | 567 Kamo Road |  | sent to Paul Lees & Heather McNeal Whangarei District Council - 13/05/2011 | CELLSITE | [15 empty] | 2011-10-07 | 2011-11-07
0 | NTH | 1168 | NTH-002-007 | Maunu Hill (TX HUB) | NTH-002-007-A | VF Co-lo | Whangarei | 3 | TIER_2 | ACTIVE | COLO | DU | COLO | grey | INLINE | COLO | 20.5 | 23.3 | 1 | -35.7388 | 174.231 | 2010-02-26 | 2010-02-25 | 2010-02-26 | 2010-02-25 | Fibre Optic, Fibre Optic | AKL-007-106-A, NTH-002-011-A | TRUE | FALSE | 2010-02-10 |  | FALSE |  | 2011-02-10 | 2011-02-10 | 2011-02-15 | 2011-02-15 | 2011-03-11 | 2011-03-15 | 2 | 2011-03-11 | 2012-04-13 |  | 2011-04-06 | 2011-06-23 | 2011-06-08 |  | 2011-06-23 | 2011-06-13 | DISCRETIONARY_FULL | 2011-04-18 | 2011-04-18 | 2011-05-30 | 2011-05-11 | 1 | 2011-05-18 | 2011-05-16 |  |  | 2011-09-07 | 2011-09-07 | 1 |  | 2011-09-07 | 2011-09-07 | 2011-09-14 |  |  |  |  | 2011-09-14 | 2011-09-18 | 2011-10-03 | 2011-10-10 | 2011-09-30 | 2011-10-17 | 2011-10-21 | [8 empty] | 2011-10-14 | 2011-10-30 | 2011-10-27 | 2011-10-21 | 2011-11-15 | 2012-02-13 | 2012-04-05 | Andrew Potter : Vodafone have a 20m Type A pole with estimated 20% spare capacity, VF ref: MNU. Colo not suitable as our microwave requirements are too large, hub site. Barbara R : Site viste 27.01.2011. Structural passed. Good option for co lo. Caravan planned 10.02.2011. WO1 issued 15.02.2011 Planning Drw Rev 0 issied and circulation complete - VNZ aPPLICATION MADE2/3 - wait for letter from LO before lodging consent. Visual assessment required for this site. | VNZ | 2011-10-13 | 2011-08-22 | 2011-08-22 | 2011-09-05 | 2011-09-05 | 2011-09-14 | 2011-09-14 | 2011-10-04 | 2011-10-10 |  | 2011-10-21 | [6 empty] | 2011-10-01 | FALSE |  | 2622024 | 6606159 | 28/173 Millington Road, Maunu |  | lodged with Heather McNeal - Consents Manager - 19/04/2011 | CELLSITE | [15 empty] | 2011-10-07 | 2011-11-07
0 | NTH | 1169 | NTH-002-008 | Otangarei | NTH-002-008-A | Mt Denby Golf Course | Whangarei | 3 | TIER_2 | ACTIVE | COLO | DU | COLO | green | INLINE | COLO | 23.4 | 23.9 |  | -35.6923 | 174.3132 | 2010-02-26 | 2010-02-25 | 2010-02-26 | 2010-02-25 | Microwave | NTH-002-005-A | TRUE | FALSE | 2010-02-11 |  | FALSE |  | 2011-05-12 | 2011-05-12 | 2011-05-19 | 2011-05-13 | 2011-06-23 | 2011-06-21 | 2 | 2011-06-23 | 2011-07-04 | 2011-07-20 | 2011-07-20 | 2011-08-31 | 2011-08-18 |  | 2011-09-30 | 2011-08-31 | DISCRETIONARY_RESTRICT | 2011-07-11 | 2011-07-12 | 2011-08-22 | 2011-08-03 | 2 | 2011-08-29 | 2011-08-03 |  |  | 2011-10-13 | 2011-11-04 | 1 |  | 2011-10-13 | 2011-11-04 | 2011-11-14 |  |  |  |  | 2011-10-18 | 2011-10-18 | 2011-11-11 | 2011-11-04 | 2011-10-31 | 2011-11-27 | 2011-11-25 | [8 empty] | 2011-11-29 | 2011-12-05 | 2011-12-07 | 2011-11-26 | 2011-12-20 | 2012-03-19 | 2012-04-13 | 27.01.2012 VNZ site situated well within high Pine trees on golf course. RF issues and future Tx issues. 12.05.011 REVISITED. LPR is on NZTA land and has to vested back to council. Have to progress co lo wherever possible (M Goss). WO1 issued. VNZ have right to remove and trim trees. VNZ have requested top spot and provision for larger antenna. Said will go with larger antenna on our RMA if we can have top. Rec VNZ prelim approval | VNZ | 2011-11-28 | 2011-08-22 | 2011-08-22 | 2011-10-12 | 2011-11-02 | 2011-11-14 | 2011-11-14 | 2011-11-04 | 2011-11-04 | 2011-11-22 | 2011-11-30 | [6 empty] | 2011-11-01 | FALSE |  | 2629539 | 6611204 | Mt Denby Golf Course, Denby Crescent, Tikipunga |  | sent to WDC 12/07/11 - 12/07/2011 | CELLSITE | [15 empty] | 2011-12-08 | 2011-12-08
0 | NTH | 1170 | NTH-002-009 | Kensington | NTH-002-009-A | VF Co-lo | Whangarei | 3 | TIER_2 | ACTIVE | COLO | DU | COLO | grey | INLINE | COLO | 15 | 17.9 |  | -35.7087 | 174.3214 | 2010-02-26 | 2010-02-25 | 2010-02-26 | 2010-02-25 | Microwave | NTH-002-011-A | TRUE | FALSE | 2010-02-10 |  | FALSE | 2011-02-09 | 2011-02-10 | 2011-02-24 | 2011-03-03 | 2011-02-28 | 2011-05-23 | 2011-05-05 | 2 | 2011-05-23 | 2014-11-26 | 2011-06-20 | 2011-06-08 | 2011-09-26 | 2011-09-02 |  | 2011-10-31 | 2011-10-10 | DISCRETIONARY_RESTRICT | 2011-05-16 | 2011-05-16 | 2011-07-11 | 2011-06-10 | 1 | 2011-07-18 | 2011-06-15 |  |  | 2011-10-14 | 2011-11-04 | 1 |  | 2011-10-14 | 2011-11-04 | 2011-11-14 |  |  |  |  | 2011-10-31 | 2011-10-31 | 2011-11-11 | 2011-11-10 | 2011-11-07 | 2011-11-21 | 2011-11-25 | [8 empty] | 2011-11-25 | 2011-12-05 | 2011-12-07 | 2011-12-21 | 2011-12-20 | 2012-03-19 | 2012-04-13 | Andrew Potter : Vodafone have a 13m Type U pole with estimated 94% spare capacity, VF ref: WBP. Double stack proposed. Data pack required. Barbara R : 27.01.2011 Structural passed however Cabinet space is tight at GL. LL suggested lifting cabinets above external WC's - requires steel platform - not ideal. Caravan planned for 24.02.2011. Landlord not happy with rental offered. Cant go much more. Work Order 1 issued, plans due 17 March. Cabinets to run parrallel with the fence, | VNZ | 2011-11-24 | 2011-08-22 | 2011-08-22 | 2011-10-03 | 2011-11-02 | 2011-11-14 | 2011-11-14 | 2011-11-10 | 2011-11-10 | 2011-11-17 | 2011-11-30 | [6 empty] | 2011-11-08 | FALSE |  | 2630250 | 6609369 | 95 Kamo Road, Kensington |  | sent to Paul Lees & Heather McNeal Whangarei District Council - 13/05/2011 | CELLSITE |  |  | 2015-05-26 | [12 empty] | 2011-12-08 | 2011-12-08
0 | NTH | 1171 | NTH-002-010 | Parahaki North |  |  | Whangarei |  | TIER_9 | [22 empty] | FALSE | [60 empty] | Parahaki North, Whangarei. (Native Forest, Memorial Drive Highest of Hill Point sort : probably 2G at 1800Mhz site ONLY) Option A: Cosite with TNZ (might be a Kordia Pole) - Only use for GSM Grid: E2631644 N6608957 Option B: GF adjacent to TNZ option Grid:E2631664 N6608987
0 | NTH | 1172 | NTH-002-011 | Whangarei (Main HUB) | NTH-002-011-A | Maori Trust Board Building | Whangarei | 3 | TIER_2 | ACTIVE | RT | DF | RT | grey | STACK_A | COSITE | 22 | 19.8 | 1 | -35.7228 | 174.3189 | 2010-02-26 | 2010-02-25 | 2010-02-26 | 2010-02-25 | Fibre Optic | AKL-007-106-A | TRUE | FALSE | 2010-02-10 |  | FALSE |  | 2011-02-10 | 2011-02-10 | 2011-02-25 | 2011-02-15 | 2011-04-07 | 2011-04-11 | 3 | 2011-04-08 | 2014-12-08 | 2011-05-30 | 2011-05-25 | 2011-07-08 | 2011-06-30 | 2 | 2011-07-08 | 2011-07-05 | DISCRETIONARY_RESTRICT | 2011-04-18 | 2011-04-18 | 2011-06-02 | 2011-05-11 | 1 | 2011-05-18 | 2011-05-16 |  |  | 2011-08-22 | 2011-08-22 | 1 |  | 2011-08-22 | 2011-08-22 | 2011-08-25 |  |  |  |  | 2011-08-25 | 2011-08-30 | 2011-09-23 | 2011-09-23 | 2011-09-10 | 2011-09-22 | 2011-09-22 | [8 empty] | 2011-10-07 | 2011-10-30 | 2011-10-27 | 2011-10-21 | 2011-11-01 | 2012-01-30 | 2012-04-03 | Barbara R : 26.01.2011 HUB site. Excellent candidate, sufficient room inside + additional small room. Could be used to house the generator. VNZ also investigating generator - possible cost share ? Building manager very positive. Caravan planned 10.02.2011. 01.02.2011 VNZ keen on gen share. VNZ deadline for install 31.03.2011. WO1 Isssued await plans on 01 March. 2d rather share VNZ generator. 2D to put in proposal to VNZ on sharing - Paul Kinghan has responded in detail to Vodafone. Planning Dwg Rev 0 issed and circulation complete. Await drawings |  | 2011-09-29 | 2011-08-22 | 2011-08-22 | 2011-09-05 | 2011-09-05 | 2011-08-25 | 2011-08-25 | 2011-09-16 | 2011-09-15 |  | 2011-10-07 | [6 empty] | 2011-09-03 | FALSE |  | 2629996 | 6607807 | 1-3 Hunt Street, Whangarei |  | lodged with Heather McNeal - Consents Manager - 19/04/2011 | CELLSITE |  |  | 2015-05-26 | [12 empty] | 2011-10-06 | 2011-09-30
0 | NTH | 1173 | NTH-002-012 | Portland | NTH-002-012-A | Portland - VF Co-lo | Whangarei | 23 | TIER_4 | ACTIVE | COLO | DU | COLO |  | INLINE | COLO | 15 | 15 |  | -35.8071 | 174.3111 | 2010-02-26 | 2011-12-19 | 2010-02-26 | 2010-02-25 | Fibre Optic | NTH-002-011-A | TRUE | FALSE | 2010-02-10 |  | FALSE |  | 2012-02-22 | 2012-02-22 | 2012-03-07 | 2012-03-09 | 2012-06-08 | 2012-05-29 | 5 | 2012-06-08 | 2015-04-23 | 2016-02-19 | 2016-02-09 | 2016-04-29 |  |  | 2016-04-29 |  | DISCRETIONARY_FULL | 2015-06-01 | 2015-05-27 | 2015-07-17 | 2015-06-17 | 5 | 2015-07-24 | 2015-06-17 | 2015-05-22 | 2015-05-20 | 2015-07-06 | 2015-06-17 | 1 |  | 2015-07-13 | 2015-06-17 | [5 empty] | 2016-06-06 | [6 empty] | 2016-04-15 | [8 empty] | 2016-07-29 | [5 empty] | 02/10/15 - URGENCY for Site to build 30/06/15 - Finally got docs from VF 31/07/15 - PO 36531 issued for Downers Build. Get underway with metalwork, clock stopped until access available. 04/08/15 - Delays with Fletcher signing. Downers to do Project plan so we can lodge final and build approval together 09/09/15 - Removing from 2015 programme due to issues with Fletchers lease agreements 16/09/15 - PO6 withdrawn. Huawei to advise costs to date, metalwork to be stored by 2D, Amend PO 4/11/15 - Lease details back with VF. Will retender for build. Chorus advised of revised RFS date 8/12/15 - Fletchers not looking responding until into New Year 9/2/16 - Head Lease terms agreed. Lease will take 2 months to execute. Brad requested to look at getting Fletcher lawyers and VF together to finalise lease conditions | VNZ | [9 empty] | 2016-07-15 |  |  |  | AUCKLAND_WHANGAREI | 2016-03-31 |  | BUILD |  | FALSE |  | 2629144 | 6598466 | 170 Portland Quarry Road |  | In portland overlay, countryside zone underlying. Existing pole exceeds height limit for zone, requires consent as discretionary activity. AT, 4.9.12 - 04/09/2012 | CELLSITE | WIPACTIVE |  |  | ROAMING |  |  |  | 2016-05-02 | [5 empty] | 2016-05-27 |  |  |  | 2012-03-09
0 | NTH | 1174 | NTH-002-013 | Marsden Point | NTH-002-013-A | Marsden Point VNZ CoLo | Whangarei | 23 | TIER_4 | ACTIVE | COLO | DU | COLO |  | STACK_A | COLO | 30 | 30 |  | -35.8575 | 174.4135 |  | 2011-12-19 |  |  | Fibre Optic | NTH-002-011-A | FALSE | FALSE |  |  | FALSE |  | 2012-02-22 | 2012-02-22 | 2012-03-21 | 2012-03-21 | 2012-06-08 | 2012-05-31 | 3 | 2012-06-08 | 2012-09-11 | 2015-03-30 | 2015-03-24 | 2015-05-08 | 2015-05-22 |  | 2015-05-15 | 2015-05-27 | DISCRETIONARY_FULL | 2015-04-06 | 2015-03-16 | 2015-05-29 | 2015-04-15 | 3 | 2015-05-29 | 2015-04-15 | 2015-04-01 | 2015-02-25 | 2015-05-15 | 2015-05-18 | 1 |  | 2015-05-22 | 2015-05-18 | [5 empty] | 2015-07-13 | 2015-07-09 | 2015-08-28 | 2015-08-19 |  |  |  | 2015-08-28 | 2015-08-25 | [7 empty] | 2015-09-18 | 2015-09-11 |  |  |  |  | 17/07/15 - VF build approval received 18/08/15 - Integrate next week. Feeders in, Cabs in antennas up mw mount up 11/09/15 - Site on air 02/10/15 - Feeders to be relocated to enable ladder to be safely used. Skycomms to advise process and timing | VNZ | [9 empty] | 2015-09-11 | 2015-09-02 |  |  | AUCKLAND_WHANGAREI | 2015-08-21 | 2015-08-25 | BUILD |  | FALSE |  | 2638304 | 6592725 | Flyger Road, Ruakaka, Whangarei |  | On designation DW68 (Water), in Notable Landscape Area. Underlying Zoning Countryside. Exceeds height limit, requires consent as a Discretionary activity. AT. 4.9.12. - 04/09/2012 | CELLSITE |  |  |  | ROAMING |  |  | 2015-04-24 | 2015-07-10 | 2015-04-29 |  |  |  |  | 2015-06-12 | 2015-06-29 |  |  | 2012-02-22
0 | NTH | 1175 | NTH-002-014 | Brynderwyn | NTH-002-014-A | Brynderwyn VFNZ Co-Lo | Whangarei | 23 | TIER_4 | ACTIVE | COLO | DU | COLO |  | STACK_A | COLO | 25 | 35 |  | -36.0731 | 174.4244 |  | 2011-12-19 |  |  | Microwave, Microwave | NTH-002-013-A, NTH-003-010-A | FALSE | FALSE |  |  | FALSE |  | 2012-03-14 | 2012-03-14 | 2012-03-21 | 2012-03-21 | 2012-06-08 | 2012-06-06 | 4 | 2012-06-08 | 2015-03-25 | 2015-03-30 | 2015-03-24 | 2015-05-22 | 2015-05-22 |  | 2015-06-05 | 2015-05-27 | DISCRETIONARY_FULL | 2015-03-20 | 2015-03-27 | 2015-05-22 | 2015-04-30 | 4 | 2015-05-29 | 2015-04-30 | 2015-04-01 | 2015-02-25 | 2015-04-08 | 2015-04-13 | 1 |  | 2015-04-15 | 2015-04-13 | [5 empty] | 2015-07-13 | 2015-07-09 | 2015-09-04 | 2015-09-10 | [12 empty] | 2015-09-29 | 2015-09-28 |  | 2015-10-30 |  | 2015-10-30 | 17/07/15 - VF build approval received 04/08/15 - Cabinets in next week. Crane in when weather OK. Sky to advise prelim dates 24/09/14 - Vol4 received. CR in for Monday night to go live 28/09/15 - Site on air. Microwave link still out of spec - monitor and repan 02/10/15 - MW has been installed at wrong height. CR required for outage to relocate | VNZ | [9 empty] | 2015-09-21 | 2015-09-22 |  |  | AUCKLAND_WHANGAREI |  |  | BUILD |  | FALSE |  | 2638886 | 6568788 | Artillary Road Off SH Brynderwyn |  | Discretionary Consent -co - lo on VF. VA required. AT 12.9.12. - 12/09/2012 | CELLSITE |  |  |  | ROAMING |  |  | 2015-05-05 | 2015-04-24 | 2015-04-29 |  |  |  |  | 2015-06-12 | 2015-06-29 |  |  | 2012-03-14
0 | NTH | 1176 | NTH-002-015 | Whangarei Hospital | NTH-002-015-E | Maunu Road LPR - NZTA | Whangarei | 3 | TIER_2 | ACTIVE | RSR | DU | P4F | grey | INLINE |  | 12.7 | 13.3 |  | -35.7345 | 174.3041 | 2010-02-26 |  | 2010-02-26 |  | Microwave | NTH-002-003-A | TRUE | FALSE | 2010-02-10 |  | FALSE | 2011-04-18 | 2011-03-23 | 2011-03-23 | 2011-03-31 | 2011-03-30 | 2011-05-06 | 2011-05-05 | 2 | 2011-05-06 | 2014-11-26 | 2011-09-15 | 2011-09-13 | 2011-09-29 | 2011-10-06 |  | 2012-04-06 |  | NES | 2011-08-31 | 2011-08-29 | 2011-09-28 | 2011-09-29 | 1 | 2011-10-05 | 2011-09-29 |  |  | 2011-09-12 | 2011-09-19 | 1 |  | 2011-09-12 | 2011-09-19 | 2011-11-12 |  |  |  |  | 2011-10-19 | 2011-10-19 | 2011-10-28 | 2011-10-27 | 2011-10-25 | 2011-11-22 | 2011-10-25 | [8 empty] | 2011-10-25 | 2011-12-05 | 2011-12-07 | 2011-12-13 | 2011-12-20 | 2012-03-19 | 2012-04-13 | Back up. WO1 issued. Cherry Pick to be done. TMP taking long. (15wd) issue WO so that when Cherry pick done we will know which site and can lodge almost immediatly. Cherry Pick complete. This is active candidate 11/5/11 - On NZTA land - Andy to get peliminary approval to build at this location |  | 2011-11-23 | 2011-08-22 | 2011-11-12 | 2011-10-04 | 2011-11-12 | 2011-10-10 | 2011-11-12 | 2011-10-27 | 2011-10-25 |  | 2011-11-30 | [6 empty] | 2011-10-25 | FALSE |  | 2628643 | 6606532 | 168A Maunu Road opposite Hospital Rd and Maunu Road T Junction |  | Lodged 29.8.2011 - 30/08/2011 Approved 29.9.11: Council reference CC1100013 P109352 - 03/10/2011 | CELLSITE |  |  | 2015-05-26 | [12 empty] | 2011-12-07 | 2011-12-07
0 | NTH | 1177 | NTH-002-016 | Sherwood Rise | NTH-002-016-D | LPR - Onerahi Rd | Whangarei | 3 | TIER_2 | ACTIVE | RSR | DU | P4F | grey | INLINE | STANDALONE | 14.4 | 14.9 | 1 | -35.7521 | 174.3679 | 2010-02-26 | 2010-02-25 | 2010-02-26 | 2010-02-25 | Microwave | NTH-002-003-A | FALSE | FALSE | 2010-02-10 |  | FALSE | 2011-02-14 | 2011-02-24 | 2011-02-24 | 2011-03-14 | 2011-03-09 | 2011-03-31 | 2011-03-31 | 2 | 2011-03-31 | 2014-11-24 | 2011-05-30 | 2011-05-25 | 2011-09-12 | 2011-09-19 |  | 2011-09-30 | 2011-09-19 | NES | 2011-04-21 | 2011-04-18 | 2011-06-02 | 2011-05-11 | 1 | 2011-05-18 | 2011-05-16 |  |  | 2011-08-12 | 2011-08-12 | 1 |  | 2011-08-12 | 2011-08-12 | 2011-09-27 |  |  |  |  | 2011-08-29 | 2011-08-29 | 2011-10-07 | 2011-10-04 | 2011-09-22 | 2011-10-14 | 2011-10-14 | [8 empty] | 2011-10-21 | 2011-10-30 | 2011-10-27 | 2011-11-04 | 2011-11-11 | 2012-02-09 | 2012-04-03 | Barbara R : Site vist 26.01.2011 LPR - 3 options. TX to LOS 2-4 Feb - then advise. Have requested info from VNZ re ex clock tower on cnr of Onerahi and Waverley. TX have done LOS. LPR with speed counter on it, is preferred. Caravan 24.02.2011. LOS TO BE REDONE. 09.03 LOS redone. Site good for Tx. WO1 issued. Rev 0 due 23.03 |  | 2011-10-17 | 2011-08-22 | 2011-08-22 | 2011-08-29 | 2011-08-29 | 2011-09-27 | 2011-09-27 | 2011-10-07 | 2011-10-04 |  | 2011-10-21 | [6 empty] | 2011-09-22 | FALSE |  | 2634379 | 6604482 | opposite 141 Onerahi Road |  | Lodged with Heather McNeal - Consents Manager - 19/04/2011 | CELLSITE |  |  | 2015-05-26 | [12 empty] | 2011-10-16 | 2011-10-25
0 | NTH | 1178 | NTH-002-017 | Whangarei Central North |  |  | Whangarei |  | TIER_9 | [22 empty] | FALSE | [60 empty] | Whangarei Central North Whangarei (Might be combined with 002-002 Whangarei Central SR) Option A: 30m TNZ pole atop the Exchange Building. Grid: 2629890 6607256 Option B: Use Vodafone Rooftop option - based on NTH 002-002 Whanageria Central. Grid: see NTH 002-002. Access: Appointment to get inside Building and therefore Tower required from TNZ. Otherwise Tower easily viewable from car park.
0 | NTH | 1179 | NTH-002-018 | Okara Park | NTH-002-018-G | LPR Stadium | Whangarei | 3 | TIER_2 | ACTIVE | RSR | DU | P4F | green | INLINE | COSITE | 13.5 | 14 |  | -35.7343 | 174.3281 | 2010-02-26 | 2010-02-25 | 2010-02-26 | 2010-02-25 | Microwave | NTH-002-011-A | TRUE | FALSE | 2010-02-11 |  | FALSE | 2011-05-15 | 2011-05-12 | 2011-05-12 | 2011-05-23 | 2011-05-18 | 2011-06-01 | 2011-05-25 | 2 | 2011-06-15 | 2014-11-24 | 2011-05-31 | 2011-05-25 | 2011-09-12 | 2011-09-19 |  | 2011-09-30 | 2011-09-19 | DISCRETIONARY_FULL | 2011-05-30 | 2011-06-01 | 2011-07-12 | 2011-07-05 | 1 | 2011-07-19 | 2011-07-05 |  |  | 2011-08-22 | 2011-08-12 | 1 |  | 2011-08-22 | 2011-08-12 | 2011-09-27 |  |  |  |  | 2011-08-29 | 2011-08-30 | 2011-10-07 | 2011-10-04 | 2011-09-29 | 2011-10-17 | 2011-10-21 | [8 empty] | 2011-10-21 | 2011-10-30 | 2011-10-27 | 2011-11-04 | 2011-11-11 | 2012-02-09 | 2012-04-03 | LPR is on the otherside of roundabout closer to the stadium. Easier build. Away from power lines. WO1 issued. Drawings on circulation. Simon and Jeff of Whangarei Council - Roads are happy with the position. |  | 2011-10-18 | 2011-08-22 | 2011-08-22 | 2011-08-29 | 2011-08-29 | 2011-09-27 | 2011-09-27 | 2011-10-07 | 2011-10-04 |  | 2011-10-21 | [6 empty] | 2011-09-29 | FALSE |  | 2630811 | 6606518 | Okara Park Roundabout Stadium side |  |  | CELLSITE |  |  | 2015-05-26 | [12 empty] | 2011-10-16 | 2011-10-25
0 | NTH | 1180 | NTH-002-019 |  |  |  | Whangarei |  | TIER_9 | [22 empty] | FALSE
0 | NTH | 1181 | NTH-002-020 | Maunu Village | NTH-002-020-A | VF Co-lo Tui Crescent Foodmart | Whangarei | 3 | TIER_2 | ACTIVE | COLO | DU | COLO | grey | INLINE | COLO | 17.9 | 18.4 | 1 | -35.7395 | 174.2824 | 2010-02-26 | 2010-02-25 | 2010-02-26 | 2010-02-25 | Leased Line | NTH-002-011-A | TRUE | FALSE | 2010-02-11 |  | FALSE |  | 2011-02-10 | 2011-02-10 | 2011-03-25 | 2011-02-15 | 2011-03-11 | 2011-03-11 | 2 | 2011-04-28 | 2011-04-27 |  | 2011-04-12 | 2011-06-24 | 2011-06-16 |  | 2011-11-30 | 2011-11-10 | LIMITED_NOTIFIED | 2011-07-18 | 2011-07-12 | 2011-10-27 | 2011-09-30 | 2 | 2011-11-03 | 2011-09-30 |  |  | 2011-11-29 | 2011-11-01 | 1 |  | 2011-11-29 | 2011-11-01 | 2011-11-25 |  |  |  |  | 2011-11-14 | 2011-11-14 | 2011-12-06 | 2011-12-06 | 2011-11-28 | 2011-12-06 | 2011-12-06 | [8 empty] | 2011-12-06 | 2011-12-12 | 2011-12-08 | 2012-01-27 | 2012-01-20 | 2012-04-19 | 2012-06-15 | Andrew Potter : Vodafone have approximate 12m pole, not details on their site database. Order datapack, this is probably going to be our best option. Barbara R : VNZ structural passed, will require additional lease area and head frame sawpout. TP allows upto 15m. Site Aqu (Andy) dealt with owner when did VNZ, will make contact. Owner is keen. Doesnt want additional mast, was a bit of hassels with this one. Will need to double stack. WO1 Issued await plans 03 March Rev 0 issued circulation complete. Will be returned to Infratel 02.03.2011 16/3 - Mikhail to let team know which tree is in the way. Have approached VNZ and asked that they address the problem (We cant as we dont have legal right to be there) Need this site as its CO LO VNZ have requested we amend the head fram to accomodate there future plans. Vodafone have approved the co location | VNZ | 2011-12-07 | 2011-11-14 | 2011-11-14 | 2011-11-23 | 2011-11-25 | 2011-11-23 | 2011-11-25 | 2011-12-06 | 2011-12-07 | 2011-11-28 | 2011-12-16 | [6 empty] | 2011-11-24 | FALSE |  | 2626671 | 6606004 | 1 Tui Crescent |  | sent up to WDC 12/07/11 - 12/07/2011 | CELLSITE | [15 empty] | 2011-12-19 | 2011-12-20
0 | NTH | 1182 | NTH-002-021 | Tikipunga | NTH-002-021-A | VF Co-lo | Whangarei | 3 | TIER_2 | ACTIVE | COLO | DU | COLO | grey | INLINE | COLO | 14.64 | 15.14 | 1 | -35.6874 | 174.3262 | 2010-02-26 | 2010-02-25 | 2010-02-26 | 2010-02-25 | Microwave | NTH-002-005-B | TRUE | FALSE | 2010-02-11 |  | FALSE |  | 2011-02-10 | 2011-02-10 | 2011-02-16 | 2011-02-16 | 2011-03-15 | 2011-03-15 | 2 | 2011-03-15 | 2011-04-07 |  | 2011-04-12 | 2011-12-19 | 2011-07-28 |  | 2011-10-31 | 2011-10-10 | LIMITED_NOTIFIED | 2011-07-25 | 2011-07-25 | 2011-10-04 | 2011-09-30 | 2 | 2011-10-11 | 2011-09-30 |  |  | 2011-11-29 | 2011-11-03 | 1 |  | 2011-11-29 | 2011-11-03 | 2011-11-25 |  |  |  |  | 2011-11-29 | 2011-11-29 | 2011-12-06 | 2011-12-12 | 2011-12-05 | 2011-11-30 | 2011-12-12 | [8 empty] | 2011-12-12 | 2011-12-12 | 2011-12-14 | 2012-01-27 | 2012-01-20 | 2012-04-19 | 2012-05-23 | Vodafone have a 10m Type 356 pole with estimated 16% spare capacity. Dish requirements (1x0.6 and 1x0.3) will more than likley overload tower therefore this option made back-up but datapack to be ordered to double check. 10.02.2011 We will have to double stack RF want 2d on top or it wont be viable. HtBoundary exceeded. Not going to be easy. Rev 1 issued. Application in to VNZ. Landlord has questions / concerns. Vodafone have approved the co location application. Landlord has signed consent and DoV. RMA submitted | VNZ | 2011-12-12 | 2011-11-14 | 2011-11-14 | 2011-11-23 | 2011-11-25 | 2011-11-23 | 2011-11-25 | 2011-12-06 | 2011-12-08 |  | 2012-01-09 | [6 empty] | 2011-12-06 | FALSE |  | 2630727 | 6611721 | 159 Kiripaka Road Tikipunga Whangarei |  | Limited Notified application lodged on 25.7.11 - 01/08/2011 | CELLSITE | [15 empty] | 2011-12-19 | 2011-12-20
0 | NTH | 1183 | NTH-002-022 | Tutukaka | NTH-002-022-C | Tutukaka - Spark CO LO | Whangarei | 23 | TIER_4 | ACTIVE | COLO | DU | COLO | Grey | INLINE | COLO | 17 | 24 |  | -35.6184 | 174.5139 |  | 2011-12-19 |  |  | Fibre Optic | NTH-002-011-A | FALSE | FALSE |  |  | FALSE |  | 2012-02-22 | 2012-02-22 | 2012-08-31 | 2012-08-31 | 2012-10-02 | 2012-10-03 | 3 | 2012-10-02 | 2015-07-09 | 2015-05-15 | 2015-05-13 | 2015-11-20 | 2015-11-13 |  | 2015-11-20 |  | DISCRETIONARY_FULL | 2015-05-04 | 2015-04-20 | 2015-11-13 | 2015-11-13 | 2 | 2015-11-13 | 2015-11-13 | 2015-05-18 | 2015-05-15 | 2015-06-19 | 2015-06-11 | 1 |  | 2015-06-26 | 2015-06-11 | [5 empty] | 2015-11-30 | 2015-11-30 | 2015-12-11 | 2015-12-18 |  |  |  | 2015-12-08 | 2015-12-14 | 2015-10-09 | [6 empty] | 2015-12-22 | 2015-12-21 |  |  |  |  | 30/3/15 - Colo application lodged with Spark 11/5/15 - Preliminary approval received. Liz requested cost of rent 04/08/15 - S92 from Council - Heritage NZ and Iwi 11/08/15 - Spark advised their works on site - looks like clash with our panels. Responded back to Spark 18/08/15 - HNZ and IWI consult on site 02 Sept. Then hopefully consent passes 29/09/15 - Council have raised another IWI. Melissa will work with Dane to see if covered by Ngati Wai 24/11/15 - Consent in, Spark Build approval received, Build starts 30 Nov 7/12/15 - pad in, cabinets down, Power and fibre by 9 Dec, . Problem with space on mast for panels (being sorted), Mediaworks link issue which may prevent GU900 being placed live. Mike Lancaster assisting with solutions | TNZ | [9 empty] | 2015-12-16 | 2015-12-16 |  |  | NORTHLAND | 2015-12-08 | 2015-12-14 | BUILD |  | FALSE |  | 2647848 | 6619093 | Matapuori Road Tutukaka |  |  | CELLSITE |  |  |  | ROAMING |  |  | 2015-08-03 | 2015-09-18 | 2015-09-16 | 2015-04-23 | 2015-04-23 | 2015-05-11 | 2015-05-22 | 2015-10-30 | 2015-10-29 |  |  | 2012-08-31
0 | NTH | 1184 | NTH-002-023 | One Tree Point | NTH-002-023-A | One Tree Point - VNZ RBI | Whangarei | 23 | TIER_4 | ACTIVE | COLO | DF | COLO |  | INLINE | COLO |  |  |  | -35.8406 | 174.4742 |  |  |  |  | Fibre Optic | NTH-002-011-A | FALSE | FALSE |  |  | FALSE |  | 2015-01-19 | 2015-02-18 | 2015-01-20 | 2015-02-18 | 2015-03-17 | 2015-03-26 | 2 | 2015-03-24 | 2015-04-09 | 2015-06-19 | 2015-05-11 | 2015-08-28 | 2015-07-28 |  | 2015-08-28 | 2015-08-25 | PERMITTED | 2015-04-20 | 2015-04-20 | 2015-05-22 | 2015-05-19 | 2 | 2015-05-29 | 2015-05-19 | 2015-05-11 | 2015-04-29 | 2015-06-12 | 2015-06-11 | 1 |  | 2015-06-12 | 2015-06-11 | [5 empty] | 2015-08-31 | 2015-08-25 | 2015-10-02 | 2015-09-30 |  |  |  | 2015-09-25 | 2015-09-22 | [7 empty] | 2015-11-11 | 2015-11-10 |  | 2015-10-30 |  | 2015-10-30 | 11/05/15 - VF Preliminary approval received 07/08/15 - Final approval received. Quote received, POR raised 24/08/15 - VF Approval to Build received 13/10/15 - Site integrated 4/11/15 - Fibre link has very high loss, and minimal margin. Chorus working on 10/11/15 - Link now has sufficient margin and Site is on air | VNZ | [9 empty] | 2015-10-16 | 2015-10-16 |  |  |  | 2015-09-25 | 2015-09-22 | BUILD |  | FALSE |  | 2643821 | 6594506 | RBI Colocation 78 Marsden Bay Drive One Tree Point Marsden Point |  |  | CELLSITE |  |  |  | ROAMING |  |  | 2015-04-24 | 2015-06-12 | 2015-06-17 | 2015-04-23 | 2015-04-23 | 2015-04-23 | 2015-04-23 | 2015-08-21 | 2015-08-19 |  |  | 2015-02-18
0 | NTH | 1185 | NTH-002-024 | Whangaruru | NTH-002-024-B | Whangaruru Co-Site | Whangarei | 23 | TIER_4 | ACTIVE | GF | DF | T2 20 RH |  | STACK_A | COSITE |  |  |  | -35.4429 | 174.318 |  | 2015-02-24 |  |  | Microwave | NTH-002-004-A | FALSE | FALSE |  |  | FALSE |  | 2015-04-24 | 2015-03-18 | 2015-05-04 | 2015-04-07 | 2015-05-22 | 2015-05-07 | 1 | 2015-06-05 | 2015-05-07 | 2015-06-26 | 2015-06-24 | 2015-07-21 | 2015-07-09 |  | 2015-10-23 | 2015-11-04 | DISCRETIONARY_FULL | 2016-05-02 |  | 2016-07-01 |  |  | 2016-07-01 |  | 2016-05-22 |  | 2016-07-08 |  |  |  | 2016-07-08 | [6 empty] | 2016-10-07 | [15 empty] | 2016-11-29 | [5 empty] | 02/10/15 - Site to HARDMATCH ONLY - not in build 23/06/15 - IWI consultation required - could lodge consent end July 09/07/15 - Lease in with 2D to sign. Co-site applications lodged 04/08/15 - VF cosite approval received 18/08/15 - On site IWI and HNZ consultation 02 Sept. Consent lodge delay till then 9/2/16 - planning for Iwi consultation 23 Feb | VNZ | [9 empty] | 2016-11-22 |  | 2015-03-25 | HIGH |  |  |  | ONHOLD |  | FALSE |  | 2630410 | 6638864 | Access off Peach Orchard Road Whangaruru |  |  | CELLSITE | WIPACTIVE |  |  | ROAMING |  |  |  | 2016-08-18 | [5 empty] | 2016-09-12 |  |  |  | 2015-04-07
0 | NTH | 1186 | NTH-003-001 |  |  |  | Kaipara |  | TIER_9
0 | NTH | 1187 | NTH-003-002 |  |  |  | Kaipara |  | TIER_9
0 | NTH | 1188 | NTH-003-003 |  |  |  | Kaipara |  | TIER_9
0 | NTH | 1189 | NTH-003-004 |  |  |  | Kaipara |  | TIER_9
0 | NTH | 1190 | NTH-003-005 |  |  |  | Kaipara |  | TIER_9
0 | NTH | 1191 | NTH-003-006 |  |  |  | Kaipara |  | TIER_9
0 | NTH | 1192 | NTH-003-007 | Mangawhai | NTH-003-007-B | Mangawhai Green Field | Kaipara | 23 | TIER_4 | ACTIVE | GF | DU | T2 20 RF |  | INLINE | COSITE | 18 | 18.5 |  | -36.0663 | 174.5644 |  | 2011-12-19 |  |  | Fibre Optic | AKL-005-088-A | FALSE | FALSE |  |  | FALSE |  | 2012-07-26 | 2012-07-26 | 2012-08-06 | 2012-08-07 | 2012-08-31 | 2012-09-11 | 2 | 2012-08-31 | 2012-09-24 | 2012-11-16 | 2012-11-27 | 2013-04-30 | 2013-06-21 |  | 2013-04-30 | 2013-06-21 | DISCRETIONARY_FULL | 2012-12-07 | 2012-11-30 | 2013-02-28 | 2012-12-18 | 2 | 2013-02-28 | 2013-01-17 | 2014-10-24 | 2014-10-21 | 2015-01-23 | 2015-02-10 | 2 |  | 2015-01-30 | 2015-05-19 | [5 empty] | 2015-05-07 | 2015-05-13 | 2015-07-31 | 2015-08-07 | 2015-07-13 | 2015-07-01 | 2015-07-30 | 2015-08-11 | 2015-08-13 | [6 empty] | 2015-08-12 | 2015-08-25 | 2015-08-19 |  |  |  |  | Huawei Build PO 35468 This site MUST be pegged before commencement. Fence is NOT the boundary. Also note the power route easement in the road. Need to do cosite with TNZ 11/05/15 - Design issue with GHD to resolve - site not flat as per CD's. Could be an issue getting rigs and trucks to site 26/05/15 - need break in weather to continue build as road is getting chopped up. Retaining wall and site prep done 07/07/15 - Ready to pour Cap and slab. Pwr and Fibre going in 04/08/15 - Pole in, fibre next week . Power next week. Integration12-14 Aug 13/08/15 - Site Integrated and Vol 4 submitted 19/08/15 - SOA |  | 2015-08-12 | [6 empty] | 2015-07-30 | 2015-07-30 | 2015-08-17 | 2015-08-13 |  |  | AUCKLAND_WHANGAREI | 2015-08-11 | 2015-08-13 | BUILD | 2015-07-13 | TRUE |  | 2651508 | 6569308 | Cove Road |  |  | CELLSITE |  |  |  | ROAMING |  | 2015-03-13 | 2015-02-04 | 2015-04-07 | 2015-04-07 | 2015-04-23 | 2015-04-23 | 2015-04-23 | 2015-04-23 | 2015-05-05 | 2015-05-05 |  |  | 2012-08-06
0 | NTH | 1193 | NTH-003-008 | Dargaville | NTH-003-008-A | Dargaville - VNZ CO LO | Kaipara | 23 | TIER_4 | ACTIVE | COLO | DU | COLO |  | INLINE | COLO | 20 | 20 |  | -35.9586 | 173.8632 |  | 2011-12-19 |  |  | Fibre Optic | NTH-002-011-A | FALSE | FALSE |  |  | FALSE |  | 2012-02-22 | 2012-02-22 | 2012-03-09 | 2012-03-09 | 2012-06-08 | 2012-05-31 | 2 | 2012-06-08 | 2015-06-09 | 2015-12-04 | 2015-11-10 | 2016-04-01 |  |  | 2016-04-01 |  | DISCRETIONARY_FULL | 2015-11-17 | 2015-11-18 | 2015-12-18 | 2015-11-30 | 1 | 2015-12-18 | 2015-12-01 | 2015-04-01 | 2015-02-25 | 2015-04-08 | 2015-04-21 | 1 |  | 2015-04-15 | 2015-04-21 | [5 empty] | 2016-04-18 | [6 empty] | 2016-03-25 | [8 empty] | 2016-06-03 | [5 empty] | 19/2/15 - Vodafone CoLo Preliminary approval granted. 13/10/15 - Head lease and VF signing end of next week - looking more positive 4/11/15 - Decision required on progressing forward. COW only mitigating 50%, has customer issues, and also neighbour not happy. 09/11/15 - Governance approved site to progress and build asap 17/11/15 - Committee meeting 15 Dec to do the VF lease sign approval, then our can be done. Consent lodge as soon as Ben supplies cheque 9/2/16 - Took till Xmas to get Council to approve officers to sign lease. Council suggested to Museum that they should go for more lease $$$. Under negotiation, which has caused dates to be pushed out | VNZ | [9 empty] | 2016-05-20 |  |  |  | NORTHLAND | 2016-03-18 |  | BUILD |  | FALSE |  | 2588472 | 6582200 | Mt Wesley Coast Road at the Dargaville Museum | Property is leasehold. Lessor Kaipara District Council. Lease has expired and to be settled between the parties. Late 2015 VDF lease agreement expiring - 13/05/2015 | RMA TBC - Permitted if complies with 18.5 - 05/04/2012 In Designation and notable landscape area. Existing structure is 25.7m and exceeds permitted height limit and requires consent as a discretionary activity. AT - 4.9.12. - 04/09/2012 | CELLSITE | WIPACTIVE |  |  | ROAMING |  |  | 2016-01-14 | 2016-01-25 | 2016-01-18 |  |  |  |  | 2016-03-11 |  |  |  | 2012-02-22
0 | NTH | 1194 | NTH-003-009 | Horokaka | NTH-003-009-A | Horokaka - KORDIA | Kaipara | 23 | TIER_4 | ACTIVE | COLO | DF | COLO |  | INLINE | COLO | 24 | 50 |  | -35.8701 | 174.1354 |  | 2011-12-19 |  |  | Microwave | NTH-002-013-A | FALSE | FALSE |  |  | FALSE |  | 2012-03-14 | 2015-02-18 | 2015-02-23 | 2012-03-14 | 2015-04-17 | 2015-04-07 | 1 | 2015-04-17 | 2015-04-07 | 2015-04-30 | 2015-05-04 | 2015-05-15 | 2015-05-04 |  | 2015-05-22 | 2015-05-20 | OPW | 2015-04-06 | 2015-03-20 | 2015-05-08 | 2015-04-11 | 1 | 2015-05-08 | 2015-04-11 | 2015-04-10 | 2015-04-05 | 2015-05-08 | 2015-05-04 | 1 |  | 2015-05-08 | 2015-05-04 | [5 empty] | 2015-07-20 | 2015-06-04 | 2015-10-30 | 2015-11-04 |  | 2015-11-10 | [10 empty] | 2015-12-14 | 2015-12-13 |  |  |  |  | PO 35727 issued to Huawei 20/05/15 01/09/15 - Linking to Marsden Point. Kordia still not started on site 24/09/15 - Girma raising BoQ for hi-wind speed capable MW dish for Horokaka 29/09/15 - Revised dates from Kordia. Expecting to integrate 22 Oct 4/11/15 - revised integration 12 Nov. Dates revised 19/11/15 - Kordia have revised dates due to limited resources 7/12/15 - Vol4 received and in process | KDA | [9 empty] | 2015-12-08 | 2015-12-07 |  |  | NORTHLAND |  |  | BUILD |  | FALSE |  | 2613165 | 6591709 | O`Carroll Road, Maungakaramea Northland |  |  | CELLSITE |  |  |  | ROAMING |  |  | 2015-04-24 | 2015-05-04 | 2015-04-30 |  |  |  |  | 2015-05-26 | 2015-05-20 |  |  | 2015-02-18
0 | NTH | 1195 | NTH-003-010 | Kaiwaka | NTH-003-010-A | Kaiwaka - VF Colo | Kaipara | 23 | TIER_4 | ACTIVE | COLO | DF | COLO |  | INLINE | COLO |  |  |  | -36.1884 | 174.4432 |  |  |  |  | Microwave | NTH-003-007-B | FALSE | FALSE |  |  | FALSE |  | 2015-04-13 | 2015-03-18 | 2015-04-20 | 2015-04-13 | 2015-05-22 | 2015-05-18 | 2 | 2015-06-05 | 2015-08-31 | 2015-06-26 | 2015-06-03 | 2015-09-25 | 2015-10-16 |  | 2015-10-02 | 2015-10-16 | DISCRETIONARY_RESTRICT | 2015-06-29 | 2015-06-29 | 2015-08-14 | 2015-07-16 | 1 | 2015-08-21 | 2015-07-16 | 2015-06-12 | 2015-06-16 | 2015-08-28 | 2015-08-11 | 2 |  | 2015-08-28 | 2015-09-08 | [5 empty] | 2015-11-02 | 2015-11-02 | 2015-12-04 | 2015-12-04 | [12 empty] | 2015-12-17 | 2015-12-10 |  |  |  |  | 03/06/15 - Colo Preliminary approval received 24/11/15 - Power to come. Build complete. Link to BER 30/11/15 - Link BER'ed. Power by 4 Dec, then integrate 7/12/15 - Faulty fibre to RRU (replaced), testing, Vol 4 before end of week | VNZ | [9 empty] | 2015-12-10 | 2015-12-04 | [5 empty] | BUILD |  | FALSE |  | 2640356 | 6555956 | Vodafone Colocation Giles Farm Pukenui Hill, SH1 Kaiwaka |  |  | CELLSITE |  |  |  | ROAMING |  |  | 2015-10-12 | 2015-08-07 | 2015-08-02 |  |  |  |  | 2015-10-02 | 2015-10-01 |  |  | 2015-04-13
0 | NTH | 1196 | NTH-003-011 | Ruawai | NTH-003-011-A | Ruawai | Kaipara | 25 | TIER_5 | ACTIVE | COLO | DF | COLO |  | STACK_A | COLO | 26 | 28 |  | -36.1369 | 174.1103 | 2015-10-22 | [5 empty] | FALSE | FALSE |  |  | FALSE |  | 2015-11-30 | 2015-11-30 | 2015-12-10 | 2015-12-08 | 2015-12-18 | 2016-01-21 | 1 | 2016-01-21 | 2016-01-21 | 2016-02-29 |  | 2016-03-31 |  |  | 2016-04-15 |  | CONTROLLED | 2016-03-09 |  | 2016-04-06 |  |  | 2016-04-06 |  | 2016-04-07 |  | 2016-04-15 | [10 empty] | 2016-04-25 |  | 2016-04-29 |  |  | 2016-04-27 |  | 2016-03-16 |  | 2016-03-23 |  | 2016-04-13 |  | 2016-04-18 |  |  | 2016-05-10 | [5 empty] | 22 Oct: RF search ring requested 12 Nov: SDP received 17 Nov: Co-lo & GF options available. Assess on caravan 2 Dec: Fibre pre qual ordered. 8 Dec: Antennas ordered 21 Jan: PD distributed. GF PD requested. 2 Feb: Co-lo lodged. Co-site application drafted. Structural assessment submitted to VF. 10 Feb: GF option PD's drafted. Awaiting comments | VNZ | [9 empty] | 2016-04-29 | [6 empty] | BUILD | 2016-04-18 | FALSE |  | 2610492 | 6562137 | Gallie Road Ruawai |  |  | CELLSITE |  |  |  | ROAMING |  |  |  | 2016-03-21 |  | 2015-12-02 | 2015-12-02 |  |  | 2016-04-11 |  |  |  | 2015-12-08
South Island | CAN | 624 | CAN-054-004 |  |  |  | Kaikoura District |  | TIER_9
South Island | CAN | 628 | CAN-058-005 |  |  |  | Hurunui District |  | TIER_9
South Island | CAN | 629 | CAN-058-006 |  |  |  | Hurunui District |  | TIER_9
South Island | CAN | 630 | CAN-058-007 |  |  |  | Hurunui District |  | TIER_9
South Island | CAN | 631 | CAN-058-008 |  |  |  | Hurunui District |  | TIER_9
South Island | CAN | 632 | CAN-058-009 | WALLACE PEAK_TELECOM |  |  | Hurunui District | 5 | TIER_9 | [22 empty] | FALSE | [60 empty] | Transmission Hub | [14 empty] | KAIKOURA
South Island | CAN | 634 | CAN-058-012 | Mt Grey BCL |  |  | Hurunui District | 5 | TIER_3 | [22 empty] | FALSE | [60 empty] | Transmission site only | [14 empty] | TRANSMISSION_ONLY
South Island | CAN | 635 | CAN-058-013 | Beltana Kordia |  |  | Hurunui District | 5 | TIER_9 | [22 empty] | FALSE | [60 empty] | Transmission site only | [14 empty] | KAIKOURA
South Island | CAN | 636 | CAN-058-014 |  |  |  | Hurunui District |  | TIER_9
South Island | CAN | 639 | CAN-059-002 | Rangiora West | CAN-059-002-A | Oxford Road | Waimakariri | 11 | TIER_3 | ACTIVE | RSR | DU | P4L |  | INLINE |  |  |  | 1 | -43.3062 | 172.5742 |  | 2012-05-30 |  |  |  |  | FALSE | FALSE |  |  | FALSE |  | 2012-07-04 | 2012-07-04 | 2012-07-11 | 2012-07-12 | 2012-07-20 | 2012-08-14 | 1 | 2012-08-10 | 2012-08-14 | 2012-08-24 | 2012-08-08 | 2012-09-10 | 2012-09-13 | 1 |  | 2012-09-13 | PERMITTED | 2012-09-12 | 2012-09-18 | 2012-10-19 | 2012-10-17 | 1 | [37 empty] | 02/07 Caravan on schedule. LOS to be done this wk. 23/7 Currend Cadidate is opposite Oakwood Dr. Permitted Height 13.9 to be chkd with RF if OK to continue. 30/7 Pole 15.5 permitted. Fibre solution. Proceed. Telco to be issued. Drawing to be finalised with Height Site. 27/8 Telco notice lodged due out 10/9. 10/09 Lease terms agreed, RMA to be lodged this week. 17/9 Telco Notice processed. WO2 to be issued this week. RMA to be lodged this week. Tx fibre request lodged, awaiting response. MW is a back up otpion as there is L.O.S. 01/10 Waiting on RMA, construction drawings end of week. 15/10 Hardmatch only. | [12 empty] | 2012-08-15 | MEDIUM | TIER_1_INFILL |  |  | HARDMATCH |  | TRUE |  | 2475465 | 5766713 |  |  | NES applies - 18/09/2012 | CELLSITE | WIPHOLDING
South Island | CAN | 641 | CAN-059-004 | Springbank |  |  | Waimakariri |  | TIER_9 | [22 empty] | FALSE | [60 empty] | Aim to provide GSM900 voice and U2100 services to indoor levels. Springbank, West Eyreton and the surrounding area. A 35 Meter greenfield site just South of Springbank will provide suitable ground elevation and provide coverage to both Towns | [14 empty] | CHRISTCHURCH_OUTER
South Island | CAN | 646 | CAN-059-009 | Pegasus | CAN-059-009-A | Commercial Car Park | Waimakariri | 11 | TIER_3 | ACTIVE | GF | DU |  |  |  | STANDALONE |  |  | 1 | -43.311 | 172.695 |  | 2012-05-30 |  |  |  |  | FALSE | FALSE |  |  | FALSE |  | 2012-08-23 | 2012-08-23 | 2012-10-01 | 2012-10-01 | 2012-10-05 | 2012-11-20 | 1 | 2012-11-26 | 2012-11-20 | 2012-10-17 | 2012-11-15 | 2013-05-15 |  |  |  |  | DISCRETIONARY_FULL | 2013-01-25 |  | 2013-06-14 | [39 empty] | 02/07 PR adv 1st opt by water tower. 2nd opt near the centre/existing cafe. Possible visit on 4/7. 23/7 Tx to look at fibre options with Telstra. Site visit completed Thur 19/7. Pump Station is new option, to be confirmed with the developer. Expected limit is 15m from planning. Acquisition Cafe is an option to be discussed with developer. 30/7 Orion substation site options identified. Telstra site RF preference. 15M height expected maximum. SA discussing options with developer. 6/8 Pete waiting feedback from developers agent on site option. 13/8 Still waiting for feedback on proposed options. 27/8 Tx options to be confirmed, LOS this week. Telstra Clear fibre option TBC. Proposal plans to be created and sent to developer for carpark option. Robert to confirm height for Antennae. 03/09 Another caravan to be scheduled for new candidate option, Telstra Hut Carpark this Friday. 2 options to be put forward. 17/9 2nd Caravan completed beside Telstra hut. 2 options being proposed. Tx request lodged. 01/10 Jaco closing Telstra for Tx Pricing. PDs being processed. 15/10 Hardmatch only. 24/10 Fibre feasability completed, possible but costly opex 2.5k p mth. Waiting on lease drawings from Richell. | [12 empty] | 2012-09-17 | MEDIUM | TIER_1_INFILL |  |  | HARDMATCH |  | TRUE |  | 2485266 | 5766227
South Island | CAN | 647 | CAN-059-010 | RBI - Ohoka |  |  | Waimakariri |  | RBI | [22 empty] | FALSE
South Island | CAN | 648 | CAN-059-011 | RBI - Swannanoa |  |  | Waimakariri |  | RBI | [22 empty] | FALSE
South Island | CAN | 649 | CAN-059-012 | RBI - Swannanoa Central |  |  | Waimakariri |  | RBI | [22 empty] | FALSE
South Island | CAN | 653 | CAN-059-016 | Daiken Pico | CAN-059-016-A | Daiken | Waimakariri |  | 2015P | ACTIVE | IB | LS | NOPOLE |  |  |  | 4 | 12 |  | -43.2676 | 172.6225 | [66 empty] | 2015-12-16 | [26 empty] | 2479364 | 5771023 | Upper Sefton Road Ashley Rangiora 7477 |  |  | CELLSITE
South Island | CAN | 654 | CAN-059-017 | Kaiapoi North | CAN-059-017-A | Active Candidate for forecasting | Waimakariri | 23 | TIER_5 | ACTIVE | [17 empty] | FALSE | FALSE |  |  | FALSE |  | 2016-03-31 | [58 empty] | RF Engineer - Cary Grice | [19 empty] | FALSE | [10 empty] | CAPACITY
South Island | CAN | 655 | CAN-062-001 | West Melton |  |  | Selwyn District | 8 | TIER_3 | [22 empty] | FALSE | [60 empty] | Aim to provide GSM900 voice and U2100 services to indoor levels. West Melton. GF. Option A: GF option. Junction of Ross Road and Old West Road, Just south of Canterbury Aero Club. Grid: 2459707 5745522 Option B: GF Option similar location - plenty of options around Grid: 2460079 5745399 | [14 empty] | RBI
South Island | CAN | 664 | CAN-062-010 | Lincoln |  |  | Selwyn District |  | TIER_9 | [22 empty] | FALSE | [60 empty] | Aim to provide GSM900 voice and U2100 services to indoor levels. Lincoln. Option A: Colo on VNZ 20m Pole with Spider Arms. Plenty of room Grid: 2466744 5728480 Option B: GF Pole in surrounding fields - plenty of options Grid: 2466781 5728452 Option C: GF option in surrounding fields. Grid: 2466781 5728452 | [14 empty] | CHRISTCHURCH_OUTER
South Island | CAN | 670 | CAN-062-016 | Halswell West |  |  | Selwyn District |  | TIER_9 | [22 empty] | FALSE
South Island | CAN | 672 | CAN-062-018 | Designline Temporary Repeater |  |  | Selwyn District |  | TIER_6
South Island | CAN | 674 | CAN-062-020 | Southbridge | CAN-062-020-A | Southbridge RBI | Selwyn District | 21 | TIER_9 | ACTIVE | RBI |  |  |  |  | COLO |  |  |  | -43.8217 | 172.2416 | [6 empty] | FALSE | FALSE |  |  | FALSE | [82 empty] | 2449002 | 5709253 | TBC | [6 empty] | ROAMING
South Island | CAN | 676 | CAN-063-002 | Methven |  |  | Ashburton District |  | TIER_9
South Island | CAN | 683 | CAN-064-001 |  |  |  | Timaru |  | TIER_9
South Island | CAN | 694 | CAN-064-012 | Highfield Old |  |  | Timaru |  | TIER_9 | [22 empty] | FALSE | [60 empty] | Highfield. Tricky location as area is heavily Residential and very little industrial. Country Club option would be fine BUT location is in a valley with residential on the higher ridges to North and especially south. A stealth option MIGHT be required. Plenty of locations we could go at . Car Park, on the Golf Course itself, adjacent to the Bowling Club Option A: GF 25m Pole at Timaru Town & Country Club, Bowls and Golf Course in the Valley. Grid: 2368592 5645422 Option B: LP Replacement corner of Seddon St & Orbell St. Small Grass reserve/path connecting to Douglas St. Location overlooks the Country Club option. Grid: 2368236 5645300 Option C: GF at St Pauls Presbyterian Church, Seddon St. Option to place a pole in yard at back of Church OR an expensive stealth option to Spire Grid: 2068229 5645189
South Island | CAN | 695 | CAN-064-013 | Parkside |  |  | Timaru |  | TIER_9 | [22 empty] | FALSE
South Island | CAN | 697 | CAN-064-015 | Telecom Temuka |  |  | Timaru | 5 | TIER_9 | [22 empty] | FALSE | [60 empty] | Transmission site only
South Island | CAN | 698 | CAN-064-016 | TNZ Exchange TX Timaru | CAN-064-016-A | Timaru TX Only site | Timaru | 4 | TIER_3 | ACTIVE | COLO | TX |  |  |  | COLO |  |  |  | -44.397 | 171.2519 | [6 empty] | FALSE | FALSE |  |  | FALSE |  | 2012-07-11 | 2012-07-19 | 2012-07-11 | 2012-07-19 | 2012-07-11 | 2012-09-21 | 1 |  | 2012-09-21 |  |  |  | 2012-08-17 |  |  | 2013-03-25 |  | 2012-09-03 | 2012-10-30 | 2012-08-23 | 2012-10-30 | 1 |  | 2012-09-07 | [13 empty] | 2012-09-10 | 2012-09-10 | 2012-10-15 | 2012-10-15 | 2012-10-15 | 2012-10-17 | 2012-10-17 | [8 empty] | 2012-10-18 |  | 2012-11-23 | 2012-12-01 | 2012-10-31 | 2013-08-13 | 2013-07-10 | TX to do Chorus application for CX600 exchange. 5/6 Chorus - TX to push application quickly. 11/06 TX to push for quote and approval by end of June. Must do WO2 in July. 2/7 Chorus quote delayed, TX to chase again. 18/7: QUOTE RECEIVED, S/Base dates entered accordingly. 23/7 draft Wo2. 10/09 CAB in Timaru. | TNZ | 2012-10-18 | [9 empty] | 2012-10-26 |  |  | TRANSMISSION_ONLY | 2012-09-23 | 2012-10-30 | BUILD | 2012-10-10 | FALSE |  | 2370734 | 5644155 | Chorus Exchange 22 Sophia Street Timaru |  |  | TXSITE | [15 empty] | 2012-10-25 | 2012-10-26 | 2012-07-19
South Island | CAN | 701 | CAN-065-002 |  |  |  | Mackenzie District |  | TIER_9
South Island | CAN | 702 | CAN-065-003 |  |  |  | Mackenzie District |  | TIER_9
South Island | CAN | 703 | CAN-065-004 |  |  |  | Mackenzie District |  | TIER_9
South Island | CAN | 704 | CAN-065-005 |  |  |  | Mackenzie District |  | TIER_9
South Island | CAN | 709 | CAN-066-001 |  |  |  | Waimate District |  | TIER_9
South Island | CAN | 710 | CAN-066-002 |  |  |  | Waimate District |  | TIER_9
South Island | CAN | 712 | CAN-066-004 | Waimate Chorus Exchange Tx col |  |  | Waimate District | 21 | TIER_9 | [22 empty] | FALSE
South Island | CAN | 714 | CAN-066-006 | Kurow Tx Only Site |  |  | Waimate District | 21 | TIER_9 | [22 empty] | FALSE
South Island | CAN | 716 | CAN-068-001 |  |  |  | Waitaki District |  | TIER_9
South Island | CAN | 717 | CAN-068-002 |  |  |  | Waitaki District |  | TIER_9
South Island | CAN | 720 | CAN-068-005 |  |  |  | Waitaki District |  | TIER_9
South Island | CAN | 721 | CAN-068-006 |  |  |  | Waitaki District |  | TIER_9
South Island | CAN | 722 | CAN-068-007 |  |  |  | Waitaki District |  | TIER_9
South Island | CAN | 723 | CAN-068-008 |  |  |  | Waitaki District |  | TIER_9
South Island | CAN | 725 | CAN-068-010 | Oamaru North |  |  | Waitaki District |  | 2015
South Island | MBN | 982 | MBN-051-001 |  |  |  | Tasman District |  | TIER_9
South Island | MBN | 983 | MBN-051-002 |  |  |  | Tasman District |  | TIER_9
South Island | MBN | 986 | MBN-051-005 |  |  |  | Tasman District |  | TIER_9
South Island | MBN | 987 | MBN-051-006 |  |  |  | Tasman District |  | TIER_9
South Island | MBN | 993 | MBN-051-013 | Brightwater |  |  | Tasman District |  | TIER_9
South Island | MBN | 994 | MBN-051-014 | Richmond East |  |  | Tasman District |  | TIER_9
South Island | MBN | 995 | MBN-051-015 | RBI - Motueka Township |  |  | Tasman District |  | RBI | [22 empty] | FALSE
South Island | MBN | 999 | MBN-051-019 | Tasman RBI |  |  | Tasman District |  | TIER_9
South Island | MBN | 1000 | MBN-051-020 | Mapua West RBI |  |  | Tasman District |  | TIER_9
South Island | MBN | 1001 | MBN-051-021 | Takaka |  |  | Tasman District |  | TIER_9 | [22 empty] | FALSE
South Island | MBN | 1002 | MBN-051-022 | Collingwood exchange |  |  | Tasman District | 21 | TIER_9 | [22 empty] | FALSE
South Island | MBN | 1004 | MBN-051-024 | kaiteriteri South |  |  | Tasman District | 7 | TIER_9 | [22 empty] | FALSE
South Island | MBN | 1008 | MBN-052-004 |  |  |  | Nelson |  | TIER_9
South Island | MBN | 1009 | MBN-052-005 |  |  |  | Nelson |  | TIER_9
South Island | MBN | 1015 | MBN-052-011 | The Brook |  |  | Nelson |  | TIER_9 | [22 empty] | FALSE
South Island | MBN | 1017 | MBN-052-013 | Dodson Valley |  |  | Nelson | 7 | TIER_9 | [22 empty] | FALSE | [60 empty] | Coverage Objective: Atawhai Township and SH6 north and south to Nelson. Good location for RF, clear LOS up the valley. 2G and 3G.
South Island | MBN | 1018 | MBN-052-014 | Brooklands |  |  | Nelson | 7 | TIER_9 | [22 empty] | FALSE | [60 empty] | This is predominately a Tx linking site, however will give useful coverage into Bay View
South Island | MBN | 1020 | MBN-052-016 | Wakapuaka | MBN-052-016-C | Adj Sewerage Fence | Nelson | 7 | TIER_3 | ACTIVE | GF | DU | P2 |  | STACK_A | COSITE | 20 | 20 | 1 | -41.203 | 173.3244 |  |  |  |  | Microwave | MBN-052-010-A | FALSE | FALSE |  |  | FALSE |  | 2012-11-16 | 2012-11-15 | 2012-11-23 | 2012-11-23 | 2012-12-19 | 2012-12-20 | 1 | 2012-12-19 | 2012-12-20 | 2013-06-07 |  | 2013-07-19 |  |  | 2013-07-19 |  | CONTROLLED | 2013-02-08 | 2013-02-07 | 2013-07-19 |  | 1 | 2013-07-19 | [36 empty] | 9/5/13: • Waiting for review by Site Acqu (Jason B.) • Council is landowner and lease requires public notification. 2 degrees’ decision on this is dependent on review. • Refer 3 emails, including one titled “…Boulder Bank Drive”. | [12 empty] | 2013-01-22 | LOW | NELSON_OUTER |  |  | HARDMATCH |  | FALSE |  | 2537194 | 6000365 | Adjacent Water Treatment Plant Boulder Bank Drive Wakapuaka, Nelson |  | Earthworks and Arch Overlay - 22/01/2013 | [18 empty] | 2012-11-22
South Island | MBN | 1022 | MBN-052-018 | Nelson Haven |  |  | Nelson |  | TIER_9 | [22 empty] | FALSE
South Island | MBN | 1023 | MBN-053-001 |  |  |  | Marlborough District |  | TIER_9
South Island | MBN | 1024 | MBN-053-002 |  |  |  | Marlborough District |  | TIER_9
South Island | MBN | 1025 | MBN-053-003 |  |  |  | Marlborough District |  | TIER_9
South Island | MBN | 1028 | MBN-053-006 | Tuamarina |  |  | Marlborough District | 7 | TIER_3 | [22 empty] | FALSE | [60 empty] | Site to cover SH1 between Picton and Blenheim. | [14 empty] | BLENHEIM
South Island | MBN | 1031 | MBN-053-009 |  |  |  | Marlborough District |  | TIER_9
South Island | MBN | 1032 | MBN-053-010 |  |  |  | Marlborough District |  | TIER_9
South Island | MBN | 1033 | MBN-053-011 |  |  |  | Marlborough District |  | TIER_9
South Island | MBN | 1035 | MBN-053-013 | Queen Charlotte Sounds |  |  | Marlborough District | 7 | TIER_3 | [22 empty] | FALSE | [60 empty] | Coverage Objective ------------------------` Cook Stait Ferry Coverage | [14 empty] | BLENHEIM
South Island | MBN | 1036 | MBN-053-014 | Woodbourne | MBN-053-014-G | Woodbourne LPR3 | Marlborough District | 7 | TIER_3 | ACTIVE | RSR | DU | P4E |  | STACK_A | STANDALONE | 17 | 18 | 1 | -41.5126 | 173.8689 |  | 2012-01-26 |  |  | Microwave | MBN-053-012-D | FALSE | FALSE |  |  | FALSE |  | 2012-09-10 | 2012-09-10 | 2012-11-09 | 2012-11-08 | 2012-11-30 | 2012-11-30 | 1 | 2012-11-30 | 2012-11-30 | 2013-05-31 |  | 2013-06-07 |  |  | 2013-06-07 |  | PERMITTED | 2012-12-21 | 2012-12-17 | 2013-02-15 | 2013-01-18 | 1 | 2013-02-15 | 2013-01-18 | [35 empty] | 9/5/13: • Lease is with NZDF for review. They are known for their lack of response! • Bryan is chasing them regularly. | [12 empty] | 2012-12-17 | MEDIUM | BLENHEIM |  |  | HARDMATCH |  | TRUE |  | 2582517 | 5965672 | Tancred Crescent Woodbourne Blenheim
South Island | MBN | 1038 | MBN-053-016 | Renwick |  |  | Marlborough District |  | TIER_9 | [22 empty] | FALSE
South Island | OTG | 1197 | OTG-069-001 |  |  |  | Central Otago |  | TIER_9
South Island | OTG | 1198 | OTG-069-002 |  |  |  | Central Otago |  | TIER_9
South Island | OTG | 1201 | OTG-069-005 |  |  |  | Central Otago |  | TIER_9
South Island | OTG | 1202 | OTG-069-006 | Cromwell | OTG-069-006-C | Cornish Point | Central Otago | 4 | TIER_3 | ACTIVE | GF | DU |  |  | INLINE | COSITE | 15 | 15 |  | -45.0597 | 169.205 | [6 empty] | FALSE | FALSE |  |  | FALSE |  | 2012-06-20 | 2012-06-20 | 2012-06-29 | 2012-06-29 | 2012-08-08 | 2012-08-24 | 1 | 2012-08-28 | 2012-08-24 | 2012-08-01 | 2012-07-06 | 2012-11-30 | 2012-11-27 | 1 |  | 2012-11-27 | PERMITTED | 2012-10-19 | 2012-11-29 | 2012-12-29 | 2012-12-10 | 1 | 2012-10-12 | [36 empty] | Site has room to construct monpole and accomodate COW at the same time if required. Current COW location agreement (inside Telecom lease are) expires Jan 2013. We may have to relocate the COW to new lease area. | [12 empty] | 2012-09-12 | LOW | OTAGO |  |  | HARDMATCH |  | TRUE |  | 2211146 | 5565153 | Off Cornish Point Road Cromwell |  |  | CELLSITE | WIPHOLDING
South Island | OTG | 1203 | OTG-069-007 | Cromwell Exchange Tx only |  |  | Central Otago | 4 | TIER_3 | [22 empty] | FALSE | [60 empty] | Tx only site | [14 empty] | TRANSMISSION_ONLY
South Island | OTG | 1205 | OTG-069-009 | Obelisk (BCL) |  |  | Central Otago |  | TIER_9 | [22 empty] | FALSE
South Island | OTG | 1206 | OTG-069-010 | RBI - Naseby |  |  | Central Otago |  | RBI | [22 empty] | FALSE
South Island | OTG | 1213 | OTG-070-006 | Shotover |  |  | Queenstown |  | TIER_9
South Island | OTG | 1214 | OTG-070-007 | Arrowtown Basin |  |  | Queenstown |  | TIER_9 | [83 empty] | perhaps future highway linking site between QNT and Cromwell
South Island | OTG | 1215 | OTG-070-008 | Kadrona Ski Fields |  |  | Queenstown |  | TIER_9
South Island | OTG | 1217 | OTG-070-010 | Cardrona Valley |  |  | Queenstown | 4 | TIER_3 | [22 empty] | FALSE | [60 empty] | Marketing reqested this Nominal - exact reason not known to RF | [14 empty] | OTAGO
South Island | OTG | 1219 | OTG-070-012 | Wanaka Central | OTG-070-012-A | Council Car Park | Queenstown | 4 | TIER_3 | ACTIVE | GF | DU | P2 |  | INLINE | COSITE | 13 | 13.5 |  | -44.695 | 169.1383 | [6 empty] | FALSE | FALSE |  |  | FALSE |  | 2012-04-12 | 2012-04-12 | 2012-05-11 | 2012-05-09 | 2012-05-30 | 2012-05-18 | 4 | 2012-05-30 | 2012-12-03 |  | 2012-04-16 | 2012-11-06 | 2012-11-07 |  |  | 2012-11-07 | DISCRETIONARY_FULL | 2012-10-22 | 2012-10-26 | 2012-12-27 | 2012-12-21 | 4 | [37 empty] | 03/04 high SSLU. Requires extra battery cabinet. Next comittee meeting 16/8 but lease can progress some before hand. 29/05 not dependent on 070-011 for tx. Requires boundary and GPR survey. 02/07 Lease terms unacceptable "Termination on Development". Need lease before RC lodge. 16/7 Next Council meeting 2/10. 27/8 Monitor council proceedings. | [13 empty] | MEDIUM | OTAGO |  |  | HARDMATCH |  | TRUE |  | 2204006 | 5605389 | Car Park Brownstone St Wanaka
South Island | OTG | 1220 | OTG-070-013 | Kadrona |  |  | Queenstown |  | TIER_9
South Island | OTG | 1225 | OTG-071-003 | Brighton |  |  | Dunedin | 11 | TIER_3 | [22 empty] | FALSE | [60 empty] | Coverage to the township of Brighton and the surrounding area. Consider co-location with Telecom. Consider a new structure. | [14 empty] | TIER_1_INFILL
South Island | OTG | 1234 | OTG-071-012 | Signal Hill |  |  | Dunedin |  | TIER_9 | [22 empty] | FALSE | [60 empty] | Coverage to the Area around Signal Hill. Coverage to Normanby, Upper Junction and Otago Harbour. Consider co-location will Telecom.
South Island | OTG | 1238 | OTG-071-016 | Waitati |  |  | Dunedin |  | TIER_9 | [22 empty] | FALSE | [60 empty] | Coverage to Waitati & surrounding area. Consider Telecom co-location. Consider 20m new pole.
South Island | OTG | 1240 | OTG-071-018 | Highcliff Rd |  |  | Dunedin |  | TIER_9 | [22 empty] | FALSE | [60 empty] | Coverage to the SW , West & East of this site. Consider water tank on the hilltop as the nominal location. New structure required.
South Island | OTG | 1249 | OTG-071-027 |  |  |  | Dunedin |  | TIER_9
South Island | OTG | 1250 | OTG-071-028 |  |  |  | Dunedin |  | TIER_9 | [22 empty] | FALSE
South Island | OTG | 1252 | OTG-071-030 |  |  |  | Dunedin |  | TIER_9
South Island | OTG | 1253 | OTG-071-031 |  |  |  | Dunedin |  | TIER_9
South Island | OTG | 1254 | OTG-071-032 |  |  |  | Dunedin |  | TIER_9 | [22 empty] | FALSE
South Island | OTG | 1255 | OTG-071-033 |  |  |  | Dunedin |  | TIER_9 | [22 empty] | FALSE
South Island | OTG | 1256 | OTG-071-034 | Waikouaiti |  |  | Dunedin |  | TIER_9 | [22 empty] | FALSE
South Island | OTG | 1257 | OTG-071-035 |  |  |  | Dunedin |  | TIER_9 | [22 empty] | FALSE
South Island | OTG | 1258 | OTG-071-036 |  |  |  | Dunedin |  | TIER_9 | [22 empty] | FALSE
South Island | OTG | 1259 | OTG-071-037 |  |  |  | Dunedin |  | TIER_9 | [22 empty] | FALSE
South Island | OTG | 1260 | OTG-071-038 |  |  |  | Dunedin |  | TIER_9 | [22 empty] | FALSE
South Island | OTG | 1261 | OTG-071-039 |  |  |  | Dunedin |  | TIER_9 | [22 empty] | FALSE
South Island | OTG | 1262 | OTG-071-040 |  |  |  | Dunedin |  | TIER_9 | [22 empty] | FALSE
South Island | OTG | 1263 | OTG-071-041 |  |  |  | Dunedin |  | TIER_9 | [22 empty] | FALSE
South Island | OTG | 1267 | OTG-071-046 | Forsyth Barr Stadium | OTG-071-046-B | Stadium RSR | Dunedin | 4 | TIER_3 | ACTIVE | RSR | DU | P4B |  | INLINE | STANDALONE | 9 | 9 | 1 | -45.8682 | 170.5241 | [6 empty] | FALSE | FALSE |  |  | FALSE |  | 2012-06-19 | 2012-06-19 | 2012-06-28 | 2012-06-28 | 2012-07-12 | 2012-08-09 | 1 | 2012-08-07 | 2012-08-09 | 2012-08-15 | 2012-08-08 | 2012-09-28 | 2012-09-25 |  | 2013-05-30 |  | PERMITTED | 2012-09-12 | 2012-09-13 | 2012-12-27 | 2012-12-21 | 1 | [37 empty] | Will need council arborist to determine if site can be built in close proximity to park reserve trees. Council will need to be convinced there is enough space left on the foot path. 16/7 PD required, prior to Council Arborist input. Boundary survey required. 13/8 Drawings with council roading & arborist. 27/8 Speak to DCC for right approach to hardmatch. 3/9 George to approve extended slit trench. SITE on HOLD requires boundary survey to hard match |  | 2012-12-19 | 2012-09-04 | 2012-09-04 | 2012-11-02 |  | 2012-11-02 |  | 2012-12-18 | [5 empty] | TIER_1_INFILL |  |  | HARDMATCH |  | TRUE |  | 2317626 | 5479264 | Union St Dunedin |  | Permitted if <12m - 27/06/2012 | [16 empty] | 2012-12-20
South Island | OTG | 1269 | OTG-071-048 | University campus | OTG-071-048-B | Poly Tech - Block H | Dunedin | 4 | TIER_3 | ACTIVE | RT | DF |  |  |  | COSITE | 45 | 45 | 1 | -45.8664 | 170.5182 |  |  |  |  | Microwave | OTG-071-010-A | FALSE | FALSE |  |  | FALSE |  | 2012-08-30 | 2012-08-30 | 2012-10-19 | 2012-11-09 | 2013-02-27 | 2013-03-11 | 2 | 2013-03-11 | 2013-05-20 | 2012-12-19 | 2012-11-22 | 2013-06-14 | 2013-08-02 | 2 | 2013-06-14 | 2013-08-02 | DISCRETIONARY_FULL | 2013-05-10 | 2013-05-13 | 2013-07-11 | 2013-06-20 | 1 | 2013-07-11 | 2013-06-20 | [35 empty] | Good roof top option, some structural input required and finalising design for Poly. Proposal sent to Poly for comment prior to WO1 and PD. Jan 2013 Re-design required placing panels on parapet walls, vists scheduled 30 Jan, PD lease and RMA all delayed due to re-design. | [12 empty] | 2013-05-13 | LOW | TIER_1_INFILL |  |  | HARDMATCH |  | TRUE |  | 2317162 | 5479449 | Otago Polytechnic Block H Forth Street Dunedin |  |  | CELLSITE | WIPHOLDING
South Island | OTG | 1271 | OTG-072-001 |  |  |  | Clutha |  | TIER_9
South Island | OTG | 1274 | OTG-072-004 |  |  |  | Clutha |  | TIER_9
South Island | OTG | 1275 | OTG-072-005 |  |  |  | Clutha |  | TIER_9
South Island | OTG | 1276 | OTG-072-006 | RBI - Owaka |  |  | Clutha |  | RBI | [22 empty] | FALSE
South Island | OTG | 1277 | OTG-072-007 | Kaltangata |  |  | Clutha |  | RBI | [83 empty] | This is RBI site - expression of interest only
South Island | STH | 1279 | STH-073-002 |  |  |  | Southland District |  | TIER_9
South Island | STH | 1280 | STH-073-003 |  |  |  | Southland District |  | TIER_9
South Island | STH | 1281 | STH-073-004 |  |  |  | Southland District |  | TIER_9
South Island | STH | 1282 | STH-073-005 |  |  |  | Southland District |  | TIER_9
South Island | STH | 1283 | STH-073-006 |  |  |  | Southland District |  | TIER_9
South Island | STH | 1284 | STH-073-007 |  |  |  | Southland District |  | TIER_9
South Island | STH | 1285 | STH-073-008 |  |  |  | Southland District |  | TIER_9
South Island | STH | 1286 | STH-073-009 |  |  |  | Southland District |  | TIER_9
South Island | STH | 1288 | STH-073-011 |  |  |  | Southland District |  | TIER_9
South Island | STH | 1289 | STH-073-012 |  |  |  | Southland District |  | TIER_9
South Island | STH | 1290 | STH-073-013 |  |  |  | Southland District |  | TIER_9
South Island | STH | 1291 | STH-073-014 |  |  |  | Southland District |  | TIER_9
South Island | STH | 1292 | STH-073-015 | RBI - Centre Hill |  |  | Southland District |  | RBI | [22 empty] | FALSE
South Island | STH | 1293 | STH-073-016 | RBI - Mt Prospect |  |  | Southland District |  | RBI | [22 empty] | FALSE
0 | SYD | 1321 | SYD-202-001 | Equinix |  |  | Sydney, Australia |  | TIER_3
0 | TNK | 1322 | TNK-033-001 | New Plymouth East | TNK-033-001-B | 316 Devon Street East | New Plymouth | 6 | TIER_3 | ACTIVE | GF | DU | T2 20 UF |  | STACK_A | STANDALONE |  |  | 2 | -39.055 | 174.0849 |  | 2011-12-20 |  | 2010-02-12 | Leased Line | TNK-033-004-A | TRUE | TRUE |  |  | TRUE |  | 2012-05-01 | 2012-05-01 | 2012-05-08 | 2012-05-15 | 2012-06-15 | 2012-06-22 | 1 | 2012-06-15 | 2012-06-22 | 2012-07-03 | 2012-07-02 | 2012-07-20 | 2012-07-02 | 1 | 2012-07-20 | 2012-07-27 | PERMITTED | 2012-06-20 | 2012-06-25 | 2012-07-20 | 2012-07-12 | 1 | 2012-07-25 | 2012-07-12 |  |  | 2012-09-07 | 2012-09-25 | 1 |  | 2012-09-07 | 2012-09-25 | 2012-08-31 |  |  |  |  | 2012-08-17 | 2012-08-15 | 2012-09-07 | 2012-09-14 | 2012-09-04 | 2012-09-15 | 2012-09-17 | [8 empty] | 2012-10-12 | 2012-11-15 | 2012-11-14 | 2012-11-28 | 2012-11-09 | 2013-05-26 | 2013-05-05 |  |  | 2012-10-09 | 2012-08-14 | 2012-08-14 | 2012-08-27 | 2012-08-31 | 2012-08-31 | 2012-08-31 | 2012-09-14 | 2012-10-11 | 2012-10-18 | 2012-10-15 | 2012-04-19 | MEDIUM | NEW_PLYMOUTH | 2012-10-12 | 2012-10-12 | BUILD | 2012-09-04 | FALSE |  | 2603962 | 6238314 | 316 Devon Street East |  |  | CELLSITE | [15 empty] | 2012-10-24 | 2012-10-26 | 2012-05-15
0 | TNK | 1323 | TNK-033-002 | New Plymouth | TNK-033-002-C | Transfield House | New Plymouth | 6 | TIER_3 | ACTIVE | RT | DU | RT |  | STACK_A | COSITE |  |  | 4 | -39.0561 | 174.0752 |  | 2011-12-20 |  | 2010-02-12 | Leased Line | TNK-033-004-A | TRUE | TRUE |  |  | FALSE |  | 2012-05-01 | 2012-05-01 | 2012-05-08 | 2012-05-15 | 2012-06-15 | 2012-06-13 | 2 | 2012-06-15 | 2013-06-25 | 2012-07-03 | 2012-06-29 | 2012-08-03 | 2012-07-30 |  | 2012-10-28 | 2012-11-12 | DISCRETIONARY_FULL | 2012-06-20 | 2012-06-25 | 2012-07-20 | 2012-08-16 | 1 | 2012-07-25 | 2012-08-16 |  |  | 2012-10-17 | 2012-10-24 | 1 |  | 2012-10-17 | 2012-10-24 | 2012-09-24 |  |  |  |  | 2012-09-10 | 2012-09-10 | 2012-10-24 | 2012-10-24 | 2012-09-28 | 2012-10-20 | 2012-10-23 | [8 empty] | 2012-10-23 | 2012-11-15 | 2012-11-14 | 2012-11-13 | 2012-11-13 | 2013-07-15 | 2013-06-19 |  |  | 2012-10-16 |  |  | 2012-09-21 | 2012-09-21 | 2012-09-24 | 2012-09-24 | 2012-10-12 |  | 2012-10-24 | 2012-10-24 | 2012-04-20 | LOW | NEW_PLYMOUTH | 2012-10-18 | 2012-10-24 | BUILD | 2012-10-03 | FALSE |  | 2603118 | 6238200 | Transfield House 21-35 Gill Street New Plymouth |  |  | CELLSITE | [15 empty] | 2012-10-29 | 2012-11-05 | 2012-05-15
0 | TNK | 1324 | TNK-033-003 | Fitzroy New Plymouth | TNK-033-003-A | Fitzroy New Plymouth,489a Devon Street East | New Plymouth | 6 | TIER_3 | ACTIVE | GF | DU | P2 |  | STACK_A | STANDALONE |  |  | 1 | -39.05 | 174.097 |  | 2011-12-20 |  | 2010-02-12 | Leased Line | TNK-033-004-A | FALSE | FALSE |  |  | FALSE |  | 2012-02-21 | 2012-02-07 | 2012-02-26 | 2012-02-21 | 2012-03-23 | 2012-04-03 | 1 | 2012-03-23 | 2012-04-03 | 2012-04-08 | 2012-04-17 | 2012-06-23 | 2012-06-15 | 1 | 2012-06-23 | 2012-06-15 | PERMITTED | 2012-03-30 | 2012-04-16 | 2012-05-18 | 2012-05-07 | 1 | 2012-05-18 | 2012-05-07 |  |  | 2012-06-28 | 2012-08-01 | 1 |  | 2012-08-01 | 2012-08-01 | 2012-08-24 |  |  |  |  | 2012-08-15 | 2012-08-14 | 2012-09-06 | 2012-09-04 | 2012-09-04 | 2012-09-14 | 2012-09-14 | [8 empty] | 2012-10-12 | 2012-11-15 | 2012-11-14 | 2012-11-28 | 2012-10-29 | 2013-04-27 | 2013-04-11 |  |  | 2012-10-10 | 2012-08-21 | 2012-08-24 | 2012-08-25 | 2012-08-31 | 2012-08-11 | 2012-08-24 | 2012-09-14 | 2012-09-14 | 2012-10-13 | 2012-10-15 | 2012-02-10 | MEDIUM | NEW_PLYMOUTH | 2012-09-16 | 2012-09-14 | BUILD | 2012-09-05 | FALSE |  | 2605013 | 6238857 | 489a Devon Street East, Fitzroy, New Plymouth |  | Status may be permitted depending on height requirements and pole design. To be confirmed following line of sight. - 20/02/2012 | CELLSITE | [15 empty] | 2012-10-28 | 2012-10-15
0 | TNK | 1325 | TNK-033-004 | Telecom Exchange Tx HUB | TNK-033-004-A | New Plymouth Telecom TX Hub | New Plymouth | 6 | TIER_3 | ACTIVE | COLO | TX | NOPOLE |  |  | COLO |  |  |  | -39.06 | 174.0771 |  |  |  | 2010-02-12 | Fibre Optic | AKL-007-106-A | FALSE | FALSE |  |  | FALSE |  |  | 2012-05-15 |  | 2012-05-15 |  | 2012-11-01 | 1 |  | 2012-11-01 |  | 2012-08-15 |  | 2012-08-15 |  |  | 2012-08-15 |  |  | 2012-11-01 |  | 2012-11-01 | 1 |  | 2012-08-15 |  |  |  | 2012-11-26 | 1 |  |  | 2012-11-26 | [5 empty] | 2012-09-05 | 2012-09-04 |  | 2012-09-04 | 2012-09-04 | 2012-09-07 | 2012-09-07 | [8 empty] | 2012-10-08 | 2012-11-13 | 2012-10-30 | 2012-12-09 | 2012-10-26 | 2013-04-24 | 2013-04-11 |  | TNZ | 2012-10-08 |  |  | 2012-08-31 |  |  |  | 2012-09-05 | 2012-09-10 | 2012-10-18 | 2012-10-12 |  |  | TRANSMISSION_ONLY | 2012-09-15 | 2012-09-07 | BUILD | 2012-09-04 | FALSE |  | 2603274 | 6237768 | TNZ Building Number 20625 92-96 LIARDET ST MARSLAND HILL NEW PLYMOUTH DISTRICT |  |  | TXSITE | [15 empty] | 2012-10-28 | 2012-10-12
0 | TNK | 1326 | TNK-033-005 | Welbourn | TNK-033-005-B | Welbourne, LPR Coronation Ave | New Plymouth | 6 | TIER_3 | ACTIVE | RSR | DU | P4F |  | INLINE | STANDALONE |  |  | 2 | -39.0685 | 174.0892 |  | 2011-12-20 |  | 2010-02-12 | Leased Line | TNK-033-004-A | FALSE | FALSE |  |  | FALSE |  |  | 2012-08-23 | 2012-10-03 | 2012-10-03 | 2012-12-05 | 2012-11-15 | 2 | 2012-12-05 | 2013-02-05 | 2013-02-28 | 2013-02-14 | 2013-02-28 | 2013-02-14 | 1 | 2013-02-28 | 2013-02-14 | PERMITTED | 2012-12-03 | 2013-01-16 | 2013-02-18 | 2013-02-18 | 2 | 2013-02-18 | 2013-02-18 |  |  | 2013-02-01 | 2013-02-04 | 1 |  | 2013-02-01 | 2013-02-04 | 2013-03-15 |  |  | 2012-12-11 |  | 2013-01-31 | 2013-02-04 | 2013-02-22 | 2013-03-15 | 2013-03-15 | 2013-02-22 | 2013-03-11 | [8 empty] | 2013-03-08 | 2013-03-15 | 2013-03-13 | 2013-03-29 | 2013-03-25 | 2013-07-23 | 2013-07-09 |  |  | 2013-02-22 |  |  |  |  | 2013-02-01 | 2013-03-15 | 2013-02-21 |  | 2013-03-10 | 2013-03-08 | 2012-02-10 | MEDIUM | NEW_PLYMOUTH | 2013-02-25 | 2013-02-25 | BUILD | 2013-02-20 | TRUE | 2012-11-19 | 2604309 | 6236812 | Coronation Ave |  |  | CELLSITE | [15 empty] | 2013-03-01 | 2013-03-12
0 | TNK | 1327 | TNK-033-006 | Vogeltown | TNK-033-006-A | Carrington Street, Transpower | New Plymouth | 6 | TIER_3 | ACTIVE | GF | DU | P2 |  | STACK_A | STANDALONE |  |  | 1 | -39.0813 | 174.0864 |  | 2011-12-20 |  | 2010-02-12 | Leased Line | TNK-033-004-A | FALSE | FALSE |  |  | FALSE |  | 2012-02-27 | 2012-02-27 | 2012-03-01 | 2012-03-01 | 2012-04-27 | 2012-05-04 | 2 | 2012-04-30 | 2012-06-28 | 2012-07-20 | 2012-07-03 | 2012-07-20 | 2012-08-07 | 2 | 2012-07-20 | 2012-08-07 | PERMITTED | 2012-05-07 | 2012-05-07 | 2012-07-20 | 2012-07-11 | 1 | 2012-07-20 | 2012-07-11 |  |  | 2012-09-07 | 2012-09-10 | 1 |  | 2012-09-07 | 2012-09-10 | 2012-09-14 |  |  |  |  | 2012-09-05 | 2012-09-06 | 2012-10-19 | 2012-10-15 | 2012-10-12 | 2012-10-17 | 2012-10-15 | [8 empty] | 2012-10-16 | 2012-11-15 | 2012-11-14 | 2012-11-13 | 2012-11-13 | 2013-06-15 | 2013-06-06 |  |  | 2012-10-18 | 2012-08-11 | 2012-08-11 | 2012-09-14 | 2012-09-14 | 2012-10-03 | 2012-09-14 | 2012-10-16 | 2012-10-15 | 2012-10-19 | 2012-10-19 | 2012-02-10 | LOW | NEW_PLYMOUTH | 2012-10-15 | 2012-10-16 | BUILD | 2012-10-14 | FALSE |  | 2604049 | 6235391 | New Plymouth |  | Could potentially be permitted if restrict height/slim mast design. - 20/02/2012 | CELLSITE | [15 empty] | 2012-10-28 | 2012-10-31
0 | TNK | 1328 | TNK-033-007 | Westown | TNK-033-007-A | Westown, Yarrow Stadium Greenfield | New Plymouth | 6 | TIER_3 | ACTIVE | GF | DU | P2 |  | STACK_A | STANDALONE |  |  | 1 | -39.0713 | 174.0649 |  | 2011-12-20 |  | 2010-02-12 | Microwave | TNK-033-001-A | FALSE | FALSE |  |  | FALSE |  | 2012-02-27 | 2012-02-27 | 2012-03-01 | 2012-03-01 | 2012-04-27 | 2012-05-15 | 1 | 2012-04-30 | 2012-05-15 | 2012-07-20 | 2012-07-11 | 2012-08-20 | 2012-08-16 | 1 | 2012-08-20 | 2012-08-16 | PERMITTED | 2012-05-07 | 2012-05-15 | 2012-06-22 | 2012-06-18 | 1 | 2012-06-22 | 2012-06-18 |  |  | 2012-09-11 | 2012-09-21 | 1 |  | 2012-09-11 | 2012-09-21 | 2012-09-14 |  |  |  |  | 2012-09-05 | 2012-09-06 | 2012-10-05 | 2012-10-02 | 2012-09-27 | 2012-11-02 | 2012-11-07 |  |  |  | 2012-02-13 |  |  |  |  | 2012-11-07 | 2012-12-15 | 2012-11-14 | 2013-01-01 | 2012-11-27 | 2013-09-15 | 2013-10-23 |  |  | 2012-11-06 | 2012-08-11 | 2012-08-11 | 2012-09-14 |  | 2012-09-14 | 2012-09-14 | 2012-10-15 | 2012-10-15 | 2012-11-10 | 2012-11-08 | 2012-02-10 | MEDIUM | NEW_PLYMOUTH |  |  | BUILD | 2012-09-26 | FALSE |  | 2602204 | 6236531 | Maratahu Street |  | Options in stadium will both trigger consent requirements (floodlight and LPR). - 20/02/2012 | CELLSITE | [15 empty] | 2012-11-14 | 2012-11-13
0 | TNK | 1329 | TNK-033-008 | Blagdon Hill | TNK-033-008-B | Spotwood, Telecom Colo South Road, (CBLA) | New Plymouth | 6 | TIER_3 | ACTIVE | COLO | DU | LATTICE |  | STACK_A | COLO |  |  | 1 | -39.0696 | 174.0403 |  | 2011-12-20 |  | 2010-02-12 | Leased Line | TNK-033-004-A | FALSE | FALSE |  |  | FALSE |  | 2012-02-21 | 2012-02-07 | 2012-02-26 | 2012-02-21 | 2012-05-04 | 2012-06-20 | 1 | 2012-05-04 | 2012-06-20 | 2012-08-30 | 2012-08-28 | 2012-09-04 | 2012-09-05 |  | 2014-04-01 |  | DISCRETIONARY_FULL | 2012-05-07 | 2012-05-07 | 2012-09-12 | 2012-09-09 | 1 | 2012-09-12 | 2012-09-09 |  |  | 2012-10-17 | 2012-10-23 | 1 |  | 2012-10-17 | 2012-10-23 | 2012-10-11 |  |  |  |  | 2012-10-22 | 2012-10-17 | 2012-10-26 | 2012-10-26 | 2012-10-25 | 2012-10-30 | 2012-11-02 | [8 empty] | 2012-11-05 | 2012-12-15 | 2012-11-14 | 2013-01-01 | 2012-11-30 | 2013-07-14 | 2013-06-19 |  | TNZ | 2012-11-02 | 2012-09-14 | 2012-08-31 | 2012-09-21 |  | 2012-09-21 | 2012-10-11 | 2012-10-30 | 2012-10-30 | 2012-11-10 | 2012-11-06 | 2012-02-10 | LOW | NEW_PLYMOUTH | 2012-10-19 | 2012-10-19 | BUILD | 2012-10-29 | FALSE |  | 2600076 | 6236744 | 91a South Rd, New Plymouth |  |  | CELLSITE | [15 empty] | 2012-11-11 | 2012-11-19
0 | TNK | 1330 | TNK-033-009 |  |  |  | New Plymouth |  | TIER_9 | [83 empty] | Moturoa. Power plant chimney stack where VNZ is.
0 | TNK | 1331 | TNK-033-010 | Hurdon | TNK-033-010-C | LPR Cnr Wallath & Tukapu | New Plymouth | 6 | TIER_3 | ACTIVE | RSR | DU | P4F |  | INLINE | STANDALONE | 15 | 15 | 2 | -39.0824 | 174.0511 |  | 2011-12-20 |  | 2010-02-12 | Microwave | TNK-033-008-B | FALSE | FALSE |  |  | FALSE |  | 2012-05-01 | 2012-05-01 | 2012-05-08 | 2012-05-18 | 2012-06-15 | 2012-06-21 | 2 | 2012-06-15 | 2012-10-23 | 2012-09-20 | 2012-09-03 | 2012-08-30 | 2012-09-03 | 1 | 2012-08-30 | 2012-09-03 | CONTROLLED | 2012-07-11 | 2012-07-09 | 2012-08-11 | 2012-08-16 | 1 | 2012-08-11 | 2012-08-16 |  |  | 2012-11-16 | 2012-11-26 | 2 |  | 2012-11-16 | 2013-02-12 | 2012-08-20 |  |  | 2012-10-24 |  | 2012-11-23 | 2012-11-26 | 2013-02-04 | 2013-02-04 | 2013-01-21 | 2013-02-04 | 2013-02-06 | [8 empty] | 2013-02-11 | 2013-02-21 | 2013-02-15 | 2013-02-22 | 2013-02-22 | 2013-06-05 | 2013-05-30 |  |  | 2013-02-07 | 2012-08-31 |  |  |  | 2012-08-20 | 2012-08-20 | 2013-01-29 | 2013-02-01 | 2013-02-15 | 2013-02-13 | 2012-05-24 | HIGH | NEW_PLYMOUTH |  |  | BUILD | 2013-01-25 | TRUE |  | 2600992 | 6235311 | Cnr Wallath Rd and Tukapu Street |  |  | CELLSITE | [15 empty] | 2013-02-11 | 2013-02-13 | 2012-05-18
0 | TNK | 1332 | TNK-033-011 | Waitara West |  |  | New Plymouth |  | TIER_9 | [83 empty] | Waitara
0 | TNK | 1333 | TNK-033-012 |  |  |  | New Plymouth |  | TIER_9
0 | TNK | 1334 | TNK-033-013 | Port Taranaki |  |  | New Plymouth | 6 | TIER_9 | [22 empty] | FALSE | [60 empty] | Coverage Objective: Marine coverage to the north. Umbrella coverage along coastlines to the east and southwest. Proposed panel antennas at top of chimney. VF already present. May need to go above VF on pole mounts if space is an issue. G1800MHz only.
0 | TNK | 1335 | TNK-033-014 | Highlands Park |  |  | New Plymouth |  | TIER_9 | [22 empty] | FALSE | [60 empty] | Coverage Objective: Residential area of Highlands Park Potential Candidate: Kordia Pole in warehouse grounds. Need 25m. This location affords natural isolation from TNK-033-006. Backup could be LPR on residential street at higher elevation.
0 | TNK | 1336 | TNK-033-015 | Bell Block | TNK-033-015-A | Hookers Greenfield | New Plymouth | 6 | TIER_3 | ACTIVE | GF | DU | T2 25 UF |  | INLINE | STANDALONE |  |  | 1 | -39.039 | 174.1446 |  | 2011-12-20 |  | 2010-02-12 | Leased Line | TNK-033-004-A | FALSE | FALSE |  |  | FALSE |  | 2012-02-27 | 2012-02-27 | 2012-03-01 | 2012-03-01 | 2012-06-15 | 2012-06-21 | 1 | 2012-06-15 | 2012-06-21 | 2012-06-24 | 2012-06-25 | 2012-08-24 | 2012-08-10 | 1 | 2012-08-24 | 2012-08-16 | PERMITTED | 2012-06-30 | 2012-06-25 | 2012-07-30 | 2012-07-11 | 1 | 2012-08-04 | 2012-07-11 |  |  | 2012-09-14 | 2012-09-26 | 1 |  | 2012-09-14 | 2012-09-26 | 2012-10-17 |  |  |  |  | 2012-08-24 | 2012-08-29 | 2012-10-23 | 2012-10-23 | 2012-10-18 | 2012-10-24 | 2012-10-26 | [8 empty] | 2012-10-26 | 2012-11-15 | 2012-11-14 | 2012-11-13 | 2012-11-13 | 2013-09-15 | 2013-11-27 |  |  | 2012-10-24 | 2012-08-11 | 2012-08-11 | 2012-08-13 | 2012-10-01 | 2012-09-13 | 2012-10-17 | 2012-10-23 | 2012-10-24 | 2012-10-23 | 2012-10-29 |  |  | NEW_PLYMOUTH | 2012-10-18 | 2012-10-24 | BUILD | 2012-10-14 | FALSE |  | 2609149 | 6240019 | 24 Paraite Rd Bell Block |  |  | CELLSITE | [15 empty] | 2012-10-30 | 2012-11-02
0 | TNK | 1337 | TNK-033-016 | Waitara | TNK-033-016-A | Waitara, VF Colo (Waitara) | New Plymouth | 6 | TIER_3 | ACTIVE | COLO | DU | COLO |  | STACK_A | COLO |  |  | 1 | -39.0087 | 174.224 |  | 2011-12-20 |  | 2010-02-12 | Leased Line | TNK-033-004-A | FALSE | FALSE |  |  | FALSE |  | 2012-02-21 | 2012-02-07 | 2012-02-26 | 2012-02-21 | 2012-05-04 | 2012-05-15 | 1 | 2012-05-04 | 2012-05-15 | 2012-08-05 | 2012-06-01 | 2012-10-12 | 2012-10-15 |  | 2012-10-12 | 2012-10-16 | DISCRETIONARY_RESTRICT | 2012-05-09 | 2012-05-14 | 2012-06-09 | 2012-06-10 | 1 | 2012-06-13 | 2012-06-10 |  |  | 2012-10-05 | 2012-10-02 | 1 |  | 2012-10-05 | 2012-10-02 | 2012-10-12 |  |  |  |  | 2012-10-08 | 2012-10-08 | 2012-10-16 | 2012-10-15 | 2012-10-08 | 2012-10-16 | 2012-10-18 | [8 empty] | 2012-10-19 | 2012-11-15 | 2012-11-14 | 2012-11-13 | 2012-11-13 | 2013-09-15 | 2013-09-19 |  | VNZ | 2012-10-16 | 2012-08-11 | 2012-08-11 | 2012-08-25 | 2012-09-12 | 2012-09-11 | 2012-10-12 | 2012-10-12 | 2012-10-24 | 2012-10-18 | 2012-10-29 | 2012-02-10 | LOW | NEW_PLYMOUTH | 2012-10-15 | 2012-10-24 | BUILD | 2012-10-10 | FALSE |  | 2616066 | 6243288 | 15 Borthwick Street New Plymouth |  | Co-lo likely to trigger consent requirement if addtional height required. - 20/02/2012 | CELLSITE | [15 empty] | 2012-10-28 | 2012-11-01
0 | TNK | 1338 | TNK-033-017 | Lepperton |  |  | New Plymouth |  | TIER_9 | [22 empty] | FALSE | [60 empty] | Coverage Objective: SH3A north and south. Rural residences in area. TNZ colo at minimum 20m or GF at minimum 20m in similar location.
0 | TNK | 1339 | TNK-033-018 | New Plymouth Airport |  |  | New Plymouth |  | TIER_9 | [22 empty] | FALSE | [60 empty] | Coverage Objective: New Plymouth airport and road links to SH3. GF at 20m preferred.
0 | TNK | 1340 | TNK-033-019 | RBI - Carrington Rd |  |  | New Plymouth |  | RBI | [22 empty] | FALSE
0 | TNK | 1341 | TNK-033-020 | RBI - Oakura |  |  | New Plymouth |  | RBI | [22 empty] | FALSE
0 | TNK | 1342 | TNK-033-021 | Spotswood West |  |  | New Plymouth |  | TIER_9
0 | TNK | 1343 | TNK-033-022 | Westown |  |  | New Plymouth |  | TIER_9
0 | TNK | 1344 | TNK-033-023 | Power Company |  |  | New Plymouth |  | TIER_9
0 | TNK | 1345 | TNK-033-024 | New Plymouth Airport |  |  | New Plymouth |  | TIER_9
0 | TNK | 1346 | TNK-033-025 | Inglewood | TNK-033-025-A | Inglewood VF Colo | New Plymouth | 6 | TIER_3 | ACTIVE | COLO | DU | COLO |  | STACK_A | COLO |  |  | 1 | -39.1517 | 174.2106 |  | 2012-01-25 |  |  | Leased Line | TNK-033-004-A | FALSE | FALSE |  |  | FALSE |  | 2012-02-21 | 2012-02-07 | 2012-02-26 | 2012-02-21 | 2012-03-23 | 2012-04-04 | 1 | 2012-03-23 | 2012-04-04 | 2012-09-10 | 2012-09-11 | 2012-10-26 | 2012-10-25 |  | 2012-10-26 | 2012-11-12 | DISCRETIONARY_RESTRICT | 2012-05-07 | 2012-05-07 | 2102-06-07 | 2012-05-21 | 1 | 2012-06-11 | 2012-05-25 |  |  | 2012-09-07 | 2012-09-10 | 1 |  | 2012-09-07 | 2012-09-10 | 2012-10-01 |  |  |  |  | 2012-09-25 | 2012-09-26 | 2012-10-05 | 2012-10-23 | 2012-09-26 | 2012-10-26 | 2012-10-27 | [8 empty] | 2012-10-29 | 2012-11-15 | 2012-11-14 | 2012-11-13 | 2012-11-13 | 2013-05-13 | 2013-04-26 |  | VNZ | 2012-10-29 |  |  | 2012-08-25 | 2012-09-12 | 2012-09-11 | 2012-10-01 | 2012-09-05 | 2012-10-24 | 2012-11-10 | 2012-10-31 | 2012-02-10 | LOW | NEW_PLYMOUTH | 2012-11-01 | 2012-11-01 | BUILD | 2012-10-05 | FALSE |  | 2614687 | 6227436 | 5 Humphries Street Inglewood |  |  | CELLSITE | [15 empty] | 2012-11-02 | 2012-11-02
0 | TNK | 1347 | TNK-034-001 |  |  |  | Stratford District |  | TIER_9
0 | TNK | 1348 | TNK-034-002 |  |  |  | Stratford District |  | TIER_9
0 | TNK | 1349 | TNK-034-003 | Stratford | TNK-034-003-E | End Electrical | Stratford District | 24 | TIER_4 | ACTIVE | GF | DF | T2 20 UF |  | STACK_A | STANDALONE |  |  |  | -39.3387 | 174.2835 |  | 2015-03-03 |  | 2015-02-26 | Fibre Optic | TNK-033-004-A | FALSE | FALSE |  |  | FALSE |  | 2015-07-02 | 2015-07-02 | 2015-07-02 | 2015-07-02 | 2015-07-10 | 2015-07-30 | 1 |  | 2015-07-30 | 2015-07-28 | 2015-07-28 | 2015-08-07 | 2015-08-06 |  | 2015-09-10 | 2015-08-11 | DISCRETIONARY_FULL | 2015-07-31 | 2015-07-31 | 2015-08-31 | 2015-08-28 | 1 |  | 2015-09-10 | 2015-07-31 | 2015-07-28 | 2015-09-04 | 2015-09-25 | 1 |  |  | 2015-09-25 | [5 empty] | 2016-02-26 | 2016-02-02 | 2016-02-19 |  |  | 2016-02-29 |  |  |  | 2015-07-28 | 2015-07-28 | [5 empty] | 2016-03-28 | [5 empty] | AS: CDI ussued | [10 empty] | 2016-03-15 |  |  |  | NEW_PLYMOUTH |  |  | BUILD |  | FALSE |  | 2620678 | 6206591 | 38 Miranda Street, Stratford |  |  | CELLSITE |  |  |  | ROAMING |  | 2015-08-20 | 2015-10-16 | 2015-08-21 | 2015-08-07 |  |  |  |  | 2016-02-12 | 2016-02-02 |  |  | 2015-07-02
0 | TNK | 1350 | TNK-034-004 | Te Maunga o Taranaki | TNK-034-004-B | Egmont Aviation Migration | Stratford District | 24 | TIER_4 | ACTIVE | GF | DF | T2 20 RF |  | STACK_A | COSITE |  |  | 1 | -39.3058 | 174.1055 |  | 2012-02-02 |  | 2015-04-15 | Microwave | TNK-033-025-A | FALSE | FALSE |  |  | FALSE |  | 2012-05-01 | 2015-05-05 | 2015-05-15 | 2015-05-15 | 2015-05-22 | 2013-02-19 | 2 | 2015-05-27 | 2015-05-27 | 2015-08-14 | 2015-09-10 | 2015-11-30 | 2015-11-23 |  | 2015-09-11 |  | PERMITTED | 2015-06-30 | 2015-06-08 | 2015-07-31 | 2015-06-25 | 2 |  | 2015-09-10 | 2015-07-17 | 2015-06-29 | 2015-11-30 | 2015-11-18 | 1 |  |  | 2015-11-18 | [5 empty] | 2016-02-29 |  | 2016-03-30 |  |  | 2016-04-15 |  | 2015-10-16 |  | 2015-07-28 | 2015-07-28 | [5 empty] | 2016-05-13 | [5 empty] | 8 Oct 2014 - SA to reforecast lease, TP to re forecast RMA. Dialogue with Airways, DoC and local Iwi to be re-established. Reveion to PD under review, Cliff to check original Tx plan. 28 Oct SA re-establishing contacts- some advice from ex WLG Pm on how to approach the task has been recieved. Site subject to RF review and confirmation 09/03 AS: John has resumed talks with IWI & Doc. will come up with update 3/2/15 - pursuing spark co-lo 11/03 - Going with GF at IWI/Doc location, Rob/John have resumed talks with Iwi guys for approval on proposed GF solution | O | [9 empty] | 2016-04-29 |  | 2012-04-30 | LOW | NEW_PLYMOUTH | 2015-10-16 |  | BUILD |  | FALSE |  | 2605379 | 6210450 | Airways location |  | Council previously thought this would be Discretionary. Council have since confirmed this should be permitted. - 16/03/2015 | CELLSITE | WIPACTIVE |  |  | ROAMING |  | 2015-05-05 | 2015-10-16 | 2015-09-15 | 2015-09-11 |  |  |  |  | 2016-02-12 | 2016-02-04 |  |  | 2015-05-15
0 | TNK | 1351 | TNK-035-001 |  |  |  | South Taranaki District |  | TIER_9
0 | TNK | 1352 | TNK-035-002 |  |  |  | South Taranaki District |  | TIER_9
0 | TNK | 1353 | TNK-035-003 |  |  |  | South Taranaki District |  | TIER_9
0 | TNK | 1354 | TNK-035-004 |  |  |  | South Taranaki District |  | TIER_9
0 | TNK | 1355 | TNK-035-005 | Waverley |  |  | South Taranaki District |  | 2015 | [22 empty] | FALSE
0 | TNK | 1356 | TNK-035-006 | Hawera | TNK-035-006-A | Hawera Water Tower Co Site | South Taranaki District | 6 | TIER_3 | ACTIVE | BO | DF | BO |  | STACK_A | COSITE |  |  | 1 | -39.5901 | 174.2851 |  | 2011-12-20 |  |  | Leased Line | TNK-033-004-A | FALSE | FALSE |  |  | FALSE |  | 2012-05-02 | 2012-05-02 | 2012-05-22 | 2012-05-25 | 2012-07-11 | 2012-07-10 | 1 | 2012-07-11 | 2012-07-10 | 2012-09-20 | 2012-09-20 | 2012-10-20 | 2012-10-05 | 1 | 2012-12-15 | 2013-03-14 | DISCRETIONARY_FULL | 2012-07-13 | 2013-03-06 | 2012-11-19 | 2013-03-06 | 1 | 2012-11-30 | 2013-03-06 |  |  | 2013-02-01 | 2013-02-07 | 2 |  | 2013-02-01 | 2013-04-11 | 2013-03-04 |  |  |  |  | 2012-11-29 | 2013-01-07 | 2013-02-25 | 2013-03-13 | 2013-01-22 | 2013-02-25 | 2013-03-11 | [8 empty] | 2013-03-13 | 2013-03-19 | 2013-03-19 | 2013-03-28 | 2013-03-28 | 2013-09-25 | 2013-10-01 |  |  | 2013-02-26 |  |  | 2013-01-01 | 2013-01-01 | 2012-12-07 | 2013-03-04 | 2013-01-25 | 2013-01-25 | 2013-03-05 | 2013-03-14 | 2012-05-01 | LOW | NEW_PLYMOUTH | 2013-02-15 | 2013-02-15 | BUILD | 2013-01-22 | FALSE |  | 2620404 | 6178679 | 55 High Street, Hawera |  |  | CELLSITE | [15 empty] | 2013-02-28 | 2013-03-14 | 2012-05-28
0 | TNK | 1357 | TNK-035-007 | Waverley | TNK-035-007-B | VF Co-lo | South Taranaki District | 24 | TIER_4 | ACTIVE | COLO | DF | NOPOLE |  | STACK_A | COLO |  |  |  | -39.7542 | 174.6519 |  | 2015-03-11 |  | 2015-06-18 | Fibre Optic | TNK-033-004-A | FALSE | FALSE |  |  | FALSE |  | 2015-04-30 | 2015-04-30 | 2015-06-30 | 2015-06-09 | 2015-06-30 | 2015-06-25 | 1 |  | 2015-06-25 | 2015-06-29 | 2015-06-26 | 2015-08-31 | 2015-08-28 |  | 2015-09-04 |  |  | 2015-08-21 | 2015-08-24 | 2015-09-25 | 2015-09-15 | 1 |  |  | 2015-09-01 | 2015-09-08 | 2015-10-09 | 2015-11-27 | 1 |  |  | 2015-11-27 | [5 empty] | 2016-04-15 |  | 2016-04-29 |  |  | 2016-05-20 |  | 2015-10-30 |  | 2015-07-28 | 2015-07-28 | [5 empty] | 2016-06-30 | [5 empty] | 11/03 AS VF site datapack requested, Chris to issue brief in parallel for back up option 20/03 AS SDP received Chris need to evaluate RF solution on VF co-lo, Natasha on site visits to come up with VF co-site or other back up | VNZ | [9 empty] | 2016-06-10 |  |  |  |  | 2015-10-30 |  | ONHOLD |  | FALSE |  | 2651561 | 6159939 | Upper Herengawe Road, Waverly |  |  | CELLSITE | WIPACTIVE |  |  | ROAMING |  |  |  | 2016-03-01 | [5 empty] | 2016-03-31 |  |  |  | 2015-06-09
0 | WKT | 1358 | WKT-011-002 |  |  |  | Thames Coromandel District |  | TIER_9
0 | WKT | 1359 | WKT-011-003 | Coromandel Township | WKT-011-003-A | Coromandel Township Greenfield | Thames Coromandel District | 22 | TIER_4 | ACTIVE | GF | DF | T2 20 RH |  | STACK_A | COSITE | 20 | 20 |  | -36.7256 | 175.5198 |  |  |  |  | Microwave | WKT-011-016-A | FALSE | FALSE |  |  | FALSE |  | 2014-11-11 | 2014-11-11 | 2014-11-18 | 2014-11-17 | 2014-12-05 | 2008-06-13 | 4 | 2014-12-19 | 2015-06-05 | 2015-06-24 | 2015-06-23 | 2015-07-24 | 2015-06-22 |  | 2015-07-31 | 2015-09-11 | NON_COMPLYING_FULL | 2015-05-20 | 2015-05-28 | 2015-07-01 | 2015-06-30 | 3 | 2015-07-08 | 2015-06-30 | 2015-05-19 | 2015-05-21 | 2015-07-31 | 2015-08-14 | 1 |  | 2015-07-31 | 2015-08-14 | [5 empty] | 2015-10-07 | 2015-10-08 | 2015-11-26 | 2015-11-30 |  | 2015-11-27 | 2015-11-30 | [9 empty] | 2015-12-11 | 2015-12-14 | 2015-12-18 | 2015-12-18 |  |  | 01/02/12 - PD's had been done in 2008 - look at option etc on site visit next week 16/02/12 - Telecom have designated area, and if within this designation, then planning wise will be permissive 16/1/15 - plans with Brad & James - negotiations with DOC underway 3/2/15 - now pursuing spark co-lo will keep this as a back up 25.2.15 - Brad & James to meet tomorrow to work through proposal 10/3/15 - Brad drafting concession application 1/4/15 - concession application submitted to DoC 15/7/15 - all cosite applications lodged | [10 empty] | 2015-12-11 | 2015-12-07 |  |  | COROMMANDEL |  |  | BUILD |  | FALSE |  | 2735487 | 6494157 | Kaipawa Trig Track, off Kennedy Bay Rd, Coromandel | - Sent Co-site applications to Spark, Chorus (Jordan), Vodafone, Police and Coast Guard. Police have approved - 20/07/2015 |  | CELLSITE |  |  |  | ROAMING |  | 2015-07-09 | 2015-07-13 | 2015-08-03 | 2015-07-28 |  | 2015-04-13 |  |  | 2015-09-14 | 2015-09-15 |  |  | 2014-11-17
0 | WKT | 1360 | WKT-011-004 | Matarangi | WKT-011-004-B | VF Co-Lo | Thames Coromandel District | 22 | TIER_4 | ACTIVE | COLO | DU | NOPOLE |  |  | COLO | [6 empty] | 2015-02-17 |  |  | Fibre Optic | WKT-016-023-B | FALSE | FALSE |  |  | FALSE |  | 2015-04-09 | 2015-04-09 | 2015-05-04 | 2015-04-14 | 2015-05-19 | 2015-05-15 | 2 | 2015-08-17 | 2015-08-12 | 2016-02-29 |  | 2016-04-11 |  |  | 2016-04-25 |  | DISCRETIONARY_FULL | 2016-01-28 | 2016-01-28 | 2016-03-07 |  | 2 | 2016-03-14 |  | 2016-02-09 |  | 2016-03-21 |  |  |  | 2016-03-21 | [13 empty] | 2016-04-29 | [14 empty] | 18.5.15 - VF co-lo application submitted 13.08.15 - updated VF application submitted 3/9/15 - received VF prelim approval based on carousal headframe design. | VNZ | [14 empty] | 2016-04-29 |  | ONHOLD |  | FALSE | [6 empty] | CELLSITE | WIPACTIVE |  |  | ROAMING | [6 empty] | 2015-04-01 |  | 2015-07-13 |  |  |  |  | 2015-04-14
0 | WKT | 1361 | WKT-011-005 | Whitianga | WKT-011-005-A | Kordia Mast | Thames Coromandel District |  | TIER_5 | ACTIVE | COLO | DU |  |  |  | COLO |  |  | 1 | -36.7832 | 175.7379 |  |  |  |  | Microwave | WKT-011-006-D | FALSE | FALSE |  |  | FALSE |  | 2012-04-13 | 2012-03-27 | 2012-05-28 | 2012-05-22 | 2012-05-28 | 2012-05-22 | 1 | 2012-05-31 | 2012-05-22 | 2012-06-22 | 2012-05-22 | 2012-07-13 |  |  | 2012-11-15 |  | OPW | 2012-06-04 | 2012-06-08 | 2012-08-31 |  | 1 | 2012-08-31 | [5 empty] | 1 | [30 empty] | (VF SDP ordered 23/1/12 but site not available from VF) 23/03/12 - pole confirmed as Kordia. Colo application done. Kelly to confirm if cabinet area will be Kordia Lease or with owner direct 22/05/12 - WO1 issued and lease terms agreed with Kordia. Drawings issued. Site cannot be built until Sep/Oct when Analogue TV turned off and mast space availablerogressing 24/05/12 - Kordia RMA application 05/10/12 - Site taken out from Build Programme | KDA | [13 empty] | COROMMANDEL |  |  | ONHOLD |  | FALSE |  | 2754762 | 6487195 | Off SH25 Whitianga North | [20 empty] | 2012-03-27
0 | WKT | 1362 | WKT-011-006 | Whitianga Central | WKT-011-006-D | Telecom land - Greenfield | Thames Coromandel District | 22 | TIER_4 | ACTIVE | GF | DU | T2 25 RH |  | STACK_A | COSITE |  |  |  | -36.8531 | 175.7133 |  |  |  |  | Fibre Optic, Fibre Optic | WKT-016-023-B | FALSE | FALSE |  |  | FALSE |  | 2012-03-30 | 2012-03-28 | 2012-04-04 | 2012-03-29 | 2012-05-28 | 2012-06-05 | 3 | 2012-05-28 | 2013-05-20 | 2012-08-03 | 2012-07-24 | 2012-08-31 | 2012-07-25 |  | 2013-02-28 | 2014-10-22 | NON_COMPLYING_LIMITED | 2012-10-03 | 2012-10-08 | 2013-02-28 | 2013-05-22 | 2 | 2012-11-26 | 2014-10-22 | 2012-08-15 | 2012-08-15 | 2012-10-12 | 2012-10-16 | 3 |  | 2014-12-03 | 2015-02-12 | 2015-03-18 |  |  |  |  | 2015-04-13 | 2015-04-02 | 2015-05-29 | 2015-04-22 | 2015-04-22 | 2015-05-18 | 2015-05-07 | 2015-05-08 | [7 empty] | 2015-05-12 | 2015-05-29 | 2015-05-25 | 2015-06-16 | 2015-06-19 |  |  | , with delays in lease/RMA and 3 week period for Project Plan approval and CR 30/10/12 - Delays with leasing/access issues. Construction dates and Chorus fibre dates reforecast. Huawei will request PAC extension. 08/01/13 - Will be hearing. Notice closes Feb, then hearing, then appeal period, so construction probably cannot start till April 14/02/13 - WO2 cancelled 16/1/15 - site is ready to build in March 2015, pole and equipment ordered 28/01/15 - slope stability investigation scheduled for 29/1/15 - LO permission has been sought 15.3.15 - RFS date 08/4/15 9/3/15 - pre start meeting on 18 March - ROW access owners have been invited | [6 empty] | 2015-03-18 | 2015-03-18 | 2015-05-05 | 2015-05-05 | 2015-06-08 | 2015-05-18 |  |  | COROMMANDEL | 2015-05-08 | 2015-05-05 | BUILD | 2015-04-28 | FALSE |  | 2752327 | 6479506 | Dacy Property Purangi Road Maramaratotara Bay |  |  | CELLSITE |  |  |  | ROAMING |  | 2014-12-18 | 2014-12-11 |  | 2015-03-30 |  |  |  | 2015-01-14 |  | 2015-03-30 |  |  | 2012-03-29
0 | WKT | 1363 | WKT-011-007 | Hahei | WKT-011-007-B | Hahei VNZ Colocate | Thames Coromandel District | 22 | TIER_4 | ACTIVE | COLO | DF | NOPOLE | grey | STACK_A | COLO | 30 | 30 |  | -36.8394 | 175.7926 |  |  |  |  | Microwave | WKT-011-006-D | FALSE | FALSE |  |  | FALSE |  | 2014-12-03 | 2014-12-02 | 2014-12-11 | 2014-11-18 | 2014-11-28 | 2012-05-24 | 5 | 2015-06-24 | 2015-07-15 | 2016-03-31 |  | 2016-05-09 |  |  | 2016-05-23 |  | NON_COMPLYING_FULL | 2015-07-13 | 2015-07-21 | 2015-08-24 | 2015-08-18 | 5 | 2015-08-24 | 2015-08-18 | 2015-07-09 | 2015-07-13 | 2015-11-09 | 2015-10-22 | 1 |  | 2015-11-16 | 2015-10-22 | [27 empty] | 10/02/12 - Site visited. Steep access last 300m. VF is a triangular guyed mast. Need to look at options here as no space for 3rd mast on site. If VF power not available, will need to run power in cable tray down hill to township 01/06/12 - Structural received. Docs sent to Liz to lodge colo application 5 June 14/06/12 - VF requested 2D to relook at colo. Their additional antennas push 2D further down due to rigging issues on mast. Trevor requested to look at options, which may include relocating nominal 02/07/12 - Teleconference with GHD to look at options of mounting antennas using out-riggers or similar. GHD to come back within week or so with options. 03/07/12 - Reforcasted dates 05/10/12 - Site taken out from Build Programme 29/1/15 - site back in programme, VF co-lo applicaiton ready to submit 2/2/15 - co-lo application submitted 23.2.15 - Trevor provided possible location for own GF site on lower hilltop. 3/3/15 - look at own GF as back up on same privately owned land on 11th - 12th March site visits 10/3/15 - fibre feasibility done - $20k - could do this if MW compromises the structural co-lo option 27/5/15 - updated co-lo application submitted - includes tower strengthening proposal and MW for linking - fibre has been determined as not feasible. 26/8/15 - VF have agreed we can open negotiations with LO again | VNZ | [13 empty] | COROMMANDEL |  |  | ONHOLD |  | FALSE |  | 2759448 | 6480807 | Lees Road Hahei |  |  | CELLSITE | WIPACTIVE |  |  | ROAMING | [6 empty] | 2015-04-01 | [6 empty] | 2014-11-18
0 | WKT | 1364 | WKT-011-008 | Pauanui | WKT-011-008-B | Pauanui/Tairua TNZ Colocate | Thames Coromandel District |  | TIER_5 | ACTIVE | COLO | DU | NOPOLE |  | STACK_A | COLO | 20 | 20 |  | -36.9712 | 175.8154 |  |  |  |  | Microwave | WKT-011-009-A | FALSE | FALSE |  |  | FALSE |  | 2012-03-23 | 2012-03-02 | 2012-03-27 | 2012-03-05 | 2012-03-22 | 2008-07-21 | 4 | 2012-03-30 | 2012-04-12 | 2012-06-22 |  | 2012-07-06 |  |  | 2012-07-27 |  | NON_COMPLYING_LIMITED | 2012-06-27 |  | 2012-08-03 |  |  | 2012-08-10 | [5 empty] | 1 | 3 | [29 empty] | 01/02/11 - Paul Road, Off SH 25 North, Tairua, was a candidate in 2008. PD's done for colocation on Telecom lattice mast 09/04/12 - Rev 0.1 received, Rev4 for issue received 11/04/12 12/04/12 - Rev 4 drawings issued. 30/04/12 - Telecom/Chorus received colo application 04/05/12 - Need Telecom Designation process - Ron to discuss with Barbara on this use, or to use process done at Tauranga 14/06/12 - Chasing colo approval. Resource Consent drafted and ready to go 21/06/12 - Preliminary approval received. rental high per month. Still chasing where their diesol tank is for consent lodgement 08/08/12 - WO2 forcasted 05/10/12 - Moved out of build programme | TNZ | [13 empty] | COROMMANDEL |  |  | ONHOLD |  | FALSE |  | 2761012 | 6466124 | Paul Road Off SH 25 North Tairua Coromandel | [20 empty] | 2012-03-05
0 | WKT | 1365 | WKT-011-009 | Pauanui South | WKT-011-009-B | Pauanui South GF | Thames Coromandel District | 22 | TIER_4 | ACTIVE | GF | DU | T2 20 RH |  |  | COSITE |  |  |  | -37.0378 | 175.873 |  |  |  |  | Microwave | WKT-011-012-A | FALSE | FALSE |  |  | FALSE |  | 2012-03-02 | 2012-03-02 | 2012-08-09 | 2012-08-09 | 2012-08-27 | 2012-09-04 | 3 | 2012-08-27 | 2015-03-02 | 2015-04-30 | 2015-04-28 | 2015-07-10 | 2015-06-25 |  | 2015-07-10 | 2015-06-30 | CONTROLLED | 2012-10-16 | 2012-11-09 | 2012-11-30 | 2012-12-17 | 2 | 2012-12-07 | 2012-12-17 | 2015-06-15 | 2015-04-29 | 2015-06-18 | 2015-06-24 | 2 |  | 2015-06-25 | 2015-08-24 | [5 empty] | 2015-08-24 | 2015-08-26 | 2015-09-29 | 2015-09-29 |  | 2015-09-30 | 2015-09-30 | [9 empty] | 2015-10-22 | 2015-10-15 | 2015-10-28 | 2015-10-28 |  |  | 23/08/12 - Coastal Boundary plan to be superimposed on PDs 05/10/12 - Moved out of build programme 17/12/12 - RMA granted 29/1/15 - back in programme - contact to be made with LO to see if they are still keen 5/2/15 - check linking - is it dependant on another site 18.2.15 - Brad to contact Matariki to see if they are willing to re-look at our proposal 25.2.15 - check with Trevor re location still ok before Brad to make contact with Matariki 26.2.15 - Trevor good with location PD's with design for up rev 2/3/15 - PD up revs issued, with Brad to contact Matariki 10/3/15 - Matariki have acknowledged receipt of our proposal 18.5.15 - tender instruction issued to Huawei | [10 empty] | 2015-10-12 | 2015-10-07 |  |  | COROMMANDEL |  |  | BUILD |  | FALSE |  | 2765904 | 6458572 | Trig Rd Off Forestry Rd, off Hikua Settlement Rd, Pauanui |  |  | CELLSITE |  |  |  | ROAMING |  | 2015-07-09 | 2015-06-10 | 2015-05-20 | 2015-05-18 |  | 2015-04-16 |  |  | 2015-07-10 | 2015-07-16 |  |  | 2012-08-09
0 | WKT | 1366 | WKT-011-010 | Onemana | WKT-011-010-A | Onemana Greenfield | Thames Coromandel District |  | TIER_5 | ACTIVE | GF | DU | P2 |  |  | COSITE | 8 | 8 |  | -37.157 | 175.8778 | [6 empty] | FALSE | FALSE |  |  | FALSE | [6 empty] | 2008-06-27 | 1 |  | 2008-06-27 |  |  |  |  | 1 | [11 empty] | 2008-10-21 |  | 2008-11-21 | 1 | 1 | 2008-11-21 | 2008-11-21 | [45 empty] | ONHOLD |  | FALSE |  | 2765903 | 6445341
0 | WKT | 1367 | WKT-011-012 | Whangamata South | WKT-011-012-A | Whangamata South Greenfield | Thames Coromandel District | 2 | TIER_3 | ACTIVE | GF | DU | T2 25 RH |  | STACK_A | COSITE | 20 | 20 | 1 | -37.2145 | 175.8551 |  |  |  |  | Fibre Optic |  | FALSE | FALSE |  |  | FALSE |  | 2012-03-30 | 2012-03-02 | 2012-04-04 | 2012-03-05 | 2012-03-22 | 2008-07-01 | 4 | 2012-03-30 | 2012-08-16 | 2012-10-15 | 2012-10-15 | 2012-10-19 | 2012-10-31 | 3 | 2012-10-26 | 2012-10-31 | NON_COMPLYING_LIMITED | 2012-08-20 | 2012-08-20 | 2012-10-12 | 2012-10-11 | 4 | 2012-10-12 | 2012-10-11 | 2012-08-14 |  | 2012-10-12 | 2012-10-23 | 2 |  | 2012-10-12 | 2012-11-02 | 2012-11-14 |  |  |  |  | 2012-10-25 | 2012-10-25 | 2012-11-15 | 2012-11-15 | 2012-11-15 | 2012-11-26 | 2012-11-26 | 2012-11-19 | 2012-11-19 | [6 empty] | 2012-11-26 | 2012-12-07 | 2012-12-04 | 2012-12-12 | 2012-12-07 | 2013-06-28 | 2013-06-27 | 18/03/13 - Sangs to clear and PSVP to pass before FAN issue 27/06/13 - FAC signed |  | 2012-11-26 | 2012-09-24 | 2012-10-06 | 2012-10-22 | 2012-11-14 | 2012-10-24 | 2012-11-14 | 2012-11-19 | 2012-11-19 | 2012-11-26 | 2012-11-28 |  |  | COROMMANDEL | 2012-11-14 | 2012-11-13 | BUILD | 2012-11-15 | FALSE |  | 2763678 | 6439031 | Tairua Road Whangamata South |  |  | CELLSITE |  |  | 2015-04-07 | [12 empty] | 2012-11-28 | 2012-11-28 | 2012-03-05
0 | WKT | 1368 | WKT-011-013 | Thames | WKT-011-013-B | Thames Hospital | Thames Coromandel District | 2 | TIER_3 | ACTIVE | RT | DU | NOPOLE |  | STACK_A | COSITE | 18 | 18 | 1 | -37.1368 | 175.5436 |  |  |  |  | Fibre Optic |  | FALSE | FALSE |  |  | FALSE |  | 2012-03-23 | 2012-03-02 | 2012-03-28 | 2012-03-05 | 2012-03-22 | 2012-05-07 | 4 | 2012-03-30 | 2012-06-05 | 2012-06-27 | 2012-06-20 | 2012-08-31 | 2012-08-31 | 2 | 2012-08-31 | 2012-08-31 | DISCRETIONARY_FULL | 2012-06-22 | 2012-06-22 | 2012-07-27 | 2012-07-16 | 4 | 2012-07-31 | 2012-07-26 | 2012-08-14 |  | 2012-10-09 | 2012-10-11 | 1 |  | 2012-10-09 | 2012-10-11 | 2012-11-13 |  |  |  |  | 2012-10-15 | 2012-10-16 | 2012-11-07 | 2012-11-07 | 2012-11-05 | 2012-11-10 | 2012-11-09 | 2012-11-09 | 2012-11-07 | [6 empty] | 2012-11-12 | 2012-12-03 | 2012-11-15 | 2012-12-12 | 2012-11-30 | 2013-06-21 | 2013-06-21 | 18/03/13 - Snags to clear for FAN issue 21/06/13 - FAC signed |  | 2012-11-11 | 2012-10-06 | 2012-10-06 | 2012-10-22 | 2012-11-13 | 2012-10-26 | 2012-11-13 | 2012-11-13 | 2012-11-07 | 2012-11-19 | 2012-11-13 | 2012-03-09 | LOW | THAMES_TAURANGA | 2012-11-09 | 2012-11-07 | BUILD | 2012-11-05 | FALSE |  | 2736298 | 6448491 | Mackay Street Thames |  |  | CELLSITE | [15 empty] | 2012-11-26 | 2012-11-26 | 2012-03-05
0 | WKT | 1369 | WKT-011-014 |  |  |  | Thames Coromandel District |  | TIER_9
0 | WKT | 1370 | WKT-011-015 | Whangamata |  |  | Thames Coromandel District |  | TIER_9 | [22 empty] | FALSE | [75 empty] | COROMMANDEL
0 | WKT | 1371 | WKT-011-016 | Preece Point | WKT-011-016-A | Preece Point RBI | Thames Coromandel District | 22 | TIER_4 | ACTIVE | RBI | DF | NOPOLE |  |  | COLO |  |  |  | -36.7758 | 175.4962 |  | 2015-02-17 |  |  | Fibre Optic | WKT-016-023-B | FALSE | FALSE |  |  | FALSE |  | 2015-04-09 | 2015-04-09 | 2015-05-04 | 2015-04-22 | 2015-05-27 | 2015-05-19 | 2 | 2015-05-27 | 2015-06-17 | 2015-06-30 | 2015-05-20 | 2015-07-06 | 2015-06-23 |  | 2015-07-27 | 2015-07-23 | DISCRETIONARY_FULL | 2015-06-01 | 2015-05-19 | 2015-06-01 | 2015-05-19 | 1 | 2015-06-01 | 2015-05-19 | 2015-05-25 | 2015-05-21 | 2015-07-06 | 2015-06-11 | 1 |  | 2015-07-06 | 2015-06-11 | [5 empty] | 2015-07-27 | 2015-07-27 | 2015-08-14 | 2015-07-31 | 2015-07-27 | 2015-08-14 | 2015-07-31 | 2015-08-17 | 2015-07-30 | [7 empty] | 2015-08-17 | 2015-08-12 | 2015-08-28 | 2015-08-28 |  |  | 17.2.15- VF co-lo data pack requested, site search brief sent to Brad 3/3/15 - received data pack from VF - looks like 3 x antenna positions available. 10/3/15 - visiting site 12th March - have sent notification to LO 30/4/15 - RBI co-lo application submitted to VF 7/5/15 - Tender instruction given 10/7/15 - awaiting VF final approval 14/7/15 - have received final VF approval and approval to build | VNZ | [7 empty] | 2015-07-29 | 2015-07-29 | 2015-08-10 | 2015-08-07 |  |  |  | 2015-08-17 | 2015-07-30 | BUILD | 2015-07-27 | FALSE |  | 2733213 | 6488657 | 955 Preeces Point Rd, Coromandel |  |  | CELLSITE |  |  |  | ROAMING |  |  | 2015-05-04 |  | 2015-05-07 |  | 2015-04-01 |  | 2015-05-18 | 2015-07-17 | 2015-07-13 | 2015-08-17 |  | 2015-04-22
0 | WKT | 1372 | WKT-011-017 | Tairua Township |  |  | Thames Coromandel District |  | TIER_9 | [22 empty] | FALSE
0 | WKT | 1373 | WKT-011-018 | Opito Bay | WKT-011-018-A | new | Thames Coromandel District |  | TIER_5 | ACTIVE | [17 empty] | FALSE | FALSE |  |  | FALSE | [78 empty] | ONHOLD
0 | WKT | 1374 | WKT-012-001 |  |  |  | Hauraki District |  | TIER_9
0 | WKT | 1375 | WKT-012-002 | Mangatarata | WKT-012-002-A | Mangatarata | Hauraki District | 1 | TIER_3 | ACTIVE | GF | DU | T2 20 RH |  | STACK_A | COSITE |  |  | 1 | -37.2782 | 175.3853 |  |  |  |  | Microwave | WKT-011-013-B | FALSE | FALSE |  |  | FALSE | 2012-08-21 |  | 2012-04-02 |  | 2012-04-05 | 2012-05-25 | 2012-05-23 | 2 | 2012-05-25 | 2012-07-02 |  | 2009-01-21 |  | 2009-01-21 |  |  | 2009-01-21 | PERMITTED | 2012-06-18 | 2012-06-26 | 2012-08-03 | 2012-07-24 | 1 | 2012-08-10 | 2012-07-30 | 2012-08-14 |  | 2012-10-11 | 2012-10-26 | 1 |  | 2012-10-11 | 2012-10-26 | 2012-11-13 |  |  |  |  | 2012-10-25 | 2012-10-25 | 2012-11-20 | 2012-11-20 | 2012-11-19 | 2012-11-23 | 2012-11-25 | [8 empty] | 2012-11-25 | 2012-12-07 | 2012-12-05 | 2012-12-19 | 2012-12-12 | 2013-06-28 | 2013-06-28 | 11 snags open and FAC date moved out, Alan aiming to have snag free by 5 April so 10 working days allowed for FAN signoff. 28/06/13 - FAC signed |  | 2012-11-23 | 2012-10-06 | 2012-10-06 | 2012-10-22 | 2012-11-13 | 2012-10-23 | 2012-11-13 | 2012-11-21 | 2012-11-21 | 2012-11-26 | 2012-11-26 |  |  | AUCKLAND_HAMILTON_SH27 |  |  | BUILD | 2012-11-19 | FALSE |  | 2721815 | 6433198 | 3817 State Highway 2, Managatarata |  | Council Ref: 205.2012.00000058.001 - 30/07/2012 | CELLSITE | [15 empty] | 2012-12-03 | 2012-12-04 | 2008-10-28
0 | WKT | 1376 | WKT-012-003 | Paeroa | WKT-012-003-A | Paeroa, VNZ Co-Site | Hauraki District | 2 | TIER_3 | ACTIVE | GF | DU | T2 20 RH |  | STACK_A | COSITE | 20 | 20 | 1 | -37.3786 | 175.6938 |  |  |  |  | Fibre Optic |  | FALSE | FALSE |  |  | FALSE |  | 2012-05-11 | 2012-05-08 | 2012-05-22 | 2012-05-29 | 2012-07-06 | 2012-07-09 | 4 | 2012-07-06 | 2015-03-05 | 2012-07-20 | 2012-07-04 | 2012-09-28 | 2012-09-28 | 1 | 2012-09-28 | 2012-10-02 | DISCRETIONARY_RESTRICT | 2012-08-31 | 2012-09-05 | 2012-10-12 | 2012-10-11 | 2 | 2012-10-12 | 2012-11-08 | 2012-09-03 |  |  | 2012-10-26 | 3 |  |  | 2015-02-12 | 2012-11-12 |  |  |  |  | 2012-11-01 |  | 2012-12-03 |  | 2012-11-20 | 2012-12-07 | 2012-12-07 | 2012-11-27 | 2012-11-27 | [6 empty] | 2012-12-07 | 2012-12-14 | 2012-12-13 | 2013-01-15 | 2012-12-19 | 2013-05-24 | 2013-06-06 | 18/03/13 - Snags to clear and pSVP to pass before FAN issue 06/06/13 - FAC Signed |  | 2012-12-07 | 2012-10-06 | 2012-10-06 | 2012-11-13 | 2012-11-12 | 2012-10-15 | 2012-11-12 | 2012-11-23 | 2012-11-23 | 2012-12-11 | 2012-12-11 | 2012-03-09 | LOW | THAMES_TAURANGA | 2012-11-22 | 2012-11-22 | BUILD | 2012-11-22 | FALSE |  | 2748820 | 6421274 | Aorangi Rd, Paeroa |  |  | CELLSITE | [15 empty] | 2012-12-12 | 2012-12-12 | 2012-05-29
0 | WKT | 1377 | WKT-012-004 | Waihi | WKT-012-004-B | Waihi Greenfield | Hauraki District | 2 | TIER_3 | ACTIVE | GF | DU | T2 15 RFH |  | STACK_A | COSITE |  | 15 | 1 | -37.3962 | 175.8196 |  |  |  |  | Fibre Optic |  | FALSE | FALSE |  |  | FALSE |  | 2012-05-11 | 2012-05-08 | 2012-05-14 | 2012-05-14 | 2012-06-26 | 2012-06-25 | 1 | 2012-06-29 | 2012-06-25 | 2012-05-17 | 2012-05-17 | 2012-08-03 | 2012-07-27 | 1 | 2012-08-03 | 2012-10-01 | PERMITTED | 2012-07-05 | 2012-07-06 | 2012-08-09 | 2012-08-01 | 1 | 2012-08-14 | 2012-08-01 |  |  | 2012-09-06 | 2012-09-06 | 1 |  | 2012-09-06 | 2012-09-06 | 2012-10-02 |  |  |  |  | 2012-09-12 | 2012-09-12 | 2012-10-02 | 2012-10-02 | 2012-10-02 | 2012-10-09 | 2012-10-09 | 2012-10-08 | 2012-10-05 | [6 empty] | 2012-10-10 | 2012-10-26 | 2012-11-08 | 2012-11-13 | 2012-10-26 | 2013-05-17 | 2013-05-03 | 18/03/13 - Snags to clear for FAN issue 23/04/13 - FAN in sign off 03/05/13 - FAC signed |  | 2012-10-09 | 2012-10-02 | 2012-10-02 | 2012-10-02 | 2012-10-02 | 2012-10-02 | 2012-10-02 | 2012-10-04 | 2012-10-04 | 2012-10-12 | 2012-10-12 |  |  | THAMES_TAURANGA | 2012-10-08 | 2012-10-04 | BUILD | 2012-10-02 | FALSE |  | 2759892 | 6418976 | Rifle Range Road Waihi |  |  | CELLSITE | [15 empty] | 2012-10-18 | 2012-10-18 | 2012-05-14
0 | WKT | 1378 | WKT-012-005 | Waihi East | WKT-012-005-A | Waihi East - VF Co-lo | Hauraki District | 2 | TIER_3 | ACTIVE | COLO | DU | COLO |  | STACK_A | COLO |  |  | 1 | -37.367 | 175.8587 |  |  |  |  | Fibre Optic |  | FALSE | FALSE |  |  | FALSE |  | 2012-02-24 | 2012-02-21 | 2012-02-29 | 2012-02-22 | 2012-05-25 | 2012-05-24 | 2 | 2012-07-16 | 2012-07-13 | 2012-09-07 | 2012-08-31 | 2012-10-19 | 2012-10-16 |  | 2012-10-19 | 2012-10-16 | DISCRETIONARY_FULL | 2012-07-30 | 2012-07-30 | 2012-08-31 | 2012-08-24 | 2 | 2012-09-07 | 2012-08-30 | 2012-09-03 |  | 2012-10-12 | 2012-10-11 | 1 |  | 2012-10-12 | 2012-10-11 | 2012-11-13 |  |  |  |  | 2012-11-08 | 2012-11-07 | 2012-11-23 | 2012-11-25 | 2012-11-12 | 2012-11-30 | 2012-12-01 | 2012-11-16 | 2012-11-14 | [6 empty] | 2012-12-01 | 2012-12-14 | 2012-12-05 | 2013-01-15 | 2012-12-14 | 2013-05-31 | 2013-05-31 | 18/03/13 - Snags to clear and pSVP to pass before FAN issue 31/05/13 - FAC signed | VNZ | 2012-11-30 | 2012-10-06 | 2012-10-06 | 2012-11-15 | 2012-11-12 | 2012-10-17 | 2012-11-13 | 2012-11-26 | 2012-11-26 | 2012-12-03 | 2012-12-04 | 2012-03-09 | LOW | THAMES_TAURANGA | 2012-11-13 | 2012-11-14 | BUILD | 2012-11-12 | FALSE |  | 2763457 | 6422108 | Everitt Property Everitt Road Waihi |  |  | CELLSITE | [15 empty] | 2012-12-07 | 2012-12-07 | 2012-02-22
0 | WKT | 1379 | WKT-012-006 |  |  |  | Hauraki District |  | TIER_9
0 | WKT | 1380 | WKT-012-007 | Ngatea |  |  | Hauraki District |  | TIER_9 | [22 empty] | FALSE
0 | WKT | 1381 | WKT-012-008 | Kopu |  |  | Hauraki District |  | TIER_9 | [22 empty] | FALSE
0 | WKT | 1382 | WKT-012-009 | RBI - Turua | WKT-012-009-A | Turua RBI | Hauraki District | 25 | TIER_5 | ACTIVE | RBI | DF | COLO |  | STACK_A | COLO | 28 | 30 |  | -37.2712 | 175.5326 |  |  |  |  | Fibre Optic | WKT-016-044-A | FALSE | FALSE |  |  | FALSE |  | 2015-10-14 | 2015-10-15 | 2015-10-20 | 2015-10-20 | 2015-10-21 | 2015-11-02 | 1 | 2015-10-22 | 2015-11-02 | 2015-11-25 | 2015-11-24 | 2015-11-27 | 2015-11-26 |  | 2016-02-03 | 2016-02-10 | PERMITTED | 2015-11-25 | 2015-11-26 | 2015-11-30 | 2015-11-27 | 1 | 2015-12-01 | 2015-12-03 | 2015-10-23 | 2015-10-30 | 2015-10-27 | 2015-10-30 | 2 |  | 2015-10-29 | 2015-12-07 | [5 empty] | 2016-02-22 |  | 2016-02-26 |  |  | 2016-02-26 |  | 2016-02-26 |  | 2016-02-10 |  | 2016-02-10 |  | 2016-02-05 |  |  | 2016-03-11 | [5 empty] | 8 Oct: Site data pack received 16 Oct: VF co-lo & Spark co-site lodged & Pre-qual requested. CD1 requested. 19 Oct: Letter to planner drafted. Will be sent when VF advises LO of co-lo request. 22 Oct: LO letter drafted to send when prelim VF approval granted. 29 Oct: CD rev1 issued for review 8 Dec: Waiting on build quote so I can raise PO6 5 Dec: ATN ordered, RFS set, Antenna quote requested. 12 Jan: Waiting on ETA for Huawei antennas 3 Feb: PO6 issued. Waiting on antennas. Construction start 22 Feb. RFS 23 Feb 10 Feb: CX Config raised for 17th Feb | VNZ | [9 empty] | 2016-03-04 |  |  |  |  | 2016-02-23 |  | BUILD | 2016-02-22 | FALSE |  | 2734888 | 6433602 | 58 Orchard East Road |  | Letter to confirm compliance sent to Council - 25/01/2016 | CELLSITE |  |  |  | ROAMING |  |  | 2016-02-10 | 2015-11-23 | 2015-11-25 | 2015-10-16 | 2015-10-16 | 2015-11-18 | 2015-11-20 | 2015-12-23 | 2016-01-12 |  |  | 2015-10-29
0 | WKT | 1383 | WKT-012-010 | RBI - Karangahake | WKT-012-010-A | Karangahake RBI | Hauraki District |  | RBI | ACTIVE | [17 empty] | FALSE | FALSE |  |  | FALSE
0 | WKT | 1384 | WKT-012-011 | Kaihere | WKT-012-011-B | Kaihere | Hauraki District | 1 | TIER_3 | ACTIVE | GF | DU | T2 20 RH |  | STACK_A | COSITE |  |  | 1 | -37.3605 | 175.4163 |  |  |  |  | Microwave | WKT-012-002-A | FALSE | FALSE |  |  | FALSE | 2012-08-21 | 2012-03-22 | 2012-03-22 | 2012-03-27 | 2012-03-27 | 2012-04-26 | 2012-05-04 | 2 | 2012-05-30 | 2012-07-02 | 2012-06-18 | 2012-05-23 | 2012-08-03 | 2012-08-03 |  | 2012-08-10 | 2012-08-03 | PERMITTED | 2012-06-18 | 2012-06-26 | 2012-08-03 | 2012-07-24 | 1 | 2012-08-10 | 2012-07-30 | 2012-08-16 |  | 2012-10-11 | 2012-10-18 | 1 |  | 2012-10-11 | 2012-10-18 | 2012-11-12 |  |  |  |  | 2012-10-23 | 2012-10-23 | 2012-11-16 | 2012-11-16 | 2012-11-13 | 2012-11-24 | 2012-11-24 | [8 empty] | 2012-11-25 | 2012-12-07 | 2012-12-05 | 2012-12-19 | 2012-12-12 | 2013-07-12 | 2013-06-28 | 8 snags open and not addressed, reforecasted. 09/04/13 - No FAN yest. FAC reforecasted 28/06/13 - FAC signed |  | 2012-11-24 | 2012-10-06 | 2012-10-06 | 2012-10-15 | 2012-11-12 | 2012-10-24 | 2012-11-12 | 2012-11-20 | 2012-11-20 | 2012-11-28 | 2012-12-03 |  |  | AUCKLAND_HAMILTON_SH27 |  |  | BUILD | 2012-11-13 | FALSE |  | 2724312 | 6423987 | 1046 SH27 Ngatea RD1 Waikato |  | Council Ref: 205.2012.00000056.001 - 30/07/2012 | CELLSITE | [15 empty] | 2012-12-03 | 2012-12-04 | 2012-03-27
0 | WKT | 1385 | WKT-012-012 | Whiritoa South | WKT-012-012-A | unknown | Hauraki District | 24 | TIER_9 | ACTIVE |  | DF |  |  | STACK_A | [12 empty] | FALSE | FALSE |  |  | FALSE |  | 2015-11-03 | [76 empty] | BUILD |  | FALSE | [6 empty] | CELLSITE |  |  |  | ROAMING
0 | WKT | 1386 | WKT-013-001 |  |  |  | Waikato District |  | TIER_9
0 | WKT | 1387 | WKT-013-002 | Te Kauwhata |  |  | Waikato District |  | TIER_9 | [22 empty] | FALSE
0 | WKT | 1388 | WKT-013-004 | Te Kauwhata Straights | WKT-013-004-A | VF Co-lo Te Kauwhata Straights | Waikato District | 22 | TIER_4 | ACTIVE | COLO | DU | COLO |  | STACK_A | COLO | 16.6 | 18 |  | -37.4142 | 175.1309 |  |  |  |  | Fibre Optic | WKT-016-023-B | FALSE | FALSE |  |  | FALSE |  | 2012-03-07 | 2012-03-07 | 2012-03-13 | 2012-03-13 | 2012-04-18 | 2012-04-27 | 5 | 2012-06-01 | 2015-08-14 | 2015-04-30 | 2015-04-15 | 2016-02-29 |  |  | 2016-02-29 |  | NON_COMPLYING_FULL | 2012-06-08 | 2012-06-15 | 2012-07-27 | 2012-07-13 | 2 | 2012-07-20 | 2012-07-19 | 2015-06-15 | 2015-04-20 | 2015-05-25 | 2015-05-29 | 1 |  | 2015-05-25 | 2015-05-29 |  |  |  | 2016-01-13 |  | 2016-03-07 |  | 2016-03-21 |  |  | 2016-03-28 |  | 2016-03-15 | [8 empty] | 2016-04-25 | [5 empty] | Prelim approval received and lease terms agreed with LO. Linking dependant on Huntly East AP/business to advise if "LO hold" letters ready to be sent or not..... 29/1/15 - back in programme, check design ok and re-activate/resend VF co-lo application 23.2.15 - up rev red lines on plans with design - VF Co-lo application ready to submit when plans issued 27.2.15 - VF co-lo application submitted 15.4.15 - Prelim approval received 20.4.14 - CDI issued 7/5/15 - Tender instruction issued to Huawei | VNZ | [9 empty] | 2016-04-11 |  |  |  | AUCKLAND_HAMILTON_SH1_S | 2016-03-15 |  | BUILD |  | TRUE | 2016-01-25 | 2698892 | 6418685 | 2481 State Highway 1, Te Kauwhata Straights, Waikato |  | Council Ref LUC0270/12. - 19/07/2012 | CELLSITE | WIPACTIVE |  |  | ROAMING |  |  | 2015-05-13 | 2015-06-05 | 2015-05-07 |  | 2015-04-13 | 2015-04-30 | 2015-04-22 | 2015-07-28 | 2015-07-13 |  |  | 2012-03-13
0 | WKT | 1389 | WKT-013-006 | Huntly East | WKT-013-006-A | Huntly East | Waikato District | 1 | TIER_3 | ACTIVE | GF | DU | P8 |  |  | COSITE | 10 | 10 | 1 | -37.5158 | 175.2253 |  |  |  |  | Microwave | WKT-015-001-A | FALSE | FALSE |  |  | FALSE |  | 2012-07-04 | 2012-07-04 | 2012-07-09 | 2012-07-11 | 2012-08-10 | 2012-08-06 | 4 | 2012-08-10 | 2013-12-13 | 2012-08-24 | 2012-08-22 | 2012-11-22 | 2012-11-30 |  | 2012-11-30 | 2012-11-30 | DISCRETIONARY_RESTRICT | 2012-10-26 | 2012-10-31 | 2013-02-05 | 2013-02-05 | 2 | 2013-02-12 | 2013-02-14 |  |  |  | 2013-05-02 | 1 |  |  | 2013-05-02 | [5 empty] | 2013-07-01 | 2013-06-25 | 2013-08-06 | 2013-08-06 | 2013-08-15 | 2013-08-19 | 2013-08-24 | [8 empty] | 2013-08-24 | 2013-08-23 | 2013-08-29 | 2013-08-30 | 2013-08-30 | 2013-11-13 | 2013-12-18 | No rights for fibre. 6 month commencement and payment tied in for 6 year terms LO to divert existing access track, payment requierd. VF and Police co-site approval, also Police approval to share power. Visual assessment required Council extension agreed until 22 January. 05/08/13 - Power on 15 August. Rest of site will be completed by then. |  | 2013-08-22 | [6 empty] | 2013-08-14 | 2013-08-19 | 2013-08-19 | 2013-08-24 |  |  | AUCKLAND_HAMILTON_SH1_S |  |  | BUILD | 2013-08-06 | FALSE |  | 2706962 | 6407208 | 747-763 Rutherford Rd, Taupiri |  | Council Ref LUC0156/13 and being processed by Opus - 12/11/2012 | CELLSITE |  |  | 2015-10-15 | [12 empty] | 2013-08-28 | 2013-08-27 | 2012-07-11
0 | WKT | 1390 | WKT-013-007 | Huntly | WKT-013-007-F | Huntly | Waikato District | 1 | TIER_3 | ACTIVE | GF | DU | T2 20 RF |  |  | COSITE |  |  | 1 | -37.5824 | 175.1524 |  |  |  |  | Fibre Optic | WKT-016-023-B | FALSE | FALSE |  |  | FALSE |  | 2012-03-07 | 2012-03-07 | 2012-03-13 | 2012-03-13 | 2012-04-23 | 2012-04-26 | 4 | 2012-06-11 | 2013-06-11 | 2012-08-24 | 2012-08-22 | 2012-11-16 | 2012-11-22 | 2 | 2012-11-16 | 2012-11-22 | DISCRETIONARY_RESTRICT | 2012-08-17 | 2012-08-20 | 2012-09-28 | 2012-09-20 | 2 | 2012-10-05 | 2012-09-25 |  |  |  | 2013-05-02 | 1 |  |  | 2013-05-02 |  |  |  | 2013-04-24 |  | 2013-06-05 | 2013-06-05 | 2013-07-11 | 2013-07-11 | 2013-07-15 | 2013-08-14 | 2013-08-14 | [8 empty] | 2013-08-14 | 2013-08-15 | 2013-08-29 | 2013-08-30 | 2013-08-30 | 2013-11-13 | 2013-12-06 | VF and TNZ co-sites approved HAIL activity site - excavated soil to be removed. 15/6/13 - civil works sarted 06/12/13 - FAC signed |  | 2013-08-14 | [6 empty] | 2013-08-13 | 2013-08-13 | 2013-08-12 | 2013-08-16 |  |  | AUCKLAND_HAMILTON_SH1_S | 2013-07-12 | 2013-07-12 | BUILD | 2013-07-15 | TRUE | 2013-04-24 | 2700333 | 6399980 | 208 Riverview Rd Huntly Waikato |  | Council Ref LUC0062/13 - 25/09/2012 | CELLSITE |  |  | 2015-10-15 | [12 empty] | 2013-08-20 | 2013-08-16 | 2012-03-13
0 | WKT | 1391 | WKT-013-008 | Whatawhata | WKT-013-008-D | VF Co-lo Whatawhata | Waikato District | 1 | TIER_3 | ACTIVE | COLO | DU | COLO |  | STACK_A | COLO |  |  | 1 | -37.788 | 175.1686 |  | 2011-06-01 |  | 2011-06-01 | Fibre Optic | WKT-016-023-B | TRUE | TRUE | 2011-06-01 |  | TRUE |  | 2011-07-15 | 2011-07-15 | 2011-07-08 | 2011-07-08 | 2011-07-26 | 2011-07-25 | 1 | 2011-07-26 | 2011-07-25 | 2011-08-12 | 2011-08-04 | 2011-12-09 | 2012-02-08 |  | 2011-12-16 | 2012-02-08 | DISCRETIONARY_RESTRICT | 2011-08-05 | 2011-08-03 | 2011-11-11 | 2011-11-10 | 1 | 2011-11-17 | 2011-11-14 |  |  | 2012-04-19 | 2012-04-20 | 2 |  | 2012-04-19 | 2012-05-14 | 2012-05-24 |  |  |  |  | 2012-05-17 | 2012-05-08 | 2012-05-29 | 2012-05-11 | 2012-05-23 | 2012-06-01 | 2012-06-05 | 2012-06-10 | 2012-06-10 | [6 empty] | 2012-06-01 |  | 2012-06-12 | 2012-06-23 | 2012-06-21 | 2013-05-10 | 2013-05-01 | 6 open snags. VF closure documentation and GHD drawings. Chorus to re-install fibre boxes. Genny inlet hatch also on tracker as open, do we agree this can now be closed as a Huawei snag? 23/04/13 - FAC in sign off 01/05/13 - FAC signed | VNZ | 2012-06-02 | 2012-05-01 | 2012-05-01 | 2012-05-24 | 2012-05-24 | 2012-05-25 | 2012-05-24 | 2012-05-30 | 2012-05-28 |  | 2012-06-12 |  |  | AUCKLAND_HAMILTON_SH1_N | 2012-06-10 | 2012-06-10 | BUILD | 2012-05-22 | FALSE |  | 2701199 | 6377140 | 111 Cemetery Road Whatawhata Hamilton |  | Council Ref: LUC0031/12 - 14/11/2011 | CELLSITE | [15 empty] | 2012-06-11 | 2012-06-12 | 2011-07-08
0 | WKT | 1392 | WKT-013-009 | Raglan | WKT-013-009-C | Raglan | Waikato District | 6 | 2014 | ACTIVE | GF | DU | T2 25 RH | Grey | STACK_A | COSITE |  |  | 1 | -37.8299 | 174.8502 |  |  |  |  | Microwave | WKT-013-032-A | FALSE | FALSE |  |  | FALSE |  | 2012-06-14 | 2012-05-09 | 2012-06-20 | 2012-06-18 | 2012-07-20 | 2012-08-02 | 1 | 2012-07-20 | 2012-08-02 | 2012-08-20 | 2012-08-16 | 2012-09-28 | 2012-09-21 | 1 | 2012-10-05 | 2012-11-14 | DISCRETIONARY_RESTRICT | 2012-09-27 | 2012-10-01 | 2012-11-07 | 2012-11-05 | 1 | 2012-11-14 | 2012-11-12 | 2014-05-16 |  | 2014-06-27 | 2014-06-23 | 1 |  | 2014-06-27 | 2014-06-23 | [5 empty] | 2014-07-21 | 2014-07-21 | 2014-08-15 | 2014-08-22 | 2014-08-22 |  | 2014-09-01 |  | 2014-09-01 | [7 empty] | 2014-09-26 | 2014-09-22 |  |  |  |  | VF & TNZ co-sites approved Linking to Raglan Telecom exchange Site Half integrated. Huge issues. Had Transfield send Gary Ward to assist. Still unable to get the site up. 15.09.14 Sending Rudolph down to try on 16.09.2014. | [10 empty] | 2014-09-16 | 2014-09-16 |  |  | RAGLAN |  |  | BUILD |  | FALSE |  | 2673070 | 6373131 | 430 Te Hutewai Road Waikato |  | Council Ref LUC0113/13 - 12/11/2012 | CELLSITE | [7 empty] | 2014-07-14 | 2014-07-14 | [8 empty] | 2012-06-18
0 | WKT | 1393 | WKT-013-010 | Taupiri | WKT-013-010-A | Taupiri Greenfield | Waikato District | 22 | TIER_4 | ACTIVE | GF | DU | T2 15 RFH |  |  | COSITE | 10 | 10 | 1 | -37.6148 | 175.1761 |  |  |  |  | Microwave | WKT-016-023-B | FALSE | FALSE |  |  | FALSE |  | 2012-03-07 | 2012-03-07 | 2012-03-13 | 2012-03-13 | 2012-03-27 | 2008-10-20 | 3 | 2012-03-28 | 2012-04-17 | 2009-03-16 | 2009-03-16 | 2009-03-16 | 2009-03-16 | 2 | 2012-06-29 | 2012-08-22 | DISCRETIONARY_RESTRICT | 2012-05-09 | 2012-05-16 | 2012-07-05 | 2012-06-15 | 3 | 2012-07-12 | 2012-06-15 | 2015-01-21 | 2015-01-21 | 2015-03-13 | 2015-03-23 | 1 |  | 2015-03-20 | 2015-03-23 | [5 empty] | 2015-05-11 | 2015-05-19 | 2015-07-24 | 2015-07-24 | 2015-06-24 | 2015-07-10 | 2015-07-16 | [8 empty] | 2015-07-30 | 2015-08-14 | 2015-08-06 |  | 2015-08-28 |  |  | Historic lease still active. New plans singed off by LO. VF Co-site approved, SFA for power if required 28/1/15 - CDI issued 21/1/15 - fibre feasability underway 9/3/15 - cabs & TX ordered, pole order underway awaiting PO approval, antenna order with Huawei 7/5/15 - PO6 for build approved and sent to Huawei 10/7/15 - awaiting VF decision on power share |  | 2015-07-08 | [8 empty] | 2015-08-03 | 2015-07-29 |  |  | AUCKLAND_HAMILTON_SH1_S |  |  | BUILD | 2015-06-26 | FALSE |  | 2702342 | 6396334 | 698 Hakarimata Rd, Taupiri |  | Council Ref LUC0246/12 - 12/06/2012 | CELLSITE |  |  |  | ROAMING |  | 2015-03-13 | 2015-03-09 | 2015-03-26 | 2015-03-30 | [5 empty] | 2015-05-07 | 2015-07-24 |  | 2012-03-13
0 | WKT | 1394 | WKT-013-011 |  |  |  | Waikato District |  | TIER_9
0 | WKT | 1395 | WKT-013-012 | Te Kowhai | WKT-013-012-A | Te Kowhai Greenfiled | Waikato District |  | TIER_5 | ACTIVE | GF | DU | T2 25 RF |  | STACK_A | STANDALONE | 25 | 25 | 1 | -37.7035 | 175.1981 |  |  |  |  | Microwave | WKT-016-023-B | FALSE | FALSE |  |  | FALSE |  | 2012-06-14 | 2012-06-14 | 2012-06-18 | 2012-06-18 | 2012-07-16 | 2012-08-07 | 2 | 2012-07-16 | 2012-08-29 | 2012-08-31 | 2012-09-12 | 2012-11-09 | 2012-11-08 | 1 | 2012-11-09 | 2012-11-08 | DISCRETIONARY_FULL | 2012-10-02 | 2012-10-05 | 2012-10-31 | 2012-11-06 | 2 | 2012-11-02 | 2012-11-12 | 2015-09-23 | 2015-09-23 | [33 empty] | HAIL activity site - excavated soil to be removed. $5k one-off payment on commencement, 12 months. 26/8/15 - TX to be confirmed then CDI can be issued. Lease is in holding rent - will commence to full rent when we schedule geotech. 23/9/15 - CDI issued | [14 empty] | AUCKLAND_HAMILTON_SH1_S |  |  | ONHOLD |  | TRUE |  | 2704035 | 6386444 | 6126 SH1 Horotiu |  | Council Ref LUC0119/13 - 12/11/2012 | CELLSITE | WIPACTIVE | [16 empty] | 2008-07-25
0 | WKT | 1396 | WKT-013-013 | Gordonton | WKT-013-013-D | VF Co-lo Gordonton | Waikato District | 1 | TIER_3 | ACTIVE | COLO | DU | COLO |  | STACK_A | COLO |  |  | 1 | -37.6844 | 175.2807 |  | 2011-06-01 |  | 2011-06-01 | Fibre Optic | WKT-016-023-B | TRUE | TRUE | 2011-06-01 |  | TRUE |  | 2011-07-15 | 2011-07-08 | 2011-07-08 | 2011-07-08 | 2011-07-26 | 2011-07-25 | 1 | 2011-07-26 | 2011-07-25 | 2011-08-23 | 2011-08-25 | 2011-09-30 | 2011-08-23 |  | 2011-12-01 | 2011-10-10 | DISCRETIONARY_RESTRICT | 2011-08-04 | 2011-08-02 | 2011-09-09 | 2011-09-06 | 1 | 2011-09-13 | 2011-09-09 |  |  | 2012-04-19 | 2012-04-20 | 2 |  | 2012-04-19 | 2013-05-03 | 2012-05-24 |  |  |  |  | 2012-05-21 | 2012-05-15 | 2012-05-22 | 2012-05-24 | 2012-05-26 | 2012-06-04 | 2012-06-01 | 2012-06-10 | 2012-06-10 | [6 empty] | 2012-06-05 | 2012-06-12 | 2012-06-12 | 2012-06-23 | 2012-06-21 | 2013-05-17 | 2013-05-16 | 6 open snags. VF closure documentation and GHD drawings. Chorus to re-install fibre boxes. Genny inlet hatch also on tracker as open, do we agree this can now be closed as a Huawei snag? 23/04/13 - FAN in sign off - still need AB 16/05/13 - FAC signed | VNZ | 2012-06-04 | 2012-05-24 | 2012-05-24 | 2012-05-24 | 2012-05-24 | 2012-05-16 | 2012-05-24 | 2012-06-04 | 2012-05-25 |  | 2012-06-12 |  |  | AUCKLAND_HAMILTON_SH1_N | 2012-06-10 | 2012-06-10 | BUILD | 2012-05-29 | FALSE |  | 2711371 | 6388381 | Ballard Prop. Ballard Rd, Gordonton |  | Council Ref: LUC0027/12 - 06/09/2011 | CELLSITE | [15 empty] | 2012-06-11 | 2012-06-12 | 2011-07-08
0 | WKT | 1397 | WKT-013-014 | Matangi | WKT-013-014-A | Matangi | Waikato District | 22 | TIER_5 | ACTIVE | RT | DF | NOPOLE |  | INLINE | COSITE | 25 | 25 |  | -37.8047 | 175.3961 |  |  |  |  | Fibre Optic | WKT-016-044-A | FALSE | FALSE |  |  | FALSE |  | 2015-09-21 | 2015-09-21 | 2015-09-24 | 2015-09-24 | 2015-10-19 | 2015-10-14 | 1 | 2015-10-23 | 2015-10-14 | 2015-11-30 | 2015-11-03 | 2015-12-21 | 2015-12-15 |  | 2016-02-22 |  | DISCRETIONARY_FULL | 2015-11-16 | 2015-11-16 | 2015-12-21 | 2015-12-11 | 1 | 2015-12-21 | 2015-12-11 | 2015-11-16 | 2015-11-05 | 2016-01-22 | 2016-01-22 | 1 |  | 2016-01-25 | 2016-01-22 | [5 empty] | 2016-03-30 |  | 2016-04-27 |  |  | 2016-05-12 |  | 2016-03-31 | [8 empty] | 2016-06-01 | [5 empty] | 26/8/15 - Tim confirmed RT site is the active one to persue - Matt to contact LO 11/1/16 - VF & Spark co-site applications submitted | [10 empty] | 2016-05-23 |  |  |  |  | 2016-03-31 |  | BUILD |  | TRUE | 2016-02-16 | 2721179 | 6374762 | Cnr Good St & Tauwhare Rd, Matangi |  |  | CELLSITE | WIPACTIVE |  |  | ROAMING |  |  | 2016-01-14 | 2016-02-16 |  |  | 2015-11-19 |  | 2015-12-14 | 2016-03-15 |  |  |  | 2015-09-23
0 | WKT | 1398 | WKT-013-015 | Tamahere | WKT-013-015-F | GF | Waikato District | 22 | TIER_5 | ACTIVE | GF | DU | T2 20 UF |  | STACK_A | STANDALONE | 19.5 | 20 | 1 | -37.8297 | 175.3582 |  |  |  |  | Fibre Optic | WKT-016-023-B | FALSE | FALSE |  |  | FALSE |  | 2012-03-08 | 2012-03-08 | 2012-03-13 | 2012-03-13 | 2012-04-23 | 2012-05-07 | 2 | 2012-05-25 | 2012-07-02 | 2012-05-28 | 2012-05-23 | 2012-06-29 | 2012-06-15 |  | 2012-07-02 | 2012-07-02 | DISCRETIONARY_RESTRICT | 2012-05-14 | 2012-05-21 | 2012-07-09 | 2012-06-26 | 1 | 2012-07-18 | 2012-06-29 | 2015-09-23 | 2015-09-23 | 2015-11-30 | 2015-12-01 | 1 |  | 2015-12-04 | 2015-12-01 |  |  |  | 2016-01-13 |  | 2016-02-15 |  | 2016-03-14 |  |  | 2016-03-31 |  | 2016-02-29 | [8 empty] | 2016-04-25 | [5 empty] | SSLU completed Boundary survey completed and slightly off fence line. 23/9/15 - CDI issued to Ritchie. | [10 empty] | 2016-04-11 |  |  |  | HAMILTON_ROTORUA | 2016-02-29 |  | BUILD |  | TRUE | 2016-01-11 | 2717768 | 6372074 | 25 Tamahere Drive Tamahere |  | Council Ref LUC2053/12 - 12/06/2012 | CELLSITE | WIPACTIVE |  |  | ROAMING |  | 2015-12-01 | 2016-01-14 | 2015-12-09 | 2015-12-08 |  |  |  | 2015-11-25 | 2016-02-01 | 2016-02-04 |  |  | 2012-03-13
0 | WKT | 1399 | WKT-013-016 | Meremere |  |  | Waikato District |  | TIER_9 | [22 empty] | FALSE
0 | WKT | 1400 | WKT-013-017 | Meremere Straights |  |  | Waikato District |  | TIER_9 | [22 empty] | FALSE
0 | WKT | 1401 | WKT-013-018 | Ngaruawahia | WKT-013-018-A | VF Co-lo Ngaruawahia | Waikato District | 22 | TIER_4 | ACTIVE | COLO | DU | COLO |  | STACK_A | COLO |  |  | 1 | -37.6617 | 175.1396 |  |  |  |  | Fibre Optic | WKT-016-044-A | FALSE | FALSE |  |  | FALSE |  | 2014-11-27 | 2014-11-19 | 2014-12-01 | 2014-11-18 | 2014-11-28 | 2012-04-26 | 5 | 2014-12-09 | 2015-04-30 | 2015-04-14 | 2015-02-19 | 2016-03-14 |  |  | 2016-03-21 |  | DISCRETIONARY_RESTRICT | 2015-04-30 | 2015-05-01 | 2015-06-11 | 2015-05-29 | 5 | 2015-06-18 | 2015-06-18 | 2015-05-04 | 2015-02-26 | 2015-05-08 | 2015-05-20 | 1 |  | 2015-05-15 | 2015-05-20 | [5 empty] | 2016-03-21 |  | 2016-04-11 |  |  | 2016-04-25 |  | 2016-03-15 | [8 empty] | 2016-05-18 | [5 empty] | Prelim approval received 9 July 2012 AP/business to advise if "LO hold" letters ready to be sent or not..... awaiting VF datapack - 30/10/14 16/1/15 - VF co-lo applicaiton submitted 16/12/14, awaiting feedback 19/2/15 - received prelim approval 25.2.15 - Brad to approach LO regarding sub-lease - ready to submit CDI & RC 3/3/15 - lease executed will take some time - hold RC submission until terms agreed, CDI issued - GHD to get to Rev0 then hold until pole information etc is available and lease terms agreed. If VF don't have pole info we'll have to send rigger to site for measure ups. 9/3/15 - only TX equipment on order - PO still to be approved. | VNZ | [9 empty] | 2016-05-09 |  |  |  | AUCKLAND_HAMILTON_SH1_S | 2016-03-15 |  | BUILD |  | FALSE |  | 2698994 | 6391207 | Ngaruawahia Brownlee Ave Waikato |  |  | CELLSITE | WIPACTIVE |  |  | ROAMING |  |  | 2015-04-24 | 2015-06-10 | 2015-05-07 |  | 2015-06-11 |  | 2015-07-22 | 2015-08-24 | 2015-08-12 |  |  | 2014-11-18
0 | WKT | 1402 | WKT-013-019 | Ohinewai |  |  | Waikato District |  | TIER_9 | [22 empty] | FALSE
0 | WKT | 1403 | WKT-013-020 | Maramarua | WKT-013-020-B | Maramarua | Waikato District | 1 | TIER_3 | ACTIVE | GF | DU | T2 25 RH |  | STACK_A | COSITE |  |  | 1 | -37.2374 | 175.3009 |  |  |  |  | Microwave | WKT-012-002-A | FALSE | FALSE |  |  | FALSE |  | 2012-03-22 | 2012-03-22 | 2012-03-27 | 2012-03-27 | 2012-05-01 | 2012-05-09 | 2 | 2012-05-01 | 2012-07-06 | 2012-05-28 | 2012-05-23 | 2012-09-07 | 2012-09-13 | 1 | 2012-09-07 | 2012-09-13 | DISCRETIONARY_RESTRICT | 2012-07-23 | 2012-08-03 | 2012-09-05 | 2012-09-03 | 2 | 2012-09-07 | 2012-09-07 | 2012-08-17 |  | 2012-10-12 | 2012-10-25 | 1 |  | 2012-10-12 | 2012-10-25 | 2012-11-12 |  |  |  |  | 2012-10-30 | 2012-10-30 | 2012-11-20 | 2012-11-20 | 2012-11-14 | 2012-11-27 | 2012-11-27 | [8 empty] | 2012-11-29 | 2012-12-07 | 2012-12-06 | 2012-12-19 | 2012-12-12 | 2013-07-05 | 2013-07-09 | 11 snags open and not addressed, reforecasted. 01/05/13 - No FAN yet. FAC reforecasted 09/07/13 - FAC signed |  | 2012-11-29 | 2012-10-06 | 2012-10-06 | 2012-10-29 | 2012-11-12 | 2012-10-19 | 2012-11-12 | 2012-12-05 | 2012-12-05 | 2012-11-30 | 2012-12-03 |  |  | AUCKLAND_HAMILTON_SH27 |  |  | BUILD | 2012-11-15 | FALSE |  | 2714452 | 6437920 | 227 Rataroa Road Miranda Maramarua |  | Site is within Ridgeline Policy Area - 06/08/2012 Council Ref LUC0049/13. - 07/09/2012 | CELLSITE | [15 empty] | 2012-12-07 | 2012-12-07 | 2012-03-27
0 | WKT | 1404 | WKT-013-021 | RBI - Newstead Central |  |  | Waikato District |  | TIER_9 | [22 empty] | FALSE | [75 empty] | AUCKLAND_HAMILTON_SH27
0 | WKT | 1405 | WKT-013-023 | Tamahere East (SH1) |  |  | Waikato District | 1 | TIER_3 | [22 empty] | FALSE | [75 empty] | HAMILTON_ROTORUA
0 | WKT | 1406 | WKT-013-024 | RBI - Eureka | WKT-013-024-A | Eureka | Waikato District | 1 | TIER_3 | ACTIVE | RBI | DU | RBILATTICE |  | STACK_A | COLO |  |  | 1 | -37.7167 | 175.4457 |  |  |  |  | Fibre Optic | WKT-016-023-B | FALSE | FALSE |  |  | FALSE |  |  | 2012-02-13 |  | 2012-02-13 |  | 2012-02-13 | 1 | 2012-02-13 | 2012-02-13 |  | 2012-02-13 |  | 2012-02-13 |  |  | 2013-04-02 | PERMITTED | 2012-02-13 | 2012-02-13 | 2012-02-13 | 2012-02-13 | 1 | 2012-02-13 | 2012-02-13 | 2012-06-05 | 2012-06-05 | 2012-06-05 | 2012-06-05 | 1 |  | 2012-06-05 | 2012-06-05 | [5 empty] | 2012-08-22 | 2012-08-16 | 2012-08-24 | 2012-08-16 | 2012-08-16 | 2012-09-12 | 2012-09-12 | 2012-08-27 | 2012-08-24 | [6 empty] | 2012-09-17 | 2012-10-03 | 2012-09-25 | 2012-10-08 | 2012-09-26 | 2013-04-17 | 2013-04-10 | 1 snag remaining for disimilar metals - do we have resolution to close this snag? VF closure documentation - waiting for Mystery creek test to be approved by VF before submitting the other. 09/04/13 - FAN in circulation. NOC, TX, Ops and Vicente to sign 10/04/13 - FAC signed | VNZ | 2012-09-17 | 2012-08-01 | 2012-08-01 | 2012-08-31 | 2012-08-31 |  |  | 2012-09-03 | 2012-08-30 | 2012-09-14 | 2012-09-21 |  |  | RBI | 2012-08-24 | 2012-08-24 | BUILD | 2012-08-29 | FALSE |  | 2725818 | 6384402 | 1681 SH26/Morrinsville road Eureka Hamilton |  | RBI SIte - 28/06/2012 | CELLSITE | [15 empty] | 2012-09-21 | 2012-09-20 | 2012-02-13
0 | WKT | 1407 | WKT-013-025 | RBI - Puketaha | WKT-013-025-A | Puketaha | Waikato District | 1 | TIER_3 | ACTIVE | RBI | DU | RBILATTICE |  | STACK_A | COLO |  |  | 1 | -37.7123 | 175.3358 |  |  |  |  | Fibre Optic | WKT-016-023-B | FALSE | FALSE |  |  | FALSE |  |  | 2012-02-13 |  | 2012-02-13 |  | 2011-11-04 | 1 | 2012-02-13 | 2011-11-04 |  | 2012-02-13 |  | 2012-02-13 |  |  | 2012-02-13 |  |  | 2012-02-13 | 2012-02-13 | 2012-02-13 | 1 |  | 2012-02-13 | 2012-06-05 | 2012-06-05 | 2012-06-05 | 2012-06-05 | 1 |  | 2012-06-05 | 2012-06-05 | [5 empty] | 2012-08-22 | 2012-08-21 | 2012-08-24 | 2012-08-23 | 2012-08-23 | 2012-09-20 | 2012-09-11 | 2012-08-27 | 2012-08-24 | [6 empty] | 2012-09-21 | 2012-10-03 | 2012-10-03 | 2012-10-17 | 2012-10-03 | 2013-07-12 | 2013-08-01 | Snag remaining for disimilar metals - do we have resolution to close this snag? ALso ALD alarm snag to be closed by Huawei. VF closure documentation - waiting for Mystery creek test to be approved by VF before submitting the other. 19/04/13 - FAN in sign off 29/04/13 - ALD Alarms issued to be resovled sign off halted 01/08/13 - FAC signed | VNZ | 2012-09-21 | 2012-07-02 | 2012-08-07 | 2012-08-24 | 2012-09-11 |  |  | 2012-09-03 | 2012-08-30 | 2012-09-14 | 2012-09-26 |  |  | RBI | 2012-08-24 | 2012-08-24 | BUILD | 2012-08-23 | FALSE |  | 2716146 | 6385151 | 601 Puketaha Road Puketaha Hamilton |  |  | CELLSITE | [15 empty] | 2012-09-27 | 2012-09-26 | 2012-02-13
0 | WKT | 1408 | WKT-013-026 | RBI - Te Kowhai West | WKT-013-026-A | Te Kowhai West - RBI | Waikato District | 25 | TIER_5 | ACTIVE | RBI | DF | RBI Pole |  | STACK_A | COLO | 23 | 25 |  | -37.736 | 175.1447 |  |  |  |  | Fibre Optic | WKT-016-044-A | FALSE | FALSE |  |  | FALSE |  | 2015-10-16 | 2015-10-16 | 2015-10-21 | 2015-10-21 | 2015-10-21 | 2015-11-02 | 1 | 2015-10-30 | 2015-11-02 | 2016-02-16 |  | 2016-02-29 |  |  | 2016-02-29 |  | PERMITTED | 2015-12-15 | 2015-12-15 | 2015-12-18 | 2016-01-16 | 1 | 2015-12-18 | 2015-12-16 | 2015-11-17 | 2015-11-17 | 2016-02-09 |  |  |  | 2016-02-10 | [6 empty] | 2016-03-14 |  | 2016-03-18 |  |  | 2016-03-18 |  | 2016-03-04 |  | 2016-02-17 |  | 2016-03-02 |  | 2016-03-08 |  |  | 2016-03-31 | [5 empty] | RBI forecast for lease end of June 2013 and RC only end September 2013 so no good for our T3 program. Moved to Tier 9 19/03/2012. 25 Nov: TI issued & site visited 8 Dec: co-lo sent 8 Dec: ATN ordered & antenna quote sent. Contractor quotes due 11 Dec. 12 Jan: Waiting on VF approval & antenna quote. Need Huawei antenna ETA. 3 Feb: Finalising Contractor quotes. Waiting on VF pre-approval & antenna quote. | VNZ | [9 empty] | 2016-03-25 |  | 2016-01-28 | LOW | AUCKLAND_HAMILTON_SH1_N | 2016-03-15 |  | BUILD | 2016-03-14 | FALSE |  | 2699243 | 6382951 | 327 Bedford Road, Te Kowhai |  |  | CELLSITE |  |  |  | ROAMING |  |  | 2016-02-10 | 2015-11-19 | 2015-11-25 | 2015-10-20 | 2015-10-20 | 2015-11-13 | 2015-11-13 | 2016-01-28 | 2016-02-02 |  |  | 2015-10-16
0 | WKT | 1409 | WKT-013-027 | RBI - Pukemiro | WKT-013-027-A | Pukemiro RBI | Waikato District | 25 | TIER_5 | ACTIVE | RBI | DF | COLO |  | STACK_A | COLO | 23 | 25 |  | -37.6191 | 175.0234 | [6 empty] | FALSE | FALSE |  |  | FALSE |  | 2015-10-15 | 2015-10-15 | 2015-10-20 | 2015-10-21 | 2015-10-21 | 2015-11-02 | 1 |  | 2015-11-02 | 2016-02-26 |  | 2016-03-25 |  |  | 2016-03-28 |  | PERMITTED | 2016-02-29 |  | 2016-03-02 |  |  | 2016-03-02 |  | 2016-02-29 |  | 2016-03-03 |  |  |  | 2016-03-04 | [6 empty] | 2016-04-04 |  | 2016-04-08 |  |  | 2016-04-07 |  | 2016-03-31 |  | 2016-03-30 |  | 2016-03-23 |  | 2016-03-16 |  |  | 2016-04-26 | [5 empty] | 15 Oct: SDP requested 16 Oct: Pre-qual requested 22 Oct: CD1 requested 5 Dec: On hold - as-builts incorrect 12 Jan: Need scan of as-built info from VF. Submit revised RF design ASAP. Escalate. 1 Feb: RF design submitted. Waiting on VF pre- approval. | VNZ | [9 empty] | 2016-04-15 |  |  |  |  | 2016-04-05 |  | BUILD | 2016-04-04 | FALSE |  | 2688848 | 6396175 | 1534 Rotowaro Road, Huntly |  |  | CELLSITE |  |  |  | ROAMING |  |  |  | 2015-11-20 | 2015-11-25 | 2015-10-16 | 2015-10-16 | 2015-11-20 | 2015-11-20 | 2016-02-26 |  |  |  | 2015-10-19
0 | WKT | 1410 | WKT-013-028 | RBI - Whatawhata West | WKT-013-028-A | RBI Whatwhat West | Waikato District |  | RBI | ACTIVE | RBI | DU | RBI Pole |  |  | COLO |  |  |  | -37.8094 | 175.1379 | [6 empty] | FALSE | FALSE |  |  | FALSE | [60 empty] | RBI forecast for lease end of September 2013 and RC only October 2013 so no good for our T3 program. Moved to Tier 9 19/03/2012. 7/10/15 - received data pack | [14 empty] | AUCKLAND_HAMILTON_SH1_N |  |  |  |  | FALSE |  | 2698443 | 6374826
0 | WKT | 1411 | WKT-013-029 | RBI - Newstead Central |  |  | Waikato District |  | TIER_9 | [22 empty] | FALSE
0 | WKT | 1412 | WKT-013-030 | RBI - Te Uku |  |  | Waikato District | 1 | TIER_3 | [22 empty] | FALSE | [75 empty] | RBI
0 | WKT | 1413 | WKT-013-031 | Tuakau | WKT-013-031-A | Tuakau | Waikato District | 22 | TIER_4 | ACTIVE | GF | DU | T2 25 UF |  | STACK_A | COSITE |  |  | 1 | -37.2493 | 174.9415 |  |  |  |  | Fibre Optic | WKT-016-023-B | FALSE | FALSE |  |  | FALSE |  | 2012-04-19 | 2012-04-19 | 2012-04-26 | 2012-04-26 | 2012-06-11 | 2012-06-13 | 2 | 2012-06-11 | 2012-09-04 | 2012-07-09 | 2012-06-29 | 2012-09-07 | 2012-09-13 | 1 | 2012-09-14 | 2012-09-13 | PERMITTED | 2012-07-09 | 2012-07-12 | 2012-09-21 | 2012-09-26 | 1 | 2012-09-28 | 2012-09-28 | 2014-10-24 | 2014-10-21 | 2015-01-30 | 2015-02-04 | 1 |  | 2015-02-13 | 2015-02-04 | 2015-03-18 |  |  |  |  | 2015-04-08 | 2015-04-08 | 2015-06-18 | 2015-06-18 | 2015-05-04 | 2015-05-11 | 2015-05-11 | 2015-05-07 | [7 empty] | 2015-05-19 | 2015-06-29 | 2015-06-23 | 2015-07-03 | 2015-06-29 |  |  | Vodafone Co-site approved 16/1/15 - awaiting CD1 issue 9/3/15 - all equipment and pole are ordered |  | 2015-05-14 |  |  |  |  | 2015-03-18 | 2015-03-18 | 2015-06-18 |  | 2015-06-23 | 2015-06-19 |  |  |  | 2015-05-07 | 2015-05-14 | BUILD | 2015-04-29 | FALSE |  | 2682541 | 6437371 | 21 Percy Graham Drive, Tuakau |  | Council Ref LUC0022/13 - 28/09/2012 | CELLSITE |  |  |  | ROAMING |  | 2014-12-18 | 2014-12-11 |  | 2015-03-30 |  |  |  | 2015-01-15 |  | 2015-03-30 |  |  | 2012-04-26
0 | WKT | 1414 | WKT-013-032 | Raglan TNZ Exchange TX Only | WKT-013-032-A | TX site | Waikato District | 6 | 2014 | ACTIVE | GF | TX |  |  |  | COSITE |  |  |  | -37.8007 | 174.8683 | [6 empty] | FALSE | FALSE |  |  | FALSE |  | 2012-07-10 | 2012-07-10 | 2012-07-11 | 2012-07-11 | 2012-09-03 | 2012-09-12 | 1 | 2012-09-03 | 2012-09-12 | 2014-07-29 | 2014-07-29 | 2014-07-30 |  |  | 2014-07-30 |  | PERMITTED | 2012-09-25 | 2012-10-02 | 2012-10-31 | 2012-10-30 | 1 | 2012-11-07 | 2012-11-05 | 2014-08-05 |  | 2014-08-05 | 2014-08-08 | 1 |  |  | 2014-08-08 | [5 empty] | 2014-08-11 | 2014-08-07 | 2014-08-20 | 2014-08-22 | 2014-08-13 | 2014-08-21 | 2014-09-01 | [9 empty] | 2014-09-25 | 2014-09-22 |  |  |  |  | Ryan to submit application through Liz. 07.10.14 BR contacted Garu Qui at Telecom requesting any info on the outstanding lease. | [10 empty] | 2014-09-16 | 2014-09-16 |  |  | TRANSMISSION_ONLY | 2014-08-15 | 2014-08-15 | BUILD | 2014-08-11 | TRUE |  | 2674727 | 6376333 | 9 Wainui road Raglan |  | Council Ref LUC0107/13 Application processed by Opus on behalf of Council. - 30/10/2012 | TXSITE | [17 empty] | 2012-07-11
0 | WKT | 1415 | WKT-015-001 | Tahuna | WKT-015-001-A | Tahuna | Matamata-Piako District | 1 | TIER_3 | ACTIVE | GF | DU | T2 20 RH |  | STACK_A | COSITE |  |  | 1 | -37.5373 | 175.4693 |  |  |  |  | Microwave | WKT-015-003-D | FALSE | FALSE |  |  | FALSE | 2012-08-21 | 2012-03-22 | 2012-03-22 | 2012-03-27 | 2012-03-27 | 2012-04-26 | 2012-04-24 | 2 | 2012-04-26 | 2012-08-02 | 2012-05-25 | 2012-05-23 | 2012-06-25 | 2012-06-25 |  | 2012-07-06 | 2012-08-22 | PERMITTED | 2012-05-04 | 2012-05-08 | 2012-06-27 | 2012-05-31 | 2 | 2012-06-15 | 2012-06-07 | 2012-08-17 |  | 2012-10-11 | 2012-10-15 | 1 |  | 2012-10-11 | 2012-10-15 | 2012-10-29 |  |  |  |  | 2012-10-18 | 2012-10-18 | 2012-11-10 | 2012-11-07 | 2012-10-31 | 2012-11-10 | 2012-11-07 | [8 empty] | 2012-11-16 | 2012-12-03 | 2012-11-28 | 2012-12-12 | 2012-11-30 | 2013-05-31 | 2013-05-29 | 5 snags still be be addressed, all design 09/04/13 - No FAN yet. FAC reforecasted 01/05/13 - No FAN yet. FAC reforecasted 29/05/13 - FAC signed |  | 2012-11-16 | 2012-10-06 | 2012-10-06 | 2012-10-11 | 2012-10-11 | 2012-10-19 | 2012-10-29 | 2012-11-08 | 2012-11-08 | 2012-11-19 | 2012-11-20 |  |  | AUCKLAND_HAMILTON_SH27 |  |  | BUILD | 2012-11-02 | FALSE |  | 2728456 | 6404245 | 609 Quine Rd, Tahuna, Waikato |  | Council Ref 103.2012.10498 - 31/05/2012 - 07/06/2012 | CELLSITE | [15 empty] | 2012-11-22 | 2012-11-22 | 2012-03-27
0 | WKT | 1416 | WKT-015-002 |  |  |  | Matamata-Piako District |  | TIER_9
0 | WKT | 1417 | WKT-015-003 | Morrinsville | WKT-015-003-D | Morrinsville | Matamata-Piako District | 1 | TIER_3 | ACTIVE | GF | DU | T2 20 RH |  | STACK_A | COSITE | 20 | 20 | 1 | -37.678 | 175.5203 |  |  |  |  | Microwave | WKT-013-024-A | FALSE | FALSE |  |  | FALSE | 2012-08-21 |  | 2012-04-02 |  | 2012-04-05 | 2012-05-31 | 2012-05-31 | 2 | 2012-05-31 | 2012-06-28 | 2012-07-20 | 2012-07-04 | 2012-08-10 | 2012-08-06 | 2 | 2012-08-17 | 2012-09-12 | PERMITTED | 2012-06-13 | 2012-06-25 | 2012-08-01 | 2012-07-05 | 2 | 2012-08-08 | 2012-07-09 | 2012-08-17 |  | 2012-10-11 | 2012-10-16 | 1 |  | 2012-10-11 | 2012-10-16 | 2012-10-29 |  |  |  |  | 2012-10-16 | 2012-10-16 | 2012-11-07 | 2012-11-07 | 2012-10-31 | 2012-11-12 | 2012-11-07 | [8 empty] | 2012-11-15 | 2012-12-03 | 2012-11-29 | 2012-12-12 | 2012-11-30 | 2013-05-17 | 2013-05-17 | 9 snags still be be addressed, design and photos 01/05/13 - No FAN yet. FAC reforecasted 17/05/13 - FAC signed |  | 2012-11-15 | 2012-10-06 | 2012-10-06 | 2012-10-11 | 2012-10-11 | 2012-10-18 | 2012-10-29 | 2012-11-08 | 2012-11-08 | 2012-11-19 | 2012-11-20 |  |  | AUCKLAND_HAMILTON_SH27 |  |  | BUILD | 2012-11-02 | FALSE |  | 2732516 | 6388514 | Cnr Kuranui & Scott Rds, Morrinsville |  | CoC application posted to MPDC. 2/7 Rev2 plans emailed to planner. - 05/07/2012 - 13/07/2012 | CELLSITE | [15 empty] | 2012-11-21 | 2012-11-21 | 2008-11-06
0 | WKT | 1418 | WKT-015-004 |  |  |  | Matamata-Piako District |  | TIER_9
0 | WKT | 1419 | WKT-015-005 | Matamata | WKT-015-005-A | Matamata Greenfield | Matamata-Piako District | 22 | TIER_4 | ACTIVE | GF | DU | P2 |  | STACK_A | STANDALONE | 25 | 25.5 | 1 | -37.8124 | 175.7715 |  |  |  |  | Fibre Optic | WKT-016-023-B | FALSE | FALSE |  |  | FALSE |  | 2012-07-10 | 2012-07-10 | 2012-07-11 | 2012-07-11 | 2012-08-10 | 2012-08-14 | 1 | 2012-08-10 | 2012-08-14 | 2012-09-03 | 2012-08-29 | 2012-09-14 | 2012-09-10 | 1 | 2012-09-21 | 2012-09-10 | PERMITTED | 2012-08-29 | 2012-08-31 | 2012-09-28 | 2012-09-13 | 1 | 2012-10-05 | 2012-09-17 |  | 2015-09-02 | 2015-10-08 | 2015-10-15 | 1 |  | 2015-10-08 | 2015-10-15 |  |  |  | 2015-10-02 |  | 2015-10-30 | 2015-10-23 | 2015-11-20 | 2015-11-23 |  | 2015-11-25 | 2015-11-25 | 2015-11-24 | 2015-11-25 | [7 empty] | 2015-12-07 | 2015-12-07 | 2015-12-18 | 2015-12-18 | [13 empty] | 2015-12-04 | 2015-12-03 |  |  | HAMILTON_ROTORUA | 2015-11-16 | 2015-11-20 | BUILD |  | TRUE |  | 2754193 | 6372947 | 19 Arawa Street, Matamata |  | Council Ref 103.2012.10557 - 17/09/2012 | CELLSITE |  |  |  | ROAMING |  | 2015-09-28 | 2015-10-06 | 2015-09-11 | 2015-09-09 |  | 2015-09-08 | 2015-09-22 | 2015-09-22 | 2015-10-16 | 2015-10-12 |  |  | 2012-07-11
0 | WKT | 1420 | WKT-015-006 |  |  |  | Matamata-Piako District |  | TIER_9
0 | WKT | 1421 | WKT-015-008 | RBI - Eureka |  |  | Matamata-Piako District |  | TIER_9 | [22 empty] | FALSE | [75 empty] | AUCKLAND_HAMILTON_SH27
0 | WKT | 1422 | WKT-015-009 | Te Aroha | WKT-015-009-A | Te Aroha | Matamata-Piako District | 1 | TIER_3 | ACTIVE | RT | DU | RT |  | STACK_A | COSITE |  |  | 1 | -37.5428 | 175.7098 |  |  |  |  | Fibre Optic | WKT-016-023-B | FALSE | FALSE |  |  | FALSE |  | 2012-03-08 | 2012-04-02 |  | 2012-04-05 | 2012-05-31 | 2012-05-31 | 3 | 2012-07-20 | 2012-09-24 | 2012-06-29 | 2012-07-02 | 2012-10-15 | 2012-10-18 | 3 | 2012-10-15 | 2012-11-13 | PERMITTED | 2012-07-11 | 2012-07-06 | 2012-08-15 | 2012-07-17 | 2 | 2012-08-22 | 2012-07-25 | 2012-08-17 | 2012-08-17 | 2012-10-15 | 2012-11-16 | 1 |  | 2012-10-15 | 2012-11-16 | 2012-11-20 |  |  | 2012-10-19 |  | 2012-11-26 | 2012-11-22 | 2012-12-13 | 2012-12-11 | 2012-12-04 | 2013-01-18 | 2012-12-14 | 2012-12-07 | 2012-12-07 | [6 empty] | 2012-12-14 | 2012-12-19 | 2012-12-18 | 2013-01-21 | 2012-12-21 | 2013-08-23 | 2013-09-03 | 6 snags still be be addressed, all design 09/04/13 - No FAN yet. FAC reforecasted |  | 2013-01-18 | 2012-10-06 | 2012-10-06 | 2012-11-22 | 2012-11-20 | 2012-11-21 | 2012-11-20 | 2012-12-06 | 2012-12-07 | 2012-12-17 | 2012-12-17 |  |  | AUCKLAND_HAMILTON_SH27 | 2012-12-05 | 2012-12-05 | BUILD | 2012-12-04 | TRUE | 2012-10-15 | 2749680 | 6403021 | 24 Lawrence Avenue, Te Aroha, Waikato |  | Council Ref: 103.2012.10524 - 25/07/2012 | CELLSITE | [15 empty] | 2012-12-19 | 2012-12-20
0 | WKT | 1423 | WKT-015-010 | RBI - Tatuanui |  |  | Matamata-Piako District |  | RBI | [22 empty] | FALSE
0 | WKT | 1424 | WKT-015-011 | Tamihana | WKT-015-011-C | Tamihana | Matamata-Piako District | 1 | TIER_3 | ACTIVE | GF | DU | T2 20 RF |  | STACK_A | STANDALONE |  |  | 1 | -37.7555 | 175.6934 |  |  |  |  | Microwave | WKT-015-003-D | FALSE | FALSE |  |  | FALSE | 2012-08-21 | 2012-05-10 | 2012-05-10 | 2012-05-22 | 2012-05-22 | 2012-07-05 | 2012-07-03 | 1 | 2012-07-05 | 2012-07-03 | 2012-07-27 | 2012-07-18 | 2012-09-07 | 2012-09-10 | 1 | 2012-09-14 | 2012-09-10 | PERMITTED | 2012-08-08 | 2012-08-08 | 2012-08-31 | 2012-08-22 | 1 | 2012-09-07 | 2012-08-23 | 2012-09-03 |  | 2012-10-18 | 2012-10-25 | 1 |  | 2012-10-18 | 2012-10-25 | 2012-11-14 |  |  | 2012-09-27 |  | 2012-11-02 | 2012-11-02 | 2012-11-23 | 2012-11-22 | 2012-11-22 | 2012-12-01 | 2012-12-01 | [8 empty] | 2012-12-01 | 2012-12-07 | 2012-12-04 | 2013-01-15 | 2012-12-12 | 2013-05-17 | 2013-05-17 | 5 snags still be be addressed, all design 09/04/13 - No FAN yet. FAC reforecasted 23/04/13 - FAN in sign off - PS3 still required 17/05/13 - FAC signed |  | 2012-12-01 | 2012-10-06 | 2012-10-06 | 2012-11-05 | 2012-11-14 | 2012-11-07 | 2012-11-14 | 2012-11-23 | 2012-11-23 | 2012-12-03 | 2012-12-03 |  |  | AUCKLAND_HAMILTON_SH27 |  |  | BUILD | 2012-11-22 | TRUE | 2012-10-01 | 2747515 | 6379463 | 128 Kirk rd Richmond Downs |  | Site within Matamata Airport Height Controls Surfaces. Height needed in the Motriki Datum. - 08/08/2012 Council Ref 103.2012.10543 - 23/08/2012 | CELLSITE | [15 empty] | 2012-12-06 | 2012-12-06
0 | WKT | 1425 | WKT-015-012 | Omahine | WKT-015-012-C | Omahine | Matamata-Piako District | 22 | TIER_4 | ACTIVE | GF | DU | T2 20 RH |  | STACK_A | COSITE |  |  | 1 | -37.8769 | 175.9339 |  |  |  |  | Microwave | WKT-019-002-A | FALSE | FALSE |  |  | FALSE |  | 2012-06-14 | 2012-06-21 | 2012-06-28 | 2012-06-28 | 2012-08-22 | 2012-08-20 | 2 | 2012-08-22 | 2015-04-22 | 2015-06-12 | 2015-06-16 | 2015-08-04 | 2015-07-23 |  | 2015-08-04 | 2015-08-10 | PERMITTED | 2012-11-30 | 2012-12-11 | 2013-01-20 | 2013-01-15 | 1 | 2013-01-27 | 2013-01-21 | 2015-06-29 | 2015-04-29 | 2015-07-31 | 2015-07-21 | 1 |  | 2015-07-31 | 2015-07-21 | [5 empty] | 2015-09-24 | 2015-09-04 | 2015-10-29 | 2015-11-02 |  | 2015-11-13 | 2015-11-17 | [9 empty] | 2015-12-07 | 2015-12-07 | 2015-12-14 | 2015-12-14 |  |  | Difficult LO asking high rental - see Erwin's report on this sites importance taking high rental into consideration. LO wants minimum $20k, lease escalation done for high rental but LO thinks he has the next Sky Tower! Consent lodged 17.2.14 - site search brief issued to Brad, VF co-lo data pack requested 23.2.15 - own site is preferred with Kordia Kaimai site as a back - up. Will need to visit area 5.3.15 - send Kordia Kaimai proposal to Shane for pricing - will weigh this up against the high rental LO is asking for our own GF site. 10/3/15 - site visit on 11th March, need to pick up/return key from/to the Swaps in Matamata note: Kordia Kaimai site is actually a Chorus tower - Jordan has requested a data pack - same LO on same ridge. 16/5/15 - cosite application sent to VF 8/9/15 - site build on hold due to LO concerns re lambing and road conditions | [10 empty] | 2015-12-07 | 2015-12-02 |  |  | HAMILTON_ROTORUA |  |  | BUILD |  | FALSE |  | 2768253 | 6365332 | 3159 SH29 Lower Kaimai, Waikato |  | Swap property subject to a Development Concept Plan, mainly for network utilities - 15/08/2012 Council Ref 103.2012.10605 - 17/12/2012 | CELLSITE |  |  |  | ROAMING |  | 2015-07-09 | 2015-07-13 | 2015-08-03 | 2015-07-17 |  |  |  |  | 2015-08-20 | 2015-08-26 |  |  | 2012-06-28
0 | WKT | 1426 | WKT-015-013 | Waharoa Transport Repeater |  |  | Matamata-Piako District |  | TIER_6 | [22 empty] | FALSE
0 | WKT | 1427 | WKT-015-014 | Matamata MW only site |  |  | Matamata-Piako District | 22 | TIER_4 | [22 empty] | FALSE
0 | WKT | 1428 | WKT-015-015 | RBI - Manawaru | WKT-015-015-A | Manawaru RBI | Matamata-Piako District |  | RBI | ACTIVE | RBI |  |  |  |  | COLO | [11 empty] | FALSE | FALSE |  |  | FALSE | [91 empty] | ROAMING
0 | WKT | 1429 | WKT-016-001 | Pukete North | WKT-016-001-B | Vodafone Colo Pukete North 86 Maui St | Hamilton | 10 | TIER_2 | ACTIVE | COLO | DU | COLO | grey | STACK_A | COLO | 18.94 |  | 1 | -37.7338 | 175.2248 |  | 2009-11-23 |  | 2009-12-15 | Microwave | WKT-016-012-A | TRUE | TRUE | 2010-02-10 | 2010-02-26 | FALSE | 2010-02-08 | 2010-04-02 | 2010-02-10 |  |  | 2010-02-24 | 2010-02-26 | 3 | 2010-02-24 | 2010-06-25 |  | 2010-03-30 | 2010-08-13 | 2010-08-05 | 1 | 2011-02-28 | 2011-05-20 | PERMITTED | 2010-04-08 | 2010-04-08 | 2010-05-10 | 2010-05-05 | 2 | 2010-05-17 | 2010-05-10 |  |  | 2011-04-04 | 2011-03-03 | 2 | 3 | 2011-03-30 | 2011-04-20 | 2011-05-10 |  |  |  |  | 2011-05-04 | 2011-05-04 | 2011-05-11 | 2011-06-10 | 2011-06-03 | 2011-06-10 | 2011-06-23 |  |  |  | 2011-02-07 |  |  |  | 2011-05-12 | 2011-06-27 | 2011-07-31 | 2011-07-28 | 2011-07-31 | 2011-07-26 | 2011-11-09 | 2012-01-27 | Final approval received from VF. Antenna amendment approved by VF and COC done. | VNZ | 2011-06-12 | 2011-05-03 | 2011-05-03 | 2011-05-09 | 2011-05-10 | 2011-05-09 | 2011-05-10 | 2011-06-10 | 2011-06-20 |  | 2011-07-13 | [7 empty] | FALSE |  | 2706302 | 6383028 | Voda Colo, North Pukete, 86 Maui St Hamilton |  |  | CELLSITE |  |  | 2015-10-14 | [13 empty] | 2011-07-13 | 2010-01-21
0 | WKT | 1430 | WKT-016-002 | Dinsdale | WKT-016-002-E | LPR | Hamilton | 10 | TIER_2 | ACTIVE | RSR | DU | P4F | grey | INLINE | STANDALONE | 15 | 15.5 | 3 | -37.795 | 175.2484 |  | 2009-11-23 |  | 2009-12-15 | Microwave | WKT-016-027-A | TRUE | TRUE | 2010-01-15 |  | FALSE | 2010-06-24 |  | 2010-05-31 |  |  | 2010-06-17 | 2010-06-21 | 4 | 2010-06-17 | 2010-10-13 | 2010-11-19 | 2010-11-19 | 2010-11-26 | 2010-12-21 | 4 | 2010-11-30 | 2010-12-21 | CONTROLLED | 2010-06-22 | 2010-06-21 | 2010-11-26 | 2010-11-15 | 4 | 2010-11-30 | 2010-11-19 |  |  | 2011-05-17 | 2011-05-13 | 1 |  | 2011-05-11 | 2011-05-13 | 2011-05-20 |  |  | 2011-03-07 |  | 2011-05-23 | 2011-05-16 | 2011-05-27 | 2011-06-03 | 2011-05-29 | 2011-06-12 | 2011-06-03 |  |  |  | 2011-02-07 |  |  |  | 2011-05-12 | 2011-06-20 | 2011-07-31 | 2011-07-28 | 2011-07-31 | 2011-07-13 | 2011-10-27 | 2011-12-01 | Hardmatched. Lease and consent used 3.0m cabinet layout. |  | 2011-06-19 | 2011-05-23 | 2011-05-23 | 2011-05-25 | 2011-05-25 | 2011-05-16 | 2011-05-20 | 2011-06-11 | 2011-06-01 |  | 2011-06-27 | [7 empty] | TRUE |  | 2708210 | 6376185 | Road Reserve, outside 247 Killarney Rd |  | Resource No. 10/2010/21470/001 (38/1/4345) - 28/07/2010 | CELLSITE | [16 empty] | 2011-06-27 | 2010-06-02
0 | WKT | 1431 | WKT-016-003 | Te Rapa North | WKT-016-003-D | Te Rapa North - voda colo | Hamilton | 10 | TIER_2 | ACTIVE | COLO | DU5 | COLO | grey | STACK_A | COLO | 20 | 23 | 1 | -37.7489 | 175.2392 |  | 2009-11-23 |  | 2009-12-15 | Microwave | WKT-016-015-A | TRUE | TRUE | 2010-02-10 | 2010-02-26 | FALSE | 2010-02-08 | 2010-04-02 | 2010-02-10 |  |  | 2010-02-26 | 2010-02-24 | 3 | 2010-02-26 | 2010-06-25 |  | 2010-03-30 | 2010-07-16 | 2010-07-14 |  | 2011-02-28 | 2011-11-15 | PERMITTED | 2010-04-08 | 2010-04-14 | 2010-05-17 | 2010-05-06 | 2 | 2010-05-24 | 2010-05-10 |  |  | 2011-03-28 | 2011-05-06 | 1 |  | 2011-03-22 | 2011-05-06 | 2011-05-13 |  |  | 2011-04-12 |  | 2011-05-30 | 2011-06-01 | 2011-06-02 | 2011-06-07 | 2011-06-03 | 2011-06-12 | 2011-06-11 |  |  |  | 2011-02-07 |  |  |  | 2011-05-12 | 2011-06-30 | 2011-07-31 | 2011-07-28 | 2011-07-31 | 2011-07-26 | 2011-10-26 | 2012-02-03 |  | VNZ | 2011-06-18 | 2011-05-03 | 2011-05-03 | 2011-05-09 | 2011-05-12 | 2011-05-09 | 2011-05-13 | 2011-06-16 | 2011-06-20 |  | 2011-07-13 | [7 empty] | TRUE |  | 2707532 | 6381319 | 55 Pukete Rd Te Rapa |  |  | CELLSITE |  |  | 2014-09-24 | [13 empty] | 2011-07-13 | 2010-01-21
0 | WKT | 1432 | WKT-016-004 | Chartwell Square (TX HUB) | WKT-016-004-A | Chartwell Square - Hukanui Rd | Hamilton | 10 | TIER_2 | ACTIVE | RT | DF5 | NOPOLE | grey | STACK_A | COSITE | 22.7 | 20.1 | 1 | -37.7504 | 175.2786 |  | 2009-11-23 |  | 2009-12-15 | Microwave | WKT-016-023-B | TRUE | TRUE | 2010-01-15 |  | FALSE | 2010-04-23 | 2010-01-14 | 2010-01-14 |  |  |  | 2010-02-16 | 6 | 2010-02-24 | 2010-09-01 |  | 2010-04-06 | 2011-01-31 | 2011-03-08 | 3 | 2011-01-31 | 2011-05-20 | PERMITTED | 2010-02-26 | 2010-12-24 | 2010-03-12 | 2011-02-03 | 6 | 2010-03-24 | 2010-03-24 |  |  | 2011-04-08 | 2011-05-06 | 4 | 6 | 2011-04-04 | 2011-05-31 | 2011-06-03 |  |  |  |  | 2011-05-23 | 2011-05-30 | 2011-06-20 | 2011-06-23 | 2011-06-14 | 2011-06-27 | 2011-06-27 |  |  |  | 2011-02-07 |  |  |  | 2011-05-12 | 2011-07-06 | 2011-07-31 | 2011-07-28 | 2011-07-31 | 2011-07-27 | 2011-10-27 | 2012-06-22 | HUB SITE. In signoff with 2degrees, then Westfield to sign. |  | 2011-06-27 | 2011-05-03 | 2011-05-03 | 2011-05-09 | 2011-05-10 | 2011-06-03 | 2011-06-03 | 2011-06-27 | 2011-06-27 |  | 2011-07-13 | [7 empty] | FALSE |  | 2710995 | 6381066 | Chartwell Shopping Centre Hukanui Road Hamilton |  | Permitted to 5.00 ARH - 20/05/2010 | CELLSITE |  |  | 2014-09-24 | [13 empty] | 2011-07-13 | 2008-05-20
0 | WKT | 1433 | WKT-016-005 | Livingstone | WKT-016-005-D | Vodafone co-lo | Hamilton | 10 | TIER_2 | ACTIVE | COLO | DU5 | COLO | grey | STACK_A | COLO | 20 | 23 | 1 | -37.7732 | 175.2438 |  | 2009-11-23 |  | 2009-12-15 | Microwave | WKT-016-009-A | TRUE | TRUE | 2010-02-10 | 2010-02-26 | FALSE |  | 2010-04-02 | 2010-02-10 |  |  | 2010-02-26 | 2010-02-25 | 3 | 2010-02-26 | 2010-06-25 |  | 2010-03-30 | 2010-08-06 | 2010-12-08 |  | 2011-02-28 | 2011-05-20 | PERMITTED | 2010-04-15 | 2010-04-15 | 2010-05-20 | 2010-05-10 | 2 | 2010-05-27 | 2010-05-12 |  |  | 2011-03-28 | 2011-04-13 | 2 |  | 2011-03-22 | 2011-04-18 | 2011-05-13 |  |  |  |  | 2011-05-12 | 2011-05-13 | 2011-05-24 | 2011-06-03 | 2011-06-05 | 2011-06-15 | 2011-06-23 |  |  |  | 2011-02-07 |  |  |  | 2011-05-12 | 2011-06-30 | 2011-07-31 | 2011-07-28 | 2011-07-31 | 2011-07-27 | 2011-10-27 | 2012-08-21 | Final approval received from VF. Antenna amendment approved by VF and COC done. | VNZ | 2011-06-21 | 2011-05-16 | 2011-05-18 | 2011-05-18 | 2011-05-19 | 2011-05-13 | 2011-05-13 | 2011-06-17 | 2011-06-23 |  | 2011-07-18 | [7 empty] | FALSE |  | 2707865 | 6378616 | 88 Avalon Dr, Nawton, Hamilton |  | Council COC Reference: 010/2010/21266 - 12/05/2010 | CELLSITE |  |  | 2014-09-24 | [13 empty] | 2011-07-18 | 2010-01-21
0 | WKT | 1434 | WKT-016-006 | Flagstaff | WKT-016-006-A | Flagstaff Floodlight pole | Hamilton | 10 | TIER_2 | ACTIVE | GF | DU | P1 | grey | INLINE | COSITE | 14.5 | 15 | 1 | -37.7384 | 175.2529 |  | 2009-11-23 |  | 2009-12-15 | Microwave | WKT-016-016-D | TRUE | TRUE | 2010-01-15 |  | FALSE | 2010-02-08 | 2010-03-05 | 2010-03-03 |  |  | 2010-03-19 | 2010-03-23 | 7 | 2010-03-19 | 2011-03-28 | 2010-05-07 | 2010-05-07 | 2010-06-11 | 2010-06-11 | 5 | 2010-06-11 | 2010-06-11 | PERMITTED | 2010-03-29 | 2010-12-24 | 2010-04-28 | 2011-02-04 | 6 | 2010-05-06 | 2010-04-29 |  |  | 2011-07-08 | 2011-07-13 | 1 |  | 2011-07-01 | 2011-07-13 | 2011-08-01 |  |  |  |  | 2011-07-18 | 2011-07-18 | 2011-08-16 | 2011-08-16 | 2011-08-17 | 2011-08-19 | 2011-08-19 |  |  |  | 2011-02-07 |  |  |  | 2011-05-12 | 2011-08-25 | 2011-09-02 | 2011-08-25 | 2011-09-13 | 2011-09-13 | 2011-12-12 | 2012-02-03 |  |  | 2011-08-22 | 2011-07-04 | 2011-07-04 | 2011-08-01 | 2011-08-01 | 2011-08-01 | 2011-08-01 | 2011-08-24 | 2011-08-24 |  | 2011-08-29 | [6 empty] | 2011-08-17 | FALSE |  | 2708768 | 6382450 | Flagstaff Shopping Centre flood light pole 1158 River Rd |  |  | CELLSITE | [15 empty] | 2011-08-22 | 2011-08-25 | 2010-03-10
0 | WKT | 1435 | WKT-016-007 | Claudelands | WKT-016-007-D | On Track - 778 Heaphy Rd | Hamilton | 10 | TIER_2 | ACTIVE | GF | DU5 | P1 | grey | STACK_A | STANDALONE | 14.9 | 15.4 | 3 | -37.781 | 175.2892 |  | 2009-11-23 |  | 2009-12-15 | Microwave | WKT-016-023-B | TRUE | TRUE | 2010-01-15 |  | FALSE | 2010-04-23 | 2010-03-05 | 2010-03-03 |  |  | 2010-03-19 | 2010-03-23 | 2 | 2010-03-19 | 2010-06-25 | 2010-05-21 | 2010-05-18 | 2010-07-30 | 2010-07-30 | 2 | 2010-08-03 | 2010-08-03 | PERMITTED | 2010-04-19 | 2010-12-24 | 2010-05-19 | 2011-01-20 | 2 | 2010-05-26 | 2010-05-24 |  |  | 2011-04-08 | 2011-04-19 | 1 |  | 2011-04-04 | 2011-04-19 | 2011-05-19 |  |  |  |  | 2011-05-21 | 2011-05-12 | 2011-06-05 | 2011-06-01 | 2011-05-26 | 2011-06-05 | 2011-06-09 |  |  |  | 2011-02-07 |  |  |  | 2011-05-12 | 2011-06-23 | 2011-07-31 | 2011-07-28 | 2011-07-31 | 2011-07-12 | 2011-10-26 | 2011-11-22 | Hardmatched with old antennas. Lease varitation and COC complete. |  | 2011-06-11 | 2011-05-03 | 2011-05-03 | 2011-05-09 | 2011-05-12 | 2011-05-16 | 2011-05-19 | 2011-06-05 | 2011-06-09 |  | 2011-06-24 | [7 empty] | FALSE |  | 2711841 | 6377642 | 778 Heaphy Rd |  | Council COC Reference: 010/2010/21284 - 24/05/2010 | CELLSITE |  |  | 2014-09-24 | [13 empty] | 2011-06-24 | 2010-03-10
0 | WKT | 1436 | WKT-016-008 | Waikato University | WKT-016-008-B | Waikato Uni - LPR #1 | Hamilton | 10 | TIER_2 | ACTIVE | RSR | DU5 | P4F | grey | INLINE | STANDALONE | 15 | 15.5 | 3 | -37.7889 | 175.319 |  | 2009-11-23 |  | 2009-12-15 | Microwave | WKT-016-010-C | TRUE | TRUE | 2010-03-17 | 2010-03-19 | FALSE |  | 2010-03-23 | 2010-03-23 |  | 2010-05-10 | 2010-04-16 | 2010-04-09 | 5 | 2010-05-06 | 2011-03-15 | 2010-05-07 | 2010-05-06 | 2010-09-10 | 2010-09-08 | 3 | 2010-09-10 | 2010-09-08 | CONTROLLED | 2010-04-23 | 2011-03-16 | 2010-05-21 | 2011-03-28 | 5 | 2010-05-28 | 2011-03-28 |  |  |  | 2011-07-07 | 1 |  | 2011-05-11 | 2011-07-07 | 2011-08-01 |  |  |  |  | 2011-07-26 | 2011-07-28 | 2011-08-13 | 2011-08-13 | 2011-08-16 | 2011-08-16 | 2011-08-19 |  |  |  | 2011-02-07 |  |  |  | 2011-05-12 | 2011-08-20 | 2011-09-01 | 2011-08-31 | 2011-09-14 | 2011-09-14 | 2011-12-13 | 2012-02-22 | Hard matched but plans to be swapped out by Council for lease and consent due to cabinet extension (drawings done). Requires a S127 due to both VF and 2degrees cabinets in frontage, permitted but underlying activity controlled therefore S127. |  | 2011-08-19 | 2011-07-04 | 2011-07-04 | 2011-08-01 | 2011-08-01 | 2011-08-01 | 2011-08-01 | 2011-08-31 | 2011-08-31 |  | 2011-09-06 | [6 empty] | 2011-08-13 | FALSE |  | 2714443 | 6376696 | Roading Reserve 136 Hillcrest Rd |  | Land Use Resource Consent Ref: 010/2010/21283 - (38/1/4329) - 25/05/2010 | CELLSITE |  |  | 2014-09-24 | [12 empty] | 2011-08-22 | 2011-08-18 | 2010-02-10
0 | WKT | 1437 | WKT-016-009 | Nawton | WKT-016-009-A | Nawton - Shopping Centre | Hamilton | 10 | TIER_2 | ACTIVE | GF | DU | P2 | grey | STACK_A | STANDALONE | 17 | 18.6 | 1 | -37.7818 | 175.2377 |  | 2009-11-23 |  | 2009-12-15 | Microwave | WKT-016-012-A | TRUE | TRUE | 2010-01-15 |  | FALSE | 2010-02-15 | 2010-01-14 | 2010-01-14 |  |  |  | 2008-07-10 | 6 | 2010-04-15 | 2010-12-01 |  | 2010-02-17 | 2009-03-02 | 2010-02-17 | 6 | 2010-03-08 | 2010-03-08 | PERMITTED | 2010-02-26 | 2011-01-24 | 2010-05-17 | 2011-02-15 | 6 | 2010-05-24 | 2010-05-13 |  |  | 2011-04-06 | 2008-10-31 | 2 | 6 | 2011-03-31 | 2011-04-26 | 2011-05-12 |  |  |  |  | 2011-05-06 | 2011-05-05 | 2011-05-31 | 2011-06-01 | 2011-06-01 | 2011-06-10 | 2011-06-01 |  |  |  | 2011-02-07 |  |  |  | 2011-05-12 | 2011-06-11 | 2011-07-31 | 2011-07-28 | 2011-07-31 | 2011-07-11 | 2011-10-10 | 2012-02-02 | Hardmatched with old antennas. Lease variation with LO for approval & waiting COC from Council (had ref to wrong height and VF). Historic Rev1 CD, needs an uprev to Rev2. |  | 2011-06-11 | 2011-05-03 | 2011-05-03 | 2011-05-09 | 2011-05-10 | 2011-05-09 | 2011-05-12 | 2011-05-31 | 2011-06-09 |  | 2011-06-24 | [7 empty] | FALSE |  | 2707305 | 6377668 | Grandview Rd intersection with Hyde Avenue Hamilton |  | Permitted to 15.00 AGL - 20/05/2010 - 21/02/2011 | CELLSITE | [16 empty] | 2011-06-24 | 2008-05-12
0 | WKT | 1438 | WKT-016-010 | Hamilton CBD North | WKT-016-010-C | Opus Building | Hamilton | 10 | TIER_2 | ACTIVE | RT | DF5 | RT | grey | INLINE | STANDALONE |  |  | 2 | -37.7811 | 175.2754 |  | 2009-11-23 |  | 2009-12-15 | Microwave | WKT-016-012-A | TRUE | TRUE | 2010-01-15 |  | FALSE | 2010-07-05 |  | 2010-06-30 |  |  | 2010-07-21 | 2010-07-22 | 2 | 2010-07-21 | 2011-03-16 | 2010-08-20 | 2010-08-24 | 2010-10-29 | 2010-10-22 | 1 | 2010-10-29 | 2010-10-22 | PERMITTED | 2010-07-28 | 2010-07-28 | 2010-08-30 | 2010-08-30 | 1 | 2010-09-06 | 2010-08-30 |  |  | 2011-04-08 | 2011-05-23 | 1 |  | 2011-04-04 | 2011-05-23 | 2011-06-22 |  |  |  |  | 2011-06-20 | 2011-06-20 | 2011-07-03 | 2011-07-14 | 2011-07-14 | 2011-06-29 | 2011-07-14 |  |  |  | 2011-02-07 |  |  |  | 2011-05-12 | 2011-07-18 | 2011-07-31 | 2011-07-28 | 2011-07-31 | 2011-07-27 | 2011-11-10 | 2011-12-22 | Hardmatched |  | 2011-07-15 | 2011-05-16 | 2011-05-23 | 2011-05-18 | 2011-05-24 | 2011-06-20 | 2011-06-22 | 2011-06-21 | 2011-07-14 |  | 2011-07-22 | [7 empty] | FALSE |  | 2710624 | 6377668 | 28 Harwood Street |  |  | CELLSITE |  |  | 2014-09-24 | [13 empty] | 2011-07-18 | 2010-07-01
0 | WKT | 1439 | WKT-016-011 | Hamilton Central | WKT-016-011-B | Hamilton Central - 41 Hood St | Hamilton | 10 | TIER_2 | ACTIVE | RT | DU5 | RT | grey | INLINE | STANDALONE | 28.15 |  | 1 | -37.7913 | 175.2839 |  | 2009-11-23 |  | 2009-12-15 | Microwave | WKT-016-012-A | TRUE | TRUE | 2010-01-15 |  | FALSE | 2010-02-08 | 2010-02-12 | 2010-02-10 |  |  | 2010-03-15 | 2010-03-15 | 3 | 2010-03-19 | 2010-06-25 | 2010-06-29 | 2010-06-23 | 2010-11-26 | 2010-12-02 | 3 | 2010-11-30 | 2010-12-02 | PERMITTED | 2010-03-26 | 2010-03-25 | 2010-04-29 | 2010-04-27 | 2 | 2010-04-30 | 2010-04-29 |  |  | 2011-04-08 | 2011-04-27 | 1 |  | 2011-04-04 | 2011-04-27 | 2011-05-05 |  |  |  |  | 2011-04-28 | 2011-04-28 | 2011-05-15 | 2011-05-09 | 2011-05-09 | 2011-05-15 | 2011-06-01 |  |  |  | 2011-02-07 |  |  |  | 2011-05-12 | 2011-05-31 | 2011-07-31 | 2011-07-28 | 2011-07-31 | 2011-07-25 | 2011-11-08 | 2011-12-01 | Hard matched |  | 2011-05-27 | 2011-04-18 | 2011-04-18 | 2011-05-09 | 2011-05-10 | 2011-05-05 | 2011-05-05 | 2011-05-15 | 2011-05-26 |  | 2011-06-20 | [7 empty] | FALSE |  | 2711341 | 6376511 | Tournament Carpark 41 Hood Street Hamilton Central |  | Councils Reference 10.2010.21208.001 - 29/04/2010 | CELLSITE |  |  | 2014-09-24 | [13 empty] | 2011-06-20 | 2010-02-10
0 | WKT | 1440 | WKT-016-012 | Waikato Hospital (TX HUB) | WKT-016-012-A | Waikato Hospital | Hamilton | 10 | TIER_2 | ACTIVE | RT | DF5 | NOPOLE | beige | STACK_A | COSITE | 43.74 | 45.3 | 1 | -37.8039 | 175.2816 |  | 2009-11-23 |  | 2009-12-15 | Fibre Optic | WKT-016-023-B | TRUE | TRUE | 2010-01-15 |  | FALSE | 2010-04-23 | 2010-02-26 | 2010-03-03 |  |  | 2010-03-26 | 2010-03-26 | 10 | 2010-03-26 | 2015-06-17 | 2010-09-15 | 2010-09-24 | 2010-11-26 | 2010-11-15 | 8 | 2010-11-30 | 2010-11-17 | PERMITTED | 2010-04-01 | 2010-08-25 | 2010-05-05 | 2010-09-09 | 7 | 2010-09-15 | 2010-09-13 |  |  | 2011-03-21 | 2011-04-15 | 2 |  | 2011-03-18 | 2011-07-04 | 2011-05-03 |  |  |  |  | 2011-04-16 | 2011-04-16 | 2011-05-28 | 2011-05-14 | 2011-05-14 | 2011-05-25 | 2011-05-31 | [7 empty] | 2011-05-12 | 2011-05-31 | 2011-07-31 | 2011-07-28 | 2011-07-31 | 2011-07-11 | 2011-10-10 | 2012-03-14 | HUB SITE (back-up socket) Hard matched |  | 2011-05-27 | 2011-05-03 | 2011-05-03 | 2011-05-09 | 2011-05-10 | 2011-05-03 | 2011-05-03 | 2011-05-24 | 2011-05-25 |  | 2011-06-27 | [7 empty] | FALSE |  | 2711107 | 6375116 | Rooftop Elizabeth Rothwell Building Waikato Hospital Hamilton |  |  | CELLSITE |  |  | 2014-09-24 | [13 empty] | 2011-06-27 | 2010-03-10
0 | WKT | 1441 | WKT-016-013 | Enderley | WKT-016-013-C | Enderly - RSR outside Shell | Hamilton | 10 | TIER_2 | ACTIVE | RSR | DU5 | P4F | grey | INLINE | STANDALONE | 15 | 15.5 | 1 | -37.7723 | 175.293 |  | 2009-11-23 |  | 2009-12-15 | Microwave | WKT-016-022-A | TRUE | TRUE | 2010-01-15 |  | FALSE |  | 2010-02-19 | 2010-02-11 |  |  | 2010-03-05 | 2010-03-05 | 5 | 2010-03-05 | 2014-07-11 | 2010-05-05 | 2010-04-27 | 2010-09-10 | 2010-09-08 | 2 | 2010-09-10 | 2010-09-08 | NES | 2010-03-12 | 2010-03-12 | 2010-04-23 | 2010-04-21 | 2 | 2010-04-30 | 2010-04-26 |  |  | 2011-03-28 | 2011-05-06 | 1 |  | 2011-03-22 | 2011-05-06 | 2011-05-12 |  |  |  |  | 2011-05-10 | 2011-05-10 | 2011-05-27 | 2011-05-20 | 2011-05-29 | 2011-06-01 | 2011-06-01 |  |  |  | 2011-02-07 |  |  |  | 2011-05-12 | 2011-07-23 | 2011-07-31 | 2011-07-28 | 2011-07-31 | 2011-07-27 | 2011-11-10 | 2011-12-01 | Hard matched but plans to be swapped out by Council for lease and consent due to cabinet extension (drawings done). |  | 2011-06-22 | 2011-05-23 | 2011-05-23 | 2011-05-25 | 2011-05-24 | 2011-05-12 | 2011-05-12 | 2011-05-31 | 2011-06-09 |  | 2011-07-18 | [7 empty] | FALSE |  | 2712201 | 6378599 | outside Shell, 243 Peach Grove Rd |  | LPR Permitted Activity under NES | CELLSITE |  |  | 2014-09-24 | [13 empty] | 2011-07-18 | 2010-02-11
0 | WKT | 1442 | WKT-016-014 | Glenview | WKT-016-014-C | LPR | Hamilton | 10 | TIER_2 | ACTIVE | RSR | DU | P4F | grey | INLINE | STANDALONE | 15 | 15.5 | 1 | -37.8242 | 175.29 |  | 2009-11-23 |  | 2009-12-15 | Microwave | WKT-016-039-A | TRUE | TRUE | 2010-02-10 | 2010-02-19 | FALSE | 2010-02-24 | 2010-02-19 | 2010-02-11 |  |  | 2010-03-08 | 2010-03-10 | 4 | 2010-03-25 | 2011-01-20 | 2010-05-05 | 2010-04-27 | 2010-09-10 | 2010-09-08 | 3 | 2010-09-10 | 2010-09-08 | CONTROLLED | 2010-03-12 | 2010-03-25 | 2010-04-28 | 2010-04-16 | 3 | 2010-05-05 | 2010-04-21 |  |  | 2011-05-17 | 2011-05-13 | 1 |  | 2011-05-11 | 2011-05-13 | 2011-05-19 |  |  | 2011-04-12 |  | 2011-05-28 | 2011-05-19 | 2011-06-02 | 2011-06-01 | 2011-06-03 | 2011-06-02 | 2011-06-03 |  |  |  | 2011-02-07 |  |  |  | 2011-05-12 | 2011-06-20 | 2011-07-31 | 2011-07-28 | 2011-07-31 | 2011-07-25 | 2011-11-08 | 2011-12-22 | Hard matched but plans to be swapped out by Council for lease and consent due to cabinet extension (drawings done). |  | 2011-06-16 | 2011-05-23 | 2011-05-23 | 2011-05-25 | 2011-05-24 | 2011-05-16 | 2011-05-19 | 2011-06-17 | 2011-06-16 |  | 2011-07-13 | [7 empty] | TRUE |  | 2711788 | 6372848 | Cnr Resthill Cres & Macdonald Road, Hamilton |  | Activity Controlled under the NES. | CELLSITE | [16 empty] | 2011-07-13 | 2010-02-11
0 | WKT | 1443 | WKT-016-015 | Te Rapa | WKT-016-015-A | Vodafone co-lo | Hamilton | 10 | TIER_2 | ACTIVE | COLO | DU5 | COLO | grey | STACK_A | COLO | 20 | 25 | 1 | -37.7577 | 175.2493 |  | 2009-11-23 |  | 2009-12-15 | Microwave | WKT-016-023-B | TRUE | TRUE | 2010-02-10 | 2010-02-26 | FALSE | 2010-04-23 | 2010-04-02 | 2010-02-10 |  |  | 2010-02-23 | 2010-02-24 | 2 | 2010-02-23 | 2010-06-28 | 2010-05-14 | 2010-04-23 | 2010-07-16 | 2011-02-15 |  | 2011-02-28 | 2011-05-20 | PERMITTED | 2010-04-30 | 2010-05-03 | 2010-06-08 | 2010-06-01 | 1 | 2010-06-15 | 2010-06-02 |  |  | 2011-03-28 | 2011-04-13 | 1 |  | 2011-03-22 | 2011-04-13 | 2011-06-01 |  |  |  |  | 2011-05-19 | 2011-05-27 | 2011-05-21 | 2011-06-09 | 2011-06-04 | 2011-06-13 | 2011-06-23 |  |  |  | 2011-02-07 |  |  |  | 2011-05-12 | 2011-06-29 | 2011-07-31 | 2011-07-28 | 2011-07-31 | 2011-07-27 | 2011-10-25 | 2012-02-03 |  | VNZ | 2011-06-20 | 2011-05-16 | 2011-05-18 | 2011-05-17 | 2011-05-19 | 2011-05-20 | 2011-06-01 | 2011-06-15 | 2011-06-20 |  | 2011-07-18 | [7 empty] | FALSE |  | 2708389 | 6380319 | 11A Norris Avenue, Hamilton |  | COC File Ref: 010/2010/21323 (35/1/477) - 02/06/2010 | CELLSITE |  |  | 2014-09-24 | [13 empty] | 2011-07-18 | 2010-01-21
0 | WKT | 1444 | WKT-016-016 | Rototuna East | WKT-016-016-D | Rototuna East Vodafone Co-lo | Hamilton | 10 | TIER_2 | ACTIVE | COLO | DU | COLO | grey | STACK_A | COLO | 14.5 | 15 | 1 | -37.7281 | 175.2884 |  | 2009-11-23 |  | 2009-12-15 | Microwave | WKT-016-004-A | TRUE | TRUE | 2010-02-10 | 2010-02-26 | FALSE | 2010-02-08 | 2010-04-02 | 2010-02-10 |  |  | 2010-02-24 | 2010-02-25 | 5 | 2010-02-24 | 2010-10-01 |  | 2010-03-30 | 2010-08-23 | 2010-12-08 |  | 2011-02-28 | 2011-05-20 | CONTROLLED | 2010-04-08 | 2010-05-13 | 2010-05-17 | 2010-05-17 | 2 | 2010-05-24 | 2010-05-20 |  |  | 2011-03-28 | 2011-04-20 | 1 |  | 2011-03-22 | 2011-04-20 | 2011-05-13 |  |  |  |  | 2011-05-23 | 2011-05-21 | 2011-05-20 | 2011-06-07 | 2011-06-03 | 2011-06-25 | 2011-06-29 |  |  |  | 2011-02-07 |  |  |  | 2011-05-12 | 2011-06-29 | 2011-07-31 | 2011-07-28 | 2011-07-31 | 2011-07-27 | 2011-11-10 | 2011-12-01 | Final approval received from VF. Antenna change incorporated with additional microwave. S127 approved for extra dish and antenna size increase. | VNZ | 2011-06-25 | 2011-05-03 | 2011-05-03 | 2011-05-09 | 2011-05-10 | 2011-05-09 | 2011-05-13 | 2011-06-17 | 2011-06-23 |  | 2011-07-13 | [7 empty] | FALSE |  | 2711923 | 6383516 | Gordonton Rd |  | Resource Consent Ref 010.2010.21239 - (38/1/4335) - 20/05/2010 | CELLSITE | [16 empty] | 2011-07-13 | 2010-01-21
0 | WKT | 1445 | WKT-016-017 | Hamilton Alma |  |  | Hamilton |  | TIER_9 | [22 empty] | FALSE | [60 empty] | Aim to provide GSM900 voice and U2100 services to indoor levels. Hamilton Alma. (Renamed "Hamilton Alma" co-ords: 2711228 & 6377172 20m . 15th Sept 09 RH) ONLY RESURRECT THIS SR NUMBER IF WKT-016-023 Ward St (The Tx Hub) is not available to RF) Based on Vodafones 40m Rooftop option at Tompkins Wake Building (Westpac) Alma Street. Option A: Voda on Tompkins Wake Building 50m, Alma St. Grid: 2711165 6077102 Option B: IBIS Hotel, Alma St 50m Grid: 2711230 6077180 Option C: Nesquirt Option: Centre Place,501 Victoria St Grid: 2711129 6377175 Option D: Nesquirt Option: Downtown Plaza,Ward Street & Corner Worley Place. Grid: 2711056 6377043 Option E: Nesquirt Option: Hamilton Central,Bryce Street Grid: 2710961 6377137
0 | WKT | 1446 | WKT-016-018 | Whitiora | WKT-016-018-F | Whitiora RSR | Hamilton | 10 | TIER_2 | ACTIVE | RSR | DU5 | P4F | grey | INLINE | STANDALONE | 15 | 15.5 | 1 | -37.769 | 175.2623 |  | 2009-11-23 |  | 2009-12-15 | Microwave | WKT-016-023-B | TRUE | TRUE | 2010-01-15 |  | FALSE | 2010-04-23 | 2010-02-19 | 2010-02-11 |  |  | 2010-03-09 | 2010-03-05 | 3 | 2010-03-09 | 2010-12-07 | 2010-05-05 | 2010-04-27 | 2010-09-10 | 2010-09-08 | 2 | 2010-09-10 | 2010-09-08 | NES | 2010-03-12 | 2010-03-12 | 2010-04-28 | 2010-04-20 | 2 | 2010-05-05 | 2010-04-22 |  |  | 2011-03-28 | 2011-05-05 | 1 |  | 2011-03-22 | 2011-05-05 | 2011-05-12 |  |  | 2011-04-12 |  | 2011-05-09 | 2011-05-09 | 2011-05-13 | 2011-05-19 | 2011-05-29 | 2011-06-14 | 2011-05-30 |  |  |  | 2011-02-07 |  |  |  | 2011-05-12 | 2011-06-24 | 2011-07-31 | 2011-07-28 | 2011-07-31 | 2011-07-27 | 2011-11-10 | 2011-12-01 | Hard matched but plans to be swapped out by Council for lease and consent due to cabinet extension (drawings done). |  | 2011-07-03 | 2011-05-23 | 2011-05-23 | 2011-05-25 | 2011-05-24 | 2011-05-12 | 2011-05-12 | 2011-06-13 | 2011-06-01 |  | 2011-07-18 | [7 empty] | TRUE |  | 2709502 | 6379030 | RSR Junc TeRapa Rd & Victoria St |  | LPR Permitted under the NES. - 22/04/2010 | CELLSITE |  |  | 2014-09-24 | [13 empty] | 2011-07-18 | 2010-02-11
0 | WKT | 1447 | WKT-016-019 | Maeroa | WKT-016-019-D | Norton Rd Industrial | Hamilton | 10 | TIER_2 | ACTIVE | GF | DU5 | P3 | grey | STACK_A | COSITE | 19.9 | 20.5 | 1 | -37.7806 | 175.2525 |  | 2009-11-23 |  | 2009-12-15 | Microwave | WKT-016-038-A | TRUE | TRUE | 2010-02-10 | 2010-02-26 | FALSE | 2010-02-24 | 2010-02-26 | 2010-02-10 |  |  | 2010-03-23 | 2010-03-23 | 3 | 2010-03-31 | 2010-06-25 | 2010-04-29 | 2010-04-27 | 2010-07-09 | 2010-07-09 | 3 | 2010-07-09 | 2010-07-09 | PERMITTED | 2010-04-07 | 2010-04-06 | 2010-05-07 | 2010-04-30 | 2 | 2010-05-14 | 2010-05-07 |  |  | 2011-04-05 | 2011-04-13 | 1 |  | 2011-03-30 | 2011-04-13 | 2011-04-18 |  |  |  |  | 2011-04-13 | 2011-04-13 | 2011-04-29 | 2011-05-05 | 2011-04-29 | 2011-05-27 | 2011-05-16 |  |  |  | 2011-02-07 |  |  |  | 2011-05-12 | 2011-07-01 | 2011-07-31 | 2011-07-28 | 2011-07-31 | 2011-07-27 | 2011-11-10 | 2012-01-31 | Hardmatched with old antennas. Lease variation complete, waiting COC from Council. |  | 2011-06-29 | 2011-04-18 | 2011-04-18 | 2011-05-09 | 2011-05-10 | 2011-04-18 | 2011-04-18 | 2011-06-10 | 2011-06-16 |  | 2011-07-13 | [7 empty] | FALSE |  | 2708610 | 6377775 | Norton Rd |  |  | CELLSITE |  |  | 2014-09-24 | [13 empty] | 2011-07-13 | 2010-02-19
0 | WKT | 1448 | WKT-016-020 | Hamilton South East | WKT-016-020-A | Hamilton SE Vodafone co-lo | Hamilton | 10 | TIER_2 | ACTIVE | COLO | DU | COLO | grey | STACK_A | COLO | 29.7 | 30.2 | 1 | -37.8117 | 175.3283 |  | 2009-11-23 |  | 2009-12-15 | Microwave | WKT-016-012-A | TRUE | TRUE | 2010-02-10 | 2010-02-26 | FALSE | 2010-02-08 | 2010-04-02 | 2010-02-10 |  |  | 2010-02-23 | 2010-02-23 | 3 | 2010-02-23 | 2010-06-25 |  | 2010-03-23 | 2010-07-16 | 2010-07-08 |  | 2011-02-28 | 2011-05-20 | DISCRETIONARY_RESTRICT | 2010-04-01 | 2010-04-09 | 2010-05-14 | 2010-05-10 | 2 | 2010-05-21 | 2010-05-13 |  |  | 2011-03-29 | 2011-04-14 | 2 | 3 | 2011-03-25 | 2011-04-21 | 2011-05-05 |  |  |  |  | 2011-05-13 | 2011-05-30 | 2011-05-17 | 2011-06-07 | 2011-06-05 | 2011-06-12 | 2011-06-16 |  |  |  | 2011-02-07 |  |  |  | 2011-05-12 | 2011-06-27 | 2011-07-31 | 2011-07-28 | 2011-07-31 | 2011-07-25 | 2011-11-08 | 2011-12-01 | Final approval received from VF. Antenna amendment approved by VF and S127 done. | VNZ | 2011-06-13 | 2011-05-03 | 2011-05-03 | 2011-05-09 | 2011-05-12 | 2011-05-09 | 2011-05-05 | 2011-06-23 | 2011-06-20 |  | 2011-07-13 | [7 empty] | FALSE |  | 2715196 | 6374146 | Riverlea Rd., Hamilton South East |  | Resource Consent Reference: 010.2010.21261 -- (37/1/3808) - 13/05/2010 | CELLSITE | [16 empty] | 2011-07-13 | 2010-01-21
0 | WKT | 1449 | WKT-016-021 | Dinsdale South | WKT-016-021-G | 279 Kahikatea Rd | Hamilton | 10 | TIER_2 | ACTIVE | GF | DU | P2 | grey | STACK_A | STANDALONE | 19.5 | 20 | 1 | -37.8058 | 175.2595 |  | 2009-11-23 |  | 2009-12-15 | Microwave | WKT-016-012-A | TRUE | TRUE | 2010-03-22 | 2010-03-31 | FALSE | 2010-04-08 | 2010-03-29 | 2010-03-30 |  |  | 2010-04-15 | 2010-04-15 | 3 | 2010-06-18 | 2010-06-28 | 2010-05-31 | 2010-06-01 | 2010-07-13 | 2010-07-09 | 3 | 2010-07-13 | 2010-07-09 | PERMITTED | 2010-04-21 | 2010-04-19 | 2010-05-21 | 2010-05-10 | 1 | 2010-05-28 | 2010-05-12 |  |  | 2011-03-18 | 2011-04-13 | 1 |  | 2011-03-15 | 2011-04-13 | 2011-04-18 |  |  |  |  | 2011-03-28 | 2011-03-28 | 2011-04-26 | 2011-04-26 | 2011-04-26 | 2011-05-16 | 2011-05-17 |  |  |  | 2011-02-07 |  |  |  | 2011-05-12 | 2011-05-31 | 2011-07-31 | 2011-07-28 | 2011-07-31 | 2011-07-12 | 2011-10-26 | 2011-12-22 | Hardmatched with old antennas. Lease variation completed, Sean doing COC. |  | 2011-05-27 | 2011-04-18 | 2011-04-18 | 2011-04-21 | 2011-05-10 | 2011-04-21 | 2011-04-18 | 2011-04-27 | 2011-06-01 |  | 2011-06-20 | [7 empty] | FALSE |  | 2709151 | 6374954 | 279 Kahikatea Rd |  | Council COC reference: 010/2010/21264 - 12/05/2010 | CELLSITE | [16 empty] | 2011-06-20 | 2010-02-10
0 | WKT | 1450 | WKT-016-022 | Hillcrest | WKT-016-022-A | Hillcrest - Water Tower Co Site | Hamilton | 10 | TIER_2 | ACTIVE | BO | DU5 | NOPOLE | grey | STACK_A | COSITE | 12.3 | 12.4 | 1 | -37.7976 | 175.3162 |  | 2009-11-23 |  | 2009-12-15 | Microwave | WKT-016-023-B | TRUE | TRUE | 2010-01-15 |  | FALSE | 2010-04-23 | 2010-01-19 | 2010-01-19 |  |  | 2010-03-02 | 2010-03-02 | 5 | 2010-03-09 | 2011-04-01 | 2010-06-29 | 2010-06-23 | 2010-11-26 | 2010-12-06 | 4 | 2010-11-30 | 2010-12-06 | PERMITTED | 2010-03-12 | 2010-03-11 | 2010-04-15 | 2010-04-12 | 2 | 2010-04-22 | 2010-04-15 |  |  | 2011-04-08 | 2011-05-06 | 1 |  | 2011-04-04 | 2011-05-06 | 2011-05-13 |  |  |  |  | 2011-05-13 | 2011-05-13 | 2011-06-10 | 2011-06-07 | 2011-06-19 | 2011-06-20 | 2011-06-23 |  |  |  | 2011-02-07 |  |  |  | 2011-05-12 | 2011-07-23 | 2011-07-31 | 2011-07-28 | 2011-07-31 | 2011-07-27 | 2011-11-10 | 2011-12-01 | Hard matched. Lease completed with new antenna, waiting COC from Council. |  | 2011-06-21 | 2011-05-03 | 2011-05-03 | 2011-05-09 | 2011-05-12 | 2011-05-13 | 2011-05-13 | 2011-06-22 | 2011-07-24 |  | 2011-07-18 | [7 empty] | FALSE |  | 2714166 | 6375742 | Hillcrest Water Tower Co Site Hillcrest Bowling Club Cambridge Road Hamilton |  |  | CELLSITE |  |  | 2014-09-24 | [13 empty] | 2011-07-18
0 | WKT | 1451 | WKT-016-023 | Ward St (Main HUB) | WKT-016-023-B | Ward St Hub | Hamilton | 10 | TIER_2 | ACTIVE | RT | DF5 | COLO | grey | STACK_A | COSITE | 42 | 60 | 1 | -37.7862 | 175.2804 |  | 2009-11-23 |  | 2009-12-15 | Fibre Optic | AKL-007-106-A | TRUE | TRUE | 2010-01-21 |  | FALSE | 2010-03-18 |  | 2010-03-12 |  |  | 2010-04-14 | 2010-04-15 | 7 | 2010-09-28 | 2012-05-30 | 2010-04-30 | 2010-04-21 | 2011-01-31 | 2011-02-08 | 6 | 2011-01-31 | 2011-05-20 | DISCRETIONARY_FULL | 2010-04-28 | 2010-04-30 | 2010-09-14 | 2010-09-09 | 4 | 2010-09-17 | 2010-09-22 |  |  | 2011-03-18 | 2011-04-15 | 1 |  | 2011-03-17 | 2011-04-15 | 2011-04-26 |  |  |  |  | 2011-03-24 | 2011-03-24 | 2011-04-30 | 2011-05-13 | 2011-05-15 | 2011-05-09 | 2011-05-15 | [7 empty] | 2011-05-12 | 2011-05-15 | 2011-07-31 | 2011-07-28 | 2011-07-31 | 2011-07-27 | 2011-10-25 | 2012-02-28 | HUB SITE using Telstraclear back-up generator. | KDA | 2011-05-13 | 2011-04-18 | 2011-04-18 | 2011-05-10 | 2011-05-10 | 2011-04-26 | 2011-04-26 | 2011-05-09 | 2011-05-15 |  | 2011-07-18 | [7 empty] | FALSE |  | 2711051 | 6377080 | 48 Ward Street Hamilton |  | Activity status for s127 is Discretionary - 30/04/2010. Ref 37/1/3571C. - 22/09/2010 | CELLSITE |  |  | 2014-09-24 | [13 empty] | 2011-07-18 | 2010-02-10
0 | WKT | 1452 | WKT-016-024 | Rototuna | WKT-016-024-C | Horsham Downs LPR - Sudbury Ct | Hamilton | 10 | TIER_2 | ACTIVE | RSR | DU | P4F | brunswick green | INLINE | STANDALONE | 15 | 15.5 | 1 | -37.7307 | 175.2722 |  | 2009-11-23 |  | 2009-12-15 | Microwave | WKT-016-032-A | TRUE | TRUE | 2010-01-15 |  | FALSE | 2010-08-17 | 2010-08-09 | 2010-08-09 |  |  | 2010-08-16 | 2010-08-17 | 2 | 2010-08-16 | 2010-12-07 | 2010-08-31 | 2010-09-08 | 2010-10-22 | 2010-10-21 | 1 | 2010-12-01 | 2011-12-01 | CONTROLLED | 2010-08-23 | 2010-08-20 | 2010-09-27 | 2010-09-01 | 1 | 2010-10-04 | 2010-09-06 |  |  | 2011-03-28 | 2011-05-13 | 1 |  | 2011-03-22 | 2011-05-13 | 2011-05-23 |  |  | 2011-04-12 |  | 2011-05-23 | 2011-05-24 | 2011-05-27 | 2011-06-01 | 2011-06-09 | 2011-06-21 | 2011-06-11 |  |  |  | 2011-02-07 |  |  |  | 2011-05-12 | 2011-06-29 | 2011-07-31 | 2011-07-28 | 2011-07-31 | 2011-07-25 | 2011-11-08 | 2011-12-01 | RF pref over RT. Hard matched but plans to be swapped out by Council for lease and consent due to cabinet extension (drawings done). |  | 2011-06-26 | 2011-05-23 | 2011-05-23 | 2011-05-25 | 2011-05-24 | 2011-05-23 | 2011-05-23 | 2011-06-16 | 2011-06-17 |  | 2011-07-13 | [7 empty] | TRUE |  | 2710490 | 6383260 | Cnr Thomas Rd & Sudbury Ct, Hamilton |  |  | CELLSITE | [16 empty] | 2011-07-13
0 | WKT | 1453 | WKT-016-025 | Fairfield | WKT-016-025-D | RSR outside Church | Hamilton | 10 | TIER_2 | ACTIVE | RSR | DU5 | P4F | brunswick green | INLINE | STANDALONE | 15 | 15.5 | 1 | -37.7681 | 175.2809 |  | 2009-11-23 |  | 2009-12-15 | Microwave | WKT-016-023-B | TRUE | TRUE | 2010-02-24 |  | FALSE | 2010-04-23 | 2010-03-12 | 2010-03-03 |  |  | 2010-03-26 | 2010-03-25 | 3 | 2010-04-21 | 2011-01-20 | 2010-04-30 | 2010-04-27 | 2010-06-25 | 2010-06-18 | 2 | 2010-09-10 | 2010-09-08 | DISCRETIONARY_RESTRICT | 2010-04-23 | 2011-02-01 | 2010-05-24 | 2011-02-21 | 3 | 2010-05-31 | 2010-05-26 |  |  | 2011-05-18 | 2011-07-01 | 1 |  | 2011-05-11 | 2011-07-01 | 2011-08-01 |  |  | 2011-04-12 |  | 2011-07-19 | 2011-07-20 | 2011-08-12 | 2011-08-22 | 2011-08-10 | 2011-08-10 | 2011-08-19 |  |  |  | 2011-02-07 |  |  |  | 2011-05-12 | 2011-08-25 | 2011-09-01 | 2011-08-25 | 2011-09-12 | 2011-09-09 | 2011-12-23 | 2011-12-22 | Hard matched on smaller cabinet layout. Lease variation with Church to sign and S127 (noise) sent to Council. |  | 2011-08-14 | 2011-07-04 | 2011-07-04 | 2011-08-01 | 2011-08-01 | 2011-07-18 | 2011-08-01 | 2011-08-23 | 2011-08-24 |  | 2011-08-25 | [6 empty] | 2011-08-10 | TRUE |  | 2711147 | 6379097 | between 1087 & 1095 Heaphy Tce (out side the Church), Hamilton |  | Land Use Consent 10.2010.00021282 - (37/1/3812) - 26/05/2010 | CELLSITE |  |  | 2014-09-24 | [12 empty] | 2011-08-22 | 2011-08-25 | 2010-03-10
0 | WKT | 1454 | WKT-016-026 | Nawton West |  |  | Hamilton |  | TIER_9 | [83 empty] | Aim to provide GSM900 voice and U2100 services to indoor levels. Nawton West. Greenfield based on either a GF Pole or LP replacement
0 | WKT | 1455 | WKT-016-027 | Western Heights | WKT-016-027-A | Western Heights - TNZ co-lo | Hamilton | 10 | TIER_2 | ACTIVE | COLO | DU | COLO | grey | STACK_A | COLO | 23.4 | 25 | 1 | -37.7946 | 175.2326 |  | 2009-11-23 |  | 2009-12-15 | Microwave | WKT-016-021-G | TRUE | TRUE | 2010-01-15 |  | FALSE |  | 2010-04-09 | 2010-03-17 |  |  | 2010-04-09 | 2010-03-23 | 4 | 2010-05-27 | 2010-10-26 | 2010-05-07 | 2010-05-07 | 2011-01-31 | 2011-02-01 |  | 2011-01-31 |  | DISCRETIONARY_RESTRICT | 2010-05-14 | 2010-05-27 | 2010-06-25 | 2010-05-31 | 2 | 2010-07-02 | 2010-06-02 |  |  | 2011-05-20 | 2011-06-13 | 2 |  | 2011-05-17 | 2011-07-04 | 2011-06-17 |  |  |  |  | 2011-06-10 | 2011-06-10 | 2011-06-17 | 2011-06-17 | 2011-06-14 | 2011-06-18 | 2011-06-17 |  |  |  | 2011-02-07 |  |  |  | 2011-05-12 | 2011-06-20 | 2011-07-31 | 2011-07-28 | 2011-07-31 | 2011-07-12 | 2011-10-26 | 2011-12-01 | Final approval received. Stage 4 next which requires project plan. | TNZ | 2011-06-19 | 2011-05-16 | 2011-05-18 | 2011-05-18 | 2011-05-19 | 2011-06-13 | 2011-06-17 | 2011-06-09 | 2011-06-17 |  | 2011-06-29 | [7 empty] | FALSE |  | 2706817 | 6376262 | Reservoir Newcastle Rd |  |  | CELLSITE | [16 empty] | 2011-06-29 | 2010-01-28
0 | WKT | 1456 | WKT-016-028 | Te Rapa West |  |  | Hamilton |  | TIER_9 | [83 empty] | Aim to provide GSM900 voice and U2100 services to indoor levels. Te Rapa West - not Tier 2
0 | WKT | 1457 | WKT-016-029 | Western Heights 3G |  |  | Hamilton |  | TIER_9 | [22 empty] | FALSE | [60 empty] | Aim to provide U2100 services to indoor levels. Western Heights 3G 3G only this site: 2 sector (North South) GF arrangement next to Vodafones similar site layout using the Water Board Brick structure near the gate entrance to the main Water Board Compound. 2G to go on the higher location (see separate site WKT-016-027) using the existing Square Tower colo with others. Option A: 3G only Cell Spilt 3G to go with Vodas 3G on the block at street level on Newcastle Road Grid: 2706977 6376329 (2G only is under WKT-016-027 located in the upper part of the compound)
0 | WKT | 1458 | WKT-016-030 | South Chartwell |  |  | Hamilton |  | TIER_9 | [83 empty] | Aim to provide GSM900 voice and U2100 services to indoor levels. South Chartwell. 15m Greenfield Pole - only location is River Road Foodmarket Shops cnr of River Rd and Donny Rd.
0 | WKT | 1459 | WKT-016-031 | Melville |  |  | Hamilton |  | TIER_9 | [22 empty] | FALSE | [60 empty] | Aim to provide GSM900 voice and U2100 services to indoor levels. Melville. Based on 25m Vodo Pole colo. Also a nearby Whoosh unbuilt option at rear 91 Kahikatea Drive. Option A: Colo on Vodafone 25m Pole with spider Arms, Gallager Management. (Preferred) Grid: 2709988 6374147 Option B: On rear of Metalled area back left area (2degrees Leased, 91 Kahikatea Drive) Grid: 2710188 6374493 Option C: 20m GF Pole Adjacent part of Field owned by Gallagher Grid: 2709988 6374147 After site search 25-27 Nov 09: Option A: VFNZ co-lo
0 | WKT | 1460 | WKT-016-032 | Chedworth Park | WKT-016-032-A | Crosby Rd Water Tower | Hamilton | 10 | TIER_2 | ACTIVE | GF | DU5 | P2 | grey | STACK_A | COSITE | 20.2 | 20.7 | 1 | -37.7544 | 175.2906 |  | 2009-11-23 |  | 2009-12-15 | Microwave | WKT-016-004-A | TRUE | TRUE | 2010-01-15 |  | FALSE | 2010-02-08 | 2010-01-19 | 2010-01-19 |  |  | 2010-03-19 | 2010-03-18 | 5 | 2010-05-07 | 2010-06-25 | 2010-07-01 | 2010-07-01 | 2010-11-26 | 2010-12-06 | 5 | 2010-11-30 | 2010-12-06 | DISCRETIONARY_RESTRICT | 2010-03-26 | 2010-03-26 | 2010-07-16 | 2010-07-19 | 5 | 2010-07-23 | 2010-07-21 |  |  | 2011-04-08 | 2011-04-19 | 3 |  | 2011-04-04 | 2011-07-11 | 2011-05-12 |  |  |  |  | 2011-06-05 | 2011-06-09 | 2011-06-20 | 2011-06-23 | 2011-06-22 | 2011-06-26 | 2011-06-27 |  |  |  | 2011-02-07 |  |  |  | 2011-05-12 | 2011-07-01 | 2011-07-31 | 2011-07-28 | 2011-07-31 | 2011-07-25 | 2011-10-24 | 2012-02-02 | Hard matched |  | 2011-06-26 | 2011-05-16 | 2011-05-18 | 2011-05-18 | 2011-05-19 | 2011-05-12 | 2011-05-12 | 2011-06-17 | 2011-06-23 |  | 2011-07-13 | [7 empty] | FALSE |  | 2712040 | 6380585 | opp 89 Crosby Rd |  |  | CELLSITE |  |  | 2014-09-24 | [13 empty] | 2011-07-13 | 2010-02-10
0 | WKT | 1461 | WKT-016-033 | Fitzroy |  |  | Hamilton |  | TIER_9 | [83 empty] | Aim to provide GSM900 voice and U2100 services to indoor levels. Fitzroy . Greenfield site.
0 | WKT | 1462 | WKT-016-034 | Hamilton East | WKT-016-034-C | Intersection of Grey & Naylor | Hamilton | 10 | TIER_2 | ACTIVE | GF | DU5 | OTHERS | grey | STACK_A | STANDALONE | 17 | 17.5 | 2 | -37.7985 | 175.2964 |  | 2009-11-23 |  | 2009-12-15 | Microwave | WKT-016-012-A | TRUE | TRUE | 2010-01-15 |  | FALSE | 2010-03-18 | 2010-03-26 | 2010-03-26 |  |  | 2010-04-15 | 2010-04-08 | 2 | 2010-06-21 | 2010-06-25 | 2010-07-21 | 2010-07-15 | 2010-08-18 | 2010-08-13 |  | 2010-08-18 | 2010-08-13 | PERMITTED | 2010-04-23 | 2011-01-24 | 2010-05-21 | 2011-02-14 | 2 | 2010-05-28 | 2010-05-12 |  |  | 2011-03-25 | 2011-04-26 | 1 |  | 2011-03-23 | 2011-04-26 | 2011-04-18 |  |  |  |  | 2011-04-26 | 2011-04-26 | 2011-05-27 | 2011-05-12 | 2011-05-12 | 2011-05-28 | 2011-05-16 |  |  |  | 2011-02-07 |  |  |  | 2011-05-12 | 2011-06-02 | 2011-07-31 | 2011-07-28 | 2011-07-31 | 2011-07-12 | 2011-10-26 | 2012-01-26 | Hardmatched with old antennas on RC consent only, waiting COC from Council. |  | 2011-05-28 | 2011-05-03 | 2011-05-03 | 2011-05-09 | 2011-05-10 | 2011-04-18 | 2011-04-18 | 2011-05-27 | 2011-06-01 |  | 2011-06-20 | [7 empty] | FALSE |  | 2712422 | 6375681 | 134 Grey Street, Hamilton |  | Council COC Reference: 010/2010/21263 - 12/05/2010 | CELLSITE |  |  | 2014-09-24 | [13 empty] | 2011-06-20 | 2010-03-03
0 | WKT | 1463 | WKT-016-035 | Lugton Park | WKT-016-035-C | LPR - across rd from carpark | Hamilton | 10 | TIER_2 | ACTIVE | RSR | DU5 | P4F | grey | INLINE | STANDALONE | 15 | 15.5 | 2 | -37.7851 | 175.3052 |  | 2009-11-23 |  | 2009-12-15 | Microwave | WKT-016-023-B | TRUE | TRUE | 2010-01-15 |  | FALSE | 2010-04-22 | 2010-04-06 | 2010-03-29 |  |  | 2010-05-06 | 2010-05-10 | 2 | 2010-05-06 | 2010-12-07 | 2010-05-13 | 2010-05-13 | 2010-10-15 | 2010-10-20 | 1 | 2010-10-15 | 2010-10-20 | CONTROLLED | 2010-05-10 | 2010-05-10 | 2010-06-09 | 2010-06-01 | 1 | 2010-06-04 | 2010-06-02 |  |  | 2011-03-28 | 2011-05-13 | 1 |  | 2011-03-22 | 2011-05-13 | 2011-05-23 |  |  |  |  | 2011-06-18 | 2011-05-27 | 2011-06-22 | 2011-06-01 | 2011-06-01 | 2011-06-03 | 2011-06-03 |  |  |  | 2011-02-07 |  |  |  | 2011-05-12 | 2011-06-12 | 2011-07-31 | 2011-07-28 | 2011-07-31 | 2011-07-12 | 2011-10-10 | 2012-02-03 |  |  | 2011-06-12 | 2011-05-23 | 2011-05-23 | 2011-05-25 | 2011-05-24 | 2011-05-23 | 2011-05-23 | 2011-06-15 | 2011-06-13 |  | 2011-06-24 | [7 empty] | FALSE |  | 2713238 | 6377146 | Lugton Park Opposite 147 Old Farm Rd, Hamilton |  | Land Use Resource Consent 010.2010.21349 - (38/1/4337) - 03/06/2010 | CELLSITE |  |  | 2014-09-24 | [13 empty] | 2011-06-24
0 | WKT | 1464 | WKT-016-036 | Fairview Downs | WKT-016-036-A | Raymond Park LPR | Hamilton | 10 | TIER_2 | ACTIVE | RSR | DU | P4F | brunswick green | INLINE | STANDALONE | 15 | 15.5 | 1 | -37.7612 | 175.3053 |  | 2009-11-23 |  | 2009-12-15 | Microwave | WKT-016-016-D | TRUE | TRUE | 2010-01-15 |  | FALSE | 2010-02-08 | 2010-03-12 | 2010-02-10 |  |  | 2010-03-08 | 2010-03-05 | 5 | 2010-08-06 | 2010-10-14 | 2010-09-30 | 2010-05-26 | 2010-10-08 | 2010-09-08 | 5 | 2010-11-30 | 2010-09-08 | CONTROLLED | 2010-08-10 | 2011-02-01 | 2010-09-07 | 2011-03-14 | 5 | 2010-09-10 | 2011-03-14 |  |  | 2011-07-01 | 2011-07-01 | 1 |  | 2011-07-01 | 2011-07-01 | 2011-08-01 |  |  |  |  | 2011-07-26 | 2011-07-25 | 2011-08-04 | 2011-08-04 | 2011-08-02 | 2011-08-05 | 2011-08-05 |  |  |  | 2011-02-07 |  |  |  | 2011-05-12 | 2011-08-08 | 2011-09-01 | 2011-08-16 | 2011-09-01 | 2011-08-31 | 2011-12-14 | 2011-12-22 | Hard matched. Lease has larger cabinets but requires new consent. |  | 2011-08-08 | 2011-07-04 | 2011-07-04 | 2011-08-01 | 2011-08-01 | 2011-08-01 | 2011-08-01 | 2011-08-04 | 2011-08-04 |  | 2011-08-17 | [6 empty] | 2011-08-02 | FALSE |  | 2713314 | 6379798 | opp cnr Raymond St and Saraindah |  | RMA status under the NES is for a Controlled Activity. | CELLSITE | [15 empty] | 2011-08-16 | 2011-08-17 | 2010-02-10
0 | WKT | 1465 | WKT-016-037 | Silverdale |  |  | Hamilton |  | TIER_9 | [83 empty] | Aim to provide GSM900 voice and U2100 services to indoor levels. Silverdale. 20m Greenfield option based on shops at Silverdale Shopping Center or a Lightpole replacement
0 | WKT | 1466 | WKT-016-038 | Frankton | WKT-016-038-A | Frankton Kordia co-lo | Hamilton | 10 | TIER_2 | ACTIVE | COLO | DU5 | COLO | grey | STACK_A | COLO | 17.6 | 41.5 | 1 | -37.7907 | 175.2653 |  | 2009-11-23 |  | 2009-12-15 | Microwave | WKT-016-023-B | TRUE | TRUE | 2010-01-14 | 2010-01-14 | FALSE | 2010-04-23 | 2010-01-14 | 2010-01-14 |  |  | 2010-03-12 | 2010-03-12 | 1 | 2010-03-12 | 2010-03-12 | 2010-05-14 | 2010-04-20 | 2010-07-16 | 2010-07-14 |  | 2011-02-28 | 2011-11-30 |  | 2010-05-11 | 2010-05-11 | 2010-06-04 | 2010-06-03 | 1 | 2010-06-04 | 2010-06-03 |  |  |  | 2011-06-20 | 1 |  |  | 2011-06-20 | 2011-06-09 |  |  |  |  | 2011-06-20 | 2011-06-09 | 2011-06-24 | 2011-06-17 | 2011-06-17 | 2011-06-28 | 2011-06-27 |  |  |  | 2011-02-07 |  |  |  | 2011-05-12 | 2011-07-01 | 2011-07-31 | 2011-07-28 | 2011-07-31 | 2011-07-26 | 2011-11-09 | 2011-12-22 | Antenna change to Kathrein 742225, no new RC required. Schedule received from Kordia and with 2degrees for signing. | KDA | 2011-06-28 | 2011-05-16 | 2011-05-18 | 2011-05-18 | 2011-05-19 | 2011-06-09 | 2011-06-09 | 2011-06-24 | 2011-06-24 |  | 2011-07-18 | [7 empty] | FALSE |  | 2709706 | 6376617 | Hamilton Station Fraser St |  |  | CELLSITE |  |  | 2014-09-24 | [13 empty] | 2011-07-18 | 2010-03-12
0 | WKT | 1467 | WKT-016-039 | Deanwell | WKT-016-039-A | VF Co-lo Deanwell | Hamilton | 10 | TIER_2 | ACTIVE | COLO | DU | COLO | grey | STACK_A | COLO | 22.3 | 23.8 | 1 | -37.8207 | 175.2684 |  | 2009-11-23 |  | 2009-11-23 | Microwave | WKT-016-012-A | TRUE | TRUE | 2010-02-10 | 2010-02-26 | FALSE | 2010-02-24 |  | 2010-02-10 |  |  | 2010-02-23 | 2010-02-24 | 3 | 2010-02-23 | 2010-06-25 |  | 2010-03-23 | 2010-08-06 | 2010-08-05 |  | 2011-02-28 | 2011-11-15 | PERMITTED | 2010-04-13 | 2010-04-08 | 2010-05-11 | 2010-05-06 | 2 | 2010-05-18 | 2010-05-10 |  |  | 2011-03-30 | 2011-04-20 | 1 |  | 2011-03-25 | 2011-04-20 | 2011-05-13 |  |  |  |  | 2011-05-25 | 2011-05-25 | 2011-05-25 | 2011-06-03 | 2011-06-04 | 2011-06-15 | 2011-06-16 |  |  |  | 2011-02-07 |  |  |  | 2011-05-12 | 2011-06-27 | 2011-07-31 | 2011-07-28 | 2011-07-31 | 2011-07-26 | 2011-11-09 | 2011-12-01 | Final approval received from VF. Antenna amendment approved by VF and COC done. | VNZ | 2011-06-19 | 2011-05-03 | 2011-05-03 | 2011-05-09 | 2011-05-10 | 2011-05-09 | 2011-05-13 | 2011-06-16 | 2011-06-23 |  | 2011-07-13 | [7 empty] | FALSE |  | 2709898 | 6373281 | 154 Collins Rd |  |  | CELLSITE | [16 empty] | 2011-07-13 | 2010-01-21
0 | WKT | 1468 | WKT-016-040 | Waikato University 2 | WKT-016-040-A | Waikato Uni - LPR #2 | Hamilton | 10 | TIER_2 | ACTIVE | RSR | DU5 | P4A | grey | INLINE | STANDALONE | 15 | 15.5 | 3 | -37.785 | 175.3209 |  | 2009-11-23 |  | 2010-03-22 | Leased Line | WKT-016-023-B | TRUE | TRUE | 2010-03-22 |  | FALSE | 2010-03-25 | 2010-03-29 | 2010-03-26 |  |  | 2010-05-06 | 2010-05-06 | 2 | 2010-05-06 | 2010-12-07 | 2010-05-20 | 2010-05-13 | 2010-09-10 | 2010-09-08 | 1 | 2010-09-10 | 2010-09-08 | CONTROLLED | 2010-05-07 | 2010-05-07 | 2010-06-17 | 2010-06-15 | 1 | 2010-06-24 | 2010-06-18 |  |  | 2011-05-06 | 2011-05-13 | 1 |  | 2011-05-04 | 2011-05-13 | 2011-05-16 |  |  | 2011-04-12 |  | 2011-06-02 | 2011-06-01 | 2011-06-06 | 2011-06-16 | 2011-06-08 | 2011-06-14 | 2011-06-11 | [7 empty] | 2011-05-12 | 2011-06-30 | 2011-07-31 | 2011-07-28 | 2011-07-31 | 2011-07-27 | 2011-11-10 | 2011-12-01 | Hard matched but plans to be swapped out by Council for lease and consent due to cabinet extension (drawings done). |  | 2011-06-14 | 2011-05-23 | 2011-05-23 | 2011-05-25 | 2011-05-24 | 2011-05-16 | 2011-05-16 | 2011-06-17 | 2011-06-27 |  | 2011-07-18 | [7 empty] | TRUE |  | 2714622 | 6377127 | Cnr Hillcrest & Silverdale Rds, Hamilton |  | Land Use Consent Ref: 10.2010.21345 (38/1/4336) - 18/06/2010 | CELLSITE |  |  | 2014-09-24 | [13 empty] | 2011-07-18
0 | WKT | 1469 | WKT-016-041 | Rototuna North | WKT-016-041-A | LPR | Hamilton | 10 | TIER_2 | ACTIVE | RSR | DU | P4F | grey | INLINE | STANDALONE | 15 | 15.5 |  | -37.7232 | 175.2544 |  | 2010-05-21 |  | 2010-05-21 | Microwave | WKT-016-016-D | TRUE | TRUE | 2010-06-17 | 2010-06-17 | FALSE | 2010-06-24 | 2010-06-24 | 2010-06-24 |  |  | 2010-07-01 | 2010-07-06 | 2 | 2010-07-01 | 2010-12-07 | 2010-07-23 | 2010-07-07 | 2010-09-10 | 2010-09-08 | 1 | 2010-09-10 | 2010-09-08 | PERMITTED | 2010-07-13 | 2010-07-12 | 2010-08-13 | 2010-08-12 | 1 | 2010-08-20 | 2010-08-13 |  |  | 2011-03-28 | 2011-05-26 | 1 |  | 2011-03-22 | 2011-05-26 | 2011-05-23 |  |  |  |  | 2011-06-13 | 2011-06-01 | 2011-06-17 | 2011-06-22 | 2011-06-08 | 2011-06-25 | 2011-06-27 |  |  |  | 2011-02-07 |  |  |  | 2011-05-12 | 2011-07-01 | 2011-07-31 | 2011-07-28 | 2011-07-31 | 2011-07-27 | 2011-11-10 | 2011-12-22 | Hard matched but plans to be swapped out by Council for lease and consent due to cabinet extension (drawings done). |  | 2011-06-25 | 2011-05-23 | 2011-05-23 | 2011-05-25 | 2011-05-24 | 2011-05-23 | 2011-05-23 | 2011-06-17 | 2011-06-17 |  | 2011-07-13 | [7 empty] | FALSE |  | 2708943 | 6384133 | cnr Resolution Drive & Borman Rd, Hamilton |  | Application reference 010.2010.21535 (35/1/483) - 22/07/2010 | CELLSITE | [16 empty] | 2011-07-13
0 | WKT | 1470 | WKT-016-042 | Hamilton TNZ Exchange TX Only | WKT-016-042-A | TX Site | Hamilton | 1 | TIER_3 | ACTIVE | COLO | TX |  |  |  | COLO |  |  |  | -37.7887 | 175.2812 | [6 empty] | FALSE | FALSE |  |  | FALSE | [6 empty] | 2012-08-23 | 1 |  | 2012-08-23 | [50 empty] | RACK SPACE ONLY. Will only be required once site number increase, i.e. after 2012 build period. | [14 empty] | TRANSMISSION_ONLY |  |  | HARDMATCH |  | FALSE |  | 2711115 | 6376801 |  |  |  | TXSITE | WIPHOLDING
0 | WKT | 1471 | WKT-016-043 | Hamilton Disaster Recovery | WKT-016-043-A | DR site | Hamilton | 1 | TIER_6 | ACTIVE | RT | TX | RT |  |  | STANDALONE |  |  |  | -37.7812 | 175.2765 | [6 empty] | FALSE | FALSE |  |  | FALSE | [55 empty] | 2013-01-01 |  | 2013-01-01 |  |  | SOA and PAC date entered so Finance can recognise site (RB 11 Mar 2014) | [19 empty] | FALSE |  | 2710717 | 6377645 | 1 Princess Street Hamilton Central Hamilton |  |  | TXSITE
0 | WKT | 1472 | WKT-016-044 | Hamilton Chorus Co-lo | WKT-016-044-A | Hamilton Chorus TX only | Hamilton |  | TIER_6 | ACTIVE | COLO | TX | COLO |  |  | COLO | [103 empty] | TXSITE | WIPACTIVE
0 | WKT | 1473 | WKT-016-045 | Waikato Hospital expansion | WKT-016-045-A | Hague Street Carpark | Hamilton | 22 | 2015P | ACTIVE | RT | DF5 | RT |  |  | COSITE |  |  |  | -37.805 | 175.2841 | [6 empty] | FALSE | FALSE |  |  | FALSE |  | 2015-03-06 | 2015-03-04 | 2015-03-10 | 2015-03-06 | 2015-04-21 | 2015-04-10 | 2 | 2015-06-08 | 2015-06-04 | 2015-06-26 | 2015-06-23 | 2015-07-29 | 2015-08-06 |  | 2015-07-31 | 2015-08-10 | DISCRETIONARY_RESTRICT | 2015-06-08 | 2015-06-08 | 2015-07-20 | 2015-07-03 | 1 | 2015-07-27 | 2015-07-03 | 2015-06-08 | 2015-06-09 | 2015-06-19 | 2015-06-26 | 1 |  | 2015-06-26 | 2015-06-26 | [27 empty] | 19.02.15 - Hospital contact on AL will arrange caravan for week beginning 2nd March | [17 empty] | HARDMATCH |  | FALSE |  | 2711319 | 6374992 | Hague Street Carpark, Waikato Hospital, Hamilton |  |  | CELLSITE | WIPACTIVE |  |  | CAPACITY | [13 empty] | 2015-03-06
0 | WKT | 1474 | WKT-017-001 | Mystery Creek |  |  | Waipa District |  | TIER_9 | [22 empty] | FALSE
0 | WKT | 1475 | WKT-017-002 | Cambridge | WKT-017-002-A | Cambridge - GF | Waipa District | 3 | 2014 | ACTIVE | GF | DU | T2 20 UF | Grey | STACK_A | STANDALONE | 25 | 20 | 1 | -37.8909 | 175.4696 |  |  |  |  | Fibre Optic | WKT-016-023-B | FALSE | FALSE |  |  | FALSE |  | 2012-04-02 | 2012-04-02 | 2012-04-05 | 2012-04-05 | 2012-08-15 | 2012-08-16 | 2 | 2012-08-15 | 2014-05-12 | 2012-08-31 | 2012-08-20 | 2012-10-05 | 2012-10-04 | 1 | 2012-10-05 | 2012-10-04 | DISCRETIONARY_FULL | 2012-09-21 | 2012-09-25 | 2012-10-24 | 2012-10-11 | 1 | 2012-10-31 | 2012-10-17 | 2014-02-25 | 2014-02-24 | 2014-04-04 | 2014-04-01 | 2 |  | 2014-04-04 | 2014-04-08 | [5 empty] | 2014-05-14 | 2014-05-12 | 2014-06-18 | 2014-06-13 | 2014-06-27 | 2014-07-09 | 2014-07-09 | 2014-07-08 | 2014-07-07 | [7 empty] | 2014-07-31 | 2014-07-23 |  |  |  |  | 6 month commencement. 13.02.14 - BR and team to visit Monday 24.02.14 19.02.14 - Existing pole in stock to be used - LC/008/03/26 24.02.14 - Team visited site. CDI issued. 10.03.14 Await CD's. Geo Tech done. Boundry to be pegged 12.03.14. 24.03.14 Chris and Ritchie to revisit site today. 3 sets of pipes under propoded site. Need to establish depth and diameter - may require design change to foundations. Earth resesitivity exceeds 10 ohms - Alex looking into solution 01.04.14 Small private sewer pipe needs to be relocated, Ritchie looking into it. Alex advises we need quite a bit of earthing to bring down the levels. Meeting with Sue and her husband on Friday to go over the plans. | [10 empty] | 2014-07-09 | 2014-07-09 |  |  | HAMILTON_ROTORUA | 2014-06-26 | 2014-06-26 | BUILD | 2014-06-25 | FALSE |  | 2727386 | 6365021 | 32 Lake St Cambridge |  | Council Ref LU/0135/12 - 17/10/2012 | CELLSITE |  |  | 2015-10-28 |  |  |  |  | 2014-05-12 | [9 empty] | 2012-04-05
0 | WKT | 1476 | WKT-017-003 | Karapiro | WKT-017-003-A | Karapiro | Waipa District | 1 | TIER_3 | ACTIVE | GF | DU | T2 25 RH |  | STACK_A | COSITE | 20 | 20 | 1 | -37.8638 | 175.538 |  |  |  |  | Fibre Optic | WKT-016-023-B | FALSE | FALSE |  |  | FALSE |  | 2012-03-08 | 2012-03-08 | 2012-03-13 | 2012-03-13 | 2012-04-24 | 2012-05-21 | 1 | 2012-04-24 | 2012-05-21 | 2012-06-25 | 2012-05-23 | 2012-07-27 | 2012-07-25 |  | 2012-08-06 | 2012-08-07 | PERMITTED | 2012-05-31 | 2012-06-05 | 2012-07-12 | 2012-06-28 | 1 | 2012-07-19 | 2012-07-05 |  |  | 2012-10-18 | 2012-10-26 | 2 |  | 2012-10-18 | 2012-11-02 | 2012-11-14 |  |  |  |  | 2012-11-09 | 2012-11-07 | 2012-11-29 | 2012-11-28 | 2012-11-22 | 2012-12-04 | 2012-12-04 | 2012-11-26 | 2012-11-26 | [6 empty] | 2012-12-05 | 2012-12-14 | 2012-12-13 | 2013-01-15 | 2012-12-17 | 2013-05-17 | 2013-05-08 | 5 snags still be be addressed, design, feeder chain and photos required of S2 azimuth change 09/04/13 - No FAN yet. FAC reforecasted |  | 2012-12-05 | 2012-11-06 | 2012-10-06 | 2012-11-13 | 2012-11-14 | 2012-11-12 | 2012-11-14 | 2012-11-29 | 2012-11-27 | 2012-12-06 | 2012-12-06 |  |  | HAMILTON_ROTORUA | 2012-11-19 | 2012-11-22 | BUILD | 2012-11-22 | FALSE |  | 2733481 | 6367856 | Gudex Rd, Sanitorium Hill, Cambridge |  | Council Ref PG/0023/12 - 29/06/2012 | CELLSITE | [15 empty] | 2012-12-06 | 2012-12-07 | 2012-03-13
0 | WKT | 1477 | WKT-017-004 | Lake Karapiro | WKT-017-004-B | VF Co-lo Lake Karapiro | Waipa District | 22 | TIER_5 | ACTIVE | COLO | DF | COLO |  | STACK_A | COLO | 24 | 25 |  | -37.9651 | 175.6003 |  |  |  |  | Microwave | WKT-017-003-A | FALSE | FALSE |  |  | FALSE |  | 2015-11-26 | 2015-11-26 | 2015-12-01 | 2015-12-01 | 2015-12-22 | 2015-12-22 | 1 | 2016-01-11 | 2015-12-22 | 2016-03-28 |  | 2016-04-18 |  |  | 2016-04-25 |  | PERMITTED | 2016-03-28 |  | 2016-04-25 |  |  | 2016-04-29 |  | 2016-03-28 |  | 2016-04-28 |  |  |  | 2016-05-05 | [6 empty] | 2016-06-27 |  | 2016-07-25 |  |  | 2016-08-08 | [10 empty] | 2016-09-12 | [5 empty] | VF data pack requested in Oct 21/10/15 - VF data pack received 22/1/16- VF Colo application submitted | VNZ | [9 empty] | 2016-08-22 | [6 empty] | BUILD |  | FALSE |  | 2738630 | 6356465 | 1507 Maungatautari Rd, Lake Karapiro Cambridge |  |  | CELLSITE | WIPACTIVE |  |  | ROAMING |  |  |  | 2016-05-09 | [5 empty] | 2016-06-06 |  |  |  | 2015-12-01
0 | WKT | 1478 | WKT-017-005 | Kihikihi | WKT-017-005-B | Co-Site VF | Waipa District | 1 | TIER_3 | ACTIVE | GF | DU | T2 25 RF |  | STACK_A | COSITE |  |  | 1 | -38.023 | 175.363 |  |  |  |  | Fibre Optic | WKT-016-023-B | FALSE | FALSE |  |  | FALSE |  |  | 2012-04-03 |  | 2012-04-05 | 2012-05-25 | 2012-05-31 | 1 | 2012-05-25 | 2012-05-31 | 2012-06-29 | 2012-07-02 | 2012-08-31 | 2012-08-23 |  | 2012-09-07 | 2012-08-23 | PERMITTED | 2012-07-06 | 2012-07-09 | 2012-07-17 | 2012-07-17 | 1 | 2012-07-20 | 2012-07-19 | 2012-09-03 |  | 2012-10-18 | 2012-11-13 | 1 |  | 2012-10-18 | 2012-11-13 | 2012-11-14 |  |  |  |  | 2012-11-02 | 2012-10-31 | 2012-12-05 | 2012-12-05 | 2012-11-22 | 2012-12-12 | 2012-12-11 | 2012-11-23 | 2012-11-26 | [6 empty] | 2012-12-11 | 2012-12-14 | 2012-12-14 | 2013-01-15 | 2012-12-17 | 2013-06-21 | 2013-05-31 | 8 snags still be be addressed, design, locks and cabinet touch up. 09/04/13 - No FAN yet. FAC reforecasted 31/05/13 - FAC signed |  | 2012-12-12 | 2012-10-06 | 2012-10-06 | 2012-11-05 | 2012-11-14 | 2012-11-12 | 2012-11-14 | 2012-11-29 | 2012-11-28 | 2012-12-12 | 2012-12-12 |  |  | HAMILTON_TEKUITI | 2012-11-18 | 2012-11-22 | BUILD | 2012-11-22 | FALSE |  | 2717621 | 6350626 | 44 Puahue Rd Kihikihi |  | Council Ref PG/0025/12. Parts of site tagged by Waipa DC as being subject to previous effluent disposal and therefore contaminated. - 19/07/2012 | CELLSITE |  |  | 2015-03-19 | [12 empty] | 2012-12-13 | 2012-12-13
0 | WKT | 1479 | WKT-017-006 | Te Awamutu | WKT-017-006-D | Te Awamutu water tank | Waipa District | 1 | TIER_3 | ACTIVE | BO | DU | BO |  | STACK_A | COSITE |  |  | 1 | -37.9943 | 175.3243 |  |  |  |  | Fibre Optic | WKT-016-023-B | FALSE | FALSE |  |  | FALSE |  | 2012-03-08 | 2012-03-08 | 2012-03-13 | 2012-03-13 | 2012-04-24 | 2012-05-01 | 4 | 2012-04-24 | 2014-12-04 | 2012-06-29 | 2012-06-27 | 2013-04-12 | 2013-05-27 |  | 2013-04-19 | 2013-05-27 | DISCRETIONARY_FULL | 2012-07-19 | 2012-07-23 | 2012-08-31 | 2012-08-15 | 3 | 2012-09-07 | 2012-08-23 | 2012-09-03 |  | 2012-10-15 | 2012-12-06 | 2 |  | 2012-10-15 | 2013-02-07 |  |  |  | 2013-03-21 |  | 2013-05-28 | 2013-05-28 | 2013-06-12 | 2013-06-10 | 2013-06-19 | 2013-06-28 | 2013-07-01 | 2013-06-21 | 2013-06-21 | [6 empty] | 2013-07-01 | 2013-07-05 | 2013-07-04 | 2013-08-26 | 2013-07-23 | 2013-10-21 | 2013-12-12 | Back and forth on CD detail means meeting now delayed until March. 18/03/13 - Raj will look after this site for Andrew. WO2 issued, and TCF letters to be dropped this week 21/03/13 - Chorus advised of revised RFS dates 26/03/13 - need urgent resolution for lease signing 22/05/13 - Lease excuted civil start 28/5 forcasted 04/07/13 - SOA 23/07/13 - PAC signed 12/12/13 - FAC signed |  | 2013-06-28 | [6 empty] | 2013-06-28 | 2013-06-28 | 2013-07-02 | 2013-07-05 |  |  | HAMILTON_TEKUITI | 2013-06-21 | 2013-06-21 | BUILD | 2013-06-20 | TRUE | 2013-03-21 | 2714310 | 6353895 | 31 Greenhill Drive Waipa Te Awamutu |  | Council Ref LU/0101/12 - 23/08/2012 | CELLSITE |  |  | 2015-03-19 | [12 empty] | 2013-07-04 | 2013-07-04 | 2012-03-13
0 | WKT | 1480 | WKT-017-007 | Deanwell |  |  | Waipa District |  | TIER_9 | [22 empty] | FALSE | [60 empty] | (formerly WKT-016-014.) Deanwell. Based on Voda 20m Pole colo. Option A: Colo on Voda 20m Pole with spider Arms, Anglo Ind Park Grid: 2709893 6373289 Option B: 20m GF Pole Same Industral Park - Several GF options Grid; 2709873 6373269 After site search 25-27 Nov 09: Option A: VFNZ co-lo
0 | WKT | 1481 | WKT-017-008 | Rukuhia | WKT-017-008-B | SH 3 Ohaupo Rd | Waipa District | 10 | TIER_2 | ACTIVE | GF | DU | P2 | grey | STACK_A | STANDALONE | 20 | 20.5 | 1 | -37.8493 | 175.3057 |  | 2009-11-23 |  | 2009-12-15 | Microwave | WKT-016-039-A | TRUE | TRUE | 2010-01-15 |  | FALSE | 2010-04-14 | 2010-04-16 | 2010-04-13 |  |  | 2010-04-22 | 2010-04-23 | 4 | 2010-04-22 | 2010-08-04 | 2010-05-31 | 2010-06-01 | 2010-08-05 | 2010-08-05 | 4 | 2010-08-05 | 2010-08-05 | DISCRETIONARY_FULL | 2010-05-20 | 2010-05-21 | 2010-08-13 | 2010-08-12 | 4 | 2010-08-20 | 2010-08-16 |  |  | 2011-07-08 | 2011-07-08 | 1 |  | 2011-04-25 | 2011-07-08 | 2011-08-01 |  |  |  |  | 2011-07-25 | 2011-07-21 | 2011-08-10 | 2011-08-10 | 2011-08-08 | 2011-08-11 | 2011-08-11 |  |  |  | 2011-02-07 |  |  |  | 2011-05-12 | 2011-08-15 | 2011-09-01 | 2011-08-16 | 2011-09-01 | 2011-09-01 | 2011-12-15 | 2011-12-22 | Hardmatched with new antenna for RC, lease variation signed by LO, just needs trustees signature. |  | 2011-08-12 | 2011-07-04 | 2011-07-04 | 2011-08-01 | 2011-08-01 | 2011-08-01 | 2011-08-01 | 2011-08-17 | 2011-08-17 |  | 2011-08-18 | [6 empty] | 2011-08-08 | FALSE |  | 2713092 | 6370032 | SH 3 Ohaupo Rd near Raynes Rd junction |  |  | CELLSITE | [15 empty] | 2011-08-17 | 2011-08-25
0 | WKT | 1482 | WKT-017-009 | Hamilton Airport | WKT-017-009-C | Hamilton Airport adjacent to Motels | Waipa District | 10 | TIER_2 | ACTIVE | GF | DU | P2 | green | STACK_A | STANDALONE | 18 | 18.5 | 3 | -37.8687 | 175.3373 |  | 2009-11-23 |  | 2009-12-15 | Leased Line | WKT-016-023-B | TRUE | TRUE | 2010-01-15 |  | FALSE | 2010-05-26 |  | 2010-04-26 |  |  | 2010-05-07 | 2010-05-10 | 5 | 2010-07-19 | 2011-02-11 | 2010-08-06 | 2010-08-04 | 2011-03-31 | 2011-05-25 | 4 | 2011-03-31 | 2011-11-30 | PERMITTED | 2010-07-28 | 2011-02-11 | 2010-08-31 | 2011-02-25 | 5 | 2010-09-17 | 2010-08-30 |  |  | 2011-07-06 | 2011-07-08 | 1 |  | 2011-07-01 | 2011-07-08 | 2011-08-01 |  |  |  |  | 2011-08-08 | 2011-08-02 | 2011-08-11 | 2011-08-11 | 2011-08-11 | 2011-08-20 | 2011-08-20 | [7 empty] | 2011-05-12 | 2011-08-25 | 2011-09-01 | 2011-08-25 | 2011-09-06 | 2011-09-06 | 2011-12-05 | 2012-02-22 |  |  | 2011-08-22 | 2011-07-04 | 2011-07-04 | 2011-08-01 | 2011-08-01 | 2011-08-01 | 2011-08-01 | 2011-08-24 | 2011-08-24 |  | 2011-08-25 | [6 empty] | 2011-08-11 | FALSE |  | 2715814 | 6367805 | adjacent to Motels |  |  | CELLSITE | [15 empty] | 2011-08-22 | 2011-08-25 | 2010-04-26
0 | WKT | 1483 | WKT-017-010 | Cambridge South |  |  | Waipa District |  | TIER_9 | [22 empty] | FALSE
0 | WKT | 1484 | WKT-017-011 | RBI - Mystery Events Centre | WKT-017-011-A | RBI Mystery Creek | Waipa District | 1 | TIER_3 | ACTIVE | RBI | DU | RBI Pole |  | STACK_A | COLO | 25 |  | 1 | -37.874 | 175.3511 |  |  |  |  | Fibre Optic | WKT-016-023-B | FALSE | FALSE |  |  | FALSE |  | 2012-02-10 | 2012-02-10 |  | 2012-02-16 |  | 2012-02-16 | 1 | 2012-02-16 | 2012-02-16 |  | 2011-12-19 |  | 2011-12-19 |  |  | 2011-12-19 |  |  | 2012-01-20 |  | 2012-01-20 | 1 |  | 2012-01-20 | 2012-06-05 | 2012-06-05 | 2012-06-05 | 2012-06-05 | 1 |  | 2012-06-05 | 2012-06-05 | [5 empty] | 2012-07-31 | 2012-07-31 | 2012-07-31 | 2012-07-31 | 2012-07-31 | 2012-09-11 | 2012-09-11 | 2012-08-27 | 2012-08-24 | [6 empty] | 2012-09-12 | 2012-10-03 | 2012-10-03 | 2012-10-03 | 2012-10-03 | 2013-04-15 | 2013-04-12 | 2 snags remaining; VF closure documentation, this site was the test site, waiting for VF to confirm OK before sending the others Dissimilar metals which can hopefully be removed as a snag. 09/04/13 - FAN with NOC and Vicente for signing 12/04/13 FAC signed | VNZ | 2012-09-11 | 2012-07-02 | 2012-07-02 | 2012-08-24 | 2012-08-24 |  |  | 2012-09-03 | 2012-08-27 | 2012-09-14 | 2012-09-19 |  |  | RBI | 2012-08-20 | 2012-08-24 | BUILD | 2012-08-30 | FALSE |  | 2717011 | 6367183 | Gate 2 125 Mystery Vreek Road Ohaupo Hamilton |  |  | CELLSITE | [15 empty] | 2012-09-19 | 2012-09-19 | 2012-02-16
0 | WKT | 1485 | WKT-017-012 | RBI - Ngahinapouri | WKT-017-012-A | RBI - Ngahinapouri | Waipa District | 22 | TIER_4 | ACTIVE | RBI | DU | RBI Pole |  | STACK_A | COLO | 25 |  |  | -37.8827 | 175.1942 |  |  |  |  | Fibre Optic | WKT-016-023-B | FALSE | FALSE |  |  | FALSE |  | 2012-02-23 | 2012-02-23 | 2012-06-14 | 2012-06-14 | 2012-06-14 | 2012-06-14 | 1 | 2015-03-27 | 2012-06-14 |  | 2012-07-26 |  | 2012-07-26 |  |  | 2012-07-26 | DISCRETIONARY_RESTRICT | 2012-07-26 | 2012-01-16 | 2012-07-26 | 2012-02-29 | 1 | 2012-07-26 | 2012-07-26 | 2015-04-30 | 2015-03-31 | 2015-06-15 | 2015-03-31 | 1 |  | 2015-06-22 | 2015-03-31 | [5 empty] | 2015-06-16 | 2015-06-16 | 2015-06-30 | 2015-06-24 | 2015-06-16 | 2015-06-30 | 2015-07-01 | 2015-06-30 | 2015-06-23 | [6 empty] | 2015-08-01 | 2015-07-20 | 2015-07-22 | 2015-07-29 | 2015-07-30 |  |  | New forcast relevant facility from Vodafone 4 October Downgraded to Hardmatch. 19.02.15 - resubmitted RBI application to VF with antenna change to 266 and 6 feeders. 19.2.15 - received the schedule of site specific conditions from VF and the RBI charges 25.2.15 - ready for contractor to submit Project Plan - to note on plan 2nd set on antenna will not be installed on day 1. 9/3/15 - only the TX equipment has a POR raised for this - awaiting PO approval 27/3/15 - antenna still to be ordered - all other equipment ordered (due mid June) - awaiting TX specs then will submit BI to Huawei 1/4/15 - BI sent to Huawei 1/5/15 - PP submitted to VF 7/5/15 - POR for build submitted 5/5 - awaiting PO6 approval | VNZ | 2015-07-01 | [6 empty] | 2015-06-26 | 2015-06-26 | 2015-07-07 | 2015-07-08 |  |  | RBI | 2015-06-30 | 2015-06-23 | BUILD | 2015-06-16 | FALSE |  | 2703196 | 6366573 | 1447 Kakaramea Road Ngahinapouri |  |  | CELLSITE |  |  |  | ROAMING |  |  | 2015-04-24 |  | 2015-03-30 |  | 2015-04-01 |  | 2015-04-15 |  | 2015-05-15 | 2015-07-15 |  | 2012-06-14
0 | WKT | 1486 | WKT-017-013 | RBI - Wharepapa South |  |  | Waipa District |  | RBI | [22 empty] | FALSE
0 | WKT | 1487 | WKT-017-014 | RBI - Te Miro |  |  | Waipa District |  | RBI | [22 empty] | FALSE
0 | WKT | 1488 | WKT-017-015 | Pukeroro | WKT-017-015-A | Pukeroro GF | Waipa District | 22 | TIER_5 | ACTIVE | GF | DF | T2 25 RF |  | STACK_A | COSITE | 24 | 25 |  | -37.883 | 175.4223 |  |  |  |  | Microwave |  | FALSE | FALSE |  |  | FALSE |  | 2015-11-26 | 2015-11-26 | 2015-12-03 | 2015-12-01 | 2015-12-22 | 2015-12-22 | 1 | 2016-01-11 | 2015-12-22 | 2016-02-29 |  | 2016-04-11 |  |  | 2016-04-25 |  | PERMITTED | 2016-02-29 |  | 2016-03-31 |  |  | 2016-03-31 |  | 2016-02-29 |  | 2016-03-31 |  |  |  | 2016-03-31 | [6 empty] | 2016-05-16 |  | 2016-06-20 |  |  | 2016-07-11 | [10 empty] | 2016-08-15 | [5 empty] | 23/11/15 - not co locatable structurally VF & Spark on same tower, cell site friendly LO, will look for a GF site on same property | [10 empty] | 2016-07-28 | [6 empty] | BUILD |  | FALSE |  | 2723253 | 6366010 | 1628 Cambridge Rd SH1 Cambridge |  |  | CELLSITE | WIPACTIVE |  |  | ROAMING |  |  |  | 2016-04-04 | [5 empty] | 2016-04-25 |  |  |  | 2015-12-01
0 | WKT | 1489 | WKT-018-001 |  |  |  | Otorohanga District |  | TIER_9
0 | WKT | 1490 | WKT-018-002 | Otorohanga | WKT-018-002-D | Otorohanga - Ourwhero Road GF | Otorohanga District | 22 | TIER_4 | ACTIVE | GF | DU | T2 20 RH |  | STACK_A | STANDALONE | 19 | 20 | 1 | -38.1737 | 175.2139 |  |  |  |  | Microwave | WKT-018-004-C | FALSE | FALSE |  |  | FALSE |  | 2012-06-14 | 2012-06-21 | 2012-07-11 | 2012-07-11 | 2012-08-10 | 2012-08-09 | 1 | 2012-08-10 | 2012-08-09 | 2012-08-31 | 2012-08-29 | 2012-11-09 | 2012-11-08 |  | 2012-11-16 | 2012-11-08 | PERMITTED | 2012-09-17 | 2012-09-19 | 2012-10-17 | 2012-10-04 | 1 | 2012-10-22 | 2012-10-09 | 2014-10-24 | 2014-10-21 | 2015-02-27 | 2015-02-25 | 1 |  | 2015-02-27 | 2015-02-25 |  |  |  | 2015-03-30 |  | 2015-05-25 | 2015-05-28 | 2015-07-31 | 2015-07-31 | 2015-06-24 | 2015-08-14 | 2015-07-31 | [9 empty] | 2015-10-12 | 2015-10-09 | 2015-10-21 |  |  |  | 28/1/15 - awaiting CD rev1 9/3/15 - Cabs and TX ordered, pole PO in sign off, Antenna order with Huawei 31/7/15 - site is finished - awaiting Pirongia to finish before integration can be done (linking through Pirongia for TX) |  | 2015-07-08 | [6 empty] | 2015-06-24 | 2015-07-27 | 2015-09-29 | 2015-10-02 |  |  | HAMILTON_TEKUITI |  |  | BUILD | 2015-06-24 | TRUE |  | 2704113 | 6334245 | 78 Ouruwhero Road Otorahanga |  | Council Ref: RM120071 - 26/09/2012 | CELLSITE |  |  |  | ROAMING |  | 2015-03-13 | 2015-02-09 |  | 2015-03-30 | [5 empty] | 2015-05-20 | 2015-09-17 |  | 2012-07-11
0 | WKT | 1491 | WKT-018-003 |  |  |  | Otorohanga District |  | TIER_9
0 | WKT | 1492 | WKT-018-004 | Pirongia | WKT-018-004-C | Pirongia Co-site VF and TNZ | Otorohanga District | 22 | TIER_4 | ACTIVE | GF | DU | T2 20 RH |  | STACK_A | COSITE |  |  | 1 | -38.0137 | 175.1648 |  |  |  |  | Microwave | WKT-017-005-B | FALSE | FALSE |  |  | FALSE |  | 2012-04-03 | 2012-04-03 | 2012-04-05 | 2012-04-05 | 2012-05-31 | 2012-05-30 | 2 | 2012-07-25 | 2012-07-24 | 2012-07-11 | 2012-06-07 | 2012-08-31 | 2012-08-23 | 2 | 2012-09-07 | 2012-08-23 | DISCRETIONARY_FULL | 2012-08-03 | 2012-08-03 | 2012-09-07 | 2012-08-30 | 2 | 2012-09-14 | 2012-09-03 | 2015-01-15 | 2015-01-15 | 2015-03-20 | 2015-03-31 | 1 |  | 2015-03-20 | 2015-03-31 | [5 empty] | 2015-05-25 | 2015-05-28 | 2015-09-29 | 2015-09-29 |  | 2015-10-30 | [10 empty] | 2015-10-09 | 2015-10-09 | 2015-10-23 | 2015-10-23 |  |  | VF & TNZ co-site approved Linking to Te Awamutu 16/1/15 - Hardmatched site now in roaming program - CDI issued today on Rev2 plans 28/1/15 - Fibre feasibility underway 9/3/15 - Cabs and TX ordered - pole order in sign off, antenna order with Huawei 1/4/15 - BI submitted to Huawei 13/7/15 - site hit rock so new design to be confirmed |  | 2015-09-04 | [6 empty] | 2015-08-31 |  | 2015-10-02 | 2015-10-05 |  |  | HAMILTON_TEKUITI |  |  | BUILD |  | FALSE |  | 2700249 | 6352104 | 47 Sainsbury Rd, Pirongia, Waikato |  | Council Ref RM120063 - 16/08/2012 | CELLSITE |  |  |  | ROAMING |  | 2015-03-13 | 2015-02-09 |  | 2015-04-01 | [5 empty] | 2015-05-20 |  |  | 2012-04-05
0 | WKT | 1493 | WKT-018-005 | RBI - Otewa |  |  | Otorohanga District |  | RBI | [22 empty] | FALSE
0 | WKT | 1494 | WKT-018-006 | RBI - Maihiihi |  |  | Otorohanga District |  | RBI | [22 empty] | FALSE
0 | WKT | 1495 | WKT-019-001 | Tirau | WKT-019-001-C | Spark Pairere Co-Lo | South Waikato District | 22 | TIER_5 | ACTIVE | COLO | DF | COLO |  | STACK_A | COLO | 24 | 25 |  | -37.96 | 175.6776 |  |  |  |  | Microwave | WKT-017-004-A | FALSE | FALSE |  |  | FALSE |  | 2015-11-26 | 2015-11-26 | 2015-12-14 | 2015-12-14 | 2016-01-20 | 2016-01-21 | 1 | 2016-01-27 | 2016-01-21 | 2016-03-21 |  | 2016-05-16 |  |  | 2016-05-23 |  | PERMITTED | 2016-03-21 |  | 2016-04-29 |  |  | 2016-04-29 |  | 2016-03-21 |  | 2016-04-29 |  |  |  | 2016-05-06 | [6 empty] | 2016-06-27 |  | 2016-07-18 |  |  | 2016-08-01 | [10 empty] | 2016-08-22 | [5 empty] | 1/12/15 - 1st back up option from RF - pole up to 25m (permitted) currently at 20m | TNZ | [9 empty] | 2016-08-15 | [6 empty] | BUILD |  | FALSE |  | 2745434 | 6356823 | Off SH1 Pairere |  |  | CELLSITE | WIPACTIVE |  |  | ROAMING |  |  |  | 2016-05-23 | [5 empty] | 2016-06-13 |  |  |  | 2015-12-14
0 | WKT | 1496 | WKT-019-002 | Tirau Township | WKT-019-002-B | GF - Macmillan Rd | South Waikato District | 22 | TIER_4 | ACTIVE | GF | DF | T2 25 RH |  | STACK_A | COSITE | 25 | 25 |  | -37.9578 | 175.7454 |  |  |  |  | Microwave | WKT-019-003-D | FALSE | FALSE |  |  | FALSE |  | 2015-07-01 | 2015-06-30 | 2015-07-08 | 2015-07-06 | 2015-08-06 | 2015-08-21 | 1 | 2015-08-11 | 2015-08-21 | 2015-11-23 | 2015-11-12 | 2016-01-25 | 2016-01-26 |  | 2016-02-02 |  | PERMITTED | 2015-11-23 | 2015-11-23 | 2016-01-11 | 2015-12-03 | 1 | 2016-01-11 | 2015-12-03 | 2015-11-09 | 2015-11-23 | 2016-02-08 |  |  |  | 2016-02-15 | [6 empty] | 2016-03-14 |  | 2016-04-18 |  |  | 2016-05-02 | [10 empty] | 2016-05-30 | [5 empty] | Spark SFA for power - will submit co-site application 3/12/15 - pole order request to Tim 13/1/16 - Spark co-site request submitted | [10 empty] | 2016-05-16 | [6 empty] | BUILD |  | FALSE |  | 2751397 | 6356885 | 15 Macmillan Rd, Tirau |  |  | CELLSITE | WIPACTIVE |  |  | ROAMING |  | 2016-02-09 | 2016-02-10 | 2016-02-15 |  |  | 2015-07-06 |  |  | 2016-03-07 |  |  |  | 2015-07-06
0 | WKT | 1497 | WKT-019-003 | Putaruru | WKT-019-003-D | Taupo Street Commercial | South Waikato District | 2 | TIER_3 | ACTIVE | GF | DU | T2 25 RF |  | STACK_A | STANDALONE |  |  | 1 | -38.0526 | 175.7813 |  |  |  |  | Fibre Optic | WKT-016-023-B | FALSE | FALSE |  |  | FALSE |  | 2012-09-04 | 2012-09-03 | 2012-09-06 | 2012-09-07 | 2012-09-21 | 2012-09-27 | 2 | 2012-09-21 | 2012-10-04 | 2012-09-05 | 2012-09-05 | 2012-10-12 | 2012-10-31 |  | 2012-10-19 | 2012-10-31 | PERMITTED | 2012-09-26 | 2012-10-10 | 2012-10-31 | 2012-11-05 | 2 | 2012-11-07 | 2012-11-07 |  | 2012-10-31 | 2012-11-30 | 2012-11-30 | 1 |  | 2012-11-30 | 2012-11-30 | 2013-01-19 |  |  | 2012-11-20 |  | 2013-02-14 | 2013-01-14 | 2013-02-01 | 2013-02-01 | 2013-01-31 | 2013-02-25 | 2013-02-20 | 2013-02-22 | 2013-02-19 | [6 empty] | 2013-02-20 | 2013-03-01 | 2013-02-27 | 2013-03-08 | 2013-03-08 | 2013-06-06 | 2013-06-06 | 15/03/13 - retaining wall to complete, Audit etc 18/03/13 - Snags to clear and PSVP to pass before FAN issue 26/04/13 - FAN in sign off 06/06/13 - FAC signed |  | 2013-02-25 | 2012-12-10 | 2013-01-09 | 2013-01-15 | 2013-01-15 | 2013-01-14 | 2013-01-19 | 2013-02-07 | 2013-02-07 | 2013-02-26 | 2013-02-25 |  |  | TOKOROA_TAUPO | 2013-02-14 | 2013-02-15 | BUILD | 2013-02-01 | TRUE | 2012-11-15 | 2754221 | 6346270 | 23 Taupo Street, Putaruru |  |  | CELLSITE | [15 empty] | 2013-02-28 | 2013-02-25
0 | WKT | 1498 | WKT-019-004 | Waiohotu |  |  | South Waikato District |  | TIER_9 | [22 empty] | FALSE
0 | WKT | 1499 | WKT-019-005 |  |  |  | South Waikato District |  | TIER_9
0 | WKT | 1500 | WKT-019-006 | Lichfield |  |  | South Waikato District |  | TIER_9 | [22 empty] | FALSE
0 | WKT | 1501 | WKT-019-007 | Tokoroa | WKT-019-007-B | Colson Hill Greenfield | South Waikato District | 2 | TIER_3 | ACTIVE | GF | DU | T2 20 RF |  | STACK_A | COSITE |  | 20 | 1 | -38.2134 | 175.8747 |  |  |  |  | Fibre Optic |  | FALSE | FALSE |  |  | FALSE |  | 2012-05-11 | 2012-05-09 | 2012-05-21 | 2012-05-29 | 2012-06-26 | 2012-07-09 | 1 | 2012-06-28 | 2012-07-09 | 2012-08-22 | 2012-08-23 | 2012-09-05 | 2012-09-10 |  | 2012-09-05 | 2012-09-10 | PERMITTED | 2012-08-03 | 2012-08-01 | 2012-09-14 | 2012-08-23 | 1 | 2012-09-21 | 2012-08-23 | 2012-08-17 |  | 2012-10-05 | 2012-10-02 | 1 |  | 2012-10-05 | 2012-10-02 | 2012-10-29 |  |  |  |  | 2012-10-10 | 2012-10-09 | 2012-10-31 | 2012-10-31 | 2012-10-25 | 2012-11-06 | 2012-11-06 | 2012-11-09 | 2012-11-08 | [6 empty] | 2012-11-12 | 2012-11-26 | 2012-11-30 | 2012-12-12 | 2012-11-30 | 2013-06-07 | 2013-06-07 | 18/03/13 - snags to clear for FAN issue 01/05/13 - No FAN yet. FAC reforecasted 07/06/13 - FAC Signed |  | 2012-11-12 | 2012-10-06 | 2012-10-06 | 2012-10-11 | 2012-10-11 | 2012-10-16 | 2012-10-29 | 2012-10-30 | 2012-10-30 | 2012-11-12 | 2012-11-13 | 2012-03-13 | MEDIUM | TOKOROA_TAUPO | 2012-10-26 | 2012-10-30 | BUILD | 2012-10-25 | FALSE |  | 2761841 | 6328175 | Colson Hill Tokoroa |  |  | CELLSITE |  |  | 2015-12-10 | [12 empty] | 2012-11-21 | 2012-11-21 | 2012-05-29
0 | WKT | 1502 | WKT-019-008 |  |  |  | South Waikato District |  | TIER_9
0 | WKT | 1503 | WKT-019-009 | Kinleith | WKT-019-009-A | Kinleith - VF Co-lo | South Waikato District | 22 | TIER_5 | ACTIVE | COLO | DF | COLO |  | STACK_A | COLO | 30 | 30.65 |  | -38.3056 | 175.9604 |  |  |  |  | Microwave | WKT-021-015-A | FALSE | FALSE |  |  | FALSE |  | 2015-11-26 | 2015-11-26 | 2015-11-30 | 2015-12-01 | 2015-12-14 | 2012-05-04 | 3 | 2015-12-17 | 2015-12-17 | 2016-03-07 |  | 2016-04-25 |  |  | 2016-04-25 |  | DISCRETIONARY_FULL | 2016-03-14 |  | 2016-04-18 |  |  | 2016-04-18 |  | 2016-03-14 |  | 2016-04-25 |  |  |  | 2016-04-25 | [6 empty] | 2016-05-30 |  | 2016-06-27 |  |  | 2016-07-11 | [10 empty] | 2016-08-11 | [5 empty] | VF Datapack requested in Oct 27/04/12 - Rev1 drawings received and in for final sign-off for release 02/05/12 - Drawings OK. GHD requested to issue files for formal release Rev 1 25/05/12 - Requested updated datapack from VF with their reserved antenna locations 14/06/12 - revised design with extended headframe. Structural OK, drawings to issue 18/06/12 - Colocation application lodged with VF for extended mast 17/07/12 - Preliminary approval received from VF 30/10/15 - have 2012 data pack - will up rev drawings with new antenna type and resubmit VF co-lo application. 1/12/15 - post caravan 27th Nov this is still preferred site - will request drawing up rev for VF co-lo application submission early 2016 18/12/15 - VF co-lo application submitted | VNZ | [9 empty] | 2016-08-01 |  |  |  | TOKOROA_TAUPO |  |  | BUILD |  | FALSE |  | 2769000 | 6317700 | Forestry Rd off SH1 Kinleith |  |  | CELLSITE | WIPACTIVE |  |  | ROAMING |  |  |  | 2016-04-25 | [5 empty] | 2016-05-16 |  |  |  | 2015-12-01
0 | WKT | 1504 | WKT-019-010 | RBI - Mangakino Central |  |  | South Waikato District |  | RBI | [22 empty] | FALSE
0 | WKT | 1505 | WKT-019-011 | Tokoroa Sth | WKT-019-011-A | GF - Blain Farm | South Waikato District | 22 | 2015P | ACTIVE | GF | DU | T2 25 RH |  | STACK_A | STANDALONE | 23 | 25 |  | -38.2331 | 175.8478 |  |  |  |  | Microwave | WKT-019-007-B | FALSE | FALSE |  |  | FALSE |  | 2014-08-06 | 2014-08-06 | 2014-08-11 | 2014-08-11 | 2014-09-01 | 2014-09-02 | 1 | 2014-09-08 | 2014-09-02 | 2014-09-12 | 2014-08-25 | 2014-10-10 | 2014-10-09 |  | 2014-10-17 | 2014-10-09 | PERMITTED | 2014-09-05 | 2014-09-05 | 2014-10-17 | 2014-09-25 | 1 | 2014-10-24 | 2014-09-25 | 2014-09-30 | 2014-09-30 | 2014-11-03 | 2014-10-29 | 2 |  | 2014-11-10 | 2015-03-03 | [5 empty] | 2015-07-27 | 2015-07-17 | 2015-09-08 | 2015-09-08 |  | 2015-08-18 | 2015-08-18 | [9 empty] | 2015-09-21 | 2015-09-21 | 2015-10-07 | 2015-10-07 |  |  | 16/1/15 - ready to build when budget approved. Will need to order pole and equipment 6.3.15 - fibre cost over $50k - MW only site, BoQ's underway for all equipment 27/3/15 - cabs, pole and TX equipment ordered - still need to order the antenna 1/4/15 - BI gone to Graham today 10/4/15 - sent quote request to Maser for antenna | [10 empty] | 2015-09-17 | 2015-09-15 | [5 empty] | BUILD |  | FALSE |  | 2759416 | 6326072 | 2681 Old Taupo Rd, Tokoroa |  |  | CELLSITE |  |  | 2015-12-10 | CAPACITY |  | 2015-03-11 | 2015-03-30 | 2015-04-01 | 2015-04-01 |  |  |  |  | 2015-06-12 | 2015-07-03 |  |  | 2014-08-11
0 | WKT | 1506 | WKT-020-001 | Te Kuiti | WKT-020-001-A | Te Kuiti Greenfield | Waitomo District | 6 | 2014 | ACTIVE | GF | DU | COLO | Grey | STACK_A | COSITE | 15 | 25 | 1 | -38.3333 | 175.1411 |  |  |  |  | Microwave | WKT-018-002-C | FALSE | FALSE |  |  | FALSE |  | 2012-04-03 | 2012-04-03 | 2012-04-05 | 2012-04-05 | 2012-06-11 | 2012-05-30 | 1 | 2012-06-11 | 2012-05-30 | 2012-07-18 | 2012-06-07 | 2012-07-27 | 2012-07-10 |  | 2012-08-06 | 2012-08-07 | PERMITTED | 2012-06-29 | 2012-06-29 | 2012-08-06 | 2012-07-11 | 1 | 2012-07-20 | 2012-07-19 | 2014-05-16 |  | 2014-07-04 | 2014-07-09 | 1 |  | 2014-07-08 | 2014-07-09 | [5 empty] | 2014-08-01 | 2014-08-01 | 2014-08-18 | 2014-08-29 | 2014-08-22 | 2014-09-08 | 2014-09-09 | 2014-09-03 | 2014-09-05 | [7 empty] | 2014-09-30 | 2014-09-23 |  |  |  |  | VF co-site approved subject to SFA being required for power Linking dependant on Te Awamutu POLE STAND SAT 23 AUG Tried for 3 days to integrate - huge issues. Had Reggie from T/F assisting. 15.09.014 Rudolph to go down and integrate. | [10 empty] | 2014-09-17 | 2014-09-16 |  |  | HAMILTON_TEKUITI |  |  | BUILD |  | FALSE |  | 2697301 | 6316692 | 153 Gadsby Rd, Waikato |  |  | CELLSITE | [7 empty] | 2014-07-15 | 2014-07-15
0 | WKT | 1507 | WKT-020-002 |  |  |  | Waitomo District |  | TIER_9
0 | WKT | 1508 | WKT-020-004 |  |  |  | Waitomo District |  | TIER_9
0 | WKT | 1509 | WKT-020-005 | RBI - Benneydale |  |  | Waitomo District |  | RBI | [22 empty] | FALSE
0 | WKT | 1510 | WKT-020-006 | RBI - Mokau North |  |  | Waitomo District |  | RBI | [22 empty] | FALSE
0 | WKT | 1511 | WKT-021-001 | Tuhingamata - Kordia | WKT-021-001-A | Tuhingamata Kordia co-lo | Taupo District | 2 | TIER_2 | ACTIVE | COLO | DU | COLO |  | STACK_A | COLO |  |  | 1 | -38.709 | 175.9969 |  | 2010-05-10 |  | 2010-04-28 | Microwave | WKT-021-003-A | FALSE | FALSE | 2010-05-10 |  | FALSE | 2011-02-02 | 2010-07-06 | 2010-07-06 | 2011-03-22 | 2011-03-22 | 2011-05-27 | 2011-06-01 | 1 | 2011-05-27 | 2011-06-01 | 2011-05-20 | 2011-05-12 | 2011-06-30 | 2011-06-17 |  | 2011-06-30 | 2011-06-23 | PERMITTED | 2011-05-30 | 2011-05-26 | 2011-06-30 | 2011-06-01 | 1 | 2011-06-30 | 2011-06-01 |  |  | 2012-01-20 | 2013-03-26 | 1 |  | 2012-01-20 | 2013-03-26 | 2011-10-06 |  |  |  |  | 2011-10-03 | 2011-10-06 | 2011-10-14 | 2011-10-13 | 2011-10-11 | 2011-11-08 | 2011-11-10 | 2011-10-21 | 2011-11-21 | 2011-10-07 |  | 2011-10-07 |  |  |  | 2011-11-10 | 2011-11-14 | 2011-11-14 | 2012-02-29 | 2011-12-16 | 2013-04-15 | 2013-04-11 | 18/03/13 - FAN in sign-off process 09/04/13 - Drwgs and Files do not match. FAC reforecasted | KDA | 2011-11-08 | 2011-08-22 | 2011-08-22 | 2011-10-07 | 2011-10-06 | 2011-10-03 | 2011-10-06 | 2011-10-14 | 2011-10-12 |  | 2011-12-05 | [6 empty] | 2011-10-10 | FALSE |  | 2770680 | 6272854 | Blueridge Drive, Acacia Bay, Taupo |  | Permitted to None None - 20/05/2010 | CELLSITE | [7 empty] | 2011-09-15 | 2011-09-15 | [6 empty] | 2011-11-30 | 2011-12-02 | 2011-03-22
0 | WKT | 1512 | WKT-021-002 | Taupo CBD | WKT-021-002-D | 116 Spa Road | Taupo District | 2 | TIER_2 | ACTIVE | GF | DU | P2 | grey | STACK_A | STANDALONE | 14.5 | 15 | 1 | -38.6826 | 176.076 |  | 2010-05-10 |  | 2010-04-28 | Microwave | WKT-021-006-A | FALSE | FALSE | 2010-05-10 |  | FALSE | 2011-03-03 | 2011-03-18 | 2011-03-09 | 2011-03-18 | 2011-03-14 | 2011-04-15 | 2011-04-15 | 3 | 2011-04-15 | 2011-11-16 | 2011-05-13 | 2011-05-13 | 2011-09-30 | 2011-09-29 | 2 | 2011-09-30 | 2011-09-29 | PERMITTED | 2011-05-13 | 2011-05-13 | 2011-06-09 | 2011-05-26 | 2 | 2011-06-16 | 2011-05-30 |  |  |  | 2011-11-25 | 1 |  |  | 2011-11-25 | 2011-12-12 |  |  |  |  | 2011-11-29 | 2011-12-01 | 2011-12-13 | 2011-12-15 | 2011-12-14 | 2011-12-16 | 2011-12-20 | [8 empty] | 2011-12-20 | 2011-12-20 | 2011-12-20 | 2012-02-18 | 2012-01-31 | 2013-05-29 | 2013-05-23 | 18/03/13 - Shroud to be fitted and earth in tower to clear before issue FAN 09/04/13 - No FAN yet. FAC reforecasted 01/05/13 - No FAN yet. FAC reforecasted |  | 2011-12-20 | 2011-12-12 | 2011-12-12 | 2011-12-12 | 2011-12-15 | 2011-12-12 | 2011-12-12 | 2011-12-14 | 2011-12-16 |  | 2012-01-17 | [5 empty] | BUILD | 2011-12-14 | FALSE |  | 2777651 | 6275549 | 116 Spa Road Taupo |  | Certificate of Compliance Ref: RM110085 - 30/05/2011 | CELLSITE | [15 empty] | 2012-01-20 | 2012-01-17 | 2011-03-14
0 | WKT | 1513 | WKT-021-003 | Taupo East - Main Hub | WKT-021-003-C | 32 Manuka Street | Taupo District | 2 | TIER_2 | ACTIVE | GF | DU | T2 20 RF |  | STACK_A | STANDALONE |  | 25 | 1 | -38.6895 | 176.1064 |  | 2010-05-10 |  | 2010-04-28 | Fibre Optic | AKL-007-166-A | FALSE | FALSE | 2010-05-10 |  | FALSE |  | 2011-07-19 | 2011-07-19 | 2011-07-25 | 2011-07-25 | 2011-08-15 | 2011-08-26 | 2 | 2011-09-20 | 2011-09-20 | 2011-08-26 | 2011-08-11 | 2011-09-02 | 2011-08-24 |  | 2011-09-09 | 2011-09-01 | DISCRETIONARY_FULL | 2011-09-23 | 2011-09-29 | 2011-10-28 | 2011-10-28 | 2 | 2011-11-02 | 2011-10-31 |  |  |  | 2011-12-05 | 1 |  |  | 2011-12-05 | 2012-01-13 |  |  |  |  | 2012-01-10 | 2012-01-10 | 2012-02-03 | 2012-02-09 | 2012-02-08 | 2012-02-17 | 2012-02-20 | 2012-03-01 | 2012-03-01 | [6 empty] | 2012-02-20 | 2012-03-06 | 2012-03-07 | 2012-02-14 | 2012-03-14 | 2013-08-30 | 2013-12-04 | 07/03/12 - Site on Air 09/04/13 - No FAN yet. FAC reforecasted. Requiring documentation on generator install, updated drawings and documents, CoC's required 01/05/13 - No FAN yet. FAC reforecasted |  | 2012-02-18 | 2012-01-13 | 2012-01-13 | 2012-01-13 | 2012-01-13 | 2012-01-27 | 2012-01-13 | 2012-02-15 | 2012-01-20 |  | 2012-02-29 |  |  |  | 2012-03-01 | 2012-03-01 | BUILD | 2012-02-07 | FALSE |  | 2780267 | 6274688 | 32 Manuka Street Taupo |  | Council Ref: RM110203 - 31/10/2011 | CELLSITE | [15 empty] | 2012-02-29 | 2012-02-29 | 2011-07-25
0 | WKT | 1514 | WKT-021-004 | Rainbow Point |  |  | Taupo District |  | TIER_9 | [22 empty] | FALSE | [60 empty] | Water Tank location in Garden Area accessed on cnr Hyde Ave & Shepherd Rd. Coverage to residential areas - Waipahihi - Gradwell - Richmond Heights - Two Mile Bay
0 | WKT | 1515 | WKT-021-005 | Acacia Bay | WKT-021-005-C | LPR Mapara Ave - HARD MATCH ONLY | Taupo District | 2 | TIER_2 | ACTIVE | RSR | DU | P4F | Green | INLINE | STANDALONE | 7.8 | 7.8 | 1 | -38.7064 | 176.0243 |  | 2010-05-10 |  | 2010-04-28 | Microwave | WKT-021-010-D | FALSE | FALSE | 2010-05-10 |  | FALSE |  | 2011-04-15 | 2011-03-09 | 2011-03-14 | 2011-03-14 | 2011-03-16 | 2011-03-17 | 2 | 2011-03-16 | 2011-07-08 | 2011-08-19 | 2011-08-19 | 2011-08-30 | 2011-08-31 |  | 2011-08-30 | 2011-08-31 | NES | 2011-09-07 | 2011-07-14 | 2011-09-28 | 2011-09-15 | 2 | 2011-10-05 | 2011-09-16 |  |  |  | 2011-11-25 | 1 |  |  | 2011-11-25 | [27 empty] | 28/10/11 - Site now ready for construction 18/11/11 - emails and calls received this week from Mr and Mrs Irons (neighbouring property). Info sent. They have contacted Council. Ongoing. 22/11/11 - CD0 in circulation today 07/12/11 - CD's all completed. Site removed from build programme. Stay at hard match . | [17 empty] | HARDMATCH |  | FALSE |  | 2773069 | 6273061 | LPR outside 82 Mapara Ave Acacia Bay Taupo |  | Council Ref: RM110131 - 15/09/2011 | [18 empty] | 2011-03-14
0 | WKT | 1516 | WKT-021-006 | Nukuhau | WKT-021-006-A | 65 Watene Lane - HARD MATCH ONLY | Taupo District | 2 | TIER_2 | ACTIVE | GF | DU | P3 | grey | STACK_A | STANDALONE | 19.5 | 20 | 1 | -38.6704 | 176.0608 |  | 2010-05-10 |  | 2010-04-28 | Microwave | WKT-021-003-A | FALSE | FALSE | 2010-05-10 |  | FALSE |  |  | 2010-12-08 | 2011-01-21 | 2011-01-27 | 2011-02-25 | 2011-03-02 | 1 | 2011-02-25 | 2011-03-02 | 2011-04-08 | 2011-04-07 | 2011-05-06 | 2011-04-27 |  | 2011-05-13 | 2011-04-27 | PERMITTED | 2011-04-11 | 2011-04-05 | 2011-05-06 | 2011-04-26 | 1 | 2011-05-13 | 2011-05-02 | [6 empty] | 2011-07-01 | [28 empty] | 14/11/11 - Joelyn advised to commence lease 1/12 if not already done 07/12/11 - CD's completed. Site now removed from Build programme and will be hard match only | [17 empty] | HARDMATCH |  | FALSE |  | 2776381 | 6276948 | 65 Watene Lane Acacia Bay Taupo |  | Refer: RM110058 - 02/05/2011 | CELLSITE | WIPHOLDING | [16 empty] | 2011-01-27
0 | WKT | 1517 | WKT-021-007 | Taupo Downtown | WKT-021-007-B | Veitch Morrison GF | Taupo District | 2 | TIER_2 | ACTIVE | GF | DU | P4A | grey | STACK_A | STANDALONE | 14.5 | 15 | 1 | -38.6882 | 176.0706 |  | 2010-05-10 |  | 2010-04-28 | Microwave | WKT-021-002-D | FALSE | FALSE | 2010-05-10 |  | FALSE |  | 2011-03-18 | 2011-03-03 | 2011-03-08 | 2011-03-08 | 2011-04-19 | 2011-04-22 | 4 |  | 2012-02-07 | 2011-05-20 | 2011-05-19 | 2011-06-17 | 2011-05-27 |  | 2011-06-24 | 2011-06-02 | PERMITTED | 2011-05-23 | 2011-05-27 | 2011-06-23 | 2011-06-09 | 2 | 2011-06-30 | 2011-06-15 |  |  |  | 2012-02-07 | 1 |  |  | 2012-02-07 | 2011-12-08 |  |  |  |  | 2011-12-08 | 2011-12-08 | 2011-12-14 | 2011-12-15 | 2011-12-14 | 2011-12-16 | 2011-12-20 | [8 empty] | 2011-12-20 | 2011-12-20 | 2011-12-21 | 2012-02-10 | 2012-01-31 | 2012-04-30 | 2012-07-31 | 28/10/11 - Huawei have been requested to build before Xmas as part of capacity for holiday period 14/11/11 - Lease commenced Nov 15/12/11 - Site under construction. Pole up, cabinets in |  | 2011-12-20 | 2011-12-08 | 2011-12-08 | 2011-12-08 | 2011-12-08 | 2011-12-08 | 2011-12-08 | 2011-12-14 | 2011-12-15 |  | 2012-01-17 | [6 empty] | 2011-12-14 | FALSE |  | 2777167 | 6274934 | Gallagher St behind Veitch Morison Valuers Ltd, 29 Heuheu Street Taupo |  | Permitted height 15m. - 21/03/2011 Council Ref: RM110090 - 15/06/2011 | CELLSITE | [15 empty] | 2012-01-20 | 2012-01-17 | 2011-03-08
0 | WKT | 1518 | WKT-021-008 | Totara Street | WKT-021-008-D | Anderderson Property | Taupo District | 2 | TIER_2 | ACTIVE | GF | DU | P2 |  | STACK_A | STANDALONE | 19.3 | 20 | 1 | -38.6805 | 176.0901 |  | 2010-05-10 |  | 2010-04-28 | Microwave | WKT-021-003-C | FALSE | FALSE | 2010-05-10 |  | FALSE |  | 2012-03-21 | 2012-03-29 | 2012-03-23 | 2012-03-29 | 2012-04-13 | 2012-04-11 | 1 | 2012-04-13 | 2012-04-11 | 2012-04-13 | 2012-03-22 | 2012-04-27 | 2012-03-30 |  | 2012-04-27 | 2012-03-30 | PERMITTED | 2012-04-13 | 2012-04-11 | 2012-05-20 | 2012-04-26 | 1 | 2012-05-27 | 2012-04-26 |  |  | 2012-06-13 | 2012-06-26 | 1 |  | 2012-06-13 | 2012-06-26 | 2012-06-27 |  |  |  |  | 2012-06-18 | 2012-06-18 | 2012-06-29 | 2012-06-28 | 2012-06-29 | 2012-07-09 | 2012-07-09 | [8 empty] | 2012-07-12 | 2012-07-13 | 2012-07-13 | 2012-08-16 | 2012-07-24 | 2013-04-26 | 2013-04-10 | 18/03/13 - ELFI to be closed before FAN issue 09/04/13 - FAN in circulation. Issues in NOC. Field Ops, TX and Vicente to sign 10/04/13 - FAC signed |  | 2012-07-09 | 2012-06-27 | 2012-06-27 | 2012-06-27 | 2012-06-27 | 2012-06-27 | 2012-06-27 | 2012-07-05 | 2012-07-03 |  | 2012-07-10 | [6 empty] | 2012-07-02 | FALSE |  | 2778888 | 6275740 | 93 Tauhara Road Taupo |  |  | CELLSITE | [15 empty] | 2012-07-13 | 2012-07-13 | 2012-03-29
0 | WKT | 1519 | WKT-021-009 | Taupo Central | WKT-021-009-C | Baptist Church - HARD MATCH ONLY | Taupo District | 2 | TIER_2 | ACTIVE | GF | DU | P4A | green | INLINE | STANDALONE | 10 | 10 | 1 | -38.6878 | 176.0889 |  | 2010-05-10 |  | 2010-04-28 | Microwave | WKT-021-001-B | FALSE | FALSE | 2010-05-10 |  | FALSE |  |  | 2010-12-09 | 2011-01-21 | 2011-01-27 | 2011-03-03 | 2011-03-08 | 3 | 2011-03-03 | 2011-05-19 | 2011-04-08 | 2011-03-24 | 2011-04-15 |  |  | 2011-04-22 |  | PERMITTED | 2011-05-30 | 2011-05-27 | 2011-06-23 | 2011-06-13 | 3 | 2011-06-28 | 2011-06-15 | [35 empty] | 07/12/11 - CD's all completed. Site removed from build programme. Hard match only. Need to decide before lease commencement, if to hold site or not. | [17 empty] | HARDMATCH |  | FALSE |  | 2778758 | 6274927 | Baptist Church 3 Taupo View Road Taupo | LEASE TERMINATED - 27/05/2014 | Council Ref: RM110092 - 15/06/2011 | [18 empty] | 2011-01-27
0 | WKT | 1520 | WKT-021-010 | Hilltop |  |  | Taupo District |  | TIER_9 | [22 empty] | FALSE | [60 empty] | Nominal is based on Shopping Centre at the corner of Taharepa rd & Rokino Rd. Coverage to - Hilltop residential area. - Areas between this site and Lake Taupo.
0 | WKT | 1521 | WKT-021-011 | Waipahihi | WKT-021-011-A | Storage Bins | Taupo District | 2 | TIER_2 | ACTIVE | GF | DU | P2 | grey | STACK_A | STANDALONE | 19.5 | 20 | 1 | -38.7043 | 176.1029 |  | 2010-05-10 |  | 2010-04-28 |  |  | FALSE | FALSE | 2010-05-10 |  | FALSE |  |  | 2011-01-21 | 2011-04-28 | 2011-04-29 | 2011-06-22 | 2011-06-16 | 2 | 2011-06-22 | 2011-06-16 | 2011-07-08 | 2011-06-30 | 2011-08-05 | 2011-07-29 | 2 | 2011-08-05 | 2011-07-29 | DISCRETIONARY_RESTRICT | 2011-06-28 | 2011-06-17 | 2011-07-15 | 2011-07-12 | 2 | 2011-07-15 | 2011-07-12 |  |  | 2011-11-07 | 2011-11-07 | 1 |  | 2011-11-07 | 2011-11-07 | 2012-01-13 |  |  |  |  | 2012-01-09 | 2012-01-09 | 2012-02-09 | 2012-02-09 | 2012-02-10 | 2012-02-22 | 2012-02-28 | [8 empty] | 2012-02-28 | 2012-03-06 | 2012-03-08 | 2012-02-10 | 2012-03-14 | 2012-05-10 | 2012-09-27 | 03/11/11 - CD0 redlines sent back 3/11 14/11/11 - Joelyn advised to commence lease 1/12 if not already done 10/02/11 - Cabinets in, pole goes up next week. Looking OK for SOA end Feb 14/02/12 - Pole up this week. Link still needs to be released from use at Taupo CBD. Look at installing 22/02. 07/03/12 - Site on Air |  | 2012-02-22 | 2012-01-13 | 2012-01-13 | 2012-01-13 | 2012-01-13 | 2012-01-13 | 2012-01-13 | 2012-02-09 | 2012-02-17 |  | 2012-03-02 | [6 empty] | 2012-02-09 | FALSE |  | 2779911 | 6273059 | Access off SH5 near Hilton Lake Hotel SH5 Taupo |  | Consent No. RM110116 - 12/07/2011 | CELLSITE | [15 empty] | 2012-03-02 | 2012-03-02 | 2011-04-28
0 | WKT | 1522 | WKT-021-012 | Taupo Airport | WKT-021-012-A | Taupo Airport | Taupo District | 2 | TIER_2 | ACTIVE | GF | DU | T2 25 UF | grey | STACK_A | STANDALONE | 24.5 | 25 | 1 | -38.74 | 176.0776 |  | 2010-05-10 |  | 2010-04-28 | Microwave | WKT-021-001-B | FALSE | FALSE | 2010-05-10 |  | FALSE |  | 2011-03-18 | 2011-03-09 | 2011-03-18 | 2011-03-14 | 2011-04-08 | 2011-04-07 | 1 | 2011-04-08 | 2011-04-07 | 2011-05-27 | 2011-05-26 | 2011-06-24 | 2011-06-16 | 1 | 2011-07-01 | 2011-06-17 | DISCRETIONARY_RESTRICT | 2011-06-21 | 2011-06-23 | 2011-07-26 | 2011-07-22 | 1 | 2011-08-03 | 2011-07-28 |  |  | 2011-11-18 | 2011-11-18 | 1 |  | 2011-11-18 | 2011-11-18 | 2012-01-13 |  |  |  |  | 2012-01-12 | 2012-01-12 | 2012-01-31 | 2012-03-15 | 2012-02-03 | 2012-02-09 | 2012-02-09 | [8 empty] | 2012-02-20 | 2012-02-28 | 2012-03-07 | 2012-02-10 | 2012-03-14 | 2012-05-10 | 2012-08-28 | 10/02/12 - Pole up, cabinets in, integrating 13 Feb. 14/02/12. Site needs to be integrated through Taupo Hub, which is not available until 18 Feb. Vol 4 on 22/02 07/03/12 - Site on Air |  | 2012-02-19 | 2012-01-13 | 2012-01-13 | 2012-01-13 | 2012-01-13 | 2011-11-25 | 2012-01-13 | 2012-02-08 | 2012-02-07 |  | 2012-02-27 | [6 empty] | 2012-02-08 | FALSE |  | 2777575 | 6269171 | Taupo Airport opp Sky Diving Operations Taupo |  | Taupo Ref: RM110123 - 28/07/2011 | CELLSITE | [15 empty] | 2012-02-27 | 2012-02-27 | 2011-03-14
0 | WKT | 1523 | WKT-021-013 | Kinloch | WKT-021-013-A | Kinloch - VF Co-lo | Taupo District | 22 | TIER_4 | ACTIVE | COLO | DU | COLO |  | STACK_A | COLO | 25 | 30 |  | -38.6669 | 175.9559 |  |  |  |  | Microwave | WKT-021-003-C | FALSE | FALSE |  |  | FALSE |  | 2012-03-23 | 2012-03-20 | 2012-03-28 | 2012-03-27 | 2012-04-17 | 2012-05-16 | 2 | 2012-04-19 | 2015-02-24 | 2015-05-29 | 2015-04-13 | 2015-08-25 | 2015-08-18 |  | 2015-09-01 | 2015-08-18 | DISCRETIONARY_FULL | 2015-05-04 | 2015-05-04 | 2015-06-15 | 2015-05-28 | 2 | 2015-06-22 | 2015-05-29 | 2015-04-21 | 2015-04-20 | 2015-05-26 | 2015-05-26 | 1 |  | 2015-05-25 | 2015-05-26 | [5 empty] | 2015-09-07 | 2015-08-24 | 2015-09-30 | 2015-09-30 |  | 2015-09-11 | 2015-09-14 | 2015-08-28 | [8 empty] | 2015-10-21 | 2015-10-19 | 2015-11-18 | 2015-11-18 |  |  | 23/03/12 - Caravanned and Rf have done prelim coverage check. OK to proceed 13/04/12 - Rev0 drawings received 27/04/12 - Redline drawings returned to GHD 07/05/12 - Redlines sent back for processing with revised options for RF to work with additional VF antennas 16/-5/12 - Drws received 14/5, and on 16.5 request made for formal issue. All good 25/05/12 - Structural requested with revised antenna locations and load 01/06/12 - Structural received. Ron to lodge VF Colo app 18/06/12 - Colocation document done - need structural to include the 3 additional VF antennas 16.2.15 - VF site data pack requested 19.2.15 - Trevor to provide site search brief - will get VF co-lo plans up rev'd with 4 port antenna and get the co-lo application underway - plans with ghd to up rev 27.2.15 - application with Trev & Brett to confirm 2/3/15 - VF col-lo application submitted 20/4/13 - CDI issued 17/8/15 - received VF approval to build - clock has started on this site. | VNZ | [9 empty] | 2015-10-14 | 2015-10-15 |  |  | TOKOROA_TAUPO | 2015-08-14 |  | BUILD |  | FALSE |  | 2767273 | 6277639 | 259 Whakaroa Road Taupo |  |  | CELLSITE |  |  |  | ROAMING |  |  | 2015-06-23 | 2015-07-17 | 2015-06-11 |  | 2015-04-16 | 2015-05-15 |  | 2015-07-31 | 2015-07-13 |  |  | 2012-03-27
0 | WKT | 1524 | WKT-021-014 |  |  |  | Taupo District |  | TIER_9
0 | WKT | 1525 | WKT-021-015 | Maroanui | WKT-021-015-A | Maroanui - VF Co-lo | Taupo District | 2 | TIER_3 | ACTIVE | COLO | DU | COLO | grey | STACK_A | COLO | 17 | 36.4 | 1 | -38.5196 | 176.0218 |  | 2011-06-01 |  | 2011-06-01 | Microwave | WKT-021-001-A | TRUE | TRUE | 2011-06-01 |  | TRUE |  | 2011-07-21 | 2011-07-18 | 2011-07-22 | 2011-07-20 | 2011-08-05 | 2011-07-29 | 5 | 2011-08-05 | 2015-08-10 | 2011-12-02 | 2011-12-01 | 2012-06-15 | 2012-06-21 |  | 2012-07-06 | 2012-07-17 | DISCRETIONARY_RESTRICT | 2011-08-12 | 2011-08-17 | 2011-09-09 | 2011-09-06 | 1 | 2011-09-16 | 2011-09-09 | 2012-02-16 | 2012-02-18 | 2012-05-02 | 2012-04-27 | 3 |  | 2012-05-02 | 2015-08-12 | 2012-05-21 | 2012-04-18 |  |  |  | 2012-05-11 | 2012-05-18 | 2012-05-24 | 2012-05-24 | 2012-05-21 | 2012-06-19 | 2012-06-18 | [8 empty] | 2012-06-18 | 2012-06-15 | 2012-06-19 | 2012-07-06 | 2012-06-28 | 2013-03-20 | 2013-03-25 | 18/03/13 - JPG photo for AB required, then FAC will be ready for signing 19/03/13 - All signed ready for FAC 25/03/13 - FAC signed | VNZ | 2012-06-19 | 2012-05-21 | 2012-05-21 | 2012-05-21 | 2012-05-21 | 2012-05-16 | 2012-05-21 | 2012-05-29 | 2012-05-29 |  | 2012-06-20 |  |  | TOKOROA_TAUPO |  |  | BUILD | 2012-05-18 | FALSE |  | 2773558 | 6293785 | Lookout Rd, Maroanui, Taupo |  | Council Ref: RM110159 - 09/09/2011 | CELLSITE | [7 empty] | 2012-04-20 | [7 empty] | 2012-06-22 | 2012-06-20 | 2011-07-20
0 | WKT | 1526 | WKT-021-016 | Wairakei | WKT-021-016-A | Wairakei - VF Co-lo | Taupo District | 2 | TIER_3 | ACTIVE | COLO | DU | COLO |  | STACK_A | COLO | 24 | 26 | 1 | -38.6382 | 176.1137 |  |  |  | 2011-06-01 | Fibre Optic |  | TRUE | TRUE | 2011-06-01 |  | TRUE |  | 2011-07-21 | 2011-07-18 | 2011-07-22 | 2011-07-20 | 2011-07-29 | 2011-07-25 | 1 | 2011-07-29 | 2011-07-25 | 2011-08-19 | 2011-12-01 | 2012-05-11 | 2012-04-17 |  | 2012-05-11 | 2012-07-11 | DISCRETIONARY_RESTRICT | 2011-08-05 | 2011-08-05 | 2011-09-02 | 2011-08-22 | 1 | 2011-09-09 | 2011-08-24 | 2012-02-18 | 2012-02-18 | 2012-05-02 | 2012-04-24 | 1 |  | 2012-05-02 | 2012-04-24 | 2012-05-24 | 2012-04-18 | 2012-04-18 |  |  | 2012-05-12 | 2012-05-10 | 2012-05-21 | 2012-05-16 | 2012-05-18 | 2012-06-04 | 2012-06-08 | 2012-06-10 | 2012-06-10 | [6 empty] | 2012-06-10 | 2012-06-15 | 2012-06-14 | 2012-06-23 | 2012-06-21 | 2013-04-19 | 2013-04-10 | 12/06/12 - PAD supplied. Site due to go to air this week 14/06/12 - SOA 09/04/13 - FAN in circulation. 5 groups to sign 10/04/13 FAC signed | VNZ | 2012-06-08 |  | 2012-05-21 | 2012-05-24 | 2012-05-21 | 2012-05-25 | 2012-05-24 | 2012-05-24 | 2012-05-24 |  | 2012-06-12 |  |  | TOKOROA_TAUPO | 2012-06-10 | 2012-06-10 | BUILD | 2012-04-25 | FALSE |  | 2781108 | 6280356 | Aratiatia Station Aratiatia Road Taupo |  | Council Ref - RM110150 - 24/08/2011 | CELLSITE | [7 empty] | 2012-04-20 | [7 empty] | 2012-06-12 | 2012-06-12 | 2011-07-20
0 | WKT | 1527 | WKT-021-017 |  |  |  | Taupo District |  | TIER_9
0 | WKT | 1528 | WKT-021-018 | Turangi | WKT-021-018-C | Genesis Control Station | Taupo District | 22 | TIER_4 | ACTIVE | GF | DU | T2 15 RFH |  | STACK_A | STANDALONE |  | 15 |  | -38.9831 | 175.7658 |  |  |  |  | Fibre Optic | WKT-016-023-B | FALSE | FALSE |  |  | FALSE |  | 2012-04-13 | 2012-04-11 | 2012-04-13 | 2012-04-11 | 2012-06-19 | 2012-06-21 | 1 | 2012-06-19 | 2012-06-21 | 2012-09-21 | 2012-10-05 | 2012-10-26 | 2012-12-14 |  | 2012-11-02 | 2012-12-14 | DISCRETIONARY_RESTRICT | 2012-08-31 | 2012-08-29 | 2012-10-05 | 2012-09-26 | 1 | 2012-10-12 | 2012-09-26 | 2014-10-24 | 2014-10-21 | 2015-02-13 | 2015-02-05 | 1 |  | 2015-02-20 | 2015-02-05 | 2015-03-18 |  |  |  |  | 2015-04-30 | 2015-04-29 | 2015-06-24 | 2015-06-25 | 2015-05-19 | 2015-05-29 | 2015-05-22 |  | 2015-04-10 | [7 empty] | 2015-07-16 | 2015-07-10 | 2015-06-29 | 2015-07-31 |  |  | 05/10/12 - Moved out of Build programme 16/6/14 - Approved to proceed to CD's 16/1/15 - arranged for scrub clearing to be done next week - geotch drilling arranged for week beginning 26th Jan. 28/1/15 - awaiting CD1 issue, fibre to be delivered to power station - 2d to arrange IBT to site with build contractors at time of build 3/9/15 - all equipment ordered, tender meeting held - awaiting pricing. Fibre delivery at risk - chorus to advise asap. alternative TX solution under proposal. 13/4/15 - PO6 issued to Huawei |  | 2015-06-28 |  |  |  |  | 2015-03-18 | 2015-03-18 | 2015-06-18 |  | 2015-07-08 | 2015-07-01 | 2012-03-09 | LOW | NATIONAL_PARK |  | 2015-04-10 | BUILD | 2015-05-19 | FALSE |  | 2749640 | 6243098 | Genesis Tokaanu Power station, 134 Te Ponanga Saddle Rd (SH47), Turangi |  |  | CELLSITE |  |  |  | ROAMING |  | 2014-12-18 | 2014-12-11 |  | 2015-04-13 |  |  |  | 2015-03-23 |  | 2015-04-13 | 2015-07-06 |  | 2012-04-11
0 | WKT | 1529 | WKT-021-019 |  |  |  | Taupo District |  | TIER_9
0 | WKT | 1530 | WKT-021-020 |  |  |  | Taupo District |  | TIER_9
0 | WKT | 1531 | WKT-021-021 | Tuhingamata |  |  | Taupo District |  | TIER_9
0 | WKT | 1532 | WKT-021-022 | Huka Village |  |  | Taupo District |  | TIER_9
0 | WKT | 1533 | WKT-021-023 | Taupo North East |  |  | Taupo District |  | TIER_9
0 | WKT | 1534 | WKT-021-024 | Mangakino | WKT-021-024-A | Mangakino - VF Co-lo | Taupo District | 22 | TIER_4 | ACTIVE | COLO | DU | LATTICE |  | STACK_A | COLO |  |  |  | -38.4542 | 175.8193 |  |  |  |  | Microwave, Microwave | WKT-019-007-B, WKT-019-007-B | FALSE | FALSE |  |  | FALSE |  | 2014-12-11 | 2014-11-18 | 2014-12-15 | 2014-11-18 | 2014-11-28 | 2012-08-23 | 3 | 2015-01-23 | 2015-04-30 | 2015-04-24 | 2015-03-30 | 2015-08-31 | 2015-09-09 |  | 2015-08-31 | 2015-09-21 | DISCRETIONARY_FULL | 2015-04-30 | 2015-04-30 | 2015-06-19 | 2015-05-28 | 3 | 2015-06-26 | 2015-05-28 | 2015-06-30 | 2015-03-30 | 2015-05-29 | 2015-06-03 | 1 |  | 2015-05-29 | 2015-06-03 | [5 empty] | 2015-09-15 | 2015-09-15 | 2015-10-15 | 2015-10-15 |  | 2015-10-16 | 2015-10-16 | 2015-09-14 | [8 empty] | 2015-10-30 | 2015-10-30 | 2015-11-20 | 2015-11-20 |  |  | Planning note : Most restrictive site. Colocation will be far better than own site. 10/11/10 Vodafone datapack received. Looks OK. Structural requested. Le Blanc triangular slim lattice 01/02/12 - Area visited. Unable to get to site (will need full 4wd). Site is high and prominant, and may have soem issues to work through 16/02/11 - do pre-plan work and caravan in March when James available for visits. May need helicopter to access. 25/07/12 - Caravan next week. Teresa will assist. Need to walk last 20min. IWI are OK, but James will need letter for Consent application 01/08/12 - WO1 issued 23/08/12 - Letter rquired from Hinu that the Ewi were consulted 30/08/12 - Structure failed with future VF euipment - Backup option required 29/01/15 - PD underway - when issued prepare and sumbit VF co-lo application 19.2.15 - awaiting information for VF co-lo application from RF and TX 19.2.15 - VF co-lo application submitted 27/3/15 - received prelim approval from VF 20/7/15 - received approval to build from VF | VNZ | [9 empty] | 2015-10-27 | 2015-10-28 |  |  | TOKOROA_TAUPO |  |  | BUILD |  | FALSE |  | 2756137 | 6301623 | 399 Kaahu Road Whakamaru |  |  | CELLSITE |  |  |  | ROAMING |  |  | 2015-07-13 | 2015-06-30 | 2015-06-11 |  | 2015-04-16 |  |  | 2015-08-03 | 2015-07-13 |  |  | 2014-11-18
0 | WKT | 1535 | WKT-021-025 | Kiddle Drive |  |  | Taupo District | 2 | TIER_9 | [22 empty] | FALSE
0 | WKT | 1536 | WKT-021-026 | Hyde Avenue | WKT-021-026-C | Greenfield Option F Greenwich Street | Taupo District | 2 | TIER_2 | ACTIVE | GF | DU | T2 15 UF |  | STACK_A | STANDALONE | 14 | 15 | 1 | -38.717 | 176.1041 | 2011-10-13 |  | 2011-10-13 |  | Microwave | WKT-021-007-B | TRUE | TRUE | 2011-10-13 | 2011-10-13 | TRUE |  | 2012-05-09 | 2012-05-09 | 2012-05-11 | 2012-05-11 | 2012-05-23 | 2012-05-25 | 1 | 2012-05-23 | 2012-05-25 | 2012-05-31 | 2012-06-11 | 2012-06-15 | 2012-07-17 |  | 2012-06-22 | 2012-07-17 | DISCRETIONARY_RESTRICT | 2012-06-08 | 2012-06-01 | 2012-06-29 | 2012-06-28 | 1 | 2012-06-29 | 2012-06-28 |  |  | 2012-08-17 | 2012-08-17 | 1 |  | 2012-08-17 | 2012-08-17 | 2012-08-18 |  |  | 2012-07-27 |  | 2012-08-22 | 2012-08-22 | 2012-09-07 | 2012-09-05 | 2012-09-03 | 2012-09-14 | 2012-09-07 | [8 empty] | 2012-09-08 | 2012-10-05 | 2012-09-28 | 2012-10-04 | 2012-09-25 | 2013-05-10 | 2013-05-08 | 18/03/13 - Snags to clear for FAN issue. Site passed revisit for PIM |  | 2012-09-17 | 2012-08-18 | 2012-08-18 | 2012-08-18 | 2012-08-18 | 2012-08-18 | 2012-08-18 | 2012-09-10 | 2012-09-06 | 2012-09-21 | 2012-09-18 | [5 empty] | BUILD | 2012-09-10 | TRUE |  | 2779968 | 6271646 | Council Land - Option F off Greenwich Street Taupo |  |  | CELLSITE | [15 empty] | 2012-09-17 | 2012-09-19 | 2012-05-11
0 | WKT | 1537 | WKT-021-027 | Wairakei COW -MORGO Conference |  |  | Taupo District | 2 | TIER_9 | [22 empty] | FALSE
0 | WKT | 1538 | WKT-021-028 | RBI - Omori | WKT-021-028-A | Omori RBI | Taupo District | 25 | TIER_5 | ACTIVE | RBI | DF | COLO |  | STACK_A | COLO | 28 | 30 |  | -38.894 | 175.7394 |  |  |  |  | Fibre Optic | WKT-016-044-A | FALSE | FALSE | 2015-12-14 |  | FALSE |  | 2015-10-16 | 2015-10-16 | 2015-10-22 | 2015-10-22 | 2015-10-22 | 2015-11-02 | 1 | 2015-10-22 | 2015-11-02 | 2016-03-04 |  | 2016-03-25 |  |  | 2016-03-28 |  | PERMITTED | 2016-03-04 |  | 2016-03-08 |  |  | 2016-03-10 |  | 2016-02-26 |  | 2016-03-08 |  |  |  | 2016-03-11 | [6 empty] | 2016-04-04 |  | 2016-04-08 |  |  | 2016-04-08 |  | 2016-04-08 |  | 2016-03-23 |  | 2016-03-30 |  | 2016-03-30 |  |  | 2016-04-22 | [5 empty] | 19 Oct: SDP received 20 Oct: Pre-qual requested. 22 Oct: Co-lo & co-site applications sent to VF & Spark 2 Nov: As-builts incorrect. Need to source correct info to redesign RF solution 7 Dec: Awaiting final design for alternate antenna fixture. Prepare co-lo. ATN & antennas ordered 12 Jan: Waiting for VF approval & quote for VF antennas. Also ETA on Huawei antennas 2 Feb: Spark reject proposed design. Escalated to get Site Acq to request Spark review & offer antenna consolidation rather than adding to the tower. 10 Feb: Paul Brierley looking into a solution that accommodates Spark & 2D. | VNZ | [9 empty] | 2016-04-15 |  |  |  |  | 2016-04-05 |  | BUILD | 2016-04-04 | FALSE |  | 2747666 | 6253050 | 123 Te Puke Road Kuratau |  |  | CELLSITE |  |  |  | ROAMING |  |  | 2016-02-10 | 2015-11-23 | 2015-11-25 | 2015-10-23 | 2015-10-23 | 2015-11-18 | 2015-11-20 | 2016-03-25 |  |  |  | 2015-10-22
0 | WKT | 1539 | WKT-021-029 | 3 Te Kuru Lane Mini-Repeater | WKT-021-029-A | Bill Osborne Repeater - Omori | Taupo District | 2 | TIER_6 | ACTIVE | IB | 900_MINI_RPTR | BO |  |  | STANDALONE |  |  |  | -38.9163 | 175.753 | [6 empty] | FALSE | FALSE |  |  | FALSE | [75 empty] | ROTORUA_TAUPO | [6 empty] | 2748768 | 6250538 | 3 Te Kuru Ln Omori 3381
0 | WKT | 1540 | WKT-021-030 | Wairakei Resort Mini-Repeater |  |  | Taupo District |  | TIER_6
0 | WLG | 1541 | WLG-043-001 |  | WLG-043-001-A | Paekakariki | Kapiti Coast District |  | TIER_1_ALL | ACTIVE | GF | A | LATTICE | grey |  |  | 12.2 | 12.2 |  | -40.9893 | 174.9574 |  |  |  |  | Microwave, Microwave | WLG-044-013-A, WLG-044-013-A | [5 empty] | 2008-09-02, 2008-09-02 | [5 empty] | 2008-09-03 | 2 | 2009-03-06 | 2009-03-03 |  |  | 2008-10-31 | 2008-10-03 | 2 | 2009-04-30 | 2009-04-28 |  | 2009-03-02 |  | 2009-04-06 |  |  | 2009-05-02 | 2009-04-02 |  | 2008-11-12 |  | 2009-04-28 | 1 | 1 | 2009-04-28 | 2009-04-28 | [5 empty] | 2009-05-15 | 2009-05-11 | 2009-06-23 | 2009-06-19 |  | 2009-06-30 | 2009-06-29 | [8 empty] | 2009-06-30 | 2009-06-30 | 2009-06-30 |  |  |  |  | 9/2/09: Stuck site. Site location moved, tower type changed and TX to sign off. RMA to be lodged. 9/3/09: RMA lodged awaiting council feedback. Consent expected to be issued April, but mayor may require further consultation. Need to obtain co-site consent to present to the landlords lawyer. 16/3/09: No problem with lease. RMA awaiting council decision - early feedback is not negative. Will follow up later this week. 23/3/09: Plans signed by Landlord and received 20/3/09. 30/3/09:Revised plan signed and lease executed. Await co-site approval only. JM to check with JC and DdV if we can build. DdV confirmed that we can build pending RMA. 6/4/09: Awaiting co-site approval. Telecom have main access right to track and power. JM to enquire if we can hard match and build? 20/4/09: CDs all signed off to issue this week. 27/4/09: Pending co-site approval ONLY! Claim all site acq complete once co-siting is received. 12/5/09: Build underway. 2nd power quote awaited. Serious access issues in bad weather. |  | 2009-06-30 | [17 empty] | FALSE |  | 2674669 | 6022300 | Access track off Paekakariki Hill Road 324 State Highway 1 PO Box 21 Paekakariki |  |  | CELLSITE | [7 empty] | 2009-05-11 | 2009-05-11 | [8 empty] | 2008-08-12
0 | WLG | 1542 | WLG-043-002 |  | WLG-043-002-C | Kapiti | Kapiti Coast District |  | TIER_1_ALL | ACTIVE | GF | A | P4B | green |  |  | 12.6 | 12.6 |  | -40.8937 | 174.9808 |  |  |  |  | Microwave, Microwave | WLG-043-001-A, WLG-043-001-A | [5 empty] | 2008-11-12, 2008-11-12 | [5 empty] | 2008-12-18 | 3 |  | 2009-02-09 |  |  | 2009-01-30 | 2009-01-16 | 1 | 2009-01-30 | 2009-01-16 |  |  |  | 2009-04-30 |  |  | 2009-04-30 | 2009-04-02 |  | 2009-02-02 |  | 2009-05-07 | 1 | 2 | 2009-05-05 | 2009-05-07 | [5 empty] | 2009-05-20 | 2009-05-18 | 2009-06-15 | 2009-06-15 |  | 2009-06-25 | 2009-06-15 | [8 empty] | 2009-06-30 | 2009-06-30 | 2009-06-30 |  |  |  |  | 9/2/09: Redesign to freestanding complete and landlord has approved the proposal. RMA lodged as a COC. Lease is complete as at 16/1/09. 9/3/09: Potential hardmatch in March. Awaiting confirmation from Antony Royal that we can carry on with this site without consultation. 19/3/09: RF approval to build. 16/3/09: Pending a decision to be made this week on consultation process. 16/3/09: All Town Planning Not Complete pending decision on consultation - to be decided this week. 23/3/09: All on course for RMA. 30/3/09: Pending public consultation. Didn't want to impact on Pekakariki and Paraparaumu. Hoping to get an answer by the end of today. 6/4/09: To TSS. 20/4/09: CDs all signed off to issue this week. |  | 2009-06-30 | [17 empty] | FALSE |  | 2676879 | 6032873 | 14-16 Seaview Rd, Paraparaumu, Kapiti Coast |  |  | CELLSITE |  |  | 2015-11-27 |  |  |  |  | 2009-05-18 | 2009-05-14 | [8 empty] | 2008-11-12
0 | WLG | 1543 | WLG-043-003 |  | WLG-043-003-A | Paraparaumu | Kapiti Coast District |  | TIER_1_ALL | ACTIVE | GF | A | P7 | green |  |  | 23.8 | 23.8 |  | -40.9206 | 175.0062 | [6 empty] | FALSE | FALSE |  |  | FALSE |  |  | 2008-08-12 |  |  |  | 2008-09-03 | 6 |  | 2015-09-07 |  |  | 2009-07-17 | 2009-07-17 |  | 2009-07-17 | 2009-07-17 |  | 2009-02-27 |  | 2009-04-30 |  |  | 2009-04-30 |  | 2009-04-21 | 2009-04-27 |  | 2009-04-28 | 1 | 4 | 2009-05-15 | 2009-04-28 | 2009-02-02 |  |  |  |  | 2009-07-20 | 2009-07-20 | 2009-08-20 | 2009-08-03 |  | 2009-08-21 | 2009-08-05 | [8 empty] | 2009-08-05 | 2009-08-30 | 2009-08-05 |  |  |  |  | 9/2/09: Stuck site. TX to confirm the dish requirement on the VF pole. 25m height to our pole. CDI 09/02/09. 9/3/09: Key 2 site. Brendan Poole for Acquisition. RMA awaiting plans. 16/3/09: Council require landscape mitigation and we are currently engaging a landscape architect to assist on the process with Council. Success may avoid notification and we may be able to get the landscaping requirement agreed as a condition of consent which means build can proceed. 23/3/09: Lease to complete after resource consent. A Key2 site. Roger B requires second landscaping quote. BB to check and instruct ASAP. 30/3/09: Pending public consultation. Didn't want to impact on Paekakariki and Paraparaumu. Hoping to get an answer by the end of today. KEY 2. 6/4/09: Waiting for approval of landscaping by Council. 16/4/09: Landscaping scheme has been agreed with Council. Landscaping plan still to be provided. 20/4/09: Key 2 site. RMA landscaping plan is approved. RMA forecasts good. Lease forecasts are ok. CDs all approved. Chase co-siting. 27/4/09: Brendan at Key 2 has received a copy of the RC. 5/5/09: Planting scheme received and needs to go to Wayne McMahon. Lease is still being prepared by the Council Solicitors. Cannot do any build activity without co-site approval. 18/5/09: Lease is imminent. Nee to chase co-siting. 21/5/09: Co-siting approval outstanding. No progress on lease with Council. Brendan Poole from Key 2 is looking after and is dealing with Shaun Hester (property manager). 26/5/09: PMcK still chasing. Now talking of taking t he site to Council for determination. Team to investigate other options 2/6/09: Going to business sub-committee on 25th June. Trying to get the lease reviewed and executed before 25th so that we can get on with the build as soon after. Town planning, Site Acq and Antony Royal, RF. 8/6/09: Council Business Sub-Committee meeting on the 25th to determine if we can continue as planned. PMcK to check for pre-construction meetings and details to run ahead of the 25th to minimise time into build. Also, PMCK to follow up option at Big Save Furniture. 15/6/09: JM to contact Sean Mallon 04 296 4690 or 0275 555690 - Council Asset Manager. PMcK should receive lease but not execute until the above meeting has determined. Contractors being teed up to start ASAP after acquisition. 22/6/09: Sub committee meeting now deferred until 3rd July 09. 29/6/09: Waiting Council determination on the site. Due 2nd July. No Voda co-site approval. Chasing Voda, we're 10m horizontal and 4.3m vertical but Voda do not take vertical into consideration. Lease states that we MUST have co-site approval. 9/7/09: KCDC have approved this site. Feedback on lease from Jess. Council seeking construction methodology and VF co-siting approval before we can execute. 14/7/09: PRIORITY SITE: Meeting with Council this week as required by them to run through H&S and site specific requirements. Cannot start without this meeting and it will be held at the first possibly opportunity. 21/7/09: In build. 28/7/09: In build. |  | 2009-08-30 | [5 empty] | 2009-02-02 | [11 empty] | FALSE |  | 2678947 | 6029836 | 47 Epiha Street (but access off end of Riwai Street) Paraparaumu Wellington |  |  | CELLSITE |  |  | 2015-10-15 |  |  |  |  | 2009-07-20 | 2009-07-17 | [8 empty] | 2008-08-14
0 | WLG | 1544 | WLG-043-004 |  | WLG-043-004-C | Waikanae | Kapiti Coast District |  | TIER_1_ALL | ACTIVE | GF | A | P2 | grey |  |  | 13.8 | 13.8 |  | -40.8738 | 175.0653 | [17 empty] | 2008-12-18 | 1 |  | 2008-12-18 |  |  | 2009-01-31 | 2009-01-29 | 1 | 2009-01-31 | 2009-01-31 |  |  |  | 2009-04-30 |  |  | 2009-04-30 | 2009-04-02 | 2009-03-10 | 2009-03-02 |  | 2009-04-28 | 1 | 1 | 2009-04-28 | 2009-04-28 | 2009-04-21 |  |  |  |  | 2009-05-15 | 2009-05-14 | 2009-05-30 | 2009-05-30 |  | 2009-06-05 | 2009-05-30 | [8 empty] | 2009-07-27 | 2009-07-27 | 2009-07-27 |  |  |  |  | 9/2/09: Lease posted 21/1/09 - complete? Notification/consultation in place for majority 043 sites, bar Forest Heights. 9/3/09: Potential hardmatch in March. Awaiting confirmation from Antony Royal that we can carry on with this site without consultation. Tenant to do the trenching? 16/3/09: All Town Planning Not Complete pending decision on consultation - to be decided this week. 30/3/09: Pending public consultation. Didn't want to impact on Paekakariki and Paraparaumu. Hoping to get an answer by the end of the day. 6/4/09: To TSS. 20/4/09: CDs all signed off for issue this week. 18/5/09: Changing the pole in Wellington. |  | 2009-07-27 |  |  |  |  | 2009-04-22 | 2009-04-21 | [11 empty] | FALSE |  | 2684046 | 6034909 | Thomas Plumbing and Gas Limited 21 Omahi Street Waikanae |  |  | CELLSITE | [7 empty] | 2009-05-14 | 2009-05-14 | [8 empty] | 2008-11-13
0 | WLG | 1545 | WLG-043-005 |  | WLG-043-005-A | Peka Peka | Kapiti Coast District | 7 | TIER_1_ALL | ACTIVE | GF | A | LATTICE | grey |  | COSITE | 22 | 22 |  | -40.844 | 175.1032 |  |  |  |  | Microwave | WLG-043-004-C | FALSE | FALSE |  |  | FALSE | [6 empty] | 2008-12-12 | 8 | 2012-01-27 | 2013-12-10 |  |  | 2009-01-21 | 2009-01-21 | 1 | 2012-04-24 | 2012-04-19 | PERMITTED | 2012-01-31 | 2012-02-10 | 2012-03-13 | 2012-03-15 | 7 | 2012-03-23 | 2012-03-15 |  | 2009-01-26 | 2009-05-26 | 2009-05-26 | 3 |  | 2009-05-26 | 2012-03-16 | [5 empty] | 2009-06-10 | 2009-06-08 | 2009-06-30 | 2009-06-29 |  | 2009-07-27 | 2009-07-27 | [8 empty] | 2009-07-27 | 2009-07-27 | 2009-07-27 |  |  |  |  | 9/2/09: Lease compelte 12/1/09. Not subject to notification/consultation process. Co-siting with OLOs not required. 9/3/09: Hardmatch. 16/3/09: Co-siting? 19/3/09: RF approval to build. 30/3/09: Access road may need repair. Anglican church responsible. 20/4/09: CDs all signed off to issue this week. Question over whether structural solution works. 5/5/09: Still waiting for structural approval of drawings. JM to speak to Warren to determine if he is happy. 12/5/09: Landlord approval to drawings is done. Checking for independant supply and then arranging TSS. 26/5/09: VF dish to relocate? 29/6/09: Built |  | 2009-07-27 | [10 empty] | 2012-02-10 | LOW | [5 empty] | FALSE |  | 2687320 | 6038145 | Hadfield Road Pekapeka Kapiti Coast |  | Upgrade not new site - 10/02/2012 | CELLSITE |  |  | 2015-11-20 |  |  |  |  | 2009-05-30 | 2009-05-27 | [8 empty] | 2008-10-09
0 | WLG | 1546 | WLG-043-006 | Paraparaumu Central | WLG-043-006-A | Crighton Building | Kapiti Coast District | 24 | 2015P | ACTIVE | GF | DF5 | T2 20 UF |  |  | STANDALONE |  |  |  | -40.9043 | 175.0021 |  | 2014-11-20 |  | 2015-05-01 | Leased Line | WLG-044-015-A | FALSE | FALSE |  |  | FALSE |  | 2015-07-07 | 2015-07-09 | 2015-07-03 | 2015-07-09 | 2015-07-31 | 2015-08-07 | 1 |  | 2015-08-07 | 2015-07-28 | 2015-07-28 | 2015-08-31 | 2015-08-20 |  |  |  | DISCRETIONARY_FULL | 2015-08-14 | 2015-08-14 | 2015-09-11 | 2015-09-14 | 1 |  |  | 2015-09-01 |  | 2015-09-30 | [10 empty] | 2016-01-18 |  | 2016-02-29 |  |  | 2016-03-11 | [10 empty] | 2016-04-15 | [5 empty] | Site searches complete 20 Jan - Caravan to be arranged once LO in agreement. 16/04: AS Caravan due on 20th April 20/04: AS Caravan completed Brenna to find out rental expectation 24/06: Candidate has become active because Trench mate crashed 09/7: AS Moved to next year build | TNZ | [9 empty] | 2016-03-31 | [6 empty] | ONHOLD |  | TRUE |  | 2678644 | 6031648 | 54 Te Roto Dr Owner: Ballinger Industries Ltd |  |  | CELLSITE | WIPACTIVE |  |  | CAPACITY |  |  |  | 2016-11-01 | [5 empty] | 2015-12-11 |  |  |  | 2015-07-09
0 | WLG | 1547 | WLG-043-007 | Raumati | WLG-043-007-L | 15 Raumati Rd (Bus Stop) | Kapiti Coast District | 7 | TIER_1_INFILL | ACTIVE | RSR | DU | P4E |  | INLINE | STANDALONE | 13.8 | 14.3 | 1 | -40.9188 | 174.9816 |  |  |  |  | Leased Line | WLG-047-071-A | TRUE | TRUE |  |  | TRUE |  | 2011-11-29 | 2011-11-25 | 2011-12-06 | 2011-11-28 | 2012-03-28 | 2012-03-28 | 4 | 2012-03-28 | 2012-08-01 | 2012-07-24 | 2012-07-31 | 2012-08-17 | 2012-08-22 |  | 2012-08-17 | 2012-08-22 | NES | 2012-04-30 | 2012-04-30 | 2012-06-08 | 2012-06-07 | 2 | 2012-07-20 | 2012-07-24 |  |  | 2012-07-31 | 2012-08-01 | 1 |  | 2012-07-31 | 2012-08-01 |  |  |  | 2012-07-13 |  | 2012-07-30 | 2012-08-02 | 2012-08-22 | 2012-09-03 | 2012-08-13 | 2012-08-17 | 2012-09-03 | [8 empty] | 2012-09-12 | 2012-09-14 | 2012-09-14 | 2012-10-20 | 2012-10-01 | 2013-04-10 | 2013-04-08 | 12.06.2014 : "D" configuration build. (APM, Battery, & 2 x RFC) using version "B" cabinets. Thus making it a "DU" Site. (As per Ron Bush/blr) |  | 2012-09-07 | 2012-06-28 | 2012-06-28 | 2012-07-18 | 2012-08-13 |  |  | 2012-08-14 | 2012-08-14 | 2012-09-12 | 2012-09-13 | 2012-04-30 | HIGH |  | 2012-09-04 | 2012-09-05 | BUILD | 2012-08-14 | TRUE |  | 2676882 | 6030085 | 15 Raumati Rd (Bus stop near Rosetta Rd) |  |  | CELLSITE |  |  | 2015-10-15 | [12 empty] | 2012-09-17 | 2012-09-17 | 2011-11-28
0 | WLG | 1548 | WLG-043-008 | Paraparaumu North | WLG-043-008-E | LPR 93 Mazengarb Rd | Kapiti Coast District | 7 | TIER_1_INFILL | ACTIVE | RSR | DU | P4F |  | INLINE | STANDALONE | 13 | 13.7 |  | -40.8868 | 175.0032 |  | 2012-04-20 |  |  | Microwave | WLG-043-005-A | FALSE | FALSE |  |  | FALSE |  | 2011-06-29 | 2011-06-29 | 2011-07-06 | 2011-07-12 | 2011-07-29 | 2011-08-01 | 4 | 2011-07-29 | 2015-04-28 | 2011-12-20 | 2012-01-24 | 2012-02-21 | 2012-02-16 |  | 2012-02-21 | 2012-02-22 | NES | 2011-12-16 | 2011-12-13 | 2012-02-15 | 2012-03-06 | 3 |  |  |  |  | 2012-03-06 | 2012-03-13 | 1 |  | 2012-03-13 | 2012-03-13 | 2012-04-03 |  |  |  |  | 2012-04-02 | 2012-04-02 | 2012-04-20 | 2012-05-11 | 2012-05-09 | 2012-05-16 | 2012-05-16 | [8 empty] | 2012-05-17 | 2012-05-31 | 2012-05-31 | 2012-06-06 | 2012-06-06 | 2012-09-04 | 2012-10-02 | 12.06.2014 : "D" configuration build. (APM, Battery, & 2 x RFC) using version "B" cabinets. Thus making it a "DU" Site. (As per Ron Bush/blr) |  | 2012-05-17 |  |  |  | 2012-05-17 |  | 2012-04-03 | 2012-04-18 | 2012-04-11 | 2012-05-23 | 2012-05-24 | [6 empty] | 2012-05-14 | FALSE |  | 2678784 | 6033592 | 93 Mazengarb Rd Paraparaumu North |  |  | CELLSITE |  |  | 2015-10-15 | [12 empty] | 2012-06-23 | 2012-05-23
0 | WLG | 1549 | WLG-043-009 | Waikanae Beach | WLG-043-009-I | Golf Club Knoll | Kapiti Coast District | 7 | TIER_3 | ACTIVE | GF | Ab | P2 |  | STACK_A | STANDALONE |  | 21.6 | 1 | -40.864 | 175.0296 |  | 2012-04-20 |  |  | Microwave | WLG-043-005-A | FALSE | FALSE |  |  | FALSE |  | 2011-12-08 | 2011-12-08 | 2011-12-15 | 2011-12-08 | 2012-02-08 | 2012-02-08 | 1 | 2012-02-08 | 2012-02-08 | 2012-03-09 | 2012-03-01 | 2012-06-29 | 2012-06-19 |  | 2012-06-29 | 2012-06-25 | DISCRETIONARY_FULL | 2012-02-15 | 2012-02-10 | 2012-11-30 | 2012-12-07 | 1 | 2012-11-30 | 2012-12-10 |  |  | 2013-01-24 | 2013-01-24 | 1 |  | 2013-01-24 | 2013-01-24 |  |  |  | 2013-01-23 |  | 2013-03-25 | 2013-03-27 | 2013-05-20 | 2013-05-17 | 2013-05-17 | 2013-06-24 | 2013-06-20 | [8 empty] | 2013-06-20 | 2013-06-30 | 2013-07-04 | 2013-07-26 | 2013-07-26 | 2013-10-24 | 2013-12-05 | 9/5/13: • Under construction • CD’s were available from 24/1/13, and WO2 was issued (16/1/13), however construction did not commence until 27/3/13. Dawie has said no PAC extension will be granted for this site. |  | 2013-05-27 | [6 empty] | 2013-03-25 | 2013-06-03 | 2013-06-25 | 2013-06-21 | 2012-12-10 | HIGH | TIER_1_INFILL |  |  | BUILD | 2013-05-07 | TRUE | 2013-01-24 | 2681066 | 6036073 | Waikanae Beach 101 Te Moana Rd, Waikanae |  |  | CELLSITE | [15 empty] | 2013-06-21 | 2013-06-24 | 2011-12-08
0 | WLG | 1550 | WLG-043-010 | Raumati South | WLG-043-010-A | Raumati South | Kapiti Coast District |  | TIER_6 | ACTIVE | [100 empty] | HARDMATCH
0 | WLG | 1551 | WLG-043-011 | Otaki Town | WLG-043-011-A | Otaki Town | Kapiti Coast District | 6 | TIER_2 | ACTIVE | GF | DU | P1 |  | INLINE | STANDALONE | 15 | 15 | 1 | -40.7582 | 175.1592 |  |  |  |  | Microwave | WLG-043-005-A | FALSE | FALSE |  |  | FALSE | 2011-11-11 | 2011-10-27 | 2011-10-27 | 2011-11-03 | 2011-11-14 | 2012-02-13 | 2012-02-13 | 1 | 2012-02-13 | 2012-02-13 | 2012-02-14 | 2012-01-23 | 2012-02-28 | 2012-05-10 | 1 | 2012-02-28 | 2012-05-10 |  | 2012-02-29 | 2012-02-14 | 2012-03-21 | 2012-05-07 | 1 | 2012-03-21 | 2012-05-07 |  |  | 2012-03-24 | 2012-07-16 | 1 |  | 2012-03-25 | 2012-07-16 | 2012-07-06 |  |  |  |  | 2012-06-28 | 2012-06-28 | 2012-07-13 | 2012-07-12 | 2012-07-11 | 2012-07-16 | 2012-07-17 | [8 empty] | 2012-07-17 | 2012-07-25 | 2012-07-25 | 2012-07-28 | 2012-07-27 | 2013-05-25 | 2013-05-29 |  |  | 2012-07-16 | 2012-06-28 | 2012-06-28 | 2012-07-04 | 2012-07-04 | 2012-07-10 | 2012-07-06 | 2012-07-13 | 2012-07-12 |  | 2012-07-25 | [5 empty] | BUILD | 2012-07-13 | FALSE |  | 2692281 | 6047558 | Otaki Town 261-263 SH1 Otaki |  |  | CELLSITE |  |  | 2015-10-15 | [12 empty] | 2012-07-24 | 2012-07-25
0 | WLG | 1552 | WLG-043-012 | Otaki Beach | WLG-043-012-A | Proposed GF | Kapiti Coast District | 24 | TIER_5 | ACTIVE | GF | DF5 | T2 20 RF |  | STACK_A | STANDALONE |  |  |  | -40.7447 | 175.1218 |  | 2015-03-13 |  | 2015-05-01 | Leased Line | MNW-042-003-A | FALSE | FALSE |  |  | FALSE |  | 2015-02-12 | 2015-02-13 | 2015-02-27 | 2015-04-16 | 2015-04-30 | 2015-04-28 | 1 | 2015-04-28 | 2015-04-28 | 2015-07-28 | 2015-07-23 | 2015-07-17 | 2015-07-23 |  |  | 2015-08-04 | DISCRETIONARY_FULL | 2015-05-15 | 2015-06-02 | 2015-07-03 | 2015-07-07 | 1 |  | 2015-08-06 | 2015-10-23 | 2015-10-01 | 2016-02-22 | [10 empty] | 2016-03-18 |  | 2016-04-15 |  |  | 2016-04-29 | [10 empty] | 2016-05-27 | [5 empty] | 09/7: AS moved to next year build | [10 empty] | 2016-05-13 | [6 empty] | BUILD |  | TRUE |  | 2689156 | 6049132 | Tasman Road Otaki Beach |  |  | CELLSITE | WIPACTIVE |  |  | ROAMING |  | 2015-11-25 | 2016-01-14 | 2016-02-26 | 2016-01-12 |  |  |  |  | 2016-03-11 |  |  |  | 2015-04-16
0 | WLG | 1553 | WLG-043-013 | Waikanae South |  |  | Kapiti Coast District | 23 | TIER_5 | [22 empty] | FALSE | [60 empty] | site ideally needs to be on this 35m high hill in order to serve new motorway & old motorway dead spots. Picture attached of proposed new motorway route. Other mounds in the area that are over 20m high will also be considered if 1st option fails. Depending on the final location we may be able to utilise the cheaper tier 5 12m solution
0 | WLG | 1554 | WLG-044-001 |  | WLG-044-001-B | Camborne | Porirua City | 7 | TIER_1_ALL | ACTIVE | GF | A | P1 | grey |  |  | 10.8 | 10.8 |  | -41.0896 | 174.8715 |  |  |  |  | Microwave | WLG-044-012-B | FALSE | FALSE |  |  | FALSE | 2008-08-12 | [5 empty] | 2008-09-03 | 5 | 2011-10-21 | 2012-03-15 |  |  | 2009-03-12 | 2009-03-12 | 2 | 2011-08-19 | 2011-08-09 | PERMITTED |  | 2011-08-30 | 2009-02-18 | 2011-08-30 | 4 | 2011-09-30 | 2011-08-30 |  | 2009-01-20 |  | 2009-02-02 | 4 |  | 2012-03-13 | 2012-03-16 | 2009-03-17 |  |  |  |  | 2009-05-11 | 2009-05-11 | 2009-05-30 | 2009-05-29 |  | 2009-06-02 | 2009-06-02 | [8 empty] | 2009-06-26 | 2009-06-30 | 2009-06-26 |  |  |  |  | 9/2/09: Lease dependant on RMA completion. 9/3/09: Lease is almost complete - already signed by NZCL. RMA needs to be complete to progress. Need to conduct RF tests as a lease condition. 16/3/09: Concerns over water tower and our pole location now cleared. Council have confirmed that if a new water tower is required they will rebuild on existing location. RMA currently working with residents to resolve their issue with RF. 19/3/09: RF approval to build. 23/3/09: Awaiting co-site approval only and RF testing. 30/3/09: Problem with Voda and accepting the co-siting for RF. LH to chase with JC for Voda by TNZ could now be a problem. LH to investigate. JM to check status of co-site approval. 6/4/09: Pending co-siting approval. We have VF approval. TNZ will not sign off so JM to chase approval to build from JC and DdV. 16/4/09: Still awaiting co-site approval only. JM requested approval to build. 20/4/09: Co-siting is good. CDs to issue this week. 27/4/09: TSS ASAP. No pole lift before 4th May 09. 5/5/09: BUILD 12/5/09: RF testing required and done prior to build. |  | 2009-06-30 |  |  |  |  | 2009-03-02 | 2009-03-17 | [11 empty] | FALSE |  | 2667206 | 6011327 | Tremaine Place, Camborne, Porirua. |  |  | CELLSITE |  |  | 2015-12-02 |  |  |  |  | 2009-05-11 | 2009-05-11 | [8 empty] | 2008-08-13
0 | WLG | 1555 | WLG-044-002 |  | WLG-044-002-F | Titahi Bay | Porirua City |  | TIER_1_ALL | ACTIVE | GF | A | P2 | green |  |  | 13.8 | 13.8 |  | -41.0976 | 174.8443 | [12 empty] | 2009-04-30 | 2009-04-22 |  |  |  | 2009-05-05 | 2 | 2009-05-08 | 2009-07-13 |  |  | 2009-08-10 | 2009-08-04 | 2 | 2009-08-10 | 2009-08-10 |  | 2009-05-22 |  | 2009-06-25 |  |  | 2009-06-26 | 2009-06-12 | 2009-06-15 | 2009-05-12 | 2009-06-30 | 2009-06-29 | 2 | 2 | 2009-06-30 | 2009-07-23 | 2009-04-21 |  |  |  |  | 2009-08-27 | 2009-08-26 | 2009-09-14 | 2009-09-11 |  | 2009-09-16 | 2009-09-16 | [8 empty] | 2009-09-17 | 2009-09-30 | 2009-09-17 |  |  |  |  | 27/4/09: John Gibbs likes this site. He will advise on level of consultation before the end of this week. 12/5/09: Consultation is letter drop with feedback to Council. Letters gone and responses close by 21st May. Feedback to be seen before understanding next steps. Lease has goen to Radio NZ, rental level being discussed. 18/5/09: Radio NZ are ok to go. Land sub-leased to DOC and going to be sub-leased to Wellington Regional Council. 26/5/09: All on track for acquisition. RMA lodged. 2/6/09: Waiting Radio NZ for confirmation from DOC to progress lease. 8/6/09: Various parties involved in sub-leasing arrangement so the site acquisition part may take a little longer to complete. 15/6/09: Negotiations approaching a close. 22/6/09: As of late last week, we now need a boundary survey and detailed site plan to add to the DoC lease. Acquisition time extended. 9/7/09: Survey plan out today. DoC approval required to release of land. 14/7/09: PRIORITY SITE: Survey plans provided. Clause in lease ref power to be amended but will complete as per timescales. 21/7/09: Survey plan has to be produced to ensure that Land Information NZ (LINZ) have recorded the division of land. HG are producing drawings and lodging. Team to determine if the lease is dependant on the registering of the drawing or the submission. 28/7/09: Legal docs executed by NZC, with Radio NZ for execution. Site acquisition time frames are as reported. 4/8/09: Meeting this week with landlord. PMcK to attend. 18/8/09: In build. |  | 2009-09-30 | [5 empty] | 2009-04-21 | [11 empty] | FALSE |  | 2664903 | 6010480 | Radio New Zealand Shelley Street Titahi Bay |  |  | CELLSITE |  |  | 2015-12-02 |  |  |  |  | 2009-08-19 | 2009-08-19 | [8 empty] | 2009-04-22
0 | WLG | 1556 | WLG-044-003 |  | WLG-044-003-B | Paremata | Porirua City |  | TIER_1_ALL | ACTIVE | RSR | Ab | P4B | green | [5 empty] | -41.1063 | 174.8673 | [13 empty] | 2008-06-30 |  |  |  | 2008-06-27 | 6 |  |  |  |  | 2009-02-19 | 2009-02-17 | 2 | 2009-10-22 | 2009-11-03 |  |  |  | 2009-11-13 |  |  | 2009-11-13 | 2009-11-13 |  | 2008-11-20 |  | 2008-12-22 | 3 |  | 2008-12-22 | 2009-07-31 | 2009-05-06 |  |  |  |  | 2010-01-22 | 2010-01-20 | 2010-02-16 | 2010-02-03 |  | 2010-02-19 | 2010-02-04 | [8 empty] | 2010-03-02 | 2010-03-05 | 2010-03-02 |  |  |  |  | 9/2/09: Update VM. Ontrack approval to scheme approved. RMA lodged. 3/3/09: Power quote required before site acquisition can continue. 9/3/09: Power route and costs to be identified as part of site acquisition. Initial quote and route not acceptable. Revised quote being worked on. RMA dependant on OnTrack and Transit approvals. 30/3/09: Awaiting power quote to present to Transit to establish route. To be sent today. 16/4/09: Agreement is complete but still need Ontrack approval to RMA before we can complete the RMA. Details of this have been sent. Transit agreement is in place. Needs to be RF tested. 20/4/09: Power route still goes through Ontrack land. Commission boundary survey to determine if we can trench through the soft. 27/4/09: Boundary survey required. Due to get feedback. 6/5/09: Boundary survey results to Victoria on Thursday. 12/5/09: Boundary survey completed. Details available tomorrow but then need to go back to power company for revised route. Vic - we have taken power over/through Ontrack land in the past without a problem providingwe meet their trenching specifications. Please explore whether it is possible to repeat this whilst we continue to investigate an alternative route. 18/5/09: Sent info to Ontrack. VM chasing approval for resource consent. 26/5/09: RL to arrange site meeting. VM to review the drawings. 2/6/09: Drawings complete and will be sent to VM today. 8/6/09: OnTrack receieved Deed of Grant last Thursday. Up to 6 weeks for approval of trenching but should be in before. RMA through 2 weeks after lease. LPR site so hoping for a could of weeks fine weather to get this site in in July. 15/6/09: Forecasts still good for site acquisition. 22/6/09: No approval to design from Rail Aithority. VM is chasing. 29/6/09: Priority site for regional RF to cover SH1. 14/7/09: Waiting for one more approval within Ontrack. Expected before the end of the week. 21/7/09: Chase VM for update. 28/7/09: VM has chased Jess over legal review. 4/8/09: Service search to do. 11/8/09: Services check to go to ontrack. 18/8/09: Discover the owner of the car park and do further utilities mark outs. 1/9/09: Doc to Jess Sage. 8/9/09: BB to check the RMA consent to determine whether we can use the only grey site. Proposing site type Ab. All site acquisition dates in order. 15/9/09: Deed of grant signed by 2degrees and now with Ontrack for affected party form. 22/9/09: Crystal at ontrack to complete affected party form plus lease. 29/9/09: Ontrack still haven't responded. Crystal at Ontrack has no idea of timescales. 6/10/09: All on course for dates specified. 13/10/09: All site acq on course. Ontrack notification of build required. 20/10/09: Still with Ontrack to sign. 27/10/09: Dates all good. 3/11/09: Stuart Smith processing planner. 10/11/09: TP is processing. Pre-build talk to OnTrack 2 weeks notice - Joe to check VM's email. 17/11/09: DO NOT BUILD. 1/12/09: Build ASAP. Build will be largely complete in december 09. Very long power run which will not be compelte until early 2010. 15/12/09: Unable to get MWH approval to build this year. Jan start and finish. |  | 2010-03-05 |  |  |  |  | 2009-05-22 | 2009-05-06 | [11 empty] | FALSE |  | 2666815 | 6009473 | Lightpole replacement in Paramata station Beside railway line at parking exit Paramata Wellington |  |  | CELLSITE |  |  | 2015-12-02 |  |  |  |  | 2009-12-04 | 2009-12-04 | [8 empty] | 2008-07-01
0 | WLG | 1557 | WLG-044-004 |  | WLG-044-004-D | Whitby North | Porirua City |  | TIER_1_ALL | ACTIVE | COLO | Ab | COLO | flax green |  | COLO | 12.8 | 12.8 |  | -41.1163 | 174.8831 | [13 empty] | 2009-03-15 |  |  |  | 2009-04-28 | 2 | 2009-07-30 | 2009-09-29 |  |  | 2009-10-30 | 2009-10-29 | 1 | 2009-10-30 | 2009-10-29 |  | 2009-08-05 |  | 2009-09-09 |  |  | 2009-10-30 | 2009-10-29 | 2009-09-03 | 2009-09-08 | 2009-10-02 | 2009-10-01 | 2 | 2 | 2009-10-02 | 2009-10-02 | [6 empty] | 2009-11-20 | 2009-12-20 | 2009-12-01 |  | 2009-12-21 | 2009-12-10 | [8 empty] | 2010-01-15 | 2010-01-15 | 2010-01-15 |  |  |  |  | 3/3/09: Still need confirmation of roles and responsibilities for co-site. 9/3/09: Peter McKeefry to complete co-lo form. RMA waiting for feedback as to whether co-lo will go notified. Jason Britten working with Vodafone to confirm who's doing what. Forecasts indicative only as confirmation of roles and resonsibilities between ourselves and Vodafone required. 16/3/09: Meeting with Porirua City Council this week to review whether they will approve the additional height required for the co-lo on a non-notified basis.30/3/09: Regional team to complete application and return to JB. Application on N:/ drive. JM to speak to SS. 16/4/09: App submitted? 20/4/09: Update from Jason needed. Design required from VF. 27/4/09: NZC completed Data Pack and drawings to go to Jason Britten today.5/5/09: Jm to update with JB and BR. 12/5/09: Answered VF questions. Expecting response in next 5-7 days. COWs? 18/5/09: JM spoke with JB yesterday. Waiting for VF feedback. 26/5/09: Update from JB. 2/6/09: Timelines from JB outstanding. Vodafone have replied. JM to talk to JB. 8/6/09: In principle solution agreed with Vodafone. Now have consent to use the same design consultants so we can actually devise a feasible proposal and know that wind loadings, structural cals etc have been taken into account. 15/6/09: Drawings from HG being chased. 22/6/09: Waiting design drawings from HG. 29/6/09: PDs still in production. Structural cals due back this week with drawings issued before the end of the week. 9/7/09: Drawings received. Drawings being circulated for internal approval. Drawings going through VF approval once we've approved but JM needs to confirm this process with Jason Britten. RMA is by no means guaranteed and the progress of the site will be determined by community response. 14/7/09: Waiting feedback from Voda on designs. All approved with NZCL. 21/7/09: RMA consultation letters dropped off for both the co-lo and an independant structure. Response time closes end of July. LH to investigate more closely raising one of the sectors at Baxters. 28/7/09: RMA have posted out the notification letters. Responses due 31st July. Available for lodging thereafter if consultation goes well. Council happy with lease. Team to determine if independant pole works. Independant structure probably won't work. John Gibbs feedback for next meeting. LH to predict from Baxters. RC to verify dish heights. JM to review dates. 4/8/09: Residents submissions back for RMA. JM to mail Barbara to chase if approval to drawings change Site Acquisition dates. Who's building? Vodafone costs? CDs done. 11/8/09: VF need to have a copy of the project plan with CDs. RC lodged but may go notified. copy to go to Barbara Richardson. Lease with Council for cabs and Voda for tower equipment. CoW location to be agreed. 18/8/09: Waiting for RMA. Going to push to get the lease started. 25/8/09: Lease agreed by PMcK. Lease with Jess before being executed this week by us. and sent to Landlord waiting for RMA. BR to confirm progress with Vodafone. 1/9/09: Jess adding clauses to lease. RMA dates good then can progress the lease. PMcK/BB to look at COW location. VF lease with BR. 8/9/09: Site meeting with contractor tomorrow to review Vodafone site and colo requirements for the submission of the Project Plan. RMA is complete but S127 submitted due to cabinets being relocated. SS to ensure the HG redesign for site type Ab. Separate lease entered into for cabinets. Lease signed in Auckland. New drawings to be issued asap. Lease drawing does not show a future BTS location so additional landtake required. Dates here are for cabinet locations. Auckland/Barbara is doing the Vodafone lease. Site type Ab. 15/9/09: Project PLan complete for Vodafone and is ready for issue with drawings 16/9/09. Lease for cabs is with Porirua City Council. Lease sent to Council on Friday. S127 to lodge for cab change. | VNZ | 2010-01-15 | [17 empty] | FALSE |  | 2668119 | 6008340 | 116A Gloaming Hill, Onepoto, Porirua |  |  | CELLSITE | [7 empty] | 2009-11-20 | 2009-11-11 | [8 empty] | 2009-04-27
0 | WLG | 1558 | WLG-044-005 |  | WLG-044-005-B | Judgeford | Porirua City |  | TIER_1_ALL | ACTIVE | GF | A | P1 | grey |  |  | 8.8 | 8.8 |  | -41.1238 | 174.957 |  |  |  |  | Microwave, Microwave | WLG-044-001-B, WLG-044-001-B | [5 empty] | 2008-09-02, 2008-09-02 | [5 empty] | 2008-09-04 | 3 | 2009-03-10 |  |  |  | 2008-10-31 | 2008-09-23 | 1 | 2008-10-31 | 2008-09-23 |  |  |  | 2008-12-24 |  |  | 2008-12-24 | 2010-08-11 |  | 2008-11-12 |  | 2009-01-09 | 2 | 1 | 2009-01-14 | 2009-01-14 | 2009-03-23 |  |  |  |  | 2009-03-02 | 2009-02-24 | 2009-04-15 | 2009-04-08 |  | 2009-04-24 | 2009-04-22 | [8 empty] | 2009-06-30 | 2009-06-30 | 2009-06-30 |  |  |  |  | 9/2/09: TSS w/c 9/2/09 25/2/09: In build. 19/3/09: Approval from RF to build. 20/4/09: Power going on tomorrow. |  | 2009-06-30 |  |  |  |  | 2009-03-20 | 2009-03-23 | [11 empty] | FALSE |  | 2674303 | 6007364 | Paremata Haywards Rd State Highway 58 Wellington |  |  | CELLSITE | [8 empty] | 2009-01-16 | [8 empty] | 2008-08-12
0 | WLG | 1559 | WLG-044-006 |  | WLG-044-006-A | Whitby | Porirua City |  | TIER_1_ALL | ACTIVE | GF | A | P1 | grey |  |  | 10.8 | 10.8 |  | -41.1152 | 174.9081 |  |  |  |  | Microwave, Leased Line | WLG-044-001-B, WLG-047-071-A | [11 empty] | 2008-01-29 | 4 |  | 2008-10-23 |  |  | 2008-04-28 | 2008-04-28 | 3 | 2008-04-28 | 2008-04-28 |  |  |  | 2009-01-12 |  |  | 2009-01-12 | 2009-01-12 |  | 2008-04-10 |  | 2008-07-17 | 3 | 4 | 2009-02-09 | 2009-02-09 | 2009-03-12 |  |  |  |  | 2009-02-16 | 2009-02-17 | 2009-03-30 | 2009-03-30 |  | 2009-03-31 | 2009-03-31 | [8 empty] | 2009-03-31 | 2009-03-31 | 2009-03-31 |  |  |  |  | 9/2/09: TSS'd CDs to issue w/c 9/2/09 9/3/09: In build. 19/3/09: Approval from RF to build. |  | 2009-03-31 |  |  |  |  | 2009-03-13 | 2009-03-12 | [11 empty] | FALSE |  | 2670216 | 6008417 | Entrance from Endeavour Dr, Hill Top, Porirua, Wellington |  |  | CELLSITE | [8 empty] | 2009-02-03 | [8 empty] | 2007-11-01
0 | WLG | 1560 | WLG-044-007 |  | WLG-044-007-B | Ascot Park | Porirua City |  | TIER_1_ALL | ACTIVE | GF | A | NOPOLE | grey |  | COSITE | 12.5 | 12.5 |  | -41.1268 | 174.862 |  |  |  |  | Microwave, Microwave | WLG-044-011-C, WLG-044-011-C | [5 empty] | 2008-11-12, 2008-11-12 | [5 empty] | 2007-05-01 | 1 | 2007-05-01 | 2007-05-01 |  |  | 2009-02-15 | 2009-02-04 |  | 2009-02-15 | 2009-02-04 |  | 2007-05-01 |  | 2008-12-18 |  |  | 2008-12-18 | 2008-12-18 |  | 2007-05-01 |  | 2010-02-26 |  |  | 2008-11-18 | [6 empty] | 2009-03-10 | 2009-03-04 | 2009-04-28 | 2009-04-24 |  | 2009-06-07 | 2009-05-08 | [8 empty] | 2009-06-23 | 2009-06-30 | 2009-06-23 |  |  |  |  | 9/2/09: TSS'd and in build. 3/3/09: Turn key by Kordia. 9/3/09: In build. 16/4/09: All ok for completion this month. Power is prdered with power on by month end. Mounts and TI work next week. 20/4/09: Power supplytbc. Still on course for April completion. |  | 2009-06-30 | [17 empty] | FALSE |  | 2666320 | 6007209 | 32a Kahurangi Heights, Ascot Park, Porirua Wellington |  |  | CELLSITE |  |  | 2015-12-02 |  |  |  |  | 2009-02-19 | 2009-02-19 | [8 empty] | 2008-09-04
0 | WLG | 1561 | WLG-044-008 |  | WLG-044-008-C | Waitangirua | Porirua City |  | TIER_1_ALL | ACTIVE | RSR | A | P4F | green |  |  | 11 | 11 |  | -41.1293 | 174.8797 | [13 empty] | 2008-12-15 |  |  |  | 2009-02-09 | 3 | 2009-03-15 | 2009-05-07 |  |  | 2009-05-12 | 2009-05-13 | 1 | 2009-05-12 | 2009-05-13 |  | 2009-05-04 |  | 2009-06-15 |  |  | 2009-06-15 | 2009-06-03 | 2009-05-20 | 2009-05-27 | 2009-06-29 | 2009-06-29 | 1 | 3 | 2009-06-29 | 2009-06-29 | [5 empty] | 2009-10-04 | 2009-10-01 | 2009-10-30 | 2009-10-21 |  | 2009-10-30 | 2009-10-21 | [8 empty] | 2009-10-23 | 2009-11-05 | 2009-10-23 |  |  |  |  | 9/2/09: Update VM. RMA dependant on local council improvement project. NZ Comms work to be done in conjunction, currently scheduled for July. 9/3/09: Lease with council and should be complete in March. RMA team to do consultation in conjunction with council. Some details still to be established so that our scheme progresses with the council's build. VM to confirm and discuss with SS and CE. 16/3/09: Meeting with Council and SS to confirm design with consultation scheduled for week 1 in April. 30/3/09: Await feedback from councils public consultation this evening. RMA cannot be lodged until we have been present at a consultation ourselves. 6/4/09: Public consultation went well. Council and our teams to meet next week to ascertain timescales and look at our consultation plan. RMA submitted upon upon Council confirmation that we have met our public consultation commitments. 16/4/09: Agreement is with Council. Meeting to be held today to determine/agree public consultation for both RMA and lease. RMA is dependant on elase completion. Subject to co-site approval with same land owner. 20/4/09: BB to meet the mall owner to establish and agree his requirements. Public consultation complete on 27/4/09. Lease complete soon after. JM to check pole status. 27/4/09:Consultation letter out last week. Feedback due this week. Lease dependant on RC. 5/5/09: Consultation all signed off. Lease progressing. 12/5/09: Lease complete. RMA awaited. 18/5/09: Forecasts still good. With Council. 26/5/09: RMA on track. 2/6/09: RC this week. 15/6/09: Pole being competitively tendered. Modifying a 4F. Need to know pole availability before forecasting build activities. 22/6/09: Waiting pole before scheduling. POle going to alternative supplier on instruction from DdV. 29/6/09: Waiting pole. Just ordered. Build? Target group? 14/7/09: Not a priority site. LANDBANKED. 21/7/09: Acquired. 28/7/09: Await pole availability. Ornate embellishments required. Design TBC. Town planning and Mana Forbes sorting. JM spoke to Mana - embellishments are only a 'nice to have'. 18/8/09: In build but site location to be confirmed. 1/9/09: Start build? JM to follow up. 8/9/09: Only site type A green allocated to this site. Still being messed around by Council. JB is aware of issues. Wanting outstanding Council problems resolved by the end of this week. 15/9/09: Council happy with RF, now have question over luminaire and the length of the arms. TSS'd for the 2nd time. 22/9/09: Meeting with council to review the pole today. Pre-start works underway. 6/10/09: In build. 20/10/09: In build. LL connected. |  | 2009-11-05 |  |  |  |  | 2009-08-24 | [12 empty] | FALSE |  | 2667804 | 6006897 | Light stand within carpark of the Waitangirua Mall. |  |  | CELLSITE | [7 empty] | 2009-09-21 | 2009-09-24 | [8 empty] | 2009-01-27
0 | WLG | 1562 | WLG-044-009 |  | WLG-044-009-A | Porirua City | Porirua City |  | TIER_1_ALL | ACTIVE | RT | B | NOPOLE | grey |  |  | 36.9 | 36.9 |  | -41.1365 | 174.8406 |  |  |  |  | Leased Line, Microwave | WLG-047-071-A, WLG-044-002-D | [5 empty] | 2008-08-12 | [5 empty] | 2008-03-12 | 4 |  | 2008-08-19 |  |  | 2008-06-15 | 2008-05-30 | 2 | 2008-06-15 | 2008-05-30 |  |  |  | 2008-06-04 |  |  | 2008-09-04 | 2008-09-04 |  | 2008-04-14 |  | 2008-07-11 | 2 | 4 | 2008-08-22 | 2008-08-22 | [6 empty] | 2008-10-14 | 2008-11-21 | 2008-11-21 |  | 2008-11-28 | 2008-12-18 | [8 empty] | 2009-03-05 | 2009-03-07 | 2009-03-05 |  |  |  |  | 25/2/09: Awaiting leased line. NOTE - BBU 3806 SWAPPED OUT WITH NEW 3900 UNIT 17/10/2012. |  | 2009-03-07 | [17 empty] | FALSE |  | 2664499 | 6006171 | Guardian Healthcare 14 Hartham Porirua Wellington |  |  | CELLSITE |  |  | 2015-12-02 | [5 empty] | 2008-10-14 | [8 empty] | 2007-10-26
0 | WLG | 1563 | WLG-044-010 |  | WLG-044-010-B | Cannons Creek | Porirua City |  | TIER_1_ALL | ACTIVE | RT | A | NOPOLE | green |  |  | 11.2 | 11.2 |  | -41.1423 | 174.8661 |  |  |  |  | Leased Line, Microwave, Microwave | WLG-047-071-A, WLG-044-012-B, WLG-044-012-B | [5 empty] | 2008-07-31, 2008-07-31 | [5 empty] | 2007-11-30 | 2 | 2009-03-20 | 2009-03-18 |  |  | 2008-04-24 | 2008-04-24 | 1 | 2008-04-24 | 2008-04-24 |  |  |  | 2008-05-09 |  |  | 2008-05-09 | 2008-05-09 |  | 2008-02-12 |  | 2008-06-10 | 1 | 1 | 2008-06-10 | 2008-06-10 | [6 empty] | 2008-07-07 | 2008-08-19 | 2008-08-19 |  | 2008-09-01 | 2008-08-26 | [8 empty] | 2008-12-16 | 2008-12-31 | 2008-12-16 |  |  |  |  | None |  | 2008-12-31 | [17 empty] | FALSE |  | 2666631 | 6005481 | Freedom Church 1 Tavern Lane Cannons Creek Wellington |  |  | CELLSITE | [8 empty] | 2008-06-11 | [8 empty] | 2007-08-20
0 | WLG | 1564 | WLG-044-011 |  | WLG-044-011-C | Linden | Porirua City |  | TIER_1_ALL | ACTIVE | GF | A | P1 | grey |  |  | 18.8 | 18.8 |  | -41.1517 | 174.8285 |  |  |  |  | Microwave | WLG-044-012-B | [5 empty] | 2008-08-20 | [5 empty] | 2008-08-27 | 2 |  | 2009-03-12 |  |  | 2008-08-29 | 2008-08-29 | 1 | 2009-04-30 |  |  |  |  | 2008-12-24 |  |  | 2008-12-24 | 2008-12-24 |  | 2008-09-16 |  | 2009-02-02 | 2 | 2 | 2009-03-20 | 2009-04-08 | 2009-01-30 |  |  |  |  | 2009-03-31 | 2009-04-01 | 2009-04-28 | 2009-04-20 |  | 2009-05-08 | 2009-04-20 | [8 empty] | 2009-06-20 | 2009-06-30 | 2009-06-20 |  |  |  |  | 25/2/09: Problem with location of wayleaves. 9/3/09: In build. revised CDs awaited. PD sent for approval today. 17/3/09: Lease to be approved on the basis of of the revised PDs/CDs now to be issued. Build in March/April Completion. No impact on RMA. Property issue re: rental payments being worked through by Legal. 30/3/09: Build can continue. Both LL and tenant have confirmed that this is ok. 16/4/09: Lift delayed and land lord request. Now 23rd April. All on course for the end of April civils completion. Lease to complete after agreement between landlord and tenant has been reached. |  | 2009-06-30 | [5 empty] | 2009-01-30 | [11 empty] | FALSE |  | 2663450 | 6004508 | 5 Kapuni Grv, Porirua, Wellington |  |  | CELLSITE | [7 empty] | 2009-03-24 | 2009-03-25 | [8 empty] | 2008-08-12
0 | WLG | 1565 | WLG-044-012 |  | WLG-044-012-B | Colonial Knob | Porirua City |  | TIER_1_ALL | ACTIVE | GF | TX | LATTICE |  |  |  | 20 | 20 |  | -41.1474 | 174.809 |  |  |  |  | Microwave | WLG-047-074-B | [5 empty] | 2008-08-21 | [5 empty] | 2008-09-10 | 6 | 2009-03-11 |  |  |  | 2008-09-30 | 2008-09-08 | 3 | 2008-09-30 | 2008-09-08 |  |  |  | 2009-03-13 |  |  | 2009-03-13 | 2009-03-03 |  | 2008-11-27 |  | 2009-02-09 | 1 | 4 | 2009-02-09 | 2009-02-09 | [5 empty] | 2009-03-19 | 2009-03-16 | 2009-04-28 | 2009-04-28 |  | 2009-06-03 | 2009-06-04 | [8 empty] | 2009-06-04 | 2009-06-05 | 2009-06-04 |  |  |  |  | 9/2/09: CDs issue w/c 9/2/09. RMA getting confirmation about painting. TSS this week. 25/2/09: Awaiting co-site approval. S127. 9/3/09: In build. 16/4/09: All good for April completion. 20/4/09: All still on course for April. 12/5/09: STM4 link to Kaukau being prioritised and installed asap. |  | 2009-06-05 | [17 empty] | FALSE |  | 2661827 | 6005016 | Colonial Knob (Near Telecom) Porirua Wellington |  |  | TXSITE | [7 empty] | 2009-03-07 | 2009-03-11 | [8 empty] | 2008-08-06
0 | WLG | 1566 | WLG-044-013 |  | WLG-044-013-A | Pukerua Bay | Porirua City |  | TIER_1_ALL | ACTIVE | GF | A | P3 | grey |  |  | 8.8 | 8.8 |  | -41.0372 | 174.8777 |  |  |  |  | Microwave, Microwave | WLG-044-012-B, WLG-044-012-B | [5 empty] | 2008-09-04, 2008-09-04 | [5 empty] | 2008-09-12 | 4 |  | 2011-04-05 |  |  | 2008-11-05 | 2008-10-29 | 1 | 2009-04-10 | 2009-04-15 |  |  |  | 2009-01-09 |  |  | 2009-03-30 | 2009-03-10 |  | 2008-11-03 |  | 2008-12-19 | 2 | 3 | 2008-12-19 | 2009-04-28 | 2009-03-20 |  |  |  |  | 2009-04-20 | 2009-04-20 | 2009-05-10 | 2009-05-06 |  | 2009-06-02 | 2009-05-28 | [8 empty] | 2009-06-30 | 2009-06-30 | 2009-06-30 |  |  |  |  | 9/2/09: Lorraine to review with Julian. Co-lo with Telecom or going alone with our own option in new location outside of Telecom leased area. DK to speak with Kirsty/Matt Buchanan. Another caravan required w/c 09/02/09. PMcK to arrange access. TX LOS at same time. 25/2/09: Confirmation from Telecom that we can use their easement area is required. 3/3/09: Possibly revert to original scheme if we can get written approval from Telecom. 16/3/09: Await TNZ approval to co-site. 9/3/09: Revised drawing to accompany co-site request done today. Preferred option to go with original design. Copy of co-site approval to go to landlord. RMA complete for orginal option. Chase through co-site once lodged. 17/3/09: Only awaiting Telecom approval. JM to chase if we can build. 30/3/09: Awaiting co-site approval only. JM to speak to JC and DdV and get approval. Team talk approval outstanding. JM to chase. TSS and do pre-build work ASAP. 16/4/09: Property issues to be resolved today/tomorrow. PLus power issues to be resolved. Looking uncertain for April. 20/4/09: Site works started. Aiming for April completion. 12/5/09: No 1.2m dish available for link to Colonial. |  | 2009-06-30 |  |  |  |  | 2009-03-13 | 2009-03-20 | [11 empty] | FALSE |  | 2667854 | 6017130 | On hill behind Kapekape Plc, 153 Rawhiti Road, Pukerua Bay |  |  | CELLSITE | [7 empty] | 2009-04-15 | 2009-04-15 | [8 empty] | 2008-08-14
0 | WLG | 1567 | WLG-044-014 | Papakowhai | WLG-044-014-A | Papakowhai Rd VF Colo | Porirua City | 7 | TIER_1_INFILL | ACTIVE | COLO | DU | COLO |  | INLINE | COLO | 15.5 | 15.5 | 1 | -41.1147 | 174.8602 |  |  |  |  | Microwave | WLG-044-001-B | FALSE | FALSE |  |  | FALSE |  | 2011-07-29 | 2011-07-11 | 2011-07-18 | 2011-07-15 | 2011-08-03 | 2011-08-09 | 1 | 2011-08-03 | 2011-08-09 | 2012-02-03 | 2012-02-03 | 2012-02-17 | 2012-02-15 | 1 | 2012-02-17 | 2012-02-20 | DISCRETIONARY_FULL | 2011-11-04 | 2011-11-04 | 2011-12-16 | 2011-11-24 | 1 |  | 2011-11-24 |  |  |  | 2012-04-16 | 1 |  | 2012-04-02 | 2012-04-16 | [5 empty] | 2012-04-18 | 2012-04-18 | 2012-05-18 | 2012-05-18 | 2012-05-08 | 2012-05-15 | 2012-05-12 | [8 empty] | 2012-05-16 | 2012-05-31 | 2012-05-15 | 2012-06-06 | 2012-06-06 | 2012-09-04 | 2012-10-02 | 12.06.2014 : "D" configuration build. (APM, Battery, & 2 x RFC) using version "B" cabinets. Thus making it a "DU" Site. (As per Ron Bush/blr) | VNZ | 2012-05-16 | [6 empty] | 2012-05-10 | 2012-05-10 | 2012-05-23 | 2012-05-15 | [6 empty] | 2012-05-08 | FALSE |  | 2666200 | 6008552 | Road Reserve between SH6 and Papakowhai Rd |  | Dealing with the Planning Manager Adrian Rammage. and also John Gibbs for consultation. - 12/07/2011 | CELLSITE | [15 empty] | 2012-05-23 | 2012-05-23
0 | WLG | 1568 | WLG-044-015 | Chorus PRO Exchange Colo | WLG-044-015-A | Porirua Hub | Porirua City |  | TIER_6 | ACTIVE | COLO | TX | COLO |  |  | COLO | [100 empty] | Chorus PRO Exchange 12 Mungavin Avenue, Porirua East, Porirua 5024 |  |  | TXSITE | WIPACTIVE
0 | WLG | 1569 | WLG-045-001 |  | WLG-045-001-A | Te Marua | Upper Hutt City |  | TIER_1_ALL | ACTIVE | GF | A | P3 | grey |  |  | 13.9 | 13.9 |  | -41.0889 | 175.1088 |  |  |  |  | Microwave, Microwave | WLG-045-002-A, WLG-045-002-A | [5 empty] | 2007-11-20, 2008-06-09 | [5 empty] | 2007-12-14 | 6 |  | 2009-02-11 |  |  | 2008-09-15 | 2008-06-12 | 5 | 2008-09-15 | 2008-06-12 |  | 2009-03-06 |  | 2009-04-10 |  |  | 2009-04-10 | 2009-04-07 |  | 2008-07-16 |  | 2008-11-28 | 2 | 6 | 2009-02-13 | 2009-02-13 | 2009-03-17 |  |  |  |  | 2009-03-02 | 2009-03-02 | 2009-03-31 | 2009-03-26 |  | 2009-04-20 | 2009-04-29 | [8 empty] | 2009-05-30 | 2009-06-05 | 2009-05-30 |  |  |  |  | 9/2/09: Landlord to be provided updated co-siting approval. 25/2/09: Scenic reserve designation to be confirmed. RMA problem. Telecom to confirm use of power. In build. 3/3/09: RMA problems being worked through. 9/3/09: In build. RMA issue re: pole width. Works continue with TP team approval. 18/3/09: RF have given approval to build. |  | 2009-06-05 |  |  |  |  | 2009-03-02 | 2009-03-17 | [11 empty] | FALSE |  | 2687137 | 6010943 | Hilltop at end of 81 Gillespies Road Co-site with TNZ Wellington |  |  | CELLSITE | [8 empty] | 2008-12-08 | [8 empty] | 2007-10-04
0 | WLG | 1570 | WLG-045-002 |  | WLG-045-002-A | Birchville | Upper Hutt City |  | TIER_1_ALL | ACTIVE | GF | A | P1 | grey |  |  | 13.8 | 13.8 |  | -41.0985 | 175.099 | [17 empty] | 2008-03-05 | 4 | 2009-03-06 | 2009-03-04 |  |  | 2009-02-28 | 2008-11-26 | 1 | 2009-02-28 | 2008-11-26 |  | 2009-03-06 |  | 2009-07-15 |  |  | 2009-07-15 | 2009-07-14 |  | 2008-04-14 |  | 2008-08-13 | 2 | 1 | 2008-12-18 | 2008-12-18 | 2009-02-16 | [5 empty] | 2008-12-10 | 2009-03-14 | 2009-03-13 |  | 2009-03-17 | 2009-03-13 | [8 empty] | 2009-03-30 | 2009-03-27 | 2009-03-30 |  |  |  |  | 25/02/09: Scenic reserve designation tbc. RMA problem being worked through. Site is pre-built, awaiting pole stand and confirmation of VF co-site approval. 3/3/09: RMA issues virtually overcome. 9/3/09: Only pole to lift later this month. 18/3/09:RF approval to build. |  | 2009-03-27 | [5 empty] | 2009-02-16 | [11 empty] | FALSE |  | 2686293 | 6009906 | Emerald Hill Park Wellington Gillies Group Limited |  |  | CELLSITE | [8 empty] | 2008-12-08 | [8 empty] | 2008-02-07
0 | WLG | 1571 | WLG-045-003 |  | WLG-045-003-A | Maoribank | Upper Hutt City |  | TIER_1_ALL | ACTIVE | GF | A | P2 | grey |  |  | 18.8 | 18.8 |  | -41.1098 | 175.0971 |  |  |  |  | Microwave, Microwave | WLG-045-002-A, WLG-045-002-A | [5 empty] | 2007-11-20, 2007-11-20 | [5 empty] | 2008-05-09 | 2 |  | 2008-08-25 |  |  | 2008-08-25 | 2008-08-19 | 1 | 2008-08-25 | 2008-08-19 |  |  |  | 2008-07-01 |  |  | 2008-10-10 | 2008-10-10 |  | 2008-06-12 |  | 2008-08-27 | 1 | 2 | 2008-08-27 | 2008-08-27 | [6 empty] | 2008-09-19 | 2008-11-28 | 2008-10-31 |  | 2008-12-15 | 2008-12-18 | [8 empty] | 2009-03-05 | 2009-03-15 | 2009-03-05 |  |  |  |  | 25/2/09: Site with temporary link to Whakatiki st - dependant on CIT. |  | 2009-03-15 | [17 empty] | FALSE |  | 2686104 | 6008646 | Rimutaka Sports Bar Wellington |  |  | CELLSITE | [8 empty] | 2008-09-01 | [8 empty] | 2007-10-31
0 | WLG | 1572 | WLG-045-004 |  | WLG-045-004-D | Elderslea North | Upper Hutt City |  | TIER_1_ALL | ACTIVE | GF | A | P2 | grey |  |  | 18.8 | 18.8 |  | -41.1179 | 175.0484 | [17 empty] | 2007-12-07 | 2 |  | 2008-04-16 |  |  | 2008-08-15 | 2008-08-06 | 1 | 2008-08-15 | 2008-08-06 |  |  |  | 2008-02-13 |  |  | 2008-02-13 | 2008-02-13 |  | 2008-02-12 |  | 2008-04-21 | 1 | 2 | 2008-04-21 | 2008-04-21 | [6 empty] | 2008-09-22 | 2008-10-10 | 2008-10-09 |  | 2008-10-20 | 2008-10-20 | [8 empty] | 2009-03-05 | 2009-03-15 | 2009-03-05 |  |  |  |  | 25/2/09: Dependant on CIT. |  | 2009-03-15 | [17 empty] | FALSE |  | 2681990 | 6007847 | 122C Whakatiki Street DM and JM Investments Trentham |  |  | CELLSITE | [8 empty] | 2008-08-27 | [8 empty] | 2007-11-06
0 | WLG | 1573 | WLG-045-005 |  | WLG-045-005-B | Totara Park | Upper Hutt City |  | TIER_1_ALL | ACTIVE | RSR | A | P4B | green |  |  | 13.2 | 13.2 |  | -41.1154 | 175.0811 |  |  |  |  | Microwave, Microwave | WLG-045-003-A, WLG-045-003-A | [5 empty] | 2008-09-02, 2008-09-02 | [5 empty] | 2008-10-22 | 1 |  | 2008-10-22 |  |  | 2009-03-06 | 2009-02-26 | 1 | 2009-03-30 | 2009-03-30 |  |  |  | 2008-11-17 |  |  | 2008-11-17 | 2008-11-17 |  | 2009-01-26 |  | 2009-02-11 | 1 | 1 | 2009-02-11 | 2009-02-11 | [5 empty] | 2009-05-05 | 2009-05-04 | 2009-05-22 | 2009-05-14 |  | 2009-06-05 | 2009-05-15 | [8 empty] | 2009-07-31 | 2009-07-29 | 2009-07-31 |  |  |  |  | 9/2/09: Update from VM. RMA complete. 9/3/09: VM to confirm if notice of prior approval is required. 16/3/09: Await notice of prior approval only. 18/3/09: Have been advised that ETA for pole is 8/5/09 30/3/09: Claim 'All site acq complete' 16/4/09: Checking for NZTA approval. 27/4/09: May need a Section 51. Need to notify Rueben with a minimum of 10 days notice. S51 need written permission before undertaking. 12/5/09: Build well progressed with pole stand this week, dependant on weather. 18/5/09: Power still to go on. |  | 2009-07-29 |  |  |  |  | 2009-04-22 | [12 empty] | FALSE |  | 2684745 | 6008061 | LPR on the Cnr of River Rd and Totara Lark Rd Upper Hutt Wellington |  |  | CELLSITE | [7 empty] | 2009-04-27 | 2009-04-14 | [8 empty] | 2008-09-19
0 | WLG | 1574 | WLG-045-006 |  | WLG-045-006-A | Upper Hutt | Upper Hutt City |  | TIER_1_ALL | ACTIVE | RT | B | NOPOLE | grey |  |  | 32.5 | 32.5 |  | -41.1245 | 175.0693 |  |  |  |  | Microwave, Microwave | WLG-045-012-A, WLG-045-012-A | [5 empty] | 2008-07-01, 2008-07-01 |  | 2009-03-10 |  |  |  | 2008-01-29 | 4 | 2009-05-07 | 2009-07-21 |  |  | 2009-05-30 | 2009-05-29 | 3 | 2009-05-30 | 2009-05-30 |  | 2009-05-26 |  | 2009-06-26 |  |  | 2009-07-07 | 2009-07-02 | 2009-05-26 | 2009-05-27 | 2009-06-30 | 2009-07-08 | 2 | 4 | 2009-06-30 | 2009-09-01 | [5 empty] | 2009-08-10 | 2009-08-10 | 2009-09-14 | 2009-09-11 |  | 2009-09-20 | 2009-09-15 | [8 empty] | 2009-09-22 | 2009-09-25 | 2009-09-22 |  |  |  |  | 9/2/09: DEAD. Caravan required for new site location at the water tower. Caravan w/c 9/2/09 9/3/09: Cannot take over Woosh. Landlord cannot break leave with Woosh. CE has organised Landlord's town planner to discuss possible solutions. Site meeting needed to review. Woosh programme etc unknown. Co-lo request to be submitted to share Woosh pole. 16/3/09: Need to meet landlords town planner on site to investigate all possible options. 30/3/09: Drawings being worked on to avoid the Woosh leased area. 6/4/09: Design work being done by Harrison Grierson. 16/4/09: Still awaiting drawings. Questionable need for this site fom technical perspective. 20/4/09: LH to visit with JC today. PDs being done by HG. Brendan still awaits drawings showing 2 x internal antennas plus cabs in new location. Could do section 127 off old scheme. 27/4/09: Ben and Pete to meet Brendan from Gillies Group to review proposal. If OK RC to be lodged. 5/5/09: Had to revisit design. Going out for sign off today. Meeting with MG and Brendan to be arranged for early this week. 12/5/09: PMcK to call Brendan. Try to meet on Thursday or Friday. RMA is not a full application. It's going to be treated as a CoC. 18/5/09: Lease is in the post. CoC for RMA. Co-site approvals to lodge. 26/5/09: Lease in Auckland for execution. RMA ok. JM to check with DdV we can build. 2/6/09: Woosh and VF to approve co-siting. 8/6/09: Council haeve changed their minds and have decided that this now requires a S127 and not the CoC as previously determined. 15/6/09: Awaiting CDs. 22/6/09: Still awaiting cheque for RMA submission. 29/6/09: Build? Need LP system approval to satisfy VF requirements. 9/7/09: On Hold. 14/7/09: Not a priority site. LANDBANKED. 21/7/09: Progress into build once we have LH feedback on signal strength/indoor coverage. 28/7/09: Progress to build. VF co-siting approval. LP connection to VF system TBC. Kosam to price and provide start dates. 18/8/09: In build. |  | 2009-09-25 | [17 empty] | FALSE |  | 2683733 | 6007079 | CBD Tower, 84-100 Main Street, Upper Hutt City, Wellington |  |  | CELLSITE | [7 empty] | 2009-08-14 | 2009-08-14 | [8 empty] | 2007-11-30
0 | WLG | 1575 | WLG-045-007 |  | WLG-045-007-H | Trentham North | Upper Hutt City |  | TIER_1_ALL | ACTIVE | GF | A | P2 | grey |  |  | 18.8 | 18.8 |  | -41.1316 | 175.0477 |  |  |  |  | Microwave, Microwave | WLG-045-012-A, WLG-045-012-A | [5 empty] | 2008-08-15, 2008-08-15 | [5 empty] | 2008-07-18 | 3 |  | 2009-02-24 |  |  | 2008-09-08 | 2008-09-04 | 1 | 2008-09-08 | 2008-09-04 |  |  |  | 2008-08-12 |  |  | 2008-11-05 | 2008-11-05 |  | 2008-09-01 |  | 2008-11-21 | 1 | 2 | 2008-11-21 | 2008-11-21 | 2008-12-15 | [5 empty] | 2008-12-10 | 2009-01-30 | 2009-01-30 |  | 2009-04-10 | 2009-04-06 | [8 empty] | 2009-04-29 | 2009-04-30 | 2009-04-29 |  |  |  |  | 9/2/09: Built except for power. 25/2/09: Dispute with land owner. Site built excluding power. To be linked to CIT. 9/3/09: Working through power issues with landlord. 16/3/09: Power only to site. |  | 2009-04-30 | [5 empty] | 2008-12-15 | [11 empty] | FALSE |  | 2681900 | 6006326 | 576D Fergusson Drive, Trentham, Upper Hutt, Wellington |  |  | CELLSITE | [8 empty] | 2008-11-28 | [8 empty] | 2008-06-12
0 | WLG | 1576 | WLG-045-008 |  |  |  | Upper Hutt City |  | TIER_1_ALL
0 | WLG | 1577 | WLG-045-009 |  | WLG-045-009-E | Trentham | Upper Hutt City |  | TIER_1_ALL | ACTIVE | GF | A | P2 | green |  |  | 18.8 | 18.8 |  | -41.1418 | 175.0375 |  |  |  |  | Microwave, Microwave | WLG-045-012-A, WLG-045-012-A | [5 empty] | 2008-05-19, 2008-05-19 | [5 empty] | 2008-02-22 | 1 |  | 2008-02-22 |  |  | 2008-08-05 | 2008-05-13 | 1 | 2008-08-05 | 2008-05-13 |  |  |  | 2008-05-02 |  |  | 2008-05-02 | 2008-05-02 |  | 2008-05-05 |  | 2008-06-06 | 1 | 1 | 2008-06-06 | 2008-06-06 | [6 empty] | 2008-06-21 | 2008-07-04 | 2008-06-30 |  |  | 2008-07-04 | [8 empty] | 2009-03-04 | 2009-03-15 | 2009-03-04 |  |  |  |  | None |  | 2009-03-10 | [17 empty] | FALSE |  | 2681018 | 6005218 | Racecourse Racecourse Rd/Granville St, Threntam Upper Hutt, Wellington |  |  | CELLSITE |  |  | 2016-01-21 | [5 empty] | 2008-06-09 | [8 empty] | 2008-02-07
0 | WLG | 1578 | WLG-045-010 |  | WLG-045-010-H | Silverstream | Upper Hutt City | 7 | TIER_1_ALL | ACTIVE | GF | A | P2 | grey |  |  | 18.8 | 18.8 |  | -41.1469 | 175.0131 |  |  |  |  | Microwave, Leased Line, Microwave | WLG-045-013-A, WLG-047-071-A, WLG-045-013-A | FALSE | FALSE |  |  | FALSE | 2008-05-30, 2008-05-30 | [5 empty] | 2008-05-30 | 3 | 2011-08-12 | 2013-07-24 |  |  | 2008-07-31 | 2008-07-25 | 2 | 2011-08-02 | 2011-08-02 |  |  | 2011-08-05 | 2008-07-24 | 2011-08-05 | 2 | 2011-08-05 | 2011-08-05 |  | 2008-07-22 |  | 2008-09-11 | 2 | 2 | 2008-09-11 | 2008-10-30 | [6 empty] | 2008-10-10 | 2008-12-18 | 2008-12-11 |  | 2008-12-18 | 2008-12-12 | [8 empty] | 2009-03-06 | 2009-03-22 | 2009-03-06 |  |  |  |  | 25/2/09: Leased line install to be confirmed and programme brought on air. |  | 2009-03-22 | [17 empty] | FALSE |  | 2678950 | 6004700 | 212 Fergusson Drive Silverstream Upper Hutt |  |  | CELLSITE | [8 empty] | 2008-09-19 | [8 empty] | 2008-04-24
0 | WLG | 1579 | WLG-045-012 |  | WLG-045-012-A | Heretaunga | Upper Hutt City |  | TIER_1_ALL | ACTIVE | RT | TX | NOPOLE | [6 empty] | -41.1428 | 175.0275 | [17 empty] | 2008-04-18 | 1 |  | 2008-04-18 |  |  | 2008-07-31 | 2008-06-30 | 1 | 2008-07-31 | 2008-06-30 |  |  |  | 2008-07-14 |  |  | 2008-07-14 | 2008-07-14 |  | 2008-05-22 |  | 2008-08-08 | 1 | 1 | 2008-08-08 | 2008-08-08 | [6 empty] | 2008-09-15 | 2008-09-30 | 2008-09-29 |  | 2008-10-10 | 2008-10-16 | [8 empty] | 2009-03-04 | 2009-03-15 | 2009-03-04 |  |  |  |  | 25/2/09: Whisper cabinet lock to be replaced before leased line complete and installed, and site brought on air. |  | 2009-03-15 | [17 empty] | FALSE |  | 2680170 | 6005120 | Somme Rd Trentham |  |  | TXSITE | [8 empty] | 2008-08-27 | [8 empty] | 2008-02-28
0 | WLG | 1580 | WLG-045-013 |  | WLG-045-013-A | Haywards Hill | Upper Hutt City |  | TIER_1_ALL | ACTIVE | GF | TX | LATTICE | [6 empty] | -41.1338 | 174.9938 |  |  |  |  | Microwave | WLG-044-012-B | FALSE | FALSE |  |  | FALSE | 2008-08-12 | [5 empty] | 2008-06-11 | 6 |  | 2014-04-11 |  |  | 2008-07-31 | 2008-07-31 | 2 | 2008-07-31 | 2008-07-31 |  |  | 2008-08-27 | 2008-08-27 | 2008-08-27 | 4 | 2008-08-27 | 2008-08-27 |  | 2008-08-12 |  | 2008-12-16 | 4 |  | 2012-03-13 | 2012-04-17 | [6 empty] | 2009-02-02 | 2009-03-30 | 2009-03-30 |  | 2009-04-06 | 2009-04-08 | [8 empty] | 2009-06-25 | 2009-06-30 | 2009-06-25 |  |  |  |  | 9/2/09: In build. Access issues being worked through. 19/3/09: RF approval given to build. |  | 2009-06-30 | [17 empty] | FALSE |  | 2677364 | 6006188 | 25C Mt Cecil Road, Highway 58, Haywards Hill, Upper Hutt |  |  | TXSITE | [8 empty] | 2008-12-08 | [8 empty] | 2008-04-24
0 | WLG | 1581 | WLG-045-014 |  | WLG-045-014-A | Mt Cecil Rd | Upper Hutt City |  | TIER_1_ALL | ACTIVE | GF | A | P1 | grey |  |  | 13.8 | 13.8 |  | -41.135 | 174.9865 |  |  |  |  | Microwave, Microwave | WLG-046-004-A, WLG-046-004-A | [5 empty] | 2008-08-18, 2008-08-18 | [5 empty] | 2008-09-12 | 2 |  | 2009-01-30 |  |  | 2008-07-31 | 2008-07-31 | 1 | 2008-07-31 | 2008-07-31 |  |  |  | 2008-10-03 |  |  | 2008-10-03 | 2008-10-03 |  | 2008-09-26 |  | 2008-10-30 | 1 | 2 | 2008-10-30 | 2008-10-30 | 2009-03-10 | [5 empty] | 2009-02-02 | 2009-03-30 | 2009-03-26 |  | 2009-03-26 | 2009-03-27 | [8 empty] | 2009-06-25 | 2009-06-30 | 2009-06-25 |  |  |  |  | 9/3/09: In build. 19/3/09: RF approval to build. |  | 2009-06-30 |  |  |  |  | 2009-03-02 | 2009-03-10 | [11 empty] | FALSE |  | 2676753 | 6006074 | 25C Mt Cecil Rd Moonshine Upper Hutt Wellington |  |  | CELLSITE | [8 empty] | 2008-12-08 | [8 empty] | 2008-08-12
0 | WLG | 1582 | WLG-045-015 |  | WLG-045-015-A | Kaitoke Greenfield | Upper Hutt City |  | TIER_1_ALL | ACTIVE | GF | Ab | P2 | green |  |  |  | 13.8 |  | -41.0576 | 175.2067 | [12 empty] | 2009-08-17 | 2009-08-19 |  |  | 2009-09-15 | 2009-09-15 | 1 | 2009-09-15 | 2009-09-15 |  |  | 2009-10-30 | 2009-10-23 |  | 2009-11-30 | 2009-12-01 |  | 2009-09-15 |  | 2009-10-20 |  |  | 2009-10-20 | 2009-10-07 | 2009-09-30 | 2009-09-15 | 2009-11-11 | 2009-11-11 | 1 | 1 | 2009-11-11 | 2009-11-11 | 2009-05-29 |  |  |  |  | 2009-11-23 | 2009-11-19 | 2010-01-30 | 2010-01-27 |  | 2010-02-05 | 2010-02-04 | [8 empty] | 2010-02-05 | 2010-02-05 | 2010-02-05 |  |  |  |  | 25/8/09: PDI with Stefan today. Lease should be straightforward. Co-lo being submitted. 1/9/09: Data pack received. Co-lo application to be submitted. 8/9/09: Site type Ab. Whole installation to be painted. WRC to prepare the lease. RMA with Upper HUtt City Council. 15/9/09: PDs available today. RMA to be lodged and lease to complete ASAP. Submit to TNZ and VNZ to share power, plus chase our own power supply. 22/9/09: Meeting with regional council on site today. Co-site applications for power have been submitted to both TNZ and VNZ. 29/9/09: Site acq and town planning on course. JM email BR to find if any feedback from other telcos on power. 6/10/09: Lease and RMA dates are good. Designation approval required. Using pole already in Wellington. 13/10/09: PMcK has received the lease. Off to landlord today. 20/10/09: JM to chase design department for drawings. Lease with Auckland. PMcK to check ownership of track. Power connection tbc. 27/10/09: Site acquisition complete. Co-site approval awaited. 3/11/09: Awaiting co-site. 10/11/09: Lease complete. Await co-site approval. Pre-build meeting held. 17/11/09: In build. 24/11/09: JM to chase co-siting approval. 1/12/09: In build. Extremely difficult access, especially after prolonged or heavy rain. 15/12/09: Pole lifted today. |  | 2010-02-05 | [5 empty] | 2009-05-29 | [11 empty] | FALSE |  | 2695450 | 6014223 | Kaitoke Regional Park Waterwork Road North of Upper Hutt |  |  | CELLSITE | [7 empty] | 2009-11-16 | 2009-11-16 | [8 empty] | 2009-08-25
0 | WLG | 1583 | WLG-045-016 | Pinehaven | WLG-045-016-E | GF Pinehaven Water Resevoir | Upper Hutt City | 7 | TIER_3 | ACTIVE | GF | D | T2 25 UF | grey | STACK_A | COSITE | 24.45 | 25 | 2 | -41.1577 | 175.009 |  |  |  |  | Microwave | WLG-045-010-H | FALSE | FALSE |  |  | FALSE |  | 2011-06-10 | 2011-06-10 | 2011-06-17 | 2011-06-17 | 2011-07-06 | 2011-07-08 | 2 | 2011-07-06 | 2012-07-11 | 2012-07-06 | 2012-07-17 | 2012-08-07 | 2012-08-03 | 1 | 2012-08-07 | 2012-08-14 | DISCRETIONARY_FULL | 2011-07-15 | 2011-07-22 | 2011-09-02 | 2011-08-18 | 1 | 2012-06-22 | 2012-06-22 |  |  | 2012-11-30 | 2012-11-30 | 1 |  | 2012-11-30 | 2012-11-30 | 2012-10-02 |  |  |  |  | 2012-10-08 | 2012-10-08 | 2012-12-07 | 2012-12-14 | 2012-12-13 | 2012-12-12 | 2012-12-17 | [8 empty] | 2012-12-14 | 2012-12-21 | 2012-12-20 | 2013-01-01 | 2012-12-21 | 2013-08-23 | 2013-09-06 | 19/12/12 Drive Testing today |  | 2012-12-12 |  |  |  |  | 2012-10-02 | 2012-10-02 | 2012-12-11 | 2012-12-24 | 2012-12-17 | 2012-12-19 |  |  | TIER_1_INFILL |  |  | BUILD | 2012-12-10 | FALSE |  | 2678583 | 6003501 | Greenfield Pinehaven Water Resevoir, Wyndham Park Duncraig St Pinehaven Upper Hutt |  | need s.176A approval from UHCC - 16/06/2011 Approval received in form of s95 approval from asset owner and RA - 22/06/2012 | CELLSITE | [15 empty] | 2012-12-14 | 2012-12-14 | 2011-06-17
0 | WLG | 1584 | WLG-045-017 | Bulls Run Cellutronics 002 | WLG-045-017-A | Bulls Run - Moonshine | Upper Hutt City |  | TIER_6 | ACTIVE | GF | 900_MACRO_RPTR | OTHERS |  |  | STANDALONE |  |  |  | -41.0847 | 175.0069 | [66 empty] | 2014-04-01 | [26 empty] | 2678591 | 6011615 | 101A Bulls Run Road, Moonshine Valley, Upper Hutt, Wellington |  |  | REPEATER
0 | WLG | 1585 | WLG-046-001 |  | WLG-046-001-A | Manor Park | Lower Hutt City |  | TIER_1_ALL | ACTIVE | GF | A | P2 | grey |  |  | 18.8 | 18.8 |  | -41.1549 | 174.9816 |  |  |  |  | Microwave, Microwave | WLG-046-006-B, WLG-046-006-B | [5 empty] | 2008-05-30, 2008-05-30 | [5 empty] | 2007-12-14 | 3 |  | 2008-06-24 |  |  | 2008-06-30 | 2008-06-23 | 2 | 2008-06-30 | 2008-06-23 |  |  |  | 2008-07-25 |  |  | 2008-07-25 | 2008-07-25 |  | 2008-03-11 |  | 2008-08-07 | 1 | 2 | 2008-08-07 | 2008-08-07 | [6 empty] | 2008-09-23 | 2008-11-28 | 2008-11-29 |  | 2008-12-05 | 2008-11-29 | [8 empty] | 2008-12-20 | 2008-12-31 | 2008-12-20 |  |  |  |  | None |  | 2008-12-31 | [17 empty] | FALSE |  | 2676292 | 6003870 | 32 Golf Road, Manor Park Upper Hutt |  |  | CELLSITE | [8 empty] | 2008-08-27 | [8 empty] | 2007-11-06
0 | WLG | 1586 | WLG-046-002 |  | WLG-046-002-B | Taita | Lower Hutt City |  | TIER_1_ALL | ACTIVE | GF | A | P1 | grey |  |  | 18.8 | 18.8 |  | -41.1784 | 174.963 |  |  |  |  | Microwave, Microwave | WLG-046-006-B, WLG-046-006-B | [5 empty] | 2008-07-28, 2008-05-19 | [5 empty] | 2008-02-22 | 2 |  | 2008-06-12 |  |  | 2008-06-30 | 2008-05-30 | 2 | 2008-06-30 | 2008-05-30 |  |  |  | 2008-08-18 |  |  | 2008-08-18 | 2008-08-18 |  | 2008-04-08 |  | 2008-06-18 | 1 | 2 | 2008-06-18 | 2008-06-18 | [6 empty] | 2008-09-08 | 2008-10-15 | 2008-10-03 |  | 2008-10-29 | 2008-10-03 | [8 empty] | 2008-12-19 | 2008-12-31 | 2008-12-19 |  |  |  |  | None |  | 2008-12-31 | [17 empty] | FALSE |  | 2674670 | 6001299 | 99 Eastern Hutt Road, Taita Kevin Jenson Trax Rentals Limited 99 Eastern Hutt Road Taita Lower Hutt 0274 374 269 / 04 567 1575 no email |  |  | CELLSITE |  |  | 2014-12-12 | [5 empty] | 2008-08-27 | [8 empty] | 2008-02-07
0 | WLG | 1587 | WLG-046-004 |  | WLG-046-004-A | Stokes Valley | Lower Hutt City |  | TIER_1_ALL | ACTIVE | GF | A | P1 | green |  |  | 13.8 | 13.8 |  | -41.1787 | 174.9738 |  |  |  |  | Microwave, Microwave | WLG-045-013-A, WLG-045-013-A | [5 empty] | 2008-08-18, 2008-08-18 | [5 empty] | 2008-02-09 | 2 |  | 2008-10-22 |  |  | 2008-11-30 | 2008-11-10 | 1 | 2008-11-30 | 2008-11-10 |  |  |  | 2008-03-27 |  |  | 2008-03-27 | 2008-03-27 |  | 2008-04-14 |  | 2008-10-31 | 1 | 2 | 2008-10-31 | 2008-10-31 | 2009-01-05 | [5 empty] | 2008-12-03 | 2009-01-30 | 2009-01-30 |  | 2009-02-13 | 2009-01-30 | [8 empty] | 2009-06-25 | 2009-06-30 | 2009-06-25 |  |  |  |  | 25/02/09: Site built, excluding power. Need written confirmation from VF to use their supply. 19/3/09: Approval from RF to build. |  | 2009-06-30 | [5 empty] | 2009-01-05 | [11 empty] | FALSE |  | 2675576 | 6001246 | the end of SHAFTESBURY GV, Stokes Valley, Wellington (Park car in front of the locked gate and walk for 700m) |  |  | CELLSITE |  |  | 2014-12-12 | [5 empty] | 2008-11-28 | [8 empty] | 2007-11-30
0 | WLG | 1588 | WLG-046-006 |  | WLG-046-006-B | Avalon | Lower Hutt City |  | TIER_1_ALL | ACTIVE | RT | B | NOPOLE | grey |  |  | 38 | 38 |  | -41.1869 | 174.9466 |  |  |  |  | Microwave, Microwave | WLG-045-013-A, WLG-045-013-A | [5 empty] | 2008-06-09, 2008-06-09 | [5 empty] | 2007-12-07 | 5 |  | 2009-05-12 |  |  | 2008-05-31 | 2008-05-09 | 1 | 2008-05-31 | 2008-05-09 |  |  |  | 2008-02-22 |  |  | 2008-02-22 | 2008-02-22 |  | 2008-04-14 |  | 2008-06-30 | 2 | 3 | 2008-09-11 | 2008-09-11 | [6 empty] | 2008-07-17 | 2008-08-15 | 2008-08-15 |  | 2008-09-05 | 2008-08-28 | [8 empty] | 2008-12-19 | 2008-12-31 | 2008-12-19 |  |  |  |  | None. NOTE - BBU 3806 SWAPPED OUT WITH NEW 3900 UNITS ON 20/03/2013. |  | 2008-12-31 | [17 empty] | FALSE |  | 2673271 | 6000379 | 45 Percy Cameron St, Avalon, Wellington |  |  | CELLSITE |  |  | 2014-12-12 | [5 empty] | 2008-07-01 | [8 empty] | 2007-10-26
0 | WLG | 1589 | WLG-046-007 |  | WLG-046-007-B | Avalon South | Lower Hutt City |  | TIER_1_ALL | ACTIVE | GF | A | P3 | green |  |  | 23.8 | 23.8 |  | -41.1954 | 174.9325 |  |  |  |  | Microwave, Microwave | WLG-046-006-B, WLG-046-006-B | [5 empty] | 2008-05-30, 2008-05-30 | [5 empty] | 2008-01-23 | 2 | 2009-03-20 | 2009-03-18 |  |  | 2008-05-31 | 2008-05-13 | 1 | 2008-05-31 | 2008-05-13 |  |  |  | 2008-03-25 |  |  | 2008-03-25 | 2008-03-25 |  | 2008-03-11 |  | 2008-05-16 | 1 | 1 | 2008-05-16 | 2008-05-16 | [6 empty] | 2008-06-25 | 2008-07-31 | 2008-07-29 |  | 2008-08-15 | 2008-08-15 | [8 empty] | 2008-12-19 | 2008-12-31 | 2008-12-19 |  |  |  |  | None |  | 2008-12-31 | [17 empty] | FALSE |  | 2672070 | 5999470 | Hutt Golf Club, Fairway Drv, Military Rd, Lower Hutt, Wellington |  |  | CELLSITE |  |  | 2014-12-12 | [5 empty] | 2008-05-19 | [8 empty] | 2007-11-16
0 | WLG | 1590 | WLG-046-008 |  | WLG-046-008-A | Naenae | Lower Hutt City |  | TIER_1_ALL | ACTIVE | GF | A | P2 | grey |  |  | 18.8 | 18.8 |  | -41.1988 | 174.9456 |  |  |  |  | Microwave, Microwave | WLG-046-006-B, WLG-046-006-B | [5 empty] | 2007-11-20, 2007-11-20 | [5 empty] | 2007-11-23 | 3 |  | 2008-02-15 |  |  | 2008-05-31 | 2008-05-26 | 1 | 2009-03-04 | 2009-03-10 |  |  |  | 2008-07-31 |  |  | 2008-07-31 | 2008-07-31 |  | 2008-02-12 |  | 2008-08-26 | 1 | 3 | 2008-08-26 | 2008-08-26 | 2009-03-20 |  |  |  |  | 2009-03-26 | 2009-03-25 | 2009-04-20 | 2009-04-17 |  | 2009-04-28 | 2009-04-29 | [8 empty] | 2009-06-24 | 2009-06-25 | 2009-06-24 |  |  |  |  | 9/2/09: Acquired save for power route confirmation. PMck to get agreement from Judy Robb. 3/3/09: Still awaiting power route confirmation. 9/3/09: Still awaiting confirmation of power route. Could go ahead and build. Timings for council cycle track installation to be confirmed. 16/3/09: Power route OK'd. TSS'd. Agreed to add a fence. 16/4/09: All on course for April civils complete. |  | 2009-06-25 |  |  |  |  | 2009-03-13 | 2009-03-20 | [11 empty] | FALSE |  | 2673157 | 5999066 | All secure self storage Cambridge Terrace Wellington |  |  | CELLSITE |  |  | 2014-12-12 |  |  |  |  | 2009-03-16 | 2009-03-10 | [8 empty] | 2007-10-04
0 | WLG | 1591 | WLG-046-009 |  | WLG-046-009-B | Epuni | Lower Hutt City |  | TIER_1_ALL | ACTIVE | RT | B | NOPOLE | grey |  |  | 20.7 | 20.7 |  | -41.2059 | 174.9255 | [17 empty] | 2008-02-09 | 3 |  | 2008-09-22 |  |  | 2008-06-27 | 2008-06-30 | 2 | 2008-06-27 | 2008-06-30 |  |  |  | 2008-07-01 |  |  | 2008-07-01 | 2008-07-01 |  | 2008-05-19 |  | 2008-07-25 | 1 | 3 | 2008-07-25 | 2008-07-25 | [6 empty] | 2008-09-04 | 2008-09-18 | 2008-09-19 |  | 2008-10-03 | 2008-09-26 | [8 empty] | 2008-12-20 | 2008-12-31 | 2008-12-20 |  |  |  |  | None |  | 2008-12-31 | [17 empty] | FALSE |  | 2671462 | 5998316 | 67a Pilmuir Street Lower Hutt |  |  | CELLSITE |  |  | 2014-12-12 | [5 empty] | 2008-09-01 | [8 empty] | 2007-12-03
0 | WLG | 1592 | WLG-046-010 | Maungaraki | WLG-046-010-B | Maungaraki Shops LPR | Lower Hutt City | 7 | TIER_1_INFILL | ACTIVE | RSR | DU | P4B |  | INLINE | STANDALONE |  | 10.8 | 1 | -41.208 | 174.8787 |  | 2011-04-20 |  |  | Microwave | WLG-046-033-B | FALSE | FALSE |  |  | FALSE |  | 2011-06-02 | 2011-06-02 | 2011-06-10 | 2011-06-02 | 2011-06-22 | 2011-06-20 | 2 | 2011-06-22 | 2011-08-01 | 2011-09-23 | 2011-10-04 | 2011-11-25 | 2011-11-16 |  |  | 2011-11-16 | NES | 2011-06-27 | 2011-06-28 | 2011-08-08 | 2011-07-15 | 2 |  | 2011-07-15 |  |  | 2011-12-15 | 2012-02-08 | 1 |  |  | 2012-02-08 | 2012-01-09 |  |  |  |  | 2012-01-10 | 2012-01-16 | 2012-01-27 | 2012-01-27 | 2012-01-19 | 2012-02-03 | 2012-02-08 | [8 empty] | 2012-02-08 | 2012-02-14 | 2012-02-10 | 2012-02-24 | 2012-02-29 | 2012-05-29 | 2012-08-24 | 12.06.2014 : "D" configuration build. (APM, Battery, & 2 x RFC) using version "B" cabinets. Thus making it a "DU" Site. (As per Ron Bush/blr) |  | 2012-02-02 | 2012-01-12 | 2011-12-07 | 2011-12-15 | 2012-01-27 | 2011-12-15 | 2012-01-09 | 2012-01-20 | 2012-01-23 | 2012-02-09 | 2012-02-08 | [6 empty] | 2012-01-19 | FALSE |  | 2667525 | 5998162 | Dowse Drive, south of Holly Grove Maungaraki Lower Hutt |  |  | CELLSITE |  |  | 2014-12-12 | [12 empty] | 2012-02-10 | 2012-02-15
0 | WLG | 1593 | WLG-046-011 |  | WLG-046-011-A | Fairfield | Lower Hutt City |  | TIER_1_ALL | ACTIVE | RT | A | NOPOLE | grey |  |  | 9.6 | 9.6 |  | -41.2104 | 174.9343 |  |  |  |  | Microwave, Microwave | WLG-046-013-C, WLG-046-013-C | [5 empty] | 2008-05-19, 2008-05-19 | [5 empty] | 2008-04-09 | 1 |  | 2008-04-09 |  |  | 2008-06-30 | 2008-06-30 | 1 | 2008-06-30 | 2008-06-30 |  |  |  | 2008-07-29 |  |  | 2008-07-29 | 2008-07-29 |  | 2008-07-29 |  | 2008-09-17 | 1 | 1 | 2008-09-17 | 2008-09-17 | [6 empty] | 2008-09-26 | 2008-10-31 | 2008-10-30 |  | 2008-11-25 | 2008-11-25 | [8 empty] | 2008-12-20 | 2008-12-31 | 2008-12-20 |  |  |  |  | None |  | 2008-12-31 | [17 empty] | FALSE |  | 2672184 | 5997793 | 310 Waiwhetu Rd, Fairfield Wellington |  |  | CELLSITE |  |  | 2014-12-12 | [5 empty] | 2008-09-22 | [8 empty] | 2008-03-04
0 | WLG | 1594 | WLG-046-013 |  | WLG-046-013-C | Lower Hutt CBD | Lower Hutt City | 7 | TIER_1_ALL | ACTIVE | RT | B | NOPOLE | grey |  |  | 35.95 | 35.95 |  | -41.2108 | 174.9026 |  |  |  |  | Fibre Optic, Fibre Optic | WLG-046-006-B, WLG-046-006-B | FALSE | FALSE |  |  | FALSE | 2008-06-09, 2008-06-09 | [5 empty] | 2007-12-07 | 4 | 2011-08-12 | 2009-06-11 |  |  | 2008-05-31 | 2008-05-15 | 1 | 2011-08-02 | 2011-08-01 |  |  | 2011-08-05 | 2008-02-15 | 2011-08-05 | 4 | 2011-08-05 | 2011-08-05 |  | 2008-03-17 |  | 2008-04-30 | 1 | 2 | 2008-04-30 | 2008-04-30 | [6 empty] | 2008-06-13 | 2008-06-30 | 2008-06-30 |  | 2008-08-08 | 2008-07-31 | [8 empty] | 2008-12-19 | 2008-12-31 | 2008-12-19 |  |  |  |  | None. Note -BBU 3806 swapped out for new 3900 unit on 17/10/2012. |  | 2008-12-31 | [17 empty] | FALSE |  | 2669528 | 5997808 | The Public Trust Building 44 Queens Drive Lower Hutt |  |  | CELLSITE |  |  | 2014-12-12 | [5 empty] | 2008-05-19 | [8 empty] | 2007-11-06
0 | WLG | 1595 | WLG-046-014 |  | WLG-046-014-G | Normandale | Lower Hutt City |  | TIER_1_ALL | ACTIVE | GF | A | P2 | grey |  |  | 13.8 | 13.8 |  | -41.2133 | 174.888 | [17 empty] | 2008-12-05 | 1 |  | 2008-12-05 |  |  | 2009-01-21 | 2008-08-29 |  | 2009-01-21 | 2009-01-21 |  |  |  | 2009-01-28 |  |  | 2009-01-28 | 2009-01-28 |  | 2009-01-26 |  | 2009-02-25 | 1 | 1 | 2009-03-02 | 2009-02-25 | 2009-02-23 |  |  |  |  | 2009-03-12 | 2009-03-06 | 2009-03-29 | 2009-03-29 |  | 2009-03-31 | 2009-03-30 | [8 empty] | 2009-04-29 | 2009-04-28 | 2009-04-29 |  |  |  |  | 9/2/09: RMA complete. Revised drawings approved by landlord. TSS'd. Must be built off rail corridor, need to co-ordinate with Ontrack and pole availability. 9/3/09: In build. |  | 2009-04-28 |  |  |  |  | 2009-02-23 | 2009-02-23 | [11 empty] | FALSE |  | 2668297 | 5997557 | 453 Hutt Road (Behind Super Cheap Auto) Lower Hutt Wellington |  |  | CELLSITE |  |  | 2014-12-12 | [5 empty] | 2009-02-23 | [8 empty] | 2008-12-01
0 | WLG | 1596 | WLG-046-016 |  | WLG-046-016-I | Alicetown | Lower Hutt City |  | TIER_1_ALL | ACTIVE | GF | A | P1 | grey |  |  | 13.8 | 13.8 |  | -41.2181 | 174.8889 | [17 empty] | 2008-11-26 | 1 |  | 2008-11-26 |  |  |  | 2008-11-06 | 1 |  | 2008-11-06 |  |  |  | 2009-01-05 |  |  | 2009-01-05 | 2009-01-05 |  | 2009-01-26 |  | 2009-02-16 | 1 | 1 | 2009-02-16 | 2009-02-16 | 2009-01-05 | [5 empty] | 2009-03-03 | 2009-03-25 | 2009-03-25 |  | 2009-03-26 | 2009-03-27 | [8 empty] | 2009-04-30 | 2009-04-30 | 2009-04-30 |  |  |  |  | 9/2/09: TSS'd 9/3/09: In build. |  | 2009-04-30 | [5 empty] | 2009-01-05 | [11 empty] | FALSE |  | 2668362 | 5997020 | 8 Victoria St, Alicetown, Lower Hutt, Wellington |  |  | CELLSITE |  |  | 2014-12-12 | [5 empty] | 2009-02-04 | [8 empty] | 2008-11-11
0 | WLG | 1597 | WLG-046-019 |  | WLG-046-019-E | Gracefield | Lower Hutt City |  | TIER_1_ALL | ACTIVE | GF | A | P2 | grey |  |  | 18.8 | 18.8 |  | -41.2387 | 174.9111 |  |  |  |  | Microwave | WLG-046-031-B | [5 empty] | 2008-05-27 | [5 empty] | 2008-01-16 | 4 | 2009-03-03 | 2009-03-31 |  |  | 2008-04-10 | 2008-04-10 | 1 | 2008-04-10 | 2008-04-10 |  |  |  | 2008-09-16 |  |  | 2008-09-16 | 2008-09-16 |  | 2008-04-08 |  | 2008-10-17 | 1 | 2 | 2008-10-17 | 2008-10-17 | 2008-12-15 | [5 empty] | 2008-11-24 | 2009-01-30 | 2009-01-30 |  | 2009-04-20 | 2009-04-21 | [8 empty] | 2009-05-27 | 2009-05-30 | 2009-05-27 |  |  |  |  | 9/2/09: Built awaiting power. 25/02/09: Site built awaiting power wayleave. 3/3/09: Further agreement required by Rail Track. 16/3/09: Still with Crystal. Drawings of trenching due tomorrow. 30/3/09: Licence in the post. All approved. Richard Burrell happy to proceed. JM to instruct power. |  | 2009-05-30 | [5 empty] | 2008-12-15 | [11 empty] | FALSE |  | 2670175 | 5994694 | 43 Seaview Road, Gracefield, Wellington |  |  | CELLSITE |  |  | 2014-12-12 | [5 empty] | 2008-11-11 | [8 empty] | 2008-01-08
0 | WLG | 1598 | WLG-046-020 |  | WLG-046-020-B | Moores Valley | Lower Hutt City |  | TIER_1_ALL | ACTIVE | GF | A | P2 | green |  |  | 13.8 | 13.8 |  | -41.2486 | 174.9406 | [17 empty] | 2008-01-16 | 4 |  | 2015-09-07 |  |  | 2008-11-30 | 2008-11-10 | 1 | 2008-11-30 | 2008-11-10 |  |  |  | 2008-04-17 |  |  | 2008-04-17 | 2008-04-17 |  | 2008-04-08 |  | 2008-07-02 | 1 | 3 | 2008-07-02 | 2008-07-02 | 2009-01-05 | [5 empty] | 2008-12-03 | 2009-01-30 | 2009-01-30 |  | 2009-01-26 | 2009-01-30 | [8 empty] | 2009-04-30 | 2009-04-30 | 2009-04-30 |  |  |  |  | 25/2/09: To be linked to Wainui Shopping Centre. |  | 2009-04-30 | [5 empty] | 2009-01-05 | [11 empty] | FALSE |  | 2672620 | 5993548 | Wainui Water Tower, Parkland, Lowerhutt, Wellington |  |  | CELLSITE |  |  | 2014-12-12 | [5 empty] | 2008-11-28 | [8 empty] | 2007-11-30
0 | WLG | 1599 | WLG-046-023 |  | WLG-046-023-A | Wainuiomata | Lower Hutt City |  | TIER_1_ALL | ACTIVE | GF | A | P1 | grey |  |  | 13.8 | 13.8 |  | -41.2599 | 174.9454 |  |  |  |  | Leased Line | WLG-047-071-A | [11 empty] | 2007-12-19 | 1 |  | 2007-12-19 |  |  | 2008-05-31 | 2008-05-12 | 1 | 2008-05-31 | 2008-05-12 |  |  |  | 2008-07-29 |  |  | 2008-07-29 | 2008-07-29 |  | 2008-04-08 |  | 2008-06-28 | 2 | 1 | 2008-07-29 | 2008-07-29 | [6 empty] | 2008-09-15 | 2008-10-10 | 2008-10-10 |  | 2008-10-15 | 2008-10-16 | [8 empty] | 2009-04-06 | 2009-04-16 | 2009-04-06 |  |  |  |  | 25/2/09: Awaiting leased line. |  | 2009-04-16 | [17 empty] | FALSE |  | 2672997 | 5992279 | 26-33 The Strand Wainuiomata, Wainuiomata, Wellington |  |  | CELLSITE | [8 empty] | 2008-07-31 | [8 empty] | 2007-10-26
0 | WLG | 1600 | WLG-046-024 |  | WLG-046-024-C | Homedale | Lower Hutt City |  | TIER_1_ALL | ACTIVE | GF | A | P1 | grey |  |  | 13.8 | 13.8 |  | -41.2753 | 174.949 |  |  |  |  | Leased Line | WLG-047-071-A | [11 empty] | 2007-12-14 | 3 |  | 2008-10-08 |  |  | 2008-05-30 | 2008-05-29 | 3 | 2008-05-30 | 2008-05-29 |  |  |  | 2008-06-03 |  |  | 2008-06-03 | 2008-06-03 |  | 2008-04-14 |  | 2008-08-27 | 1 | 2 | 2008-08-27 | 2008-08-27 | [6 empty] | 2008-09-18 | 2008-10-31 | 2008-10-23 |  |  | 2008-10-23 | [8 empty] | 2009-03-06 | 2009-03-30 | 2009-03-06 |  |  |  |  | None |  | 2009-03-30 | [17 empty] | FALSE |  | 2673257 | 5990559 | 37 Burden Avenue Homedale Wainuiomata |  |  | CELLSITE | [8 empty] | 2008-09-01 | [8 empty] | 2007-12-04
0 | WLG | 1601 | WLG-046-025 |  | WLG-046-025-C | Eastbourne | Lower Hutt City |  | TIER_1_ALL | ACTIVE | RSR | A | P4B | green |  |  | 13.2 | 13.2 |  | -41.29 | 174.8973 |  |  |  |  | Leased Line | WLG-047-071-A | [11 empty] | 2007-12-20 | 3 |  | 2008-04-24 |  |  | 2008-08-29 | 2008-07-31 | 3 | 2008-08-29 | 2008-07-31 |  |  |  | 2008-02-22 |  |  | 2008-02-22 | 2008-02-22 |  | 2008-04-10 |  | 2008-05-23 | 2 | 3 | 2008-09-05 | 2008-09-05 | [6 empty] | 2008-09-04 | 2008-10-10 | 2008-10-10 |  | 2008-10-21 | 2008-10-20 | [8 empty] | 2009-03-06 | 2009-03-09 | 2009-03-06 |  |  |  |  | 25/2/09: Leased line install TBC. Site programme to be brought on air. |  | 2009-03-09 | [17 empty] | FALSE |  | 2668888 | 5989022 | LPR o/s 29 Oroua St, Eastbourne, Wellington |  |  | CELLSITE | [8 empty] | 2008-09-01 | [8 empty] | 2007-11-21
0 | WLG | 1602 | WLG-046-027 |  | WLG-046-027-C | Waiwhetu | Lower Hutt City |  | TIER_1_ALL | ACTIVE | GF | A | P3 | grey |  |  | 13.8 | 13.8 |  | -41.2226 | 174.9118 |  |  |  |  | Microwave | WLG-046-033-B | [11 empty] | 2008-10-17 | 1 | 2008-10-15 | 2008-10-17 |  |  | 2008-09-30 | 2008-09-05 | 1 | 2008-09-30 | 2008-09-05 |  |  |  | 2008-11-18 |  |  | 2008-11-18 | 2008-11-18 |  | 2008-12-22 |  | 2009-01-28 | 1 | 1 | 2009-01-28 | 2009-01-28 | 2008-12-19 | [5 empty] | 2009-02-02 | 2009-02-20 | 2009-02-20 |  | 2009-04-05 | 2009-04-06 | [8 empty] | 2009-04-30 | 2009-04-29 | 2009-04-30 |  |  |  |  | Transmission to do LOS 16/3/09: Power only to resolve. |  | 2009-04-29 |  |  |  |  | 2008-12-31 | 2008-12-19 | [11 empty] | FALSE |  | 2670271 | 5996485 | Hutt Plumbers 16 Hawkins Street Waiwhetu Lower Hutt |  |  | CELLSITE |  |  | 2014-12-12 | [5 empty] | 2009-02-03 | [8 empty] | 2008-08-27
0 | WLG | 1603 | WLG-046-028 |  | WLG-046-028-D | Waterloo | Lower Hutt City |  | TIER_1_ALL | ACTIVE | RT | B | NOPOLE | grey |  |  | 11.2 | 11.2 |  | -41.2141 | 174.9208 |  |  |  |  | Microwave, Microwave | WLG-046-013-C, WLG-046-013-C | [5 empty] | 2008-05-26, 2008-05-26 |  | 2008-04-01 |  |  |  | 2008-04-23 | 3 |  | 2008-07-08 |  |  | 2008-10-30 | 2008-10-07 | 3 | 2008-10-30 | 2008-10-07 |  |  |  | 2009-01-20 |  |  | 2009-01-20 | 2009-01-20 |  | 2008-12-01 |  | 2009-02-12 | 1 | 3 | 2009-02-12 | 2009-02-12 | [5 empty] | 2009-05-15 | 2009-05-08 | 2009-06-28 | 2009-06-29 |  | 2009-07-03 | 2009-07-01 | [8 empty] | 2009-07-02 | 2009-07-06 | 2009-07-02 |  |  |  |  | 9/2/09: to TSS w/c 9/2/09 9/3/09: In build. 16/4/09: Still waiting for Arrow pricing. 12/5/09: IN build with SkyComms. Lots of steel to fabricate. 29/6/09: Built. |  | 2009-07-06 | [17 empty] | FALSE |  | 2671047 | 5997414 | Waterloo Interchange, Oxford Tce, Lower Hutt, Wellington |  |  | CELLSITE |  |  | 2014-12-12 | [5 empty] | 2009-02-23 | [8 empty] | 2008-03-31
0 | WLG | 1604 | WLG-046-031 |  | WLG-046-031-B | Petone South | Lower Hutt City |  | TIER_1_ALL | ACTIVE | RT | B | NOPOLE | grey | [5 empty] | -41.2261 | 174.8694 | [17 empty] | 2008-01-29 | 5 |  | 2013-08-12 |  |  | 2008-05-31 | 2008-05-13 | 1 | 2008-05-31 | 2008-05-13 |  |  |  | 2008-05-02 |  |  | 2008-12-18 | 2008-12-18 |  | 2008-04-14 |  | 2008-06-30 | 4 | 2 | 2008-12-10 | 2008-12-10 | [5 empty] | 2009-02-09 | 2009-02-11 | 2009-03-17 | 2009-03-16 |  | 2009-03-20 | 2009-03-20 | [8 empty] | 2009-03-20 | 2009-03-25 | 2009-03-20 |  |  |  |  | 25/2/09: Citylink fibre in, site in build. NOTE - BBU 3806 SWAPPED OUT WITH NEW 3900 UNIT ON 20/03/2013. |  | 2009-03-25 | [17 empty] | FALSE |  | 2666710 | 5996168 | SecuritEase Building 75 The Esplanade Petone Wellington |  |  | CELLSITE |  |  | 2014-12-12 | [5 empty] | 2008-12-08 | [8 empty] | 2007-12-04
0 | WLG | 1605 | WLG-046-032 |  | WLG-046-032-B | Petone North | Lower Hutt City |  | TIER_1_ALL | ACTIVE | GF | A | P2 | grey |  |  | 13.8 | 13.8 |  | -41.2211 | 174.877 |  |  |  |  | Microwave, Microwave | WLG-046-031-B, WLG-046-031-B | [5 empty] | 2008-09-03, 2009-01-07 |  |  |  |  | 2009-04-02 | 2008-09-19 | 3 | 2009-03-13 | 2009-03-04 |  |  | 2008-09-07 | 2008-08-29 | 2 | 2008-09-07 | 2008-08-29 |  |  |  | 2008-12-18 |  |  | 2009-02-15 | 2008-12-18 |  | 2008-10-21 |  | 2008-12-18 | 1 | 1 | 2008-12-18 | 2008-12-18 | 2009-02-02 | [5 empty] | 2009-01-30 | 2009-02-28 | 2009-02-25 |  | 2009-02-28 | 2009-02-27 | [8 empty] | 2009-03-24 | 2009-03-24 | 2009-03-24 |  |  |  |  | None |  | 2009-03-24 |  |  |  |  | 2009-01-28 | 2009-02-02 | [11 empty] | FALSE |  | 2667355 | 5996711 | 9 Regent Street Petone Wellington |  |  | CELLSITE |  |  | 2014-12-12 | [5 empty] | 2009-01-08 | [8 empty] | 2008-08-27
0 | WLG | 1606 | WLG-046-033 |  | WLG-046-033-B | Moera | Lower Hutt City | 7 | TIER_1_ALL | ACTIVE | GF | A | P2 | grey |  |  | 18.8 | 18.8 |  | -41.2294 | 174.9018 |  |  |  |  | Microwave, Microwave | WLG-046-019-E, WLG-046-019-E | FALSE | FALSE |  |  | FALSE | 2008-09-29, 2008-09-29 | [5 empty] | 2008-07-18 | 3 | 2011-08-12 | 2009-03-04 |  |  | 2008-09-30 | 2008-07-25 | 2 | 2011-08-02 | 2011-08-01 |  |  | 2011-08-05 | 2008-09-08 | 2011-08-05 | 3 | 2011-08-05 | 2011-08-05 |  | 2008-08-27 |  | 2008-11-12 | 1 | 2 | 2008-11-12 | 2008-11-12 | 2009-02-09 | [5 empty] | 2008-12-03 | 2009-02-28 | 2009-02-26 |  | 2009-02-28 | 2009-03-03 | [8 empty] | 2009-04-30 | 2009-04-29 | 2009-04-30 |  |  |  |  | None |  | 2009-04-29 | [5 empty] | 2009-02-09 | [11 empty] | FALSE |  | 2669412 | 5995747 | 39-41 Randwick Road Moera Lower Hutt |  |  | CELLSITE |  |  | 2014-12-12 | [5 empty] | 2008-11-17 | [8 empty] | 2008-06-13
0 | WLG | 1607 | WLG-046-035 |  | WLG-046-035-B | Pencarrow | Lower Hutt City |  | TIER_1_ALL | ACTIVE | GF | A | P2 | flax green |  | COLO | 10 | 10 |  | -41.3168 | 174.8798 | [12 empty] | 2009-08-10 | 2009-08-10 |  |  | 2009-08-26 | 2009-09-18 | 1 | 2009-08-26 | 2009-09-18 |  |  | 2009-12-20 | 2010-03-18 |  | 2009-12-20 |  |  | 2009-07-03 |  | 2009-07-30 |  |  | 2009-07-30 | 2009-07-20 | 2009-08-26 | 2009-08-26 | 2009-09-18 | 2009-10-06 | 1 | 1 | 2009-09-18 | 2009-10-06 | [5 empty] | 2009-11-22 | 2009-11-10 | 2009-12-22 | 2009-12-17 |  | 2009-12-24 | 2009-12-17 | [8 empty] | 2009-12-21 | 2009-12-24 | 2009-12-21 |  |  |  |  | 9/2/09: Stuck site. Jason Britten doing co-lo. 3/3/09: Confirmation of roles and responsibilities required. 9/3/09: Jason Britten still chasing Vodafone to establish roles and responsibilities. 16/3/09: JM to speak with JB. 30/3/09: Indicative drawings received to approve. VF doing the RMA. 16/4/09: Co-lo application to lodge. Questionable technical requirement. 20/4/09: Update from Jason needed. 27/4/09: Question over whether we continue with this site. John Challinor to confirm. 5/5/09: TNZ co-lo - no feedback. VF not lodged the RC for the co-lo. Form submitted. JM to speak with BR/JB. Team to visit site to determine which option is best and decide whether we lodge on our own option which will go to a hearing. 12/5/09: JM to advise JB that he is to investigate the TNZ option. Team arranging access to the land to caravan. VF about to lodge RC so our design is agreed. 18/5/09: JM spoke with JB yesterday. JB further investigating TNZ option. VF option still progressing with joint build. VF has submitted for RC with us included. 26/5/09: Update from JB. 2/6/09: JB for update. Send the TNZ proposal - check with JB it's received and sent. VF is progressing. Plus investigating options at Mt Crawford. Site data pack requested. 8/6/09: Three options being investigated for Seatoun. 1) This candidate is the VF option which has progressed to RC submission by Vodafone. Vodafone have no Build timescales so they'd be looking to us to get the site constructed. 2) This is the preferred option to share an existing TNZ tower. There is an online application that is partially complete. PMcK to sort out access to caravan. 3)Option to back up one or two is at Mt Crawford on land designated for TNZ use. 15/6/09: Back up solution. 22/6/09: Back up to TNZ Camp Bay Site WLG-046-035-C. 4/8/09: JM to chase build drawings and costs. 11/8/09: Site to be pegged for RF. Site acquisition to determine VF lease area and to investigate whether we can terminate our existing lease and sub-let an area from Vodafone. Await VF project plan and CDs. 18/8/09: Still waiting. JB to confirm what's happening with the lease. PMcK may have to discuss lease variation with VF and LL. 25/8/09: PMcK to speak with Belinda about the VF lease to see if it allows for sub-leasing. Power supply to be confirmed. Tower to be painted flax green. JM to chase HG re: PD and CD issue. 1/9/09: Structural calcs done? Lease arrangement agreed? PMcK to speak to landlord re: cancelling our lease and following up VF lease. JMaxwell re: power. 8/9/09: Existing lease with landlord to be revoked and new lease to be entered into through Vodafone. LL ok with the proposal. Voda have not done the LL deal yet. Barbara is progressing. RMA is complete plus RMA have approved the new sectors as have Vodafone with the exception of the sector spacing. 15/9/09: BR to close out the lease with Vodafone. BR needs drawings showing the change in sectors with confirmation of the separations between the antennas. 22/9/09: All sublet via VFNZ. Drawings issued to VF by Harrison Grierson and will be circulated internally for approval. Flax green site type A to be used. 29/9/09: Await VF lease only. 6/10/09: BR to update on Vodafone lease. PMcK lease complete. BR to advise progress of VF lease. 20/10/09: JM to check with BR. 27/10/09: BR to update. 10/11/09: Lease to complete end of this week. In build. 17/11/09: Consent of owner required. In build. 24/11/09: In build. LL approval still to be given. JM to chase lease. |  | 2009-12-24 | [17 empty] | FALSE |  | 2667359 | 5986082 | 525 Muritai Road, Eastbourne |  |  | CELLSITE | [7 empty] | 2009-11-09 | 2009-11-11 | [8 empty] | 2009-08-25
0 | WLG | 1608 | WLG-046-036 |  | WLG-046-036-A | Gear Island | Lower Hutt City |  | TIER_1_ALL | ACTIVE | GF | A | P3 | green |  |  | 18.8 | 18.8 |  | -41.228 | 174.8917 | [17 empty] | 2008-11-20 | 3 |  | 2009-02-17 |  |  | 2009-03-15 | 2009-03-19 | 3 | 2009-03-15 | 2009-03-15 |  |  |  | 2009-01-26 |  |  | 2009-01-26 | 2009-01-26 |  | 2009-02-02 | 2009-02-13 | 2009-03-12 | 1 | 3 | 2009-03-13 | 2009-03-12 | 2009-02-02 |  |  |  |  | 2009-04-01 | 2009-04-01 | 2009-05-10 | 2009-04-30 |  | 2009-05-18 | 2009-05-14 | [8 empty] | 2009-05-28 | 2009-05-30 | 2009-05-28 |  |  |  |  | 9/2/09: Council water board have concerns over potential RF interference and with proximity to a water pipe. Stefan/Lorraine and PMcK to meet on site. 9/3/09: Lease signed by NZCL. Need WRC and GOlf Club to sign. April build. 16/3/09: Lease imminent. 23/3/09: Chase "All Site Acq Complete" actual to be claimed. 30/3/09: All complete. 16/4/09: All on course for April civils completion. Problem with water table. POle lift delayed a week. 20/4/09: Still on course for civils completion in April. 12/5/09: Pole stood waiting for power towards end of this week. |  | 2009-05-30 |  |  |  |  | 2009-02-27 | 2009-02-02 | [11 empty] | FALSE |  | 2668782 | 5995830 | Shandon Golf Club, 471 Jackson Street PO Box 38104 Wellington Mail Centre Petone 5012 Travis Gawler ( travis@golf.co.nz ) 04 9396305 |  |  | CELLSITE |  |  | 2014-12-12 |  |  |  |  | 2009-04-01 | 2009-03-30 | [8 empty] | 2008-10-10
0 | WLG | 1609 | WLG-046-037 | Kelson | WLG-046-037-F | LPR 177 Major Drive-Hard Match Only | Lower Hutt City | 7 | TIER_1_INFILL | ACTIVE | RSR | D | P4B | grey | INLINE | STANDALONE | 11.2 | 12.2 | 2 | -41.1774 | 174.9354 |  |  |  |  | Leased Line, Microwave | WLG-047-071-A, WLG-046-013-C | FALSE | FALSE |  |  | FALSE |  | 2011-06-30 | 2011-06-29 | 2011-07-05 | 2011-07-05 | 2011-07-22 | 2011-07-19 | 3 | 2011-09-27 | 2011-09-27 | 2011-10-18 | 2011-10-04 | 2011-11-25 | 2011-11-16 |  |  | 2011-11-16 | NES | 2011-07-26 | 2011-08-04 | 2011-09-09 | 2011-08-29 | 1 |  | 2011-08-29 | [35 empty] | Council have requested a completion date for this LPR. 2D has specified Dec 2012. If not complete by then, advise Council and request an extension. (Refer site folder on server for Council reponse to Telco Notice.) | [17 empty] | HARDMATCH |  | FALSE |  | 2672361 | 6001460 | 177 Major Drive Kelson Lower Hutt |  | do noise assessment to ensure compliance after boundary line is confirmed - 30/06/2011 | CELLSITE | WIPHOLDING
0 | WLG | 1610 | WLG-046-038 | Lower Hutt East | WLG-046-038-A | Lower Hutt East | Lower Hutt City | 6 | 2014 | ACTIVE | RT | DF | RT | Grey | STACK_A | STANDALONE |  |  |  | -41.2091 | 174.9091 |  |  |  |  | Leased Line | WLG-046-006-B | FALSE | FALSE |  |  | FALSE |  | 2014-02-19 | 2014-02-19 | 2013-12-02 | 2013-12-02 | 2013-12-02 | 2013-11-12 | 2 | 2013-12-02 | 2014-09-25 | 2013-12-02 | 2013-12-02 | 2014-03-10 | 2014-02-28 |  | 2014-03-10 | 2014-02-28 | PERMITTED |  | 2013-11-29 | 2014-01-17 | 2013-12-19 | 1 | 2014-01-20 | 2013-12-19 | 2014-02-17 | 2014-03-01 | 2014-03-16 | 2014-03-12 | 1 |  | 2014-04-08 | 2014-03-12 | [5 empty] | 2014-06-16 | 2014-06-16 | 2014-08-04 | 2014-08-01 | 2014-07-15 | 2014-07-18 | 2014-08-01 | 2014-07-15 | 2014-07-15 | [7 empty] | 2014-08-13 | 2014-08-14 | [15 empty] | 2014-08-01 | 2014-08-04 | 2013-11-29 | MEDIUM | TIER_1_INFILL | 2014-07-15 | 2014-07-15 | BUILD | 2014-06-30 | FALSE |  | 2670076 | 5997990 | 65 Walterloo Rd |  |  | CELLSITE |  |  | 2014-12-12 | [14 empty] | 2013-12-02
0 | WLG | 1611 | WLG-046-039 | Homedale | WLG-046-039-A | Mt Crowther | Lower Hutt City |  | TIER_6 | ACTIVE | [100 empty] | HARDMATCH
0 | WLG | 1612 | WLG-046-040 | Kelson Micro 1 | WLG-046-040-A | Kelson Microcell A | Lower Hutt City | 24 | 2015 | ACTIVE | RSR | MC | NOPOLE |  |  |  | 8 | 9.14 |  | -41.1797 | 174.9323 |  | 2014-09-30 |  |  | Fibre Optic | WLG-046-006-B | FALSE | FALSE |  |  | FALSE |  | 2014-08-27 | 2014-08-27 | 2014-09-02 | 2014-09-02 | 2014-09-15 | 2014-09-10 | 1 | 2014-09-30 | 2014-09-10 | 2014-11-14 | 2014-10-29 | 2014-11-14 | 2014-10-29 | 1 |  | 2014-11-18 | DISCRETIONARY_RESTRICT | 2014-11-13 | 2014-11-13 | 2014-12-19 | 2014-12-08 | 1 |  | 2014-12-08 | 2014-10-20 | 2014-10-20 | 2015-01-16 | 2015-01-14 | 1 |  |  | 2015-01-14 | [5 empty] | 2015-03-02 | 2015-03-02 | 2015-03-06 | 2015-03-06 |  | 2015-03-27 | 2015-03-27 | [9 empty] | 2015-04-17 | 2015-04-16 |  |  |  |  | Concrete lightpole. 1 MC unit required on Fibre. PD Rev 1 issued and forwarded to HCC. (Prelim application) They HCC want to know how we will attach to the concrete pole without compromising the integ. 29.09.14 Chris Adams to call the HCC facilities manager and discuss. 1.10.14 Chris called. HCC is happy as long as we submit the PS1 and Calcs with the application. Chris / Ritchie to have this ready for Phil by Fri 10th Oct 15 Oct - PS1 has been sent to council RC and telco act notice to follow. Ben to discuss power connection with council. 28 Oct - CD on Circ FO ordered, power enquiry in RC to be lodged, Wgt electricity liaison reqd for power delivery - qoute recieved delivery issues to be resloved, 6 Jan power ordered, Fibre ordered, await installation qoute - resource confirmed by TSL. Delay with power conection has delayed installation. 16 Feb - Brackets to be fabricated. 6 March installation complete - requires SFP to finish TI | [10 empty] | 2015-04-17 |  | 2014-12-09 | LOW |  | 2015-02-04 | 2015-02-04 | BUILD |  | TRUE | 2014-12-19 | 2672092 | 6001212 | Outside 135 Major Dr Lower Hutt Wellington | Date Lease Issued is the date the Telco notice was sent. - 20/10/2014 - 22/10/2014 |  | CELLSITE |  |  |  | SMALL CELLS | [13 empty] | 2014-09-02
0 | WLG | 1613 | WLG-046-041 | Kelson Micro 2 | WLG-046-041-A | Kelson Microcell B | Lower Hutt City | 24 | 2015 | ACTIVE | RSR | MC | NOPOLE |  |  |  | 8 | 9.14 |  | -41.1743 | 174.937 |  | 2014-09-30 |  |  | Fibre Optic | WLG-046-006-B | FALSE | FALSE |  |  | FALSE |  | 2014-08-27 | 2014-08-27 | 2014-09-02 | 2014-09-02 | 2014-09-15 | 2014-09-19 | 1 | 2014-09-30 | 2014-09-19 | 2014-11-14 | 2014-10-29 | 2014-11-14 | 2014-10-29 | 1 |  | 2014-11-18 | DISCRETIONARY_RESTRICT | 2014-11-14 | 2014-11-13 | 2014-12-19 | 2014-12-05 | 1 |  | 2014-12-05 | 2014-12-05 | 2014-12-05 | 2015-01-16 | 2015-01-14 | 1 |  |  | 2015-01-14 | [5 empty] | 2015-03-02 | 2015-03-02 | 2015-03-06 | 2015-03-06 |  | 2015-04-09 | [10 empty] | 2015-04-17 | 2015-04-16 |  |  |  |  | Concrete lightpole. 1 MC unit required on Fibre. PD Rev 1 issued and forwarded to HCC. (Prelim application) They HCC want to know how we will attach to the concrete pole without compromising the integ. 29.09.14 Chris Adams to call the HCC facilities manager and discuss. 1.10.14 Chris called. HCC is happy as long as we submit the PS1 and Calcs with the application. Chris / Ritchie to have this ready for Phil by Fri 10th 15 Oct - PS1 has been sent to council RC and telco act notice to follow. Ben to discuss power connection with council. 28 Oct - CD on circ FO ordered, power enquiry in 11 Nov, RC to be lodged, Wgt electricity liaison reqd for power delivery. Qoute recieved delivery issues to be resloved. 6 Jan power ordered, Fibre ordered, await installation qoute - resource confirmed by TSL. Delay with power conection has delayed installation. 16 Feb Further Chorus FO delivery delays build 6 March installation complete - requires SFP to finish TI | [10 empty] | 2015-04-17 |  |  |  |  | 2015-04-16 | 2015-03-03 | BUILD |  | TRUE | 2014-12-19 | 2672504 | 6001799 | Ourside 214 Major Dr Lower Hutt Wellington | Date Lease Issued is the date the Telco notice was sent. - 20/10/2014 - 22/10/2014 |  | CELLSITE |  |  |  | SMALL CELLS | [13 empty] | 2014-09-02
0 | WLG | 1614 | WLG-047-001 |  | WLG-047-001-B | Wilton | Wellington City |  | TIER_1_ALL | ACTIVE | GF | A | P2 | grey |  |  | 18.8 | 18.8 |  | -41.26 | 174.7593 |  |  |  |  | Microwave | WLG-047-074-B | [7 empty] | 2008-02-15 |  |  |  | 2008-03-26 | 9 |  | 2009-11-16 |  |  | 2009-08-31 | 2009-09-04 | 7 | 2009-08-31 | 2009-10-13 |  |  |  | 2008-07-21 |  |  | 2009-05-30 | 2009-05-14 | 2009-06-15 | 2009-05-12 | 2009-09-15 | 2009-09-18 | 3 | 7 | 2009-09-15 | 2009-10-21 | 2009-03-23 |  |  |  |  | 2009-11-09 | 2009-11-09 | 2009-11-26 | 2009-11-24 |  | 2009-12-11 | 2009-12-15 | [8 empty] | 2009-12-18 | 2009-12-16 | 2009-12-18 |  |  |  |  | 9/2/09: Stuck site. Transpower? Copy of foundation agreement being sought. 25/2/09: Transpower option stuck. Now, to 1) investigate own option; 2) acquire rights to Woosh site; 3)Telecom co-lo 9/3/09: Woosh have agreed to investigate co-lo. Cherry picking to confirm height requirement. Still need foundation agreement with Transpower. Can't forecast - it's taken a year to get this far! 16/3/09: Need to access site for RF and TX to do detailed survey. Peter McKeefry to obtain access info. 23/3/09: Peter McKeefry to contact David Viviers, Transpower property manager, about getting access. Going back to square one and starting afresh. PMck to provide details of Woosh agreement. We need panoramics at at least two heights. 30/3/09: Struggling to get access. Could use Woosh to get access? 6/4/09: To cherry pick 8th April 09. Going on Woosh site. Our gear to go on Woosh location so need to ensure that they can go on our site. 16/4/09: Site identified as co-site with Woosh. To submit application. 20/4/09: Determined site location. LH to forward copies of the Woosh drawings to SS. Currently they have a 15m pole with them at the top. Now proposing a 20m pole. Will issue PDI once we know. Team to check pole location for current RMA works. JM to chase. 27/4/09: 2 x sets of drawings being produced. One set showng Woosh and ourselves for co-lo approval and one showing just us for RMA approval. Will submit for S127 asap whilst co-lo approval is sought. 5/5/09: PMcK to check if lease date can be brought forward. SS has issed drawings with and without Woosh. PMcK to complete co-lo form and submit with drawings to BR. SS waiting for a CDI. 12/5/09: Need to get engineering dept approval at Transpower before the property department will approve the lease. RMA need a S127 for climbing pegs. Co-siting form to go to Barbara. 18/5/09: Transpower going through internal approval process. They have requested more information. With Stefan. RMA complete. 26/5/09: PMcK needs some power details confirmed before being able to progress. 2/6/09: PDs being issued today. 8/6/09: Waiting for Transpower internal approvals. PMck to chase Transpower and Woosh. 15/6/09: Hopefully getting final Transpower docs this week. Lease being prepared. Long build time expected due to site on a power station. 22/6/09: Await return of lease. Taking an eon through Transpower.. JM to speak to Mana to see if we can put some pressure on. 9/7/09: Awaiting details on electrical and earthing system on Transpower land. 14/7/09: Transpower are preparing the doc for signing by Woosh and NZCL. All approved by Transpower. Will acquire and land bank. 21/7/09: Still not lease exchanged. Sheryll Gosnell at Transpower is dealing with this. 28/7/09: Legal docs with Auckland for NZC execution. Woosh to then execute. CDs this week. JM to check pole availability and type. Transpower site inductions required? 4/8/09: With Jess. Sublesase with Woosh to be agreed. 11/8/09: 2degrees legal have finished with the lease. Woosh approval required and then needing to get Transpower final approval. JM speak with Sheryl Gosnell ref preferred contractors/indcutions etc. Progress with Tower. 18/8/09: Lease terms agreed and should be able to be executed by Woosh. 25/8/09: Belinda talking to Woosh re: ownership rights of equipment being covered by side letter. Lease ready for execution. Woosh to sign first, then us. 1/9/09: Lease executed 31st August. JM to speak to Transpower-Sheryll Gosnell. 8/9/09: Lease signed. JM waiting for response from Transpower re: access protocols and inductions etc. Site type A allocated. 15/9/09: Woosh all complete. 2degrees already talking with Transpower re: inductions etc and access protocols. Power quote is awaited for independant supply. 22/9/09: Lease still not signed by Auckland. Waiting for induction date once legals have completed. 29/9/09:Can't build without induction which is being held up by legals. |  | 2009-12-16 |  |  |  |  | 2009-03-20 | 2009-03-23 | [11 empty] | FALSE |  | 2657404 | 5992596 | Transpower Wilton, End of Chartwell Dr, Crofton Downs, Wellington |  |  | CELLSITE | [7 empty] | 2009-10-05 | 2009-10-05 | [8 empty] | 2008-03-06
0 | WLG | 1615 | WLG-047-002 |  | WLG-047-002-C | Tawa | Wellington City |  | TIER_1_ALL | ACTIVE | RT | B | NOPOLE | grey |  |  | 16.8 | 16.8 |  | -41.1694 | 174.8253 |  |  |  |  | Microwave, Microwave, Leased Line | WLG-047-003-A, WLG-047-003-A, WLG-047-071-A | [5 empty] | 2007-08-30, 2007-08-30 | [5 empty] | 2008-01-29 | 1 |  | 2008-01-29 |  |  | 2008-05-31 | 2008-05-13 | 1 | 2008-05-31 | 2008-05-13 |  |  |  | 2008-03-11 |  |  | 2008-03-11 | 2008-03-11 |  | 2008-04-10 |  | 2008-06-30 | 2 | 1 | 2008-07-23 | 2008-07-23 | [6 empty] | 2008-08-06 | 2008-08-31 | 2008-08-31 |  | 2008-09-08 | 2008-09-08 | [8 empty] | 2008-12-24 | 2009-02-27 | 2008-12-24 |  |  |  |  | None |  | 2009-02-27 | [17 empty] | FALSE |  | 2663140 | 6002548 | 210-212 Main Road Tawa Wellington |  |  | CELLSITE | [8 empty] | 2008-07-01 | [8 empty] | 2007-12-05
0 | WLG | 1616 | WLG-047-003 |  | WLG-047-003-A | Grenada North | Wellington City |  | TIER_1_ALL | ACTIVE | GF | A | P2 | grey |  |  | 18.8 | 18.8 |  | -41.1817 | 174.83 |  |  |  |  | Microwave, Microwave | WLG-044-012-B, WLG-044-012-B | [5 empty] | 2008-08-12, 2008-09-08 | [5 empty] | 2008-01-16 | 5 | 2009-03-06 | 2009-03-26 |  |  | 2008-08-25 | 2008-08-20 |  | 2009-04-30 | 2009-04-21 |  |  |  | 2009-02-09 |  |  | 2009-02-09 | 2009-02-09 |  | 2009-03-02 |  | 2009-03-26 | 2 | 5 | 2009-04-01 | 2009-06-12 | 2009-04-21 |  |  |  |  | 2009-05-11 | 2009-05-13 | 2009-06-29 | 2009-06-29 |  | 2009-07-03 | 2009-07-01 | [8 empty] | 2009-07-07 | 2009-07-10 | 2009-07-07 |  |  |  |  | 25/2/09: Pole height being reduced. No RMA inpact. 9/3/09: Lease signed but not "All Site Acq Complete", awaiting co-site approval only. JM to check whether we can build without co-site approval. Now building 15m pole. CD forecast is good. 16/3/09: Await TNZ co-site approval. 19/3/09: Approval from Dawie de Vaal to build. 23/3/09: No Vodafone drawings. We have to show Vodafone site at Roger's request. CDs compelte apatr from this but can't issue until resolved. JM to confirm with DdV/JC/RB if we can continue. All Site Acq milestone to complete when we have the co-siting approvals. 30/3/09: Awaiting co-site. We've been requested to add details of VF pole to drawings but can't get any details. JM to email Barbara. Do the TSS and pre-build. 6/4/09: Awaiting TNZ co-site approval only. 16/4/09: Still await co-site approval. 20/4/09: Co-site approval is good. To TSS asap. 12/5/09: Started on site. 18/5/09: In build. Meeting with the Council at 4pm today. 26/5/09: Issue over pile foundation resolved. Drawings to be updated and sent to Council before meeting on site and discussing the works and new location. BB to meet processing planner on site at the same time. 29/6/09: Built. |  | 2009-07-10 |  |  |  |  | 2009-04-22 | 2009-04-21 | [11 empty] | FALSE |  | 2663508 | 6001172 | Water Tower 40 Gladys Scott Place (Entrance with gate) Wellington |  |  | CELLSITE | [7 empty] | 2009-05-11 | 2009-05-11 | [8 empty] | 2007-11-30
0 | WLG | 1617 | WLG-047-004 |  | WLG-047-004-A | Glenside | Wellington City |  | TIER_1_ALL | ACTIVE | RSR | A | P4B | green |  |  | 13 | 13 |  | -41.204 | 174.8205 |  |  |  |  | Leased Line | WLG-047-071-A | [11 empty] | 2007-12-20 | 4 |  | 2008-05-23 |  |  | 2009-02-19 | 2009-02-17 | 4 | 2009-03-30 | 2009-03-20 |  |  |  | 2009-02-17 |  |  | 2009-02-17 | 2009-02-17 |  | 2008-06-30 |  | 2008-06-28 | 1 | 4 | 2008-06-28 | 2008-06-28 | 2009-02-25 |  |  |  |  | 2009-05-15 | 2009-04-28 | 2009-05-30 | 2009-05-13 |  | 2009-06-05 | 2009-05-28 | [8 empty] | 2009-07-09 | 2009-07-10 | 2009-07-09 |  |  |  |  | 9/2/09: Lease with VM 9/3/09: JM to check why not all site acq complete in DB. Notice of prior approval required. To be confirmed by VM. 16/3/09: Notice of Prior Approval? 16/4/09: Awaiting Rueben from TA. 20/4/09: Now a May site due to late start date. 6/5/09: Make sure Rueben is given at least 10 days notice. 12/5/09: Pole stood, power to go on. |  | 2009-07-10 | [5 empty] | 2009-02-25 | [11 empty] | FALSE |  | 2662658 | 5998709 | Streetlight replacement Churton Park offramp Glenside Wellington |  |  | CELLSITE | [7 empty] | 2009-05-15 | 2009-04-14 | [8 empty] | 2007-11-21
0 | WLG | 1618 | WLG-047-005 |  | WLG-047-005-B | Churton Park | Wellington City |  | TIER_1_ALL | ACTIVE | RSR | A | P4B | green |  |  | 14.2 | 14.2 |  | -41.2095 | 174.8029 |  |  |  |  | Microwave, Microwave | WLG-047-074-B, WLG-047-074-B | [5 empty] | 2008-05-27, 2008-05-27 | [5 empty] | 2007-12-20 | 4 |  | 2008-04-04 |  |  | 2008-04-29 | 2008-04-29 | 2 | 2008-04-29 | 2008-04-29 |  |  |  | 2008-07-30 |  |  | 2008-07-30 | 2008-07-30 |  | 2008-04-10 |  | 2008-05-23 | 2 | 4 | 2008-08-12 | 2008-08-12 | [6 empty] | 2008-10-16 | 2008-10-25 | 2008-10-24 |  |  | 2008-10-24 | [8 empty] | 2008-12-15 | 2008-12-31 | 2008-12-15 |  |  |  |  | None |  | 2008-12-23 | [17 empty] | FALSE |  | 2661168 | 5998128 | 50 Abilene Crescent Churton Park Wellington |  |  | CELLSITE | [8 empty] | 2008-10-01 | [8 empty] | 2007-11-21
0 | WLG | 1619 | WLG-047-006 |  | WLG-047-006-G | Johnsonville | Wellington City |  | TIER_1_ALL | ACTIVE | RT | B | NOPOLE | green |  |  | 10.9 | 10.9 |  | -41.2229 | 174.8088 |  |  |  |  | Microwave, Microwave | WLG-047-074-B, WLG-047-074-B | FALSE | FALSE |  |  | FALSE | 2008-05-21, 2008-05-21 | [5 empty] | 2008-03-25 | 2 | 2009-03-06 | 2009-03-03 |  |  | 2008-06-30 | 2008-06-23 | 1 | 2008-06-30 | 2008-06-23 |  |  |  | 2008-06-12 |  |  | 2008-06-12 | 2008-06-12 |  | 2008-06-03 |  | 2008-07-23 | 2 | 1 | 2008-08-29 | 2008-08-29 | [6 empty] | 2008-09-01 | 2008-09-30 | 2008-09-29 |  | 2008-10-10 | 2008-10-10 | [8 empty] | 2008-12-11 | 2008-12-31 | 2008-12-11 |  |  |  |  | None |  | 2008-12-23 | [17 empty] | FALSE |  | 2661632 | 5996633 | 1 Norman Lane Johnsonville |  |  | CELLSITE |  |  | 2015-12-02 | [5 empty] | 2008-07-31 | [8 empty] | 2008-02-15
0 | WLG | 1620 | WLG-047-007 | Newlands Infill | WLG-047-007-C | Newlands | Wellington City |  | TIER_1_ALL | ACTIVE | RSR | A | P4B | grey |  |  | 13.8 | 13.8 |  | -41.2234 | 174.822 |  |  |  |  | Leased Line | WLG-047-071-A | [11 empty] | 2007-12-14 | 4 |  | 2008-09-11 |  |  | 2008-04-28 | 2008-04-28 | 1 | 2008-04-28 | 2008-04-28 |  |  |  | 2008-10-16 |  |  | 2008-10-16 | 2008-10-16 |  | 2008-05-05 |  | 2008-06-28 | 1 | 3 | 2008-06-28 | 2008-06-28 | [6 empty] | 2008-11-10 | 2008-11-28 | 2008-11-28 |  | 2008-11-26 | 2008-11-28 | [8 empty] | 2009-03-09 | 2009-06-26 | 2009-03-09 |  |  |  |  | 25/2/09: Awaiting leased line. |  | 2009-06-26 | [17 empty] | FALSE |  | 2662737 | 5996551 | The Inn Keeper pub 15 Batchelor street Paparangi Wellington |  |  | CELLSITE |  |  | 2015-12-02 | [5 empty] | 2008-11-11 | [8 empty] | 2007-11-30
0 | WLG | 1621 | WLG-047-008 |  |  |  | Wellington City |  | TIER_1_ALL
0 | WLG | 1622 | WLG-047-009 |  | WLG-047-009-A | Raroa | Wellington City |  | TIER_1_ALL | ACTIVE | GF | A | P1 | grey |  |  | 13.8 | 13.8 |  | -41.2348 | 174.8037 |  |  |  |  | Leased Line | WLG-047-071-A | [11 empty] | 2008-01-16 | 5 | 2009-03-20 | 2009-07-28 |  |  | 2008-07-31 | 2008-06-23 | 1 | 2008-07-31 | 2008-06-23 |  |  |  | 2008-08-19 |  |  | 2008-10-29 | 2008-10-29 |  | 2008-05-19 |  | 2008-10-21 | 1 | 2 | 2008-10-21 | 2008-10-21 | 2009-03-12 |  |  |  |  | 2009-03-10 | 2009-03-04 | 2009-04-20 | 2009-04-15 |  | 2009-04-23 | 2009-04-21 | [8 empty] | 2009-05-29 | 2009-05-29 | 2009-05-29 |  |  |  |  | 9/2/09: No problem with access. In build. 25/02/09: Some access difficulties re: health and safety, and induction. 9/3/09: In build. 19/3/09: Approval from Dawie de Vaal to build. 23/3/09: Pending co-site approval. 16/4/09: All good for April completion. 20/4/09: All complete pending power. |  | 2009-05-29 |  |  |  |  | 2009-03-13 | 2009-03-12 | [11 empty] | FALSE |  | 2661181 | 5995322 | Raroa Quarry Raroa Wellington (Access from the end of Plumer Street) |  |  | CELLSITE |  |  | 2015-12-02 | [5 empty] | 2009-01-16 | [8 empty] | 2007-12-05
0 | WLG | 1623 | WLG-047-012 | Ngauranga Gorge | WLG-047-012-E | Ngauranga Gorge | Wellington City |  | TIER_1_ALL | ACTIVE | GF | A | P3 | grey |  |  | 18.8 | 18.8 |  | -41.2477 | 174.814 |  |  |  |  | Leased Line | WLG-047-071-A | [11 empty] | 2008-03-17 | 8 | 2009-03-04 | 2015-09-07 |  |  | 2009-02-28 | 2009-02-17 | 3 | 2009-02-28 | 2009-02-17 | DISCRETIONARY_FULL |  | 2013-12-06 | 2008-12-08 | 2014-01-06 | 7 | 2008-12-08 | 2014-01-06 |  | 2008-12-08 |  | 2009-02-04 | 1 | 4 | 2009-02-04 | 2009-02-04 | 2009-03-13 |  |  |  |  | 2009-03-15 | 2009-03-13 | 2009-04-27 | 2009-04-17 |  | 2009-04-30 | 2009-04-17 | [8 empty] | 2009-05-13 | 2009-06-06 | 2009-05-13 |  |  |  |  | 9/2/09: with co-siting. 9/3/09: In build. 19/3/09: Approval from RF to build. 16/4/09: Concrete all in. Pole lift 16/4/09. All good for this month. |  | 2009-06-06 |  |  |  |  | 2009-03-13 | 2009-03-13 |  |  |  |  | 2014-01-07 | LOW | [5 empty] | FALSE |  | 2662013 | 5993867 | Between Hutt road and Wellington Urban Motorway Ngauranga |  | Resource Consent required for upgrade to site. - 07/01/2014 | CELLSITE |  |  | 2014-12-12 | [5 empty] | 2009-02-23 | [8 empty] | 2008-03-17
0 | WLG | 1624 | WLG-047-015 |  | WLG-047-015-D | Wadestown Village | Wellington City |  | TIER_1_ALL | ACTIVE | RT | B | NOPOLE | grey |  |  | 16 | 16 |  | -41.2619 | 174.7744 |  |  |  |  | Leased Line | WLG-047-071-A | [11 empty] | 2008-02-27 | 4 | 2009-03-20 | 2009-03-18 |  |  | 2008-04-08 | 2008-04-14 | 3 | 2008-04-08 | 2008-04-14 |  |  |  | 2008-07-25 |  |  | 2008-07-25 | 2008-07-25 |  | 2008-05-19 |  | 2008-09-08 | 3 | 3 | 2008-12-18 | 2008-12-18 | [6 empty] | 2008-10-15 | 2008-10-27 | 2008-10-24 |  | 2008-11-07 | 2008-11-03 | [8 empty] | 2009-03-03 | 2009-03-20 | 2009-03-03 |  |  |  |  | 25/2/09: Leased line install TBC. Site programme to be brought on air. |  | 2009-03-20 | [17 empty] | FALSE |  | 2658663 | 5992368 | Spectrum Gallery 102D Wadestown road Wadestown Wellington |  |  | CELLSITE | [8 empty] | 2008-09-09 | [8 empty] | 2008-02-07
0 | WLG | 1625 | WLG-047-016 |  | WLG-047-016-D | Kaiwharawhara | Wellington City |  | TIER_1_ALL | ACTIVE | GF | A | P1 | grey |  |  | 13.8 | 13.8 |  | -41.2577 | 174.7874 |  |  |  |  | Leased Line | WLG-047-071-A | [11 empty] | 2008-04-23 | 2 |  | 2008-09-18 |  |  | 2008-07-31 | 2008-07-10 | 1 | 2008-07-31 | 2008-07-10 |  |  |  | 2008-09-03 |  |  | 2008-10-23 | 2008-10-23 |  | 2008-07-22 |  | 2008-10-09 | 1 | 2 | 2008-10-09 | 2008-10-09 | [6 empty] | 2008-11-07 | 2008-11-28 | 2008-11-28 |  | 2008-12-12 | 2008-11-28 | [8 empty] | 2009-03-06 | 2009-03-06 | 2009-03-06 |  |  |  |  | 25/2/09: Awaiting leased line. |  | 2009-03-06 | [17 empty] | FALSE |  | 2659759 | 5992810 | 36 -54Kaiwharawhara Road, Kaiwharawhara, Wellington |  |  | CELLSITE | [8 empty] | 2008-10-30 | [8 empty] | 2008-03-17
0 | WLG | 1626 | WLG-047-018 |  | WLG-047-018-C | Northland | Wellington City |  | TIER_1_ALL | ACTIVE | RT | B | NOPOLE | grey |  |  | 7.2 | 7.2 |  | -41.2744 | 174.7589 |  |  |  |  | Leased Line | WLG-047-071-A | [11 empty] | 2008-03-05 | 5 |  | 2009-04-08 |  |  | 2008-05-27 | 2008-05-14 | 2 | 2009-05-10 | 2009-04-28 |  |  |  | 2008-07-18 |  |  | 2009-05-08 | 2008-07-18 |  | 2008-05-19 |  | 2008-09-18 | 3 | 5 | 2009-03-31 | 2009-05-20 | [5 empty] | 2009-04-16 | 2009-04-16 | 2009-04-29 | 2009-04-29 |  | 2009-06-11 | 2009-06-08 | [8 empty] | 2009-06-11 | 2009-06-18 | 2009-06-11 |  |  |  |  | 9/2/09: Revised scheme recently approved. New PDs required with permitted activity. Revised CDs required. Need to re-TSS. Bespoke pole required. 9/3/09: CDs to issue 10/3/09. In build. Still awaiting pricing for poles. 23/3/09: Pending co-site approval. redesign of site required for RF. Solution to be proposed to the landlord this week. If ok, full designs to be drawn. 30/3/09: PMcK to talk to landlord by Wed 1/4/09. Ss to issue draft of CDs. 6/4/09: Pending co-site approval from TNZ. Sector 1 needs to be reviewed by RF. To happen 8/4/09. 16/4/09: Started today. All going well. Awaiting co-site approval. 20/4/09: Seperate pole to be installed for sector 3. LL duct to go in. 27/4/09: Only co-site approval outstanding. 12/5/09: Leased line in. |  | 2009-06-18 | [17 empty] | FALSE |  | 2657334 | 5991000 | Pembroke Motors 2000 107 Pembroke Road Wilton Wellington |  |  | CELLSITE |  |  | 2015-11-26 | [5 empty] | 2009-02-23 | [8 empty] | 2008-02-26
0 | WLG | 1627 | WLG-047-019 |  | WLG-047-019-C | Kelburn | Wellington City |  | TIER_1_ALL | ACTIVE | GF | A | P1 | grey |  |  | 10.8 | 10.8 |  | -41.2894 | 174.762 |  |  |  |  | Leased Line | WLG-047-071-A | [11 empty] | 2008-11-26 | 2 | 2009-03-04 | 2009-03-03 |  |  |  | 2008-11-12 | 1 | 2009-03-31 | 2009-03-23 |  |  |  | 2009-01-15 |  |  | 2009-01-15 | 2009-01-15 |  | 2009-01-26 |  | 2009-02-09 | 1 | 1 | 2009-02-09 | 2009-02-09 | 2009-02-02 |  |  |  |  | 2009-04-01 | 2009-04-01 | 2009-04-30 | 2009-04-30 |  | 2009-05-04 | 2009-04-30 | [8 empty] | 2009-06-10 | 2009-06-12 | 2009-06-10 |  |  |  |  | 9/2/09: In build. Co-siting required. 25/02/09: NOT in-build. RTB pending co-site approval. 9/3/09: On hold awaiting co-site approval. 11/3/09: Off hold. 23/3/09: Pending co-site approval. 19/3/09: Approval from RF to build. 16/3/09: In build. 16/4/09: On course for April completion. 20/4/09: Still on course for civils completion in April. |  | 2009-06-12 |  |  |  |  | 2009-01-30 | 2009-02-02 | [11 empty] | FALSE |  | 2657563 | 5989327 | Kelburn Village, 87 Upland Rd, Kelburn, Wellington |  |  | CELLSITE |  |  | 2015-11-26 | [5 empty] | 2009-02-04 | [8 empty] | 2008-11-11
0 | WLG | 1628 | WLG-047-020 |  | WLG-047-020-D | Appleton Park | Wellington City |  | TIER_1_ALL | ACTIVE | RSR | A | P4B | green |  |  | 14.2 | 14.2 |  | -41.2868 | 174.7538 |  |  |  |  | Leased Line | WLG-047-071-A | [11 empty] | 2007-12-19 | 4 | 2009-03-13 | 2009-03-04 |  |  | 2008-04-29 | 2008-04-29 | 2 | 2008-04-29 | 2008-04-29 |  |  |  | 2008-08-28 |  |  | 2008-08-28 | 2008-08-28 |  | 2008-05-02 |  | 2008-08-14 | 1 | 3 | 2008-08-14 | 2008-08-14 | [6 empty] | 2008-10-09 | 2008-10-25 | 2008-10-23 |  |  | 2008-11-20 | [8 empty] | 2008-12-16 | 2008-12-31 | 2008-12-16 |  |  |  |  | None |  | 2008-12-31 | [17 empty] | FALSE |  | 2656883 | 5989629 | Appleton Park carpark Birdwood Street Karori Wellington |  |  | CELLSITE | [8 empty] | 2008-09-17 | [8 empty] | 2007-11-21
0 | WLG | 1629 | WLG-047-021 |  | WLG-047-021-J | Karori East | Wellington City |  | TIER_1_ALL | ACTIVE | GF | Ab | P2 | grey |  |  | 13.8 | 13.8 |  | -41.2825 | 174.7459 | [12 empty] | 2009-06-10 | 2009-06-10 |  |  | 2009-07-22 | 2009-07-22 | 2 | 2009-07-22 | 2009-09-07 |  |  | 2009-09-18 | 2009-09-18 | 2 | 2009-09-18 | 2009-09-18 |  | 2009-07-24 |  | 2009-09-30 |  |  | 2009-09-30 | 2009-09-14 | 2009-09-21 | 2009-09-08 | 2009-09-25 | 2009-10-05 | 1 | 2 | 2009-09-25 | 2009-10-05 | [5 empty] | 2009-10-19 | 2009-10-15 | 2009-11-10 | 2009-11-10 |  | 2009-11-29 | 2009-11-27 | [8 empty] | 2009-12-22 | 2009-12-18 | 2009-12-22 |  |  |  |  | 15/6/09: PMcK going to contact landlord today. Need to get access to do the designs. PDI to be issued today.TX to have upper slot on pole. Linking to Wilton and possibly Montgomery or Pembroke. Landlord deal still being negotiated. May need to replce his exisiting store room which will require building consent. 22/6/09: Draft drawings with landlord for approval. 29/6/09: Will drive once Montgomery is finished to check requirement for site. 9/7/09: Landlord difficult to deal with. 14/7/09: LL in hospital. Still chasing. Will acquire and land bank. 21/7/09: Still waiting for performance results from Montgomery Road. Numbers of dishes tbc. Suspect landlord is not 100%. Pete McK to meet with LH. 28/7/09: Landlord still undecided. PMcK and LH to visit 28/7/09. PMcK to offer increase to sweetener. Site feasibility to be determined before the end of this week. 11/8/09: LL wants to see drawings with garage. LL keeps changing his mind over pole location. 18/8/09: LL may not been that keen. VM looking at back-up at butchers on Gipp St. 25/8/09: Wanting to bring this site to a head. RMA will be in this month and we'll chase the landlord for a decision following that. VM working on feasibility of identified back up at Gipp St Butchers. before we push the landlord at the Four Square really hard. 1/9/09: PMcK and LH met with Dillip yesterday. All went well. Need to redesign-move pole and erect garage. JM and SS to meet with Dillip. 8/9/09: Have applied for a new CoC for revised pole location. PMcK to meet with LL today and put pressure on. Building consent needed for replacement garage. Site type Ab but indoors so not subject to consent issues. BACK UP is Gipp Street butchers. Caravan on Thursday. This is a rooftop site and will have greater flexibility for future linking. 15/9/09: RMA complete. Lease in good shape to complete this week. Tower to be found with climbing pegs. 2 dishes on the pole only. 22/9/09: Lease completed. Geotech still to complete. Works halted t due POs not being in place. Need to work across the storage issues. Landlord needs to shift a load of material into new temp storage and new garage to be sourced and installed by 2degrees. 29/9/09: Building consent has given preliminary approval for garage. CDs complete and to be issued. 6/10/09: In build. 27/10/09: Meeting to be arrange with Clarks. 10/11/09: Pole stood. |  | 2009-12-18 | [17 empty] | FALSE |  | 2656229 | 5990123 | 147 Karori Road Karori Wellington |  |  | CELLSITE |  |  | 2016-02-03 |  |  |  |  | 2009-10-15 | 2009-10-15 | [8 empty] | 2009-06-16
0 | WLG | 1630 | WLG-047-022 |  | WLG-047-022-A | Karori West | Wellington City |  | TIER_1_ALL | ACTIVE | GF | A | P2 | green |  |  | 10.8 | 10.8 |  | -41.2816 | 174.7315 | [13 empty] | 2007-12-10 |  |  |  | 2008-03-17 | 9 | 2008-12-12 | 2009-07-20 |  |  | 2008-06-24 | 2008-05-30 | 1 | 2009-06-30 | 2009-06-15 |  | 2009-03-13 |  | 2009-05-13 |  |  | 2009-05-13 | 2009-04-24 |  | 2008-05-19 |  | 2008-12-12 | 4 | 7 | 2009-03-15 | 2009-06-16 | 2009-04-21 |  |  |  |  | 2009-06-15 | 2009-06-15 | 2009-07-10 | 2009-07-07 |  | 2009-07-12 | 2009-07-14 | [8 empty] | 2009-07-14 | 2009-07-15 | 2009-07-14 |  |  |  |  | 9/2/09: Going with pole. S127 to be submitted. Awaiting LOS. 25/2/09: LOS confirmed to Mt Vic. Need to acquire rights to acquire dish higher up tower. 9/3/09: RMA need to re-lodge for new option. Lease requires a revised plan only. Need to get rights to an additional dish @ 22m for linking. 16/3/09: Awaiting co-site. 23/3/09: Await co-site approval. Drawings showing move of pole due to future Voda link to be issued this week. 30/3/09: VF have rejected the co-site again. Questions over the future RF and dish locations for VF. We cannot lose height. 6/4/09: Await co-siting approval . Waiting for feedback from VF. 16/4/09: Still awaiting co-site approval. LF attempting to meet on site. 20/4/09: VF co-site is causing problems.LH has offered an on-site meeting to clarify what VFs issues are. Build without co-site. 27/4/09: Co-siting for VF awaited. DdV has instructed to build. 5/5/09: Build. Chopper lift-notify residents. 12/5/09: Need to get confirmation from Council that they are happy with the revised proposal. 18/5/09: TSS and build. 26/5/09: Waiting for Council property to approve the new location. 8/6/09: Pole location has moved and revised drawings are with Council for approval. They are aware that this is number one priority. Contractors geared up to start. Difficult build. 15/6/09: In build. 29/6/09: In build 7/7/09: In build. |  | 2009-07-15 |  |  |  |  | 2009-04-22 | 2009-04-21 | [11 empty] | FALSE |  | 2655023 | 5990252 | Wellington Council land opposite 31 Montgomery Ave Karori Wellington |  |  | CELLSITE |  |  | 2016-02-03 |  |  |  |  | 2009-07-05 | 2009-06-15 | [8 empty] | 2008-02-07
0 | WLG | 1631 | WLG-047-023 |  | WLG-047-023-I | Brooklyn | Wellington City |  | TIER_1_ALL | ACTIVE | GF | A | P1 | grey |  |  | 13.8 | 13.8 |  | -41.3056 | 174.764 |  |  |  |  | Leased Line | WLG-047-071-A | [11 empty] | 2008-05-30 | 2 |  | 2008-10-01 |  |  | 2008-07-31 | 2008-06-23 | 1 | 2008-07-31 | 2008-06-23 |  |  |  | 2008-08-18 |  |  | 2008-10-23 | 2008-10-23 |  | 2008-07-16 |  | 2008-09-11 | 1 | 1 | 2008-09-11 | 2008-09-11 | 2009-02-16 | [5 empty] | 2008-11-03 | 2009-02-28 | 2009-02-27 |  | 2009-03-03 | 2009-03-03 | [8 empty] | 2009-04-06 | 2009-04-06 | 2009-04-06 |  |  |  |  | None |  | 2009-04-06 | [5 empty] | 2009-02-16 | [11 empty] | FALSE |  | 2657690 | 5987531 | 55-71 Cleveland Road Brooklyn Wellington |  |  | CELLSITE |  |  | 2015-11-26 | [5 empty] | 2008-09-18 | [8 empty] | 2008-04-24
0 | WLG | 1632 | WLG-047-024 |  | WLG-047-024-C | Owhiro Bay | Wellington City |  | TIER_1_ALL | ACTIVE | GF | A | P1 | grey |  |  | 10.8 | 10.8 |  | -41.3385 | 174.7561 |  |  |  |  | Leased Line | WLG-047-071-A | [11 empty] | 2008-02-09 | 4 |  | 2008-11-06 |  |  | 2008-08-15 | 2008-09-17 | 4 | 2008-08-15 | 2008-09-17 |  |  |  | 2008-11-27 |  |  | 2008-11-27 | 2008-11-27 |  | 2008-04-08 |  | 2009-02-25 | 1 | 4 | 2009-02-27 | 2009-02-25 | 2009-02-19 |  |  |  |  | 2009-03-20 | 2009-03-20 | 2009-04-29 | 2009-04-20 |  | 2009-05-08 | 2009-05-08 | [8 empty] | 2009-05-12 | 2009-05-14 | 2009-05-12 |  |  |  |  | 25/02/09: Difficult hill top build. 9/3/09: In build. 16/3/09: Awaiting co-site. 16/4/09: Looking good. TI lift with chopper Thurs or Fri. All ok. |  | 2009-05-14 | [5 empty] | 2009-02-19 | [11 empty] | FALSE |  | 2656955 | 5983886 | about 167(a) Happy Valley Rd, Island Bay Wellington |  |  | CELLSITE |  |  | 2015-11-26 | [5 empty] | 2009-02-04 | [8 empty] | 2007-11-16
0 | WLG | 1633 | WLG-047-025 |  | WLG-047-025-A | Berhampore | Wellington City |  | TIER_1_ALL | ACTIVE | RT | B | NOPOLE | grey |  |  | 15 | 15 |  | -41.3245 | 174.7762 | [12 empty] | 2009-05-06 | 2009-05-06 |  |  | 2009-05-20 | 2009-05-22 | 3 | 2009-05-20 | 2009-08-24 |  |  | 2010-02-15 | 2010-02-22 |  | 2010-02-15 |  |  | 2009-08-17 |  | 2009-09-24 |  |  | 2009-09-24 | 2009-09-14 | 2009-06-30 | 2009-06-09 | 2009-08-14 | 2009-07-31 | 2 | 3 | 2009-09-15 | 2009-09-02 | [5 empty] | 2010-03-16 | 2010-04-19 | 2010-04-30 | 2010-04-29 |  | 2010-05-07 | 2010-05-04 | [8 empty] | 2010-05-04 | 2010-05-07 | 2010-05-04 |  |  |  |  | 27/4/09: Council property being consulted as to whether they will accept a site here. This is preferred by NZC and council to the Adelaide road GF candidate. 5/5/09: Site visit tomorrow to measure up. RMA dependant on lease approval. 12/5/09: Just waiting for PDs. RMA dependant on lease. 18/5/09: PDI issued. Waiting for drawings. LH checking height of antennas. Vodafone co-site. 26/5/09: Housing still to determine if OK. 2/6/09: Still waiting for feedback from Council. 8/6/09: Rooftop site previously discounted by Council but now possibly a go-er. 15/6/09: Housing still reviewing RF info provided by NZC. Housing approval required before we can progress. 22/6/09: Housing manager still reviewing the RF information provided. 29/6/09: Priority site with regional RF to cover Island Bay. 9/6/09: Dejan is chasing. Now need iwi approval as part of RMA process. This follows the lease approval. 14/7/09: Granville Flats is going no where and council aren't responding to requests for progress or information. Still with their Asset Manager to determine if we can go ahead. Team determining whether we can resurrect and progress teh Adelaide Road Greenfield site if only to perhaps give Granville a kick. 21/7/09: JM meeting with Council tomorrow. Granville Flats is still preferred. RMA lodged lightpole at 15m with lease complete. JM to talk to Belinda re: Peter revisiting Island Bay option with increased rental. 28/7/09: Vm chasing. Council cancelled meeting with JM last week. Dejan now not available. JM to discuss progress of flats and Island Bay plan. Dejan from Council off on holiday until 3rd. Deadline set to 7th August for feedback. 18/8/09: Meeting today between Council Management. 1/9/09: Lease doc to go to Joelyn ASAP. Council timescale awaited. Council to advise if we can do lease and RMA in parallel. COW-PMcK talking to Anglican church. Known to be telecoms favourable. 8/9/09: Lease with Joelyn for signing. 10ths Trust approval required for lease and RMA, as head lessor. Mana Forbes well connected with the Trust. Team to ask Mana to give whatever assistance he can. Re: COW - Possible location identified. With Church for approval at meeting tonight. Vicar is onside. JM to check the drawings for linking as we need 15m minimum for height of dish. BB to speak with Council to determine RMA requirement. Possible leased line. RF require min of 12m if leased line. 15/9/09: Lease has had legal review before sending to Council. RMA received. 22/9/09: Lease with Auckland for signing. 6/10/09: All on course for dates specified. 13/10/09: 2 x small errors in licence being completed. 20/10/09: Council to sign lease and forward to Tenths Trust. 27/10/09: Date all good. 3/11/09: Licence signed, with Tenths Trust. 10/11/09: With 10th Trust. 10ths Trust unhelpful. 17/11/09: JM to speak with Tim and Jess. 24/11/09: Council gone quiet... 1/12/09: Out of acquisition this week. 15/12/09: Council to speak to VM today. Tenths trust name to be added to licence. |  | 2010-05-07 | [17 empty] | FALSE |  | 2658672 | 5985407 | Granville Flats 557-559 Adelaide Rd Wellington |  |  | CELLSITE |  |  | 2015-11-26 |  |  |  |  | 2010-03-09 | 2010-04-19 | [8 empty] | 2009-05-06
0 | WLG | 1634 | WLG-047-026 |  | WLG-047-026-B | Island Bay | Wellington City |  | TIER_1_ALL | ACTIVE | COLO | Ab | COLO | Grey |  | COLO |  |  |  | -41.3342 | 174.7738 | [12 empty] | 2009-08-20 | 2009-08-20 |  |  |  | 2008-03-04 | 2 | 2009-09-25 | 2009-09-24 |  |  | 2010-02-16 | 2010-04-16 | 1 | 2010-06-30 | 2010-06-30 |  | 2009-09-04 |  | 2009-10-14 |  |  | 2009-10-14 | 2009-10-07 | 2010-06-17 | 2009-09-15 |  | 2009-10-27 | 2 | 2 | 2009-10-24 | 2009-09-02 | [5 empty] | 2010-08-06 | 2010-08-06 | 2010-09-03 | 2010-08-29 |  | 2010-09-05 | 2010-09-06 | [8 empty] | 2010-09-08 | 2010-09-08 | 2010-09-09 |  |  |  |  | 11/8/09: Lease to be reviewed and confirmation required from site acquisition if LL with deal. Original RC cancelled and in historic area so will need to confirm Councils opinion on this. LH to cherry pick to confirm requirements. TX to attend. PMcK to kick off lease negotiations. JD to investigate use of Boffa Miskell. Once cherry picked and we have Council opinion on Granville flats we can determine use of existing pole or extension/swap out. 18/8/09: Cherry picked yesterday. Height required for antenna is 17.5m to top of sectors. Woosh are at 15 to top of antenna. Dishes can go below Woosh sectors. NUmber of dishes to be confirmed. RMA team have asked for comments from Heritage 25/8/09: Chasing Woosh for confirmation of whether we can share their pole and take some of their equipment rights. LL OK. Heritage are OK with our sectors above Woosh. Need to chase BR. 8/9/09: LH to discuss with JC. Island Bay reactivated because of the possibility of losing Granville Flats. The Flats is now proceeding. Need to acquire this site, but landbank for tier 2. On site space is very limited and no ro0om for Ab typ configurations. Cabinet relocation requested by the landlord, so space more confined. Need site type A but will verify with a further site visit. 15/9/09: Lease in good shape. Revised PD required for new cab location at LL request. Site type Ab. PDs due before the 18th. Independant supply. Power quote to be sourced. PMcK doing the lease for the cabinets, BR doing the Woosh agreement. 22/9/09: To be redesigned to allow for RRUs to be closer to the pole. No impact on RMA, although PMcK will have to confirm with Landlord. Woosh approval also required. 29/9/09: Lease with Landlord. 6/10/09: Docs with landlord. PMcK to chase. 13/10/09: With landlord's wife to sign. PMcK to collect today. 20/10/09: Lease with Auckland. LL has signed. Waiting for Auckland execution. 27/10/09: Lease signed by LL for cabinets. Woosh now want top slot. 3/11/09: Lease for cabs with Jess. Barbara to say N to Woosh. Boundary survey required. 10/11/09: Woosh co-lo issues. Await site acquisition. 17/11/09: DO NO BUILD. Matt Daly is acquisition consultaant for Woosh. Boundary survey required. 1/12/09: Can now build. Awaiting Woosh lease. 8/12/09: PMcK lease complete. Await Woosh lease. Barbara Richardson chasing. 15/12/09: Barbara Richardson-Woosh. | WO | 2010-09-08 | [17 empty] | FALSE |  | 2658452 | 5984334 | Island Bay Butcher 127 THE PARADE, Island Bay |  |  | CELLSITE |  |  | 2015-11-27 |  |  |  |  | 2010-06-30 | 2010-07-30 | [8 empty] | 2008-02-07
0 | WLG | 1635 | WLG-047-027 |  | WLG-047-027-C | Wadestown East | Wellington City |  | TIER_1_ALL | ACTIVE | RSR | A | P4B | green |  |  | 11.2 | 11.2 |  | -41.2625 | 174.777 |  |  |  |  | Leased Line | WLG-047-071-A | [11 empty] | 2008-09-12 | 2 |  | 2009-03-17 |  |  | 2009-02-15 | 2008-12-04 | 1 | 2009-03-30 | 2009-03-20 |  |  |  | 2009-01-22 |  |  | 2009-01-22 | 2009-01-22 |  | 2008-10-07 |  | 2008-11-14 | 2 | 2 | 2009-05-06 | 2009-04-30 | [5 empty] | 2009-05-22 | 2009-05-18 | 2009-06-05 | 2009-05-28 |  | 2009-06-12 | 2009-06-01 | [8 empty] | 2009-06-11 | 2009-06-12 | 2009-06-11 |  |  |  |  | 1 Please be aware that this site may change to under NES, pole ordered type 4B but may change to 4C, CD not coming out yet. CD Rev 1 still showing type 4B pole.-Helen 9/2/09: No NES implications. 9/3/09: VM to confirm if notice of prior approval required. 16/3/09: Notice of Prior Approval? 18/3/09: Have been advised ETA for pole is 8/5/09. 12/5/09: NOPA quite stringent with requirements. Extg overhead cables to be removed before works start. |  | 2009-06-12 |  |  |  |  | 2009-04-22 | [12 empty] | FALSE |  | 2658877 | 5992292 | Cnr of Lennel Rd and Moorhouse St, Wadestown, Wellington |  |  | CELLSITE | [7 empty] | 2009-04-27 | 2009-05-13 | [8 empty] | 2008-07-28
0 | WLG | 1636 | WLG-047-028 |  | WLG-047-028-H | Hataitai | Wellington City |  | TIER_1_ALL | ACTIVE | GF | A6 | P2 | grey |  |  | 16.8 | 16.8 |  | -41.3049 | 174.7933 | [13 empty] | 2009-06-10 |  |  | 2009-06-11 | 2009-06-11 | 2 | 2009-06-11 | 2009-06-18 |  |  | 2009-06-18 | 2009-06-26 | 2 | 2009-06-25 | 2009-06-26 |  | 2009-06-11 |  | 2009-07-11 |  |  | 2009-07-11 | 2009-06-26 | 2009-06-09 | 2009-06-09 | 2009-06-30 | 2009-06-29 | 1 | 1 | 2009-06-30 | 2009-06-29 | [5 empty] | 2009-07-08 | 2009-07-03 | 2009-07-31 | 2009-07-22 |  | 2009-08-03 | 2009-07-28 | [8 empty] | 2009-07-28 | 2009-08-07 | 2009-07-28 |  |  |  |  | 8/6/09: No early access template. Landlord OK. JM to advance build and check with DdV/NT. 15/6/09: Change to drawings requested by landlord. 22/6/09: Lease is agreed and being sent to Auckland. RMA on course or earlier. Could start ground works. Deactivate the service road option (WLG-047-028-G) 29/6/09: In build. 14/7/09: In build. 21/7/09: Acquired and in build. |  | 2009-08-06 | [17 empty] | FALSE |  | 2660147 | 5987555 | Parsons and Associates Electrical1976 Limited 28 Moxham Avenue Haitaitai Wellington |  |  | CELLSITE |  |  | 2014-09-01 |  |  |  |  | 2009-07-15 | 2009-07-01 | [8 empty] | 2009-06-09
0 | WLG | 1637 | WLG-047-029 |  | WLG-047-029-D | Kilbirnie | Wellington City |  | TIER_1_ALL | ACTIVE | GF | A6 | P2 | grey |  |  | 13.8 | 13.8 |  | -41.3204 | 174.7945 |  |  |  |  | Microwave, Microwave | WLG-047-069-A, WLG-047-069-A | [5 empty] | 2008-11-18, 2008-11-18 | [5 empty] | 2008-07-22 | 3 |  | 2015-09-03 |  |  | 2008-08-31 | 2008-08-19 | 1 | 2008-08-31 | 2008-08-19 |  |  |  | 2008-11-06 |  |  | 2008-11-06 | 2008-11-06 |  | 2008-08-27 |  | 2008-11-28 | 1 | 2 | 2008-11-28 | 2008-11-28 | 2009-02-02 | [5 empty] | 2009-01-13 | 2009-02-28 | 2009-02-25 |  | 2009-03-03 | 2009-03-04 | [8 empty] | 2009-03-20 | 2009-03-23 | 2009-03-20 |  |  |  |  | 23/2/09: Power available |  | 2009-03-23 |  |  |  |  | 2009-01-28 | 2009-02-02 | [11 empty] | FALSE |  | 2660213 | 5985828 | 16 Coutts Street, Kilbirnie, Wellington |  |  | CELLSITE |  |  | 2014-09-01 | [5 empty] | 2008-12-08 | [8 empty] | 2008-06-12
0 | WLG | 1638 | WLG-047-030 |  | WLG-047-030-D | Wellington Airport | Wellington City |  | TIER_1_ALL | ACTIVE | GF | A6 | P2 | grey |  |  | 18.8 | 18.8 |  | -41.3292 | 174.8134 |  |  |  |  | Microwave, Microwave | WLG-047-069-A, WLG-047-069-A | [5 empty] | 2008-05-22, 2008-05-22 | [5 empty] | 2008-02-27 | 2 |  | 2008-09-23 |  |  | 2008-03-12 | 2008-03-12 | 2 | 2008-03-12 | 2008-03-12 |  |  |  | 2008-06-05 |  |  | 2008-10-10 | 2008-10-10 |  | 2008-04-08 |  | 2008-05-16 | 1 | 2 | 2008-05-16 | 2008-05-16 | [6 empty] | 2008-06-13 | 2008-07-04 | 2008-06-27 |  |  | 2008-07-04 | [8 empty] | 2008-09-24 |  | 2008-09-24 |  |  |  |  | None | [19 empty] | FALSE |  | 2661776 | 5984819 | Located on Golf Course Wall 1 Stewart Duff Drive Miramar Wellington |  |  | CELLSITE |  |  | 2014-09-01 | [5 empty] | 2008-06-06 | [8 empty] | 2008-02-08
0 | WLG | 1639 | WLG-047-031 | Seatoun | WLG-047-031-J | Seatoun Park | Wellington City | 7 | TIER_1_INFILL | ACTIVE | RSR | DU | P4F | green | INLINE | STANDALONE | 14.75 | 15.25 | 1 | -41.3249 | 174.8334 |  |  |  |  | Leased Line | WLG-047-071-A | FALSE | FALSE |  |  | FALSE |  |  | 2010-01-01 | 2010-08-11 | 2010-08-11 | 2010-08-15 | 2010-08-15 | 2 | 2010-11-08 | 2010-11-08 |  | 2011-03-12 | 2010-08-06 | 2011-03-12 |  | 2010-08-27 | 2012-06-25 | PERMITTED | 2010-11-08 | 2010-11-08 | 2010-09-09 | 2010-12-08 | 2 | 2010-09-13 | 2010-12-08 |  |  | 2011-03-23 | 2011-04-21 | 1 |  |  | 2011-04-21 | 2011-05-09 |  |  |  |  | 2011-05-13 | 2011-05-06 | 2011-05-16 | 2011-05-25 | 2011-07-07 | 2011-07-22 | 2011-07-18 | [8 empty] | 2011-09-29 | 2011-10-04 | 2011-10-07 | 2011-08-31 | 2011-11-01 | 2012-01-30 | 2012-07-03 | 25/2/09: Leased line install to be confirmed and programme brought on air. 08/09/11 : PAD recieved into 2Degrees by Ron B 12.06.2014 : "D" configuration build. (APM, Battery, & 2 x RFC) using version "B" cabinets. Thus making it a "DU" Site. (As per Ron Bush/blr) |  | 2011-08-07 |  | 2011-03-02 | 2011-06-06 | 2011-07-18 | 2010-10-15 | 2011-05-09 | 2011-07-06 | 2011-07-07 |  | 2011-11-01 | [7 empty] | FALSE |  | 2663462 | 5985267 | Floodlight on Seatoun Park, off Monro St Seatoun Wellington |  | NES Complying floolight replacement in Road reserve - 03/08/2010 Mail drop to 39 houses around park - 26/10/10. - 26/10/2010 | CELLSITE | [15 empty] | 2011-06-29 | 2011-09-07
0 | WLG | 1640 | WLG-047-032 |  | WLG-047-032-F | Miramar | Wellington City |  | TIER_1_ALL | ACTIVE | GF | A | P2 | grey |  |  | 13.8 | 13.8 |  | -41.3103 | 174.822 | [17 empty] | 2008-12-10 | 1 | 2008-12-12 | 2008-12-10 |  |  |  | 2008-11-13 |  | 2008-11-13 | 2008-11-13 |  |  |  | 2009-02-03 |  |  | 2009-02-03 | 2009-02-03 |  | 2009-01-26 |  | 2009-02-16 | 1 | 1 | 2009-02-16 | 2009-02-16 | 2009-02-02 |  |  |  |  | 2009-03-05 | 2009-03-06 | 2009-04-06 | 2009-04-03 |  | 2009-04-06 | 2009-04-03 | [8 empty] | 2009-04-27 | 2009-04-24 | 2009-04-27 |  |  |  |  | 9/2/09: CDs to be issued w/c 9/2/09. TSS. 9/3/09: In build. 19/3/09: RF approval to build. |  | 2009-04-24 | [5 empty] | 2009-02-02 | [11 empty] | FALSE |  | 2662540 | 5986911 | 126 Park Road Miramar Wellington |  |  | CELLSITE | [7 empty] | 2009-02-16 | 2009-02-23 | [8 empty] | 2008-12-01
0 | WLG | 1641 | WLG-047-033 |  | WLG-047-033-A | Shark Bay | Wellington City |  | TIER_1_ALL | ACTIVE | GF | A | P2 | green |  |  | 15 | 15 |  | -41.2988 | 174.8201 |  |  |  |  | Microwave, Microwave | WLG-047-069-A, WLG-047-069-A | [5 empty] | 2008-05-22, 2008-08-13 | [5 empty] | 2007-09-21 | 4 | 2009-01-08 | 2009-01-08 |  |  | 2008-09-15 | 2008-08-28 | 2 | 2008-09-15 | 2008-08-28 |  |  |  | 2008-09-11 |  |  | 2008-11-09 | 2008-11-09 |  | 2008-05-08 |  | 2008-11-17 | 1 | 3 | 2008-11-17 | 2008-11-17 | 2009-02-02 | [5 empty] | 2008-12-08 | 2009-02-27 | 2009-02-23 |  | 2009-03-12 | 2009-03-04 | [8 empty] | 2009-03-10 | 2009-03-12 | 2009-03-10 |  |  |  |  | 9/2/09: In build. S127 approved. Power consent still o/s. |  | 2009-03-12 |  |  |  |  | 2009-01-21 | 2009-02-02 | [11 empty] | FALSE |  | 2662405 | 5988186 | Clearing just past TNZ site, Shelly Bay road Shark Bay Wellington |  |  | CELLSITE | [8 empty] | 2008-12-08 | [8 empty] | 2007-08-23
0 | WLG | 1642 | WLG-047-034 |  | WLG-047-034-F | Pipitea | Wellington City |  | TIER_1_ALL | ACTIVE | RT | B6 | NOPOLE | grey |  |  | 20.2 | 20.2 |  | -41.2648 | 174.7838 | [17 empty] | 2009-02-09 | 1 |  | 2009-02-09 |  |  | 2009-01-15 | 2009-01-13 |  | 2009-01-15 | 2009-01-13 |  |  |  | 2009-03-31 |  |  | 2009-03-31 | 2009-03-10 |  | 2009-02-24 |  | 2009-05-07 | 1 | 1 | 2009-05-07 | 2009-05-07 | [5 empty] | 2009-05-25 | 2009-05-25 | 2009-06-18 | 2009-05-28 |  | 2009-06-25 | 2009-06-12 | [8 empty] | 2009-06-18 | 2009-06-30 | 2009-06-18 |  |  |  |  | 9/2/09: CDs ready to issue w/c 9/2/09 9/3/09: TSS 20/4/09: CDs to issue this week. 12/5/09: TSSd. |  | 2009-06-30 | [17 empty] | FALSE |  | 2659447 | 5992021 | 71 Hutt Road Pipitea Wellington |  |  | CELLSITE |  |  | 2014-09-01 |  |  |  |  | 2009-05-15 | 2009-05-12 | [8 empty] | 2008-11-27
0 | WLG | 1643 | WLG-047-035 |  |  |  | Wellington City |  | TIER_1_ALL
0 | WLG | 1644 | WLG-047-036 |  | WLG-047-036-A | Thorndon North | Wellington City |  | TIER_1_ALL | ACTIVE | RT | B6 | NOPOLE | grey |  |  | 35.5 | 35.5 |  | -41.2728 | 174.7823 |  |  |  |  | Microwave, Microwave | WLG-047-037-A, WLG-047-037-A | [5 empty] | 2008-02-12, 2008-02-12 | [5 empty] | 2008-02-16 | 2 | 2009-03-20 | 2009-03-18 |  |  | 2008-03-27 | 2008-03-27 | 1 | 2008-03-27 | 2008-03-27 |  |  |  | 2008-04-17 |  |  | 2008-04-17 | 2008-04-17 |  | 2008-04-09 |  | 2008-06-10 | 1 | 2 | 2008-06-10 | 2008-06-10 | [6 empty] | 2008-07-14 | 2008-07-31 | 2008-07-31 |  | 2008-08-14 | 2008-08-15 | [8 empty] | 2008-12-18 | 2008-12-19 | 2008-12-18 |  |  |  |  | None |  | 2008-12-05 | [17 empty] | FALSE |  | 2659297 | 5991140 | 202 Thorndon Quay Wellington |  |  | CELLSITE |  |  | 2014-09-01 | [5 empty] | 2008-06-11 | [8 empty] | 2007-12-07
0 | WLG | 1645 | WLG-047-037 |  | WLG-047-037-A | Thorndon | Wellington City | 7 | TIER_1_ALL | ACTIVE | RT | B6 | NOPOLE | grey |  |  | 47.5 | 47.5 |  | -41.2748 | 174.7791 |  |  |  |  | Fibre Optic, Fibre Optic | WLG-047-071-A, WLG-047-071-A | FALSE | FALSE |  |  | FALSE | 2008-06-09, 2008-06-09 | [5 empty] | 2007-08-17 | 3 | 2011-06-30 | 2012-02-08 |  |  | 2007-11-21 | 2007-11-21 | 1 | 2011-07-04 | 2011-07-04 |  |  | 2011-07-04 | 2008-02-28 | 2011-07-04 | 2 | 2011-07-04 | 2011-07-04 |  | 2008-02-11 |  | 2008-04-30 | 3 | 2 | 2008-08-21 | 2008-08-21 | [6 empty] | 2008-05-15 | 2008-05-30 | 2008-05-30 |  | 2008-06-06 | 2008-06-06 | [8 empty] | 2008-11-27 | 2008-12-31 | 2008-11-27 |  |  |  |  | None. NOTE - BBU 3806 SWAPPED OUT FOR NEW 3900 UNITS 20/03/2013. | [19 empty] | FALSE |  | 2659030 | 5990925 | AT & T 15-17 Murphy Street Wellington |  |  | CELLSITE |  |  | 2014-09-01 | [5 empty] | 2008-05-01 | [8 empty] | 2007-07-23
0 | WLG | 1646 | WLG-047-038 |  | WLG-047-038-C | Lambton Quay North | Wellington City |  | TIER_1_ALL | ACTIVE | RT | B6 | NOPOLE | grey |  |  | 48.6 | 48.6 |  | -41.2803 | 174.7762 |  |  |  |  | Microwave, Microwave | WLG-047-040-A, WLG-047-040-A | [5 empty] | 2008-06-09, 2008-06-09 | [5 empty] | 2007-11-30 | 1 |  | 2007-11-30 |  |  | 2008-02-20 | 2008-02-20 | 1 | 2008-02-20 | 2008-02-20 |  |  |  | 2008-03-11 |  |  | 2008-03-11 | 2008-03-11 |  | 2008-02-11 |  | 2008-04-30 | 2 | 1 | 2008-05-08 | 2008-05-08 | [6 empty] | 2008-06-03 | 2008-06-30 | 2008-06-27 |  | 2008-08-22 | 2008-08-27 | [8 empty] | 2008-12-05 | 2008-12-20 | 2008-12-05 |  |  |  |  | None Note - BBU 3806 SWAPPED OUT FOR 3900 ON 17/10/12. F3 Dual RRU installed 4/13. |  | 2008-12-06 | [17 empty] | FALSE |  | 2658775 | 5990319 | 101 Lambton Quay, Wellington CBD, Wellington |  |  | CELLSITE |  |  | 2014-09-01 | [5 empty] | 2008-05-01 | [8 empty] | 2007-10-18
0 | WLG | 1647 | WLG-047-039 | Westpac Stadium 1 | WLG-047-039-G | Stadium In Building Solution | Wellington City | 6 | TIER_1_INFILL | ACTIVE | BO | D6 | RT | grey | STACK_A | COSITE | 26.8 | 27.3 | 1 | -41.2741 | 174.7857 |  |  |  |  | Microwave | WLG-047-037-A | FALSE | FALSE |  |  | FALSE |  | 2011-03-25 | 2011-03-24 | 2011-04-20 | 2011-04-27 | 2011-05-17 | 2011-05-17 | 1 | 2011-05-17 | 2011-05-17 |  | 2011-06-03 | 2011-06-28 | 2011-06-23 | 1 |  | 2011-07-01 | PERMITTED | 2011-05-24 | 2011-05-24 | 2011-07-06 | 2011-07-04 | 1 |  | 2011-07-04 |  |  | 2011-06-03 | 2011-06-10 | 1 |  | 2011-07-07 | 2011-06-10 | 2011-07-18 |  |  |  |  | 2011-06-21 | 2011-07-01 | 2011-07-21 | 2011-07-14 | 2011-07-14 | 2011-07-20 | 2011-08-19 | [8 empty] | 2011-08-19 | 2011-08-30 | 2011-08-30 | 2011-09-21 | 2011-10-31 | 2012-01-30 | 2012-06-29 | 07/09/11 : PAD documents submitted and received by Ron Bush- but rejected by Ian. Resubmitted with copy of PAN and HSQR on 13/9. confirmed D cabinet config. |  | 2011-07-27 |  | 2011-07-06 | 2011-08-05 | 2011-07-18 |  | 2011-07-18 | 2011-07-22 | 2011-08-19 | [9 empty] | FALSE |  | 2659583 | 5990994 | 147 Waterloo Quay Wellington 6011 |  | within a hazard area and ground shaking area - 27/04/2011 | CELLSITE |  |  | 2014-09-01 | [12 empty] | 2011-08-11 | 2011-09-07
0 | WLG | 1648 | WLG-047-040 |  | WLG-047-040-A | Terrace West | Wellington City | 7 | TIER_1_ALL | ACTIVE | RT | B6 | NOPOLE | grey |  |  | 75 | 75 |  | -41.2805 | 174.775 |  |  |  |  | Microwave, Microwave | WLG-047-071-A, WLG-047-071-A | FALSE | FALSE |  |  | FALSE | 2008-05-22, 2008-05-22 | [5 empty] | 2008-01-29 | 2 | 2011-08-12 | 2011-12-02 |  |  | 2008-05-31 | 2008-05-30 | 1 | 2012-05-04 | 2012-05-07 |  |  | 2011-08-05 | 2008-05-19 | 2011-08-05 | 2 | 2011-08-05 | 2011-08-05 |  | 2008-04-10 |  | 2008-06-11 | 3 |  | 2008-06-11 | 2012-03-20 | [6 empty] | 2008-07-12 | 2008-08-29 | 2008-08-19 |  | 2008-08-29 | 2008-09-01 | [8 empty] | 2008-12-02 | 2008-12-20 | 2008-12-02 |  |  |  |  | None |  | 2008-12-06 | [17 empty] | FALSE |  | 2658670 | 5990294 | Unisys Tower 54-68 The Terrace Wellington |  |  | CELLSITE |  |  | 2014-09-01 | [5 empty] | 2008-06-12 | [8 empty] | 2007-07-20
0 | WLG | 1649 | WLG-047-041 |  | WLG-047-041-C | Featherston St | Wellington City |  | TIER_1_ALL | ACTIVE | RT | B6 | NOPOLE | grey |  |  | 35.8 | 35.8 |  | -41.2818 | 174.7776 |  |  |  |  | Microwave, Microwave | WLG-047-038-C, WLG-047-038-C | [5 empty] | 2008-06-09, 2008-06-09 | [5 empty] | 2007-11-06 | 1 |  | 2007-11-06 |  |  | 2008-04-30 | 2008-04-30 | 1 | 2008-04-30 | 2008-04-30 |  |  |  | 2008-05-07 |  |  | 2008-05-07 | 2008-05-07 |  | 2008-02-12 |  | 2008-04-30 | 2 | 1 | 2008-06-10 | 2008-06-10 | [6 empty] | 2008-07-10 | 2008-08-15 | 2008-08-15 |  | 2008-08-29 | 2008-08-19 | [8 empty] | 2008-12-04 | 2008-12-20 | 2008-12-04 |  |  |  |  | None. NOTE - BBU 3806 SWAPPED FOR NEW 3900 UNITS 20/03/2013. |  | 2008-12-06 | [17 empty] | FALSE |  | 2658886 | 5990153 | ACC House 110 Featherston Street Wellington |  |  | CELLSITE |  |  | 2014-09-01 | [5 empty] | 2008-05-08 | [8 empty] | 2007-08-20
0 | WLG | 1650 | WLG-047-042 |  |  |  | Wellington City |  | TIER_1_ALL
0 | WLG | 1651 | WLG-047-043 |  | WLG-047-043-G | Lambton Quay | Wellington City |  | TIER_1_ALL | ACTIVE | RT | B6 | NOPOLE | grey |  |  | 34.8 | 34.8 |  | -41.2846 | 174.7753 | [16 empty] | 2009-02-16 | 2009-02-16 | 1 | 2009-02-16 | 2009-02-16 |  |  | 2009-02-28 | 2008-12-18 |  | 2009-02-28 | 2009-02-17 |  |  |  | 2009-03-30 |  |  | 2009-03-30 | 2009-03-09 |  | 2009-02-24 |  | 2009-04-28 | 1 | 1 | 2009-04-28 | 2009-04-28 | [5 empty] | 2009-06-02 | 2009-06-06 | 2009-06-19 | 2009-06-11 |  | 2009-06-15 | 2009-06-15 | [8 empty] | 2009-06-19 | 2009-06-30 | 2009-06-19 |  |  |  |  | 9/2/09: Lease is signed. RF and TX to inspect this week. Landlords precious over appearance of building. Stefan to draw up...All issues resolved site signed off by all parties 13 Feb 09 SS 9/3/09: Linking to BP. 16/3/09: JM to speak with EB. 16/4/09: Await revised drawing. 20/4/09: CDs issued. TSS ASAP. 12/5/09: 2 x chopper lifts required. |  | 2009-06-30 | [17 empty] | FALSE |  | 2658686 | 5989844 | Capital on the Quay 256-274 Lambton Quay Wellington |  |  | CELLSITE |  |  | 2014-09-01 |  |  |  |  | 2009-05-18 | 2009-05-18 | [8 empty] | 2008-11-27
0 | WLG | 1652 | WLG-047-044 | Customhouse Quay(Perp Trust) | WLG-047-044-A | Customhouse Quay | Wellington City |  | TIER_1_ALL | ACTIVE | RT | B6 | NOPOLE | grey |  |  | 35.7 | 35.7 |  | -41.2862 | 174.7766 | [17 empty] | 2007-08-23 | 2 |  | 2014-10-29 |  |  | 2008-09-30 | 2008-09-24 | 1 | 2008-09-30 | 2008-09-24 |  |  |  | 2008-03-11 |  |  | 2008-03-11 | 2008-03-11 |  | 2008-04-10 |  | 2008-07-25 | 3 |  | 2008-07-25 | [7 empty] | 2014-12-15 | 2008-11-30 | 2014-12-15 |  | 2008-12-12 | 2008-12-12 | [8 empty] | 2009-01-30 | 2009-02-27 | 2009-01-30 |  |  |  |  | Note - BBU 3806 SAPPED OUT FOR 3900 ON 17/10/12. |  | 2009-02-27 | [17 empty] | FALSE |  | 2658793 | 5989664 | Perpetual Trust Building 111 Customhouse Quay Wellington |  |  | CELLSITE |  |  | 2014-09-01 | [5 empty] | 2008-10-16 | [8 empty] | 2007-08-27
0 | WLG | 1653 | WLG-047-045 |  | WLG-047-045-E | Willis St North | Wellington City |  | TIER_1_ALL | ACTIVE | RT | B6 | NOPOLE | grey |  |  | 42.8 | 42.8 |  | -41.2894 | 174.7747 |  |  |  |  | Microwave, Microwave | WLG-047-050-A, WLG-047-050-A | [5 empty] | 2008-06-09, 2008-06-09 | [5 empty] | 2007-11-30 | 1 |  | 2007-11-30 |  |  | 2008-04-30 | 2008-04-30 | 1 | 2008-04-30 | 2008-04-30 |  |  |  | 2008-03-11 |  |  | 2008-03-11 | 2008-03-11 |  | 2008-02-12 |  | 2008-06-10 | 1 | 1 | 2008-06-10 | 2008-06-10 | [6 empty] | 2008-07-28 | 2008-08-31 | 2008-08-31 |  | 2008-08-31 | 2008-09-02 | [8 empty] | 2008-12-05 | 2008-12-30 | 2008-12-05 |  |  |  |  | Note - BBU 3806 SWAPPED OUT FOR 3900 ON 18/10/12. Site type Changed to B . SS 31/7/2013 |  | 2008-12-16 | [17 empty] | FALSE |  | 2658623 | 5989311 | Kordia House 109-125 Willis St, Wellington |  |  | CELLSITE |  |  | 2014-09-01 | [5 empty] | 2008-06-11 | [8 empty] | 2007-10-04
0 | WLG | 1654 | WLG-047-046 |  | WLG-047-046-G | Willis St South | Wellington City |  | TIER_1_ALL | ACTIVE | RT | B6 | NOPOLE | grey |  |  | 20.3 | 20.3 |  | -41.2926 | 174.7726 |  |  |  |  | Microwave | WLG-047-045-E | [11 empty] | 2008-07-18 | 3 |  | 2009-02-25 |  |  | 2008-11-30 | 2008-11-12 | 1 | 2008-11-30 | 2008-11-12 |  |  |  | 2008-09-23 |  |  | 2008-09-23 | 2008-09-23 |  | 2008-09-08 |  | 2008-10-20 | 2 | 2 | 2008-12-05 | 2008-12-05 | [6 empty] | 2008-12-03 | 2009-01-14 | 2008-12-22 |  | 2009-01-21 | 2009-01-30 | [8 empty] | 2009-01-30 | 2009-02-27 | 2009-01-30 |  |  |  |  | None |  | 2009-02-27 | [17 empty] | FALSE |  | 2658444 | 5988952 | 204 Willis St, CBD, Wellington, |  |  | CELLSITE |  |  | 2014-09-01 | [5 empty] | 2008-11-28 | [8 empty] | 2008-06-12
0 | WLG | 1655 | WLG-047-047 |  | WLG-047-047-E | Wakefield St | Wellington City |  | TIER_1_ALL | ACTIVE | RT | B6 | NOPOLE | grey |  |  | 36.7 | 36.7 |  | -41.2905 | 174.7781 |  |  |  |  | Microwave | WLG-047-053-A | [5 empty] | 2008-08-06 | [5 empty] | 2008-03-25 | 1 |  | 2008-03-25 |  |  | 2008-07-31 | 2008-08-20 | 1 | 2009-03-06 | 2009-03-09 |  |  |  | 2008-07-20 |  |  | 2008-07-20 | 2008-06-20 |  | 2008-06-03 |  | 2008-07-24 | 3 | 1 | 2008-09-04 | 2009-03-02 | [5 empty] | 2009-04-14 | 2009-04-14 | 2009-04-30 | 2009-04-28 |  | 2009-06-12 | 2009-06-09 | [8 empty] | 2009-06-17 | 2009-06-17 | 2009-06-17 |  |  |  |  | 9/2/09: await architect approval. 9/3/09: Tss'd. In build. Site acq is complete - just EMSS to update with actual. 16/3/09: One more approval required for RF. LH is chasing. 16/4/09: Started. Meeting with landlord today. Update to be provided. In build. 20/4/09: Still on course for civils completion in April. 12/5/09: Await TI completion. NPTE - BBU 3806 SWAPPED OUT FOR 3900 ON 17/10/12. |  | 2009-06-17 | [17 empty] | FALSE |  | 2658906 | 5989177 | 142-146 Wakefiled St Wellington |  |  | CELLSITE |  |  | 2014-09-01 |  |  |  |  | 2009-03-10 | 2009-03-10 | [8 empty] | 2008-02-19
0 | WLG | 1656 | WLG-047-048 |  | WLG-047-048-E | Chaffers | Wellington City |  | TIER_1_ALL | ACTIVE | RT | B6 | NOPOLE | grey |  |  | 29.25 | 29.25 |  | -41.2924 | 174.7832 |  |  |  |  | Microwave | WLG-047-053-A | [11 empty] | 2008-10-15 | 2 |  | 2009-02-11 |  |  | 2008-12-31 | 2008-12-10 | 2 | 2008-12-31 | 2008-12-10 |  |  |  | 2008-12-09 |  |  | 2008-12-09 | 2008-12-09 |  | 2009-01-26 |  | 2009-03-05 | 1 | 2 | 2009-03-04 | 2009-03-05 | [5 empty] | 2009-05-09 | 2009-04-22 | 2009-05-07 | 2009-05-07 |  | 2009-06-16 | 2009-06-15 | [8 empty] | 2009-06-17 | 2009-06-30 | 2009-06-17 |  |  |  |  | 9/2/09: Telecom in close proximity on different title. CDs to issue in Feb. 9/3/09: In build. 19/3/09: Approval from RF to build. 16/4/09: Pre-build. 12/5/09: Await TI completion. Note- BBU 3806 SWAPPED FOR 3900 ON 17/10/12. F3 DUAL RRU INSTALLED ON 4/13. |  | 2009-06-30 | [17 empty] | FALSE |  | 2659332 | 5988965 | Cnr Wakefield & Chaffers St Wellington Central |  |  | CELLSITE |  |  | 2014-09-01 | [5 empty] | 2009-02-04 | [8 empty] | 2008-08-25
0 | WLG | 1657 | WLG-047-049 |  | WLG-047-049-A | Taranaki St | Wellington City |  | TIER_1_ALL | ACTIVE | RT | B6 | NOPOLE | grey |  |  | 22 | 22 |  | -41.294 | 174.7782 | [17 empty] | 2007-12-07 | 4 |  | 2009-02-25 |  |  | 2008-05-31 | 2008-05-08 | 2 | 2008-05-31 | 2008-05-08 |  |  |  | 2008-03-07 |  |  | 2008-03-07 | 2008-03-07 |  | 2008-03-17 |  | 2008-04-30 | 3 | 3 | 2008-08-22 | 2008-08-22 | [6 empty] | 2008-05-15 | 2008-05-30 | 2008-05-30 |  | 2008-06-13 | 2008-06-24 | [8 empty] | 2008-11-27 | 2008-12-31 | 2008-11-27 |  |  |  |  | None |  | 2008-12-31 | [17 empty] | FALSE |  | 2658912 | 5988790 | Konica Minolta 79 Taranaki Street (directly opposite T-junction) Wellington |  |  | CELLSITE |  |  | 2014-09-01 | [5 empty] | 2008-05-09 | [8 empty] | 2007-10-29
0 | WLG | 1658 | WLG-047-050 |  | WLG-047-050-A | Kent Tce | Wellington City |  | TIER_1_ALL | ACTIVE | RT | B6 | NOPOLE | grey |  |  | 28.8 | 28.8 |  | -41.2961 | 174.7831 | [17 empty] | 2007-09-03 | 5 | 2009-03-06 | 2009-07-13 |  |  | 2007-11-21 | 2007-11-21 | 1 | 2007-11-21 | 2007-11-21 |  |  |  | 2008-03-03 |  |  | 2008-03-03 | 2008-03-03 |  | 2008-02-11 |  | 2008-04-30 | 3 | 2 | 2008-08-22 | 2008-08-22 | [6 empty] | 2008-06-12 | 2008-06-30 | 2008-06-30 |  | 2008-08-15 | 2008-08-15 | [8 empty] | 2008-11-27 | 2008-12-31 | 2008-11-27 |  |  |  |  | None | [19 empty] | FALSE |  | 2659311 | 5988556 | Quinovic House 32-34 Kent Terrace Wellington |  |  | CELLSITE |  |  | 2014-09-01 | [5 empty] | 2008-05-01 | [8 empty] | 2007-07-23
0 | WLG | 1659 | WLG-047-052 |  | WLG-047-052-E | Te Aro | Wellington City |  | TIER_1_ALL | ACTIVE | RT | B6 | NOPOLE | grey |  |  | 18 | 18 |  | -41.2951 | 174.7738 |  |  |  |  | Microwave, Microwave | WLG-047-053-A, WLG-047-053-A | [5 empty] | 2008-06-09, 2008-06-09 | [5 empty] | 2008-06-27 | 3 | 2009-03-20 | 2009-04-08 |  |  | 2008-08-25 | 2008-08-26 | 1 | 2008-08-25 | 2008-08-26 |  |  |  | 2008-08-14 |  |  | 2008-08-14 | 2008-08-14 |  | 2008-07-22 |  | 2008-11-03 | 1 | 1 | 2008-11-03 | 2008-11-03 | [6 empty] | 2008-12-08 | 2009-01-26 | 2009-01-26 |  | 2009-02-27 | 2009-02-20 | [8 empty] | 2009-03-02 | 2009-03-15 | 2009-03-02 |  |  |  |  | None |  | 2009-03-15 | [17 empty] | FALSE |  | 2658536 | 5988673 | 15 Walter St, CBD, Wellington |  |  | CELLSITE |  |  | 2014-09-01 | [5 empty] | 2008-11-11 | [8 empty] | 2008-05-12
0 | WLG | 1660 | WLG-047-053 |  | WLG-047-053-A | Mercure | Wellington City |  | TIER_1_ALL | ACTIVE | RT | B6 | NOPOLE | grey |  |  | 27.3 | 27.3 |  | -41.2967 | 174.7707 | [17 empty] | 2008-01-23 | 3 |  | 2009-02-25 |  |  | 2008-12-31 | 2008-11-26 | 2 | 2008-12-31 | 2008-11-26 |  |  |  | 2008-03-13 |  |  | 2008-03-13 | 2008-03-13 |  | 2008-12-01 |  | 2009-01-15 | 1 | 2 | 2009-01-15 | 2009-01-15 | [6 empty] | 2009-01-27 | 2009-02-10 | 2009-02-09 |  | 2009-03-02 | 2009-03-02 | [8 empty] | 2009-03-02 | 2009-03-15 | 2009-03-02 |  |  |  |  | 23/02/09: Optical alternators missing |  | 2009-03-15 | [17 empty] | FALSE |  | 2658271 | 5988504 | Merecure Hotel C.P Hotels Ltd 355 Willis Street Wellington |  |  | CELLSITE |  |  | 2014-09-01 | [5 empty] | 2009-01-16 | [8 empty] | 2007-11-16
0 | WLG | 1661 | WLG-047-054 |  | WLG-047-054-A | Tory St | Wellington City |  | TIER_1_ALL | ACTIVE | RT | B6 | NOPOLE | grey |  |  | 15.4 | 15.4 |  | -41.297 | 174.779 |  |  |  |  | Microwave, Microwave | WLG-047-049-A, WLG-047-049-A | [5 empty] | 2008-06-09, 2008-06-09 | [5 empty] | 2008-03-12 | 1 |  | 2008-03-12 |  |  | 2008-06-30 | 2008-06-30 | 1 | 2008-06-30 | 2008-06-30 |  |  |  | 2008-08-14 |  |  | 2008-08-14 | 2008-08-14 |  | 2008-07-01 |  | 2008-09-12 | 2 | 1 | 2008-12-05 | 2008-12-05 | [6 empty] | 2008-12-03 | 2009-01-23 | 2009-01-16 |  | 2009-01-23 | 2009-01-23 | [8 empty] | 2009-01-27 | 2009-02-27 | 2009-01-27 |  |  |  |  | None |  | 2009-02-27 | [17 empty] | FALSE |  | 2658970 | 5988456 | Bible Society 144 Tory Street Wellington |  |  | CELLSITE |  |  | 2014-09-01 | [5 empty] | 2008-09-24 | [8 empty] | 2008-02-07
0 | WLG | 1662 | WLG-047-055 |  | WLG-047-055-A | Adelaide Rd | Wellington City |  | TIER_1_ALL | ACTIVE | RT | B6 | NOPOLE | grey |  |  | 19.9 | 19.9 |  | -41.3069 | 174.7778 |  |  |  |  | Microwave, Microwave | WLG-047-049-A, WLG-047-049-A | [5 empty] | 2008-06-09, 2008-06-09 | [5 empty] | 2007-09-21 | 2 | 2009-03-13 | 2009-03-12 |  |  | 2008-06-30 | 2008-05-30 | 1 | 2008-06-30 | 2008-05-30 |  |  |  | 2008-05-07 |  |  | 2008-05-07 | 2008-05-07 |  | 2008-04-10 |  | 2008-06-30 | 3 | 1 | 2008-07-18 | 2008-07-18 | [6 empty] | 2008-07-15 | 2008-09-23 | 2008-09-23 |  | 2008-10-03 | 2008-09-19 | [8 empty] | 2008-12-02 | 2008-12-31 | 2008-12-02 |  |  |  |  | None | [19 empty] | FALSE |  | 2658843 | 5987364 | Loafers Lodge 160 Adelaide Road Wellington |  |  | CELLSITE |  |  | 2014-09-01 | [5 empty] | 2008-07-01 | [8 empty] | 2007-08-16
0 | WLG | 1663 | WLG-047-056 |  | WLG-047-056-A | Newtown | Wellington City |  | TIER_1_ALL | ACTIVE | RT | B6 | NOPOLE | grey |  |  | 20 | 20 |  | -41.3175 | 174.7782 |  |  |  |  | Microwave, Microwave | WLG-047-055-A, WLG-047-055-A | [5 empty] | 2008-06-09, 2008-06-09 | [5 empty] | 2008-04-23 | 4 |  | 2009-08-12 |  |  | 2008-07-31 | 2008-06-30 | 1 | 2008-07-31 | 2008-06-30 |  |  |  | 2008-07-14 |  |  | 2008-07-14 | 2008-07-14 |  | 2008-07-01 |  | 2008-09-05 | 2 | 3 | 2009-08-07 | 2009-09-07 | [6 empty] | 2008-10-10 | 2008-11-30 | 2008-11-24 |  | 2008-12-03 | 2008-12-12 | [8 empty] | 2008-12-15 | 2008-12-31 | 2008-12-15 |  |  |  |  | None. NOTE - BBU 3806 SWAPPED OUT FOR NEW 3900 UNITS ON 20/03/2013. |  | 2008-12-31 | [17 empty] | FALSE |  | 2658856 | 5986184 | Wakefield Hospital 99 Rintoul Street Wellington |  |  | CELLSITE |  |  | 2014-09-01 | [5 empty] | 2008-09-09 | [8 empty] | 2008-03-17
0 | WLG | 1664 | WLG-047-057 |  | WLG-047-057-I | Basin Reserve | Wellington City |  | TIER_1_ALL | ACTIVE | RT | B6 | NOPOLE | grey |  |  | 13.8 | 13.8 |  | -41.3012 | 174.7793 |  |  |  |  | Microwave | WLG-047-050-A | [5 empty] | 2008-08-13 | [5 empty] | 2008-09-19 | 1 |  | 2008-09-19 |  |  | 2009-01-21 | 2009-01-21 | 1 | 2009-01-21 | 2009-01-21 |  |  |  | 2008-10-09 |  |  | 2008-10-09 | 2008-10-09 |  | 2008-09-26 |  | 2008-12-12 | 1 | 1 | 2008-12-12 | 2008-12-12 | [5 empty] | 2009-03-13 | 2009-03-12 | 2009-04-28 | 2009-04-28 |  | 2009-06-18 | 2009-06-16 | [8 empty] | 2009-06-17 | 2009-06-18 | 2009-06-17 |  |  |  |  | 9/2/09: RMA and Lease Complete. Not claimed in DB. 9/3/09: In build. 16/4/09: Dis board previously installed has been stolen. Ok for this month. TI lift. 20/4/09: Issue with fire stopping. Still on course for April completion. 12/5/09: Await TI completion. |  | 2009-06-18 | [17 empty] | FALSE |  | 2658982 | 5987995 | Cnr Rugby & Belfast Sts Wellington |  |  | CELLSITE |  |  | 2014-09-01 | [5 empty] | 2009-02-23 | [8 empty] | 2008-08-12
0 | WLG | 1665 | WLG-047-059 |  |  |  | Wellington City |  | TIER_1_ALL
0 | WLG | 1666 | WLG-047-060 |  | WLG-047-060-A | Crofton Downs | Wellington City |  | TIER_1_ALL | ACTIVE | GF | A | P2 | green |  |  | 18.8 | 18.8 |  | -41.2547 | 174.7662 |  |  |  |  | Leased Line | WLG-047-071-A | [11 empty] | 2007-09-12 | 2 |  | 2008-04-28 |  |  | 2008-11-30 | 2008-10-24 | 2 | 2008-11-30 | 2008-10-24 |  |  |  | 2008-06-20 |  |  | 2008-06-20 | 2008-06-20 |  | 2008-06-03 |  | 2008-09-12 | 1 | 2 | 2008-09-12 | 2008-09-12 | 2009-03-13 | [5 empty] | 2008-12-07 | 2009-03-30 | 2009-03-28 |  | 2009-04-30 | 2009-04-17 | [8 empty] | 2009-04-21 | 2009-04-30 | 2009-04-21 |  |  |  |  | 25/2/09: Pre-built, awaiting pole. 9/3/09: In build. 16/3/09: Awaiting pole. |  | 2009-04-30 |  |  |  |  | 2009-03-16 | 2009-03-13 | [11 empty] | FALSE |  | 2657995 | 5993172 | Crofton Downs Wellington |  |  | CELLSITE | [8 empty] | 2008-12-08 | [8 empty] | 2007-08-22
0 | WLG | 1667 | WLG-047-061 |  | WLG-047-061-B | Ngaio | Wellington City |  | TIER_1_ALL | ACTIVE | RSR | A | P2 | green |  |  | 13.8 | 13.8 |  | -41.2507 | 174.7727 |  |  |  |  | Microwave, Microwave | WLG-047-062-B, WLG-047-062-B | [5 empty] | 2008-11-17, 2008-11-17 | [5 empty] | 2008-10-15 | 3 |  | 2009-05-05 |  |  | 2008-12-31 | 2008-12-04 | 1 | 2009-03-30 | 2009-03-20 |  |  |  | 2009-03-12 |  |  | 2009-02-12 | 2009-02-12 |  | 2009-01-26 |  | 2009-02-09 | 1 | 1 | 2009-02-09 | 2009-02-09 | 2009-04-20 |  |  |  |  | 2009-04-20 | 2009-04-16 | 2009-04-30 | 2009-04-28 |  | 2009-05-30 | 2009-05-08 | [8 empty] | 2009-06-04 | 2009-06-12 | 2009-06-04 |  |  |  |  | 9/2/09: VM site. 3/3/09: Awaiting notice of prior approval. 18/3/09: Have been advised that ETA for pole is 30/3/09 16/4/09: Pole forecast 22/4/09. All going ok. 20/4/09: Still on course for civils completion April. |  | 2009-06-12 |  |  |  |  | 2009-04-22 | 2009-04-20 | [11 empty] | FALSE |  | 2658542 | 5993609 | O/s Ngaio Tennis Club, 1 Whaikowhai St, Ngaio, Wellington |  |  | CELLSITE | [7 empty] | 2009-04-18 | 2009-04-14 | [8 empty] | 2008-09-11
0 | WLG | 1668 | WLG-047-062 |  |  |  | Wellington City |  | TIER_1_ALL
0 | WLG | 1669 | WLG-047-063 |  | WLG-047-063-B | Khandallah North | Wellington City |  | TIER_1_ALL | ACTIVE | GF | A | P2 | grey |  |  | 18.8 | 18.8 |  | -41.247 | 174.7918 |  |  |  |  | Leased Line | WLG-047-071-A | [11 empty] | 2008-07-16 | 2 |  | 2008-08-05 |  |  | 2008-08-29 | 2008-08-29 | 2 | 2008-08-29 | 2008-08-29 |  |  |  | 2009-01-06 |  |  | 2009-01-06 | 2009-01-06 |  | 2008-08-27 |  | 2008-11-28 | 1 | 2 | 2008-11-28 | 2008-11-28 | 2009-03-12 | [5 empty] | 2009-02-02 | 2009-04-04 | 2009-03-26 |  | 2009-04-15 | 2009-03-27 | [8 empty] | 2009-05-22 | 2009-05-29 | 2009-05-22 |  |  |  |  | 9/3/09: In build. |  | 2009-06-06 |  |  |  |  | 2009-03-16 | 2009-03-12 | [11 empty] | FALSE |  | 2660150 | 5993990 | 23 Ganges Road, Khandallah, Wellington |  |  | CELLSITE | [8 empty] | 2009-01-08 | [8 empty] | 2008-06-12
0 | WLG | 1670 | WLG-047-065 |  | WLG-047-065-C | Lyall Bay | Wellington City |  | TIER_1_ALL | ACTIVE | RT | B6 | NOPOLE | grey |  |  | 14 | 14 |  | -41.3271 | 174.8025 |  |  |  |  | Microwave, Microwave | WLG-047-069-A, WLG-047-069-A | [5 empty] | 2008-09-04, 2008-09-04 | [5 empty] | 2008-11-21 | 1 |  | 2008-11-21 |  |  | 2009-01-15 | 2009-01-13 | 1 | 2009-01-15 | 2009-01-15 |  |  |  | 2009-01-07 |  |  | 2009-01-07 | 2009-01-07 |  | 2008-12-08 |  | 2009-03-05 | 1 | 1 | 2009-03-04 | 2009-03-05 | [5 empty] | 2009-03-24 | 2009-03-24 | 2009-05-10 | 2009-05-05 |  | 2009-06-02 | 2009-06-02 | [8 empty] | 2009-05-27 | 2009-05-27 | 2009-05-27 |  |  |  |  | 9/2/09: CDs w/c 9/2/09 9/3/09: In build. Still progressing with TNZ option. Still want confirmation of roles and responsibilities. 16/4/09: All good for April completion but dependant on what's found when roof is opened. 20/4/09: Still on course for civils completion in April. 12/5/09: Await TI completion. |  | 2009-05-27 | [17 empty] | FALSE |  | 2660870 | 5985079 | Warehouse Building 127-147 Tirangi Road Lyall Bay Wellington |  |  | CELLSITE |  |  | 2014-09-01 |  |  |  |  | 2009-03-10 | 2009-03-10 | [8 empty] | 2008-08-15
0 | WLG | 1671 | WLG-047-066 |  | WLG-047-066-B | Maupuia | Wellington City |  | TIER_1_ALL | ACTIVE | RT | B6 | NOPOLE | grey |  |  | 9.75 | 9.75 |  | -41.3133 | 174.8132 |  |  |  |  | Microwave | WLG-047-030-D | [5 empty] | 2008-08-25 | [5 empty] | 2008-09-10 | 1 |  | 2008-09-10 |  |  | 2008-11-30 | 2008-10-20 | 1 | 2008-11-30 | 2008-10-20 |  |  |  | 2008-10-07 |  |  | 2008-10-07 | 2008-10-07 |  | 2008-09-26 |  | 2008-11-20 | 1 | 1 | 2008-11-20 | 2008-11-20 | [6 empty] | 2008-12-08 | 2009-01-15 | 2008-12-22 |  | 2009-01-27 | 2009-01-27 | [8 empty] | 2009-01-30 | 2009-04-30 | 2009-01-30 |  |  |  |  | None |  | 2009-04-30 | [17 empty] | FALSE |  | 2661795 | 5986588 | 27 Maupuia Rd Miramar Wellington |  |  | CELLSITE |  |  | 2014-09-01 | [5 empty] | 2008-12-08 | [8 empty] | 2008-07-22
0 | WLG | 1672 | WLG-047-067 |  | WLG-047-067-A | Paparangi | Wellington City |  | TIER_1_ALL | ACTIVE | RSR | A | P4B | green |  |  | 11.2 | 11.2 |  | -41.2173 | 174.8186 |  |  |  |  | Microwave, Microwave | WLG-047-074-B, WLG-047-074-B | [5 empty] | 2008-05-22, 2008-05-22 | [5 empty] | 2008-02-22 | 4 |  | 2008-07-21 |  |  | 2008-04-29 | 2008-04-29 | 4 | 2008-04-29 | 2008-04-29 |  |  |  | 2008-05-15 |  |  | 2008-07-31 | 2008-07-31 |  | 2008-04-10 |  | 2008-06-24 | 2 | 4 | 2008-07-24 | 2008-07-24 | [6 empty] | 2008-07-15 | 2008-08-25 | 2008-08-26 |  | 2008-09-15 | 2008-08-22 | [8 empty] | 2008-12-10 | 2008-12-31 | 2008-12-10 |  |  |  |  | None |  | 2008-12-23 | [17 empty] | FALSE |  | 2662466 | 5997238 | Oppsite 226 Helston Rd, Paparangi, Wellington |  |  | CELLSITE |  |  | 2015-12-02 | [5 empty] | 2008-06-25 | [8 empty] | 2007-12-07
0 | WLG | 1673 | WLG-047-069 |  | WLG-047-069-A | Mt Victoria | Wellington City |  | TIER_1_ALL | ACTIVE | RT | TX | NOPOLE | [6 empty] | -41.2959 | 174.7969 |  |  |  |  | Microwave, Microwave | WLG-047-071-A, WLG-047-071-A | [5 empty] | 2008-05-23, 2008-05-23 | [5 empty] | 2008-04-09 | 6 |  | 2012-02-08 |  |  | 2008-11-30 | 2008-11-25 | 3 | 2008-11-30 | 2008-11-25 |  | 2008-10-09 |  | 2008-10-23 |  |  | 2008-10-23 | 2008-10-23 |  | 2008-06-03 |  | 2008-10-31 | 1 | 3 | 2008-10-31 | 2008-10-31 | [6 empty] | 2008-12-08 | 2009-01-30 | 2008-12-22 |  | 2009-02-13 | 2009-01-15 | [8 empty] | 2009-01-30 | 2009-02-28 | 2009-01-30 |  |  |  |  | None |  | 2009-02-28 | [17 empty] | FALSE |  | 2660470 | 5988555 | 22 Alexandra Road Mt Victoria Lookout Wellington |  |  | TXSITE | [8 empty] | 2008-12-08 | [8 empty] | 2008-03-05
0 | WLG | 1674 | WLG-047-070 | Houghton Bay | WLG-047-070-B | 39 Houghton Bay Road | Wellington City | 6 | 2014 | ACTIVE | RSR | MC | SP | Grey | [5 empty] | -41.3314 | 174.7856 |  |  |  |  | Fibre Optic | WLG-047-071-A | FALSE | FALSE |  |  | FALSE |  | 2014-03-11 | 2014-03-11 |  | 2014-02-13 | 2014-03-28 | 2014-03-17 | 3 |  | 2014-05-28 | 2014-06-16 | 2014-05-09 | 2014-06-16 | 2014-06-27 |  | 2014-06-16 | 2014-06-27 | DISCRETIONARY_FULL | 2014-04-10 | 2014-04-04 | 2014-05-10 | 2014-05-29 | 2 | 2014-05-15 | 2014-05-30 |  |  | 2014-05-09 | 2014-05-05 | 2 |  | 2014-04-20 | 2014-08-05 | [5 empty] | 2014-07-19 | 2014-07-28 | 2014-08-15 | 2014-08-22 | 2014-08-22 | 2014-08-15 | 2014-08-22 | 2014-08-11 | 2014-08-21 | [7 empty] | 2014-09-10 | 2014-08-28 |  |  |  |  | 28/8 Site on air, F1+F2 and all OK. | [10 empty] | 2014-08-29 | 2014-08-27 | 2014-04-04 | MEDIUM |  | 2014-08-08 | 2014-08-20 | BUILD | 2014-08-08 | FALSE |  | 2659444 | 5984631 | 39 Houghton Bay Road |  |  | CELLSITE | [17 empty] | 2014-02-13
0 | WLG | 1675 | WLG-047-071 | St Johns House(Well Switch) | WLG-047-071-A | Wellington Switch | Wellington City |  | TIER_1_ALL | ACTIVE | RT | TX | NOPOLE | [6 empty] | -41.2832 | 174.7744 | [6 empty] | FALSE | FALSE |  |  | FALSE | [6 empty] | 2008-03-26 | 1 |  | 2008-03-26 |  |  | 2008-02-27 | 2008-02-27 | 1 | 2008-02-27 | 2008-02-27 |  |  |  | 2008-05-29 |  |  | 2008-05-29 | 2008-05-29 |  | 2008-04-22 |  | 2008-06-18 | 2 | 1 | 2008-07-29 | 2008-07-29 | [6 empty] | 2008-07-28 | 2008-08-31 | 2008-08-31 |  |  | 2008-09-30 | [8 empty] | 2008-12-24 | 2009-02-28 | 2008-12-24 |  |  |  |  | None |  | 2009-02-28 | [17 empty] | FALSE |  | 2658615 | 5989999 | TBA |  |  | TXSITE | [8 empty] | 2008-06-19 | [8 empty] | 2008-02-14
0 | WLG | 1676 | WLG-047-074 |  | WLG-047-074-B | Mt Kau Kau | Wellington City | 7 | TIER_1_ALL | ACTIVE | COLO | TX | NOPOLE |  |  | COLO |  |  |  | -41.234 | 174.7794 |  |  |  |  | Microwave, Microwave | WLG-047-071-A, WLG-047-071-A | FALSE | FALSE |  |  | FALSE | 2008-05-22, 2008-05-22 | [5 empty] | 2007-05-01 | 1 |  | 2007-05-01 |  |  |  | 2008-09-12 | 1 | 2013-05-17 | [7 empty] | 2008-09-29 | 2008-09-29 |  | 2007-05-01 |  | 2007-05-01 | [10 empty] | 2008-11-14 | 2008-11-28 | 2008-11-28 |  |  | 2008-12-05 | [8 empty] | 2008-12-22 | 2009-02-28 | 2008-12-22 |  |  |  |  | None | KDA | 2009-02-28 | [17 empty] | FALSE |  | 2659146 | 5995452 | Mt Kaukau (TV transmitter), Wellington |  |  | TXSITE | [8 empty] | 2008-10-13 | [8 empty] | 2008-08-14
0 | WLG | 1677 | WLG-047-075 | Glenmore st - Tinakori Rd | WLG-047-075-A | Tinakori rd | Wellington City |  | TIER_6 | ACTIVE | [5 empty] | COSITE |  |  |  | -41.2711 | 174.7649 |  |  |  |  | Microwave, Microwave | WLG-047-071-A, WLG-047-071-A | [5 empty] | 2008-05-22, 2008-05-22 | [5 empty] | 2008-08-29 | 2 |  |  |  |  | 2009-06-30 |  |  | 2009-06-30 |  |  |  |  | 2008-10-07 |  |  | 2008-10-07 | 2008-10-07 | [6 empty] | 2009-06-30 | [28 empty] | 9/2/09: with Matt Buchanan. |  | 2009-07-31 | [15 empty] | HARDMATCH |  | FALSE |  | 2657844 | 5991357 | Tinakori Hill Wellington | [20 empty] | 2008-08-01
0 | WLG | 1678 | WLG-047-076 |  | WLG-047-076-A | Terrace East | Wellington City |  | TIER_1_ALL | ACTIVE | RT | B6 | NOPOLE | grey |  |  | 28.5 | 28.5 |  | -41.2819 | 174.7752 | [16 empty] | 2009-01-09 | 2009-01-09 | 1 | 2009-01-09 | 2009-01-09 |  |  |  | 2008-11-21 |  | 2008-11-21 | 2008-11-21 |  |  |  | 2009-02-16 |  |  | 2009-02-16 | 2009-02-16 |  | 2009-02-24 |  | 2009-03-26 | 1 | 1 | 2009-03-31 | 2009-03-26 | [5 empty] | 2009-04-15 | 2009-04-14 | 2009-04-30 | 2009-04-28 |  | 2009-06-16 | 2009-06-12 | [8 empty] | 2009-06-22 | 2009-06-23 | 2009-06-22 |  |  |  |  | 9/2/09: CDIs 9/2/09. 9/3/09: TSS 16/3/09: In build. 16/4/09: TI lift on Sunday. 2xac units to relocate. Abseil access involved. Started today. 20/4/09: Still on course for civils completion in April. 12/5/09: Await TI completion. |  | 2009-06-23 | [17 empty] | FALSE |  | 2658681 | 5990143 | Genesis House 93 The Terrace Wellington |  |  | CELLSITE |  |  | 2014-09-01 |  |  |  |  | 2009-03-25 | 2009-02-23 | [8 empty] | 2008-11-11
0 | WLG | 1679 | WLG-047-078 |  | WLG-047-078-A | Vodafone Wellingto Switch | Wellington City |  | TIER_6 | ACTIVE |  | TX | [7 empty] | -41.3032 | 174.7787 | [66 empty] | 2009-01-01 | [26 empty] | 2658932 | 5987773 | 58 Adelaide Rd, Newtown, Wellington |  |  | TXSITE
0 | WLG | 1680 | WLG-047-079 | Wellington Office | WLG-047-079-A | Wellington Office | Wellington City |  | TIER_6 | ACTIVE |  | TX | [7 empty] | -41.2872 | 174.7772 | [6 empty] | FALSE | FALSE |  |  | FALSE | [17 empty] | PERMITTED | [64 empty] | 2658840 | 5989545 | Cnr Maning Ln and Victoria St Wellington
0 | WLG | 1681 | WLG-047-080 | Victoria Uni | WLG-047-080-G | Kelburn Pde | Wellington City | 7 | TIER_1_INFILL | ACTIVE | RSR | DU5 | P4F |  | INLINE | COSITE | 14.5 | 15 | 2 | -41.2892 | 174.7674 |  |  |  |  | Microwave | WLG-047-040-A | FALSE | FALSE |  |  | FALSE |  | 2011-08-14 | 2011-08-14 | 2011-08-21 | 2011-08-21 | 2011-09-07 | 2011-09-12 | 1 | 2011-09-07 | 2011-09-12 | 2011-10-13 | 2011-10-13 | 2011-11-25 | 2011-11-16 |  | 2011-11-16 | 2011-11-16 | PERMITTED | 2011-09-14 | 2011-09-16 | 2011-10-27 | 2011-10-17 | 1 | 2011-10-27 | 2011-10-17 |  |  | 2012-02-29 | 2012-02-28 | 1 |  | 2012-02-29 | 2012-02-28 | 2012-03-27 |  |  |  |  | 2012-02-27 | 2012-02-27 | 2012-04-06 | 2012-04-10 | 2012-03-27 | 2012-03-29 | 2012-03-30 | [8 empty] | 2012-03-30 | 2012-04-12 | 2012-04-10 | 2012-05-23 | 2012-05-01 | 2012-07-30 | 2012-08-30 | 12.06.2014 : "D" configuration build. (APM, Battery, & 2 x RFC) using version "B" cabinets. Thus making it a "DU" Site. (As per Ron Bush/blr) |  | 2012-03-29 | 2012-03-27 | 2012-03-27 |  | 2012-03-27 |  | 2012-03-27 | 2012-03-27 | 2012-03-27 | 2012-04-05 | 2012-04-17 | [6 empty] | 2012-03-26 | FALSE |  | 2658015 | 5989342 | Kelburn Pde Kelburn |  | WCC Planner Brett Smith - 29/09/2011 | CELLSITE |  |  | 2014-09-01 | [13 empty] | 2012-04-17
0 | WLG | 1682 | WLG-047-082 | Cook Strait | WLG-047-082-B | Hawkins Hill GF | Wellington City | 7 | TIER_3 | ACTIVE | GF | DU | SP |  | STACK_A | COSITE | 9.7 | 12.4 | 1 | -41.3423 | 174.7076 |  | 2012-01-26 |  |  |  |  | FALSE | FALSE |  |  | FALSE |  | 2012-03-08 | 2012-03-08 | 2012-03-30 | 2012-03-30 | 2012-05-09 | 2012-05-11 | 1 | 2012-05-09 | 2012-05-11 | 2013-03-15 | 2013-02-14 | 2013-05-10 | 2013-05-01 | 1 | 2013-05-10 | 2013-05-01 | DISCRETIONARY_FULL | 2012-08-28 | 2012-09-07 | 2012-10-09 | 2012-10-05 | 1 | 2012-10-09 | 2012-10-05 |  |  | 2013-06-06 |  |  |  | 2013-06-06 | [6 empty] | 2013-06-10 |  | 2013-06-25 |  |  | 2013-07-05 | [10 empty] | 2013-07-29 |  | 2013-08-15 |  | 2013-11-30 |  | 9/5/13: • Draft CD available for quoting of VOR. • Geotech was planned for 7/5. Not sure of latest date. • Pole has been ordered. • Easy build!! | [10 empty] | 2013-07-15 |  |  |  | COOK_STRAIT |  |  | HARDMATCH |  | FALSE |  | 2652895 | 5983548 | Long Gully Farm Hawkins Hill Brooklyn Wellington |  |  | CELLSITE | WIPHOLDING | [16 empty] | 2012-03-30
0 | WLG | 1683 | WLG-047-086 | Westpac Stadium 2 | WLG-047-086-A | Westpac Stadium IB Site 2 | Wellington City | 7 | TIER_1_INFILL | ACTIVE | RT | D6 | RT |  | STACK_A | COSITE |  |  | 1 | -41.2741 | 174.7857 | [6 empty] | FALSE | FALSE |  |  | FALSE |  | 2011-03-25 | 2011-03-24 | 2011-04-20 | 2011-04-27 |  | 2011-05-17 | 1 |  | 2011-05-17 |  | 2011-06-03 | 2011-06-28 | 2011-06-23 |  |  | 2011-07-01 | PERMITTED | 2011-05-24 | 2011-05-04 | 2011-07-06 | 2012-05-04 | 1 | 2011-08-22 | 2011-08-22 |  |  | 2011-06-03 |  |  |  | 2011-07-07 | [6 empty] | 2011-06-21 | 2011-07-01 | 2011-07-21 | 2011-08-01 | 2011-07-14 | 2011-07-20 | 2011-08-30 | [9 empty] | 2011-08-30 | 2011-08-30 | 2011-09-16 | 2011-10-31 | 2011-12-15 | 2012-06-29 | This is part 2 of WLG-047-039-G -refer this site code for design of RT and Inbuilding site using 2 x D type cabinets. | [19 empty] | FALSE |  | 2659583 | 5990994 | 147 Waterloo Quay Wellington 6011 |  |  | CELLSITE |  |  | 2014-09-01
0 | WLG | 1684 | WLG-047-087 | Ohariu Valley | WLG-047-087-A | TNZ Colo | Wellington City | 7 | TIER_6 | ACTIVE | COLO | D | COLO |  | INLINE | COLO |  |  | 2 | -41.2068 | 174.7868 | [6 empty] | FALSE | FALSE |  |  | FALSE |  | 2012-07-19 | 2012-08-30 | 2012-09-06 | 2012-09-05 | 2012-10-19 | 2012-10-08 | 1 | 2012-10-19 | 2012-10-08 | 2012-11-16 |  | 2012-11-23 |  |  | 2012-11-23 |  | PERMITTED | 2012-10-26 |  | 2012-12-06 |  |  | 2012-12-06 | [36 empty] | TNZ Code: WOHU; Name: OHARIU VALLEY | TNZ | [16 empty] | HARDMATCH |  | FALSE |  | 2659825 | 5998462 | 598 Ohariu Valley Rd Ohariu Wellington | [20 empty] | 2012-09-05
0 | WLG | 1685 | WLG-047-088 | Cherry Tree Ohariu Valley Mini |  |  | Wellington City |  | TIER_6 | [83 empty] | Will be removed when new Ohariu Valley site (WLG-047-087) is put to air or moved to customer's new house when he moves at end of 2012. Repeater and hardware owned by 2degrees Cellutronics Yagi installed on existing roof Television pole. 900MHz repeater in the kitchen cupboard with power provided. internal omni antenna on top of the cupboards.
0 | WLG | 1686 | WLG-047-089 | 73-80 Boulcott Street | WLG-047-089-A | 2 Degrees Office | Wellington City |  | TIER_6 | ACTIVE | [15 empty] | Fibre Optic | WLG-047-071-A | [89 empty] | Level 13 73-89 Boulcott Street Wellington
0 | WLG | 1687 | WLG-047-090 | Thorndon - Infill | WLG-047-090-A | Thorndon East | Wellington City | 21 | 2014 | ACTIVE | RT | DF5 | RT | Grey | STACK_A | STANDALONE |  |  |  | -41.277 | 174.7799 |  | 2014-09-01 |  |  | Fibre Optic | WLG-047-037-A | FALSE | FALSE |  |  | FALSE |  | 2014-03-11 | 2014-03-11 | 2014-03-12 | 2014-03-12 | 2014-04-11 | 2014-05-05 | 1 |  | 2014-05-05 | 2014-08-29 | 2014-09-01 | 2014-09-26 | 2014-09-08 |  | 2014-10-15 | 2014-09-08 | PERMITTED | 2014-05-01 | 2014-05-09 | 2014-06-01 | 2014-05-26 | 1 | 2014-06-10 | 2014-05-26 | 2014-05-15 | 2014-05-06 | 2014-08-20 | 2014-09-24 | 1 |  | 2014-08-22 | 2014-09-24 | [5 empty] | 2014-11-10 | 2014-11-06 | 2014-11-13 | 2014-11-13 | 2014-11-03 | 2014-11-13 | 2014-11-11 | 2014-11-12 | 2014-11-11 | [7 empty] | 2014-12-03 | 2014-11-28 |  |  |  |  | 08.08.14 Roof top site, no alternative candidate. Chris A to visit the site next week with Stefan (11 - 15 Aug) CD's to be issued post Chris visit. 18.09.14 Tender meeting held on site. (Transfield, Infratel, Kordia, DWD) 01.10.14 QUOTATIONS DUE IN AT 8am 8 Oct - Tender awarded - Infratel 15 Oct Infratel in planning stage and stell to be fabricated 28 Oct Hope to start build next week, working with Archives NZ is slow going 30 Oct Archives NZ will not allow work to start next week new start date 10 Nov. 4 Nov CRs raised, Int chklist complete. 19 Nov - Drive Test delayed - some licence issues to clear up, SOA date still achievable | [10 empty] | 2014-11-18 | 2014-11-17 | 2014-05-09 | LOW |  | 2014-11-05 | 2014-11-06 | BUILD | 2014-10-31 | FALSE |  | 2659092 | 5990672 | 10 Mulgrave street Pipitea Wellington | Draft lease sent through mid Feb, asked for comments before 11/3/14 site visit. New manager in place, who contact Justin Angell reports to. Justin has got provisional agreement from manager but nothing formal. Has requested our help to do a presentation to staff about RF emissions. - 12/03/2014 |  | CELLSITE |  |  | 2014-11-28 | CAPACITY | [13 empty] | 2014-03-12
0 | WLG | 1688 | WLG-047-091 | Miramar | WLG-047-091-A | WETA Building | Wellington City |  | TIER_6 | ACTIVE | [100 empty] | HARDMATCH
0 | WLG | 1689 | WLG-047-092 | Newtown East | WLG-047-092-A | Newtown East VF Colo | Wellington City | 24 | 2015P | ACTIVE | COLO | DU5 | COLO |  | STACK_A | COLO |  |  |  | -41.3139 | 174.7818 |  | 2015-03-03 |  | 2015-01-01 | Fibre Optic | WLG-047-049-A | FALSE | FALSE |  |  | FALSE |  | 2015-07-01 | 2015-06-01 | 2014-04-15 | 2014-04-15 | 2014-05-09 | 2014-05-16 | 6 | 2015-01-01 | 2015-01-06 | 2014-11-14 | 2014-10-28 | 2015-02-05 | 2014-12-16 |  | 2015-02-20 | 2014-12-16 | DISCRETIONARY_RESTRICT | 2014-10-13 | 2014-09-26 | 2014-11-14 | 2014-11-03 | 2 | 2014-11-21 | 2014-11-03 | 2014-08-11 | 2014-09-08 | 2015-01-21 | 2015-01-16 | 2 |  | 2015-01-21 | 2015-06-02 |  |  |  | 2015-04-17 |  | 2015-05-22 | 2015-05-19 | 2015-07-17 | 2015-07-02 | 2015-07-28 | 2015-09-13 | 2015-09-13 | 2015-07-31 | 2015-07-28 | 2015-07-28 | 2015-07-28 | 2015-07-28 | 2015-07-28 | 2015-07-28 | 2015-07-28 |  | 2015-11-16 | 2015-11-19 |  |  |  |  | 16.12.14 Await the couriered lease then can accept condions and let Mike Tribe know Fibre route is ok. Changed the team back to Phil. Build ot for tender - equipment availibility to be confirmed 10/03 AS Project Plan sample copy given to Kordia for completion 19/05: AS under construction AS 27/08 Weather delay - weekend job only 19/11/15 - Site completed and on air with LTE | VNZ | [9 empty] | 2015-10-26 |  | 2014-09-30 | LOW |  | 2015-07-28 | 2015-07-28 | BUILD | 2015-07-28 | TRUE | 2015-02-13 | 2659161 | 5986576 | 23 Newtown Ave Newtown Wellington |  |  | CELLSITE |  |  | 2015-11-19 | CAPACITY |  | 2015-03-19 | 2015-05-12 | 2015-04-16 | 2015-04-16 |  |  |  |  | 2015-05-19 | 2015-05-19 |  |  | 2014-04-09
0 | WLG | 1690 | WLG-047-093 | Boulcott | WLG-047-093-A | Boulcott St Car Park | Wellington City | 24 | 2015P | ACTIVE | RT | DF5 | RT |  | STACK_A | STANDALONE | 20 |  |  | -41.2862 | 174.7747 |  | 2014-11-20 |  | 2015-06-18 | Fibre Optic | WLG-047-071-A | FALSE | FALSE |  |  | FALSE |  | 2015-02-11 | 2015-02-13 | 2015-04-30 | 2015-05-29 | 2015-05-31 | 2015-06-03 | 1 | 2015-06-03 | 2015-06-03 | 2015-07-28 | 2015-07-28 | 2015-08-28 | 2015-08-25 |  |  | 2015-08-04 | PERMITTED | 2015-06-12 | 2015-06-15 | 2015-07-10 | 2015-07-10 | 1 |  | 2015-08-06 | 2015-07-01 | 2015-06-29 | 2015-08-31 |  | 1 | [8 empty] | 2016-01-18 |  | 2016-02-29 |  |  | 2016-03-11 | [10 empty] | 2016-04-15 | [5 empty] | Site searches complete 22 Jan, caravan to be arranged when we have feedback from LOs 4/2/15 - Site placed to Hardmatch only by Brendon/Trevor on review with TPMO. Installation difficulties will increase cost 16/04 AS: PDI issued 09/7 AS: moved to next year build | [10 empty] | 2016-03-31 | [6 empty] | ONHOLD |  | FALSE |  | 2658635 | 5989662 | Car Park Boulcott St | Template lease documents sent to LO for review (along with special conditions, see below) on the 27/02/15. Rental has been agreed at $15K plus GST pa. To follow up re template lease docs on 06/03/15 - 04/03/2015 | Certificate of Compliance - 16/06/2015 | CELLSITE | WIPACTIVE |  |  | CAPACITY |  |  |  | 2015-11-02 | [5 empty] | 2015-12-04 |  |  |  | 2015-05-07
0 | WLG | 1691 | WLG-047-094 | Jervois Quay Relocate | WLG-047-094-A | 36 Customhouse Quay | Wellington City | 21 | 2014 | ACTIVE | RT | DF5 | RT |  | STACK_A | STANDALONE |  |  |  | -41.2832 | 174.7779 |  | 2014-11-10 |  |  |  |  | FALSE | FALSE |  |  | FALSE |  | 2014-03-11 | 2014-03-11 |  | 2014-04-07 | 2014-07-21 | 2014-07-01 | 1 | 2014-07-21 | 2014-07-01 | 2014-06-20 | 2014-06-06 | 2014-07-27 | 2014-07-04 |  | 2014-07-30 | 2014-10-08 | PERMITTED | 2014-07-27 | 2014-07-08 | 2014-08-25 | 2014-08-01 | 1 | 2014-08-25 | 2014-08-01 | 2014-08-05 |  | 2014-08-26 | 2014-09-15 | 2 |  | 2014-09-05 | 2014-09-29 | [5 empty] | 2014-11-27 | 2014-12-01 | 2014-12-16 | 2014-12-18 | 2014-11-04 | 2015-01-09 | 2015-01-09 | 2014-12-15 | 2014-12-18 | [7 empty] | 2015-03-13 | 2015-03-12 |  |  |  |  | 08.08.14 Site has been HARD MATCHED. This site Must move. CDI issued. Chris to visit when there 11-15 August This site is to be tendered as soon as CD's are issued. 18.09.14 Tender meeting held (Transfield, Kordia, Infratel and DWD) 01.10.14 QUOTATIONS due at 8am 8 Oct - Tender awarded - Kordia 15 Oct Kordia on planning stage, steel to be fabricated. 28 Oct Awaiting start date, pushing kordia slight delay in saftey system and FO 30 Oct FO back on track saftey system causing delays, Vertec pulled out of the job Kordia engaging new saftey system contractor.4 Nov - building has changed owners, Kordia denied entry today. SPM/SA investigating. 11 Nov new saftey contractor and Helo contractor engaged. 24 Nov. Cons yet to start completion date pushed out, integration still possible in year but no more tolerance for delay. 19/12/14 - Bad weather in WN has resulted in the integration unable to be undertaken before Xmas. Deferred to early 2015 and will be a managed transfer old to new site. Integration on 15th Jan failed, resheduled for next week. 21 Jan: Site integrated, await Vol 4 SOA delayed due to unavailable drive test vehicle. 12 Mar Site provisionally on air, 047-042 on standby to come back on if required | [10 empty] | 2015-01-26 | 2015-01-26 | 2014-07-08 | LOW |  | 2014-12-12 | 2014-12-12 | BUILD | 2014-11-04 | FALSE |  | 2658905 | 5989991 | 36 Customhouse Quay |  |  | CELLSITE |  |  |  | RELOCATION | [13 empty] | 2014-04-07
0 | WLG | 1692 | WLG-047-095 | Wakefield St Relocate | WLG-047-095-A | 126 Wakefield Street, Wellington | Wellington City | 24 | 2015P | ACTIVE | RT | DF5 | NOPOLE |  | STACK_A | STANDALONE |  |  |  | -41.29 | 174.7774 |  | 2014-09-30 |  | 2015-01-01 | Fibre Optic | WLG-047-049-A | FALSE | FALSE |  |  | FALSE |  | 2014-09-18 | 2014-09-18 | 2014-09-22 | 2014-09-22 | 2014-11-28 | 2014-11-19 | 1 | 2014-11-28 | 2014-11-19 | 2014-11-14 | 2014-11-25 | 2015-07-17 | 2015-06-16 |  | 2015-07-31 | 2015-07-14 | DISCRETIONARY_RESTRICT | 2014-12-05 | 2014-12-05 | 2015-05-31 | 2015-05-27 | 1 |  | 2015-08-06 | 2015-07-01 | 2015-06-16 | 2015-08-07 | [10 empty] | 2016-03-04 |  | 2016-04-01 |  |  | 2016-04-15 | [10 empty] | 2016-05-13 | [5 empty] | Candidate in SiteBase for reporting visibility. HARD MATCH ONLY Chris to visit site with Stefan (11-15 Aug). Stefan thinks 1 site can work. Challenging area, very few options if any. If not only 1 site then will have to make it 2. 09/7 AS: Moved to next year build 18.09.14 Met with John and Hank on site. Willing to have us. Measured up. Access is to be via a hatch in the lift / store room roof. 14 Oct - PD on circulation - we need to design in a saftey system for access to panels, location of panels under review. Saftey issues resolved with design/SA/LO/FOps - PD to go back to design. Hand rails added, site now RRU solution. 11 Nov - await new PD. Fibre route required to finalise PD Decision on timing to build site to be confirmed by Head of RAN. Note that the equipment is a 3 month lead time, so early decision for order required. 7/05 AS: Build this year with the budget from Downtown shopping relocation | [10 empty] | 2016-04-29 |  | 2014-12-05 | LOW |  |  |  | BUILD |  | FALSE |  | 2658852 | 5989235 | 126 Wakefield Road Te Aro Wellington |  |  | CELLSITE | WIPACTIVE |  |  | RELOCATION |  |  |  | 2016-01-18 | [5 empty] | 2016-02-26 |  |  |  | 2014-09-22
0 | WLG | 1693 | WLG-047-096 | Thorndon West |  |  | Wellington City |  | TIER_9
0 | WLG | 1694 | WLG-047-097 | Karori South Micro | WLG-047-097-A | Karori Microcell | Wellington City | 24 | 2015 | ACTIVE | COLO | MC | NOPOLE |  |  | COLO |  |  |  | -41.2956 | 174.7214 |  | 2014-12-30 |  |  | Microwave | WLG-047-022-A | FALSE | FALSE |  |  | FALSE |  | 2014-08-27 | 2014-08-27 | 2014-09-10 | 2014-09-10 | 2014-09-25 | 2014-10-01 | 1 | 2014-09-30 | 2014-10-01 | 2014-10-31 | 2014-10-31 |  | 2014-11-18 |  |  |  | PERMITTED | 2014-11-25 | 2014-11-18 | 2014-11-25 | 2014-11-18 | 1 |  | 2014-11-04 | 2014-11-28 | 2014-11-28 | 2014-12-05 | 2014-12-10 | 1 |  | 2014-11-04 | 2014-12-10 | [5 empty] | 2014-12-01 | 2014-12-08 | 2015-01-16 | 2015-01-16 | 2014-12-08 | 2015-02-10 | 2015-02-12 | 2015-02-11 | 2015-02-12 | [7 empty] | 2015-05-01 | 2015-05-05 |  |  |  |  | 01.10.2014 - Application + plans and examples of MC's sent to Shane. 22.10.14 Have received Kordia approval. Ben to submit RMA 30.1.2014 Have Kordia approval. Dont need to do RMA or CD's. RMA is not required from Kordia perspective and they do Construction drawings. 24 Nov - Korid apricing job which includes recovery of DMR equipment from other sites. VF have been asked if they can supply us power. Capacity in VF power supply, we may need sub meter. Will need full meter and own network connection. ICP applied for. Power will be the critical path to this integration 18/12/14 - Issues with linking and equipment will delay SOA to 2015. 26 Jan - resources not avialble to complete prior to this week, issues with software and cabinet hardware forced delay. Dated pushed to allow for forescat weather week ending 6 Feb. Problems with DMR link delaying TI complete. FAulty ODU replaced 11 Feb - BERT test carried out. 19 Feb suspected faulty MC delayed integration, new unit to be sent via Core-CS to check it. Upgraded MCs delivered, integration to be attempted 9 March. 12 March - still unable to integrate 2D liaising with Huawei | KDA | [9 empty] | 2015-05-01 | [6 empty] | BUILD | 2014-12-01 | FALSE |  | 2654145 | 5988715 | South Karori Road Wellington |  |  | CELLSITE |  |  |  | SMALL CELLS | [13 empty] | 2014-09-10
0 | WLG | 1695 | WLG-047-098 | Glenmore St MC | WLG-047-098-A | Glenmore Bridge | Wellington City | 24 | TIER_9 | ACTIVE | RSR | MC | NOPOLE |  |  | STANDALONE |  |  |  | -41.287 | 174.7585 |  |  |  |  | Leased Line | WLG-047-071-A | FALSE | FALSE |  |  | FALSE |  | 2014-08-27 | 2014-08-27 | 2014-10-29 | 2014-10-29 | 2014-11-14 | 2014-11-12 | 2 | 2014-11-14 | 2014-11-20 |  | 2014-12-16 | 2015-05-29 | 2014-12-12 |  |  |  | PERMITTED | 2015-02-13 | 2015-02-09 | 2015-03-13 | 2015-02-20 | 2 |  | 2015-02-20 | 2015-06-12 | 2015-06-16 | 2015-07-10 | [10 empty] | 2015-08-07 |  | 2015-08-31 |  |  | 2015-08-31 | [10 empty] | 2015-09-18 | [5 empty] | Jason met with the Wellington Council on 26.09 - they are willing to progress our Light Pole applications. Next step - do a caravan with council. 8 Oct 2014 - Need to meet with council, hope to complete week ending 24 Oct due to council availibility 28 Oct Await PD. 4 Nov PD on circulation. 11 Nov PD back to design for amend and issue. Telco Act Notice lodged. Awaiting feedback from council prior to RMA lodge. Council require survey of structure prior to accepting proposal, bridge surveyed 23 Jan | [10 empty] | 2015-09-04 |  | 2015-02-16 | LOW |  |  |  | BUILD |  | TRUE |  | 2657277 | 5989607 | Lightpole Attached to the Glenmore Bridge |  |  | CELLSITE | WIPACTIVE |  |  | SMALL CELLS | [13 empty] | 2014-10-29
0 | WLG | 1696 | WLG-048-001 |  |  |  | Wairarapa |  | TIER_9
0 | WLG | 1697 | WLG-048-002 | Masterton Straights | WLG-048-002-B | Masterton Straights GF | Wairarapa | 6 | TIER_3 | ACTIVE | GF | DU | T2 20 UF |  | STACK_A | STANDALONE |  |  | 1 | -40.9557 | 175.6515 |  | 2012-02-01 |  |  | Leased Line | WLG-047-071-A | FALSE | FALSE |  |  | FALSE |  | 2012-06-12 | 2012-04-05 | 2012-04-19 | 2012-04-20 | 2012-05-25 | 2012-05-30 | 1 | 2012-05-25 | 2012-05-30 | 2012-05-13 | 2012-04-13 | 2012-06-25 | 2012-06-19 |  | 2012-06-25 | 2012-06-19 | PERMITTED | 2012-05-29 | 2012-06-01 | 2012-06-29 | 2012-06-15 | 1 | 2012-06-29 | 2012-06-15 |  |  | 2012-09-07 | 2012-09-10 | 1 |  | 2012-09-07 | 2012-09-10 | [5 empty] | 2012-08-15 | 2012-08-15 | 2012-09-07 | 2012-09-04 | 2012-08-31 | 2012-09-07 | 2012-09-10 | [8 empty] | 2012-09-13 | 2012-11-13 | 2012-10-18 | 2012-11-13 | 2012-10-23 | 2013-04-25 | 2013-04-26 |  | VNZ | 2012-09-13 | 2012-08-21 | 2012-08-28 | 2012-08-25 |  | 2012-08-24 |  | 2012-08-29 | 2012-09-03 | 2012-10-18 | 2012-10-09 | 2012-04-16 | HIGH | WAIRARAPA | 2012-09-11 | 2012-09-10 | BUILD | 2012-08-29 | FALSE |  | 2733166 | 6024499 | 7 Russell Street Masterton |  |  | CELLSITE |  |  | 2015-10-20 | [12 empty] | 2012-10-28 | 2012-10-09
0 | WLG | 1698 | WLG-048-003 | Masterton | WLG-048-003-B | Masterton GF | Wairarapa | 6 | TIER_3 | ACTIVE | GF | DU | T2 25 UF |  | STACK_A | STANDALONE |  |  |  | -40.9405 | 175.6585 |  | 2012-02-01 |  |  | Microwave | WLG-048-002-B | FALSE | FALSE |  |  | FALSE |  | 2012-06-12 | 2012-04-05 | 2012-04-26 | 2012-04-26 | 2012-05-25 | 2012-05-30 | 1 | 2012-05-25 | 2012-05-30 | 2012-05-13 | 2012-04-13 | 2012-06-25 | 2012-06-27 | 1 | 2012-06-25 | 2012-06-27 | PERMITTED | 2012-05-29 | 2012-06-01 | 2012-06-29 | 2012-06-15 | 1 | 2012-06-29 | 2012-06-15 |  |  | 2012-09-11 | 2012-09-06 | 1 |  | 2012-09-11 | 2012-09-06 | 2012-09-13 |  |  |  |  | 2012-08-27 | 2012-08-27 | 2012-09-14 | 2012-09-20 | 2012-09-21 | 2012-09-25 | 2012-09-27 | [8 empty] | 2012-10-01 | 2012-11-13 | 2012-10-18 | 2012-11-13 | 2012-10-29 | 2013-04-27 | 2013-04-15 |  |  | 2012-10-01 | 2012-08-01 | 2012-08-01 | 2012-08-31 |  | 2012-08-31 | 2012-09-13 | 2012-09-24 | 2012-09-24 | 2012-10-18 | 2012-10-12 | 2012-04-16 | MEDIUM | WAIRARAPA |  |  | BUILD | 2012-09-21 | FALSE |  | 2733812 | 6026165 | 152 Lincoln Road Masterton |  |  | CELLSITE |  |  | 2015-10-20 | [12 empty] | 2012-10-15 | 2012-10-15
0 | WLG | 1699 | WLG-048-004 |  |  |  | Wairarapa |  | TIER_9
0 | WLG | 1700 | WLG-048-005 | Otahoua |  |  | Wairarapa | 6 | TIER_3 | [22 empty] | FALSE | [60 empty] | Primary Coverage Objective: ROAMING MITIGATION coverage on Castleclff road towards Riversdale COLO at Vodafone Backup: Greenfield nearby but additional height and distance is critical for co-site isolation | [14 empty] | WAIRARAPA
0 | WLG | 1701 | WLG-048-006 |  |  |  | Wairarapa |  | TIER_9
0 | WLG | 1702 | WLG-048-007 | RBI - Castle Point |  |  | Wairarapa |  | RBI | [22 empty] | FALSE
0 | WLG | 1703 | WLG-048-008 | RBI - Riversdale Beach |  |  | Wairarapa |  | RBI | [22 empty] | FALSE
0 | WLG | 1704 | WLG-049-001 | Carterton | WLG-049-001-A | Carterton VF Colo | Carterton District | 6 | TIER_3 | ACTIVE | COLO | DU | COLO |  | STACK_A | COLO |  |  | 2 | -40.9735 | 175.5067 |  | 2012-02-03 |  |  | Microwave | WLG-048-002-B | FALSE | FALSE |  |  | FALSE |  | 2012-03-05 | 2012-02-22 | 2012-03-10 | 2012-03-01 | 2012-05-07 | 2012-06-12 | 2 | 2012-05-07 | 2012-09-24 | 2012-09-15 | 2012-09-14 | 2012-10-25 | 2012-10-12 |  | 2012-10-25 | 2012-10-16 | PERMITTED | 2012-05-18 | 2012-06-07 | 2012-06-18 | 2012-06-15 | 1 | 2012-06-20 | 2012-06-15 |  |  | 2012-09-11 | 2012-09-25 | 1 |  | 2012-09-11 | 2012-09-25 | 2012-10-12 |  |  |  |  | 2012-10-22 | 2012-10-19 | 2012-10-26 | 2012-10-26 | 2012-10-25 | 2012-10-29 | 2012-11-15 | [8 empty] | 2012-11-15 | 2012-12-03 | 2012-11-15 | 2012-12-03 | 2012-11-30 | 2013-05-28 | 2013-05-02 |  | VNZ | 2012-11-02 | 2012-09-07 |  | 2012-09-07 | 2012-10-12 | 2012-08-27 | 2012-10-12 | 2012-10-25 | 2012-11-13 | 2012-11-14 | 2012-11-15 | 2012-04-16 | LOW | WAIRARAPA |  |  | BUILD | 2012-10-24 | FALSE |  | 2720929 | 6022877 | Hururua Rd Carterton |  |  | CELLSITE | [15 empty] | 2012-11-19 | 2012-11-21
0 | WLG | 1705 | WLG-049-002 | RBI - Carterton Central |  |  | Carterton District |  | RBI | [22 empty] | FALSE
0 | WLG | 1706 | WLG-049-003 | Greytown_Micro |  |  | Carterton District |  | TIER_9 | [22 empty] | FALSE | [60 empty] | A Dual Micro roadside solution on council poles will be targeted. Poles which are currently surplus stock are an alternative to be used to maximise cost effectiveness if existing infrastructure is not practical.
0 | WLG | 1707 | WLG-050-001 | Featherston | WLG-050-001-A | Featherston VNZ CoLo | South Wairarapa District | 6 | TIER_3 | ACTIVE | COLO | DU | COLO |  | STACK_A | COLO |  |  | 1 | -41.1064 | 175.3159 |  | 2012-01-25 |  |  | Microwave | WLG-049-001-A | FALSE | FALSE |  |  | FALSE |  | 2012-03-05 | 2012-02-22 | 2012-03-10 | 2012-03-01 | 2012-06-26 | 2012-06-28 | 1 | 2012-06-26 | 2012-06-28 | 2012-09-15 | 2012-09-21 | 2012-12-09 | 2012-11-23 |  | 2012-12-09 | 2012-12-21 | PERMITTED | 2012-06-29 | 2012-07-02 | 2012-07-29 | 2012-07-20 | 1 | 2012-07-29 | 2012-07-20 |  |  | 2012-09-11 | 2012-09-10 | 1 |  | 2012-09-11 | 2012-09-10 | 2012-10-19 |  |  |  |  | 2013-01-16 | 2013-01-16 | 2013-01-25 | 2013-01-25 | 2013-01-25 | 2013-01-30 | 2013-01-30 | [8 empty] | 2013-01-31 | 2013-02-15 | 2013-02-15 | 2013-02-19 | 2013-02-19 | 2013-07-05 | 2013-06-28 |  | VNZ | 2013-01-31 | 2012-09-10 | 2012-08-01 | 2012-09-10 | 2012-10-19 | 2012-09-14 | 2012-10-19 | 2013-01-28 | 2013-01-28 | 2013-02-18 | 2013-02-07 | 2012-04-16 | LOW | WAIRARAPA |  |  | BUILD | 2013-01-25 | FALSE |  | 2704487 | 6008562 | Corner Rimutaka Hill Road and State Highway 2 |  |  | CELLSITE | [15 empty] | 2013-02-08 | 2013-02-11
0 | WLG | 1708 | WLG-050-002 | Martinborough | WLG-050-002-A | Martinborough VNZ Co-Lo | South Wairarapa District | 6 | TIER_3 | ACTIVE | COLO | DU | COLO |  | STACK_A | COLO |  |  | 1 | -41.1827 | 175.4841 |  | 2012-01-25 |  |  | Leased Line | WLG-047-071-A | FALSE | FALSE |  |  | FALSE |  | 2012-03-05 | 2012-02-22 | 2012-03-10 | 2012-03-01 | 2012-06-26 | 2012-06-29 | 2 | 2012-06-26 | 2013-11-01 | 2012-09-15 | 2012-09-20 | 2012-11-19 | 2012-11-23 |  | 2012-11-30 | 2013-01-30 | PERMITTED | 2012-06-29 | 2012-07-02 | 2012-07-29 | 2012-07-20 | 1 | 2012-07-29 | 2012-07-20 |  |  | 2012-09-11 | 2012-09-13 | 1 |  | 2012-09-11 | 2012-09-13 | 2012-10-19 |  |  |  |  | 2012-10-01 | 2012-10-02 | 2012-10-12 | 2012-10-26 | 2012-10-19 | 2012-11-02 | 2012-11-02 | [8 empty] | 2012-11-08 | 2012-11-15 | 2012-11-14 | 2013-01-01 | 2012-11-30 | 2013-09-16 | 2013-12-03 |  | VNZ | 2012-11-09 | 2012-09-14 |  | 2012-09-14 | 2012-10-19 | 2012-09-11 | 2012-10-19 | 2012-10-15 | 2012-10-31 | 2012-11-10 | 2012-11-09 | 2012-04-16 | LOW | WAIRARAPA | 2012-11-06 | 2012-11-02 | BUILD | 2012-10-12 | FALSE |  | 2718365 | 5999706 | Riverside Road, Martinborough |  |  | CELLSITE | [15 empty] | 2012-11-16 | 2012-11-16
0 | WLG | 1709 | WLG-050-003 | Greytown Microcell | WLG-050-003-B | Ocolyte Pole | South Wairarapa District | 24 | 2015 | ACTIVE | RSR | MC | NOPOLE |  |  |  | 6 | 8.8 |  | -41.0808 | 175.4593 |  | 2014-08-11 |  |  |  |  | FALSE | FALSE |  |  | FALSE |  | 2014-08-29 | 2014-08-29 | 2014-10-30 | 2014-10-30 | 2014-11-14 | 2014-11-17 | 2 |  | 2014-11-19 | 2014-12-05 | 2014-12-09 | 2014-12-19 | 2015-01-06 |  |  | 2015-02-02 | CONTROLLED | 2014-12-19 | 2014-12-16 | 2015-01-30 | 2015-01-24 | 2 |  | 2015-01-24 | 2014-12-19 | 2014-12-18 | 2015-01-16 | 2015-01-08 | 1 |  | 2015-01-16 | 2015-01-08 |  |  |  | 2015-01-20 |  | 2015-03-16 | 2015-03-16 | 2015-03-18 | 2015-03-18 | 2015-03-11 | [11 empty] | 2015-03-27 | 2015-03-26 |  |  |  |  | We have measured up this site. It is not prefered by RF but they could make it work if they have to. Presented Fancy Pole request to Council first - to guage their reaction. 28 Oct Ocolyte pole active as last option, RF Ok with 2 x MC at 7m. Ben has montage to take to community board mtg. Community Board outcome positive PDI issued. PD issued, Telco Act Notice lodged. Awaiting information from Council to be able to lodge consent. 6 Jan Fibre ordered, await power quote. Chorus FO delivery delays build. invitation to tender issued. 18 MArch installation complete | [10 empty] | 2015-03-25 | 2015-03-26 |  |  |  | 2015-02-26 | 2015-03-06 | BUILD | 2015-03-09 | TRUE | 2015-01-30 | 2716606 | 6011077 | Corner of Hastwel and Main St Greytown |  |  | CELLSITE |  |  |  | SMALL CELLS | [13 empty] | 2014-10-30
South Island | STH | 1294 | STH-073-017 | RBI - Stewart Island |  |  | Southland District |  | RBI | [22 empty] | FALSE
South Island | STH | 1295 | STH-073-018 | RBI - Stewart Island |  |  | Southland District |  | RBI | [22 empty] | FALSE
South Island | STH | 1296 | STH-073-019 | RBI - Mt Prospect Te Anau |  |  | Southland District |  | RBI | [22 empty] | FALSE
South Island | STH | 1298 | STH-073-021 |  |  |  | Southland District |  | TIER_9
South Island | STH | 1314 | STH-075-010 | Gladstone |  |  | Invercargill City |  | TIER_9 | [22 empty] | FALSE
South Island | STH | 1315 | STH-075-011 | Grasmere |  |  | Invercargill City |  | TIER_9 | [22 empty] | FALSE
South Island | STH | 1317 | STH-075-013 | Kingswell |  |  | Invercargill City |  | TIER_9 | [22 empty] | FALSE
South Island | STH | 1318 | STH-075-014 | Rosedale - Hardmatch |  |  | Invercargill City |  | TIER_9 | [22 empty] | FALSE
South Island | STH | 1319 | STH-075-015 | Invercargill Temporary Link |  |  | Invercargill City | 5 | TIER_9 | [22 empty] | FALSE
South Island | WST | 1711 | WST-055-002 |  |  |  | Buller District |  | TIER_9
South Island | WST | 1712 | WST-055-003 |  |  |  | Buller District |  | TIER_9
South Island | WST | 1721 | WST-057-002 |  |  |  | Westland District |  | TIER_9
South Island | WST | 1722 | WST-057-003 |  |  |  | Westland District |  | TIER_9
|  |  |  | SPM Report |  | tier_identifier=[u'ALL'], show_dead_sites=False, show_all_nominals=True, comb_targ_act_dt=False, candidate_status=ACTIVE, assigned_team=[]
|  |  |  | Created: | 2016-02-11 08:57

## Sheet1
AKL
BOP
CAN | South Island
CHC
COB
COW
GSB
HKB
MBN | South Island
MNW
NTH
OTG | South Island
STH | South Island
SYD
TNK
WKT
WLG
WST | South Island

## Sheet2
|  | Sl. No | Site Id | Site Name | Candidate Id | Candidate Name | Territorial Authority | Team | Tier Identifier | Candidate Status | Property Type | Target Date Site On Air Complete | Project
South Island | CAN | 707 | CAN-065-008 | Tekapo | CAN-065-008-A | VF Co-site Mt John | Mackenzie District | 21 | TIER_4 | ACTIVE | GF | 2016-01-14
South Island | MBN | 998 | MBN-051-018 | Motueka South | MBN-051-018-A | TBC - New Site | Tasman District | 21 | TIER_9 | ACTIVE |  | 2016-01-22
South Island | MBN | 1040 | MBN-053-018 | Seddon Exchange colo | MBN-053-018-A | Chorus Exchange | Marlborough District | 21 | TIER_4 | ACTIVE | COLO | 2016-01-29
South Island | MBN | 1039 | MBN-053-017 | Seddon | MBN-053-017-B | VF Colo | Marlborough District | 21 | TIER_4 | ACTIVE | COLO | 2016-02-03
South Island | CAN | 671 | CAN-062-017 | Rolleston South | CAN-062-017-B | Orion - Burnham School Rd | Selwyn District | 21 | 2015P | ACTIVE | RSR | 2016-02-11
South Island | WST | 1713 | WST-055-004 | Westport Outer | WST-055-004-A | Kordia colo | Buller District | 21 | TIER_4 | ACTIVE | COLO | 2016-02-25
South Island | WST | 1715 | WST-055-006 | Reefton Tx Exchange colo | WST-055-006-A | Chorus Exchange | Buller District | 21 | TIER_4 | ACTIVE | COLO | 2016-03-04
South Island | OTG | 1204 | OTG-069-008 | Tarras | OTG-069-008-B | VF Colo | Central Otago | 21 | TIER_4 | ACTIVE | COLO | 2016-03-08
South Island | OTG | 1272 | OTG-072-002 | Balclutha | OTG-072-002-G | Chorus Colo | Clutha | 21 | TIER_4 | ACTIVE | COLO | 2016-03-10
South Island | STH | 1320 | STH-075-016 | RBI - Lorneville | STH-075-016-A | Lorneville RBI | Invercargill City | 25 | TIER_5 | ACTIVE | RBI | 2016-03-11 | RBI
South Island | CAN | 637 | CAN-058-015 | RBI - Leithfield | CAN-058-015-A | Leithfield RBI | Hurunui District | 25 | TIER_5 | ACTIVE | RBI | 2016-03-15 | RBI
South Island | CAN | 652 | CAN-059-015 | RBI - Swannanoa | CAN-059-015-A | Swannanoa RBI | Waimakariri | 25 | TIER_5 | ACTIVE | RBI | 2016-03-25 | RBI
South Island | STH | 1299 | STH-073-022 | Riverton | STH-073-022-A | Vodafone Co-Lo | Southland District | 21 | TIER_4 | ACTIVE | COLO | 2016-03-30 | NR
South Island | CAN | 651 | CAN-059-014 | RBI - Cust | CAN-059-014-A | Cust RBI | Waimakariri | 25 | TIER_5 | ACTIVE | RBI | 2016-03-31 | RBI
South Island | WST | 1714 | WST-055-005 | Reefton | WST-055-005-C | Reefton Green Field | Buller District | 21 | TIER_4 | ACTIVE | GF | 2016-04-04
South Island | CAN | 673 | CAN-062-019 | RBI - Glentunnel | CAN-062-019-A | Glentunnel RBI | Selwyn District | 25 | TIER_5 | ACTIVE | RBI | 2016-04-21 | RBI
South Island | MBN | 1037 | MBN-053-015 | Springlands | MBN-053-015-B | Supermarket RSR | Marlborough District | 21 | 2015P | ACTIVE | RSR | 2016-04-22
South Island | STH | 1287 | STH-073-010 | Winton | STH-073-010-C | Green Field | Southland District | 21 | TIER_4 | ACTIVE | GF | 2016-05-16 | NR
South Island | OTG | 1221 | OTG-070-014 | Queenstown Central | OTG-070-014-C | Church Street | Queenstown | 21 | TIER_4 | ACTIVE | RT | 2016-05-30 | NR
South Island | CAN | 713 | CAN-066-005 | Kurow | CAN-066-005-C | Spark Colo | Waimate District | 21 | TIER_4 | ACTIVE | COLO | 2016-07-15 | NR
South Island | STH | 1300 | STH-073-023 | Woodlands | STH-073-023-A | Woosh Colo | Southland District | 21 | TIER_5 | ACTIVE | COLO | 2016-07-31 | NR
South Island | CAN | 718 | CAN-068-003 | Big Hill | CAN-068-003-B | VF colo | Waitaki District | 21 | TIER_4 | ACTIVE | COLO | 2016-08-12 | NR
South Island | STH | 1304 | STH-074-004 | Hedgehope | STH-074-004-A | Chorus co-lo | Gore District | 21 | TIER_5 | ACTIVE | COLO | 2016-08-30 | NR
South Island | MBN | 997 | MBN-051-017 | Kaiteriteri | MBN-051-017-F | GF - TNZ Co-site | Tasman District | 21 | TIER_5 | ACTIVE | GF | 2016-08-31 | NR
South Island | CAN | 699 | CAN-064-017 | Clandeboye | CAN-064-017-A | Community hall | Timaru | 21 | TIER_5 | ACTIVE | GF | 2016-09-09 | NR
South Island | STH | 1278 | STH-073-001 | Fonterra Edendale | STH-073-001-B | Scenic Reserve Road | Southland District | 21 | TIER_5 | ACTIVE | GF | 2016-09-30 | NR

## Sheet3
SiteName |  | Project | Date
STH-073-022 | Riverton | NR | 2016-04-08
OTG-070-014 | Queenstown Central | NR | 2016-06-03
STH-073-010 | Winton | NR | 2016-06-17
CHC-060-100 | Akaroa | NR | 2016-06-17
CAN-066-005 | Kurow | NR | 2016-07-08
STH-073-023 | Woodlands | NR | 2016-07-24
CAN-068-003 | Big Hill | NR | 2016-08-05
MBN-051-017 | Kaiteriteri | NR | 2016-08-24
CAN-064-017 | Clandeboye | NR | 2016-09-02
STH-074-004 | Hedgehope | NR | 2016-09-09
STH-073-001 | Fonterra Edendale | NR | 2016-09-23